## CIP_2024
Request_No | Year | Source ID | CHAR05 | Client Region | Client Region | One View Number | Description | Description | JSON String | Description | Planned Start Date | Planned End Date | Date in Format YYYYMMDD in 8 Characters | CHAR05 | Description | Description | Description | Description | Amount | Amount | Character Field Length = 10 | Description | Project number | Character Length 1 | JSON String | Planned Start Date | Planned End Date | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Appropriation request | Description
240129_471 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Replacement of existing lights with LED lighting (x 50 branches), Energy |  | Engineering: Retail | 2024-03-04 | 2024-08-30 |  | CAPEX | PR/2 | R.PR/2/03 | RETAIL - Energy |  | 22500000 | [10 empty] | Continue
240129_443 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Install alternative power (x 10 Sites) Battery Walls & Solar, Energy |  | Engineering: Retail | 2024-02-26 | 2024-08-30 |  | CAPEX | PR/2 | R.PR/2/03 | RETAIL - Energy |  | 15000000 | [10 empty] | Continue
240129_032 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76439X | Absa Towers West | Absa Towers West, BMS Upgrade, BMS and EMS Systems |  | Engineering: Corporate | 2024-02-15 | 2024-09-30 |  | CAPEX | PR/1 | R.PR/1/09 | CORP - BMS and EMS Systems |  | 5950050.5 | [10 empty] | Continue
240129_357 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, LED Yellow Lights, Electrical |  | Engineering: Retail | 2024-04-01 | 2024-09-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 4800000 | [10 empty] | Continue
240129_432 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Install smart electricity and water meters (x 45 Sites), Energy |  | Engineering: Retail | 2024-03-04 | 2024-08-30 |  | CAPEX | PR/2 | R.PR/2/03 | RETAIL - Energy |  | 4550000 | [10 empty] | Continue
240129_041 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, EOL Programme (LCC Based) - Mechanical, Mechanical |  | Engineering: Corporate | 2024-04-01 | 2024-09-15 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 4404286.82 | [10 empty] | Continue
240129_580 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Audio & Visual, Fabric, Audio Visual |  | Fabric : Corporate | 2024-02-15 | 2024-09-25 |  | CAPEX | PR/3 | R.PR/3/09 | CORP - Fabric - Audio Visual |  | 4000000 | [10 empty] | Continue
240129_358 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, EOL Programme (LCC Based) - Electrical, Electrical |  | Engineering: Retail | 2024-04-01 | 2024-09-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 3595735 | [10 empty] | Continue
240129_299 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, LED Yellow Lights, Electrical |  | Engineering: Corporate | 2024-04-01 | 2024-09-15 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 2420000 | [10 empty] | Continue
240129_047 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21335X | 270 Republic Road | 270 Republic Road, 4 Chiller compressor replacements, Mechanical |  | Engineering: Corporate | 2024-02-28 | 2024-10-15 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 2000000 | [10 empty] | Continue
240129_419 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, National allowance for the use of Ergonomist furniture and equipment , Fabric, Ergonomist Group OHS |  | Fabric : Corporate | 2024-02-15 | 2024-10-30 |  | CAPEX | PR/3 | R.PR/3/11 | CORP - FABRIC - Ergonomist Group OHS |  | 2000000 | [10 empty] | Continue
240129_260 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Retail Documentation Compliance Programme (Phase 3) - additional requests for remedial works, BAU Compliance Documentation |  | BAU Retail | 2024-02-15 | 2024-06-28 |  | CAPEX | PR/9 | D.PR/9/04 | RETAIL - BAU Compliance Documentation |  | 2000000 | [10 empty] | Continue
240129_359 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Surge Protection, Electrical |  | Engineering: Retail | 2024-04-01 | 2024-09-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 2000000 | [10 empty] | Continue
240129_549 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, MTR Room A44 & A45, Fabric, Other |  | Fabric : Corporate | 2024-02-05 | 2024-03-25 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1724200.93 | [10 empty] | Works Approved (2023)
240129_508 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Building performance improvement initiatives, Energy |  | Engineering: Corporate | 2024-04-15 | 2024-08-30 |  | CAPEX | PR/1 | R.PR/1/03 | CORP - Energy |  | 1650000 | [10 empty] | Continue
240129_431 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Emergency lighting, Electrical |  | Engineering: Retail | 2024-03-15 | 2024-08-30 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 1642666.67 | [10 empty] | Continue
240129_318 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Shower rooms and ablutions ( -2, -1) require a complete upgrade ( tile replacement wall and floor, blind removal, basins, mirrors, taps ( tap system to be converted from battery usage to direct power use) and window vinyl.), Fabric, Other |  | Fabric : Corporate | 2024-04-10 | 2024-06-20 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1600000 | [10 empty] | Continue
240129_372 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 79271X | 13 Top Road | 13 Top Road , Shading net replacement & repainting of Structures / Installation of carports, Fabric, Other |  | Fabric : Corporate | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1500000 | [10 empty] | Continue
240129_562 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 78083X | Springbok | Springbok, Minor Works, Fabric, Other |  | Fabric: Retail | 2024-07-09 | 2024-08-05 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 1500000 | [10 empty] | Cancel
240129_300 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Bulk UPS Battery replacements, Electrical |  | Engineering: Corporate | 2023-01-15 | 2023-09-25 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1500000 | [10 empty] | Continue
240131_018 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76384X | Absa Boksburg | Absa Boksburg - HVAC Upgrade |  | Engineering: Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 1357860 | [10 empty] | Defer
240129_301 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, EOL Programme (LCC Based) - Electrical, Electrical |  | Engineering: Corporate | 2024-04-01 | 2024-06-24 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1320605 | [10 empty] | Continue
240129_302 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Surge Protection, Electrical |  | Engineering: Corporate | 2024-04-01 | 2024-09-15 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1300000 | [10 empty] | Continue
240129_533 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Chakula Ground Floor patio flooring upgrade. , Fabric, Other |  | Fabric : Corporate | 2024-05-01 | 2024-06-01 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1200000 | [10 empty] | Cancel
240129_532 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Ground floor main restaurant, serving area counter (Quartz) including carcass, Fabric, Other |  | Fabric : Corporate | 2024-03-30 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1200000 | [10 empty] | Continue
240129_509 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Building performance improvement initiatives, Energy |  | Engineering: Retail | 2024-04-15 | 2024-08-30 |  | CAPEX | PR/2 | R.PR/2/03 | RETAIL - Energy |  | 1200000 | [10 empty] | Continue
240129_548 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West-Troye St-Johannesburg, Upgrades to restaurant cupboards, Fabric, Other |  | Fabric : Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1182240.28 | [10 empty] | Defer
240129_445 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Call Centre Auckland Park, Replace the entire palisade fence around the building with concrete walling, Fabric, Other |  | Fabric : Corporate | 2024-05-01 | 2024-06-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1155000 | [10 empty] | Continue
240129_578 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, National allowance for the purchase/installation of white goods |  | BAU FM Work | 2024-04-01 | 2024-06-28 |  | CAPEX | PR/8 | R.PR/8/06 | BAU FM - White Goods |  | 1150000 | [10 empty] | Continue
240129_033 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites , Installation of generator bulk tank with a catchment area. 500L, New assets |  | Engineering: Retail | 2024-01-26 | 2024-04-30 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 1127155 | [10 empty] | Continue
240129_315 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Block A,VAMM storeroom and vault in training area, Fabric, Other |  | Fabric : Corporate | 2024-03-01 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1000000 | [10 empty] | Continue
240129_287 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, supply and Install drainage system to mitigate flooding (Phase 2), Water & Systems |  | Engineering: Corporate | 2024-01-20 | 2024-05-30 |  | CAPEX | PR/1 | R.PR/1/07 | CORP - Water and System |  | 1000000 | [10 empty] | Continue
240129_002 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Glass roof upgrade (Sqm2?) - Support Structure, Engineering and Infrastructure |  | Engineering: Corporate | 2024-04-01 | 2024-05-30 |  | CAPEX | PR/1 | R.PR/1/02 | CORP - Engineering and Infrastructure |  | 1000000 | [10 empty] | Continue
240129_001 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Crack unit replacements, Mechanical |  | Engineering: Corporate | 2024-02-02 | 2024-10-16 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 1000000 | [10 empty] | Continue
240129_534 | 2024 | CIP2024 |  | Region 3 | Free State | 22405X | Bethlehem | Bethlehem, Bethlehem 1 floor to create a open space offices. Signage for Business Bank, Fabric, Other |  | Fabric : Corporate | 2024-02-22 | 2024-03-20 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 1000000 | [10 empty] | Continue
240129_050 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 79059X | Maponya Ma | Maponya Mall, Install an abs stand-alone HVAC system, LL system is currently malfunctioning , Mechanical |  | Engineering: Retail | 2024-01-31 | 2024-03-31 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 1000000 | [10 empty] | Continue
240129_049 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Retail Sites, Install UPS systems on site that don't have UPS, Electrical |  | Engineering: Corporate | 2024-01-15 | 2024-12-12 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1000000 | [10 empty] | Continue
240129_521 | 2024 | CIP2024 |  | Region 2 | National | Various | Various Sites | Various Sites (REG2), Headwind Budget - Various - Bulk PO - Eng Prioritised Requests, Electrical |  | Engineering: Corporate | 2024-01-15 | 2024-09-25 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1000000 | [10 empty] | Continue
240129_522 | 2024 | CIP2024 |  | Region 3 | National | Various | Various Sites | Various Sites (REG3), Headwind Budget, Electrical |  | Engineering: Corporate | 2024-01-15 | 2024-09-25 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1000000 | [10 empty] | Continue
240129_519 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various, Headwind Budget, Electrical |  | Engineering: Corporate | 2024-01-15 | 2024-09-25 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1000000 | [10 empty] | Continue
240129_473 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various, Headwind Budget, Electrical |  | Engineering: Corporate | 2024-01-15 | 2024-09-25 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 1000000 | [10 empty] | Continue
240129_541 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76600X | Absa Alexandria | Absa Alexandria, Refurbish kitchen/ablutions, replace floor/carpets tiles teller area. Repaint interior. Ceiling, Fabric, Other |  | Fabric: Retail | 2024-08-01 | 2024-09-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 850000 | [10 empty] | Defer
240129_337 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77877X | Absa Robertson | Absa Robertson, Wallpaper needs to be replaced. Floor tiles needs to be replaced., chipped and cracked. , The bathrooms needs to be upgraded. (New floor tiles, new wall tiles, new toilet fittings, new basins and new taps) , Fabric, Other |  | Fabric: Retail | 2024-04-15 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 850000 | [10 empty] | Continue
240129_506 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 70633X | Bizana Shopping Square | Bizana Shopping Square, Generator Replacement, Electrical |  | Engineering: Retail | 2024-06-15 | 2024-07-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 850000 | [10 empty] | Continue
240129_368 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 78671X | Kabokweni | Kabokweni, Repaint branch to introduce LUX colours; replace Back of House & BA office carpets; repaint Back of House and all front of house offices walls; replace ablution and kitchen ceramic wall tiles; replace all banking hall tiles including ATM lobby; replace all ceiling tiles in branch; supply new chairs for staff and customers; redo signage (internal and lifestyle graphics to shopfront); register LED with national energy office., Fabric, Other |  | Fabric: Retail | 2024-03-18 | 2024-03-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 850000 | [10 empty] | Continue
240129_505 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 22196X | The Nautilus Builiding - Jeffreys Bay | The Nautilus Builiding - Jeffreys Bay, Generator Replacement, Electrical |  | Engineering: Retail | 2024-06-15 | 2024-07-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 850000 | [10 empty] | Continue
240129_349 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 79176X | Absa Kuyasa Shopping Centre - Mdantsane | Absa Kuyasa Shopping Centre - Mdantsane, Ceiling tiles replace entire site - Refresh, Fabric, Other |  | Fabric: Retail | 2024-07-15 | 2024-08-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 825000 | [10 empty] | Continue
240129_380 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 78655X | Montana (Fin Forum) | Montana (Fin Forum), Carpet replacement - entire branch, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 818592 | [10 empty] | Continue
240129_329 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 79379X | Absa Active park,Newcastle | Absa Active park,Newcastle, Full refurb of office area including furniture and LED lighting, Fabric, Other |  | Fabric : Corporate | 2024-04-12 | 2024-04-26 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 800000 | [10 empty] | Continue
240129_520 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Replace light covers on the hanging pendant lights at reception and coffee bar on upper ground., Electrical |  | Engineering: Corporate | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 800000 | [10 empty] | Continue
240129_319 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 35041X | Alice lane North | Alice Lane South, Countertops - Ground Floor Restaurant Serving Area, Damaged Counter Tops and Cupboards, Fabric, Other |  | Fabric : Corporate | 2024-02-28 | 2024-03-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 800000 | [10 empty] | Continue
240129_542 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 77111X | Absa Prins Albert | Absa Prins Albert, Full Revamp of site - upgrade ablutions, kitchen, banking hall, offices, back office ( remove wooden cladding), teller area, Atm Room and Lobby - walls, floors. Refurbish wooden ceiling and replace louvre windows. Install hydroboil. Replace furniture, internal signage. Replace blinds. , Fabric, Other |  | Fabric: Retail | 2024-07-01 | 2024-08-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 750000 | [10 empty] | Under review
240129_543 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 78140X | Absa Uniondale | Absa Uniondale, Upgrade ablutions/ kitchen/ teller/banking hall/offices/back office area/ ATM room - walls, floor tiles, carpets, ceilings. Windows to be replaced -old metal frames. Replace furniture, moveable , benches. Refurbish exterior. Hydroboil installation. Replace internal signage. Install BCTU and small footprint mantrap door., Fabric, Other |  | Fabric: Retail | 2024-06-01 | 2024-08-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 750000 | [10 empty] | Defer
240129_388 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77584X | Ermelo | Ermelo, Convert the PA into 2x sales cubicles; relocate self help service desk; Convert Forex Desk into an enclosed office; replace stainless steel banking hall benches with wooden benches; repaint teller areas., Fabric, Other |  | Fabric: Retail | 2024-03-15 | 2024-03-23 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 750000 | [10 empty] | Continue
240129_369 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77028X | Kriel | Kriel, Upgrade of Teller counters; Painting of branch walls to introduce lux colours; upgrade to ablution facilities. Installation of LED Lights in entire branch, Fabric, Other |  | Fabric: Retail | 2024-08-09 | 2024-08-23 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 750000 | [10 empty] | Continue
240129_531 | 2024 | CIP2024 |  | Region 3 | Free State | 22161X | Absa Bloemfontein Forum | Absa Bloemfontein Forum, Building storerooms at a parkade, Fabric, Other |  | Fabric : Corporate | 2024-02-24 | 2024-03-06 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 735363.14 | [10 empty] | Continue
240129_579 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Catering - OE Smalls Top up provision, Catering |  | BAU FM Work | 2023-01-15 | 2023-09-25 |  | CAPEX | PR/8 | R.PR/8/04 | CORP - BAU Catering |  | 728517.43 | [10 empty] | Cancel
240129_295 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 36271X | Absa Upington | Absa Upington, Replacement of LED Panels installed in 2017, Electrical |  | Engineering: Retail | 2024-02-22 | 2024-02-26 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 714208.88 | [10 empty] | Continue
240129_544 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 36106X | Baywest Mall | Baywest Mall, Minor Works, Fabric, Other |  | Fabric: Retail | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 700000 | [10 empty] | Defer
240129_573 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Block A consolidation of room A11-A12, Fabric, Other |  | Fabric : Corporate | 2024-04-01 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 680000 | [10 empty] | Works Approved (2023)
240129_451 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Auckland Park , Replacement of 6 x Hydro taps, Fabric, Other |  | Fabric : Corporate | 2024-01-20 | 2024-01-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 673481.32 | [10 empty] | Continue
240129_321 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Replacement external floor tiles, Block A Pink toilet lobby , Block A smoke exit lobby / Ramp, Block A x3 Emergency exit lobby, Block E external floor tiles including Ramp, Block A Training centre install drainage system and drip trays on 27 External pot plants and re-tile surface., Fabric, Other |  | Fabric : Corporate | 2024-04-01 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 650000 | [10 empty] | Continue
240129_332 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 22460X | Absa Ridgeside | Absa Ridgeside, Installation of new blinds (automated) at the reception / look into making louvers moveable. Replacement of the deck chairs and tables Purchase of the new furniture for main and client suit reception Combining client suits 7 and 8 to accommodate 30 People, Fabric, Other |  | Fabric : Corporate | 2024-03-15 | 2024-03-20 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 600000 | [10 empty] | Continue
240129_574 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Replace/upgrade all pause area cupboards phased approached, Fabric, Other |  | Fabric : Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 600000 | [10 empty] | Defer
240129_308 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 78140X | Absa Uniondale | Absa Uniondale, Electrical Infrastructure Degrading, Electrical |  | Engineering: Retail | 2024-06-01 | 2024-08-30 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 600000 | [10 empty] | Continue
240129_528 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 35041X | Alice lane North | Alice Lane South, Reception counter, cupboard and waiting area , Fabric, Other |  | Fabric : Corporate | 2024-05-01 | 2024-06-01 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 600000 | [10 empty] | Cancel
240129_563 | 2024 | CIP2024 |  | Region 3 | Free State | 76978X | Greytown | Greytown, Internal Refurbishment, Fabric, Other |  | Fabric: Retail | 2024-04-11 | 2024-04-22 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 600000 | [10 empty] | Cancel
240129_389 | 2024 | CIP2024 |  | Region 3 | Free State | 78841X | Ladybrand (17A Joubert Street ) | Ladybrand (17A Joubert Street ), Minor Works Upgrade: Need to upgrade the branch to the new Corporate Identity, new floor tiles, painting signage and floor carpets and external signage. OHS finding, as per SRA finding: Emergency door , Fabric, Other |  | Fabric: Retail | 2024-03-04 | 2024-03-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 600000 | [10 empty] | Continue
240129_444 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus , Upgrade/Refurb- Replace Hydro taps x 4 Units, Fabric, Other |  | Fabric : Corporate | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 550000 | [10 empty] | Continue
240129_370 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77548X | Mtubatuba | Mtubatuba, Replacement of floor finishes and ceiling tiles, upgrade of Ablutions and kitchen, painted of colours., Fabric, Other |  | Fabric: Retail | 2024-05-02 | 2024-05-12 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 550000 | [10 empty] | Continue
240129_036 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21330X | Birch Acres Mal | Birch Acres Mall, HVAC replacement entire branch + ATM, Mechanical |  | Engineering: Retail | 2024-06-01 | 2024-06-30 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 540000 | [10 empty] | Continue
240129_037 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77203X | Bracken City Shopping Centre | Bracken City Shopping Centre, HVAC Replacement, Mechanical |  | Engineering: Retail | 2024-06-01 | 2024-06-30 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 529200 | [10 empty] | Continue
240129_373 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78451X | 8 Top Road | 8 Top Road, Carpet replacement through out building and new carpet installation in office space where there is currently tiles and cement flooring, Fabric, Other |  | Fabric : Corporate | 2024-03-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 500000 | [10 empty] | Continue
240129_472 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Call Centre Auckland Park, BMS HVAC Controllers upgrade, BMS and EMS Systems |  | Engineering: Corporate | 2024-03-01 | 2024-03-30 |  | CAPEX | PR/1 | R.PR/1/09 | CORP - BMS and EMS Systems |  | 500000 | [10 empty] | Continue
240129_298 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus , UPS Battery Replacement, Electrical |  | Engineering: Corporate | 2024-04-01 | 2024-05-30 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 500000 | [10 empty] | Continue
240129_317 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Complete upgrade for Basement 3 cleaning and catering change rooms and we do not have gender assigned change room facilities that provide showers proper lockers and ablutions and hygiene equipment, Fabric, Other |  | Fabric : Corporate | 2024-02-01 | 2024-02-28 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 500000 | [10 empty] | Continue
240129_565 | 2024 | CIP2024 |  | Region 3 | Free State | 78855X | Hennenman | Hennenman, Upgrade the kitchen and toilet area, Fabric, Other |  | Fabric: Retail | 2024-04-12 | 2024-04-26 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 500000 | [10 empty] | Under review
240129_564 | 2024 | CIP2024 |  | Region 3 | North West | 77784X | Mega City | Mega City, Replace carpets in BOH, Treasury ,tellers and customer services area(Secure area), Fabric, Other |  | Fabric: Retail | 2024-03-04 | 2024-03-08 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 500000 | [10 empty] | Under review
240129_338 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77399X | Absa Caledon | Absa Caledon, Replace carpet tiles, Repaint branch, Fabric, Other |  | Fabric: Retail | 2024-04-15 | 2024-05-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 485000 | [10 empty] | Continue
240129_322 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Block C refurbishment x8 water damaged pause area cabinets including recycle station cabinet doors, Fabric, Other |  | Fabric : Corporate | 2024-04-01 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 485000 | [10 empty] | Continue
240129_339 | 2024 | CIP2024 |  | Region 2 | Western Cape | 78324X | Airport Shopping Centre - Belhar | Airport Shopping Centre - Belhar, Replace old spec ceiling tiles, Replace old spec floor tiles, Replace the office Blinds, Fabric, Other |  | Fabric: Retail | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 475000 | [10 empty] | Defer
240129_360 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21861X | Sanridge Square Shopping Centre | Sanridge Square Shopping Centre, HVAC replacement entire branch , Mechanical |  | Engineering: Retail | 2024-05-01 | 2024-06-30 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 468000 | [10 empty] | Continue
240129_316 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Call Centre Auckland Park, Replacement - all Barclays blue desk panels, Fabric, Other |  | Fabric : Corporate | 2024-06-01 | 2024-07-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 450000 | [10 empty] | Continue
240129_011 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Walk off Mats, Fabric, Other |  | Fabric : Corporate | 2024-01-20 | 2024-02-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 450000 | [10 empty] | Continue
240129_325 | 2024 | CIP2024 |  | Region 3 | Free State | 22161X | Bloemfontein Forum | Bloemfontein Forum, Build a close office with desk dividers for sales Hub on the 1st floor for 10 staff, Fabric, Other |  | Fabric : Corporate | 2024-01-05 | 2024-03-06 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 450000 | [10 empty] | Continue
240129_566 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 78145X | Carolina | Carolina, Replace Carpets on first floor to new CI; paint walls to new CI colours; replace all ceiling boards in branch; revamp all ablutions., Fabric, Other |  | Fabric: Retail | 2024-04-20 | 2024-04-28 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 450000 | [10 empty] | Under review
240129_411 | 2024 | CIP2024 |  | Region 3 | North West | 22197X | Mmabatho Crossings (Mafikeng) | Mmabatho Crossings (Mafikeng), Repaint branch and replace front offices glass frosting, Fabric, Other |  | Fabric: Retail | 2024-03-11 | 2024-03-21 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 450000 | [10 empty] | Continue
240129_340 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 77876X | Absa Patensie | Absa Patensie, Upgrade kitchen/ablutions/replace tiles/carpets back office/ Banking hall tiles/refurbish teller area/moveable , new furniture, refurbish ATM lobby/room. Assess structural fault in branch and new mantrap door., Fabric, Other |  | Fabric: Retail | 2024-05-20 | 2024-06-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 425000 | [10 empty] | Continue
240129_561 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77216X | Trade Route Mall | Trade Route Mall, Floor tiles, spray ceiling- replace carpets ( Outside branch operating hours), Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 406770 | [10 empty] | Under review
240129_043 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, supply and Install flammable storage room (Phase 2), Fire |  | Engineering: Corporate | 2024-02-01 | 2024-04-30 |  | CAPEX | PR/1 | R.PR/1/06 | CORP - Fire |  | 400000 | [10 empty] | Continue
240129_413 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 21868X | Metash building Pongola | Metash building Pongola, Replacement of carpets and application of new brave colours on walls, removal of queue rails from banking hall, Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-03-10 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 400000 | [10 empty] | Continue
240129_412 | 2024 | CIP2024 |  | Region 3 | Free State | 78607X | Welkom | Welkom, Replace carpets, paint of walls, replace ceiling tiles for the entire branch, Fabric, Other |  | Fabric: Retail | 2024-09-09 | 2024-09-23 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 400000 | [10 empty] | Continue
240129_387 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77326X | Southgate Mall | Southgate Mall, Kitchen unit is damaged requires replacement and floor tiles, close vacant cubicles and make online banking private (Outside branch operating hours), Fabric, Other |  | Fabric: Retail | 2024-08-01 | 2024-08-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 391302.74 | [10 empty] | Continue
240129_304 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Call Centre Auckland Park, Connect FCU Controllers To BMS, Mechanical |  | Engineering: Corporate | 2024-07-01 | 2024-07-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 380000 | [10 empty] | Continue
240129_091 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 22937X | Moffett Office Park | Moffett Office Park, MOP, Replace 2 X chiller condensing coils for chiller 1 and chiller 2 due to their deteriorating condition , Mechanical |  | Engineering: Corporate | 2024-02-15 | 2024-02-20 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 376630.67 | [10 empty] | Works Approved (2023)
240129_348 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 77262X | Garden Route Centre - Knysna | Garden Route Centre - Knysna, Repaint interior of site Brave colours. Replace venetian blind in banking hall. Internet Kiosk installation new spec. . , Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 375000 | [10 empty] | Continue
240129_386 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 79059X | Maponya Mall | Maponya Mall, Tube system from ATM to Treasury (Outside branch operating hours), Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 366704 | [10 empty] | Continue
240129_581 | 2024 | CIP2024 |  | Region 2 | Western Cape | 36225X | Bridge Park | Bridge Park, Kitchen Vinyl, Fabric, Other |  | Fabric : Corporate | 2024-10-01 | 2024-10-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 360000 | [10 empty] | Cancel
240129_341 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 76426X | Absa Somerset East | Absa Somerset East, Replace ATM lobby/room floor tiles & repaint. + ATM Meta Wall, Fabric, Other |  | Fabric: Retail | 2024-05-15 | 2024-06-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 350000 | [10 empty] | Continue
240129_342 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 77596X | Absa Willowmore | Absa Willowmore, Upgrade ablutions/ kitchen/ teller/banking hall replace carpets with floor tiles, and moveable q rail. Replace furniture, benches. Replace internal signage. , Fabric, Other |  | Fabric: Retail | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 350000 | [10 empty] | Defer
240129_529 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Coffee Bar, restaurant and patio tables, chairs and umbrellas upgrade., Fabric, Other |  | Fabric : Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 350000 | [10 empty] | Defer
240129_555 | 2024 | CIP2024 |  | Region 3 | Limpopo | 22539X | Blouberg(Senwabarwana) | Blouberg(Senwabarwana), Replace all Ceramic Tiles in banking hall with new CI tiles. (Tentative until we see what TCR Remediation project will cover)., Fabric, Other |  | Fabric: Retail | 2024-03-08 | 2024-03-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 350000 | [10 empty] | Under review
240129_567 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77543X | Pavillion | Pavillion, Upgrade of Ablutions replace floor tiles and Carpets- paint to new colours, Fabric, Other |  | Fabric: Retail | 2024-04-19 | 2024-04-29 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 350000 | [10 empty] | Under review
240129_414 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77316X | Schoemansdal (Matsamo Plaza) | Schoemansdal (Matsamo Plaza), Provide additional bathroom - there is only Single bathroom for 10 staff members; Replace old sales consultants desk with new spec to optimize space; Same for Customer services; and pause area to be reconfigured to accommodate new toilet facilities., Fabric, Other |  | Fabric: Retail | 2024-05-11 | 2024-05-21 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 350000 | [10 empty] | Continue
240129_046 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77216X | Trade Route MalL | Trade Route Mall, Install BMS System and interface the equipment together with the newly installed HVAC system, Mechanical |  | Engineering: Corporate | 2024-01-20 | 2024-06-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 350000 | [10 empty] | Continue
240129_361 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21714X | Laudium Square | Laudium Square, HVAC replacement, Mechanical |  | Engineering: Retail | 2024-04-01 | 2024-05-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 342000 | [10 empty] | Continue
240129_560 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77812X | River Square | River Square, Floor tiles and carpets replacement, Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 302323.24 | [10 empty] | Under review
240129_557 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77647X | Absa Fochville | Absa Fochville, Replacement of floor tiles and poster frames - external building painting (outside branch operating hours), Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 301300 | [10 empty] | Continue
240129_420 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Upgrade of the Hydro taps (x3) at ATW pause areas (Old parts that are expensive to maintain), Fabric, Other |  | Fabric : Corporate | 2024-03-01 | 2024-03-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 300000 | [10 empty] | Continue
240129_430 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Corp Plugs for meetings rooms, Electrical |  | Engineering: Corporate | 2024-10-20 | 2024-11-20 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 300000 | [10 empty] | Continue
240129_320 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Prayer rooms revamp (x2) ( new shower facilities, cabinets, walls to be painted), Fabric, Other |  | Fabric : Corporate | 2024-10-01 | 2024-10-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 300000 | [10 empty] | Continue
240129_569 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77409X | Durban North (18 Swapo Road) | Durban North (18 Swapo Road), Replacement of ceiling tiles and floor tiles on stairway, Fabric, Other |  | Fabric: Retail | 2024-03-14 | 2024-03-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 300000 | [10 empty] | Under review
240129_568 | 2024 | CIP2024 |  | Region 3 | Limpopo | 36251X | Groblersdal MalI | Groblersdal Mall, Paint to all walls and doors in branch introducing lux colours; replace carpets to front of house and back office including cash areas, Fabric, Other |  | Fabric: Retail | 2024-05-17 | 2024-05-23 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 300000 | [10 empty] | Under review
240129_371 | 2024 | CIP2024 |  | Region 3 | North West | 77784X | Mega City | Mega City, Modifications on the existing HVAC , Mechanical |  | Engineering: Retail | 2024-03-25 | 2024-04-29 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 300000 | [10 empty] | Continue
240129_390 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76783X | Janefurse | Janefurse, Replace all Carpet to front of house and back office including cash areas; Repaint doors and walls in branch introducing lux colours, Fabric, Other |  | Fabric: Retail | 2024-05-11 | 2024-05-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 285000 | [10 empty] | Continue
240129_343 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77700X | 49 Main Road Gansbaai | 49 Main Road Gansbaai, Replace old spec floor tiles, Fabric, Other |  | Fabric: Retail | 2024-05-01 | 2024-05-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 275000 | [10 empty] | Continue
240129_402 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 78456X | Roxys Village Walk (Bronkhorstspruit) | Roxys Village Walk (Bronkhorstspruit), Carpet replacement. Bumper rail and repainting, Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 273808 | [10 empty] | Continue
240129_540 | 2024 | CIP2024 |  | Region 2 | Western Cape | 78113X | Absa Malmesbury | Absa Malmesbury, Replace Carpet on 1st Floor, Fabric, Other |  | Fabric: Retail | 2024-05-20 | 2024-06-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 260000 | [10 empty] | Under review
240129_344 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 76549X | Absa Despatch | Absa Despatch, Replace chairs, ATM room makeover. Pave generator area., Fabric, Other |  | Fabric: Retail | 2024-06-01 | 2024-06-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 250000 | [10 empty] | Continue
240129_045 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Auckland Park, upgrade of the parkade Satt system on the roof to the weather proofed sensors, Mechanical |  | Engineering: Corporate | 2024-02-01 | 2024-06-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 250000 | [10 empty] | Continue
240129_558 | 2024 | CIP2024 |  | Region 3 | Free State | 78754X | Bloem CBD | Bloem CBD, Replace Greenwave BMS with current BMS, BMS and EMS Systems |  | Engineering: Retail | 2024-02-08 | 2024-02-08 |  | CAPEX | PR/2 | R.PR/2/09 | RETAIL - BMS and EMS Systems |  | 250000 | [10 empty] | Continue
240129_326 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 79297X | Carnarvon | Carnarvon, Replace external louvers, Fabric, Other |  | Fabric : Corporate | 2024-03-19 | 2024-03-23 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 250000 | [10 empty] | Continue
240129_336 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 78145X | Carolina | Carolina, Painting of plastered sections to the external building facades; painting and remediation of rain water goods; replacement of ATM lobby floor tiles to match with entrance lobby tiles; painting of carports and backyard palisade fence. Installation of LED Lights in entire branch (Recent TMR installed only 3 LED lights in Teller area), Fabric, Other |  | Fabric : Corporate | 2024-04-20 | 2024-04-28 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 250000 | [10 empty] | Continue
240129_550 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77861X | Eshowe | Eshowe, Replace carpets, Upgrade of Ablutions and kitchen, Fabric, Other |  | Fabric: Retail | 2024-05-15 | 2024-05-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 250000 | [10 empty] | Under review
240129_391 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77974X | Mkhuhlu | Mkhuhlu, Extend the BA’s office to include a cleaning storage cabinet and increase space in the back office; replace Kitchen cabinets with new units., Fabric, Other |  | Fabric: Retail | 2024-06-08 | 2024-06-11 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 250000 | [10 empty] | Continue
240129_352 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 35034X | Secunda Mall | Secunda Mall, Replace all carpets in back office; Replace Vinyl floor tiles in ATM Room; Replace ceramic tiles at the entrance lobby; Repaint walls at front and back of house., Fabric, Other |  | Fabric: Retail | 2024-05-10 | 2024-05-16 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 250000 | [10 empty] | Continue
240129_424 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77566X | Volksrust | Volksrust, Painting of external walls to building facades); painting and remediation of rain water goods; replacement of ATM lobby wall tiles along the entrance façade; paint to yard palisade fence, Fabric, Other |  | Fabric : Corporate | 2024-03-19 | 2024-03-25 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 250000 | [10 empty] | Continue
240129_553 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77647X | Absa Fochville | Absa Fochville, Spray / replace ceiling tiles, Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 249750 | [10 empty] | Continue
240129_345 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 36206X | Broadway Building - Uitenhage | Broadway Building - Uitenhage, Paint brave colours in interior, tile back office area due heavy foot traffic to ablutions and kitchen., Fabric, Other |  | Fabric: Retail | 2024-08-01 | 2024-08-15 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 240000 | [10 empty] | Continue
240129_290 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77700X | 49 Main Road Gansbaai | 49 Main Road Gansbaai, HVAC upgrade, Mechanical |  | Engineering: Retail | 2024-05-01 | 2024-05-15 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 225000 | [10 empty] | Continue
240129_536 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77657X | Absa Lower Long Street | Absa Lower Long Street, Sluice's Room's X 3 - 2nd 3rd and 4th floors, Fabric, Other |  | Fabric : Corporate | 2024-05-15 | 2024-06-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 225000 | [10 empty] | Continue
240129_403 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21857X | Tsakane Mall | Tsakane Mall, Carpet and floor tile replacement + painting, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 202087.98 | [10 empty] | Continue
240129_379 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78786X | 17 Harrison Street (Main Street) | 17 Harrison Street (Main Street), Frosting requires by the ATM lobby (during branch operating hours), Fabric, Other |  | Fabric: Retail | 2024-05-01 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Continue
240129_306 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Call Centre Auckland Park, Replace HVAC Unit Filters, Mechanical |  | Engineering: Corporate | 2024-03-01 | 2024-03-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 200000 | [10 empty] | Continue
240129_527 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77878X | Absa Square RHO | Absa Square RHO, Replace existing desking with open desk seating arrangement similar to Absa Towers, Fabric, Other |  | Fabric : Corporate | 2024-04-12 | 2024-04-26 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 200000 | [10 empty] | Cancel
240129_525 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78944X | Absa Towers Main | Absa Towers Main, Replace HVAC Unit Filters, Mechanical |  | Engineering: Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 200000 | [10 empty] | Defer
240129_305 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Replace HVAC Unit Filters, Mechanical |  | Engineering: Corporate | 2024-03-01 | 2024-03-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 200000 | [10 empty] | Continue
240129_538 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 77427X | Centurion Building | Centurion Building, replacement of blinds / frosting, Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Defer
240129_425 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 70641X | Grand Palace | Grand Palace, Replace Carpets with Vinyl tiles in Server room; Change direction of door swing for the door along fire escape route to open towards flow of traffic; Create Cleaning storeroom; provide new signage for redefined fire escape route., Fabric, Other |  | Fabric : Corporate | 2024-04-05 | 2024-04-12 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 200000 | [10 empty] | Continue
240129_393 | 2024 | CIP2024 |  | Region 3 | Limpopo | 36246X | Musina Mall | Musina Mall, Replace back office carpets; Repaint all teller area walls; and repaint ATM room walls., Fabric, Other |  | Fabric: Retail | 2024-03-22 | 2024-03-26 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Continue
240129_551 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77839X | Raisethorpe | Raisethorpe, Refurbish kitchen and pause area, Fabric, Other |  | Fabric: Retail | 2024-07-05 | 2024-07-12 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Under review
240129_404 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78058X | Rayton Park Plaza | Rayton Park Plaza, Partition dividers between consultant desks, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Continue
240129_031 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 22460X | Ridgeside ABSA RHO | Ridgeside ABSA RHO, Masterpack Breakers , Electrical |  | Engineering: Corporate | 2024-06-07 | 2024-06-16 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 200000 | [10 empty] | Continue
240129_392 | 2024 | CIP2024 |  | Region 3 | Limpopo | 36254X | Thavhani Mali | Thavhani Mall, Replace all Carpet to front of house and back office, repaint pause area and installing bumper rails to affected walls., Fabric, Other |  | Fabric: Retail | 2024-03-29 | 2024-04-05 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Continue
240129_570 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77891X | Ulundi shopping centre | Ulundi shopping centre , Upgrade Ablutions and back office area, Fabric, Other |  | Fabric: Retail | 2024-05-15 | 2024-05-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 200000 | [10 empty] | Under review
240129_441 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77360X | Absa Spar | Absa Spar, Replacement APC UPS, Mechanical |  | Engineering: Retail | 2024-02-16 | 2024-02-18 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 175710.09 | [10 empty] | Continue
240129_327 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 76958X | Arbour Crossing Retail Centre | Arbour Crossing Retail Centre, Replace ceiling tiles, Fabric, Other |  | Fabric : Corporate | 2024-03-21 | 2024-03-25 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 160000 | [10 empty] | Continue
240129_440 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76718X | Hoedspruit | Hoedspruit, APC Unit Replacement, Mechanical |  | Engineering: Retail | 2024-01-17 | 2024-01-18 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 159736.44 | [10 empty] | Continue
240129_309 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 77401X | Absa Beaufort West | Absa Beaufort West, DB Upgrade / Access Issue (Safety), Electrical |  | Engineering: Retail | 2024-06-15 | 2024-06-30 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Continue
240129_323 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77641X | Absa Bredasdorp | Absa Bredasdorp, Secure the boundary Fence , Fabric, Other |  | Fabric : Corporate | 2024-07-10 | 2024-07-20 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 150000 | [10 empty] | Continue
240129_537 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Block out vinyl for wrap station, Fabric, Other |  | Fabric : Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 150000 | [10 empty] | Defer
240129_467 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 76439X | Central City Shopping Centre Mabopane | Central City Shopping Centre Mabopane, Installation of generator steel cage shelter , Engineering and Infrastructure |  | Engineering: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/2 | R.PR/2/02 | RETAIL - Engineering and Infrastructure |  | 150000 | [10 empty] | Continue
240129_293 | 2024 | CIP2024 |  | Region 3 | Free State | 79303X | Fleurdal Mall | Fleurdal Mall, Installation of UPS and electrical reticulation, Electrical |  | Engineering: Retail | 2024-03-15 | 2024-03-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Under review
240129_312 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 78645X | Hope Town | Hope Town, Installation of UPS and electrical reticulation, Electrical |  | Engineering: Retail | 2024-02-06 | 2024-02-13 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Continue
240129_394 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76721X | Mokopane | Mokopane, Replace Carpets, Install bumper rails in teller area, Fabric, Other |  | Fabric: Retail | 2024-04-22 | 2024-04-28 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 150000 | [10 empty] | Continue
240129_311 | 2024 | CIP2024 |  | Region 3 | North West | 36104X | Moruleng Mall | Moruleng Mall, Installation of UPS (Upgrade from 3kVA to 15kVA), Electrical |  | Engineering: Retail | 2024-03-02 | 2024-03-02 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Continue
240129_292 | 2024 | CIP2024 |  | Region 3 | Free State | 79067X | Petrusburg | Petrusburg, Installation of UPS and electrical reticulation, Electrical |  | Engineering: Retail | 2024-03-16 | 2024-03-16 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Continue
240129_310 | 2024 | CIP2024 |  | Region 3 | North West | 78032X | Phokeng Mall | Phokeng Mall, Installation of UPS (Upgrade from 3kVA to 15kVA), Electrical |  | Engineering: Retail | 2024-03-02 | 2024-03-02 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Continue
240129_291 | 2024 | CIP2024 |  | Region 3 | Free State | 79334X | Trompsburg | Trompsburg, Installation of UPS and electrical reticulation, Electrical |  | Engineering: Retail | 2024-03-15 | 2024-03-15 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 150000 | [10 empty] | Continue
240129_547 | 2024 | CIP2024 |  | National | National | Various | Various Sites | Various Sites, Catering - EOL Equipment 2023, Catering |  | BAU FM Work | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/8 | R.PR/8/04 | CORP - BAU Catering |  | 137931.62 | [10 empty] | Defer
240129_039 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice lane North, Replacement of generator starter batteries (special out LCC consideration), Electrical |  | Engineering: Corporate | 2024-09-10 | 2024-10-10 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 130000 | [10 empty] | Continue
240129_353 | 2024 | CIP2024 |  | Region 3 | North West | 37181X | Church Str Klerksdorp | Church Str Klerksdorp, Install Privacy screen at 1st ATM, include move of q-rails and replace damaged tiles , Fabric, Other |  | Fabric: Retail | 2024-06-14 | 2024-06-18 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 120000 | [10 empty] | Continue
240129_381 | 2024 | CIP2024 |  | Region 3 | Free State | 78655X | Montana (Fin Forum) | Montana (Fin Forum), Frosting on shop front windows, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 120000 | [10 empty] | Continue
240129_382 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22896X | 230 Lilian Ngoyi Street | 230 Lilian Ngoyi Street, Carpet replacement at the welcome desk, Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 102324 | [10 empty] | Continue
240129_040 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21335X | 270 Republic Road | 270 Republic Road, Replacement of generator starter batteries (special out LCC consideration), Electrical |  | Engineering: Corporate | 2024-03-01 | 2024-09-27 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 100000 | [10 empty] | Continue
240129_374 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78451X | 8 Top Road | 8 Top Road, All blinds require replacement - Office , Fabric, Other |  | Fabric : Corporate | 2024-05-01 | 2024-06-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 100000 | [10 empty] | Continue
240129_375 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78451X | 8 Top Road | 8 Top Road, Roof over office at mech workshop, Fabric, Other |  | Fabric : Corporate | 2024-06-01 | 2024-06-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 100000 | [10 empty] | Continue
240129_494 | 2024 | CIP2024 |  | Region 3 | Free State | 78350X | Absa Parys | Absa Parys, Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-03-04 | 2024-03-18 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_422 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Block K enclose garden refusal disposal area (Shipping container), Fabric, Other |  | Fabric : Corporate | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 100000 | [10 empty] | Continue
240129_421 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Replace all roof wooden doors to aluminium as the wooden get affected by weather., Fabric, Other |  | Fabric : Corporate | 2024-05-01 | 2024-05-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 100000 | [10 empty] | Continue
240129_303 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice lane North, Replacement of CRAC Unit Filters, Mechanical |  | Engineering: Corporate | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 100000 | [10 empty] | Continue
240129_449 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77421X | Bethal | Bethal , Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-05-21 | 2024-05-30 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_559 | 2024 | CIP2024 |  | Region 3 | Free State | 22161X | Bloemfontein Forum | Bloemfontein Forum, New Installation of a bulk diesel tank to support the Generator Day Tank., New Assets |  | Engineering: Corporate | 2024-02-08 | 2024-02-22 |  | CAPEX | PR/1 | R.PR/1/10 | CORP - New assets |  | 100000 | [10 empty] | Continue
240129_448 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 37064X | Delmas | Delmas, Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-04-22 | 2024-05-05 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_447 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77584X | Ermelo | Ermelo, Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-04-16 | 2024-04-28 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_493 | 2024 | CIP2024 |  | Region 3 | Free State | 78306X | Frankfort | Frankfort , Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-02-29 | 2024-03-15 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_313 | 2024 | CIP2024 |  | Region 3 | North West | 77784X | Mega City | Mega City, Linking UPS to BMS, Electrical |  | Engineering: Retail | 2024-03-01 | 2024-03-01 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 100000 | [10 empty] | Continue
240129_492 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 79051X | Nquthu | Nquthu, Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-03-18 | 2024-04-01 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_395 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77511X | Paulpietersburg (17 High Street) | Paulpietersburg (17 High Street), Replacement of carpets and application new brand colours on walls, Fabric, Other |  | Fabric: Retail | 2024-03-14 | 2024-03-19 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 100000 | [10 empty] | Continue
240129_491 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77893X | Port Edward | Port Edward, Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-04-03 | 2024-04-18 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_490 | 2024 | CIP2024 |  | Region 3 | Free State | 79293X | Theunissen | Theunissen, Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-03-13 | 2024-03-27 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_475 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77729X | Umlazi | Umlazi, Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-03-18 | 2024-04-01 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_446 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77602X | White River | White River, Installation of water tank, booster pump and filtration system , New assets |  | Engineering: Retail | 2024-06-18 | 2024-06-26 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 100000 | [10 empty] | Continue
240129_405 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 37163X | Kempton Square Central Park, External signage to be added in main road, Fabric, Other | Kempton Square Central Park, External signage to be added in main road, Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 90000 | [10 empty] | Continue
240129_496 | 2024 | CIP2024 |  | Region 3 | North West | 77787X | Mogwase Shopping Centre | Mogwase Shopping Centre, Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-03-11 | 2024-04-18 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 90000 | [10 empty] | Continue
240129_495 | 2024 | CIP2024 |  | Region 3 | Free State | 79096X | Warden | Warden, Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-03-15 | 2024-03-30 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 90000 | [10 empty] | Continue
240129_552 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76785X | Kwagga | Kwagga, Replace Kitchen Cupboard with new, Fabric, Other |  | Fabric: Retail | 2024-04-20 | 2024-04-22 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 85000 | [10 empty] | Cancel
240129_439 | 2024 | CIP2024 |  | Region 3 | Free State | 79293X | Theunissen | Theunissen, HVAC Unit, Mechanical |  | Engineering: Retail | 2024-02-24 | 2024-02-24 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 80720.4 | [10 empty] | Continue
240129_396 | 2024 | CIP2024 |  | Region 3 | North West | 77114X | 99 Walter Sisulu Potchefstroom | 99 Walter Sisulu Potchefstroom, Close off entrance of back area gate due to unwanted vagrants utilizing the area, Fabric, Other |  | Fabric: Retail | 2024-01-20 | 2024-01-21 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 80000 | [10 empty] | Continue
240129_435 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76808X | Absa Tzaneen HotelDanie Joubert | Absa Tzaneen HotelDanie Joubert , Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | Engineering: Retail | 2024-01-22 | 2024-01-26 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 79414.86 | [10 empty] | Continue
240129_324 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 77596X | Absa Willowmore | Absa Willowmore, Windows to be replaced (glass), Fabric, Other |  | Fabric : Corporate | 2024-04-15 | 2024-05-10 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 75000 | [10 empty] | Continue
240129_314 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77446X | Blue Haze Shopping Centre | Blue Haze Shopping Centre, Linking generator to BMS, Electrical |  | Engineering: Retail | 2024-05-15 | 2024-05-18 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 75000 | [10 empty] | Continue
240129_426 | 2024 | CIP2024 |  | Region 3 | Free State | 78702X | Botshabelo Shopping Centre | Botshabelo Shopping Centre, Change or replace main shopfront with roller rooter door , Fabric, Other |  | Fabric: Retail | 2024-04-15 | 2024-04-22 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 75000 | [10 empty] | Continue
240129_535 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 22937X | Moffett Office Park | Moffett Office Park, MOP, Sluice's Room X1, Fabric, Other |  | Fabric : Corporate | 2024-04-15 | 2024-05-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 75000 | [10 empty] | Continue
240129_524 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 22460X | Ridgeside ABSA RHO | Ridgeside ABSA RHO, Replacement of Generator Batteries (Generator 1, 2 & 3), Electrical |  | Engineering: Corporate | 2024-03-22 | 2024-03-24 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 75000 | [10 empty] | Continue
240129_474 | 2024 | CIP2024 |  | Region 3 | Free State | 78702X | Absa Botshabelo | Absa Botshabelo , HVAC Replacement- Hide away, Mechanical |  | Engineering: Retail | 2023-12-05 | 2023-12-06 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 70720.4 | [10 empty] | Continue
240129_307 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76849X | Absa Call Centre Auckland Park | Absa Call Centre Auckland Park, Cassette Unit, Mechanical |  | Engineering: Corporate | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/1 | R.PR/1/05 | CORP - Mechanical |  | 70000 | [10 empty] | Continue
240129_035 | 2024 | CIP2024 |  | Region 3 | Free State | 77745X | Absa Heilbron | Absa Heilbron , Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-02-24 | 2024-02-24 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 70000 | [10 empty] | Continue
240129_034 | 2024 | CIP2024 |  | Region 3 | North West | 79227X | Absa Taung | Absa Taung , Installation of water tank, booster pump and filtration system, New assets |  | Engineering: Retail | 2024-01-22 | 2024-02-02 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 70000 | [10 empty] | Continue
240129_406 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 78727X | Daveyton Shopping Centre | Daveyton Shopping Centre, External signage to be added in main road, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 70000 | [10 empty] | Continue
240129_407 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76576X | OR Tambo International Airport | OR Tambo International Airport, Repainting and carpet replacement, Fabric, Other |  | Fabric: Retail | 2024-07-01 | 2024-07-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 68850 | [10 empty] | Continue
240129_433 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76949X | Lea Glen Stores | Lea Glen Stores, Installation of Electric Fence , Electrical |  | Engineering: Corporate | 2024-10-01 | 2024-10-30 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 66500 | [10 empty] | Continue
240129_518 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 35041X | Alice lane North | Alice lane South, Replacement of generator starter batteries (special out LCC consideration), Electrical |  | Engineering: Corporate | 2024-03-15 | 2024-08-30 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 60000 | [10 empty] | Continue
240129_507 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 36206X | Broadway Building - Uitenhage | Broadway Building - Uitenhage, Install the cages for the outdoor units that are exposed., Mechanical |  | Engineering: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 60000 | [10 empty] | Continue
240129_296 | 2024 | CIP2024 |  | Region 3 | Free State | 78830X | Langenhovenpark | Langenhovenpark , New HVAC installation in the back office, New assets |  | Engineering: Retail | 2024-07-11 | 2024-07-13 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 60000 | [10 empty] | Continue
240129_346 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 76436X | Linton Arcade | Linton Arcade, Contra vision shopfront replace., Fabric, Other |  | Fabric: Retail | 2024-02-15 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 60000 | [10 empty] | Continue
240129_571 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76554X | Multiflora (Flower Market ETC) | Multiflora (Flower Market ETC), upgrade of kitchen + hydroboil - replace floor tiles , Fabric, Other |  | Fabric: Retail | 2024-07-01 | 2024-07-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 59104 | [10 empty] | Under review
240129_415 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77139X | Protea Gardens Shopping Centre | Protea Gardens Shopping Centre, replace floor tiles, respray ceiling tiles- blinds for tellers and carpet replacement (outside branch operating hours), Fabric, Other |  | Fabric: Retail | 2024-07-01 | 2024-07-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 57051.5 | [10 empty] | Continue
240129_545 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 37159X | Riversdale | Riversdale, Kitchen Upgrade, Fabric, Other |  | Fabric: Retail | 2024-07-01 | 2024-08-06 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 55000 | [10 empty] | Under review
240129_516 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 78314X | The Fynbos Centre, Stillbay, Buitenkant Street. | The Fynbos Centre, Stillbay, Buitenkant Street. , HVAC in the ATM room, Mechanical |  | Engineering: Retail | 2024-05-15 | 2024-05-30 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 55000 | [10 empty] | Continue
240129_384 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22896X | 230 Lilian Ngoyi Street | 230 Lilian Ngoyi Street, Frosting internal on Offices, Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_416 | 2024 | CIP2024 |  | Region 3 | North West | 77725X | Absa Bank Mafikeng CBD | Absa Bank Mafikeng CBD, New Installation of HVAC in the BA office., New assets |  | Engineering: Retail | 2024-05-10 | 2024-05-13 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 50000 | [10 empty] | Continue
240129_378 | 2024 | CIP2024 |  | Region 3 | North West | 77433X | Absa Bank Swartruggens | Absa Bank Swartruggens, New Installation of HVAC in the ATM room., New assets |  | Engineering: Retail | 2024-05-17 | 2024-05-19 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 50000 | [10 empty] | Continue
240129_331 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 22460X | Absa Ridgeside | Absa Ridgeside, Automation of doors on the canteen and the forth floor balcony , Fabric, Other |  | Fabric : Corporate | 2024-03-15 | 2024-03-16 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 50000 | [10 empty] | Continue
240211_001 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Block out vinyl for wrap station, Fabric, Other |  | Fabric : Corporate | 2024-09-15 | 2024-10-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_385 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 77427X | Centurion Building | Centurion Building, Marketing frosting on Shop Front requires replacement, Fabric, Other |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_328 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 78398X | Chatterton | Chatterton, Replace carpets in Cash operations office, Fabric, Other |  | Fabric : Corporate | 2024-02-17 | 2024-02-18 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_409 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 36216X | Cosmo Mall | Cosmo Mall, Repainting, carpets and floor tiles, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_383 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 76686X | Ga-Rankuwa Shopping Centre | Ga-Rankuwa Shopping Centre, Replace frosting on shop front, Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_398 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77938X | Komatipoort Spar Centre | Komatipoort Spar Centre, Provide access to the elevated storeroom (Retractable staircase); install walk off mat to main entrance door., Fabric, Other |  | Fabric: Retail | 2024-02-10 | 2024-02-13 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_452 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77329X | Lenasia | Lenasia, Link BMS to generator , BMS and EMS Systems |  | Engineering: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/2 | R.PR/2/09 | RETAIL - BMS and EMS Systems |  | 50000 | [10 empty] | Continue
240129_429 | 2024 | CIP2024 |  | Region 3 | North West | 77725X | Mafikeng CBD | Mafikeng CBD, Connection of the Teller work stations to UPS, Electrical |  | Engineering: Retail | 2024-03-01 | 2024-03-01 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 50000 | [10 empty] | Continue
240129_297 | 2024 | CIP2024 |  | Region 3 | Free State | 78545X | Mimosa Mall , New HVAC installation in the treasury area , New assets | Mimosa Mall , New HVAC installation in the treasury area , New assets |  | Engineering: Retail | 2024-03-08 | 2024-03-08 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 50000 | [10 empty] | Continue
240129_003 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77033X | Pharows House | Pharows House , Fresh Air/Extraction system , Mechanical |  | Engineering: Retail | 2024-02-28 | 2024-03-03 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 50000 | [10 empty] | Continue
240129_397 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 77102X | Pinetown | Pinetown, Replacement of boom, Fabric, Other |  | Fabric: Retail | 2024-02-19 | 2024-02-19 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_294 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 21312X | Postmasburg | Postmasburg, Install emergency lighting in the Branch., Electrical |  | Engineering: Retail | 2024-05-11 | 2024-05-11 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 50000 | [10 empty] | Continue
240129_408 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 76563X | Quo Vadis Centre (Westonaria) | Quo Vadis Centre (Westonaria), replacement of shop front frosting, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Continue
240129_572 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 76514X | Tshwane Market | Tshwane Market , MW-Replace Tiles in the branch with darker colour tiles - dirty from bulk money, Repaint the entire branch, Replacement of carpet , Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Defer
240129_556 | 2024 | CIP2024 |  | Region 3 | Free State | 78702X | UOVS, | UOVS, Branch require new office: teller chairs, couches, 4 x chairs and a table for pause area, Fabric, Other |  | Fabric: Retail | 2024-02-28 | 2024-02-28 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 50000 | [10 empty] | Under review
240129_288 | 2024 | CIP2024 |  | Region 3 | KwaZulu - Natal | 78193X | Windermere | Windermere, Replacement of HVAC in ATM room, Mechanical |  | Engineering: Retail | 2024-06-06 | 2024-06-06 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 50000 | [10 empty] | Continue
240129_335 | 2024 | CIP2024 |  | Region 3 | North West | 79117X | Christiana | Christiana, Install paving around generator cage and water tank, Fabric, Other |  | Fabric : Corporate | 2024-06-10 | 2024-06-13 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 45000 | [10 empty] | Continue
240129_418 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77271X | Mountain Mill Shopping Centre | Mountain Mill Shopping Centre, Install HVAC unit in the hosting office, Mechanical |  | Engineering: Retail | 2024-07-01 | 2024-07-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 45000 | [10 empty] | Continue
240129_427 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77271X | Mountain Mill Shopping Centre | Mountain Mill Shopping Centre, Install HVAC unit in the server room, Mechanical |  | Engineering: Retail | 2024-07-01 | 2024-07-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 45000 | [10 empty] | Continue
240129_442 | 2024 | CIP2024 |  | Region 3 | Free State | 78326X | Jan Kempdorp-De La Rey St-Jan Kempdorp | Jan Kempdorp-De La Rey St-Jan Kempdorp, Replacement of an AC Split Unit in the Branch Manager's office, Mechanical |  | Engineering: Retail | 2024-01-31 | 2024-01-31 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 42649.08 | [10 empty] | Continue
240129_330 | 2024 | CIP2024 |  | Region 3 | North West | 77605X | Absa Wolmaransstad Ground Floor, Absa Building 18A Kruger Street, Replacement of PC Boards & Installation of surge protection Absa Wolmaransstad is a leasehold branch situated in the North West Province. The branch reported that the air conditioning is not working and has been turned off completely. Portable units were provided as a temporary solution. This happened during a power outage in the area. The vendor went to the site to investigate and discovered that the PC boards in the air-conditioning units were burnt. According to the vendor, the damage to the PC boards was most likely caused by a power surge. There is currently no surge protection in the branch's main distribution board. Note: Supported by BFM Engineering. No GMP Cost Impact, only components will be replaced. Scope of Work • Replace PC Boards in DVR, Server Room, Manager's Office & ATM Room as required.(x8) • Supply & install Type 3 surge protector as required (x1). • Electrical COC will be issued upon completion., Electrical | Absa Wolmaransstad Ground Floor, Absa Building 18A Kruger Street, Replacement of PC Boards & Installation of surge protection Absa Wolmaransstad is a leasehold branch situated in the North West Province. The branch reported that the air conditioning is not working and has been turned off completely. Portable units were provided as a temporary solution. This happened during a power outage in the area. The vendor went to the site to investigate and discovered that the PC boards in the air-conditioning units were burnt. According to the vendor, the damage to the PC boards was most likely caused by a power surge. There is currently no surge protection in the branch's main distribution board. Note: Supported by BFM Engineering. No GMP Cost Impact, only components will be replaced. Scope of Work • Replace PC Boards in DVR, Server Room, Manager's Office & ATM Room as required.(x8) • Supply & install Type 3 surge protector as required (x1). • Electrical COC will be issued upon completion., Electrical |  | Engineering: Retail | 2024-03-18 | 2024-03-19 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 42380.4 | [10 empty] | Cancel
240129_436 | 2024 | CIP2024 |  | Region 3 | Mpumalanga | 77571X | Absa Kamaqhekeza | Absa Kamaqhekeza , Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | Engineering: Retail | 2024-01-17 | 2024-01-18 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 41821.55 | [10 empty] | Continue
240129_434 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76709X | Absa Eden Square | Absa Eden Square, Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | Engineering: Retail | 2024-01-22 | 2024-01-23 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 40338.58 | [10 empty] | Continue
240129_350 | 2024 | CIP2024 |  | Region 2 | Western Cape | 77702X | 116 Main Road Somerset West | 116 Main Road Somerset West, Replace the shade cloth in Parking Area (Is this not Landlord Responsibility), Double Bay?, Fabric, Other |  | Fabric: Retail | 2024-07-01 | 2024-07-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 40000 | [10 empty] | Continue
240129_354 | 2024 | CIP2024 |  | Region 3 | Free State | 78841X | Absa 17A Joubert Street | Absa 17A Joubert Street, Connection of various work stations to UPS, Electrical |  | Engineering: Retail | 2024-03-18 | 2024-03-18 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 40000 | [10 empty] | Continue
240129_351 | 2024 | CIP2024 |  | Region 3 | North West | 77150X | Austin Crossing Centre | Austin Crossing Centre, Connection of various work stations to UPS, Electrical |  | Engineering: Retail | 2024-05-10 | 2024-05-10 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 40000 | [10 empty] | Continue
240129_334 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 78684X | Hartswater | Hartswater, Connection of various work stations to UPS, Electrical |  | Engineering: Retail | 2024-03-11 | 2024-03-11 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 40000 | [10 empty] | Continue
240129_377 | 2024 | CIP2024 |  | Region 3 | Free State | 77962X | Orkney | Orkney, Installation of extractor fans in the bathrooms, Mechanical |  | Engineering: Retail | 2024-05-17 | 2024-05-17 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 40000 | [10 empty] | Continue
240129_333 | 2024 | CIP2024 |  | Region 3 | Free State | 78615X | Phuthaditjhaba Shopping Centre | Phuthaditjhaba Shopping Centre, Connection of various work stations to UPS, Electrical |  | Engineering: Retail | 2024-03-19 | 2024-03-19 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 40000 | [10 empty] | Continue
240129_577 | 2024 | CIP2024 |  | Region 2 | Western Cape | 36225X | Bridge Park Bridgeway Century City | Bridge Park Bridgeway Century City, Way finder Client suite Area (Monitor for Condeco), Fabric, Other |  | Fabric : Corporate | 2024-03-01 | 2024-03-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 35000 | [10 empty] | Cancel
240129_437 | 2024 | CIP2024 |  | Region 3 | Limpopo | 76783X | Absa Jane Furse | Absa Jane Furse, Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | Engineering: Retail | 2024-01-22 | 2024-01-23 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 32660.43 | [10 empty] | Continue
240129_355 | 2024 | CIP2024 |  | Region 3 | North West | 77725X | Absa Bank Mafikeng CBD | Absa Bank Mafikeng CBD, Connection of various work stations to UPS, Electrical |  | Engineering: Retail | 2024-05-20 | 2024-05-20 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 30000 | [10 empty] | Continue
240129_010 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Gas cage and 2X9 kg cylinders, Fabric, Other |  | Fabric : Corporate | 2024-03-01 | 2024-03-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 30000 | [10 empty] | Continue
240129_539 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 77381X | Absa Towers North | Absa Towers North (Retail), Evacuation door at kitchen, requires a ramp for wheel chair access ( evac chair), Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 30000 | [10 empty] | Continue
240129_450 | 2024 | CIP2024 |  | Region 3 | North West | 77745X | Absa Vryburg | Absa Vryburg, Drilling of holes to allow rain water drainage, Mechanical |  | Engineering: Retail | 2024-02-26 | 2024-02-27 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 30000 | [10 empty] | Continue
240129_362 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 36267X | Bisho Seda Building | Bisho Seda Building, Drip tray for x2 ATM room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 30000 | [10 empty] | Continue
240129_502 | 2024 | CIP2024 |  | Region 3 | North West | 22485X | Boitekong Mall | Boitekong Mall, New Installation of filtration system for the hydroboilers, New assets |  | Engineering: Retail | 2024-02-05 | 2024-02-05 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 30000 | [10 empty] | Continue
240129_423 | 2024 | CIP2024 |  | Region 2 | Western Cape | 36225X | Bridge Park Bridgeway Century City | Bridge Park Bridgeway Century City, Shower rooftop - Replace Chipped Stone , Fabric, Other |  | Fabric : Corporate | 2024-04-15 | 2024-05-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 30000 | [10 empty] | Continue
240129_428 | 2024 | CIP2024 |  | Region 3 | Free State | 78625X | Harrismith | Harrismith, Connecting customer service and teller to UPS, Electrical |  | Engineering: Retail | 2024-02-12 | 2024-02-12 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 30000 | [10 empty] | Continue
240129_504 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 35109X | Jubilee Mall | Jubilee Mall, Water filtration System, Water and System |  | Engineering: Retail | 2024-06-01 | 2024-06-30 |  | CAPEX | PR/2 | R.PR/2/07 | RETAIL - Water and System |  | 30000 | [10 empty] | Continue
240129_501 | 2024 | CIP2024 |  | Region 3 | North West | 77806X | Lichtenburg | Lichtenburg, New Installation of filtration system for the hydroboilers, New assets |  | Engineering: Retail | 2024-02-12 | 2024-02-12 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 30000 | [10 empty] | Continue
240129_500 | 2024 | CIP2024 |  | Region 3 | North West | 77725X | Mafikeng CBD | Mafikeng CBD, New Installation of filtration system for the hydroboilers, New assets |  | Engineering: Retail | 2024-02-19 | 2024-02-19 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 30000 | [10 empty] | Continue
240129_498 | 2024 | CIP2024 |  | Region 3 | North West | 77784X | Mega City | Mega City, New Installation of filtration system for the hydroboilers, New assets |  | Engineering: Retail | 2024-03-04 | 2024-03-04 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 30000 | [10 empty] | Continue
240129_499 | 2024 | CIP2024 |  | Region 3 | North West | 22197X | Mmabatho Crossings (Mafikeng) | Mmabatho Crossings (Mafikeng), New Installation of filtration system for the hydroboilers, New assets |  | Engineering: Retail | 2024-02-26 | 2024-02-26 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 30000 | [10 empty] | Continue
240129_503 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 37152X | Renbro Shopping Centre | Renbro Shopping Centre, Water filtration System (smaller system), Water and System |  | Engineering: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/2 | R.PR/2/07 | RETAIL - Water and System |  | 30000 | [10 empty] | Continue
240129_554 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 36299X | Sunward Park Lifestyle Centre | Sunward Park Lifestyle Centre, Change the door so it opens towards inside (pause area and ablutions), Fabric, Other |  | Fabric: Retail | 2024-06-01 | 2024-06-01 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 30000 | [10 empty] | Cancel
240129_399 | 2024 | CIP2024 |  | Region 3 | North West | 79227X | Taung, Install | Taung, Install paving around generator cage, Fabric, Other |  | Fabric: Retail | 2024-07-26 | 2024-07-28 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 30000 | [10 empty] | Continue
240129_497 | 2024 | CIP2024 |  | Region 3 | North West | 21941X | Zeerust | Zeerust, New Installation of filtration system for the hydroboilers, New assets |  | Engineering: Retail | 2024-03-04 | 2024-03-04 |  | CAPEX | PR/2 | R.PR/2/10 | RETAIL - New assets |  | 30000 | [10 empty] | Continue
240129_400 | 2024 | CIP2024 |  | Region 3 | Limpopo | 35151X | Tubatse Crossing | Tubatse Crossing, Replace Vinyl tiles in Server room, Fabric, Other |  | Fabric: Retail | 2024-05-11 | 2024-05-13 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 25000 | [10 empty] | Continue
240129_575 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Absa Towers West, Prepare and Respray cold room , Fabric, Other |  | Fabric : Corporate | 2024-03-01 | 2024-03-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 24150 | [10 empty] | Cancel
240129_517 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 37006X | Meadowdale | Meadowdale, Replacement of Generator starter batteries, Electrical |  | Engineering: Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/1 | R.PR/1/04 | CORP - Electrical |  | 21600 | [10 empty] | Defer
240129_438 | 2024 | CIP2024 |  | Region 3 | Northern Cape | 78504X | Absa Kuruman | Absa Kuruman, Replacement of Motor Gate, Electrical |  | Engineering: Retail | 2024-01-30 | 2024-01-30 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 20156.74 | [10 empty] | Continue
240129_356 | 2024 | CIP2024 |  | Region 3 | Free State | 77546X | Absa Koster | Absa Koster, Installation of plug points in the ATM and treasury, Electrical |  | Engineering: Retail | 2024-06-13 | 2024-06-13 |  | CAPEX | PR/2 | R.PR/2/04 | RETAIL - Electrical |  | 20000 | [10 empty] | Continue
240129_576 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 22491X | Absa Pretoria Campus | Absa Pretoria Campus, Wellness Centre Upgrade, Fabric, Other |  | Fabric : Corporate | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 20000 | [10 empty] | Continue
240129_401 | 2024 | CIP2024 |  | Region 3 | North West | 77996X | Sannieshof | Sannieshof, Burglar bar door add at vault, Fabric, Other |  | Fabric: Retail | 2024-06-11 | 2024-06-12 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 20000 | [10 empty] | Continue
240129_363 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 79209X | Absa Aliwal North | Absa Aliwal North, Drip tray for HVAC in server room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 15000 | [10 empty] | Continue
240129_364 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 78540X | Absa Cofimvaba | Absa Cofimvaba, Drip tray for HVAC in server room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 15000 | [10 empty] | Continue
240129_365 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 20949X | Absa Ntabankulu | Absa Ntabankulu, Drip tray for HVAC in server room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 15000 | [10 empty] | Continue
240129_417 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 79189X | Absa Settles Square Greenfields | Absa Settles Square Greenfields, Drip tray for HVAC in server room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 15000 | [10 empty] | Continue
240129_347 | 2024 | CIP2024 |  | Region 2 | Western Cape | 78130X | Absa Vredendal | Absa Vredendal, Bumper Rails to be installed, Fabric, Other |  | Fabric: Retail | 2024-04-01 | 2024-04-20 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 15000 | [10 empty] | Continue
240129_366 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 76387X | Newton Park | Newton Park, Drip tray for HVAC in server room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 15000 | [10 empty] | Continue
240129_367 | 2024 | CIP2024 |  | Region 2 | Eastern Cape | 70631X | Rhino Centre Lusikisiki | Rhino Centre Lusikisiki, Drip tray for HVAC in server room with water pump, Mechanical |  | Engineering: Retail | 2024-03-15 | 2024-04-20 |  | CAPEX | PR/2 | R.PR/2/05 | RETAIL - Mechanical |  | 15000 | [10 empty] | Continue
240129_410 | 2024 | CIP2024 |  | Region 1 | Gauteng North | 35109X | Jubilee Mall | Jubilee Mall, Walk off mat at front entrance , Fabric, Other |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  | CAPEX | PR/3 | R.PR/3/13 | RETAIL - Fabric - Other |  | 8000 | [10 empty] | Continue
240129_376 | 2024 | CIP2024 |  | Region 1 | Gauteng South | 79271X | 13 Top Road | 13 Top Road, Installation of blinds, Fabric, Other |  | Fabric : Corporate | 2024-04-01 | 2024-04-15 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | 2500 | [10 empty] | Continue
240129_537a | 2024 | CIP2024 |  | Region 1 | Gauteng South | 70656X | Alice lane North | Alice Lane North, Block out vinyl for wrap station, Fabric, Other |  | Fabric : Corporate | 2025-01-01 | 2025-12-31 |  | CAPEX | PR/3 | R.PR/3/05 | CORP - Fabric - Other |  | -50000 | [10 empty] | Defer

## Rollovers_2023
Request_No | Source ID | Project Number | Value | lookup |  | Project number | Request_No
240131_013 | ROL2023 | ALP-CR0022 | 89594.913 | 70000829 |  | ALP-CR0022 | 70000829
240129_087 | ROL2023 | ALP-CR0029 | 1108817.11 | 90000118 |  | ALP-CR0029 | 90000118
240129_118 | ROL2023 | ALP-CR0032 | 11567.9305 | 90000121 |  | ALP-CR0032 | 90000121
240129_514 | ROL2023 | ALP-CR0034 | 1008119.42 | 90000343 |  | ALP-CR0034 | 90000343
240129_513 | ROL2023 | ALP-CR0037 | 800218.01 | 90000346 |  | ALP-CR0037 | 90000346
240129_159 | ROL2023 | ALP-CR0038 | 600657 | 90000490 |  | ALP-CR0038 | 90000490
240129_152 | ROL2023 | ALP-EC0016 | 1519237.8 | 90000447 |  | ALP-EC0016 | 90000447
240129_166 | ROL2023 | ALP-EC0018 | 768233.45 | 90000483 |  | ALP-EC0018 | 90000483
240129_064 | ROL2023 | ALP-GN0010 | 2557617.9975 | 70000017 |  | ALP-GN0010 | 70000017
240129_280 | ROL2023 | ALP-GN0011 | 104026.999 | 70000018 |  | ALP-GN0011 | 70000018
240129_104 | ROL2023 | ALP-GN0013 | 354402.561 | 70000019 |  | ALP-GN0013 | 70000019
240129_100 | ROL2023 | ALP-GN0015 | 1795821.97 | 90000779 |  | ALP-GN0015 | 90000779
240129_249 | ROL2023 | ALP-GS0022 | 207778.09 | 70000854 |  | ALP-GS0022 | 70000854
240129_065 | ROL2023 | ALP-GS0024 | 625946.278 | 70000855 |  | ALP-GS0024 | 70000855
240129_105 | ROL2023 | ALP-GS0036 | 88621.645 | 70000028 |  | ALP-GS0036 | 70000028
240129_109 | ROL2023 | ALP-GS0042 | 874175.9385 | 70000032 |  | ALP-GS0042 | 70000032
240129_252 | ROL2023 | ALP-GS0046 | 30353.4105 | 70000036 |  | ALP-GS0046 | 70000036
240129_263 | ROL2023 | ALP-GS0047 | 140191.2675 | 70000837 |  | ALP-GS0047 | 70000837
240129_213 | ROL2023 | ALP-GS0048 | 74834.893 | 70000838 |  | ALP-GS0048 | 70000838
240129_512 | ROL2023 | ALP-GS0050 | 985001.3465 | 70000037 |  | ALP-GS0050 | 70000037
240129_232 | ROL2023 | ALP-GS0053 | 18674.4475 | 90000124 |  | ALP-GS0053 | 90000124
240129_055 | ROL2023 | ALP-GS0057 | 10345176.11 | 90000229 |  | ALP-GS0057 | 90000229
240129_171 | ROL2023 | ALP-GS0064 | 10129149.75 | 90000594 |  | ALP-GS0064 | 90000594
240129_059 | ROL2023 | ALP-GS0066 | 889836.87 | 90000611 |  | ALP-GS0066 | 90000611
240129_258 | ROL2023 | ALP-GS0067 | 1156314.56 | 90000624 |  | ALP-GS0067 | 90000624
240129_174 | ROL2023 | ALP-GS0068 | 1127081 | 90000698 |  | ALP-GS0068 | 90000698
240129_179 | ROL2023 | ALP-GS0069 | 900778.74 | 90000731 |  | ALP-GS0069 | 90000731
240129_285 | ROL2023 | ALP-GS0070 | 60159.053 | 90000732 |  | ALP-GS0070 | 90000732
240129_054 | ROL2023 | ALP-GS0072 | 2634278.73 | 90000740 |  | ALP-GS0072 | 90000740
240129_058 | ROL2023 | ALP-GS0074 | 3112110 | 90000755 |  | ALP-GS0074 | 90000755
240129_151 | ROL2023 | ALP-GS0075 | 1134152.8275 | 90000756 |  | ALP-GS0075 | 90000756
240129_101 | ROL2023 | ALP-GS0076 | 1773654.63 | 90000780 |  | ALP-GS0076 | 90000780
240129_511 | ROL2023 | ALP-GS0079 | 1580931.21 | 90000800 |  | ALP-GS0079 | 90000800
240129_053 | ROL2023 | ALP-GS0082 | 1490130.83 | 90000808 |  | ALP-GS0082 | 90000808
240129_210 | ROL2023 | ALP-GS0083 | 1118581.16 | 90000810 |  | ALP-GS0083 | 90000810
240129_175 | ROL2023 | ALP-GS0086 | 808786.44 | 90000836 |  | ALP-GS0086 | 90000836
240129_060 | ROL2023 | ALP-KZ0007 | 1488433.46 | 70000038 |  | ALP-KZ0007 | 70000038
240129_082 | ROL2023 | ALP-KZ2003 | 39997.782 | 90000126 |  | ALP-KZ2003 | 90000126
240129_114 | ROL2023 | ALP-KZ2004 | 968574 | 90000158 |  | ALP-KZ2004 | 90000158
240131_015 | ROL2023 | ALP-KZ2005 | 55234.0745 | 90000219 |  | ALP-KZ2005 | 90000219
240129_153 | ROL2023 | ALP-KZ2006 | 832777 | 90000519 |  | ALP-KZ2006 | 90000519
240129_093 | ROL2023 | ALP-KZ2007 | 1288285 | 90000520 |  | ALP-KZ2007 | 90000520
240129_094 | ROL2023 | ALP-KZ2008 | 1286621 | 90000521 |  | ALP-KZ2008 | 90000521
240129_097 | ROL2023 | ALP-KZ2009 | 4324829 | 90000669 |  | ALP-KZ2009 | 90000669
240129_052 | ROL2023 | ALP-LP0001 | 30855.73 | #N/A |  | ALP-LP0201 | 90000089
240129_085 | ROL2023 | ALP-LP0201 | 887570 | 90000089 |  | ALP-LP0201 | 90000310
240129_084 | ROL2023 | ALP-MP0206 | 726985 | 90000605 |  | ALP-MP0206 | 90000605
240129_086 | ROL2023 | ALP-MP0207 | 569351.03 | 90000100 |  | ALP-MP0207 | 90000100
240129_074 | ROL2023 | ALP-N00009 | 902146.8555 | 70000858 |  | ALP-MP0207 | 90000728
240129_212 | ROL2023 | ALP-N00015 | 951889.62 | 70000853 |  | ALP-N00009 | 70000858
240131_001 | ROL2023 | ALP-N00019 | 288488.3905 | 70000861 |  | ALP-N00015 | 70000853
240129_168 | ROL2023 | ALP-N00019 | 190226.1 | 70000861 | X | ALP-N00019 | 70000861
240129_062 | ROL2023 | ALP-N00021 | 690218.7645 | 70000862 |  | ALP-N00021 | 70000862
240129_063 | ROL2023 | ALP-N00022 | 1128206.999 | 70000863 |  | ALP-N00022 | 70000863
240129_169 | ROL2023 | ALP-N00024 | 55834.225 | 70000047 |  | ALP-N00024 | 70000047
240129_170 | ROL2023 | ALP-N00025 | 567029.2005 | 70000048 |  | ALP-N00025 | 70000048
240129_068 | ROL2023 | ALP-N00029 | 2452443.393 | 70000051 |  | ALP-N00029 | 70000051
240129_067 | ROL2023 | ALP-N00030 | 8021318.904 | 70000052 |  | ALP-N00030 | 70000052
240129_214 | ROL2023 | ALP-N00034 | 854629.64 | 70000844 |  | ALP-N00034 | 70000844
240129_187 | ROL2023 | ALP-N00035 | 25380.5 | 70000056 |  | ALP-N00035 | 70000056
240129_110 | ROL2023 | ALP-N00037 | 168962.922 | 90000128 |  | ALP-N00037 | 90000128
240129_191 | ROL2023 | ALP-N00038 | 102088.72 | 90000129 |  | ALP-N00038 | 90000129
240129_070 | ROL2023 | ALP-N00039 | 126396.0295 | 90000130 |  | ALP-N00039 | 90000130
240131_017 | ROL2023 | ALP-N00041 | 447166.41 | 90000132 |  | ALP-N00041 | 90000132
240129_195 | ROL2023 | ALP-N00043 | 484971.53 | 90000160 |  | ALP-N00043 | 90000160
240129_218 | ROL2023 | ALP-N00044 | 2437659.91 | 90000195 |  | ALP-N00044 | 90000195
240129_075 | ROL2023 | ALP-N00046 | 1939755.745 | 90000299 |  | ALP-N00046 | 90000299
240129_226 | ROL2023 | ALP-N00047 | 11384897.11 | 90000302 |  | ALP-N00047 | 90000302
240129_221 | ROL2023 | ALP-N00050 | 47356525 | 90000584 |  | ALP-N00050 | 90000584
240129_180 | ROL2023 | ALP-N00051 | 494445.3405 | 90000595 |  | ALP-N00051 | 90000595
240129_098 | ROL2023 | ALP-N00054 | 3334665.5455 | 90000608 |  | ALP-N00054 | 90000608
240129_203 | ROL2023 | ALP-N00056 | 19281887.81 | 90000736 |  | ALP-N00056 | 90000736
240129_224 | ROL2023 | ALP-N00057 | 1319754.02 | 90000744 |  | ALP-N00057 | 90000744
240129_134 | ROL2023 | ALP-N00067 | 7871417.57 | 90000874 |  | ALP-N00067 | 90000874
240129_135 | ROL2023 | ALP-N00068 | 6091895.16 | 90000875 |  | ALP-N00068 | 90000875
240129_201 | ROL2023 | ALP-N00069 | 1408997.59 | 90000882 |  | ALP-N00069 | 90000882
240129_071 | ROL2023 | ALP-WC0021 | 951618.35 | 90000162 |  | ALP-WC0021 | 90000162
240129_148 | ROL2023 | ALP-WC0025 | 1582320.135 | 90000471 |  | ALP-WC0025 | 90000471
240129_103 | ROL2023 | ASP-CR0266 | 94973.5 | 70000625 |  | ASP-CR0266 | 70000625
240129_202 | ROL2023 | ASP-CR0312 | 2614.456 | 70000114 |  | ASP-CR0312 | 70000114
240129_515 | ROL2023 | ASP-CR0354 | 1153858.21 | 70000141 |  | ASP-CR0354 | 70000141
240129_096 | ROL2023 | ASP-CR0374 | 193485.775 | 90000002 |  | ASP-CR0374 | 90000002
240129_122 | ROL2023 | ASP-CR0391 | 2644.632 | 90000019 |  | ASP-CR0391 | 90000019
240129_119 | ROL2023 | ASP-CR0393 | 3509.94 | 90000021 |  | ASP-CR0393 | 90000021
240129_129 | ROL2023 | ASP-CR0397 | 178956.92 | 90000025 |  | ASP-CR0397 | 90000025
240129_111 | ROL2023 | ASP-CR0425 | 3061.33 | 90000262 |  | ASP-CR0425 | 90000262
240129_155 | ROL2023 | ASP-CR0430 | 194513 | 90000291 |  | ASP-CR0430 | 90000291
240129_078 | ROL2023 | ASP-CR0440 | 44934.07 | 90000337 |  | ASP-CR0440 | 90000337
240129_225 | ROL2023 | ASP-CR0443 | 10460.98 | 90000391 |  | ASP-CR0443 | 90000391
240131_012 | ROL2023 | ASP-CR0456 | 2809.39 | 90000450 |  | ASP-CR0456 | 90000450
240129_081 | ROL2023 | ASP-CR0461 | 43270.836 | 90000475 |  | ASP-CR0461 | 90000475
240129_219 | ROL2023 | ASP-CR0472 | 35800.65 | 90000516 |  | ASP-CR0472 | 90000516
240129_161 | ROL2023 | ASP-CR0478 | 3400.0035 | 90000574 |  | ASP-CR0478 | 90000574
240129_083 | ROL2023 | ASP-CR0488 | 335642.74 | 90000645 |  | ASP-CR0488 | 90000645
240129_198 | ROL2023 | ASP-CR0499 | 34071.97 | 90000701 |  | ASP-CR0499 | 90000701
240129_220 | ROL2023 | ASP-CR0505 | 52340 | 90000715 |  | ASP-CR0505 | 90000715
240129_156 | ROL2023 | ASP-CR0508 | 120774.3235 | 90000719 |  | ASP-CR0508 | 90000719
240131_016 | ROL2023 | ASP-CR0518 | 33896.894 | 90000784 |  | ASP-CR0518 | 90000784
240129_200 | ROL2023 | ASP-CR0519 | 9509.9825 | 90000790 |  | ASP-CR0519 | 90000790
240129_108 | ROL2023 | ASP-CR0535 | 114743.34 | 90000873 |  | ASP-CR0535 | 90000873
240129_215 | ROL2023 | ASP-EC0278 | 34804.975 | 90000041 |  | ASP-EC0278 | 90000041
240129_072 | ROL2023 | ASP-EC0282 | 376684.69 | 90000146 |  | ASP-EC0282 | 90000146
240129_089 | ROL2023 | ASP-EC0340 | 23807.99 | 90000613 |  | ASP-EC0340 | 90000613
240129_092 | ROL2023 | ASP-EC0369 | 178505.84 | 90000759 |  | ASP-EC0369 | 90000759
240129_223 | ROL2023 | ASP-EC0370 | 28357.98 | 90000760 |  | ASP-EC0370 | 90000760
240129_095 | ROL2023 | ASP-EC0371 | 9748.15 | 90000785 |  | ASP-EC0371 | 90000785
240129_120 | ROL2023 | ASP-EC0375 | 38865.2 | 90000804 |  | ASP-EC0375 | 90000804
240129_286 | ROL2023 | ASP-GN0084 | 57500 | #N/A |  | ASP-GN0126 | 70000711
240129_251 | ROL2023 | ASP-GN0117 | 3405.61 | #N/A |  | ASP-GN0140 | 70000219
240129_199 | ROL2023 | ASP-GN0126 | 55750.6545 | 70000711 |  | ASP-GN0149 | 70000226
240129_107 | ROL2023 | ASP-GN0140 | 29292.6505 | 70000219 |  | ASP-GN0152 | 70000229
240129_106 | ROL2023 | ASP-GN0149 | 179156.7175 | 70000226 |  | ASP-GN0156 | 70000233
240131_003 | ROL2023 | ASP-GN0152 | 6076.31 | 70000229 |  | ASP-GN0157 | 70000234
240129_204 | ROL2023 | ASP-GN0156 | 1798.853 | 70000233 |  | ASP-GN0163 | 70000239
240129_261 | ROL2023 | ASP-GN0157 | 20865.6 | 70000234 |  | ASP-GN0182 | 90000139
240129_206 | ROL2023 | ASP-GN0163 | 1798.853 | 70000239 |  | ASP-GN0184 | 90000184
240129_267 | ROL2023 | ASP-GN0182 | 106121.3215 | 90000139 |  | ASP-GN0187 | 90000204
240129_266 | ROL2023 | ASP-GN0184 | 3347.42 | 90000184 |  | ASP-GN0189 | 90000234
240129_113 | ROL2023 | ASP-GN0187 | 36895.151 | 90000204 |  | ASP-GN0191 | 90000245
240129_271 | ROL2023 | ASP-GN0189 | 42527.552 | 90000234 |  | ASP-GN0193 | 90000271
240129_222 | ROL2023 | ASP-GN0191 | 12431.454 | 90000245 |  | ASP-GN0197 | 90000355
240129_274 | ROL2023 | ASP-GN0193 | 6168.84 | 90000271 |  | ASP-GN0206 | 90000422
240129_117 | ROL2023 | ASP-GN0197 | 20705.152 | 90000355 |  | ASP-GN0207 | 90000452
240129_164 | ROL2023 | ASP-GN0206 | 88952.5 | 90000422 |  | ASP-GN0208 | 90000453
240129_121 | ROL2023 | ASP-GN0207 | 38544.504 | 90000452 |  | ASP-GN0209 | 90000454
240129_145 | ROL2023 | ASP-GN0208 | 56077.726 | 90000453 |  | ASP-GN0210 | 90000455
240129_123 | ROL2023 | ASP-GN0209 | 28674.3415 | 90000454 |  | ASP-GN0212 | 90000457
240129_125 | ROL2023 | ASP-GN0210 | 19029.786 | 90000455 |  | ASP-GN0215 | 90000522
240129_124 | ROL2023 | ASP-GN0212 | 1240.62 | 90000457 |  | ASP-GN0217 | 90000545
240129_278 | ROL2023 | ASP-GN0215 | 57109 | 90000522 |  | ASP-GN0218 | 90000546
240129_238 | ROL2023 | ASP-GN0217 | 20046.9035 | 90000545 |  | ASP-GN0219 | 90000579
240129_133 | ROL2023 | ASP-GN0218 | 49267.1615 | 90000546 |  | ASP-GN0220 | 90000580
240129_139 | ROL2023 | ASP-GN0219 | 278231.23 | 90000579 |  | ASP-GN0221 | 90000581
240129_246 | ROL2023 | ASP-GN0220 | 19481 | 90000580 |  | ASP-GN0222 | 90000582
240129_142 | ROL2023 | ASP-GN0221 | 41923.227 | 90000581 |  | ASP-GN0224 | 90000596
240129_140 | ROL2023 | ASP-GN0222 | 20463.3415 | 90000582 |  | ASP-GN0226 | 90000635
240129_136 | ROL2023 | ASP-GN0224 | 37467 | 90000596 |  | ASP-GN0227 | 90000638
240129_277 | ROL2023 | ASP-GN0226 | 257036.5 | 90000635 |  | ASP-GN0230 | 90000674
240129_088 | ROL2023 | ASP-GN0227 | 480991.18 | 90000638 |  | ASP-GS0421 | 70000723
240129_154 | ROL2023 | ASP-GN0230 | 181447.5175 | 90000674 |  | ASP-GS0462 | 70000288
240129_208 | ROL2023 | ASP-GS0421 | 12882.139 | 70000723 |  | ASP-GS0467 | 70000292
240129_236 | ROL2023 | ASP-GS0462 | 60403.589 | 70000288 |  | ASP-GS0468 | 70000293
240129_193 | ROL2023 | ASP-GS0467 | 20312.1625 | 70000292 |  | ASP-GS0472 | 70000297
240129_177 | ROL2023 | ASP-GS0468 | 17831.624 | 70000293 |  | ASP-GS0473 | 70000298
240129_183 | ROL2023 | ASP-GS0472 | 3162.5 | 70000297 |  | ASP-GS0480 | 70000304
240129_184 | ROL2023 | ASP-GS0473 | 4302.8745 | 70000298 |  | ASP-GS0484 | 70000306
240129_178 | ROL2023 | ASP-GS0480 | 16651.149 | 70000304 |  | ASP-GS0488 | 70000309
240129_231 | ROL2023 | ASP-GS0484 | 81779.3865 | 70000306 |  | ASP-GS0489 | 70000310
240129_182 | ROL2023 | ASP-GS0488 | 106224.649 | 70000309 |  | ASP-GS0496 | 70000317
240131_002 | ROL2023 | ASP-GS0489 | 239512.018 | 70000310 |  | ASP-GS0501 | 70000321
240129_239 | ROL2023 | ASP-GS0496 | 1624.973 | 70000317 |  | ASP-GS0511 | 70000740
240129_181 | ROL2023 | ASP-GS0501 | 1798.853 | 70000321 |  | ASP-GS0512 | 70000741
240129_205 | ROL2023 | ASP-GS0511 | 21742.2795 | 70000740 |  | ASP-GS0513 | 70000742
240129_176 | ROL2023 | ASP-GS0512 | 8050 | 70000741 |  | ASP-GS0518 | 70000334
240129_186 | ROL2023 | ASP-GS0513 | 473524 | 70000742 |  | ASP-GS0520 | 70000336
240129_188 | ROL2023 | ASP-GS0518 | 17926.085 | 70000334 |  | ASP-GS0522 | 70000338
240129_240 | ROL2023 | ASP-GS0520 | 4068.1595 | 70000336 |  | ASP-GS0527 | 70000342
240129_237 | ROL2023 | ASP-GS0522 | 5908.286 | 70000338 |  | ASP-GS0539 | 70000352
240129_189 | ROL2023 | ASP-GS0527 | 3210.064 | 70000342 |  | ASP-GS0544 | 70000356
240129_190 | ROL2023 | ASP-GS0539 | 3139.5 | 70000352 |  | ASP-GS0553 | 70000364
240129_192 | ROL2023 | ASP-GS0544 | 8628.128 | 70000356 |  | ASP-GS0555 | 70000366
240129_194 | ROL2023 | ASP-GS0553 | 812.4865 | 70000364 |  | ASP-GS0556 | 70000367
240129_242 | ROL2023 | ASP-GS0555 | 5175 | 70000366 |  | ASP-GS0558 | 70000369
240129_241 | ROL2023 | ASP-GS0556 | 35435.893 | 70000367 |  | ASP-GS0582 | 70000387
240129_243 | ROL2023 | ASP-GS0558 | 24624.191 | 70000369 |  | ASP-GS0583 | 70000388
240129_244 | ROL2023 | ASP-GS0582 | 488125.3315 | 70000387 |  | ASP-GS0587 | 70000757
240131_004 | ROL2023 | ASP-GS0583 | 16738.25 | 70000388 |  | ASP-GS0597 | 90000048
240129_209 | ROL2023 | ASP-GS0587 | 21976.8565 | 70000757 |  | ASP-GS0607 | 90000058
240129_207 | ROL2023 | ASP-GS0597 | 24290.3 | 90000048 |  | ASP-GS0612 | 90000148
240131_005 | ROL2023 | ASP-GS0607 | 438003.812 | 90000058 |  | ASP-GS0613 | 90000149
240129_211 | ROL2023 | ASP-GS0612 | 1754.969 | 90000148 |  | ASP-GS0619 | 90000142
240129_262 | ROL2023 | ASP-GS0613 | 6721.06 | 90000149 |  | ASP-GS0620 | 90000143
240129_217 | ROL2023 | ASP-GS0619 | 410.8605 | 90000142 |  | ASP-GS0622 | 90000185
240129_265 | ROL2023 | ASP-GS0620 | 107149.203 | 90000143 |  | ASP-GS0629 | 90000210
240129_264 | ROL2023 | ASP-GS0622 | 11456.3 | 90000185 |  | ASP-GS0630 | 90000211
240129_269 | ROL2023 | ASP-GS0629 | 132299.0245 | 90000210 |  | ASP-GS0632 | 90000213
240129_270 | ROL2023 | ASP-GS0630 | 8312.982 | 90000211 |  | ASP-GS0635 | 90000216
240129_268 | ROL2023 | ASP-GS0632 | 35208.4 | 90000213 |  | ASP-GS0642 | 90000259
240129_282 | ROL2023 | ASP-GS0635 | 150443.46 | 90000216 |  | ASP-GS0645 | 90000272
240131_006 | ROL2023 | ASP-GS0642 | 170639.42 | 90000259 |  | ASP-GS0646 | 90000273
240129_272 | ROL2023 | ASP-GS0645 | 3347.42 | 90000272 |  | ASP-GS0649 | 90000277
240129_273 | ROL2023 | ASP-GS0646 | 4562.9125 | 90000273 |  | ASP-GS0650 | 90000278
240129_227 | ROL2023 | ASP-GS0649 | 56361.5 | 90000277 |  | ASP-GS0655 | 90000290
240129_234 | ROL2023 | ASP-GS0650 | 19503.8735 | 90000278 |  | ASP-GS0667 | 90000318
240129_228 | ROL2023 | ASP-GS0655 | 6142.3915 | 90000290 |  | ASP-GS0669 | 90000320
240129_131 | ROL2023 | ASP-GS0667 | 313698.15 | 90000318 |  | ASP-GS0676 | 90000338
240129_229 | ROL2023 | ASP-GS0669 | 5306.1 | 90000320 |  | ASP-GS0677 | 90000339
240129_196 | ROL2023 | ASP-GS0676 | 260793.33 | 90000338 |  | ASP-GS0678 | 90000360
240129_116 | ROL2023 | ASP-GS0677 | 49217 | 90000339 |  | ASP-GS0680 | 90000376
240131_007 | ROL2023 | ASP-GS0678 | 331206.11 | 90000360 |  | ASP-GS0688 | 90000399
240129_235 | ROL2023 | ASP-GS0680 | 35805.8595 | 90000376 |  | ASP-GS0690 | 90000401
240129_130 | ROL2023 | ASP-GS0688 | 38216.501 | 90000399 |  | ASP-GS0691 | 90000402
240129_276 | ROL2023 | ASP-GS0690 | 182398.4065 | 90000401 |  | ASP-GS0692 | 90000405
240129_275 | ROL2023 | ASP-GS0691 | 71918.125 | 90000402 |  | ASP-GS0698 | 90000458
240129_233 | ROL2023 | ASP-GS0692 | 27774.7195 | 90000405 |  | ASP-GS0709 | 90000482
240129_132 | ROL2023 | ASP-GS0698 | 364629.9595 | 90000458 |  | ASP-GS0714 | 90000503
240129_126 | ROL2023 | ASP-GS0709 | 13856.81 | 90000482 |  | ASP-GS0715 | 90000513
240129_080 | ROL2023 | ASP-GS0714 | 405949.747 | 90000503 |  | ASP-GS0718 | 90000524
240129_077 | ROL2023 | ASP-GS0715 | 79759.6185 | 90000513 |  | ASP-GS0719 | 90000525
240129_069 | ROL2023 | ASP-GS0718 | 47175.44 | 90000524 |  | ASP-GS0720 | 90000526
240129_066 | ROL2023 | ASP-GS0719 | 108092.16 | 90000525 |  | ASP-GS0729 | 90000583
240129_259 | ROL2023 | ASP-GS0720 | 263952.209 | 90000526 |  | ASP-GS0730 | 90000591
240129_165 | ROL2023 | ASP-GS0729 | 188322.804 | 90000583 |  | ASP-GS0731 | 90000597
240129_279 | ROL2023 | ASP-GS0730 | 33432.5585 | 90000591 |  | ASP-GS0732 | 90000609
240129_162 | ROL2023 | ASP-GS0731 | 131393.71 | 90000597 |  | ASP-GS0733 | 90000610
240129_141 | ROL2023 | ASP-GS0732 | 17324.175 | 90000609 |  | ASP-GS0736 | 90000642
240129_138 | ROL2023 | ASP-GS0733 | 125350 | 90000610 |  | ASP-GS0737 | 90000647
240129_281 | ROL2023 | ASP-GS0736 | 3285.09 | 90000642 |  | ASP-GS0738 | 90000648
240129_143 | ROL2023 | ASP-GS0737 | 152197.003 | 90000647 |  | ASP-GS0740 | 90000667
240129_173 | ROL2023 | ASP-GS0738 | 278484.76 | 90000648 |  | ASP-GS0743 | 90000678
240129_144 | ROL2023 | ASP-GS0740 | 130556.05 | 90000667 |  | ASP-GS0747 | 90000694
240129_146 | ROL2023 | ASP-GS0743 | 75282.45 | 90000678 |  | ASP-GS0749 | 90000723
240129_250 | ROL2023 | ASP-GS0747 | 13564.25 | 90000694 |  | ASP-GS0750 | 90000724
240129_163 | ROL2023 | ASP-GS0749 | 407616.3385 | 90000723 |  | ASP-GS0751 | 90000729
240129_245 | ROL2023 | ASP-GS0750 | 48537.0035 | 90000724 |  | ASP-GS0752 | 90000730
240129_284 | ROL2023 | ASP-GS0751 | 123681.166 | 90000729 |  | ASP-GS0757 | 90000773
240129_283 | ROL2023 | ASP-GS0752 | 20213.6535 | 90000730 |  | ASP-GS0758 | 90000774
240131_008 | ROL2023 | ASP-GS0757 | 43910.68 | 90000773 |  | ASP-GS0759 | 90000775
240131_009 | ROL2023 | ASP-GS0758 | 211616.79 | 90000774 |  | ASP-GS0761 | 90000787
240131_010 | ROL2023 | ASP-GS0759 | 127119.7005 | 90000775 |  | ASP-GS0763 | 90000801
240129_248 | ROL2023 | ASP-GS0759 | 3509.938 | 90000775 | X | ASP-GS0771 | 90000824
240129_158 | ROL2023 | ASP-GS0761 | 341036.5365 | 90000787 |  | ASP-KZ0222 | 70000609
240131_011 | ROL2023 | ASP-GS0763 | 15802.219 | 90000801 |  | ASP-KZ0225 | 90000063
240129_247 | ROL2023 | ASP-GS0763 | 1754.969 | 90000801 | X | ASP-KZ0226 | 90000064
240129_172 | ROL2023 | ASP-GS0771 | 394544.02 | 90000824 |  | ASP-KZ0227 | 90000065
240129_150 | ROL2023 | ASP-KZ0222 | 253892.2275 | 70000609 |  | ASP-KZ0248 | 90000312
240129_112 | ROL2023 | ASP-KZ0225 | 4095.012 | 90000063 |  | ASP-KZ0258 | 90000451
240129_073 | ROL2023 | ASP-KZ0226 | 279805.9 | 90000064 |  | ASP-KZ0259 | 90000478
240129_079 | ROL2023 | ASP-KZ0227 | 488433.4625 | 90000065 |  | ASP-KZ0263 | 90000662
240129_115 | ROL2023 | ASP-KZ0248 | 108645.68 | 90000312 |  | ASP-LP0108 | 70000447
240129_149 | ROL2023 | ASP-KZ0258 | 181249.68 | 90000451 |  | ASP-LP0136 | 70000469
240129_090 | ROL2023 | ASP-KZ0259 | 441690.16 | 90000478 |  | ASP-LP0166 | 90000434
240129_147 | ROL2023 | ASP-KZ0263 | 8579 | 90000662 |  | ASP-LP0182 | 90000770
240131_014 | ROL2023 | ASP-KZ2002 | 63173.985 | #N/A |  | ASP-MP0066 | 70000850
240129_185 | ROL2023 | ASP-LP0108 | 66458.5 | 70000447 |  | ASP-MP0088 | 70000478
240129_102 | ROL2023 | ASP-LP0136 | 50171.05 | 70000469 |  | ASP-MP0127 | 70000504
240129_076 | ROL2023 | ASP-LP0166 | 447055.69 | 90000434 |  | ASP-MP0154 | 90000098
240129_167 | ROL2023 | ASP-LP0182 | 2247.1 | 90000770 |  | ASP-MP0163 | 90000438
240129_061 | ROL2023 | ASP-MP0066 | 77226.7 | 70000850 |  | ASP-MP0171 | 90000686
240129_056 | ROL2023 | ASP-MP0088 | 61954.36 | 70000478 |  | ASP-N00053 | 90000340
240129_057 | ROL2023 | ASP-MP0127 | 68703.45 | 70000504 |  | ASP-N00057 | 90000389
240129_128 | ROL2023 | ASP-MP0154 | 10424.9225 | 90000098 |  | ASP-WC0282 | 90000353
240129_137 | ROL2023 | ASP-MP0163 | 12862.2555 | 90000438
240129_157 | ROL2023 | ASP-MP0171 | 77320.93 | 90000686
240129_099 | ROL2023 | ASP-N00053 | 98210 | 90000340
240129_216 | ROL2023 | ASP-N00057 | 21702.7475 | 90000389
240129_197 | ROL2023 | ASP-N00057 | 13589.6465 | 90000389 | X
240129_127 | ROL2023 | ASP-WC0282 | 93477.0985 | 90000353
240129_160 | ROL2023 | N/A | 6000000 | #N/A
240129_230 | ROL2023 | N/A | 50000 | #N/A | X

## OPEX_2024
Request_No | Year | Source ID | CHAR05 | Client Region | Client Region | One View Number | Description | Description | JSON String | Description | Planned Start Date | Planned End Date | Date in Format YYYYMMDD in 8 Characters | CHAR05 | Description | Description | Description | Description | Amount | Amount | Character Field Length = 10 | Description | Project number | Character Length 1 | JSON String | Planned Start Date | Planned End Date | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Appropriation request | Description
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 21526X | Absa Towers West | Setting and Torquing of the Vertical and Horizontal Façade & Roof Steel Structure |  | Engineering: Corporate | 2024-01-20 | 2024-02-10 |  |  | PR/1 | PR/1/02 | CORP - Engineering and Infrastructure |  | 1124980.14
| 2024 | OPEX24 |  | Region 1 | Gauteng North | 77036X | Hatfield Mall | Bumper rails and repainting |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 150000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 78944X | Absa Towers Main | Generator exhaust extension |  | Engineering: Corporate | 2024-06-01 | 2024-06-30 |  |  | PR/1 | PR/1/04 | CORP - Electrical |  | 150000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 78451X | 8 Top Road | Show room floor repainting (Epoxy) |  | Fabric: Corporate | 2024-09-01 | 2024-09-30 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 150000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 22896X | 230 Lilian Ngoyi Street | repainting of branch |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 120300
| 2024 | OPEX24 |  | Region 1 | Gauteng North | 77146X | Menlyn Park Shopping Centre | Bumper rails and repainting |  | Fabric: Retail | 2024-03-01 | 2024-03-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 120000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 36202X | Lakeside Mall | bumper rails and repainting |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 96607.7236
| 2024 | OPEX24 |  | Region 1 | Gauteng North | 76686X | Ga-Rankuwa Shopping Centre | Bumper rails and repainting |  | Fabric: Retail | 2024-07-01 | 2024-07-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 74500
| 2024 | OPEX24 |  | Region 1 | Gauteng North | 76693X | Mamelodi Crossing Centre | Bumper rails and repainting |  | Fabric: Retail | 2024-07-01 | 2024-07-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 70680
| 2024 | OPEX24 |  | Region 1 | Gauteng North | 76680X | Pretoria North (Northpark Mall Shopping Centre) | Bumper rails and repainting |  | Fabric: Retail | 2024-07-01 | 2024-07-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 63000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 76438X | Absa Central Avenue | Maintenance of water proofing - Done in 2020 |  | Waterproofing | 2024-04-01 | 2024-04-30 |  |  |  | 200 |  |  | 50000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 37148X | Sunnypark Shopping Centre | Bumper rails and repainting - damages from SBV |  | Fabric: Retail | 2024-07-01 | 2024-07-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 42300
| 2024 | OPEX24 |  | Region 1 | Gauteng North | 37014X | Queenswood Quarter | Bumper rails and repainting |  | Fabric: Retail | 2024-07-01 | 2024-07-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 40000
| 2024 | OPEX24 |  | Region 1 | Gauteng South | 36299X | Sunward Park Lifestyle Centre | bumper rails and repainting |  | Fabric: Retail | 2024-09-01 | 2024-09-30 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 40000
| 2024 | OPEX24 |  | Region 2 | Western Cape | 77657X | Absa Lower Long Street | Waterproofing - 8th Floor |  | Waterproofing | 2024-03-15 | 2024-05-15 |  |  |  | 200 |  |  | 2000000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 76442X | Absa Graaff-Reinet | Refurbish/Paint full exterior of the site walls, wooden shutters, window frames, facia boards -heritage site |  | Fabric: Corporate | 2024-05-15 | 2024-06-30 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 1250000
| 2024 | OPEX24 |  | Region 2 | Region 2 | 78132X | Absa Piketberg | Exterior building refurb/Paint |  | Fabric: Corporate | 2024-06-15 | 2024-07-15 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 1050000
| 2024 | OPEX24 |  | Region 2 | Region 2 | 78113X | Absa Malmesbury | Exterior building refurb/Paint |  | Fabric: Corporate | 2024-04-15 | 2024-05-15 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 950000
| 2024 | OPEX24 |  | Region 2 | Region 2 | 78131X | Absa Citrusdal | Exterior building refurb/Paint |  | Fabric: Corporate | 2024-05-15 | 2024-06-15 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 850000
| 2024 | OPEX24 |  | Region 2 | Region 2 | 77671X | Bonnievale | Exterior building refurb/Paint |  | Fabric: Corporate | 2024-07-15 | 2024-08-15 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 850000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 76426X | Absa Somerset East | Exterior repaint - Window Frames |  | Fabric: Corporate | 2024-04-15 | 2024-05-30 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 750000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 77688X | Absa Albertinia | Full Waterproofing |  | Waterproofing | 2024-07-01 | 2024-08-30 |  |  |  | 200 |  |  | 650000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 78140X | Absa Uniondale | Full Waterproofing |  | Waterproofing | 2024-06-01 | 2024-08-30 |  |  |  | 200 |  |  | 650000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 77876X | Absa Patensie | External building refurbish/Paint |  | Fabric: Corporate | 2024-04-20 | 2024-05-20 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 425000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 77512X | Absa Grahamstown | Repaint interior of site, new brave colours. |  | Fabric: Retail | 2024-08-01 | 2024-08-31 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 200000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 76934X | Absa Cradock | Repaint interior of site, new brave colours. |  | Fabric: Retail | 2024-07-15 | 2024-08-15 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 185000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 78381X | Cathcart Rd Queenstown | Painting new brave colours |  | Fabric: Retail | 2024-08-25 | 2024-09-25 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 185000
| 2024 | OPEX24 |  | Region 2 | Eastern Cape | 36281X | Libode Shopping Centre | Paint entire interior of site, Brave colours. |  | Fabric: Retail | 2024-07-20 | 2024-08-05 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 90000
| 2024 | OPEX24 |  | Region 3 | Free State | 78810X | Villiers | External Refurbishment +Remove all the grass at the back area and replace with paving, need to installed bigger grits at the main area for storm draining, Staff require carport |  | Fabric: Corporate | 2024-02-12 | 2024-03-08 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 800000
| 2024 | OPEX24 |  | Region 3 | Free State | 78856X | Absa Koppies Bloemfontein | External Refurbishment |  | Fabric: Corporate | 2024-02-01 | 2024-02-08 |  |  | PR/3 | PR/3/05 | CORP - Fabric - Other |  | 450000
| 2024 | OPEX24 |  | Energy | Various Sites | Various | Various Sites | Retail Green Star rating |  | Engineering: Retail | 2024-03-04 | 2024-08-31 |  | PR/2 |  | PR/2/03 | RETAIL - Energy |  | 3500000
| 2024 | OPEX24 |  | Energy | Gauteng South | 21526X | Absa Towers West | ISO 50001: 2011 Certification, EnMS implementation & End-User Training |  | Engineering: Corporate | 2024-03-04 | 2024-08-31 |  |  | PR/1 | PR/1/03 | CORP - Engineering and Infrastructure |  | 750000
| 2024 | OPEX24 |  | Energy | Gauteng North | 22491X | Absa Pretoria Campus | Green Star rating - EBP renewal |  | Engineering: Corporate | 2024-03-04 | 2024-08-31 |  |  | PR/1 | PR/1/03 | CORP - Engineering and Infrastructure |  | 450000
| 2024 | OPEX24 |  | Energy | Gauteng South | 77381X | Absa Towers North | Green Star rating - EBP renewal |  | Engineering: Corporate | 2024-03-04 | 2024-08-31 |  |  | PR/1 | PR/1/03 | CORP - Engineering and Infrastructure |  | 400000
| 2024 | OPEX24 |  | National | Various Sites | Various | Various Sites | Retail Documentation Compliance Programme (Phase 3 part 2b) - council submissions |  | Retail - BAU Compliance Documentation | 2024-02-15 | 2024-06-28 |  |  | PR/9 | PR/9/04 | RETAIL - BAU Compliance Documentation |  | 5000000
| 2024 | OPEX24 |  | National | Various Sites | Various | Various Sites | Small FM Items- Vinyl's, Decals, etc - BULK PO |  | Fabric: Retail | 2024-02-15 | 2024-09-25 |  |  | PR/3 | PR/3/13 | RETAIL - Fabric - Other |  | 750000
| 2024 | OPEX24 |  | National | Various Sites | Various | Various Sites | Audio & Visual |  | Fabric: Corporate | 2024-02-15 | 2024-09-25 |  |  | PR/3 | PR/3/09 | CORP - Fabric - Audio Visual |  | 1000000

## BOW_27 Feb 2024
Absa CIP Reference | Project Name | Proposed Start Date | Proposed End Date | Project Status | Absa CIP | One View Ref | Accountable Executive | Project Group | Type | Core/Key /Supporting Assets | Supplier End of Life (EOL) | Project Status Detail | Project Description | Supplier Reference (Other) | Supplier Reference | Lease Expiry Date | Lease Status | 2023 Roll-Overs | 2024 CIP (Excl. Roll-Overs) | 2024 CIP (Incl 2023 Roll-Overs) | # Projects
240129_221 | Various Corp Sites, Corporate Battery Energy Storage Systems (BES | 2024-02-19 | 2024-05-31 | Works Approved (2023) | R.PR/1/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction | Various Sites, Corporate Battery Energy Storage Systems (BESS), Energy | ALP-N00050 |  |  | TBC | 47356525 | 0 | 47356525 | 1
240129_471 | Various Retail Sites, Replacement of existing lights with LED light | 2024-03-04 | 2024-08-30 | Continue | R.PR/2/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Utility cost savings, carbon emission reduction, building energy performance improvement, | Various Sites, Replacement of existing lights with LED lighting (x 50 branches), Energy |  | 2400488 |  | TBC | 0 | 22500000 | 22500000 | 1
240129_203 | Various Corp Sites, Load Shedding mitigation, Electrical | 2023-11-01 | 2024-03-31 | Works Approved (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Started and Not Completed in 2023, Project in progress | Various Sites, Load Shedding mitigation, Electrical | ALP-N00056 |  |  | TBC | 19281887.81 | 0 | 19281887.81 | 1
240129_443 | Various Retail Sites, Install alternative power (x 10 Sites) Batter | 2024-02-26 | 2024-08-30 | Continue | R.PR/2/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction, | Various Sites, Install alternative power (x 10 Sites) Battery Walls & Solar, Energy |  | 2400489 |  | TBC | 0 | 15000000 | 15000000 | 1
240129_226 | Various Retail Sites, Alternative Power/Solar, Design, Supply & Ins | 2024-02-05 | 2024-05-31 | Works Approved (2023) | R.PR/2/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction | Alternative Power/Solar, Various Sites, Design, Supply & Installation of Solar PV Systems (Bonnievale, De Doorns, Wesselsbron and Oude Bloemhof), Energy | ALP-N00047 |  |  | TBC | 11384897.11 | 0 | 11384897.11 | 1
240129_055 | Absa Towers West, Lifts ports replacements on 27 X lifts - P | 2023-09-04 | 2024-03-31 | Works Approved (2023) | R.PR/1/05 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Project Started and Not Completed in 2023, Rollover-Project | Absa Towers West, Lifts ports replacements on 27 X lifts - Phase 2. (Block A, B and C), Mechanical | ALP-GS0057 | 2400263 |  | TBC | 10345176.11 | 0 | 10345176.11 | 1
240129_171 | Alice Lane Podium, Minor Works - CPF Fish Bowl, Remediation | 2023-10-20 | 2024-10-18 | Works Complete (2023) | R.PR/5/12 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice Lane Podium, Minor Works - CPF Fish Bowl, Remediation | ALP-GS0064 | 0 |  | Complete | 10129149.75 | 0 | 10129149.75 | 1
240129_067 | Various Retail Sites, (Phase 3- part 1a) 104 sites, BAU Doc Compliance | 2022-05-19 | 2024-03-30 | Works Approved (2023) | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in progress. Supplier will achieve Practical completion end of Nov. final completion requires final inspections to take place. Snags will have to be addressed thereafter. Last invoice in Feb '24. | Various Sites, Retail Documentation Compliance Programme Fire remedial works (Phase 3- part 1a) 104 sites, BAU Compliance Documentation | ALP-N00030 |  |  | TBC | 8021318.904 | 0 | 8021318.904 | 1
240129_134 | Various Corp Sites, Corporate EOL LED panels (Yellow lights) prog | 2023-02-19 | 2024-05-31 | Works Approved (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Project Started and Not Completed in 2023, EOL | Various Sites, Corporate EOL LED panels (Yellow lights) programme, Electrical | ALP-N00067 |  |  | TBC | 7871417.57 | 0 | 7871417.57 | 1
240129_135 | Various Retail Sites, Retail EOL LED panels (Yellow lights) program | 2023-02-19 | 2024-05-31 | Works Approved (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Started and Not Completed in 2023, EOL | Various Sites, Retail EOL LED panels (Yellow lights) programme, Electrical | ALP-N00068 |  |  | TBC | 6091895.16 | 0 | 6091895.16 | 1
240129_160 | Alice Lane North, BMS system, BMS and EMS Systems | 2024-03-15 | 2024-10-07 | Continue | R.PR/1/09 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice Lane, BMS system, BMS and EMS Systems | N/A | N/A |  | TBC | 6000000 | 0 | 6000000 | 1
240129_032 | Absa Towers West, BMS Upgrade, BMS and EMS Systems | 2024-02-15 | 2024-09-30 | Continue | R.PR/1/09 | 76439X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Rescheduled from 2023, | Absa Towers West, BMS Upgrade, BMS and EMS Systems |  | 2400206 |  | TBC | 0 | 5950050.5 | 5950050.5 | 1
240129_357 | Various Retail Sites, LED Yellow Lights, Electrical | 2024-04-01 | 2024-09-15 | Continue | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | TBC | Various Sites, LED Yellow Lights, Electrical |  | 2400506 |  | TBC | 0 | 4800000 | 4800000 | 1
240129_432 | Various Retail Sites, Install smart electricity and water meters (x | 2024-03-04 | 2024-08-30 | Continue | R.PR/2/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Enhanced quality of ESG/ sustainability reporting and disclosures, utility cost savings, | Various Sites, Install smart electricity and water meters (x 45 Sites), Energy |  | 2400490 |  | TBC | 0 | 4550000 | 4550000 | 1
240129_041 | Various Corp Sites, EOL Programme (LCC Based) - Mechanical, Mecha | 2024-04-01 | 2024-09-15 | Continue | R.PR/1/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Various Sites, EOL Programme (LCC Based) - Mechanical, Mechanical |  | 2400502 |  | TBC | 0 | 4404286.82 | 4404286.82 | 1
240129_097 | Absa Ridgeside , Internal and external painting, including r | 2023-12-07 | 2024-02-29 | Works Approved (2023) | R.PR/3/05 | 22460X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Ridgeside , Internal and external painting, including refurbishment of pause area cupboards, Fabric, Other | ALP-KZ2009 |  |  | TBC | 4324829 | 0 | 4324829 | 1
240129_580 | Various Corp Sites, Audio & Visual, Fabric, Audio Visual | 2024-02-15 | 2024-09-25 | Continue | R.PR/3/09 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | 15/06/2023: Moved from Region 1- National. Aukland Park R1,6m for 24 screens and projectors. | Various Sites, Audio & Visual, Fabric, Audio Visual |  | 2400503 |  | TBC | 0 | 4000000 | 4000000 | 1
240129_358 | Various Retail Sites, EOL Programme (LCC Based) - Electrical, Elect | 2024-04-01 | 2024-09-15 | Continue | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | TBC | Various Sites, EOL Programme (LCC Based) - Electrical, Electrical |  | 2400508 |  | TBC | 0 | 3595735 | 3595735 | 1
240129_098 | Alice Lane North, Parking Guidance System Upgrade (SATT System Sen | 2024-01-20 | 2024-10-03 | Works Approved (2023) | R.PR/1/09 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice Lane, Parking Guidance System Upgrade (SATT System Sensors), BMS and EMS Systems | ALP-N00054 |  |  | TBC | 3334665.5455 | 0 | 3334665.5455 | 1
240129_058 | 270 Republic Road, Installing New Carports, Fabric, Other | 2023-11-20 | 2024-03-31 | Works Approved (2023) | R.PR/3/05 | 21335X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | 270 Republic Road, Installing New Carports, Fabric, Other | ALP-GS0074 |  |  | TBC | 3112110 | 0 | 3112110 | 1
240129_054 | 270 Republic Road, Jace Panels and Controllers, Mechanical | 2023-11-01 | 2023-11-30 | Works Complete (2023) | R.PR/1/05 | 21334X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Completed and not invoiced in 2023, Rollover from CIP2023 | 270 Republic Road, Jace Panels and Controllers, Mechanical | ALP-GS0072 | 0 |  | Complete | 2634278.73 | 0 | 2634278.73 | 1
240129_064 | Absa Pretoria Campus, Refurbishing of the Ceilings and Fire | 2023-11-15 | 2024-02-29 | Works Approved (2023) | R.PR/1/06 | 22491X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Started and Not Completed in 2023, Rollover-Project | Absa Pretoria Campus, Refurbishing of the Ceilings and Fire Sprinkler System, Fire | ALP-GN0010 |  |  | TBC | 2557617.9975 | 0 | 2557617.9975 | 1
240129_068 | Various Retail Sites, (Phase 3- part 1a) 48 sites, BAU Doc Compliance | 2022-05-19 | 2024-03-30 | Works Approved (2023) | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in progress. Supplier will achieve Practical completion end of Nov. final completion requires final inspections to take place. Snags will have to be addressed thereafter. Last invoice in Feb '24. | Various Sites, Retail Documentation Compliance Programme Fire remedial works (Phase 3- part 1a) 48 Sites, BAU Compliance Documentation | ALP-N00029 |  |  | TBC | 2452443.393 | 0 | 2452443.393 | 1
240129_218 | Alternative Power/Solar, Lichtenburg & Emalahleni | 2024-02-05 | 2024-05-31 | Works Approved (2023) | R.PR/2/03 | 77806X & 76953X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction | Alternative Power/Solar, Lichtenburg (ALT Pwr) & Mandela Drive (Emalahleni) (ALT Pwr), Retail Solar PV Program Energy. 77806X & 76953X | ALP-N00044 |  |  | TBC | 2437659.91 | 0 | 2437659.91 | 1
240129_299 | Various Corp Sites, LED Yellow Lights, Electrical | 2024-04-01 | 2024-09-15 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Various Sites, LED Yellow Lights, Electrical |  | 2400509 |  | TBC | 0 | 2420000 | 2420000 | 1
240129_047 | 270 Republic Road, 4 Chiller compressor replacements, Mechan | 2024-02-28 | 2024-10-15 | Continue | R.PR/1/05 | 21335X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Newly added, requested budget R2,000,000.00 - Part of LCC, | 270 Republic Road, 4 Chiller compressor replacements, Mechanical |  | 2400001 |  | TBC | 0 | 2000000 | 2000000 | 1
240129_419 | Various Sites, National allowance for the use of Ergonomist | 2024-02-15 | 2024-10-30 | Continue | R.PR/3/11 | Various | Marachel Bessenger | RISK | NATIONAL | Supporting Assets | No | TBC | Various Sites, National allowance for the use of Ergonomist furniture and equipment , Fabric, Ergonomist Group OHS |  | 2400512 |  | TBC | 0 | 2000000 | 2000000 | 1
240129_260 | Various Retail Sites, Retail Documentation Compliance Programme (Ph | 2024-02-15 | 2024-06-28 | Continue | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Funding for additional requests for remedial works requested by the municipalities (plumbing, electrical, glazing), | Various Sites, Retail Documentation Compliance Programme (Phase 3) - additional requests for remedial works, BAU Compliance Documentation |  | 2400511 |  | TBC | 0 | 2000000 | 2000000 | 1
240129_359 | Various Retail Sites, Surge Protection, Electrical | 2024-04-01 | 2024-09-15 | Continue | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Various Sites, Surge Protection, Electrical |  | 2400276 |  | TBC | 0 | 2000000 | 2000000 | 1
240129_075 | Various Retail Sites, Retail Documentation Compliance Programme: Fi | 2023-05-11 | 2024-03-30 | Works Approved (2023) | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in progress. Supplier will achieve Practical completion end of Nov 2023. Final completion requires final inspections to take place between ESM's & suppliers. Snags will have to be addressed thereafter. Last invoice dependant on when last site achieves final completion - needs to be before the end of Q2 '24. | Various Sites, Retail Documentation Compliance Programme: Fire remedial works (Phase 3- part 1b), BAU Compliance Documentation | ALP-N00046 |  |  | TBC | 1939755.745 | 0 | 1939755.745 | 1
240129_100 | Absa Rosstax, Absa Rosstax refurbishment, Fabric, Other | 2024-01-15 | 2024-05-30 | Works Approved (2023) | R.PR/3/13 | 76646X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Project | Absa Rosstax, Absa Rosstax refurbishment, Fabric, Other | ALP-GN0015 |  |  | TBC | 1795821.97 | 0 | 1795821.97 | 1
240129_101 | 8 Top Road, Supply and install New Galvanized steel carports | 2023-11-20 | 2024-04-30 | Works Approved (2023) | R.PR/3/05 | 78451X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Project | 8 Top Road, Supply and install New Galvanized steel carports with UV Knittex Shade Netting, Fabric, Other | ALP-GS0076 |  |  | TBC | 1773654.63 | 0 | 1773654.63 | 1
240129_549 | Absa Pretoria Campus, MTR Room A44 & A45, Fabric, Other | 2024-02-05 | 2024-03-25 | Works Approved (2023) | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Rescheduled from 2023, | Absa Pretoria Campus, MTR Room A44 & A45, Fabric, Other |  | 2400095 |  | TBC | 0 | 1724200.93 | 1724200.93 | 1
240129_508 | Various Corp Sites, Building performance improvement initiatives, | 2024-04-15 | 2024-08-30 | Continue | R.PR/1/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | Building performance improvement (EPCs, Green Star), utility cost savings, carbon emission reduction | Various Sites, Building performance improvement initiatives, Energy |  | 2400494 |  | TBC | 0 | 1650000 | 1650000 | 1
240129_431 | Various Retail Sites, Emergency lighting, Electrical | 2024-03-15 | 2024-08-30 | Continue | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | 0 | 15/06/2023: Addition | Various Sites, Emergency lighting, Electrical |  | 2400507 |  | TBC | 0 | 1642666.67 | 1642666.67 | 1
240129_318 | Alice Lane North, Shower rooms and ablutions ( -2, -1) requi | 2024-04-10 | 2024-06-20 | Continue | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project with prayer room, | Alice Lane North, Shower rooms and ablutions ( -2, -1) require a complete upgrade ( tile replacement wall and floor, blind removal, basins, mirrors, taps ( tap system to be converted from battery usage to direct power use) and window vinyl.), Fabric, Other |  | 2400002 |  | TBC | 0 | 1600000 | 1600000 | 1
240129_148 | Absa Worcester, Minor Works (Not Part of CIP), Fabric, Other | 2023-10-23 | 2023-11-20 | Works Complete (2023) | R.PR/3/13 | 78016X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, | Absa Worcester, Minor Works (Not Part of CIP), Fabric, Other | ALP-WC0025 | 0 |  | Complete | 1582320.135 | 0 | 1582320.135 | 1
240129_511 | Absa Towers West, HVAC - Upgrade of the Ricard diffuser MCUs | 2024-05-01 | 2024-06-30 | Works Approved (2023) | R.PR/1/04 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Project Started and Not Completed in 2023, Rollover-Project | Absa Towers West, HVAC - Upgrade of the Ricard diffuser MCUs from analogue to digital - the current MCUs are obsolete, Electrical | ALP-GS0079 | 2400068 |  | TBC | 1580931.21 | 0 | 1580931.21 | 1
240129_152 | Sterkspruit, Minor Works (Not Part of CIP), Fabric, Other | 2023-11-07 | 2023-11-22 | Works Complete (2023) | R.PR/3/13 | 78939X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, | Sterkspruit, Minor Works (Not Part of CIP), Fabric, Other | ALP-EC0016 | 0 |  | Complete | 1519237.8 | 0 | 1519237.8 | 1
240129_372 | 13 Top Road, Shading net replacement & repainting of Struct | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/05 | 79271X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | Yes | Supported, | 13 Top Road , Shading net replacement & repainting of Structures / Installation of carports, Fabric, Other |  | 2400048 |  | TBC | 0 | 1500000 | 1500000 | 1
240129_562 | Springbok, Minor Works, Fabric, Other | 2024-07-09 | 2024-08-05 | Cancel | R.PR/3/13 | 78083X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Springbok, Minor Works, Fabric, Other |  | 2400461 |  | TBC | 0 | 1500000 | 1500000 | 1
240129_300 | Various Corp Sites, Bulk UPS Battery replacements, Electrical | 2023-01-15 | 2023-09-25 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Various Sites, Bulk UPS Battery replacements, Electrical |  | 2400514 |  | TBC | 0 | 1500000 | 1500000 | 1
240129_053 | Trade Route Mall, HVAC Upgrade, Mechanical | 2023-12-13 | 2024-04-30 | Works Approved (2023) | R.PR/2/05 | 77216X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Started and Not Completed in 2023, Rollover-Project | Trade Route Mall, HVAC Upgrade, Mechanical | ALP-GS0082 |  |  | TBC | 1490130.83 | 0 | 1490130.83 | 1
240129_060 | Ridgeside Absa RHO, Expansion joint remedial works, Engineer | 2023-09-17 | 2023-09-18 | Works Complete (2023) | R.PR/1/02 | 22460X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Ridgeside Absa RHO, Expansion joint remedial works, Engineering and Infrastructure | ALP-KZ0007 | 0 |  | Complete | 1488433.46 | 0 | 1488433.46 | 1
240129_201 | Various Retail Sites, Emergency Engineering Request/Fire/life/Safet | 2023-12-01 | 2024-01-31 | Works Approved (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Roll over. Delays experienced with municipality feedback & additional requests coming from various municipalities i.e. glazing Coc's, plumbing Coc's, traffic impact assessments. Planned completion dependent on municipality feedback. | Various Sites, Emergency Engineering Request/Fire/life/Safety, Mechanical | ALP-N00069 |  |  | TBC | 1408997.59 | 0 | 1408997.59 | 1
240131_018 | Absa Boksburg - HVAC Upgrade | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/05 | 76384X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Newly added requested budget R1,357 860 | Absa Boksburg - HVAC Upgrade |  |  |  | TBC | 0 | 1357860 | 1357860 | 1
240129_301 | Various Corp Sites, EOL Programme (LCC Based) - Electrical, Elect | 2024-04-01 | 2024-06-24 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Various Sites, EOL Programme (LCC Based) - Electrical, Electrical |  | 2400510 |  | TBC | 0 | 1320605 | 1320605 | 1
240129_224 | Alternative Power/Battery Wall, Arbour Crossing, Arbour Cros | 2024-02-12 | 2024-02-29 | Works Approved (2023) | R.PR/1/03 | 70634X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction | Alternative Power/Battery Wall, Arbour Crossing, Arbour Crossing Retail Centre battery wall, Energy | ALP-N00057 |  |  | TBC | 1319754.02 | 0 | 1319754.02 | 1
240129_302 | Various Corp Sites, Surge Protection, Electrical | 2024-04-01 | 2024-09-15 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Various Sites, Surge Protection, Electrical |  | 2400277 |  | TBC | 0 | 1300000 | 1300000 | 1
240129_093 | Absa Nquthu, Minor Works - replace ceiling, floor tiles, car | 2024-01-18 | 2024-01-31 | Works Approved (2023) | R.PR/3/13 | 79051X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Nquthu, Minor Works - replace ceiling, floor tiles, carpets and skirting, merchandising, Fabric, Other | ALP-KZ2007 |  |  | TBC | 1288285 | 0 | 1288285 | 1
240129_094 | Absa Stanger, Minor Works - replace ceiling, floor tiles, ca | 2024-01-18 | 2024-01-31 | Works Approved (2023) | R.PR/3/13 | 77928X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Stanger, Minor Works - replace ceiling, floor tiles, carpets and skirting and paint, Fabric, Other | ALP-KZ2008 |  |  | TBC | 1286621 | 0 | 1286621 | 1
240129_533 | Alice Lane North, Chakula Ground Floor patio flooring upgrad | 2024-05-01 | 2024-06-01 | Cancel | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | As per Hanlie Louw email 9-Feb-24, project can be surrendered (Give Back) it is no longer needed | Alice Lane North, Chakula Ground Floor patio flooring upgrade. , Fabric, Other |  | 2400006 |  | TBC | 0 | 1200000 | 1200000 | 1
240129_532 | Alice Lane North, Ground floor main restaurant, serving area | 2024-03-30 | 2024-05-30 | Continue | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Furniture on the deck | Alice Lane North, Ground floor main restaurant, serving area counter (Quartz) including carcass, Fabric, Other |  | 2400004 |  | TBC | 0 | 1200000 | 1200000 | 1
240129_509 | Various Retail Sites, Building performance improvement initiatives, | 2024-04-15 | 2024-08-30 | Continue | R.PR/2/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Building performance improvement (EPCs, Green Star), utility cost savings, carbon emission reduction | Various Sites, Building performance improvement initiatives, Energy |  | 2400496 |  | TBC | 0 | 1200000 | 1200000 | 1
240129_548 | Absa Towers West-Troye St-Johannesburg, Upgrades to restaura | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | As per Hanlie Louw email 9-Feb-24, project to be deferred to 2015 Q1 | Absa Towers West-Troye St-Johannesburg, Upgrades to restaurant cupboards, Fabric, Other |  | 2400021 |  | TBC | 0 | 1182240.28 | 1182240.28 | 1
240129_258 | Alice lane South, Minor Works - Legal & Compliance Fish Bowe | 2023-11-15 | 2023-12-06 | Works Complete (2023) | R.PR/5/12 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane South, Minor Works - Legal & Compliance Fish Bowel, Remediation | ALP-GS0067 | 0 |  | Complete | 1156314.56 | 0 | 1156314.56 | 1
240129_445 | Absa Call Centre Auckland Park, Replace the entire palisade | 2024-05-01 | 2024-06-30 | Continue | R.PR/3/05 | 76849X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | 12% added to budget as requested- was R 1031 250 | Absa Call Centre Auckland Park, Replace the entire palisade fence around the building with concrete walling, Fabric, Other |  | 2400053 |  | TBC | 0 | 1155000 | 1155000 | 1
240129_515 | Absa Virginia, Installation of 165kva generator, Mechanical | 2023-08-25 | 2023-09-05 | Works Complete (2023) | R.PR/2/05 | 79312X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Virginia, Installation of 165kva generator, Mechanical | ASP-CR0354 | 0 |  | Complete | 1153858.21 | 0 | 1153858.21 | 1
240129_578 | Various Corp Sites, allowance for the purchase/installation of white goods | 2024-04-01 | 2024-06-28 | Continue | R.PR/8/06 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | Yes | Microwaved, hydroboils etc. | Various Sites, National allowance for the purchase/installation of white goods |  | 2400516 |  | TBC | 0 | 1150000 | 1150000 | 1
240129_151 | 8 Top Road, Supply and install bird proofing, Fabric, Other | 2023-11-08 | 2024-01-30 | Works Approved (2023) | R.PR/3/05 | 78451X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Project | 8 Top Road, Supply and install bird proofing, Fabric, Other | ALP-GS0075 |  |  | TBC | 1134152.8275 | 0 | 1134152.8275 | 1
240129_063 | Various Sites, Document compliance phase 2b (77 Sites), BAU | 2021-09-30 | 2024-03-30 | Works Complete (2023) | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Project completed - Savings being utilized for additional requests made by various municipalities i.e. glazing Coc's, plumbing Coc's, traffic impact assessments. PO to remain open until completion of compliance programme. | Various Sites, Document compliance phase 2b (77 Sites), BAU Compliance Documentation | ALP-N00022 | 0 |  | Complete | 1128206.999 | 0 | 1128206.999 | 1
240129_033 | Various Retail Sites, Installation of generator bulk tank with a c | 2024-01-26 | 2024-04-30 | Continue | R.PR/2/10 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | RFQ in progress , | Various Sites , Installation of generator bulk tank with a catchment area. 500L, New assets |  | 2400242 |  | TBC | 0 | 1127155 | 1127155 | 1
240129_174 | Highlands Meadowdale, Construction of a Boundary Wall and Cl | 2023-12-01 | 2024-02-29 | Works Approved (2023) | R.PR/3/05 | 37006X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Highlands Meadowdale, Construction of a Boundary Wall and Clearview Fence, Fabric, Other | ALP-GS0068 |  |  | TBC | 1127081 | 0 | 1127081 | 1
240129_210 | Absa Towers North, Chiller 5 &3 Replacement of Electrically | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/05 | 77381X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Started and Not Completed in 2023, Rollover project | Absa Towers North, Chiller 5 &3 Replacement of Electrically Damaged Chiller Components and Surge Arrestor installation for 5 Chillers. (ooc), Mechanical | ALP-GS0083 |  |  | TBC | 1118581.16 | 0 | 1118581.16 | 1
240129_087 | Absa Reitz , Cosmic Upgrade , Fabric, Other | 2023-11-12 | 2023-12-08 | Works Complete (2023) | R.PR/3/13 | 78402X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Reitz , Cosmic Upgrade , Fabric, Other | ALP-CR0029 | 0 |  | Complete | 1108817.11 | 0 | 1108817.11 | 1
240129_514 | Absa Ficksburg, Installation of 80kva generator, Mechanical | 2023-08-14 | 2023-08-31 | Works Complete (2023) | R.PR/2/05 | 70645X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Ficksburg, Installation of 80kva generator, Mechanical | ALP-CR0034 | 0 |  | Complete | 1008119.42 | 0 | 1008119.42 | 1
240129_315 | Absa Pretoria Campus, Block A,VAMM storeroom and vault in tr | 2024-03-01 | 2024-03-31 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Description updated and Budget Required 1M, | Absa Pretoria Campus, Block A,VAMM storeroom and vault in training area, Fabric, Other |  | 2400138 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_287 | Absa Pretoria Campus, supply and Install drainage system to | 2024-01-20 | 2024-05-30 | Continue | R.PR/1/07 | 22491X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | New Add - Phase 1 done in 2023 Budget Requirement 1M, | Absa Pretoria Campus, supply and Install drainage system to mitigate flooding (Phase 2), Water & Systems |  | 2400026 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_002 | Absa Towers West, Glass roof upgrade (Sqm2?) - Support Struc | 2024-04-01 | 2024-05-30 | Continue | R.PR/1/02 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Mholi to share the report with CRES Engineering. R1M in 2023 & R2M in 2024, | Absa Towers West, Glass roof upgrade (Sqm2?) - Support Structure, Engineering and Infrastructure |  | 2400056 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_001 | Alice Lane North, Crack unit replacements, Mechanical | 2024-02-02 | 2024-10-16 | Continue | R.PR/1/05 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Newly added, requested budget R1,000,000.00, | Alice Lane North, Crack unit replacements, Mechanical |  | 2400006 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_534 | Bethlehem, Bethlehem 1 floor to create a open space offices. | 2024-02-22 | 2024-03-20 | Continue | R.PR/3/05 | 22405X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Bethlehem, Bethlehem 1 floor to create a open space offices. Signage for Business Bank, Fabric, Other |  | 2400361 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_050 | Maponya Mall, Install an abs stand-alone HVAC system, LL sy | 2024-01-31 | 2024-03-31 | Continue | R.PR/2/05 | 79059X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Newly added requested budget R1,000,000.00 New Infrastructure by Absa, | Maponya Mall, Install an abs stand-alone HVAC system, LL system is currently malfunctioning , Mechanical |  | 2400027 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_049 | Various Retail Sites, Install UPS systems on site that don't | 2024-01-15 | 2024-12-12 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Newly added requested budget R1,000,000.00, | Various Retail Sites, Install UPS systems on site that don't have UPS, Electrical |  | 2400028 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_521 | Various Corp Sites, REG2, Unplanned | 2024-01-15 | 2024-09-25 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Various Sites (REG2), Headwind Budget - Various - Bulk PO - Eng Prioritised Requests, Electrical | ALP-N00061 | 2400266 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_522 | Various Corp Sites, REG3, ' | 2024-01-15 | 2024-09-25 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Various Sites (REG3), Headwind Budget, Electrical |  | 2400477 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_519 | Various Corp Sites, REG 1, Unplanned | 2024-01-15 | 2024-09-25 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Various, Headwind Budget, Electrical |  | 2400057 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_473 | Various Corp Sites, REG A, Unplanned | 2024-01-15 | 2024-09-25 | Continue | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | TBC | Various, Headwind Budget, Electrical |  | 2400058 |  | TBC | 0 | 1000000 | 1000000 | 1
240129_512 | Absa Towers North, Structural Crack repairs, Mechanical | 2023-11-01 | 2023-11-30 | Works Complete (2023) | R.PR/1/05 | 77381X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers North, Structural Crack repairs, Mechanical | ALP-GS0050 | 0 |  | Complete | 985001.3465 | 0 | 985001.3465 | 1
240129_114 | Absa Scottburg, Replace HVAC Systems, including fresh-air an | 2024-02-05 | 2024-02-16 | Works Approved (2023) | R.PR/2/05 | 77691X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Started and Not Completed in 2023, Project in Execution | Absa Scottburg, Replace HVAC Systems, including fresh-air and extraction, Mechanical | ALP-KZ2004 |  |  | TBC | 968574 | 0 | 968574 | 1
240129_212 | Various Corp Sites, Corporate Solar PV Program (Auckland Park, Ri | 2023-11-30 | 2024-02-29 | Works Approved (2023) | R.PR/1/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction | Various Sites, Corporate Solar PV Program (Auckland Park, Ridgeside, Bridge Park East, and 270 RR), Energy | ALP-N00015 |  |  | TBC | 951889.62 | 0 | 951889.62 | 1
240129_071 | Cogmans Centre Montague, HVAC Replacement (Not Part of CIP), | 2024-02-15 | 2024-03-15 | Works Approved (2023) | R.PR/2/05 | 77744X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Started and Not Completed in 2023, Final OHS approval pending | Cogmans Centre Montague, HVAC Replacement (Not Part of CIP), Mechanical | ALP-WC0021 |  |  | TBC | 951618.35 | 0 | 951618.35 | 1
240129_074 | Various Sites, Phase 1 RBB Documentation Compliance (86 si | 2021-04-29 | 2024-03-30 | Works Complete (2023) | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Project completed - Savings being utilized for additional requests made by various municipalities i.e. glazing Coc's, plumbing Coc's, traffic impact assessments. PO to remain open until completion of compliance programme. | Various Sites, Phase 1 RBB Documentation Compliance (86 sites), BAU Compliance Documentation | ALP-N00009 | 0 |  | Complete | 902146.8555 | 0 | 902146.8555 | 1
240129_179 | 270 Republic Road, Water Tanks Refurbishments, Water & Syste | 2023-11-11 | 2024-01-31 | Works Approved (2023) | R.PR/1/07 | 21335X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | 270 Republic Road, Water Tanks Refurbishments, Water & Systems | ALP-GS0069 |  |  | TBC | 900778.74 | 0 | 900778.74 | 1
240129_059 | Alice Lane South, Installation of New Wooden Deck, Fabric, O | 2023-11-20 | 2024-01-31 | Works Approved (2023) | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice Lane South, Installation of New Wooden Deck, Fabric, Other | ALP-GS0066 |  |  | TBC | 889836.87 | 0 | 889836.87 | 1
240129_085 | Absa Poineer Centre, Upgrade of kitchen area and ablutions | 2024-01-04 | 2024-01-25 | Works Approved (2023) | R.PR/3/13 | 76790X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Poineer Centre , Upgrade of kitchen area and ablutions facilities , Fabric, Other | ALP-LP0201 |  |  | TBC | 887570 | 0 | 887570 | 1
240129_109 | Absa Call Centre Auckland Park, Refurbishment of Halaal kitchen | 2023-02-28 | 2023-12-14 | Works Approved (2023) | R.PR/3/05 | 76849X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Started and Not Completed in 2023, Rollover-Financial | Auckland Park, Refurbishment of Halaal kitchen, Coffee, Fabric, Other | ALP-GS0042 |  |  | TBC | 874175.9385 | 0 | 874175.9385 | 1
240129_214 | Alternative Power/Battery Wall, Dutywa (ALT Pwr), Retail Sol | 2023-08-07 | 2024-02-16 | Works Approved (2023) | R.PR/2/03 | 35033X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Power supply resilience, increase % contribution of renewables, utility cost savings, carbon emission reduction | Alternative Power/Battery Wall, Dutywa (ALT Pwr), Retail Solar PV Program | ALP-N00034 |  |  | TBC | 854629.64 | 0 | 854629.64 | 1
240129_541 | Absa Alexandria, Refurbish kitchen/ablutions, replace floor/ | 2024-08-01 | 2024-09-15 | Defer | R.PR/3/13 | 76600X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed - 2024 due to priority's 2023, | Absa Alexandria, Refurbish kitchen/ablutions, replace floor/carpets tiles teller area. Repaint interior. Ceiling, Fabric, Other | ALP-EC0025 | 2400269 |  | TBC | 0 | 850000 | 850000 | 1
240129_337 | Absa Robertson, Wallpaper needs to be replaced. Floor tiles | 2024-04-15 | 2024-05-30 | Continue | R.PR/3/13 | 77877X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Robertson, Wallpaper needs to be replaced. Floor tiles needs to be replaced., chipped and cracked. , The bathrooms needs to be upgraded. (New floor tiles, new wall tiles, new toilet fittings, new basins and new taps) , Fabric, Other | ASP-WC0341 | 2400270 |  | TBC | 0 | 850000 | 850000 | 1
240129_506 | Bizana Shopping Square, Generator Replacement, Electrical | 2024-06-15 | 2024-07-15 | Continue | R.PR/2/04 | 70633X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Added as per meeting held on 23 June 2023, Possible Generator from Stores as also prioritised to receive Solar/Battery Wall | Bizana Shopping Square, Generator Replacement, Electrical | ALP-EC0030 | 2400520 |  | TBC | 0 | 850000 | 850000 | 1
240129_368 | Kabokweni, Repaint branch to introduce LUX colours; replace | 2024-03-18 | 2024-03-30 | Continue | R.PR/3/13 | 78671X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Retain 100% of funds, pending business case 2024, | Kabokweni, Repaint branch to introduce LUX colours; replace Back of House & BA office carpets; repaint Back of House and all front of house offices walls; replace ablution and kitchen ceramic wall tiles; replace all banking hall tiles including ATM lobby; replace all ceiling tiles in branch; supply new chairs for staff and customers; redo signage (internal and lifestyle graphics to shopfront); register LED with national energy office., Fabric, Other |  | 2400399 |  | TBC | 0 | 850000 | 850000 | 1
240129_505 | The Nautilus Builiding - Jeffreys Bay, Generator Replacement | 2024-06-15 | 2024-07-15 | Continue | R.PR/2/04 | 22196X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Added as per meeting held on 23 June 2023 - Battery Wall or Solar | The Nautilus Builiding - Jeffreys Bay, Generator Replacement, Electrical | ALP-EC0032 | 2400521 |  | TBC | 0 | 850000 | 850000 | 1
240129_153 | Absa Kokstad, Replace HVAC Systems, including fresh-air and | 2024-02-05 | 2024-02-16 | Works Approved (2023) | R.PR/2/05 | 78005X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Started and Not Completed in 2023, Project in Execution | Absa Kokstad , Replace HVAC Systems, including fresh-air and extraction, Mechanical | ALP-KZ2006 |  |  | TBC | 832777 | 0 | 832777 | 1
240129_349 | Absa Kuyasa Shopping Centre - Mdantsane, Ceiling tiles repla | 2024-07-15 | 2024-08-15 | Continue | R.PR/3/13 | 79176X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Retain 100% of funds, pending business case 2024 - 2024 due to priority's 2023, | Absa Kuyasa Shopping Centre - Mdantsane, Ceiling tiles replace entire site - Refresh, Fabric, Other | ALP-EC0023 | 2400271 |  | TBC | 0 | 825000 | 825000 | 1
240129_380 | Montana (Fin Forum), Carpet replacement - entire branch, Fab | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 78655X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | Montana (Fin Forum), Carpet replacement - entire branch, Fabric, Other |  | 2400061 |  | TBC | 0 | 818592 | 818592 | 1
240129_175 | Alice lane North, Supply Operational Equipment, Catering | 2023-12-01 | 2023-12-15 | Works Complete (2023) | R.PR/8/04 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane North, Supply Operational Equipment, Catering | ALP-GS0086 | 0 |  | Complete | 808786.44 | 0 | 808786.44 | 1
240129_513 | Absa Victoria West, Installation of 40kva generator, Mechani | 2023-09-05 | 2023-09-18 | Works Complete (2023) | R.PR/2/05 | 21821X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Victoria West, Installation of 40kva generator, Mechanical | ALP-CR0037 | 0 |  | Complete | 800218.01 | 0 | 800218.01 | 1
240129_329 | Absa Active Park, Newcastle, Full refurb of office area inclu | 2024-04-12 | 2024-04-26 | Continue | R.PR/3/05 | 79379X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Absa Active park,Newcastle, Full refurb of office area including furniture and LED lighting, Fabric, Other |  | 2400339 |  | TBC | 0 | 800000 | 800000 | 1
240129_520 | Absa Towers West, Replace light covers on the hanging pendan | 2024-09-01 | 2024-09-30 | Continue | R.PR/1/04 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | All lights to be replaced, not only cracked covers. Does need to be replaced like for like, new solution needed | Absa Towers West, Replace light covers on the hanging pendant lights at reception and coffee bar on upper ground., Electrical |  | 2400062 |  | TBC | 0 | 800000 | 800000 | 1
240129_319 | Alice Lane South, Countertops - Ground Floor Restaurant Serv | 2024-02-28 | 2024-03-30 | Continue | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Alice Lane South, Countertops - Ground Floor Restaurant Serving Area, Damaged Counter Tops and Cupboards, Fabric, Other |  | 2400011 |  | TBC | 0 | 800000 | 800000 | 1
240129_166 | Moffett Office Park, MTR Room (Not Part of CIP), Fabric, Oth | 2024-02-19 | 2024-02-29 | Works Approved (2023) | R.PR/3/05 | 22937X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Final schedule confirmed | Moffett Office Park, MTR Room (Not Part of CIP), Fabric, Other | ALP-EC0018 |  |  | TBC | 768233.45 | 0 | 768233.45 | 1
240129_542 | Absa Prins Albert, Full Revamp of site fabric - upgrade ablutions, | 2024-07-01 | 2024-08-30 | Under review | R.PR/3/13 | 77111X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed - 2024 due to priority's 2023, | Absa Prins Albert, Full Revamp of site - upgrade ablutions, kitchen, banking hall, offices, back office ( remove wooden cladding), teller area, Atm Room and Lobby - walls, floors. Refurbish wooden ceiling and replace louvre windows. Install hydroboil. Replace furniture, internal signage. Replace blinds. , Fabric, Other | ALP-EC0020 | 2400272 |  | TBC | 0 | 750000 | 750000 | 1
240129_543 | Absa Uniondale, Upgrade ablutions/ kitchen/ teller/banking h | 2024-06-01 | 2024-08-30 | Defer | R.PR/3/13 | 78140X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed - 2024 due to priority's 2023, | Absa Uniondale, Upgrade ablutions/ kitchen/ teller/banking hall/offices/back office area/ ATM room - walls, floor tiles, carpets, ceilings. Windows to be replaced -old metal frames. Replace furniture, moveable , benches. Refurbish exterior. Hydroboil installation. Replace internal signage. Install BCTU and small footprint mantrap door., Fabric, Other | ALP-EC0021 | 2400274 |  | TBC | 0 | 750000 | 750000 | 1
240129_388 | Ermelo, Convert the PA into 2x sales cubicles; relocate sel | 2024-03-15 | 2024-03-23 | Continue | R.PR/3/13 | 77584X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Ermelo, Convert the PA into 2x sales cubicles; relocate self help service desk; Convert Forex Desk into an enclosed office; replace stainless steel banking hall benches with wooden benches; repaint teller areas., Fabric, Other |  | 2400382 |  | TBC | 0 | 750000 | 750000 | 1
240129_369 | Kriel, Upgrade of Teller counters; Painting of branch walls | 2024-08-09 | 2024-08-23 | Continue | R.PR/3/13 | 77028X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Retain 100% of funds, pending business case 2024, | Kriel, Upgrade of Teller counters; Painting of branch walls to introduce lux colours; upgrade to ablution facilities. Installation of LED Lights in entire branch, Fabric, Other |  | 2400405 |  | TBC | 0 | 750000 | 750000 | 1
240129_531 | Absa Bloemfontein Forum, Building storerooms at a parkade, F | 2024-02-24 | 2024-03-06 | Continue | R.PR/3/05 | 22161X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | RFQ in progress , | Absa Bloemfontein Forum, Building storerooms at a parkade, Fabric, Other |  | 2400256 |  | TBC | 0 | 735363.14 | 735363.14 | 1
240129_579 | Various Sites, Catering - OE Smalls Top up provision, Catering | 2023-01-15 | 2023-09-25 | Cancel | R.PR/8/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | R1,4m is total spend, BFM contributes 50%. Move to Opex | Various Sites, Catering - OE Smalls Top up provision, Catering |  | 2400518 |  | TBC | 0 | 728517.43 | 728517.43 | 1
240129_084 | Absa Piet Retief, Refresh building facade- Mosaics- Canopy, | 2023-11-13 | 2023-11-30 | Works Approved (2023) | R.PR/3/05 | 77121X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Piet Retief , Refresh building facade- Mosaics- Canopy, Fabric, Other | ALP-MP0206 |  |  | TBC | 726985 | 0 | 726985 | 1
240129_295 | Absa Upington, Replacement of LED Panels installed in 2017, | 2024-02-22 | 2024-02-26 | Continue | R.PR/2/04 | 36271X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | OOC Request, funding issue , | Absa Upington, Replacement of LED Panels installed in 2017, Electrical |  | 2400251 |  | TBC | 0 | 714208.88 | 714208.88 | 1
240129_544 | Baywest Mall, Minor Works, Fabric, Other | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/13 | 36106X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Late request from EB 10 Jul 23, | Baywest Mall, Minor Works, Fabric, Other | ALP-EC0022 | 240000A |  | TBC | 0 | 700000 | 700000 | 1
240129_062 | Various Sites, Phase 2 Retail document compliance (56 sites) | 2021-08-05 | 2024-03-30 | Works Complete (2023) | D.PR/9/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Project completed - Savings being utilized for additional requests made by various municipalities i.e. glazing Coc's, plumbing Coc's, traffic impact assessments. PO to remain open until completion of compliance programme. | Various Sites, Phase 2 Retail document compliance (56 sites), BAU Compliance Documentation | ALP-N00021 | 0 |  | Complete | 690218.7645 | 0 | 690218.7645 | 1
240129_573 | Absa Pretoria Campus, Block A consolidation of room A11-A12, | 2024-04-01 | 2024-05-30 | Works Approved (2023) | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Absa Pretoria Campus, Block A consolidation of room A11-A12, Fabric, Other |  | 2400066 |  | TBC | 0 | 680000 | 680000 | 1
240129_451 | Absa Call Centre Auckland Park, Replacement of 6 x Hydro taps, Fabric, | 2024-01-20 | 2024-01-30 | Continue | R.PR/3/05 | 76849X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | No | TBC | Absa Auckland Park , Replacement of 6 x Hydro taps, Fabric, Other |  | 2400032 |  | TBC | 0 | 673481.32 | 673481.32 | 1
240129_321 | Absa Pretoria Campus, Replacement external floor tiles, Bloc | 2024-04-01 | 2024-05-30 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Absa Pretoria Campus, Replacement external floor tiles, Block A Pink toilet lobby , Block A smoke exit lobby / Ramp, Block A x3 Emergency exit lobby, Block E external floor tiles including Ramp, Block A Training centre install drainage system and drip trays on 27 External pot plants and re-tile surface., Fabric, Other |  | 2400067 |  | TBC | 0 | 650000 | 650000 | 1
240129_065 | Alice lane North, Critical UPS to Statics, Remediation | 2022-10-10 | 2023-09-20 | Works Complete (2023) | R.PR/5/11 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane North, Critical UPS to Statics, Remediation | ALP-GS0024 | 0 |  | Complete | 625946.278 | 0 | 625946.278 | 1
240129_159 | Absa Carnarvon, Replace HVAC Systems, including fresh-air an | 2024-02-19 | 2023-03-01 | Under review | R.PR/2/05 | 79297X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project Started and Not Completed in 2023, Project in Execution | Absa Carnarvon, Replace HVAC Systems, including fresh-air and extraction, Mechanical | ALP-CR0038 |  |  | TBC | 600657 | 0 | 600657 | 1
240129_332 | Absa Ridgeside, Installation of new blinds (automated) at th | 2024-03-15 | 2024-03-20 | Continue | R.PR/3/05 | 22460X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | 15/06/2023- Budget increased from R450k to R600K, Look into adjustable louvers Consider reupholstery for main reception furniture | Absa Ridgeside, Installation of new blinds (automated) at the reception / look into making louvers moveable. Replacement of the deck chairs and tables Purchase of the new furniture for main and client suit reception Combining client suits 7 and 8 to accommodate 30 People, Fabric, Other |  | 2400351 |  | TBC | 0 | 600000 | 600000 | 1
240129_574 | Absa Towers West, Replace/upgrade all pause area cupboards | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | Yes | TBC | Absa Towers West, Replace/upgrade all pause area cupboards phased approached, Fabric, Other |  | 2400071 |  | TBC | 0 | 600000 | 600000 | 1
240129_308 | Absa Uniondale, Electrical Infrastructure Degrading, Electri | 2024-06-01 | 2024-08-30 | Continue | R.PR/2/04 | 78140X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | TBC | Absa Uniondale, Electrical Infrastructure Degrading, Electrical | ALP-EC0031 | 2400278 |  | TBC | 0 | 600000 | 600000 | 1
240129_528 | Alice Lane South, Reception counter, cupboard and waiting ar | 2024-05-01 | 2024-06-01 | Cancel | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | East Wing is exclusive to Absa - description updated. As per email from Hanlie Louw 9-Feb-24 this is no longer required this can be Surrender – (Give Back) (Not needed) | Alice Lane South, Reception counter, cupboard and waiting area , Fabric, Other |  | 2400013 |  | TBC | 0 | 600000 | 600000 | 1
240129_563 | Greytown, Internal Refurbishment, Fabric, Other | 2024-04-11 | 2024-04-22 | Cancel | R.PR/3/13 | 76978X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Greytown, Internal Refurbishment, Fabric, Other |  | 2400390 |  | TBC | 0 | 600000 | 600000 | 1
240129_389 | Ladybrand (17A Joubert Street ), Minor Works Upgrade: Need t | 2024-03-04 | 2024-03-30 | Continue | R.PR/3/13 | 78841X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Ladybrand (17A Joubert Street ), Minor Works Upgrade: Need to upgrade the branch to the new Corporate Identity, new floor tiles, painting signage and floor carpets and external signage. OHS finding, as per SRA finding: Emergency door , Fabric, Other |  | 2400334 |  | TBC | 0 | 600000 | 600000 | 1
240129_086 | Absa Volksrust, Revamp ablutions - Replace floor and wall ti | 2023-11-25 | 2023-11-30 | Works Complete (2023) | R.PR/3/13 | 77566X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Volksrust, Revamp ablutions - Replace floor and wall tiles - Toilet Extraction , Fabric, Other | ALP-MP0207 | 0 |  | Complete | 569351.03 | 0 | 569351.03 | 1
240129_170 | Various Sites, Various- Energy Performance certificate, Ener | 2022-02-22 | 2024-01-31 | Works Complete (2023) | R.PR/1/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, Various- Energy Performance certificate, Energy | ALP-N00025 | 0 |  | Complete | 567029.2005 | 0 | 567029.2005 | 1
240129_444 | Absa Pretoria Campus, Upgrade/Refurb- Replace Hydro taps x | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | Yes | 100k allocated in 23 in case of emergency otherwise 24 | Absa Pretoria Campus , Upgrade/Refurb- Replace Hydro taps x 4 Units, Fabric, Other |  | 2400064 |  | TBC | 0 | 550000 | 550000 | 1
240129_370 | Mtubatuba, Replacement of floor finishes and ceiling tiles, | 2024-05-02 | 2024-05-12 | Continue | R.PR/3/13 | 77548X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Retain 100% of funds, pending business case 2024, | Mtubatuba, Replacement of floor finishes and ceiling tiles, upgrade of Ablutions and kitchen, painted of colours., Fabric, Other |  | 2400430 |  | TBC | 0 | 550000 | 550000 | 1
240129_036 | Birch Acres Mall, HVAC replacement entire branch + ATM, Mech | 2024-06-01 | 2024-06-30 | Continue | R.PR/2/05 | 21330X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Supported, | Birch Acres Mall, HVAC replacement entire branch + ATM, Mechanical |  | 2400072 |  | TBC | 0 | 540000 | 540000 | 1
240129_037 | Bracken City Shopping Centre, HVAC Replacement, Mechanical | 2024-06-01 | 2024-06-30 | Continue | R.PR/2/05 | 77203X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Supported, | Bracken City Shopping Centre, HVAC Replacement, Mechanical |  | 2400073 |  | TBC | 0 | 529200 | 529200 | 1
240129_373 | 8 Top Road, Carpet replacement through out building and new | 2024-03-01 | 2024-04-30 | Continue | R.PR/3/05 | 78451X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Supported, | 8 Top Road, Carpet replacement through out building and new carpet installation in office space where there is currently tiles and cement flooring, Fabric, Other |  | 2400076 |  | TBC | 0 | 500000 | 500000 | 1
240129_472 | Absa Call Centre Auckland Park, BMS HVAC Controllers upgrade | 2024-03-01 | 2024-03-30 | Continue | R.PR/1/09 | 76849X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | TBC | Absa Call Centre Auckland Park, BMS HVAC Controllers upgrade, BMS and EMS Systems |  | 2400078 |  | TBC | 0 | 500000 | 500000 | 1
240129_298 | Absa Pretoria Campus, UPS Battery Replacement, Electrical | 2024-04-01 | 2024-05-30 | Continue | R.PR/1/04 | 22491X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Absa Pretoria Campus , UPS Battery Replacement, Electrical |  | 2400050 |  | TBC | 0 | 500000 | 500000 | 1
240129_317 | Alice Lane North, Complete upgrade for Basement 3 cleaning a | 2024-02-01 | 2024-02-28 | Continue | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project, | Alice Lane North, Complete upgrade for Basement 3 cleaning and catering change rooms and we do not have gender assigned change room facilities that provide showers proper lockers and ablutions and hygiene equipment, Fabric, Other |  | 2400014 |  | TBC | 0 | 500000 | 500000 | 1
240129_565 | Hennenman, Upgrade the kitchen and toilet area, Fabric, Othe | 2024-04-12 | 2024-04-26 | Under review | R.PR/3/13 | 78855X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Hennenman, Upgrade the kitchen and toilet area, Fabric, Other |  | 2400394 |  | TBC | 0 | 500000 | 500000 | 1
240129_564 | Mega City, Replace carpets in BOH, Treasury ,tellers and cus | 2024-03-04 | 2024-03-08 | Under review | R.PR/3/13 | 77784X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Mega City, Replace carpets in BOH, Treasury ,tellers and customer services area(Secure area), Fabric, Other |  | 2400418 |  | TBC | 0 | 500000 | 500000 | 1
240129_180 | Various Sites, Various- Replacement of UPS batteries 2, Elec | 2022-05-19 | 2024-01-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, Various- Replacement of UPS batteries 2, Electrical | ALP-N00051 | 0 |  | Complete | 494445.3405 | 0 | 494445.3405 | 1
240129_079 | Absa Bell Street, External refurbishment - Painting of build | 2023-10-03 | 2023-10-15 | Works Complete (2023) | R.PR/3/05 | 76978X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Bell Street, External refurbishment - Painting of building & Waterproofing, Fabric, Other | ASP-KZ0227 | 0 |  | Complete | 488433.4625 | 0 | 488433.4625 | 1
240129_244 | Alice Lane North , Equinox BMS, BMS and EMS Systems | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/09 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane North , Equinox BMS, BMS and EMS Systems | ASP-GS0582 |  |  | Complete | 488125.3315 | 0 | 488125.3315 | 1
240129_338 | Absa Caledon, Replace carpet tiles, Repaint branch, Fabric, | 2024-04-15 | 2024-05-15 | Continue | R.PR/3/13 | 77399X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Caledon, Replace carpet tiles, Repaint branch, Fabric, Other | ASP-WC0345 | 2400281 |  | TBC | 0 | 485000 | 485000 | 1
240129_322 | Absa Pretoria Campus, Block C refurbishment x8 water damaged | 2024-04-01 | 2024-05-30 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Absa Pretoria Campus, Block C refurbishment x8 water damaged pause area cabinets including recycle station cabinet doors, Fabric, Other |  | 2400082 |  | TBC | 0 | 485000 | 485000 | 1
240129_195 | Various Corp Sites, Bulk Various Sites, Electrical | 2023-11-01 | 2024-01-31 | Works Approved (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Started and Not Completed in 2023, Project in progress | Various Sites, Bulk Various Sites, Electrical | ALP-N00043 |  |  | TBC | 484971.53 | 0 | 484971.53 | 1
240129_088 | Absa Pretoria Campus, Chiller Plants X5 Condenser Fans and X | 2023-11-10 | 2024-01-30 | Works Approved (2023) | R.PR/1/05 | 22491X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Started and Not Completed in 2023, Rollover-Project | Absa Pretoria Campus, Chiller Plants X5 Condenser Fans and X1 Heat Exchanger replacement, Mechanical | ASP-GN0227 |  |  | TBC | 480991.18 | 0 | 480991.18 | 1
240129_339 | Airport Shopping Centre - Belhar, Replace old spec ceiling t | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/13 | 78324X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Airport Shopping Centre - Belhar, Replace old spec ceiling tiles, Replace old spec floor tiles, Replace the office Blinds, Fabric, Other | ASP-WC0348 | 2400282 |  | TBC | 0 | 475000 | 475000 | 1
240129_186 | Auckland Park, Safety net installation, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Safety net installation, Fabric, Other | ASP-GS0513 |  |  | Complete | 473524 | 0 | 473524 | 1
240129_360 | Sanridge Square, Shopping Centre, HVAC replacement entire bra | 2024-05-01 | 2024-06-30 | Continue | R.PR/2/05 | 21861X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | TBC | Sanridge Square Shopping Centre, HVAC replacement entire branch , Mechanical |  | 2400083 |  | TBC | 0 | 468000 | 468000 | 1
240129_316 | Absa Call Centre Auckland Park, Replacement - all Barclays b | 2024-06-01 | 2024-07-31 | Continue | R.PR/3/05 | 76849X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Initiatives that was part of the a 3 year Plan and budgets provisioned for in CIP 2024, | Absa Call Centre Auckland Park, Replacement - all Barclays blue desk panels, Fabric, Other |  | 2400084 |  | TBC | 0 | 450000 | 450000 | 1
240129_011 | Absa Pretoria Campus, Walk off Mats, Fabric, Other | 2024-01-20 | 2024-02-15 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Newly added budget required 450K, | Absa Pretoria Campus, Walk off Mats, Fabric, Other |  | 2400044 |  | TBC | 0 | 450000 | 450000 | 1
240129_325 | Bloemfontein Forum, Build a close office with desk dividers | 2024-01-05 | 2024-03-06 | Continue | R.PR/3/05 | 22161X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Bloemfontein Forum, Build a close office with desk dividers for sales Hub on the 1st floor for 10 staff, Fabric, Other |  | 2400364 |  | TBC | 0 | 450000 | 450000 | 1
240129_566 | Carolina, Replace Carpets on first floor to new CI; paint wa | 2024-04-20 | 2024-04-28 | Under review | R.PR/3/13 | 78145X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Carolina, Replace Carpets on first floor to new CI; paint walls to new CI colours; replace all ceiling boards in branch; revamp all ablutions., Fabric, Other |  | 2400375 |  | TBC | 0 | 450000 | 450000 | 1
240129_411 | Mmabatho Crossings (Mafikeng), Repaint branch and replace fr | 2024-03-11 | 2024-03-21 | Continue | R.PR/3/13 | 22197X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Mmabatho Crossings (Mafikeng), Repaint branch and replace front offices glass frosting, Fabric, Other |  | 2400414 |  | TBC | 0 | 450000 | 450000 | 1
240131_017 | Manufacturing, Supply and Installation of LED Lighting at 3A | 2023-08-07 | 2023-12-15 | Works Complete (2023) | R.PR/1/03 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Project Completed and not invoiced in 2023, POC In progress | Manufacturing, Supply and Installation of LED Lighting at 3Absa Corporate Sites | ALP-N00041 |  |  | Complete | 447166.41 | 0 | 447166.41 | 1
240129_076 | Absa Danie Joubert Tzaneen , HVAC Modifications at the 1st f | 2023-11-05 | 2023-11-28 | Works Approved (2023) | R.PR/2/05 | 76808X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Danie Joubert Tzaneen , HVAC Modifications at the 1st floor Samsung VRV system, Mechanical | ASP-LP0166 |  |  | TBC | 447055.69 | 0 | 447055.69 | 1
240129_090 | Absa Bluff Hillside, Installation of LED lights, Energy | 2023-11-01 | 2023-11-13 | Works Complete (2023) | R.PR/2/03 | 77346X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Bluff Hillside, Installation of LED lights, Energy | ASP-KZ0259 | 0 |  | Complete | 441690.16 | 0 | 441690.16 | 1
240131_005 | Quo Vadis Centre, Westonaria Ceiling til | 2023-03-09 | 2023-09-15 | Works Complete (2023) | R.PR/3/13 | 70289X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Quo Vadis Centre, Westonaria Ceiling til | ASP-GS0607 |  |  | Complete | 438003.812 | 0 | 438003.812 | 1
240129_340 | Absa Patensie, Upgrade kitchen/ablutions/replace tiles/carpe | 2024-05-20 | 2024-06-20 | Continue | R.PR/3/13 | 77876X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Patensie, Upgrade kitchen/ablutions/replace tiles/carpets back office/ Banking hall tiles/refurbish teller area/moveable , new furniture, refurbish ATM lobby/room. Assess structural fault in branch and new mantrap door., Fabric, Other | ASP-EC0384 | 2400284 |  | TBC | 0 | 425000 | 425000 | 1
240129_163 | Absa Towers West, Relocate Multifaith room, Fabric, Other | 2023-12-03 | 2024-01-31 | Works Complete (2023) | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Financial | Absa Towers West, Relocate Multifaith room, Fabric, Other | ASP-GS0749 |  |  | Complete | 407616.3385 | 0 | 407616.3385 | 1
240129_561 | Trade Route Mall, Floor tiles, spray ceiling- replace carpet | 2024-03-01 | 2024-04-30 | Under review | R.PR/3/13 | 77216X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comment - Description updated by Region , | Trade Route Mall, Floor tiles, spray ceiling- replace carpets ( Outside branch operating hours), Fabric, Other |  | 2400085 |  | TBC | 0 | 406770 | 406770 | 1
240129_080 | Alice Lane South, Upgrade of the 3rd floor Client Suite Kitc | 2023-11-15 | 2024-01-17 | Works Approved (2023) | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice lane South, Upgrade of the 3rd floor Client Suite Kitchen., Fabric, Other | ASP-GS0714 |  |  | TBC | 405949.747 | 0 | 405949.747 | 1
240129_043 | Absa Pretoria Campus, supply and Install flammable storage r | 2024-02-01 | 2024-04-30 | Continue | R.PR/1/06 | 22491X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | New Add - Phase 1 done in 2023 Budget Requirement 400K, | Absa Pretoria Campus, supply and Install flammable storage room (Phase 2), Fire |  | 2400046 |  | TBC | 0 | 400000 | 400000 | 1
240129_413 | Metash building Pongola, Replacement of carpets and applicat | 2024-03-01 | 2024-03-10 | Continue | R.PR/3/13 | 21868X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Metash building Pongola, Replacement of carpets and application of new brave colours on walls, removal of queue rails from banking hall, Fabric, Other |  | 2400422 |  | TBC | 0 | 400000 | 400000 | 1
240129_412 | Welkom, Replace carpets, paint of walls, replace ceiling til | 2024-09-09 | 2024-09-23 | Continue | R.PR/3/13 | 78607X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Welkom, Replace carpets, paint of walls, replace ceiling tiles for the entire branch, Fabric, Other |  | 2400483 |  | TBC | 0 | 400000 | 400000 | 1
240129_172 | Absa Gilloolys View, Boardroom Expansion, Fabric, Other | 2024-02-16 | 2024-03-31 | Continue | R.PR/3/05 | 37140X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover project | Absa Gilloolys View, Boardroom Expansion, Fabric, Other | ASP-GS0771 |  |  | TBC | 394544.02 | 0 | 394544.02 | 1
240129_387 | Southgate Mall, Kitchen unit is damaged requires replacement | 2024-08-01 | 2024-08-30 | Continue | R.PR/3/13 | 77326X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comment - Description updated by Region, | Southgate Mall, Kitchen unit is damaged requires replacement and floor tiles, close vacant cubicles and make online banking private (Outside branch operating hours), Fabric, Other |  | 2400091 |  | TBC | 0 | 391302.74 | 391302.74 | 1
240129_304 | Absa Call Centre Auckland Park, Connect FCU Controllers To B | 2024-07-01 | 2024-07-30 | Continue | R.PR/1/05 | 76849X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Absa Call Centre Auckland Park, Connect FCU Controllers To BMS, Mechanical |  | 2400092 |  | TBC | 0 | 380000 | 380000 | 1
240129_072 | Walmer Park Shopping Centre, Generator Rust Repairs (Part of | 2023-10-22 | 2023-11-23 | Works Complete (2023) | R.PR/2/04 | 77686X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023 | Walmer Park Shopping Centre, Generator Rust Repairs (Part of CIP 2023), Electrical | ASP-EC0282 | 0 |  | Complete | 376684.69 | 0 | 376684.69 | 1
240129_091 | Moffett Office Park, MOP, Replace 2 X chiller condensing coi | 2024-02-15 | 2024-02-20 | Works Approved (2023) | R.PR/1/05 | 22937X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Reduced as approved for 2024 was R875K, No Objection to Adjust Meeting 24 Nov, | Moffett Office Park, MOP, Replace 2 X chiller condensing coils for chiller 1 and chiller 2 due to their deteriorating condition , Mechanical | ASP-EC0361 | 2400268 |  | TBC | 0 | 376630.67 | 376630.67 | 1
240129_348 | Garden Route Centre - Knysna, Repaint interior of site Brave | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 77262X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed - Was R650K, soft seating to be ordered 2023., | Garden Route Centre - Knysna, Repaint interior of site Brave colours. Replace venetian blind in banking hall. Internet Kiosk installation new spec. . , Fabric, Other | ASP-EC0388 | 2400285 |  | TBC | 0 | 375000 | 375000 | 1
240129_386 | Maponya Mall, Tube system from ATM to Treasury (Outside bran | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 79059X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comment - Description and CIP name changed by region, | Maponya Mall, Tube system from ATM to Treasury (Outside branch operating hours), Fabric, Other |  | 2400093 |  | TBC | 0 | 366704 | 366704 | 1
240129_132 | Absa Southgate, Absa Southgate New Tube system, Fabric, Othe | 2023-08-03 | 2023-09-15 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Southgate, Absa Southgate New Tube system, Fabric, Other | ASP-GS0698 | 0 |  | Complete | 364629.9595 | 0 | 364629.9595 | 1
240129_581 | Bridge Park, Kitchen Vinyl, Fabric, Other | 2024-10-01 | 2024-10-30 | Cancel | R.PR/3/05 | 36225X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Addition 16 Nov Meeting - Based on previously obtained Cost to be confirmed, No Objection Meeting 24 Nov. As per Hanlie Louw email 9-Feb-24, project can be surrendered (Give Back) it is no longer needed | Bridge Park, Kitchen Vinyl, Fabric, Other | ASP-WC0354 | 2400112 |  | TBC | 0 | 360000 | 360000 | 1
240129_104 | Absa Pretoria Campus , Restuarant refurbishment, Fabric, Oth | 2023-09-23 | 2023-10-30 | Works Complete (2023) | R.PR/3/05 | 22491X & 35038X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Restuarant refurbishment, Fabric, Other | ALP-GN0013 | 0 |  | Complete | 354402.561 | 0 | 354402.561 | 1
240129_341 | Absa Somerset East, Replace ATM lobby/room floor tiles & rep | 2024-05-15 | 2024-06-30 | Continue | R.PR/3/13 | 76426X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Somerset East, Replace ATM lobby/room floor tiles & repaint. + ATM Meta Wall, Fabric, Other | ASP-EC0385 | 2400286 |  | TBC | 0 | 350000 | 350000 | 1
240129_342 | Absa Willowmore, Upgrade ablutions/ kitchen/ teller/banking | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/13 | 77596X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Willowmore, Upgrade ablutions/ kitchen/ teller/banking hall replace carpets with floor tiles, and moveable q rail. Replace furniture, benches. Replace internal signage. , Fabric, Other | ASP-EC0386 | 2400287 |  | TBC | 0 | 350000 | 350000 | 1
240129_529 | Alice Lane North, Coffee Bar, restaurant and patio tables, c | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project, if part of the refresh , | Alice Lane North, Coffee Bar, restaurant and patio tables, chairs and umbrellas upgrade., Fabric, Other | 0 | 2400015 |  | TBC | 0 | 350000 | 350000 | 1
240129_555 | Blouberg(Senwabarwana), Replace all Ceramic Tiles in banking | 2024-03-08 | 2024-03-15 | Under review | R.PR/3/13 | 22539X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | Blouberg(Senwabarwana), Replace all Ceramic Tiles in banking hall with new CI tiles. (Tentative until we see what TCR Remediation project will cover)., Fabric, Other |  | 2400365 |  | TBC | 0 | 350000 | 350000 | 1
240129_567 | Pavillion, Upgrade of Ablutions replace floor tiles and Carp | 2024-04-19 | 2024-04-29 | Under review | R.PR/3/13 | 77543X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Pavillion, Upgrade of Ablutions replace floor tiles and Carpets- paint to new colours, Fabric, Other |  | 2400438 |  | TBC | 0 | 350000 | 350000 | 1
240129_414 | Schoemansdal (Matsamo Plaza), Provide additional bathroom - | 2024-05-11 | 2024-05-21 | Continue | R.PR/3/13 | 77316X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Schoemansdal (Matsamo Plaza), Provide additional bathroom - there is only Single bathroom for 10 staff members; Replace old sales consultants desk with new spec to optimize space; Same for Customer services; and pause area to be reconfigured to accommodate new toilet facilities., Fabric, Other |  | 2400417 |  | TBC | 0 | 350000 | 350000 | 1
240129_046 | Trade Route Mall, Install BMS System and interface the equip | 2024-01-20 | 2024-06-30 | Continue | R.PR/1/05 | 77216X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Newly added requested budget R350 000.00, | Trade Route Mall, Install BMS System and interface the equipment together with the newly installed HVAC system, Mechanical |  | 2400050 |  | TBC | 0 | 350000 | 350000 | 1
240129_361 | Laudium Square, HVAC replacement, Mechanical | 2024-04-01 | 2024-05-20 | Continue | R.PR/2/05 | 21714X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | TBC | Laudium Square, HVAC replacement, Mechanical |  | 2400094 |  | TBC | 0 | 342000 | 342000 | 1
240129_158 | Alice lane North, Replacement of 2nd Floor Blinds - new blin | 2023-12-13 | 2024-02-29 | Works Approved (2023) | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice lane North, Replacement of 2nd Floor Blinds - new blinds, Fabric, Other | ASP-GS0761 |  |  | TBC | 341036.5365 | 0 | 341036.5365 | 1
240129_083 | Absa Kleksdorp , Minor works, Fabric, Other | 2023-11-05 | 2023-11-20 | Works Complete (2023) | R.PR/3/13 | 77176X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Kleksdorp , Minor works, Fabric, Other | ASP-CR0488 | 0 |  | Complete | 335642.74 | 0 | 335642.74 | 1
240131_007 | Towers North Replacement of Chiller 2 C | 2023-06-19 | 2023-09-15 | Works Complete (2023) | R.PR/1/05 | 77381X | Conrad Mills | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Towers North Replacement of Chiller 2 C | ASP-GS0678 |  |  | Complete | 331206.11 | 0 | 331206.11 | 1
240129_131 | Absa Clearwater, Clearwater Re-upholster couches x 11 (Cl, F | 2023-08-03 | 2023-09-15 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Clearwater, Clearwater Re-upholster couches x 11 (Cl, Fabric, Other | ASP-GS0667 | 0 |  | Complete | 313698.15 | 0 | 313698.15 | 1
240129_560 | River Square, Floor tiles and carpets replacement, Fabric, O | 2024-09-01 | 2024-09-30 | Under review | R.PR/3/13 | 77812X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comment, | River Square, Floor tiles and carpets replacement, Fabric, Other |  | 2400099 |  | TBC | 0 | 302323.24 | 302323.24 | 1
240129_557 | Absa Fochville, Replacement of floor tiles and poster frames | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 77647X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana - Description updated by Region, | Absa Fochville, Replacement of floor tiles and poster frames - external building painting (outside branch operating hours), Fabric, Other |  | 2400100 |  | TBC | 0 | 301300 | 301300 | 1
240129_420 | Absa Towers West, Upgrade of the Hydro taps (x3) at ATW paus | 2024-03-01 | 2024-03-30 | Continue | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | Yes | TBC | Absa Towers West, Upgrade of the Hydro taps (x3) at ATW pause areas (Old parts that are expensive to maintain), Fabric, Other |  | 2400102 |  | TBC | 0 | 300000 | 300000 | 1
240129_430 | Alice Lane North, Corp Plugs for meetings rooms, Electrical | 2024-10-20 | 2024-11-20 | Continue | R.PR/1/04 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | 13/06/2023 As per meeting held this item was removed Workspace redesign | Alice Lane North, Corp Plugs for meetings rooms, Electrical |  | 2400016 |  | TBC | 0 | 300000 | 300000 | 1
240129_320 | Alice Lane North, Prayer rooms revamp (x2) ( new shower faci | 2024-10-01 | 2024-10-15 | Continue | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Alice Lane North, Prayer rooms revamp (x2) ( new shower facilities, cabinets, walls to be painted), Fabric, Other |  | 2400018 |  | TBC | 0 | 300000 | 300000 | 1
240129_569 | Durban North (18 Swapo Road), Replacement of ceiling tiles a | 2024-03-14 | 2024-03-20 | Under review | R.PR/3/13 | 77409X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Durban North (18 Swapo Road), Replacement of ceiling tiles and floor tiles on stairway, Fabric, Other |  | 2400338 |  | TBC | 0 | 300000 | 300000 | 1
240129_568 | Groblersdal Mall, Paint to all walls and doors in branch int | 2024-05-17 | 2024-05-23 | Under review | R.PR/3/13 | 36251X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Groblersdal Mall, Paint to all walls and doors in branch introducing lux colours; replace carpets to front of house and back office including cash areas, Fabric, Other |  | 2400391 |  | TBC | 0 | 300000 | 300000 | 1
240129_371 | Mega City, Modifications on the existing HVAC , Mechanical | 2024-03-25 | 2024-04-29 | Continue | R.PR/2/05 | 77784X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Mega City, Modifications on the existing HVAC , Mechanical |  | 2400419 |  | TBC | 0 | 300000 | 300000 | 1
240131_001 | Various Sites, National- Reistallation of the BOCC syst, Electrical (240131_001) | 2022-02-02 | 2024-01-31 | Works Complete (2023) | R.PR/2/02 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress. | Various Sites, National- Reistallation of the BOCC syst, Electrical | ALP-N00019 | 0 |  | Complete | 288488.3905 | 0 | 288488.3905 | 1
240129_390 | Janefurse, Replace all Carpet to front of house and back off | 2024-05-11 | 2024-05-15 | Continue | R.PR/3/13 | 76783X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Janefurse, Replace all Carpet to front of house and back office including cash areas; Repaint doors and walls in branch introducing lux colours, Fabric, Other |  | 2400398 |  | TBC | 0 | 285000 | 285000 | 1
240129_073 | Absa Paulpietersburg, External Refurbishment, Fabric, Other | 2023-10-03 | 2023-10-13 | Works Complete (2023) | R.PR/3/05 | 77511X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Paulpietersburg, External Refurbishment, Fabric, Other | ASP-KZ0226 | 0 |  | Complete | 279805.9 | 0 | 279805.9 | 1
240129_173 | Clearwater Office Park , Clearwater O/P hotdesking area, Fab | 2024-02-23 | 2024-03-31 | Continue | R.PR/3/05 | 77174X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover project | Clearwater Office Park , Clearwater O/P hotdesking area, Fabric, Other | ASP-GS0738 |  |  | TBC | 278484.76 | 0 | 278484.76 | 1
240129_139 | Sanridge Square, Sanridge Square Ceiling replacement and, Fa | 2023-08-23 | 2023-09-24 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Sanridge Square, Sanridge Square Ceiling replacement and, Fabric, Other | ASP-GN0219 | 0 |  | Complete | 278231.23 | 0 | 278231.23 | 1
240129_343 | 49 Main Road Gansbaai, Replace old spec floor tiles, Fabric, | 2024-05-01 | 2024-05-15 | Continue | R.PR/3/13 | 77700X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | 49 Main Road Gansbaai, Replace old spec floor tiles, Fabric, Other | ASP-WC0349 | 2400292 |  | TBC | 0 | 275000 | 275000 | 1
240129_402 | Roxys Village Walk (Bronkhorstspruit), Carpet replacement. | 2024-03-01 | 2024-03-31 | Continue | R.PR/3/13 | 78456X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Roxys Village Walk (Bronkhorstspruit), Carpet replacement. Bumper rail and repainting, Fabric, Other |  | 2400103 |  | TBC | 0 | 273808 | 273808 | 1
240129_259 | Alice lane North, CRAC Units DD Report , Mechanical | 2023-10-01 | 2023-10-16 | Works Complete (2023) | R.PR/1/05 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane North, CRAC Units DD Report , Mechanical | ASP-GS0720 | 0 |  | Complete | 263952.209 | 0 | 263952.209 | 1
240129_196 | Alice lane North, Installation of Induction Jet UV Light, El | 2023-10-10 | 2023-10-20 | Works Complete (2023) | R.PR/1/04 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane North, Installation of Induction Jet UV Light, Electrical | ASP-GS0676 | 0 |  | Complete | 260793.33 | 0 | 260793.33 | 1
240129_540 | Absa Malmesbury, Replace Carpet on 1st Floor, Fabric, Other | 2024-05-20 | 2024-06-20 | Under review | R.PR/3/13 | 78113X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Malmesbury, Replace Carpet on 1st Floor, Fabric, Other | ASP-WC0346 | 2400293 |  | TBC | 0 | 260000 | 260000 | 1
240129_277 | Absa Pretoria Campus , DD & Consulting Stormwater, Water & | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/07 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , DD & Consulting Stormwater, Water & Systems | ASP-GN0226 |  |  | Complete | 257036.5 | 0 | 257036.5 | 1
240129_150 | Absa Inkandla (Ithala), Replace floor tiles, Fabric, Other | 2023-11-27 | 2023-12-08 | Works Complete (2023) | R.PR/3/13 | 77968X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Inkandla (Ithala), Replace floor tiles, Fabric, Other | ASP-KZ0222 |  |  | Complete | 253892.2275 | 0 | 253892.2275 | 1
240129_344 | Absa Despatch, Replace chairs, ATM room makeover. Pave gener | 2024-06-01 | 2024-06-30 | Continue | R.PR/3/13 | 76549X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Despatch, Replace chairs, ATM room makeover. Pave generator area., Fabric, Other | ASP-EC0382 | 2400295 |  | TBC | 0 | 250000 | 250000 | 1
240129_045 | Absa Call Centre Auckland Park, upgrade of the parkade Satt system | 2024-02-01 | 2024-06-30 | Continue | R.PR/1/05 | 76849X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Newly added requested budget R250,000.00, | Auckland Park, upgrade of the parkade Satt system on the roof to the weather proofed sensors, Mechanical |  | 2400056 |  | TBC | 0 | 250000 | 250000 | 1
240129_558 | Bloem CBD, Replace Greenwave BMS with current BMS, BMS and E | 2024-02-08 | 2024-02-08 | Continue | R.PR/2/09 | 78754X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | Yes | System is not repairable and obsolete. Confirmed by Greenwave, the Schneider OEM., | Bloem CBD, Replace Greenwave BMS with current BMS, BMS and EMS Systems |  | 2400362 |  | TBC | 0 | 250000 | 250000 | 1
240129_326 | Carnarvon, Replace external louvers, Fabric, Other | 2024-03-19 | 2024-03-23 | Continue | R.PR/3/05 | 79297X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Carnarvon, Replace external louvers, Fabric, Other |  | 2400374 |  | TBC | 0 | 250000 | 250000 | 1
240129_336 | Carolina, Painting of plastered sections to the external bui | 2024-04-20 | 2024-04-28 | Continue | R.PR/3/05 | 78145X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Ilana Comment - Move to Corporate? (same outlet as initiative 2400375), | Carolina, Painting of plastered sections to the external building facades; painting and remediation of rain water goods; replacement of ATM lobby floor tiles to match with entrance lobby tiles; painting of carports and backyard palisade fence. Installation of LED Lights in entire branch (Recent TMR installed only 3 LED lights in Teller area), Fabric, Other |  | 2400376 |  | TBC | 0 | 250000 | 250000 | 1
240129_550 | Eshowe, Replace carpets, Upgrade of Ablutions and kitchen, F | 2024-05-15 | 2024-05-20 | Under review | R.PR/3/13 | 77861X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Retain 100% of funds, pending business case 2024, | Eshowe, Replace carpets, Upgrade of Ablutions and kitchen, Fabric, Other |  | 2400384 |  | TBC | 0 | 250000 | 250000 | 1
240129_391 | Mkhuhlu, Extend the BA’s office to include a cleaning storag | 2024-06-08 | 2024-06-11 | Continue | R.PR/3/13 | 77974X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Mkhuhlu, Extend the BA’s office to include a cleaning storage cabinet and increase space in the back office; replace Kitchen cabinets with new units., Fabric, Other |  | 2400425 |  | TBC | 0 | 250000 | 250000 | 1
240129_352 | Secunda Mall, Replace all carpets in back office; Replace Vi | 2024-05-10 | 2024-05-16 | Continue | R.PR/3/13 | 35034X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | OneView number corrected as per Ilana comment., | Secunda Mall, Replace all carpets in back office; Replace Vinyl floor tiles in ATM Room; Replace ceramic tiles at the entrance lobby; Repaint walls at front and back of house., Fabric, Other |  | 2400459 |  | TBC | 0 | 250000 | 250000 | 1
240129_424 | Volksrust, Painting of external walls to building facades); | 2024-03-19 | 2024-03-25 | Continue | R.PR/3/05 | 77566X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Volksrust, Painting of external walls to building facades); painting and remediation of rain water goods; replacement of ATM lobby wall tiles along the entrance façade; paint to yard palisade fence, Fabric, Other |  | 2400480 |  | TBC | 0 | 250000 | 250000 | 1
240129_553 | Absa Fochville, Spray / replace ceiling tiles, Fabric, Other | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 77647X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | Absa Fochville, Spray / replace ceiling tiles, Fabric, Other |  | 2400109 |  | TBC | 0 | 249750 | 249750 | 1
240129_345 | Broadway Building - Uitenhage, Paint brave colours in interi | 2024-08-01 | 2024-08-15 | Continue | R.PR/3/13 | 36206X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Broadway Building - Uitenhage, Paint brave colours in interior, tile back office area due heavy foot traffic to ablutions and kitchen., Fabric, Other | ASP-EC0387 | 2400297 |  | TBC | 0 | 240000 | 240000 | 1
240131_002 | 12 Alice lane- DC CRAC Units | 2022-08-30 | 2023-10-26 | Works Complete (2023) | R.PR/1/05 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | 12 Alice lane- DC CRAC Units | ASP-GS0489 |  |  | Complete | 239512.018 | 0 | 239512.018 | 1
240129_290 | 49 Main Road Gansbaai, HVAC upgrade, Mechanical | 2024-05-01 | 2024-05-15 | Continue | R.PR/2/05 | 77700X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Mholi to advise to split over 2 years 50%, | 49 Main Road Gansbaai, HVAC upgrade, Mechanical | ASP-WC0349 | 2400298 |  | TBC | 0 | 225000 | 225000 | 1
240129_536 | Absa Lower Long Street, Sluice's Room's X 3 - 2nd 3rd and 4t | 2024-05-15 | 2024-06-15 | Continue | R.PR/3/05 | 77657X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Addition 16 Nov Meeting- Estimate - R75k each, No Objection Meeting 24 Nov | Absa Lower Long Street, Sluice's Room's X 3 - 2nd 3rd and 4th floors, Fabric, Other | ASP-WC0351 | 2400120 |  | TBC | 0 | 225000 | 225000 | 1
240131_009 | Absa Boksburg 2 roller Shutters | 2023-11-14 | 2023-12-21 | Works Complete (2023) | R.PR/3/13 | 70238X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Boksburg 2 roller Shutters | ASP-GS0758 |  |  | Complete | 211616.79 | 0 | 211616.79 | 1
240129_249 | Auckland Park, Lift Replacement, Mechanical | 2023-01-11 | 2023-12-14 | Works Complete (2023) | R.PR/1/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Lift Replacement, Mechanical | ALP-GS0022 | 0 |  | Complete | 207778.09 | 0 | 207778.09 | 1
240129_403 | Tsakane Mall, Carpet and floor tile replacement + painting, | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 21857X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Tsakane Mall, Carpet and floor tile replacement + painting, Fabric, Other |  | 2400112 |  | TBC | 0 | 202087.98 | 202087.98 | 1
240129_379 | 17 Harrison Street (Main Street), Frosting requires by the A | 2024-05-01 | 2024-05-30 | Continue | R.PR/3/13 | 78786X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported - Description changed by Region, | 17 Harrison Street (Main Street), Frosting requires by the ATM lobby (during branch operating hours), Fabric, Other |  | 2400113 |  | TBC | 0 | 200000 | 200000 | 1
240129_306 | Absa Call Centre Auckland Park, Replace HVAC Unit Filters | 2024-03-01 | 2024-03-30 | Continue | R.PR/1/05 | 76849X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Absa Call Centre Auckland Park, Replace HVAC Unit Filters, Mechanical |  | 2400114 |  | TBC | 0 | 200000 | 200000 | 1
240129_527 | Absa Square RHO, Replace existing desking with open desk sea | 2024-04-12 | 2024-04-26 | Cancel | R.PR/3/05 | 77878X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Desks to be done via Moves and Churns, transport costs. Transfer to Opex | Absa Square RHO, Replace existing desking with open desk seating arrangement similar to Absa Towers, Fabric, Other |  | 2400354 |  | TBC | 0 | 200000 | 200000 | 1
240129_525 | Absa Towers Main, Replace HVAC Unit Filters, Mechanical | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/05 | 78944X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Absa Towers Main, Replace HVAC Unit Filters, Mechanical |  | 2400116 |  | TBC | 0 | 200000 | 200000 | 1
240129_305 | Absa Towers West, Replace HVAC Unit Filters, Mechanical | 2024-03-01 | 2024-03-30 | Continue | R.PR/1/05 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | H&S issue, might be stock | Absa Towers West, Replace HVAC Unit Filters, Mechanical |  | 2400119 |  | TBC | 0 | 200000 | 200000 | 1
240129_538 | Centurion Building, replacement of blinds / frosting, Fabric | 2024-03-01 | 2024-03-31 | Defer | R.PR/3/13 | 77427X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | FM to check stores for blinds from Bridge Park - LED scheduled for 2023.OneView number changed as per Ilana comments, | Centurion Building, replacement of blinds / frosting, Fabric, Other |  | 2400120 |  | TBC | 0 | 200000 | 200000 | 1
240129_425 | Grand Palace, Replace Carpets with Vinyl tiles in Server roo | 2024-04-05 | 2024-04-12 | Continue | R.PR/3/05 | 70641X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Grand Palace, Replace Carpets with Vinyl tiles in Server room; Change direction of door swing for the door along fire escape route to open towards flow of traffic; Create Cleaning storeroom; provide new signage for redefined fire escape route., Fabric, Other |  | 2400389 |  | TBC | 0 | 200000 | 200000 | 1
240129_393 | Musina Mall, Replace back office carpets; Repaint all teller | 2024-03-22 | 2024-03-26 | Continue | R.PR/3/13 | 36246X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Musina Mall, Replace back office carpets; Repaint all teller area walls; and repaint ATM room walls., Fabric, Other |  | 2400431 |  | TBC | 0 | 200000 | 200000 | 1
240129_551 | Raisethorpe, Refurbish kitchen and pause area, Fabric, Other | 2024-07-05 | 2024-07-12 | Under review | R.PR/3/13 | 77839X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Retain 100% of funds, pending business case 2024, | Raisethorpe, Refurbish kitchen and pause area, Fabric, Other |  | 2400450 |  | TBC | 0 | 200000 | 200000 | 1
240129_404 | Rayton Park Plaza, Partition dividers between consultant des | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 78058X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Rayton Park Plaza, Partition dividers between consultant desks, Fabric, Other |  | 2400122 |  | TBC | 0 | 200000 | 200000 | 1
240129_031 | Ridgeside ABSA RHO, Masterpack Breakers , Electrical | 2024-06-07 | 2024-06-16 | Continue | R.PR/1/04 | 22460X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | R200k removed, | Ridgeside ABSA RHO, Masterpack Breakers , Electrical |  | 2400453 |  | TBC | 0 | 200000 | 200000 | 1
240129_392 | Thavhani Mall, Replace all Carpet to front of house and back | 2024-03-29 | 2024-04-05 | Continue | R.PR/3/13 | 36254X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Thavhani Mall, Replace all Carpet to front of house and back office, repaint pause area and installing bumper rails to affected walls., Fabric, Other |  | 2400464 |  | TBC | 0 | 200000 | 200000 | 1
240129_570 | Ulundi shopping centre , Upgrade Ablutions and back office a | 2024-05-15 | 2024-05-20 | Under review | R.PR/3/13 | 77891X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Ulundi shopping centre , Upgrade Ablutions and back office area, Fabric, Other |  | 2400474 |  | TBC | 0 | 200000 | 200000 | 1
240129_155 | Absa Koppies , Branch need x3 Carports & Paving, Fabric, Oth | 2023-11-15 | 2023-11-30 | Works Complete (2023) | R.PR/3/05 | 78856X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Koppies , Branch need x3 Carports & Paving, Fabric, Other | ASP-CR0430 | 0 |  | Complete | 194513 | 0 | 194513 | 1
240129_096 | Vrede, Cosmic Upgrade - VO , Fabric, Other | 2023-10-01 | 2023-10-02 | Works Complete (2023) | R.PR/3/13 | 77122X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Vrede, Cosmic Upgrade - VO , Fabric, Other | ASP-CR0374 | 0 |  | Complete | 193485.775 | 0 | 193485.775 | 1
240129_168 | Various Sites, National- Reistallation of the BOCC syst, Electrical (240129_168) | 2022-02-02 | 2024-01-31 | Works Complete (2023) | R.PR/2/02 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, National- Reistallation of the BOCC syst, Electrical | ALP-N00019 | 0 |  | Complete | 190226.1 | 0 | 190226.1 | 1
240129_165 | Absa Towers West, Relocate Walk-In Centre, Fabric, Other | 2023-12-08 | 2024-01-31 | Works Approved (2023) | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Financial | Absa Towers West, Relocate Walk-In Centre, Fabric, Other | ASP-GS0729 |  |  | TBC | 188322.804 | 0 | 188322.804 | 1
240129_276 | Absa Towers North, Integration of UPS, Electrical | 2023-07-04 | 2023-12-30 | Works Complete (2023) | R.PR/1/04 | 77381X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Started and Not Completed in 2023, Rollover-Financial | Absa Towers North, Integration of UPS, Electrical | ASP-GS0690 |  |  | Complete | 182398.4065 | 0 | 182398.4065 | 1
240129_154 | Wonderpark, Wonderpark Service Desk & x2 Chairs, Fabric, Oth | 2023-10-27 | 2024-02-15 | Works Approved (2023) | R.PR/3/13 | 76677X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Started and Not Completed in 2023, Rollover-Financial | Wonderpark, Wonderpark Service Desk & x2 Chairs, Fabric, Other | ASP-GN0230 |  |  | TBC | 181447.5175 | 0 | 181447.5175 | 1
240129_149 | Absa Ladysmith , Installation of new office cubicle, Fabric | 2023-11-20 | 2023-11-27 | Works Complete (2023) | R.PR/3/13 | 21052X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Ladysmith , Installation of new office cubicle, Fabric, Other | ASP-KZ0258 | 0 |  | Complete | 181249.68 | 0 | 181249.68 | 1
240129_106 | The Grove, mall, Minor Works - Painting lights & benche, Fabr | 2023-04-11 | 2023-04-30 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | The Grove mall, Minor Works - Painting lights & benche, Fabric, Other | ASP-GN0149 | 0 |  | Complete | 179156.7175 | 0 | 179156.7175 | 1
240129_129 | Absa Mahikeng , Replace internal signage, blinds and waiting | 2023-11-15 | 2024-01-30 | Works Complete (2023) | R.PR/3/13 | 77725X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Mahikeng , Replace internal signage, blinds and waiting area chairs, Fabric, Other | ASP-CR0397 | 0 |  | Complete | 178956.92 | 0 | 178956.92 | 1
240129_092 | Butterworth, UPS Replacement (Not Part of CIP), Electrical | 2023-11-06 | 2023-11-08 | Works Complete (2023) | R.PR/2/04 | 78501X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023 | Butterworth, UPS Replacement (Not Part of CIP), Electrical | ASP-EC0369 | 0 |  | Complete | 178505.84 | 0 | 178505.84 | 1
240129_441 | Absa Spar, Replacement APC UPS, Mechanical | 2024-02-16 | 2024-02-18 | Continue | R.PR/2/05 | 77360X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Absa Spar, Replacement APC UPS, Mechanical |  | 2400253 |  | TBC | 0 | 175710.09 | 175710.09 | 1
240131_006 | Clearwate 3 X Video Conferencing Units | 2023-05-03 | 2023-09-15 | Works Complete (2023) | R.PR/3/09 | 70352X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Clearwate 3 X Video Conferencing Units | ASP-GS0642 |  |  | Complete | 170639.42 | 0 | 170639.42 | 1
240129_110 | Various Corp Sites, Bulk Various Sites, White Goods | 2023-02-20 | 2024-01-31 | Works Approved (2023) | R.PR/8/06 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Project in progress | Various Sites, Bulk Various Sites, White Goods | ALP-N00037 |  |  | TBC | 168962.922 | 0 | 168962.922 | 1
240129_327 | Arbour Crossing Retail Centre, Replace ceiling tiles, Fabric | 2024-03-21 | 2024-03-25 | Continue | R.PR/3/05 | 76958X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Arbour Crossing Retail Centre, Replace ceiling tiles, Fabric, Other |  | 2400357 |  | TBC | 0 | 160000 | 160000 | 1
240129_440 | Hoedspruit, APC Unit Replacement, Mechanical | 2024-01-17 | 2024-01-18 | Continue | R.PR/2/05 | 76718X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Hoedspruit, APC Unit Replacement, Mechanical |  | 2400247 |  | TBC | 0 | 159736.44 | 159736.44 | 1
240129_143 | Alice Lane South, Replacement of Umbrellas, Fabric, Other | 2023-12-11 | 2024-01-31 | Works Approved (2023) | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice lane South, Replacement of Umbrellas, Fabric, Other | ASP-GS0737 |  |  | TBC | 152197.003 | 0 | 152197.003 | 1
240129_282 | Auckland Park, Replacement of Compressor, Mechanical | 2023-09-13 | 2023-11-25 | Works Complete (2023) | R.PR/1/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Replacement of Compressor, Mechanical | ASP-GS0635 | 0 |  | Complete | 150443.46 | 0 | 150443.46 | 1
240129_309 | Absa Beaufort West, DB Upgrade / Access Issue (Safety), Elec | 2024-06-15 | 2024-06-30 | Continue | R.PR/2/04 | 77401X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Beaufort West, DB Upgrade / Access Issue (Safety), Electrical | ASP-EC0394 | 2400302 |  | TBC | 0 | 150000 | 150000 | 1
240129_323 | Absa Bredasdorp, Secure the boundary Fence, Fabric, Other | 2024-07-10 | 2024-07-20 | Continue | R.PR/3/05 | 77641X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Absa Bredasdorp, Secure the boundary Fence , Fabric, Other | ASP-WC0350 | 2400303 |  | TBC | 0 | 150000 | 150000 | 1
240129_537 | Alice Lane North, Block out vinyl for wrap station, Fabric, | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Catering to solution and provide temp sheets throughout the day. As per Hanlie Louw email 9-Feb-24, project to be reduced to R50,000 refer to 240129_537, 240129_537a and 240211_001. | Alice Lane North, Block out vinyl for wrap station, Fabric, Other |  | 2400020 |  | TBC | 0 | 150000 | 150000 | 1
240129_467 | Central City Shopping Centre Mabopane, Installation of gener | 2024-09-01 | 2024-09-30 | Continue | R.PR/2/02 | 76439X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Supported, | Central City Shopping Centre Mabopane, Installation of generator steel cage shelter , Engineering and Infrastructure |  | 2400131 |  | TBC | 0 | 150000 | 150000 | 1
240129_293 | Fleurdal Mall, Installation of UPS and electrical reticulati | 2024-03-15 | 2024-03-15 | Under review | R.PR/2/04 | 79303X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | No Emergency back up Power on site, | Fleurdal Mall, Installation of UPS and electrical reticulation, Electrical |  | 2400385 |  | TBC | 0 | 150000 | 150000 | 1
240129_312 | Hope Town, Installation of UPS and electrical reticulation, | 2024-02-06 | 2024-02-13 | Continue | R.PR/2/04 | 78645X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Hope Town, Installation of UPS and electrical reticulation, Electrical |  | 2400396 |  | TBC | 0 | 150000 | 150000 | 1
240129_394 | Mokopane, Replace Carpets, Install bumper rails in teller ar | 2024-04-22 | 2024-04-28 | Continue | R.PR/3/13 | 76721X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Mokopane, Replace Carpets, Install bumper rails in teller area, Fabric, Other |  | 2400428 |  | TBC | 0 | 150000 | 150000 | 1
240129_311 | Moruleng Mall, Installation of UPS (Upgrade from 3kVA to 15k | 2024-03-02 | 2024-03-02 | Continue | R.PR/2/04 | 36104X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Moruleng Mall, Installation of UPS (Upgrade from 3kVA to 15kVA), Electrical |  | 2400429 |  | TBC | 0 | 150000 | 150000 | 1
240129_292 | Petrusburg, Installation of UPS and electrical reticulation, | 2024-03-16 | 2024-03-16 | Continue | R.PR/2/04 | 79067X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | No Emergency back up Power on site, | Petrusburg, Installation of UPS and electrical reticulation, Electrical |  | 2400440 |  | TBC | 0 | 150000 | 150000 | 1
240129_310 | Phokeng Mall, Installation of UPS (Upgrade from 3kVA to 15kV | 2024-03-02 | 2024-03-02 | Continue | R.PR/2/04 | 78032X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Phokeng Mall, Installation of UPS (Upgrade from 3kVA to 15kVA), Electrical |  | 2400441 |  | TBC | 0 | 150000 | 150000 | 1
240129_291 | Trompsburg, Installation of UPS and electrical reticulation, | 2024-03-15 | 2024-03-15 | Continue | R.PR/2/04 | 79334X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | No Emergency back up Power on site, | Trompsburg, Installation of UPS and electrical reticulation, Electrical |  | 2400469 |  | TBC | 0 | 150000 | 150000 | 1
240129_263 | Absa Towers North, Replacement of 21 Cond, Mechanical | 2023-03-23 | 2023-10-20 | Works Complete (2023) | R.PR/1/05 | 77381X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers North, Replacement of 21 Cond, Mechanical | ALP-GS0047 | 0 |  | Complete | 140191.2675 | 0 | 140191.2675 | 1
240129_547 | Various Corp Sites, Catering - EOL Equipment 2023, Catering | 2025-01-01 | 2025-12-31 | Defer | R.PR/8/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | Yes | remove 35%, | Various Sites, Catering - EOL Equipment 2023, Catering | 0 | 2400519 |  | TBC | 0 | 137931.62 | 137931.62 | 1
240129_269 | Absa Towers North, Upgrade of Fire Panel, Fire | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/06 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers North, Upgrade of Fire Panel, Fire | ASP-GS0629 |  |  | Complete | 132299.0245 | 0 | 132299.0245 | 1
240129_162 | Auckland Park, Supply and install internal Signage, Fabric, | 2023-11-10 | 2023-12-14 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Supply and install internal Signage, Fabric, Other | ASP-GS0731 | 0 |  | Complete | 131393.71 | 0 | 131393.71 | 1
240129_144 | Absa Call Centre Auckland Park, Supply and install Salad Bar, Other | 2023-06-09 | 2024-01-30 | Works Approved (2023) | R.PR/3/05 | 76849X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Started and Not Completed in 2023, Rollover-Financial | Auckland Park, Supply and install Salad Bar, Fabric, Other | ASP-GS0740 |  |  | TBC | 130556.05 | 0 | 130556.05 | 1
240129_039 | Alice lane North, Replacement of generator starter batteries | 2024-09-10 | 2024-10-10 | Continue | R.PR/1/04 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Alice lane North, Replacement of generator starter batteries (special out LCC consideration), Electrical |  | 2400022 |  | TBC | 0 | 130000 | 130000 | 1
240131_010 | Absa Southdale Close off Tellers | 2023-11-07 | 2023-12-21 | Works Complete (2023) | R.PR/3/13 | 70027X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Southdale Close off Tellers | ASP-GS0759 |  |  | Complete | 127119.7005 | 0 | 127119.7005 | 1
240129_070 | Various Retail Sites, Bulk Various Sites, Fabric, Other | 2023-11-01 | 2024-01-31 | Works Approved (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in progress | Various Sites, Bulk Various Sites, Fabric, Other | ALP-N00039 |  |  | TBC | 126396.0295 | 0 | 126396.0295 | 1
240129_138 | Alice lane South, Absa Alice Lane South Video Conferencing, | 2023-12-01 | 2023-12-20 | Works Complete (2023) | R.PR/3/09 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane South, Absa Alice Lane South Video Conferencing, Fabric, Other | ASP-GS0733 | 0 |  | Complete | 125350 | 0 | 125350 | 1
240129_284 | 270 Republic Road, Replacement of generator, Electrical | 2023-10-05 | 2023-12-15 | Works Complete (2023) | R.PR/1/04 | 21334X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | 270 Republic Road, Replacement of generator, Electrical | ASP-GS0751 | 0 |  | Complete | 123681.166 | 0 | 123681.166 | 1
240129_156 | Absa Bloemfontein CBD , Installation of new office cubicle, | 2023-11-15 | 2023-11-20 | Works Complete (2023) | R.PR/3/13 | 78754X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Bloemfontein CBD , Installation of new office cubicle, Fabric, Other | ASP-CR0508 | 0 |  | Complete | 120774.3235 | 0 | 120774.3235 | 1
240129_353 | Church Str Klerksdorp, Install Privacy screen at 1st ATM, in | 2024-06-14 | 2024-06-18 | Continue | R.PR/3/13 | 37181X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | OneView number corrected as per Ilana comment., | Church Str Klerksdorp, Install Privacy screen at 1st ATM, include move of q-rails and replace damaged tiles , Fabric, Other |  | 2400379 |  | TBC | 0 | 120000 | 120000 | 1
240129_381 | Montana (Fin Forum), Frosting on shop front windows, Fabric, | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 78655X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | Montana (Fin Forum), Frosting on shop front windows, Fabric, Other |  | 2400145 |  | TBC | 0 | 120000 | 120000 | 1
240129_108 | Absa Tromsburg , Installation of water tank, booster pump an | 2023-12-14 | 2023-12-15 | Works Complete (2023) | R.PR/2/10 | 79334X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Tromsburg , Installation of water tank, booster pump and filtration system, New assets | ASP-CR0535 | 0 |  | Complete | 114743.34 | 0 | 114743.34 | 1
240129_115 | Absa Newcastle, Installation of external signage, Fabric, O | 2023-11-16 | 2023-11-17 | Works Approved (2023) | R.PR/3/13 | 78136X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Newcastle , Installation of external signage, Fabric, Other | ASP-KZ0248 |  |  | TBC | 108645.68 | 0 | 108645.68 | 1
240129_066 | Alice lane North, Replace Generator Batteries, Electrical | 2023-12-01 | 2023-12-20 | Works Approved (2023) | R.PR/1/04 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice lane North, Replace Generator Batteries, Electrical | ASP-GS0719 |  |  | TBC | 108092.16 | 0 | 108092.16 | 1
240129_265 | Auckland Park, Upgrade the Honeywell N, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Upgrade the Honeywell N, Electrical | ASP-GS0620 |  |  | Complete | 107149.203 | 0 | 107149.203 | 1
240129_182 | Absa Towers North, Replace wobbly/loose raised, Fabric, Othe | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers North, Replace wobbly/loose raised, Fabric, Other | ASP-GS0488 |  |  | Complete | 106224.649 | 0 | 106224.649 | 1
240129_267 | Absa Brooklyn, Relocation of 110 KVA SDMO generator, Fabric, | 2023-04-12 | 2023-04-30 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Brooklyn, Relocation of 110 KVA SDMO generator, Fabric, Other | ASP-GN0182 | 0 |  | Complete | 106121.3215 | 0 | 106121.3215 | 1
240129_280 | Absa Pretoria Campus , Structural crack repair, Mechanical | 2023-08-23 | 2023-12-01 | Works Complete (2023) | R.PR/1/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Structural crack repair, Mechanical | ALP-GN0011 | 0 |  | Complete | 104026.999 | 0 | 104026.999 | 1
240129_382 | 230 Lilian Ngoyi Street, Carpet replacement at the welcome d | 2024-03-01 | 2024-03-31 | Continue | R.PR/3/13 | 22896X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | 230 Lilian Ngoyi Street, Carpet replacement at the welcome desk, Fabric, Other |  | 2400140 |  | TBC | 0 | 102324 | 102324 | 1
240129_191 | Various Sites, UPS Batteries, Electrical, PO# C000071627 | 2022-02-02 | 2024-01-31 | Works Complete (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, UPS Batteries, Electrical | ALP-N00038 | 0 |  | Complete | 102088.72 | 0 | 102088.72 | 1
240129_040 | 270 Republic Road, Replacement of generator starter batterie | 2024-03-01 | 2024-09-27 | Continue | R.PR/1/04 | 21335X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | 270 Republic Road, Replacement of generator starter batteries (special out LCC consideration), Electrical |  | 2400141 |  | TBC | 0 | 100000 | 100000 | 1
240129_374 | 8 Top Road, All blinds require replacement - Office , Fabri | 2024-05-01 | 2024-06-30 | Continue | R.PR/3/05 | 78451X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Supported, | 8 Top Road, All blinds require replacement - Office , Fabric, Other |  | 2400143 |  | TBC | 0 | 100000 | 100000 | 1
240129_375 | 8 Top Road, Roof over office at mech workshop, Fabric, Other | 2024-06-01 | 2024-06-30 | Continue | R.PR/3/05 | 78451X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Supported, | 8 Top Road, Roof over office at mech workshop, Fabric, Other |  | 2400142 |  | TBC | 0 | 100000 | 100000 | 1
240129_494 | Absa Parys, Installation of water tank, booster pump and fil | 2024-03-04 | 2024-03-18 | Continue | R.PR/2/10 | 78350X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Absa Parys, Installation of water tank, booster pump and filtration system , New assets |  | 2400349 |  | TBC | 0 | 100000 | 100000 | 1
240129_422 | Absa Pretoria Campus, Block K enclose garden refusal disposa | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Absa Pretoria Campus, Block K enclose garden refusal disposal area (Shipping container), Fabric, Other |  | 2400125 |  | TBC | 0 | 100000 | 100000 | 1
240129_421 | Absa Towers West, Replace all roof wooden doors to aluminium | 2024-05-01 | 2024-05-30 | Continue | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Absa Towers West, Replace all roof wooden doors to aluminium as the wooden get affected by weather., Fabric, Other |  | 2400144 |  | TBC | 0 | 100000 | 100000 | 1
240129_303 | Alice lane North, Replacement of CRAC Unit Filters, Mechanic | 2024-04-01 | 2024-04-30 | Continue | R.PR/1/05 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Alice lane North, Replacement of CRAC Unit Filters, Mechanical |  | 2400024 |  | TBC | 0 | 100000 | 100000 | 1
240129_449 | Bethal , Installation of water tank, booster pump and filtra | 2024-05-21 | 2024-05-30 | Continue | R.PR/2/10 | 77421X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Requested by the Region due to water shortages., | Bethal , Installation of water tank, booster pump and filtration system , New assets |  | 2400360 |  | TBC | 0 | 100000 | 100000 | 1
240129_559 | Bloemfontein Forum, New Installation of a bulk diesel tank t | 2024-02-08 | 2024-02-22 | Continue | R.PR/1/10 | 22161X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | Yes | This site has IT presence and refilling daily is not operationally viable. , | Bloemfontein Forum, New Installation of a bulk diesel tank to support the Generator Day Tank., New Assets |  | 2400363 |  | TBC | 0 | 100000 | 100000 | 1
240129_448 | Delmas, Installation of water tank, booster pump and filtrat | 2024-04-22 | 2024-05-05 | Continue | R.PR/2/10 | 37064X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Requested by the Region due to water shortages., | Delmas, Installation of water tank, booster pump and filtration system, New assets |  | 2400380 |  | TBC | 0 | 100000 | 100000 | 1
240129_447 | Ermelo, Installation of water tank, booster pump and filtrat | 2024-04-16 | 2024-04-28 | Continue | R.PR/2/10 | 77584X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Requested by the Region due to water shortages., | Ermelo, Installation of water tank, booster pump and filtration system, New assets |  | 2400383 |  | TBC | 0 | 100000 | 100000 | 1
240129_493 | Frankfort , Installation of water tank, booster pump and fil | 2024-02-29 | 2024-03-15 | Continue | R.PR/2/10 | 78306X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Frankfort , Installation of water tank, booster pump and filtration system , New assets |  | 2400387 |  | TBC | 0 | 100000 | 100000 | 1
240129_313 | Mega City, Linking UPS to BMS, Electrical | 2024-03-01 | 2024-03-01 | Continue | R.PR/2/04 | 77784X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Mega City, Linking UPS to BMS, Electrical |  | 2400420 |  | TBC | 0 | 100000 | 100000 | 1
240129_492 | Nquthu, Installation of water tank, booster pump and filtrat | 2024-03-18 | 2024-04-01 | Continue | R.PR/2/10 | 79051X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Nquthu, Installation of water tank, booster pump and filtration system , New assets |  | 2400434 |  | TBC | 0 | 100000 | 100000 | 1
240129_395 | Paulpietersburg (17 High Street), Replacement of carpets and | 2024-03-14 | 2024-03-19 | Continue | R.PR/3/13 | 77511X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Paulpietersburg (17 High Street), Replacement of carpets and application new brand colours on walls, Fabric, Other |  | 2400333 |  | TBC | 0 | 100000 | 100000 | 1
240129_491 | Port Edward, Installation of water tank, booster pump and fi | 2024-04-03 | 2024-04-18 | Continue | R.PR/2/10 | 77893X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Port Edward, Installation of water tank, booster pump and filtration system , New assets |  | 2400445 |  | TBC | 0 | 100000 | 100000 | 1
240129_490 | Theunissen, Installation of water tank, booster pump and fil | 2024-03-13 | 2024-03-27 | Continue | R.PR/2/10 | 79293X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Theunissen, Installation of water tank, booster pump and filtration system, New assets |  | 2400466 |  | TBC | 0 | 100000 | 100000 | 1
240129_475 | Umlazi, Installation of water tank, booster pump and filtrat | 2024-03-18 | 2024-04-01 | Continue | R.PR/2/10 | 77729X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Umlazi, Installation of water tank, booster pump and filtration system , New assets |  | 2400475 |  | TBC | 0 | 100000 | 100000 | 1
240129_446 | White River, Installation of water tank, booster pump and fi | 2024-06-18 | 2024-06-26 | Continue | R.PR/2/10 | 77602X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Requested by the Region due to water shortages., | White River, Installation of water tank, booster pump and filtration system , New assets |  | 2400484 |  | TBC | 0 | 100000 | 100000 | 1
240129_099 | Various Sites, 3 X Ice Cream machines, Catering | 2021-08-02 | 2024-01-31 | Works Complete (2023) | R.PR/8/04 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, 3 X Ice Cream machines, Catering | ASP-N00053 | 0 |  | Complete | 98210 | 0 | 98210 | 1
240129_103 | Absa Ottosdal, Installation of water tank, booster pump and | 2024-01-22 | 2023-12-09 | Works Approved (2023) | R.PR/2/10 | 78143X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Ottosdal , Installation of water tank, booster pump and filtration system, New assets | ASP-CR0266 |  |  | TBC | 94973.5 | 0 | 94973.5 | 1
240129_127 | Oude Bloemhof, Minor Works - (Not Part of CIP) - (Fence Out | 2023-08-14 | 2023-12-15 | Works Approved (2023) | R.PR/3/05 | 77946X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Partially Completed and patially Invoiced | Oude Bloemhof, Minor Works - (Not Part of CIP) - (Fence Outstanding) , Fabric, Other | ASP-WC0282 |  |  | TBC | 93477.0985 | 0 | 93477.0985 | 1
240129_405 | Kempton Square Central Park, External signage to be added in | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 37163X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Kempton Square Central Park, External signage to be added in main road, Fabric, Other |  | 2400147 |  | TBC | 0 | 90000 | 90000 | 1
240129_496 | Mogwase Shopping Centre, Installation of water tank, booster | 2024-03-11 | 2024-04-18 | Continue | R.PR/2/10 | 77787X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Mogwase Shopping Centre, Installation of water tank, booster pump and filtration system, New assets |  | 2400427 |  | TBC | 0 | 90000 | 90000 | 1
240129_495 | Warden, Installation of water tank, booster pump and filtrat | 2024-03-15 | 2024-03-30 | Continue | R.PR/2/10 | 79096X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Warden, Installation of water tank, booster pump and filtration system, New assets |  | 2400482 |  | TBC | 0 | 90000 | 90000 | 1
240131_013 | Absa Jan Kempdorp - ATM Extension | 2023-07-06 | 2023-12-18 | Works Complete (2023) | R.PR/3/13 | 71347X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Core Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Jan Kempdorp - ATM Extension | ALP-CR0022 |  |  | Complete | 89594.913 | 0 | 89594.913 | 1
240129_164 | Absa Pretoria Campus , Refurbishment 18 faded Directional Si | 2023-11-01 | 2023-12-30 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Refurbishment 18 faded Directional Signage, Fabric, Other | ASP-GN0206 | 0 |  | Complete | 88952.5 | 0 | 88952.5 | 1
240129_105 | Tsakane Mall, Installation of 60kva gene, Fabric, Other | 2023-01-09 | 2023-02-05 | Works Complete (2023) | R.PR/3/13 | 21857X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Tsakane Mall, Installation of 60kva gene, Fabric, Other | ALP-GS0036 | 0 |  | Complete | 88621.645 | 0 | 88621.645 | 1
240129_552 | Kwagga, Replace Kitchen Cupboard with new, Fabric, Other | 2024-04-20 | 2024-04-22 | Cancel | R.PR/3/13 | 76785X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Retain 100% of funds, pending business case 2024. As per Hanlie Louw email 9-Feb-24, project can be surrendered (Give Back) it is no longer needed | Kwagga, Replace Kitchen Cupboard with new, Fabric, Other |  | 2400407 |  | TBC | 0 | 85000 | 85000 | 1
240129_231 | Auckland Park, Temperature Difference, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Temperature Difference, Electrical | ASP-GS0484 |  |  | Complete | 81779.3865 | 0 | 81779.3865 | 1
240129_439 | Theunissen, HVAC Unit, Mechanical | 2024-02-24 | 2024-02-24 | Continue | R.PR/2/05 | 79293X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Theunissen, HVAC Unit, Mechanical |  | 2400246 |  | TBC | 0 | 80720.4 | 80720.4 | 1
240129_396 | 99 Walter Sisulu Potchefstroom, Close off entrance | 2024-01-20 | 2024-01-21 | Continue | R.PR/3/13 | 77114X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | 99 Walter Sisulu Potchefstroom, Close off entrance of back area gate due to unwanted vagrants utilizing the area, Fabric, Other |  | 2400335 |  | TBC | 0 | 80000 | 80000 | 1
240129_077 | Alice lane North, Replacement of external Absa Vinyl, Fabric | 2023-11-15 | 2023-11-20 | Works Complete (2023) | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane North, Replacement of external Absa Vinyl, Fabric, Other | ASP-GS0715 | 0 |  | Complete | 79759.6185 | 0 | 79759.6185 | 1
240129_435 | Absa Tzaneen Hotel Danie Joubert, Replacement of indoor PC | 2024-01-22 | 2024-01-26 | Continue | R.PR/2/04 | 76808X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Absa Tzaneen HotelDanie Joubert , Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | 2400249 |  | TBC | 0 | 79414.86 | 79414.86 | 1
240129_157 | Kamaqhekeza, Installation of new 1500litres water tank with | 2023-10-09 | 2023-10-21 | Works Complete (2023) | R.PR/2/10 | 77571X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Kamaqhekeza, Installation of new 1500litres water tank with filtration system, New assets | ASP-MP0171 | 0 |  | Complete | 77320.93 | 0 | 77320.93 | 1
240129_061 | Absa Piet Retief , Installation of water tank, New assets | 2023-02-08 | 2023-11-30 | Works Complete (2023) | R.PR/2/10 | 77121X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Piet Retief , Installation of water tank, New assets | ASP-MP0066 | 0 |  | Complete | 77226.7 | 0 | 77226.7 | 1
240129_146 | Absa Towers West, Replace Exco Desks, Fabric, Other | 2023-12-05 | 2023-12-14 | Works Approved (2023) | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Financial | Absa Towers West, Replace Exco Desks, Fabric, Other | ASP-GS0743 |  |  | TBC | 75282.45 | 0 | 75282.45 | 1
240129_324 | Absa Willowmore, Windows to be replaced (glass), Fabric, Oth | 2024-04-15 | 2024-05-10 | Continue | R.PR/3/05 | 77596X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Absa Willowmore, Windows to be replaced (glass), Fabric, Other | ASP-EC0401 | 2400307 |  | TBC | 0 | 75000 | 75000 | 1
240129_314 | Blue Haze Shopping Centre, Linking generator to BMS, Electri | 2024-05-15 | 2024-05-18 | Continue | R.PR/2/04 | 77446X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Blue Haze Shopping Centre, Linking generator to BMS, Electrical |  | 2400366 |  | TBC | 0 | 75000 | 75000 | 1
240129_426 | Botshabelo Shopping Centre, Change or replace main shopfront | 2024-04-15 | 2024-04-22 | Continue | R.PR/3/13 | 78702X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | TBC | Botshabelo Shopping Centre, Change or replace main shopfront with roller rooter door , Fabric, Other |  | 2400368 |  | TBC | 0 | 75000 | 75000 | 1
240129_535 | Moffett Office Park, MOP, Sluice's Room X1, Fabric, Other | 2024-04-15 | 2024-05-15 | Continue | R.PR/3/05 | 22937X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Addition 16 Nov Meeting - Estimate - Dependant on approved solution, No Objection Meeting 24 Nov | Moffett Office Park, MOP, Sluice's Room X1, Fabric, Other | ASP-EC0402 | 2400124 |  | TBC | 0 | 75000 | 75000 | 1
240129_524 | Ridgeside ABSA RHO, Replacement of Generator Batteries (Gene | 2024-03-22 | 2024-03-24 | Continue | R.PR/1/04 | 22460X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Ridgeside ABSA RHO, Replacement of Generator Batteries (Generator 1, 2 & 3), Electrical |  | 2400454 |  | TBC | 0 | 75000 | 75000 | 1
240129_213 | Alice lane South, First Flr Soundproofing 01 & 102, Remediat | 2022-10-10 | 2023-03-15 | Works Complete (2023) | R.PR/5/12 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane South, First Flr Soundproofing 01 & 102, Remediation | ALP-GS0048 | 0 |  | Complete | 74834.893 | 0 | 74834.893 | 1
240129_275 | Absa Vaal Mall , Installation of UPS, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Vaal Mall , Installation of UPS, Electrical | ASP-GS0691 |  |  | Complete | 71918.125 | 0 | 71918.125 | 1
240129_474 | Absa Botshabelo , HVAC Replacement- Hide away, Mechanical | 2023-12-05 | 2023-12-06 | Continue | R.PR/2/05 | 78702X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Absa Botshabelo , HVAC Replacement- Hide away, Mechanical | ASP-CR0492 | 2400257 |  | TBC | 0 | 70720.4 | 70720.4 | 1
240129_307 | Absa Call Centre Auckland Park, Cassette Unit, Mechanical | 2024-09-01 | 2024-09-30 | Continue | R.PR/1/05 | 76849X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | TBC | Absa Call Centre Auckland Park, Cassette Unit, Mechanical |  | 2400088 |  | TBC | 0 | 70000 | 70000 | 1
240129_035 | Absa Heilbron, Installation of water tank, booster pump and | 2024-02-24 | 2024-02-24 | Continue | R.PR/2/10 | 77745X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | RFQ in progress , | Absa Heilbron , Installation of water tank, booster pump and filtration system, New assets |  | 2400244 |  | TBC | 0 | 70000 | 70000 | 1
240129_034 | Absa Taung, Installation of water tank, booster pump and fi | 2024-01-22 | 2024-02-02 | Continue | R.PR/2/10 | 79227X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | RFQ in progress , | Absa Taung , Installation of water tank, booster pump and filtration system, New assets |  | 2400243 |  | TBC | 0 | 70000 | 70000 | 1
240129_406 | Daveyton Shopping Centre, External signage to be added in ma | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 78727X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Daveyton Shopping Centre, External signage to be added in main road, Fabric, Other |  | 2400152 |  | TBC | 0 | 70000 | 70000 | 1
240129_407 | OR Tambo International Airport, Repainting and carpet replac | 2024-07-01 | 2024-07-30 | Continue | R.PR/3/13 | 76576X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | OR Tambo International Airport, Repainting and carpet replacement, Fabric, Other |  | 2400153 |  | TBC | 0 | 68850 | 68850 | 1
240129_057 | Absa Mkhuhlu, Installation of water tank, New assets | 2023-02-10 | 2023-11-30 | Works Complete (2023) | R.PR/2/10 | 77974X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Mkhuhlu, Installation of water tank, New assets | ASP-MP0127 | 0 |  | Complete | 68703.45 | 0 | 68703.45 | 1
240129_433 | Lea Glen Stores, Installation of Electric Fence , Electrical | 2024-10-01 | 2024-10-30 | Continue | R.PR/1/04 | 76949X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | Jodie (RSM Supports, | Lea Glen Stores, Installation of Electric Fence , Electrical |  | 2400154 |  | TBC | 0 | 66500 | 66500 | 1
240129_185 | Absa Mankweng, Installation of new 2500ltr watar tank, New a | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/10 | 76781X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Mankweng, Installation of new 2500ltr watar tank, New assets | ASP-LP0108 |  |  | Complete | 66458.5 | 0 | 66458.5 | 1
240131_014 | Absa Arbour Crossing- Minor Refurbishmen | 2023-12-09 | 2023-12-18 | Works Complete (2023) | R.PR/3/05 | 70634X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Arbour Crossing- Minor Refurbishmen | ASP-KZ2002 |  |  | Complete | 63173.985 | 0 | 63173.985 | 1
240129_056 | Absa Volksrust, Installation of water tank, New assets | 2023-02-05 | 2023-11-30 | Works Complete (2023) | R.PR/2/10 | 77566X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Volksrust, Installation of water tank, New assets | ASP-MP0088 | 0 |  | Complete | 61954.36 | 0 | 61954.36 | 1
240129_236 | Highlands Warehouse, new inverter aircond, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Highlands Warehouse, new inverter aircond, Mechanical | ASP-GS0462 |  |  | Complete | 60403.589 | 0 | 60403.589 | 1
240129_285 | 270 Republic Road, Repair of the Compressors chilllers, Mech | 2023-11-10 | 2023-11-30 | Works Complete (2023) | R.PR/1/05 | 21334X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | 270 Republic Road, Repair of the Compressors chilllers, Mechanical | ALP-GS0070 | 0 |  | Complete | 60159.053 | 0 | 60159.053 | 1
240129_518 | Alice Lane South, Replacement of generator starter batteries | 2024-03-15 | 2024-08-30 | Continue | R.PR/1/04 | 35041X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | TBC | Alice lane South, Replacement of generator starter batteries (special out LCC consideration), Electrical |  | 2400025 |  | TBC | 0 | 60000 | 60000 | 1
240129_507 | Broadway Building - Uitenhage, Install the cages for the out | 2024-04-01 | 2024-04-30 | Continue | R.PR/2/05 | 36206X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Budget Adjusted as R45k insufficient, No Objection to adjust Meeting 24 Nov | Broadway Building - Uitenhage, Install the cages for the outdoor units that are exposed., Mechanical | ASP-EC0403 | 2400312 |  | TBC | 0 | 60000 | 60000 | 1
240129_296 | Langenhovenpark , New HVAC installation in the back office, | 2024-07-11 | 2024-07-13 | Continue | R.PR/2/10 | 78830X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Running on R22 Gas, | Langenhovenpark , New HVAC installation in the back office, New assets |  | 2400408 |  | TBC | 0 | 60000 | 60000 | 1
240129_346 | Linton Arcade, Contra vision shopfront replace., Fabric, Oth | 2024-02-15 | 2024-03-31 | Continue | R.PR/3/13 | 76436X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Linton Arcade, Contra vision shopfront replace., Fabric, Other | ASP-EC0390 | 2400308 |  | TBC | 0 | 60000 | 60000 | 1
240129_571 | Multiflora (Flower Market ETC), upgrade of kitchen + hydrobo | 2024-07-01 | 2024-07-30 | Under review | R.PR/3/13 | 76554X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Multiflora (Flower Market ETC), upgrade of kitchen + hydroboil - replace floor tiles , Fabric, Other |  | 2400157 |  | TBC | 0 | 59104 | 59104 | 1
240129_286 | Absa Rosstax, HVAC Professional Cost, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Rosstax, HVAC Professional Cost, Mechanical | ASP-GN0084 |  |  | Complete | 57500 | 0 | 57500 | 1
240129_278 | Absa Pretoria Campus , Flammable Storeroom desi, Fire | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/06 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Flammable Storeroom desi, Fire | ASP-GN0215 |  |  | Complete | 57109 | 0 | 57109 | 1
240129_415 | Protea Gardens Shopping Centre, replace floor tiles, respray | 2024-07-01 | 2024-07-30 | Continue | R.PR/3/13 | 77139X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments - Region updated scope description, | Protea Gardens Shopping Centre, replace floor tiles, respray ceiling tiles- blinds for tellers and carpet replacement (outside branch operating hours), Fabric, Other |  | 2400158 |  | TBC | 0 | 57051.5 | 57051.5 | 1
240129_227 | Mall of Carnival , Minor Works, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Mall of Carnival , Minor Works, Fabric, Other | ASP-GS0649 |  |  | Complete | 56361.5 | 0 | 56361.5 | 1
240129_145 | Hercules, Hercules Minor Works, Fabric, Other | 2023-09-13 | 2023-10-10 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Hercules, Hercules Minor Works, Fabric, Other | ASP-GN0208 | 0 |  | Complete | 56077.726 | 0 | 56077.726 | 1
240129_169 | Various Sites, UPS Batteries, Electrical, PO# C002899453 | 2022-02-02 | 2024-01-31 | Works Complete (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, UPS Batteries, Electrical | ALP-N00024 | 0 |  | Complete | 55834.225 | 0 | 55834.225 | 1
240129_199 | Centurion , Signage, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Centurion , Signage, Fabric, Other | ASP-GN0126 |  |  | Complete | 55750.6545 | 0 | 55750.6545 | 1
240131_015 | Absa Die Restant Newcastle-Seperate Gen | 2023-06-14 | 2023-12-18 | Works Complete (2023) | R.PR/2/04 | 71215X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Die Restant Newcastle-Seperate Gen | ALP-KZ2005 |  |  | Complete | 55234.0745 | 0 | 55234.0745 | 1
240129_545 | Riversdale, Kitchen Upgrade, Fabric, Other | 2024-07-01 | 2024-08-06 | Under review | R.PR/3/13 | 37159X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Oneview Number Correct 37159X - Old Number was 77042X before Sale of the Building, | Riversdale, Kitchen Upgrade, Fabric, Other | ASP-EC0391 | 2400310 |  | TBC | 0 | 55000 | 55000 | 1
240129_516 | The Fynbos Centre, Stillbay, Buitenkant Street. , HVAC in th | 2024-05-15 | 2024-05-30 | Continue | R.PR/2/05 | 78314X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Possible revamp/Relocation 2024, | The Fynbos Centre, Stillbay, Buitenkant Street. , HVAC in the ATM room, Mechanical | ASP-EC0404 | 2400311 |  | TBC | 0 | 55000 | 55000 | 1
240129_220 | Absa Bloemhof , Aircon Unit in the Treasury Room , Mechanica | 2023-11-16 | 2023-11-17 | Works Complete (2023) | R.PR/2/05 | 79119X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Bloemhof , Aircon Unit in the Treasury Room , Mechanical | ASP-CR0505 | 0 |  | Complete | 52340 | 0 | 52340 | 1
240129_102 | Absa Malamulele/Mangalani, Teller Replace, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | 76784X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Malamulele/Mangalani, Teller Replace, Fabric, Other | ASP-LP0136 |  |  | Complete | 50171.05 | 0 | 50171.05 | 1
240129_384 | 230 Lilian Ngoyi Street, Frosting internal on Offices, Fabri | 2024-03-01 | 2024-03-31 | Continue | R.PR/3/13 | 22896X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | 230 Lilian Ngoyi Street, Frosting internal on Offices, Fabric, Other |  | 2400161 |  | TBC | 0 | 50000 | 50000 | 1
240129_416 | Absa Bank Mafikeng CBD, New Installation of HVAC in the BA o | 2024-05-10 | 2024-05-13 | Continue | R.PR/2/10 | 77725X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Bank Mafikeng CBD, New Installation of HVAC in the BA office., New assets |  | 2400340 |  | TBC | 0 | 50000 | 50000 | 1
240129_378 | Absa Bank Swartruggens, New Installation of HVAC in the ATM | 2024-05-17 | 2024-05-19 | Continue | R.PR/2/10 | 77433X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Bank Swartruggens, New Installation of HVAC in the ATM room., New assets |  | 2400342 |  | TBC | 0 | 50000 | 50000 | 1
240129_230 | Absa Harrison Street, HVAC - Extractor Fans required in ablu | 2024-02-16 | 2024-02-20 | Continue | R.PR/2/05 | 78786X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover from CIP2023 | Absa Harrison Street, HVAC - Extractor Fans required in ablution , Mechanical | N/A | N/A |  | TBC | 50000 | 0 | 50000 | 1
240129_331 | Absa Ridgeside, Automation of doors on the canteen and the f | 2024-03-15 | 2024-03-16 | Continue | R.PR/3/05 | 22460X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | 15/06/2023- Budget increased from R20k to R50K | Absa Ridgeside, Automation of doors on the canteen and the forth floor balcony , Fabric, Other |  | 2400352 |  | TBC | 0 | 50000 | 50000 | 1
240211_001 | Alice Lane North, Block out vinyl for wrap station, Fabric, | 2024-09-15 | 2024-10-15 | Continue | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Catering to solution and provide temp sheets throughout the day. As per Hanlie Louw email 9-Feb-24, project to be reduced to R50,000 refer to 240129_537, 240129_537a and 240211_001. | Alice Lane North, Block out vinyl for wrap station, Fabric, Other |  | 2400020 |  | TBC | 0 | 50000 | 50000 | 1
240129_385 | Centurion Building, Marketing frosting on Shop Front require | 2024-03-01 | 2024-03-31 | Continue | R.PR/3/13 | 77427X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported. OneView number changed as per Ilana comments, | Centurion Building, Marketing frosting on Shop Front requires replacement, Fabric, Other |  | 2400163 |  | TBC | 0 | 50000 | 50000 | 1
240129_328 | Chatterton, Replace carpets in Cash operations office, Fabri | 2024-02-17 | 2024-02-18 | Continue | R.PR/3/05 | 78398X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | TBC | Chatterton, Replace carpets in Cash operations office, Fabric, Other |  | 2400377 |  | TBC | 0 | 50000 | 50000 | 1
240129_409 | Cosmo Mall, Repainting, carpets and floor tiles, Fabric, Oth | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 36216X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Cosmo Mall, Repainting, carpets and floor tiles, Fabric, Other |  | 2400164 |  | TBC | 0 | 50000 | 50000 | 1
240129_383 | Ga-Rankuwa Shopping Centre, Replace frosting on shop front, | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 76686X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | Ga-Rankuwa Shopping Centre, Replace frosting on shop front, Fabric, Other |  | 2400165 |  | TBC | 0 | 50000 | 50000 | 1
240129_398 | Komatipoort Spar Centre, Provide access to the elevated stor | 2024-02-10 | 2024-02-13 | Continue | R.PR/3/13 | 77938X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Komatipoort Spar Centre, Provide access to the elevated storeroom (Retractable staircase); install walk off mat to main entrance door., Fabric, Other |  | 2400404 |  | TBC | 0 | 50000 | 50000 | 1
240129_452 | Lenasia, Link BMS to generator , BMS and EMS Systems | 2024-04-01 | 2024-04-30 | Continue | R.PR/2/09 | 77329X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Supported, | Lenasia, Link BMS to generator , BMS and EMS Systems |  | 2400166 |  | TBC | 0 | 50000 | 50000 | 1
240129_429 | Mafikeng CBD, Connection of the Teller work stations to UPS, | 2024-03-01 | 2024-03-01 | Continue | R.PR/2/04 | 77725X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Check with Planner | Mafikeng CBD, Connection of the Teller work stations to UPS, Electrical |  | 2400412 |  | TBC | 0 | 50000 | 50000 | 1
240129_297 | Mimosa Mall , New HVAC installation in the treasury area , N | 2024-03-08 | 2024-03-08 | Continue | R.PR/2/10 | 78545X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Running on R22 Gas, | Mimosa Mall , New HVAC installation in the treasury area , New assets |  | 2400424 |  | TBC | 0 | 50000 | 50000 | 1
240129_003 | Pharows House , Fresh Air/Extraction system , Mechanical | 2024-02-28 | 2024-03-03 | Continue | R.PR/2/05 | 77033X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project added by Tshamano , | Pharows House , Fresh Air/Extraction system , Mechanical |  | 2400222 |  | TBC | 0 | 50000 | 50000 | 1
240129_397 | Pinetown, Replacement of boom, Fabric, Other | 2024-02-19 | 2024-02-19 | Continue | R.PR/3/13 | 77102X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Pinetown, Replacement of boom, Fabric, Other |  | 2400444 |  | TBC | 0 | 50000 | 50000 | 1
240129_294 | Postmasburg, Install emergency lighting in the Branch., Elec | 2024-05-11 | 2024-05-11 | Continue | R.PR/2/04 | 21312X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | No emergency lighting at this branch, | Postmasburg, Install emergency lighting in the Branch., Electrical |  | 2400448 |  | TBC | 0 | 50000 | 50000 | 1
240129_408 | Quo Vadis Centre (Westonaria), replacement of shop front fro | 2024-04-01 | 2024-04-30 | Continue | R.PR/3/13 | 76563X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Quo Vadis Centre (Westonaria), replacement of shop front frosting, Fabric, Other |  | 2400167 |  | TBC | 0 | 50000 | 50000 | 1
240129_572 | Tshwane Market , MW-Replace Tiles in the branch with darker | 2024-09-01 | 2024-09-30 | Defer | R.PR/3/13 | 76514X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Tshwane Market , MW-Replace Tiles in the branch with darker colour tiles - dirty from bulk money, Repaint the entire branch, Replacement of carpet , Fabric, Other |  | 2400168 |  | TBC | 0 | 50000 | 50000 | 1
240129_556 | UOVS, Branch require new office: teller chairs, couches, 4 x | 2024-02-28 | 2024-02-28 | Under review | R.PR/3/13 | 78702X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | UOVS, Branch require new office: teller chairs, couches, 4 x chairs and a table for pause area, Fabric, Other |  | 2400476 |  | TBC | 0 | 50000 | 50000 | 1
240129_288 | Windermere, Replacement of HVAC in ATM room, Mechanical | 2024-06-06 | 2024-06-06 | Continue | R.PR/2/05 | 78193X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Condenser is corroded, | Windermere, Replacement of HVAC in ATM room, Mechanical |  | 2400485 |  | TBC | 0 | 50000 | 50000 | 1
240129_133 | Menlyn Maine, Menlyn Maine Addition of a 3rd Consultan, Fabr | 2023-08-03 | 2023-08-30 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Menlyn Maine, Menlyn Maine Addition of a 3rd Consultan, Fabric, Other | ASP-GN0218 | 0 |  | Complete | 49267.1615 | 0 | 49267.1615 | 1
240129_116 | Golden Walk Shopping Centre-Victoria St-Germiston, Golden Wa | 2023-10-30 | 2024-04-30 | Works Approved (2023) | R.PR/3/13 | 70623X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Project | Golden Walk Shopping Centre-Victoria St-Germiston, Golden Walk SC Install ATM signage, Fabric, Other | ASP-GS0677 |  |  | TBC | 49217 | 0 | 49217 | 1
240129_245 | Absa Daveyton , Replace external signage, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Daveyton , Replace external signage, Fabric, Other | ASP-GS0750 |  |  | Complete | 48537.0035 | 0 | 48537.0035 | 1
240129_069 | Alice Lane South, Replace Generator Batteries, Electrical | 2023-12-01 | 2023-12-20 | Works Approved (2023) | R.PR/1/04 | 35041X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Project Started and Not Completed in 2023, Rollover from CIP2023 | Alice lane South, Replace Generator Batteries, Electrical | ASP-GS0718 |  |  | TBC | 47175.44 | 0 | 47175.44 | 1
240129_335 | Christiana, Install paving around generator cage and water t | 2024-06-10 | 2024-06-13 | Continue | R.PR/3/05 | 79117X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Freehold building - Corporate / Engineering?, | Christiana, Install paving around generator cage and water tank, Fabric, Other |  | 2400378 |  | TBC | 0 | 45000 | 45000 | 1
240129_418 | Mountain Mill Shopping Centre, Install HVAC unit in the host | 2024-07-01 | 2024-07-20 | Continue | R.PR/2/05 | 77271X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Budget Adjusted as R25k bit low, No Objection to adjust Meeting 24 Nov | Mountain Mill Shopping Centre, Install HVAC unit in the hosting office, Mechanical | ASP-WC0356 | 2400318 |  | TBC | 0 | 45000 | 45000 | 1
240129_427 | Mountain Mill Shopping Centre, Install HVAC unit in the serv | 2024-07-01 | 2024-07-20 | Continue | R.PR/2/05 | 77271X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Budget Adjusted as R30k bit low, No Objection to adjust Meeting 24 Nov | Mountain Mill Shopping Centre, Install HVAC unit in the server room, Mechanical | ASP-WC0355 | 2400317 |  | TBC | 0 | 45000 | 45000 | 1
240129_078 | Absa Vryburg, External Signage , Fabric, Other | 2024-02-12 | 2023-02-12 | Works Approved (2023) | R.PR/3/13 | 77745X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Started and Not Completed in 2023, Project in Execution | Absa Vryburg, External Signage , Fabric, Other | ASP-CR0440 |  |  | TBC | 44934.07 | 0 | 44934.07 | 1
240131_008 | Absa Primrose Install of Roller Shutter | 2023-11-13 | 2023-12-21 | Works Complete (2023) | R.PR/3/13 | 70297X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Primrose Install of Roller Shutter | ASP-GS0757 |  |  | Complete | 43910.68 | 0 | 43910.68 | 1
240129_081 | Absa Kroonstad , Teller cash recycler Removal and replacemen | 2023-11-15 | 2023-11-20 | Works Complete (2023) | R.PR/3/13 | 37158X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Kroonstad , Teller cash recycler Removal and replacement, Fabric, Other | ASP-CR0461 | 0 |  | Complete | 43270.836 | 0 | 43270.836 | 1
240129_442 | Jan Kempdorp-De La Rey St-Jan Kempdorp, Replacement of an A | 2024-01-31 | 2024-01-31 | Continue | R.PR/2/05 | 78326X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Jan Kempdorp-De La Rey St-Jan Kempdorp, Replacement of an AC Split Unit in the Branch Manager's office, Mechanical |  | 2400254 |  | TBC | 0 | 42649.08 | 42649.08 | 1
240129_271 | Absa Pretoria Campus , HVAC - New Installation, Mechanical | 2023-05-04 | 2023-06-30 | Works Complete (2023) | R.PR/1/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , HVAC - New Installation, Mechanical | ASP-GN0189 | 0 |  | Complete | 42527.552 | 0 | 42527.552 | 1
240129_330 | Absa Wolmaransstad, Ground Floor, Absa Building, 18A Kruger St | 2024-03-18 | 2024-03-19 | Cancel | R.PR/2/04 | 77605X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Wolmaransstad Ground Floor, Absa Building 18A Kruger Street, Replacement of PC Boards & Installation of surge protection Absa Wolmaransstad is a leasehold branch situated in the North West Province. The branch reported that the air conditioning is not working and has been turned off completely. Portable units were provided as a temporary solution. This happened during a power outage in the area. The vendor went to the site to investigate and discovered that the PC boards in the air-conditioning units were burnt. According to the vendor, the damage to the PC boards was most likely caused by a power surge. There is currently no surge protection in the branch's main distribution board. Note: Supported by BFM Engineering. No GMP Cost Impact, only components will be replaced. Scope of Work • Replace PC Boards in DVR, Server Room, Manager's Office & ATM Room as required.(x8) • Supply & install Type 3 surge protector as required (x1). • Electrical COC will be issued upon completion., Electrical |  | 2400356 |  | TBC | 0 | 42380.4 | 42380.4 | 1
240129_142 | Diepsloot , Diepsloot Bulk Teller Upgrade, Fabric, Other | 2023-08-25 | 2023-09-25 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Diepsloot , Diepsloot Bulk Teller Upgrade, Fabric, Other | ASP-GN0221 | 0 |  | Complete | 41923.227 | 0 | 41923.227 | 1
240129_436 | Absa Kamaqhekeza, Replacement of indoor PC Board and insta | 2024-01-17 | 2024-01-18 | Continue | R.PR/2/04 | 77571X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Absa Kamaqhekeza , Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | 2400250 |  | TBC | 0 | 41821.55 | 41821.55 | 1
240129_434 | Absa Eden Square, Replacement of indoor PC Board and instal | 2024-01-22 | 2024-01-23 | Continue | R.PR/2/04 | 76709X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Absa Eden Square, Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | 2400248 |  | TBC | 0 | 40338.58 | 40338.58 | 1
240129_350 | 116 Main Road Somerset West, Replace the shade cloth in Park | 2024-07-01 | 2024-07-20 | Continue | R.PR/3/13 | 77702X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Supported - Broll to be engaged re LL responsibility, | 116 Main Road Somerset West, Replace the shade cloth in Parking Area (Is this not Landlord Responsibility), Double Bay?, Fabric, Other | ASP-WC0343 | 2400313 |  | TBC | 0 | 40000 | 40000 | 1
240129_354 | Absa 17A Joubert Street, Connection of various work stations | 2024-03-18 | 2024-03-18 | Continue | R.PR/2/04 | 78841X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa 17A Joubert Street, Connection of various work stations to UPS, Electrical |  | 2400337 |  | TBC | 0 | 40000 | 40000 | 1
240129_351 | Austin Crossing Centre, Connection of various work stations | 2024-05-10 | 2024-05-10 | Continue | R.PR/2/04 | 77150X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Austin Crossing Centre, Connection of various work stations to UPS, Electrical |  | 2400358 |  | TBC | 0 | 40000 | 40000 | 1
240129_334 | Hartswater, Connection of various work stations to UPS, Elec | 2024-03-11 | 2024-03-11 | Continue | R.PR/2/04 | 78684X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Hartswater, Connection of various work stations to UPS, Electrical |  | 2400393 |  | TBC | 0 | 40000 | 40000 | 1
240129_377 | Orkney, Installation of extractor fans in the bathrooms, Mec | 2024-05-17 | 2024-05-17 | Continue | R.PR/2/05 | 77962X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Orkney, Installation of extractor fans in the bathrooms, Mechanical |  | 2400435 |  | TBC | 0 | 40000 | 40000 | 1
240129_333 | Phuthaditjhaba Shopping Centre, Connection of various work s | 2024-03-19 | 2024-03-19 | Continue | R.PR/2/04 | 78615X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Phuthaditjhaba Shopping Centre, Connection of various work stations to UPS, Electrical |  | 2400442 |  | TBC | 0 | 40000 | 40000 | 1
240129_082 | Absa Nkandla, Replacement of floor tiles and carpets, provis | 2023-11-27 | 2023-12-08 | Works Complete (2023) | R.PR/3/13 | 77968X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Nkandla, Replacement of floor tiles and carpets, provision of 2x consultant desks, Fabric, Other | ALP-KZ2003 | 0 |  | Complete | 39997.782 | 0 | 39997.782 | 1
240129_120 | Mount Frere, UPS Service Replacement Unit (Not Part of CIP), | 2023-12-05 | 2024-01-31 | Works Complete (2023) | R.PR/2/04 | 78953X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023 | Mount Frere, UPS Service Replacement Unit (Not Part of CIP), Electrical | ASP-EC0375 | 0 |  | Complete | 38865.2 | 0 | 38865.2 | 1
240129_121 | Absa Pretoria Campus , Replace damaged tar, Fabric, Other | 2023-06-25 | 2023-07-16 | Works Complete (2023) | R.PR/3/05 | 22491X & 35038X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Replace damaged tar, Fabric, Other | ASP-GN0207 | 0 |  | Complete | 38544.504 | 0 | 38544.504 | 1
240129_130 | Cradock, Installation of Noise Attentuators, Fabric, Other | 2023-07-26 | 2023-08-15 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Cradock, Installation of Noise Attentuators, Fabric, Other | ASP-GS0688 | 0 |  | Complete | 38216.501 | 0 | 38216.501 | 1
240129_136 | Absa Pretoria Campus , Supply 2 X TV Screens, Fabric, Other | 2023-06-06 | 2023-06-30 | Works Complete (2023) | R.PR/3/05 | 22491X & 35038X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Supply 2 X TV Screens, Fabric, Other | ASP-GN0224 | 0 |  | Complete | 37467 | 0 | 37467 | 1
240129_113 | Absa Keywest, Supply and Install a Compatible, Fabric, Other | 2023-04-12 | 2023-12-07 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Keywest, Supply and Install a Compatible, Fabric, Other | ASP-GN0187 | 0 |  | Complete | 36895.151 | 0 | 36895.151 | 1
240129_235 | Lea Glen Stores, Replacement of gutters, Fabric, Other | 2023-06-30 | 2023-07-15 | Works Complete (2023) | R.PR/3/05 | 76949X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Lea Glen Stores, Replacement of gutters, Fabric, Other | ASP-GS0680 | 0 |  | Complete | 35805.8595 | 0 | 35805.8595 | 1
240129_219 | Absa Trompsburg , Installation of Mid wall split Unit, Mecha | 2023-10-24 | 2023-10-25 | Works Complete (2023) | R.PR/2/05 | 79334X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Trompsburg , Installation of Mid wall split Unit, Mechanical | ASP-CR0472 | 0 |  | Complete | 35800.65 | 0 | 35800.65 | 1
240129_241 | Tsakane Mall, New 12 000Btu/h Inverter Mi, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Tsakane Mall , New 12 000Btu/h Inverter Mi, Electrical | ASP-GS0556 |  |  | Complete | 35435.893 | 0 | 35435.893 | 1
240129_268 | Alice Lane North , Upgrade Power Monitoring, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/04 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane North , Upgrade Power Monitoring, Electrical | ASP-GS0632 |  |  | Complete | 35208.4 | 0 | 35208.4 | 1
240129_577 | Bridge Park Bridgeway Century City, Way finder Client suite | 2024-03-01 | 2024-03-15 | Cancel | R.PR/3/05 | 36225X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | As per Hanlie Louw email 9-Feb-24, project can be surrendered (Give Back) it is no longer needed | Bridge Park Bridgeway Century City, Way finder Client suite Area (Monitor for Condeco), Fabric, Other | ASP-WC0352 | 2400314 |  | TBC | 0 | 35000 | 35000 | 1
240129_215 | Ntabankulu, HVAC and Cages (Not Part of CIP), Mechanical | 2023-06-19 | 2024-01-31 | Works Approved (2023) | R.PR/2/05 | 20949X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023 | Ntabankulu, HVAC and Cages (Not Part of CIP), Mechanical | ASP-EC0278 |  |  | TBC | 34804.975 | 0 | 34804.975 | 1
240129_198 | Absa Britz Mall , Install of midwall Split Unit, New assets | 2023-11-16 | 2023-11-17 | Works Complete (2023) | R.PR/2/10 | 22864X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Britz Mall , Install of midwall Split Unit, New assets | ASP-CR0499 |  |  | Complete | 34071.97 | 0 | 34071.97 | 1
240131_016 | Absa Orkney - PC Board Replacement | 2023-07-10 | 2023-12-18 | Works Complete (2023) | R.PR/2/04 | 71304X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Orkney - PC Board Replacement | ASP-CR0518 |  |  | Complete | 33896.894 | 0 | 33896.894 | 1
240129_279 | Auckland Park, Installation of Greywater bypass pipe, Water | 2023-08-08 | 2023-10-30 | Works Complete (2023) | R.PR/1/07 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Installation of Greywater bypass pipe, Water & Systems | ASP-GS0730 | 0 |  | Complete | 33432.5585 | 0 | 33432.5585 | 1
240129_437 | Absa Jane Furse, Replacement of indoor PC Board and install | 2024-01-22 | 2024-01-23 | Continue | R.PR/2/04 | 76783X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Absa Jane Furse, Replacement of indoor PC Board and installation of type +2 Surge Protection, Electrical |  | 2400252 |  | TBC | 0 | 32660.43 | 32660.43 | 1
240129_052 | Thohoyadou West, Replace all HVAC equip, Electrical | 2023-11-22 | 2023-11-23 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Thohoyadou West , Replace all HVAC equip, Electrical | ALP-LP0001 | 0 |  | Complete | 30855.73 | 0 | 30855.73 | 1
240129_252 | Protea Glen, New Generator off MW Budget, Mechanical | 2023-01-13 | 2023-01-30 | Works Complete (2023) | R.PR/2/05 | 77381X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Protea Glen, New Generator off MW Budget, Mechanical | ALP-GS0046 | 0 |  | Complete | 30353.4105 | 0 | 30353.4105 | 1
240129_355 | Absa Bank Mafikeng CBD, Connection of various work stations | 2024-05-20 | 2024-05-20 | Continue | R.PR/2/04 | 77725X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Bank Mafikeng CBD, Connection of various work stations to UPS, Electrical |  | 2400341 |  | TBC | 0 | 30000 | 30000 | 1
240129_010 | Absa Pretoria Campus, Gas cage and 2X9 kg cylinders, Fabric, | 2024-03-01 | 2024-03-30 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Newly added budget required 30K, | Absa Pretoria Campus, Gas cage and 2X9 kg cylinders, Fabric, Other |  | 2400090 |  | TBC | 0 | 30000 | 30000 | 1
240129_539 | Absa Towers North (Retail), Evacuation door at kitchen, req | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 77381X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana comment, | Absa Towers North (Retail), Evacuation door at kitchen, requires a ramp for wheel chair access ( evac chair), Fabric, Other |  | 2400178 |  | TBC | 0 | 30000 | 30000 | 1
240129_450 | Absa Vryburg, Drilling of holes to allow rain water drainage | 2024-02-26 | 2024-02-27 | Continue | R.PR/2/05 | 77745X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | RFQ in progress , | Absa Vryburg, Drilling of holes to allow rain water drainage, Mechanical |  | 2400245 |  | TBC | 0 | 30000 | 30000 | 1
240129_362 | Bisho Seda Building, Drip tray for x2 ATM room with water pu | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 36267X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Bisho Seda Building, Drip tray for x2 ATM room with water pump, Mechanical | ASP-EC0397 | 2400315 |  | TBC | 0 | 30000 | 30000 | 1
240129_502 | Boitekong Mall, New Installation of filtration system for th | 2024-02-05 | 2024-02-05 | Continue | R.PR/2/10 | 22485X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Boitekong Mall, New Installation of filtration system for the hydroboilers, New assets |  | 2400367 |  | TBC | 0 | 30000 | 30000 | 1
240129_423 | Bridge Park Bridgeway Century City, Shower rooftop - Replace | 2024-04-15 | 2024-05-15 | Continue | R.PR/3/05 | 36225X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Bridge Park Bridgeway Century City, Shower rooftop - Replace Chipped Stone , Fabric, Other | ASP-WC0353 | 2400316 |  | TBC | 0 | 30000 | 30000 | 1
240129_428 | Harrismith, Connecting customer service and teller to UPS, E | 2024-02-12 | 2024-02-12 | Continue | R.PR/2/04 | 78625X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Check if not Done with revamp | Harrismith, Connecting customer service and teller to UPS, Electrical |  | 2400392 |  | TBC | 0 | 30000 | 30000 | 1
240129_504 | Jubilee Mall, Water filtration System, Water and System | 2024-06-01 | 2024-06-30 | Continue | R.PR/2/07 | 35109X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Jubilee Mall, Water filtration System, Water and System |  | 2400180 |  | TBC | 0 | 30000 | 30000 | 1
240129_501 | Lichtenburg, New Installation of filtration system for the h | 2024-02-12 | 2024-02-12 | Continue | R.PR/2/10 | 77806X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Lichtenburg, New Installation of filtration system for the hydroboilers, New assets |  | 2400410 |  | TBC | 0 | 30000 | 30000 | 1
240129_500 | Mafikeng CBD, New Installation of filtration system for the | 2024-02-19 | 2024-02-19 | Continue | R.PR/2/10 | 77725X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Mafikeng CBD, New Installation of filtration system for the hydroboilers, New assets |  | 2400413 |  | TBC | 0 | 30000 | 30000 | 1
240129_498 | Mega City, New Installation of filtration system for the hyd | 2024-03-04 | 2024-03-04 | Continue | R.PR/2/10 | 77784X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Mega City, New Installation of filtration system for the hydroboilers, New assets |  | 2400421 |  | TBC | 0 | 30000 | 30000 | 1
240129_499 | Mmabatho Crossings (Mafikeng), New Installation of filtratio | 2024-02-26 | 2024-02-26 | Continue | R.PR/2/10 | 22197X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Mmabatho Crossings (Mafikeng), New Installation of filtration system for the hydroboilers, New assets |  | 2400415 |  | TBC | 0 | 30000 | 30000 | 1
240129_503 | Renbro Shopping Centre, Water filtration System (smaller sys | 2024-09-01 | 2024-09-30 | Continue | R.PR/2/07 | 37152X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Renbro Shopping Centre, Water filtration System (smaller system), Water and System |  | 2400181 |  | TBC | 0 | 30000 | 30000 | 1
240129_554 | Sunward Park Lifestyle Centre, Change the door so it opens t | 2024-06-01 | 2024-06-01 | Cancel | R.PR/3/13 | 36299X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Supported by Ilana, | Sunward Park Lifestyle Centre, Change the door so it opens towards inside (pause area and ablutions), Fabric, Other |  | 2400182 |  | TBC | 0 | 30000 | 30000 | 1
240129_399 | Taung, Install paving around generator cage, Fabric, Other | 2024-07-26 | 2024-07-28 | Continue | R.PR/3/13 | 79227X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Taung, Install paving around generator cage, Fabric, Other |  | 2400463 |  | TBC | 0 | 30000 | 30000 | 1
240129_497 | Zeerust, New Installation of filtration system for the hydro | 2024-03-04 | 2024-03-04 | Continue | R.PR/2/10 | 21941X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | TBC | Zeerust, New Installation of filtration system for the hydroboilers, New assets |  | 2400487 |  | TBC | 0 | 30000 | 30000 | 1
240129_107 | Central City Shopping Centre Mabopane, Construction of New o | 2023-04-12 | 2023-04-30 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Central City Shopping Centre Mabopane, Construction of New office and Boardroom, Fabric, Other | ASP-GN0140 | 0 |  | Complete | 29292.6505 | 0 | 29292.6505 | 1
240129_123 | Rayton Park Plaza, Rayton Park Plaza Minor Works, Fabric, Ot | 2023-07-05 | 2023-07-30 | Works Complete (2023) | R.PR/3/13 | 78058X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Rayton Park Plaza, Rayton Park Plaza Minor Works, Fabric, Other | ASP-GN0209 | 0 |  | Complete | 28674.3415 | 0 | 28674.3415 | 1
240129_223 | Vincent Office Park, Connect HVAC to Generator, Mechanical | 2023-11-15 | 2023-11-17 | Works Complete (2023) | R.PR/1/05 | 79369X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023 | Vincent Office Park, Connect HVAC to Generator, Mechanical | ASP-EC0370 | 0 |  | Complete | 28357.98 | 0 | 28357.98 | 1
240129_233 | 270 Republic Road, Installation of a Swing (Fire) Door, Fire | 2023-07-05 | 2023-08-30 | Works Complete (2023) | R.PR/3/05 | 21334X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | 270 Republic Road, Installation of a Swing (Fire) Door, Fire | ASP-GS0692 | 0 |  | Complete | 27774.7195 | 0 | 27774.7195 | 1
240129_187 | Various Sites, UPS Batteries, Electrical #PO C000060051 | 2023-02-23 | 2024-01-31 | Works Complete (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, UPS Batteries, Electrical | ALP-N00035 | 0 |  | Complete | 25380.5 | 0 | 25380.5 | 1
240129_400 | Tubatse Crossing, Replace Vinyl tiles in Server room, Fabric | 2024-05-11 | 2024-05-13 | Continue | R.PR/3/13 | 35151X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Tubatse Crossing, Replace Vinyl tiles in Server room, Fabric, Other |  | 2400472 |  | TBC | 0 | 25000 | 25000 | 1
240129_243 | 268 Republic Rd , Fire systems and evacuation, Fire | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/06 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | 268 Republic Rd , Fire systems and evacuation, Fire | ASP-GS0558 |  |  | Complete | 24624.191 | 0 | 24624.191 | 1
240129_207 | Alice Lane South , Replace cushions or reu, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane South , Replace cushions or reu, Fabric, Other | ASP-GS0597 |  |  | Complete | 24290.3 | 0 | 24290.3 | 1
240129_575 | Absa Towers West, Prepare and Respray cold room , Fabric, Ot | 2024-03-01 | 2024-03-30 | Cancel | R.PR/3/05 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Absa Towers West, Prepare and Respray cold room , Fabric, Other |  | 2400186 |  | TBC | 0 | 24150 | 24150 | 1
240129_089 | Vincent Office Park, Interleading Door - Ablutions + Tiles U | 2023-11-08 | 2023-11-10 | Works Complete (2023) | R.PR/3/05 | 79369X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Project Completed and not invoiced in 2023 | Vincent Office Park, Interleading Door - Ablutions + Tiles Under Fridges (X3) (Not Part of CIP), Fabric, Other | ASP-EC0340 | 0 |  | Complete | 23807.99 | 0 | 23807.99 | 1
240129_209 | Alice Lane North , Coffee bar door repla, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane North , Coffee bar door repla, Fabric, Other | ASP-GS0587 |  |  | Complete | 21976.8565 | 0 | 21976.8565 | 1
240129_205 | Alice Lane Towers, Kitchen Plumbing Repair, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane Towers, Kitchen Plumbing Repair, Fabric, Other | ASP-GS0511 |  |  | Complete | 21742.2795 | 0 | 21742.2795 | 1
240129_216 | Various Retail Sites, Various EC- Generator starter batteries, Elec | 2023-07-26 | 2024-01-31 | Works Approved (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Project in progress | Various Sites, Various EC- Generator starter batteries, Electrical | ASP-N00057 |  |  | TBC | 21702.7475 | 0 | 21702.7475 | 1
240129_517 | Meadowdale, Replacement of Generator starter batteries, Elec | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/04 | 37006X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Roll over to 2yr programme, | Meadowdale, Replacement of Generator starter batteries, Electrical |  | 2400188 |  | TBC | 0 | 21600 | 21600 | 1
240129_261 | Absa Pretoria Campus , Install new manhole, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/1/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Install new manhole, Mechanical | ASP-GN0157 |  |  | Complete | 20865.6 | 0 | 20865.6 | 1
240129_117 | The Boulders, The Boulders Shopping Centre Minor Works, Fabr | 2023-06-09 | 2023-07-07 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | The Boulders, The Boulders Shopping Centre Minor Works, Fabric, Other | ASP-GN0197 | 0 |  | Complete | 20705.152 | 0 | 20705.152 | 1
240129_140 | Absa Keywest, Key West Install vinyl marketing poster, Fabri | 2023-08-15 | 2024-02-15 | Works Approved (2023) | R.PR/3/13 | 22890X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Started and Not Completed in 2023, Rollover-Project | Absa Keywest, Key West Install vinyl marketing poster, Fabric, Other | ASP-GN0222 |  |  | TBC | 20463.3415 | 0 | 20463.3415 | 1
240129_193 | Absa Towers North, Exterior Wall Tiles Polish, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers North, Exterior Wall Tiles Polish, Fabric, Other | ASP-GS0467 |  |  | Complete | 20312.1625 | 0 | 20312.1625 | 1
240129_283 | 268 Republic Road, Replacement Generator Batteries, Electric | 2023-10-05 | 2023-11-30 | Works Complete (2023) | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | 268 Republic Road, Replacement Generator Batteries, Electrical | ASP-GS0752 | 0 |  | Complete | 20213.6535 | 0 | 20213.6535 | 1
240129_438 | Absa Kuruman, Replacement of Motor Gate, Electrical | 2024-01-30 | 2024-01-30 | Continue | R.PR/2/04 | 78504X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | OOC Request, funding issue , | Absa Kuruman, Replacement of Motor Gate, Electrical |  | 2400255 |  | TBC | 0 | 20156.74 | 20156.74 | 1
240129_238 | Cradlestone, Cradlestone Relocation of the Forex scr, Fabri | 2023-08-03 | 2023-12-30 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Cradlestone, Cradlestone Relocation of the Forex scr, Fabric, Other | ASP-GN0217 | 0 |  | Complete | 20046.9035 | 0 | 20046.9035 | 1
240129_356 | Absa Koster, Installation of plug points in the ATM and trea | 2024-06-13 | 2024-06-13 | Continue | R.PR/2/04 | 77546X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Koster, Installation of plug points in the ATM and treasury, Electrical |  | 2400347 |  | TBC | 0 | 20000 | 20000 | 1
240129_576 | Absa Pretoria Campus, Wellness Centre Upgrade, Fabric, Other | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/05 | 22491X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | TBC | Absa Pretoria Campus, Wellness Centre Upgrade, Fabric, Other |  | 2400169 |  | TBC | 0 | 20000 | 20000 | 1
240129_401 | Sannieshof, Burglar bar door add at vault, Fabric, Other | 2024-06-11 | 2024-06-12 | Continue | R.PR/3/13 | 77996X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | To proceed as per Ilana comment., | Sannieshof, Burglar bar door add at vault, Fabric, Other |  | 2400458 |  | TBC | 0 | 20000 | 20000 | 1
240129_234 | 270 Republic Road, Minor Works - Signage, blinds and paintin | 2023-07-05 | 2023-08-30 | Works Complete (2023) | R.PR/3/05 | 21334X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | 270 Republic Road, Minor Works - Signage, blinds and painting, Fabric, Other | ASP-GS0650 | 0 |  | Complete | 19503.8735 | 0 | 19503.8735 | 1
240129_246 | Absa Rosstax, DD - security entrance door, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Rosstax, DD - security entrance door, Fabric, Other | ASP-GN0220 |  |  | Complete | 19481 | 0 | 19481 | 1
240129_125 | Absa Monument Park, Absa Monument Park "Spray Paint Ceilings | 2023-07-11 | 2023-07-30 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Monument Park, Absa Monument Park "Spray Paint Ceilings, Fabric, Other | ASP-GN0210 | 0 |  | Complete | 19029.786 | 0 | 19029.786 | 1
240129_232 | Auckland Park, Renovations to Fish Bow, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Auckland Park, Renovations to Fish Bow, Fabric, Other | ALP-GS0053 |  |  | Complete | 18674.4475 | 0 | 18674.4475 | 1
240129_188 | Southgate Mall , ATM Room, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Southgate Mall , ATM Room, Fabric, Other | ASP-GS0518 |  |  | Complete | 17926.085 | 0 | 17926.085 | 1
240129_177 | Fochville, Carpet Replacement and Painting, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Fochville, Carpet Replacement and Painting, Fabric, Other | ASP-GS0468 |  |  | Complete | 17831.624 | 0 | 17831.624 | 1
240129_141 | Alice lane South, Installation of Wireless Charging, Fabric, | 2023-08-23 | 2023-10-26 | Works Complete (2023) | R.PR/3/09 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane South, Installation of Wireless Charging, Fabric, Audio Visual | ASP-GS0732 | 0 |  | Complete | 17324.175 | 0 | 17324.175 | 1
240131_004 | Towers West Supply and Install new TV sc | 2022-11-24 | 2023-12-14 | Works Complete (2023) | R.PR/3/09 | 21526X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Towers West Supply and Install new TV sc | ASP-GS0583 |  |  | Complete | 16738.25 | 0 | 16738.25 | 1
240129_178 | Alice Lane, Minor works block out blinds, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane, Minor works block out blinds, Fabric, Other | ASP-GS0480 |  |  | Complete | 16651.149 | 0 | 16651.149 | 1
240131_011 | 20 Goldman Street Florida, Install frosting vinyl | 2023-11-10 | 2023-12-21 | Works Complete (2023) | R.PR/3/13 | 70027X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | 20 Goldman Str - Install frosting vinyl | ASP-GS0763 |  |  | Complete | 15802.219 | 0 | 15802.219 | 1
240129_363 | Absa Aliwal North, Drip tray for HVAC in server room with wa | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 79209X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Aliwal North, Drip tray for HVAC in server room with water pump, Mechanical | ASP-EC0393 | 2400319 |  | TBC | 0 | 15000 | 15000 | 1
240129_364 | Absa Cofimvaba, Drip tray for HVAC in server room with water | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 78540X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Cofimvaba, Drip tray for HVAC in server room with water pump, Mechanical | ASP-EC0395 | 2400320 |  | TBC | 0 | 15000 | 15000 | 1
240129_365 | Absa Ntabankulu, Drip tray for HVAC in server room with wate | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 20949X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Absa Ntabankulu, Drip tray for HVAC in server room with water pump, Mechanical | ASP-EC0396 | 2400321 |  | TBC | 0 | 15000 | 15000 | 1
240129_417 | Absa Settles Square Greenfields, Drip tray for HVAC in serve | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 79189X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | 27 Nov - Mail From TSM - No longer required. | Absa Settles Square Greenfields, Drip tray for HVAC in server room with water pump, Mechanical | ASP-EC0400 | 2400322 |  | TBC | 0 | 15000 | 15000 | 1
240129_347 | Absa Vredendal, Bumper Rails to be installed, Fabric, Other | 2024-04-01 | 2024-04-20 | Continue | R.PR/3/13 | 78130X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Ilana Comment - Proceed, | Absa Vredendal, Bumper Rails to be installed, Fabric, Other | ASP-WC0347 | 2400323 |  | TBC | 0 | 15000 | 15000 | 1
240129_366 | Newton Park, Drip tray for HVAC in server room with water pu | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 76387X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Newton Park, Drip tray for HVAC in server room with water pump, Mechanical | ASP-EC0398 | 2400324 |  | TBC | 0 | 15000 | 15000 | 1
240129_367 | Rhino Centre Lusikisiki, Drip tray for HVAC in server room w | 2024-03-15 | 2024-04-20 | Continue | R.PR/2/05 | 70631X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | TBC | Rhino Centre Lusikisiki, Drip tray for HVAC in server room with water pump, Mechanical | ASP-EC0399 | 2400325 |  | TBC | 0 | 15000 | 15000 | 1
240129_126 | Alice lane South, Installation of Glass Panel Vinyl on the 3 | 2023-10-10 | 2023-10-20 | Works Complete (2023) | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane South, Installation of Glass Panel Vinyl on the 3rd-floor Legal Area, Fabric, Other | ASP-GS0709 | 0 |  | Complete | 13856.81 | 0 | 13856.81 | 1
240129_197 | Various Sites, Generator Stater Battries, Electrical | 2022-05-19 | 2024-01-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets | No | Project Completed and not invoiced in 2023, POC In progress | Various Sites, Generator Stater Battries, Electrical | ASP-N00057 | 0 |  | Complete | 13589.6465 | 0 | 13589.6465 | 1
240129_250 | Dobsonville, Hygiene survey, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Dobsonville, Hygiene survey, Fabric, Other | ASP-GS0747 |  |  | Complete | 13564.25 | 0 | 13564.25 | 1
240129_208 | Norwood Mall , Carpet replacement through, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Norwood Mall , Carpet replacement through, Fabric, Other | ASP-GS0421 |  |  | Complete | 12882.139 | 0 | 12882.139 | 1
240129_137 | Absa Siyabuswa Mall , Minor Works, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | 36259X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Siyabuswa Mall , Minor Works, Fabric, Other | ASP-MP0163 |  |  | Complete | 12862.2555 | 0 | 12862.2555 | 1
240129_222 | Absa Pretoria Campus , 14 X Door Seal, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , 14 X Door Seal, Fabric, Other | ASP-GN0191 |  |  | Complete | 12431.454 | 0 | 12431.454 | 1
240129_118 | Absa Postmasburg, Cosmetic Upgrade, Fabric, Other | 2023-05-05 | 2023-05-22 | Works Complete (2023) | R.PR/3/13 | 21312X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Postmasburg, Cosmetic Upgrade, Fabric, Other | ALP-CR0032 |  |  | Complete | 11567.9305 | 0 | 11567.9305 | 1
240129_264 | Trade route mall, UPS Power dedicated plug, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Trade route mall- , UPS Power dedicated plug, Electrical | ASP-GS0622 |  |  | Complete | 11456.3 | 0 | 11456.3 | 1
240129_225 | Absa Mimosa Mall, Connecting Teller computes to UPS, Electr | 2023-11-29 | 2023-11-30 | Works Complete (2023) | R.PR/2/04 | 78545X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Mimosa Mall, Connecting Teller computes to UPS, Electrical | ASP-CR0443 | 0 |  | Complete | 10460.98 | 0 | 10460.98 | 1
240129_128 | Absa Spar Centre Lydenburg , Minor Works, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | 77360X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Spar Centre Lydenburg , Minor Works, Fabric, Other | ASP-MP0154 |  |  | Complete | 10424.9225 | 0 | 10424.9225 | 1
240129_095 | Burgersdorp, Connect DVR to UPS (Not Part of CIP), Electric | 2023-11-08 | 2023-11-08 | Works Complete (2023) | R.PR/2/04 | 79098X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, | Burgersdorp, Connect DVR to UPS (Not Part of CIP), Electrical | ASP-EC0371 | 0 |  | Complete | 9748.15 | 0 | 9748.15 | 1
240129_200 | Absa Mimosa Mall , Connect Teller computer to UPS, New asset | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/10 | 78545X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Mimosa Mall , Connect Teller computer to UPS, New assets | ASP-CR0519 |  |  | Complete | 9509.9825 | 0 | 9509.9825 | 1
240129_192 | 20 Goldman Street Florida, Kitchen, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | 70027X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | 20 Goldman Street Florida , Kitchen, Fabric, Other | ASP-GS0544 |  |  | Complete | 8628.128 | 0 | 8628.128 | 1
240129_147 | Absa Durban North, Close off 2x teller counters with blinds, | 2023-11-23 | 2023-11-24 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Durban North, Close off 2x teller counters with blinds, Fabric, Other | ASP-KZ0263 | 0 |  | Complete | 8579 | 0 | 8579 | 1
240129_270 | Greenstone Mall, Supply and install 3 add, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Greenstone Mall, Supply and install 3 add, Electrical | ASP-GS0630 |  |  | Complete | 8312.982 | 0 | 8312.982 | 1
240129_176 | Highlands Warehouse, Boundary Wall Repai, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Highlands Warehouse, Boundary Wall Repai, Fabric, Other | ASP-GS0512 |  |  | Complete | 8050 | 0 | 8050 | 1
240129_410 | Jubilee Mall, Walk off mat at front entrance , Fabric, Other | 2024-09-01 | 2024-09-30 | Continue | R.PR/3/13 | 35109X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | to proceed as per Ilana comments, | Jubilee Mall, Walk off mat at front entrance , Fabric, Other |  | 2400190 |  | TBC | 0 | 8000 | 8000 | 1
240129_262 | Tsakane Mall, Install 24000 BTU, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Tsakane Mall , Install 24000 BTU, Electrical | ASP-GS0613 |  |  | Complete | 6721.06 | 0 | 6721.06 | 1
240129_274 | Sanridge Square, Sanridge SquareSupply and install a drip, M | 2024-02-15 | 2024-03-15 | Works Approved (2023) | R.PR/2/05 | 21861X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  | 0 | Project Started and Not Completed in 2023, Rollover-Project | Sanridge Square, Sanridge SquareSupply and install a drip, Mechanical | ASP-GN0193 |  |  | TBC | 6168.84 | 0 | 6168.84 | 1
240129_228 | Northmead Square , MW-Carpet replacement,, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Northmead Square , MW-Carpet replacement,, Fabric, Other | ASP-GS0655 |  |  | Complete | 6142.3915 | 0 | 6142.3915 | 1
240131_003 | Olievenhoutbosch Plaza Connect ATM to LL | 2022-08-01 | 2023-09-15 | Works Complete (2023) | R.PR/2/04 | 70195X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project Completed and not invoiced in 2023, POC In progress | Olievenhoutbosch Plaza Connect ATM to LL | ASP-GN0152 |  |  | Complete | 6076.31 | 0 | 6076.31 | 1
240129_237 | 270 Republic Road , INSOG Power points for, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | 21334X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | 270 Republic Road , INSOG Power points for, Electrical | ASP-GS0522 |  |  | Complete | 5908.286 | 0 | 5908.286 | 1
240129_229 | Springs Mall, Close off 1 x teller counter, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Springs Mall, Close off 1 x teller counter, Fabric, Other | ASP-GS0669 |  |  | Complete | 5306.1 | 0 | 5306.1 | 1
240129_242 | Highlands Warehouse , RT SYSTEMS, BMS and EMS Systems | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/09 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Highlands Warehouse , RT SYSTEMS, BMS and EMS Systems | ASP-GS0555 |  |  | Complete | 5175 | 0 | 5175 | 1
240129_273 | The Grove, Drip Tray, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | The Grove, Drip Tray, Mechanical | ASP-GS0646 |  |  | Complete | 4562.9125 | 0 | 4562.9125 | 1
240129_184 | Birch acres, Minor works, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Birch acres, Minor works, Fabric, Other | ASP-GS0473 |  |  | Complete | 4302.8745 | 0 | 4302.8745 | 1
240129_112 | Absa 18 Swapo Street, Installation of Blinds, Fabric, Other | 2023-11-22 | 2023-11-23 | Works Complete (2023) | R.PR/3/13 | 77409X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa 18 Swapo Street, Installation of Blinds, Fabric, Other | ASP-KZ0225 | 0 |  | Complete | 4095.012 | 0 | 4095.012 | 1
240129_240 | Carnival Mall , Replacement Server Room Mi, Electrical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Carnival Mall , Replacement Server Room Mi, Electrical | ASP-GS0520 |  |  | Complete | 4068.1595 | 0 | 4068.1595 | 1
240129_119 | Colesburg, Replace Kitchen&bathroom, Fabric, Other | 2023-11-22 | 2023-11-23 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Colesburg, Replace Kitchen&bathroom, Fabric, Other | ASP-CR0393 | 0 |  | Complete | 3509.94 | 0 | 3509.94 | 1
240129_248 | Absa Southdale , Close off Tellers, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Southdale , Close off Tellers, Fabric, Other | ASP-GS0759 |  |  | Complete | 3509.938 | 0 | 3509.938 | 1
240129_251 | Sunnypark , Supply new decal, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Sunnypark , Supply new decal, Fabric, Other | ASP-GN0117 |  |  | Complete | 3405.61 | 0 | 3405.61 | 1
240129_161 | Absa Mooi River Mall, Supply of (2x) leather couches on the | 2023-11-15 | 2024-01-30 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Mooi River Mall, Supply of (2x) leather couches on the ground floor and installation of graphics on the first floor. , Fabric, Other | ASP-CR0478 | 0 |  | Complete | 3400.0035 | 0 | 3400.0035 | 1
240129_266 | Alex plaza, Supply and install drip tray, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alex plaza, Supply and install drip tray, Mechanical | ASP-GN0184 |  |  | Complete | 3347.42 | 0 | 3347.42 | 1
240129_272 | Park Station , Supply and install a drip, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Park Station , Supply and install a drip, Mechanical | ASP-GS0645 |  |  | Complete | 3347.42 | 0 | 3347.42 | 1
240129_281 | Absa Towers West, Repair Faulty Switcher , Electrical | 2023-07-25 | 2023-08-08 | Under review | R.PR/1/04 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | No | Project Started and Not Completed in 2023, Rollover-Financial | Absa Towers West , Repair Faulty Switcher , Electrical | ASP-GS0736 |  |  | TBC | 3285.09 | 0 | 3285.09 | 1
240129_189 | Oakfields , Replacement of decal, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Oakfields , Replacement of decal, Fabric, Other | ASP-GS0527 |  |  | Complete | 3210.064 | 0 | 3210.064 | 1
240129_183 | Meyerton, Bolts and Tiling at ATM Room, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Meyerton, Bolts and Tiling at ATM Room, Fabric, Other | ASP-GS0472 |  |  | Complete | 3162.5 | 0 | 3162.5 | 1
240129_190 | Absa Pretoria Campus , Installation of a new ra, Fabric, Oth | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Pretoria Campus , Installation of a new ra, Fabric, Other | ASP-GS0539 |  |  | Complete | 3139.5 | 0 | 3139.5 | 1
240129_111 | Koster, External Refurbishment, Fabric, Other | 2023-11-22 | 2023-11-23 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Koster, External Refurbishment, Fabric, Other | ASP-CR0425 | 0 |  | Complete | 3061.33 | 0 | 3061.33 | 1
240131_012 | Absa Bloemfontein Forum-Additional plugs | 2023-07-10 | 2023-12-18 | Works Complete (2023) | R.PR/2/04 | 71476X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | Project Completed and not invoiced in 2023, POC In progress | Absa Bloemfontein Forum-Additional plugs | ASP-CR0456 |  |  | Complete | 2809.39 | 0 | 2809.39 | 1
240129_122 | Absa Wibsa Upington , Paint Walls CIT Ar, Fabric, Other | 2023-08-14 | 2023-08-30 | Works Complete (2023) | R.PR/3/13 | 36271X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Wibsa Upington , Paint Walls CIT Ar, Fabric, Other | ASP-CR0391 |  |  | Complete | 2644.632 | 0 | 2644.632 | 1
240129_202 | Absa Hennenman, Installation of plugs, New assets | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/10 | 78855X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Key Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Hennenman, Installation of plugs, New assets | ASP-CR0312 |  |  | Complete | 2614.456 | 0 | 2614.456 | 1
240129_376 | 13 Top Road, Installation of blinds, Fabric, Other | 2024-04-01 | 2024-04-15 | Continue | R.PR/3/05 | 79271X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Supported, | 13 Top Road, Installation of blinds, Fabric, Other |  | 2400192 |  | TBC | 0 | 2500 | 2500 | 1
240129_167 | Absa Blouberg Mall, Kitchen Sink Replace, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | 22539X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets |  | Project Completed and not invoiced in 2023, Works completed, invoicing in progress | Absa Blouberg Mall, Kitchen Sink Replace, Fabric, Other | ASP-LP0182 |  |  | Complete | 2247.1 | 0 | 2247.1 | 1
240129_181 | Alice Lane North , 2nd Floor Glass Writeable wall, Fabric, O | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Alice Lane North , 2nd Floor Glass Writeable wall, Fabric, Other | ASP-GS0501 |  |  | Complete | 1798.853 | 0 | 1798.853 | 1
240129_206 | Silverton , Front Shop windows, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Silverton , Front Shop windows, Fabric, Other | ASP-GN0163 |  |  | Complete | 1798.853 | 0 | 1798.853 | 1
240129_204 | Thabo Sehume, Install 250KG Space Saver D, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Thabo Sehume, Install 250KG Space Saver D, Fabric, Other | ASP-GN0156 |  |  | Complete | 1798.853 | 0 | 1798.853 | 1
240129_247 | 20 Goldman Street Florida, Install frosting vinyl, Fabric, | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | 70027X | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | 20 Goldman Street Florida , Install frosting vinyl, Fabric, Other | ASP-GS0763 |  |  | Complete | 1754.969 | 0 | 1754.969 | 1
240129_211 | Birch Acres , Paint Ceilings and walls, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Birch Acres , Paint Ceilings and walls, Fabric, Other | ASP-GS0612 |  |  | Complete | 1754.969 | 0 | 1754.969 | 1
240129_239 | Highlands Warehouse, Aircon unit replacement, Mechanical | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/2/05 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Highlands Warehouse, Aircon unit replacement, Mechanical | ASP-GS0496 |  |  | Complete | 1624.973 | 0 | 1624.973 | 1
240129_124 | Absa Cosmo Mall, Upgrade BIC and paint wa, Fabric, Other | 2023-08-03 | 2023-09-15 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL | Supporting Assets | 0 | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Cosmo Mall, Upgrade BIC and paint wa, Fabric, Other | ASP-GN0212 | 0 |  | Complete | 1240.62 | 0 | 1240.62 | 1
240129_194 | Absa Towers West, Restaurant Furniture, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/05 | Various | Conrad Mills | FACILITIES MANAGEMENT | CORP |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers West, Restaurant Furniture, Fabric, Other | ASP-GS0553 |  |  | Complete | 812.4865 | 0 | 812.4865 | 1
240129_217 | Daveyton, Sales Consultant Desk, Fabric, Other | 2023-01-01 | 2023-12-31 | Works Complete (2023) | R.PR/3/13 | Various | Conrad Mills | FACILITIES MANAGEMENT | RETAIL |  |  | Project Completed and not invoiced in 2023, Rollover-Financial | Daveyton, Sales Consultant Desk, Fabric, Other | ASP-GS0619 |  |  | Complete | 410.8605 | 0 | 410.8605 | 1
240129_007 | Absa Bothaville, Replace HVAC Systems, including fresh-air a | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 79114X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 700 000, | Absa Bothaville, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400343 |  | TBC | 0 | 0 | 0 | 1
240129_006 | Absa Bultfontein, Replace HVAC Systems, including fresh-air | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 79115X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 700 000, | Absa Bultfontein, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400344 |  | TBC | 0 | 0 | 0 | 1
240129_042 | Absa Call Centre Auckland Park, Supply and Install cat ladde | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/05 | 76849X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | New Add - Phase 1 done in 2023 Budget Requirement 1,3M, | Absa Call Centre Auckland Park, Supply and Install cat ladder and roof walk rails (Phase 2), Mechanical | 0 | 0 |  | TBC | 0 | 0 | 0 | 1
240129_029 | Absa Odendaalsrus, Replace HVAC Systems, including fresh-air | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 79056X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 800 000, | Absa Odendaalsrus, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400348 |  | TBC | 0 | 0 | 0 | 1
240129_510 | Absa Towers West , 5th Floor Compliance Phone B, Ways of Wor | 2025-01-01 | 2025-12-31 | Defer | R.PR/5/14 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | No | Project Completed and not invoiced in 2023, Rollover-Financial | Absa Towers West , 5th Floor Compliance Phone B, Ways of Work | ALP-GS0040 | 0 |  | TBC | 0 | 0 | 0 | 1
240129_044 | Absa Towers West, Fire Alarm System upgrade, Mechanical | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/05 | 21526X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | Newly added requested budget R20 million (end of life) Was R20M - to go for RFP , | Absa Towers West, Fire Alarm System upgrade, Mechanical | 0 | 0 |  | TBC | 0 | 0 | 0 | 1
240129_005 | Absa Virginia, Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 79312X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 500 000, | Absa Virginia, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400355 |  | TBC | 0 | 0 | 0 | 1
240129_526 | Alice Lane Podium, Boardroom and meeting room G20,G21 to be | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 21843X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Core Assets | No | AV budget @R1,5M - Check with Rhulani and Cherese if added | Alice Lane Podium, Boardroom and meeting room G20,G21 to be upgraded with MTR and BOYD +Agora Tech IT equipment (replace projector with screen and touch pad ), Fabric, Other | 0 | 2400030 |  | TBC | 0 | 0 | 0 | 1
240129_523 | Alice Lane Podium, Functions kitchen revamp (tiling, floors, | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 21843X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Core Assets | No | TBC | Alice Lane Podium, Functions kitchen revamp (tiling, floors, tops, ceiling, lighting, design layout), Fabric, Other | 0 | 2400038 |  | TBC | 0 | 0 | 0 | 1
240129_489 | Alice Lane South, Bar fridges - pause area fridges replaceme | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 35041X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Core Assets | No | Fridges against white goods budget -Added, | Alice Lane South, Bar fridges - pause area fridges replacement x 10, Fabric, Other | 0 | 2400039 |  | TBC | 0 | 0 | 0 | 1
240129_051 | Alice lane South, Installation of Kwena Cable 2, Insurance C | 2025-01-01 | 2025-12-31 | Defer | D.PR/9/07 | 70656X | Jacobus Janse van Rensburg | ENGINEERING | CORP |  | 0 | Project Completed and not invoiced in 2023, Rollover from CIP2023 | Alice lane South, Installation of Kwena Cable 2, Insurance Claims | ALP-GS0080 | 0 |  | TBC | 0 | 0 | 0 | 1
240129_453 | Auckland Park , Auckland Park tiling to reception areas and | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 76849X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Supporting Assets | No | Moved from CIP2025 Budget required 2,2M, | Auckland Park , Auckland Park tiling to reception areas and lift lobbies, Fabric, Other | 0 | 0 |  | TBC | 0 | 0 | 0 | 1
240129_038 | Bridge Park Bridgeway Century City, BMS Upgrade, BMS and EMS | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/09 | 36225X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | No | To remain - Futher investigations required Remove on 07/12/2023 by CRES Engineering : R 555000, | Bridge Park Bridgeway Century City, BMS Upgrade, BMS and EMS Systems | N/A | 2400280 |  | TBC | 0 | 0 | 0 | 1
240129_008 | Grand Palace, Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/05 | 70641X | Jacobus Janse van Rensburg | ENGINEERING | CORP | Core Assets | Yes | Project moved out from our scope - R 750 000, | Grand Palace, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400388 |  | TBC | 0 | 0 | 0 | 1
240129_028 | Jan Kemp dorp, Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 78326X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 750 000, | Jan Kemp dorp, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400397 |  | TBC | 0 | 0 | 0 | 1
240129_027 | Limpopo Mall , Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 78979X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 750 000, | Limpopo Mall , Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400411 |  | TBC | 0 | 0 | 0 | 1
240129_009 | Pinetown, Replacement of Generator, Electrical | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/04 | 77102X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | No | Project moved out from our scope - R 750 000, | Pinetown, Replacement of Generator, Electrical | 0 | 2400443 |  | TBC | 0 | 0 | 0 | 1
240129_030 | Raisethope, Replace HVAC Systems, including fresh-air and ex | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 77839X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out of our scope R700000, | Raisethope, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400449 |  | TBC | 0 | 0 | 0 | 1
240129_530 | Rustenburg Burger Street, Consolidate 1st floor and clean up | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 77057X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Remove to RE Earmarked for possible R3,5M - to Be Dilaps, | Rustenburg Burger Street, Consolidate 1st floor and clean up of 2nd and 3rd floor, Fabric, Other | 0 | 2400456 |  | TBC | 0 | 0 | 0 | 1
240129_004 | Shelly Beach, Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 77417X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 1 000 000, | Shelly Beach, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400460 |  | TBC | 0 | 0 | 0 | 1
240129_026 | Thulamahashe Plaza, Replace HVAC Systems, including fresh-ai | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 79265X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 750 000, | Thulamahashe Plaza, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400468 |  | TBC | 0 | 0 | 0 | 1
240129_025 | Twin City Burgersfort, Replace HVAC Systems, including fresh | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 36240X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 750 000, | Twin City Burgersfort, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400473 |  | TBC | 0 | 0 | 0 | 1
240129_048 | Various Retail Sites, Replace Yellow lights on sites that ar | 2025-01-01 | 2025-12-31 | Defer | R.PR/1/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | CORP | Key Assets | No | Newly added requested budget R3,500,000.00 National Program - to be mentioned to Absa, | Various Retail Sites, Replace Yellow lights on sites that are not part of 2023 roll-out, Electrical | 0 | 0 |  | TBC | 0 | 0 | 0 | 1
240129_546 | Various Retail Sites (REG2), Various - Bulk PO - Eng Prioritised Re | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/04 | Various | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Supporting Assets | No | R600k removed as per CRES Engineering, | Various Sites (REG2), Various - Bulk PO - Eng Prioritised Requests - Retail Electrical (Allowance for 30 Sites), Electrical | N/A | 2400279 |  | TBC | 0 | 0 | 0 | 1
240129_289 | Victoria West, Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 21821X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | HVAC giving numerous problems and using R22 gas, | Victoria West, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400478 |  | TBC | 0 | 0 | 0 | 1
240129_020 | Wingin Centre, Replace HVAC Systems, including fresh-air and | 2025-01-01 | 2025-12-31 | Defer | R.PR/2/05 | 76714X | Jacobus Janse van Rensburg | ENGINEERING | RETAIL | Core Assets | Yes | Project moved out from our scope - R 750 000, | Wingin Centre, Replace HVAC Systems, including fresh-air and extraction, Mechanical | 0 | 2400486 |  | TBC | 0 | 0 | 0 | 1
240129_537a | Alice Lane North, Block out vinyl for wrap station, Fabric, | 2025-01-01 | 2025-12-31 | Defer | R.PR/3/05 | 70656X | Conrad Mills | FACILITIES MANAGEMENT | CORP | Key Assets | No | Catering to solution and provide temp sheets throughout the day. As per Hanlie Louw email 9-Feb-24, project to be reduced to R50,000 refer to 240129_537, 240129_537a and 240211_001. | Alice Lane North, Block out vinyl for wrap station, Fabric, Other |  | 2400020 |  | TBC | 0 | -50000 | -50000 | 1