## Sheet1
Request_No | Description | JSON String | JSON String | Priority | Client Region | Client Region | One View Number | Location | Description | Single-Character Indicator | Planned Start Date | Planned End Date | Plan Quarter | Project number | Description | User Name | ABSP Work Orders | Sub-Divided Property | JSON String | Description | Status | JSON String | Year | Risk Level | Origin of call request | Lease End Date | User Name | Date in Format YYYYMMDD in 8 Characters | All correct | Amount | JSON String | Description | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Amount | JSON String | JSON String | JSON String | JSON String | Description | Character Field Length = 10 | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Description | Description | Request_No | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Amount | Amount | JSON String | JSON String | Doc Nr | Amount | Description | Amount | Reference No. | Amount | Amount | Doc Nr | Amount | Doc Nr | Amount | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters | Date in Format YYYYMMDD in 8 Characters
70000000 | Smart electrical and water metering (2022) | Supply, installation and commissioning of 87 Smart electrical & water meters at selected retail sites |  |  | Energy | National | Various |  | Various Sites | N | 2022-07-05 | 2023-03-31 |  | ABS-G00005 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Wesigye Mukuru | rollover | Various sites which are freehold and leasehold sites | 2022 |  | V |  | DUPREEZK | 2022-07-05 |  | 3226114 |  | 100 | 2022-06-02 | 2022-06-02 | 3226113.88 | Project financial (R402193) rolled over from 2022 with new PO number being C000059965 | {"MANDT":"111","REFERENCE":70000000,"ONEVIEW":"Various Sites","DATE01":"2022-04-26","DATE02":"2022-05-03","DATE03":"2022-05-24","DATE04":"2022-05-31","DATE05":"2022-06-21","DATE06":"2022-07-05","DATE07":"2023-06-15","DATE08":"2023-07-06","DATE09":"2023-08-20","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-05","FORECAST_END":"2023-06-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGludm9pY2VkIGZvciBhbmQgZmluYWwgYWNjb3VudCBzdWJtaXR0ZWQuIFByb2plY3QgY2xvc2VkIG91dA==","RATING":""} |  |  | C000059965 | PHASE11 | 2022-07-05 | 2023-06-15 | ONISMS MANYEWE | Nokuthula Manzini | 23000496 | 2022-06-23 | 2022-07-01 | 2022-06-20 | 2022-06-23 | 2023-01-09 | 402193.43 | 2403123 |  |  | C000059965 | 402193.43 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000001 | Smart electricity meter hardware install | Smart electricity meter hardware installation and water meter modem installation at the Absa Ridgeside Regional Office, Absa Lower Long Street and Absa Pretoria Campus.As part of Absa s Energy and Utility management strategy,Bidvest Facilities Management was mandated to develop and propose a strategy for rolling out smart meters on the non metered sites that are included in its portfolio.The implementation of this initiative will enable the client to achieve the following objectives: Accurate measurement and reporting of the utility usage Identification of utilities and cost optimization opportunities Evaluation of the impact of optimization projects. Recovery of funds lost due to overbilling. Identification of future unexpected costs due to underbilling. Compliance with mandatory reporting as per legal and governance requirementsNote: Position of the meters: PTA Campus is the Vodacom Tower, Ridgeside and Lower Long is at the main incomer. Scope of Work Identify room where meters are located. Ensure area is safe to work in. Install and fix meter enclosure close to the DB by either drilling holes to secure the meter enclosure, not exceedingly more than 2 meters above floor level (if not HIRA is required) and connect the electrical meter. Open/Remove the front cover of the electrical distribution board. Install Current Transformers (CTs). The necessary PPE and electrically insulated tools will be used. Solid Core Current Transformerss requires the main incomer isolator to be switch off. If the site is deemed to require shutdown, Bidvest FM will reschedule this exercise to a later agreed date (after freeze period in January 2020) and seek approval from the FM, TM, BM and IT commit to the times for the switch off. Close the front cover of the electrical board. Commission the electrical meter. Confirm Meter Communications. |  |  | Special Projects | Various | Various |  | Various |  | 2022-07-11 | 2023-03-31 |  | ABS-G00006 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | ONISMS MANYEWE |  |  | 2022 |  | Freeho |  | DUPREEZK | 2022-07-11 |  | 5705.05 |  | Approved | 2022-07-14 | 2022-07-14 | 0 |  |  |  |  | C000027657 | CLOSED |  |  | TREVOR BEELDERS | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000002 | Carport lighting sensor solution | Supply, install and commission motion sensors in the car park |  |  | Energy | Gauteng South | 22491X | 1000-70065-01 | Absa Pretoria Campus |  | 2022-08-15 | 2023-03-31 |  | ABS-G00007 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Jaca Kgomotso |  |  | 2022 |  | F |  | DUPREEZK | 2022-08-15 |  | 681422.64 | Realization of savings as as result of project implementation | 100 | 2022-06-02 | 2022-06-14 | 681422.64 | Project approved at BTB sitting on 14th June 2023 | {"MANDT":"111","REFERENCE":70000002,"ONEVIEW":"22491X","DATE01":"2022-06-06","DATE02":"2022-06-13","DATE03":"2022-07-04","DATE04":"2022-07-11","DATE05":"2022-08-01","DATE06":"2022-08-15","DATE07":"2023-07-31","DATE08":"2023-08-31","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-08-15","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgaW5zdGFsbGF0aW9uIG9mIHBvd2VyIGNhYmxlcyBieSBjb250cmFjdG9y","RATING":""} |  |  | C000060074 | PHASE11 | 2022-08-15 | 2023-07-31 | ONISMS MANYEWE | Nokuthula Manzini | 0 | 2022-07-06 | 2022-07-25 | 2022-06-29 | 2022-07-04 | 2023-01-09 | 592541.43 | 0 |  |  | C000031315 | 592541.43 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000003 | Replacement of Vandalised HVAC Units and | Replacement of Vandalised HVAC Units and Stolen Copper/ Electrical Cabling |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Absa Bloemfontein |  | 2022-02-15 | 2022-03-31 |  | ALP-CR0015 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-16 |  | 202478.9 |  | Approved | 2022-04-28 | 2022-04-28 | 2328507.37 |  |  |  |  | C000060053 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-09 | 377323.84 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000004 | Remedial Work | Remedial Work |  |  | Region 3 | Free State | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley |  | 2022-11-01 | 2022-11-01 |  | ALP-CR0018 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | NOMNGANGAL | 2022-07-06 |  | 298151.03 |  | 100 | 2022-09-29 | 2022-09-29 | 2981510.34 |  |  |  |  | C000060192 | PHASE11 | 2022-11-01 | 2022-11-01 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-01-13 | 2592617.69 | 0 |  |  | C000060192 | 2592617.69 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000005 | Minor Works | Minor Works |  |  | Region 3 | Free State | 77605X | 1000-71295-01 | Wolmaransstad-Kruger St-Wolmaransstad |  | 2022-10-20 | 2022-10-28 |  | ALP-CR0019 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-03 |  | 70787.47 |  | 100 | 2022-09-29 | 2022-09-29 | 707874.71 |  |  |  |  | C000063445 | PHASE11 | 2022-10-28 | 2022-11-18 | NANDE MAQUBELA | Juanita Van Coller | 23000481 |  |  |  |  | 2023-01-24 | 615543.23 | 0 |  |  | C000063445 | 615543.23 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000006 | Minor Works | Minor Works |  |  | Region 3 | Free State | 79227X | 1000-71608-01 | Taung Forum-Station Rd-Taung |  | 2022-11-30 | 2022-11-30 |  | ALP-CR0021 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-02 |  | 60405.19 |  | 100 | 2022-09-29 | 2022-09-29 | 604051.94 |  |  |  |  | C000068008 | PHASE11 | 2022-11-30 | 2022-11-30 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-02-14 | 525262.61 | 0 |  |  | C000068008 | 525262.61 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000007 | Minor Works | Minor Works |  |  | Region 3 | Northern Cape | 79329X | 1000-71361-01 | De Aar-Voortrekker St-De Aar |  | 2022-11-30 | 2022-11-30 |  | ALP-CR0023 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L | 2000-01-01 | NOMNGANGAL | 2022-11-02 |  | 571196.17 |  | 100 | 2022-11-10 | 2022-11-10 | 571196.17 |  |  |  |  | C000081193 | PHASE10 | 2022-11-30 | 2022-12-21 | NANDE MAQUBELA | Juanita Van Coller | 23000490 |  |  |  |  | 2023-04-21 | 496692.32 | 0 |  |  | C000081193 | 496692.32 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000008 | Minor Works | Minor Works |  |  | Region 3 | Free State | 78306X | 1000-71536-01 | Frankfort-Brand St-Frankfort |  | 2022-11-30 |  |  | ALP-CR0024 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Liso Jordan |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-11-04 |  | 66605.36 |  | 100 | 2022-09-29 | 2022-09-29 | 765961.7 | 08.08.2023 FM, there is contingency & savings value saved into the project. | {"MANDT":"111","REFERENCE":70000008,"ONEVIEW":"78306X","DATE01":"2022-09-21","DATE02":"2022-10-19","DATE03":"2022-10-26","DATE04":"2022-10-26","DATE05":"2022-11-30","DATE06":"2022-12-30","DATE07":"2023-01-20","DATE08":"2023-03-06","DATE09":"2023-03-31","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-30","FORECAST_END":"2023-01-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060052 | PHASE11 | 2022-12-30 | 2023-01-20 | NANDE MAQUBELA | Floyd Mofokeng | 23000478 |  |  |  |  | 2023-08-31 | 664497.13 | 0 |  |  | C000048102 | 664497.13 | CIP2023XP | 9458.95 |  | 0 | 0 |  | 0 |  | 0
70000009 | Minor Works | Minor Works |  |  | Region 2 | Eastern Cape | 70631X | 1000-71001-01 | Absa Lusikisiki |  | 2022-04-25 | 2022-06-30 |  | ALP-EC0006 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-07 |  | 854013.62 |  | Approved | 2022-03-31 | 2022-03-31 | 854013.62 |  |  |  |  | C000019182 | CLOSED | 2022-04-25 | 2022-06-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000010 | Linton Arcade - 60kVA New Installation | Linton Arcade - 60kVA New Installation | bnVsbCA%3D |  | Region 2 | Eastern Cape | 76436X | 1000-71457-01 | Linton Arcade-Cape Rd-Port Elizabeth | N | NaNN------ | NaNN------ |  | ALP-EC0007 | CLSD BUDG AVAC RESA SETC: | SAP_018 | false | false | null | Laxine Maliffe | na | null | 0 |  | L | 2025-01-30 | CEASARS | 2022-08-01 |  | 876274.37 | null | 100 | 2022-10-20 | 2022-10-20 | 876274.37 | null | {"MANDT":"111","REFERENCE":70000010,"ONEVIEW":"76436X","DATE01":"2022-05-26","DATE02":"2022-06-30","DATE03":"2022-10-05","DATE04":"2022-10-20","DATE05":"2022-10-20","DATE06":"2023-03-06","DATE07":"2023-03-31","DATE08":"2023-04-13","DATE09":"2023-05-28","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:35:97:15:0:137:25:13:45:25","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-06","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgQXByIC0gRmluYWwgUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Medium"} |  |  | C000063167 | PHASE11 | 2023-03-06 | 2023-03-31 | RODERICK NEVAY | Nokuthula Manzini | 23000474 |  | 2023-01-16 |  |  | 2023-01-30 | 761977.71 | 0 |  |  | C000063167 | 761977.1 | CIP2023XP | 75367.92 |  | 0 | 0 |  | 0 |  | 0
70000011 | Morcross Centre - Matatiele | Morcross Centre - Matatiele - Minor Works |  |  | Region 2 | Eastern Cape | 77213X | 1000-71025-01 | Morcross Centre-Cnr Jagger & North St-Matatiele | N | 2022-10-31 |  |  | ALP-EC0008 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-08-05 |  | 1309317.67 |  | 100 | 2022-09-01 | 2022-09-01 | 1309317.67 | Contingency Remaining R 45 737.34 Incl Vat | {"MANDT":"111","REFERENCE":70000011,"ONEVIEW":"77213X","DATE01":"2022-04-01","DATE02":"2022-04-13","DATE03":"2022-07-31","DATE04":"2022-08-31","DATE05":"2022-09-01","DATE06":"2022-11-11","DATE07":"2022-11-26","DATE08":"2022-12-06","DATE09":"2023-01-20","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:12:109:31:1:71:15:10:45:1","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-11","FORECAST_END":"2022-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNlIDYgRGVjIA==","RATING":"Low"} |  |  | C000062832 | PHASE11 | 2022-11-11 | 2022-11-26 | RODERICK NEVAY | Juanita van Coller | 23000461 |  |  |  |  | 2023-01-20 | 1138537.1 | 1072208.05 |  |  | C000062832 | 66329.05 | CIP2023XP | 109413.99 |  | 0 | 0 |  | 0 |  | 0
70000012 | 6th Avenue Shopping Centre Reinstatement | 6th Avenue Shopping Centre -Reinstatement |  |  | Region 2 | Eastern Cape | 76669X | 1000-70793-01 | Absa 6th Ave Shopping Centre | N | 2022-10-01 | 2022-11-28 |  | ALP-EC0009 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | GAMIETR | 2022-10-11 |  | 608184.93 |  | 100 | 2022-10-12 | 2022-10-12 | 608184.93 | Test | {"MANDT":"111","REFERENCE":70000012,"ONEVIEW":"76669X","DATE01":"2022-03-01","DATE02":"2022-03-31","DATE03":"2022-07-31","DATE04":"2022-10-12","DATE05":"2022-10-12","DATE06":"2022-10-12","DATE07":"2022-11-28","DATE08":"2023-01-24","DATE09":"2023-03-10","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:30:122:73:0:0:47:57:45:26","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-12","FORECAST_END":"2022-11-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjQgSmFuIEZpbmFsIFBPQyBTdWJtaXR0ZWQ=","RATING":"Low"} |  |  | C000062109 | PHASE11 | 2022-10-12 | 2022-11-28 | RODERICK NEVAY | Juanita van Coller | 23000488 |  |  |  |  | 2023-01-18 | 528856.46 | 442874.72 |  |  | C000043554 | 85981.74 |  | 52602.15 |  | 0 | 0 |  | 0 |  | 0
70000013 | Vincent Office Park Installation of New 40kVA Generator and | Vincent Office Park Installation of New 40kVA Generator and 15kVA Uninterrupted Power Supply |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Vincent Office Park-Western Ave-East London | N | 2023-03-31 | 2023-05-31 |  | ALP-EC0011 | CLSD BUDG ISBD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-11-08 |  | 1022473.03 |  | 100 | 2022-12-08 | 2022-12-08 | 1022473.03 | Contingency Remaining R 47030.27 Incl Vat | {"MANDT":"111","REFERENCE":70000013,"ONEVIEW":"79369X","DATE01":"2022-10-01","DATE02":"2022-11-07","DATE03":"2022-11-23","DATE04":"2022-11-23","DATE05":"2022-12-08","DATE06":"2023-02-15","DATE07":"2023-04-11","DATE08":"2023-05-18","DATE09":"2023-05-25","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:37:16:0:15:69:55:37:7:32","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-15","FORECAST_END":"2023-04-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFN1Ym1pdHRlZCAxOCBNYXk=","RATING":"Medium"} |  |  | C000080825 | PHASE11 | 2023-02-15 | 2023-04-11 | RODERICK NEVAY | Nokuthula Manzini | 23000469 |  | 2023-03-28 |  |  | 2023-04-20 | 889106.98 | 0 |  |  | C000080825 | 889106.99 | CIP2023XP | 79225.8 |  | 0 | 0 |  | 0 |  | 0
70000014 | Pretoria Campus Refurbish Carports | Scope of Works: Implement temporary support structures prior to removing steel posts to parking bays; Remove all existing posts (1230 of), remove from site and provide disposal certificate; Prepare ground to install new posts; Install the new steel posts with concrete support in the ground; Support posts dimensions: 75mm x 75mm x 2mm; Sand and treat existing steel elements with anti-rust prior to painting; Paint all steel elements (new support posts and existing horizontal beams); Include waterproof rubber sleeve to minimise rust and water damage at ground level; Rubble removal and make good paving; Allow for weekend work. | bnVsbCA%25253D |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2022-04-20 | 2023-04-29 |  | ALP-GN0006 | CLSD BUDG AVAC RESA SETC: | SAP_018 | false | false | null | Phathutshedzo Neduvhuledza | na | null | 0 |  | F |  | GAMIETR | 2022-01-25 |  | 5125000.5 | Approved | 100 | 2021-12-09 | 2023-10-07 | 1882133.8 |  | {"MANDT":"111","REFERENCE":70000014,"ONEVIEW":"22491X","DATE01":"2021-11-10","DATE02":"2021-11-17","DATE03":"2021-12-08","DATE04":"2021-12-15","DATE05":"2022-01-05","DATE06":"2022-01-01","DATE07":"2023-04-29","DATE08":"2023-05-25","DATE09":"2023-07-09","DATE10":"2023-07-31","DATE11":"2023-07-09","DATE12":"2023-07-09","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"628:7:21:7:21:-4:483:26:45:27","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMi8yMCBOTjogQ29uZmlybWVkIHdpdGggUE0gRmluYWwgUE9DIGRvbmUK","RATING":""} |  |  | C000059840 | PHASE11 | 2022-01-01 | 2023-04-29 | PRESHANE MUNTHREE | Obakeng Phuti | 23000457 |  |  |  |  | 2023-01-09 | 1002095.65 | 765250.57 |  |  | 2909792 | 871387.53 | CIP2023XP | 158779.4 |  | 0 | 0 | - | 0.01 | - | 0.02 |  |  | 2023-01-09 | 2023-03-09
70000015 | Upgrade & Construction of New Concrete P | Upgrade & Construction of New Concrete Palisade Fence |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus |  | 2022-06-01 | 2022-12-15 |  | ALP-GN0007 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-02-28 |  | 1609513.75 |  | Approved | 2021-11-18 | 2021-11-18 | 1123192.01 |  |  |  |  | C000059849 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-09 | 156722.59 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000016 | Dilaps Phase 2 Minor Works | Dilaps Phase 2 Minor Works |  |  | Region 1 | Gauteng North | 0 | 1000-70416-01 | Absa Hillcrest Office Park |  | 2022-07-18 | 2022-08-31 |  | ALP-GN0009 | CLSD BUDG AVAC RESA: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2022-07-20 |  | 56690.79 | Project is closed and cannot be altered | 100 | 2022-07-25 | 2022-07-25 | 651944.12 | 29/05/23 AS Project Closed. | {"MANDT":"111","REFERENCE":70000016,"ONEVIEW":"0","DATE01":"2022-05-09","DATE02":"2022-05-16","DATE03":"2022-06-06","DATE04":"2022-06-13","DATE05":"2022-07-04","DATE06":"2022-07-18","DATE07":"2022-08-31","DATE08":"2022-09-21","DATE09":"2022-11-05","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":20,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-18","FORECAST_END":"2022-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000061756 | PHASE11 | 2022-07-18 | 2022-08-31 | PRESHANE MUNTHREE | Obakeng Phuti | 23000484 |  |  |  |  | 2023-01-17 | 42940.11 | 0 |  |  | C000027479 | 566907.94 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000017 | PTA Refurbishing of the Ceilings and Fire Sp | Erect onsite scaffolding in sequence of work carried out in Block A and C. .Supply and install new ceiling tiles and ceiling grid in affected areas, tiles size 1200 x 600 x 12,5mm thick matching existing. .Supply and install additional pipe hangers for the ranger pipes to ensure there is solid anchor points. .Supply and install additional pipe hangers to ensure the installation meets the minimum distance requirement for pipe hangers. .Repair of the rusted booster connection. .Testing and Commissioning of the Fire Systems. .Certification of the system and components on completion. .12 Month Guarantee on installation. .IT Technician allowance for decommissioning and recommissioning PC screen where required. .Security Guarding Services for duration of the project |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2021-01-29 |  |  | ALP-GN0010 | REL BUDG AVAC RESA SETC: |  | R | false |  | Njabulo Ngubane |  |  | 2022 |  | F |  | GAMIETR | 2022-11-03 |  | 2557618.01 |  | 100 | 2022-10-27 | 2022-10-27 | 2557618.01 |  | {"MANDT":"111","REFERENCE":70000017,"ONEVIEW":"22491X","DATE01":"2020-11-20","DATE02":"2022-04-29","DATE03":"2022-05-18","DATE04":"2023-10-20","DATE05":"2022-07-15","DATE06":"2023-12-01","DATE07":"2024-01-31","DATE08":"2024-02-21","DATE09":"2024-04-06","DATE10":"2024-04-30","DATE11":"2024-04-06","DATE12":"2024-04-06","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":85,"PROG05":100,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"1196:525:19:520:-462:504:61:21:45:45:45:27","PROGRESS":44,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-01","FORECAST_END":"2024-01-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMi8yMCBOTjogUHJvamVjdCBpbiBwcm9ncmVzcywgY29tcGxldGlvbiBwbGFubmVkIGZvciBlbmQgb2YgSmFuIDIwMjQu","RATING":""} |  |  | C000094792 | PHASE09 | 2023-12-01 | 2024-01-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000455 | 2023-07-04 |  |  |  | 2023-06-30 | 2224015.65 | 0 |  |  | C000094792 | 2224015.65 | CIP2023XP | 221438.79 |  | 0 | 0 |  | 0 |  | 0
70000018 | Pretoria Campus Repairs to Identified St | Repair expansion joints on floors and walls in blocks A, C and M; Repair foundation settlement cracks in Block M externally; Repair vertical and horizontal joints as identified in report for Blocks A and C; Repair category 3 cracks in the main wall and cross joint shear wall cracks in the A.68 Patch room. Repair category 5 foundation settlement stepped cracks externally in Block M as per Engineer report Structural Engineer sign off | bnVsbCA%253D |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-01-03 | 2023-05-30 |  | ALP-GN0011 | REL BUDG AVAC RESA SETC: | SAPMT | false | false | null | Christopher Mpofu | na | Project support by CRES Eng | 0 |  | F |  | GAMIETR | 2022-11-03 |  | 480000 | Project approved and supported by CRES Eng Head. | 60 | 2022-08-01 | 2022-09-12 | 741448.38 | Supported by CRES Eng | {"MANDT":"111","REFERENCE":70000018,"ONEVIEW":"22491X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2023-07-31","DATE07":"2023-10-30","DATE08":"2023-10-30","DATE09":"2023-11-30","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-31","FORECAST_END":"2023-10-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBleGVjdXRpb24gdG8gdGhlIGZpcnN0IHdlZWsgb2YgNXRoIE9jdG9iZXIgMjAyMy4KQXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQT8OiwoDCmXMgdG8gYmUgaXNzdWVkIGluIHRoZSBpbnRlcmltIAotUGxhbm5lZCBzdGFydCAtMTAvMTAvMjAyMwotUGxhbm5lZCBjb21wbGV0aW9uLTIzLzEyLzIwMjMKLUZpbmFuY2lhbCByb2xsLW92ZXI=","RATING":"Medium"} |  |  | C000104088 | PHASE11 | 2023-07-31 | 2023-11-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000479 | 2023-08-01 | 2023-09-11 | 2023-08-14 | 2023-08-18 | 2023-09-01 | 630590.42 | 0 |  |  | C000104088 | 630590.42 | CIP2023XP | 64194.67 |  | 0 | 0 |  | 0 |  | 0
70000019 | Pretoria Campus Block E Restaurant and Deck Upgrade | -Submit design drawings , 3D drawings renders including shop drawings -Remove identified existing counters and cart-away -Supply and install new counters and tops where proposed in the main restaurant area and coffee bar -Remove existing old composite timber deck including support beams and replace with new Arched solid composite grey unified boards -Supply and install splashback gloss tile finish to match existing above coffee area sink -Supply and install (2) hour fire rated double door in delivery area with vents (to match existing) -Prepare and paint concrete floor with epoxy paint in delivery and chemical area -Supply and install light pendants in identified areas as per design -Relocate recycle bins to the main front wall next to the plates stacker -Re-position cold room fridge to the identified area as per proposed design -Issue COC on electrical and plumbing on completion |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-05-14 | 2023-05-29 |  | ALP-GN0013 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  | Project to commence on the 8/05/2023 | 2022 |  | F |  | GAMIETR | 2022-11-09 |  | 3576093.11 |  | 60 | 2022-08-18 | 2022-08-18 | 3576093.11 |  | {"MANDT":"111","REFERENCE":70000019,"ONEVIEW":"22491X","DATE01":"2022-04-21","DATE02":"2022-04-28","DATE03":"2022-05-19","DATE04":"2022-05-26","DATE05":"2022-06-16","DATE06":"2023-05-15","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-09-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2VkIG91dHN0YW5kaW5nIFZPJ3MgdG8gYmUgYXBwcm92ZWQgYnkgVlAgbm90IHBhcnQgb2YgdGhlIG9yaWdpbmFsIHByb2plY3Qgc2NvcGUuLA==","RATING":"Low"} |  |  | C000048603 | PHASE11 | 2023-05-15 | 2023-07-31 | PRESHANE MUNTHREE | Obakeng Phuti | 23000451 | 2022-09-23 | 2022-10-21 | 2022-10-24 | 2022-10-27 | 2022-11-10 | 3109646.18 | 0 |  |  | C000048603 | 3109646.17 | CIP2023XP | 272395.49 |  | 0 | 0 |  | 0 |  | 0
70000020 | Quadrum O/P Minor Refresh | Work station desks (as per approved Absa spec). Move furniture as required for carpet installation. Removal of deteriorated carpets & floor tiles and cart away (486 square meters) Supply and install new carpets & floor tiles, as per CRES Designâs specifications: *Belgotex Davenport â Color: Breadnut semi flexible vinyl tiles 500 x 500 in plank format = 26m2 *Belgotex Cirrus Nimbus - Color: Custom X 001 1000 x 250 in plank format = 438m2 *Belgotex Cirrus Stratus - Color: Custom X 002 500 x 500 in plank format = 15m2 *Full bodied porcelain floor tiles 600 x 600mm fixed with adhesive to screed = 8m2 Supply and install 2 500 x 700 x 900mm high with solid countertop in the Pause area, as per CRES Designâs specifications Paint interior walls and columns, as per CRES Designâs specifications: *1:2 coats Dulux ecosure primer and paint - colour: silver quill 30GG 61/010 = 939m2 *1:2 coats Dulux ecosure primer and paint - in varying colours: 30RR 12/281; 48RR 08/222; 64RR 12/436; 16YR 18/587;60YR 29/559; 60YR 26/605 = 364m2 LED light replacement. Supply and install anti-static vinyl flooring to IT room (15m2). Relocate 17 CPU's from existing desks into the IT room. Installation of a cooling rack to house the 17x CPU's. Supply & install x7 Bays of Nut & Bolt Shelving for IT room. IT allowance for cable management. Electrical support for disconnection and reconnection of existing power panels and issue a CoC. Provide security and enhanced cleaning services. The carpet lead times are between 5 to 6 weeks from PO being issued to the manufacturer (Belgotex). Furniture lead times are between 6-12 weeks from PO being issued. |  |  | Region 1 | Gauteng South | 21332X | 1000-70025-01 | Quadrum Office Park-Constantia Blvd-Roodepoort | N | 2022-01-20 | 2022-03-18 |  | ALP-GS0026 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  | L |  | GAMIETR | 2021-12-22 |  | 1700000 |  | 100 | 2021-12-15 | 2021-12-15 | 3059540.38 |  | {"MANDT":"111","REFERENCE":70000020,"ONEVIEW":"21332X","DATE01":"2021-10-13","DATE02":"2021-10-20","DATE03":"2021-11-10","DATE04":"2021-11-17","DATE05":"2021-12-08","DATE06":"2022-01-21","DATE07":"2023-03-19","DATE08":"2023-04-09","DATE09":"2023-05-24","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"534:7:21:7:21:44:422:21:45:5","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-21","FORECAST_END":"2023-03-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000059961 | PHASE11 | 2022-01-21 | 2023-03-19 | PRESHANE MUNTHREE | Buhle Qwabe | 23000555 |  |  |  |  | 2023-01-09 | 503453.77 | 2157016.13 |  |  | C000059961 | 503453.78 | CIP2023XP | 0 |  | 1 | 0 |  | 0 |  | 0
70000021 | Repair cracks on walls and floors | Repair cracks on walls and floors |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West |  | 2022-01-19 | 2022-05-31 |  | ALP-GS0028 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-01-25 |  | 61821.19 |  | Approved | 2021-11-18 | 2021-11-18 | 710943.77 |  |  |  |  | 2904915 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000022 | Lift Drivers | Lift Drivers |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West |  | 2022-01-19 | 2022-05-30 |  | ALP-GS0029 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | GAMIETR | 2022-02-16 |  | 325370.38 |  | 100 | 2021-12-09 | 2021-12-09 | 3741759.4 |  | {"MANDT":"111","REFERENCE":70000022,"ONEVIEW":"21526X","DATE01":"2021-11-10","DATE02":"2021-11-17","DATE03":"2021-12-08","DATE04":"2021-12-15","DATE05":"2022-01-05","DATE06":"2022-01-19","DATE07":"2022-05-30","DATE08":"2022-06-20","DATE09":"2022-03-05","DATE10":"2022-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-19","FORECAST_END":"2022-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000075339 | PHASE11 | 2022-01-19 | 2022-05-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000517 |  |  |  |  | 2023-03-22 | 207545.94 | 0 |  |  | 2902763 | 3253703.83 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000023 | Condenser Coil Units | Condenser Coil Units |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North |  | 2021-01-29 | 2022-05-31 |  | ALP-GS0030 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-02-24 |  | 99555.91 |  | 100 | 2022-02-03 | 2022-02-03 | 1144893.18 |  | {"MANDT":"111","REFERENCE":70000023,"ONEVIEW":"77381X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2021-01-29","DATE07":"2022-05-31","DATE08":"2022-06-21","DATE09":"2021-03-15","DATE10":"2021-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-01-29","FORECAST_END":"2022-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000059839 | PHASE11 | 2021-01-29 | 2022-05-31 | PRESHANE MUNTHREE | Buhle Qwabe | 23000466 |  |  |  |  | 2023-01-09 | 93795.92 | 0 |  |  | 2910594 | 995559.13 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000024 | Smoke Detectors | Smoke Detectors |  |  | Region 1 | Gauteng South | 78946X | 1000-71416-01 | Absa Towers East |  | 2022-04-01 | 2022-05-31 |  | ALP-GS0031 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-03 |  | 211845.49 |  | Approved | 2022-02-10 | 2022-02-10 | 2436223.13 |  |  |  |  | C000059963 | CLOSED | 2022-04-01 | 2022-05-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 315916.36 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000025 | Installation of 90 PropelAir toilets at | Installation of 90 PropelAir toilets at Auckland Park Call Centre |  |  | Region 1 | Gauteng South | 37075X | 1000-71392-01 | Absa Call Centre Auckland Park |  | 2022-03-29 | 2022-06-30 |  | ALP-GS0032 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-03-30 |  | 242886.24 |  | 100 | 2022-03-03 | 2022-03-03 | 2793191.8 |  | {"MANDT":"111","REFERENCE":70000025,"ONEVIEW":"37075X","DATE01":"2022-01-18","DATE02":"2022-01-25","DATE03":"2022-02-15","DATE04":"2022-02-22","DATE05":"2022-03-15","DATE06":"2022-03-29","DATE07":"2022-06-30","DATE08":"2022-07-21","DATE09":"2022-05-13","DATE10":"2022-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-29","FORECAST_END":"2022-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062830 | PHASE11 | 2022-03-29 | 2022-05-30 | PRESHANE MUNTHREE | Buhle Qwabe | 23000462 |  |  |  |  | 2023-01-20 | 1351090.12 | 0 |  |  | 2913694 | 2428862.43 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000026 | Waterproofing | Waterproofing |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-01-29 | 2022-07-31 |  | ALP-GS0034 | REL CNF BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-31 |  | 135495.3 |  | 100 | 2022-02-10 | 2022-02-10 | 1558196.05 |  |  | {"APRO_TYPE":"AB","NAME":"Waterproofing","REASON":"80","ENVIR_INVEST":"70000","PRIORITY":"3","APPROVA_YEAR":0,"PLANNED_APPR":"--","IMPLEMENT_ST":"--","COUNTRY_INVS":"ZA","APPLICANT":"","AUTHORIZER":"","INVESTPROG":"","YEAR":0,"POSITION_ID":"","R_CO_CODE":"1000","REQ_COST_C":"19509200","REQ_PROFIT_C":"19509200","DIVISION":"07","R_CO_CODE2":"1000","REQ_COST_C2":"19509200","REQ_PROFIT_C2":"19509200","PLANT":"AB10","CURRENCY":"ZAR","V_NAME":"Q3","VARIANT":"10","COSTS":"","COSTS1":"0","COSTS2":"0","COSTS3":"0","COSTS4":"0","COSTS5":"0","COSTS6":"0","COSTS7":"0","COSTS8":"0","COSTS9":"0","STATUS":"FAPR","VERSION":"B3","FUNCT_LOCATION":"","DETAILS":"","ABSAREQNO":70000026} |  | 2913868 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000027 | Dilaps | Dilaps |  |  | Region 1 | Gauteng South | 78946X | 1000-71416-01 | Absa Towers East |  | 2022-05-27 | 2022-08-31 |  | ALP-GS0035 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-06-01 |  | 52652.49 |  | Approved | 2022-05-26 | 2022-05-26 | 605503.65 |  |  |  |  | C000062061 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-18 | 526524.91 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000028 | Installation of New 60KVA Generator | Installation of New 60KVA Generator | Vm0xd1IyRnRVWGROVm1SWVYwZDRWbFl3WkRSV1ZteFZVbXQwVmsxV2NIbFdWM1JQWVZkRmVXVkZUbFpTYkVZelYyNXNRbEJUUVQwZyA= |  | Region 1 | Gauteng South | 21857X | 1000-70041-01 | Tsakane Mall-Cnr Modjadji & Malandela St-Tsakane |  | 2022-05-30 | 2022-12-15 |  | ALP-GS0036 | REL BUDG AVAC RESA SETC: | SAPMT | false | false | null | Yashir Somaru | na | null | 0 |  | L |  | LOUISR | 2022-06-06 |  | 49848.96 | Pre loaded - without notes | 100% | 2022-05-05 | 2022-05-05 | 573263.04 | None |  |  |  | C000060073# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 77062.3 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000029 | Installation of New 60KVA Generator | Installation of New 60KVA Generator |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2021-01-29 | 2022-08-31 |  | ALP-GS0038 | CRTD: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-08 |  | 503950 | Approved at CB/BTB |  | 2022-05-12 | 2022-12-01 | 705834.55 | Approved |  |  |  | C000060072# | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-01-09 | 528155.21 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000030 | Painting of the North facing Building Fa | Painting of the North facing Building Facade |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Auckland Park |  | 2022-07-30 | 2022-10-31 |  | ALP-GS0039 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-15 |  | 145060 |  | Approved | 2022-06-09 | 2022-06-09 | 1668190.08 |  |  |  |  | C000059966# | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 135157.51 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000031 | Absa Towers West Compliance Project 5th F | - Electrical installation - Removal of IT cabling and computer screens and storage of same - Remove corporate plugs and save under access flooring - Remove identified furniture not requisite to new design to Absa stores - Re-arrange existing furniture as per Architect drawing - Alterations for 2 x private lounges shopfront ,mechanical and fire related works - Supply and install 4 x writable walls - Security guarding services to be provided for duration of project - Procure new furniture as per new design specification |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-08-29 | 2022-12-19 |  | ALP-GS0040 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2022-08-11 |  | 840674.53 |  | 100 | 2022-08-11 | 2022-08-11 | 840674.53 |  | {"MANDT":"111","REFERENCE":70000031,"ONEVIEW":"21526X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-08-30","DATE07":"2022-12-20","DATE08":"2023-01-10","DATE09":"2023-02-24","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"284:7:21:7:21:46:112:21:45:4","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-08-30","FORECAST_END":"2022-12-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060050 | PHASE11 | 2022-08-30 | 2022-12-20 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000475 |  |  |  |  | 2023-01-09 | 482916.98 | 0 |  |  | C000060050 | 731021.33 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000032 | Auckland Park Refurbish Halaal & coffee bar | Halaal Kitchen and Coffee Bar: Extend wall and counters in the Halaal kitchen Supply and install new non-slip floor tiles in the kitchen area Remove glass writable wall Demolish existing wall adjacent to call centre and install folding doors Allow for acoustic sound buffer in the new wall Relay fire sprinklers to suit new layout Install new pendant lighting fixtures Electrical work including Distribution Board for affected work Test, commission and issue Electrical Certificate of compliance (COC) ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ ÃÂÃÂ Gym Area: Extend Gym space to existing engineering stores inclusive of required builders work Fresh air system to be provided to meet the minimum regulations (As per Engineer assessment report) Supply and install LED lighting in the existing and new Gym extended area Install new power skirting with sufficient power points and issue COC Fire Protection services and updating of drawings BMS upgrade |  |  | Region 1 | Gauteng South | 21332X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-04-14 | 2023-05-29 |  | ALP-GS0042 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2022-08-23 |  | 180000 |  | 100 | 2022-10-27 | 2022-10-27 | 3908450.55 |  | {"MANDT":"111","REFERENCE":70000032,"ONEVIEW":"21332X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-04-15","DATE07":"2023-05-30","DATE08":"2023-06-20","DATE09":"2023-08-04","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-04-15","FORECAST_END":"2023-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCAgY29tcGxldGVkIGFuZCBoYW5kZWQgb3ZlciB0byBBYnNhLgpGaW5hbCBQT0MgZm9yIFZPJ3MgaW4gcHJvZ3Jlc3M=","RATING":""} |  |  | C000070608 | PHASE11 | 2022-04-15 | 2023-05-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000450 | 2023-01-23 | 2023-02-27 |  |  | 2023-02-28 | 3398653.04 | 0 |  |  | C000070608 | 3398653.04 | CIP2023XP | 310346.3 |  | 0 | 0 |  | 0 |  | 0
70000033 | Alice Lane Podium Soundproofing | Phase 1 : Sound proofing Klausâs office and the Kopano meeting room The Podium CPF's main office (Klaus's office) is adjacent an eight (8) seater boardroom (kopano meeting room), when meetings are held the noise levels are such that all conversations taking place can be heard in the office plan area. Therefore, it was requested to provide acoustic treatment/ soundproofing in accordance with Absa architecs specification for the office and meeting room. In addition, the meeting room is to be enabled as a Microsoft Teams Room(MTR). MTR unit to be installed was held back against the meeting room enablement project by ITO and thus will not impact project costs. This cost will be allocated against the building cost centre (21843X) as agreed with Absa CRES. Phase 2: Increasing CPF Fish Bowl succeeding phase 1. |  |  | Region 1 | Gauteng South | 21843X | 1000-70039-01 | 15 Alice Lane Podium-Alice Ln-Sandton | N | 2022-10-23 | 2022-04-14 |  | ALP-GS0043 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-09-26 |  | 57065.62 |  | 100 | 2022-09-15 | 2022-09-15 | 656254.71 |  | {"MANDT":"111","REFERENCE":70000033,"ONEVIEW":"21843X","DATE01":"2022-05-21","DATE02":"2022-05-28","DATE03":"2022-06-18","DATE04":"2022-06-25","DATE05":"2022-07-16","DATE06":"2023-01-16","DATE07":"2023-05-29","DATE08":"2023-06-19","DATE09":"2023-08-03","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-16","FORECAST_END":"2023-05-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q29tcGlsaW5nIFBPQy4g","RATING":"Low"} |  |  | C000064024 | PHASE11 | 2023-01-16 | 2023-05-29 | PRESHANE MUNTHREE | Michael Maluleka | 23000483 | 2022-11-09 | 2022-10-24 |  |  | 2023-01-26 | 570656.28 | 0 |  |  | C000064024 | 570656.27 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000034 | Lakeside Installation of New 40KV | Civil Works :Building bund wall around existing plinth. - Inspect existing plinth structural integrity and supply report Supply, deliver, Install and Commission 40KVA Generator: - Connect generator to BMS - Perform Factory Acceptance Test (FAT) - Supply Fire extinguisher - Issue COC - Updated electrical layout - Install ClearVu Fence - First Fuel Fill - 6th and 12th Month Service level agreement Security Guarding Services; |  |  | Region 1 | Gauteng South | 36202X | 1000-71373-01 | Lakeside Mall-Tom Jones St-Benoni | N | 2022-11-14 | 2022-12-04 |  | ALP-GS0044 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-10-11 |  | 56076.17 |  | 100 | 2022-09-01 | 2022-09-01 | 644876.04 | Contigency not utilised. | {"MANDT":"111","REFERENCE":70000034,"ONEVIEW":"36202X","DATE01":"2022-07-12","DATE02":"2022-07-19","DATE03":"2022-08-09","DATE04":"2022-08-16","DATE05":"2022-09-06","DATE06":"2022-11-15","DATE07":"2022-09-05","DATE08":"2022-09-26","DATE09":"2022-11-10","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"231:7:21:7:21:70:-71:21:45:19","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-15","FORECAST_END":"2022-09-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Medium"} |  |  | C000080433 | PHASE11 | 2022-11-15 | 2022-09-05 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000485 |  |  |  |  | 2023-04-11 | 499463.27 | 0 |  |  | C000042624 | 560761.77 | CIP2023XP | 55684.33 |  | 0 | 0 |  | 0 |  | 0
70000035 | Protea Gardens New Generator | Supply and Install 45KVA Generator: - Supply and install clear view fencing - Supply Fire extinguisher - Perform Factory Acceptance TestÃÂ (FAT) - Issue COC - Updated electrical layout - Build a bund wall to house generator set. - 12 Months Service level agreement Security Guarding Services; Enhanced Cleaning Services |  | h | Region 1 | Gauteng South | 77139X | 1000-71394-01 | Protea Gardens Installation of a Generator | N | 2022-11-14 | 2022-12-04 |  | ALP-GS0045 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-10-17 |  | 771862.92 | BTB Approval | 100 | 2022-09-01 | 2022-09-15 | 771862.92 | %0A | {"MANDT":"111","REFERENCE":70000035,"ONEVIEW":"77139X","DATE01":"2022-05-21","DATE02":"2022-05-28","DATE03":"2022-06-18","DATE04":"2022-06-25","DATE05":"2022-07-16","DATE06":"2022-07-30","DATE07":"2022-12-30","DATE08":"2023-01-20","DATE09":"2023-03-06","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-30","FORECAST_END":"2022-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RnVsbCBQQyB2YWx1ZSBoYXMgYmVlbiBzdWJtaXR0ZWQgLSBJc3N1ZXMgd2l0aCBzdXBwbGllciBpbnZvaWNlLiAtUE0gdG8gcHJvdmlkZSBmZWVkYmFjayA=","RATING":""} |  |  | C000060048 | PHASE11 | 2022-07-30 | 2022-12-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000477 | 2022-10-04 | 2022-10-11 |  |  | 2023-01-09 | 671185.22 | 0 |  |  | C000044057 | 671185.22 | CIP2023XP | 66743.14 |  | 0 | 0 |  | 0 |  | 0
70000036 | Protea Glen Installation Generator | 1.Supply and Install 20KVA Generator: - Connect generator to BMS - Perform Factory Acceptance TestÃÂÃÂ (FAT) - Supply Fire extinguisher - Issue COC - Updated electrical layout - Build a bund wall to house generator set. - 12 Month Service level agreement 2.Security Guarding Services; 3.Cleaning Services on completion of installation. |  | h | Region 1 | Gauteng South | 35107X | 1000-70087-01 | Protea Glen Shopping Centre-Cnr R558 & Protea Blvd-Soweto | N | 2023-02-22 | 2023-03-29 |  | ALP-GS0046 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-10-17 |  | 55236.87 | BTB Approval | 100 | 2022-09-01 | 2022-08-24 | 635224.11 |  | {"MANDT":"111","REFERENCE":70000036,"ONEVIEW":"35107X","DATE01":"2022-05-21","DATE02":"2022-05-28","DATE03":"2022-06-18","DATE04":"2022-06-25","DATE05":"2022-07-16","DATE06":"2022-07-30","DATE07":"2023-03-30","DATE08":"2023-04-08","DATE09":"2023-05-23","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"405:7:21:7:21:14:243:9:45:18","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-30","FORECAST_END":"2023-03-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060049 | PHASE11 | 2022-07-30 | 2023-03-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000486 |  | 2022-10-11 |  |  | 2023-01-09 | 552368.79 | 525975 |  |  | C000044812 | 26393.91 | CIP2023XP | 54901.76 |  | 0 | 0 |  | 0 |  | 0
70000037 | Towers North Repairs Structural Cracks | Basement level 3 on a surface bed cracks category 1 cracks Basement Level 1 trough slab and Basement Level 2 trough slab category 2 cracks Upper Ground floor level coffer slab and Lower Ground floor level trough slab category 3 cracks 1st floor coffer slab with access flooring and 2nd floor coffer slab with access flooring category 3 cracks 3rd floor coffer slab with access flooring and 4th floor coffer slab with access flooring category 3 cracks 5th floor coffer slab with access flooring and 6th floor coffer slab with access flooring category 3 cracks Structural Engineer sign off Security Guarding Services |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2022-01-29 | 2022-12-30 |  | ALP-GS0050 | REL BUDG AVAC RESA SETC: |  | R | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2022-11-28 |  | 2959500 | Supported by CRES Eng | 60 | 2022-11-22 | 2022-11-22 | 985001.35 |  | {"MANDT":"111","REFERENCE":70000037,"ONEVIEW":"77381X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-01-29","DATE07":"2023-10-02","DATE08":"2023-12-22","DATE09":"2024-02-05","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":60,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"953:7:21:7:21:14:611:81:45:3","PROGRESS":42,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-29","FORECAST_END":"2023-10-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBvbiBleGVjdXRpb24gY29tbWVuY2VtZW50IGRhdGUgMDUvMTAvMjAyMyAKQ29tcGxldGlvbiAgZGF0ZSAzMC8xMC8yMDIzClByb2plY3Qgd2lsbCBiZSBmdWxseSBpbnZvaWNlZCB0aGlzIHllYXIgaW52b2ljZWQu","RATING":"Medium"} |  |  | C000108881 | PHASE11 | 2022-01-29 | 2023-10-02 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000472 | 2023-07-01 | 2023-07-31 | 2023-07-13 | 2023-09-06 | 2023-09-07 | 856522.91 | 0 |  |  | C000108881 | 856522.91 | CIP2023XP | 909614.22 |  | 0 | 0 |  | 0 |  | 0
70000038 | Expansion Joint Remedial Works | Expansion Joint Remedial Works |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2022-12-30 |  |  | ALP-KZ0007 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | F |  | CEASARS | 2022-08-16 |  | 129827.14 |  | 100 | 2022-05-05 | 2022-05-05 | 1493012.17 |  |  |  |  | C000028426 | PHASE09 | 2023-05-17 | 2023-06-30 | NANDE MAQUBELA | Juanita Van Coller | 23000460 | [5 empty] | 1298271.45 | 0 |  |  | C000142162 | 1298271.45 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000039 | Minor Works | Minor Works |  |  | Region 3 | KwaZulu-Natal | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg |  | 2022-11-03 |  |  | ALP-KZ2001 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 78784.03 |  | 100 | 2022-09-01 | 2022-09-01 | 906016.42 |  |  |  |  | C000060058 | PHASE11 | 2022-11-03 | 2022-12-09 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-09 | 787840.37 | 0 |  |  | C000044823 | 787840.37 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000040 | Minor Works | Minor Works |  |  | Region 3 | KwaZulu-Natal | 70634X | 1000-71145-01 | Arbour Crossing Retail Centre-Arbour Rd-Amanzimtoti |  | 2022-10-27 | 2022-11-30 |  | ALP-KZ2002 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-25 |  | 66910.56 |  | 100 | 2022-09-01 | 2022-09-01 | 781748.73 |  |  |  |  | C000060070 | PHASE11 | 2022-11-18 | 2023-02-13 | NANDE MAQUBELA | Juanita Van Coller | 23000476 |  |  |  |  | 2023-01-09 | 669105.67 | 0 |  |  | C000060070 | 669105.67 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000041 | Floor Space Consolidation Project | Floor Space Consolidation Project |  |  | Region 3 | Limpopo | 76717X | 1000-70518-01 | 76E Schoeman Street-Schoeman St-Polokwane |  | 2022-11-03 |  |  | ALP-LP0200 | REL BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-10 |  | 299822.76 |  | 100 | 2022-10-20 | 2022-10-20 | 3447961.77 |  | {"MANDT":"111","REFERENCE":70000041,"ONEVIEW":"76717X","DATE01":"2022-08-25","DATE02":"2022-09-22","DATE03":"2022-09-29","DATE04":"2022-09-29","DATE05":"2022-11-03","DATE06":"2022-12-03","DATE07":"2023-02-24","DATE08":"2023-04-07","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-03","FORECAST_END":"2023-02-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RmluYWwgaW52b2ljZSBkZWxheWVkIGR1ZSB0byBwZW5kaW5nIHNuYWdzIC0gRVRBIDMwIFNlcHQKIFBhcnQgaW52b2ljZSBzdWJtaXR0ZWQgLSBGaW5hbCBpbnZvaWNpbmcgZW5kIG9mIEp1bHkKMzAuMDguMjAyMyBPUCAtIFBhcnRpYWwgYmlsbGluZyBkb25lIGluIEF1ZzIz","RATING":""} |  |  | C000123971 | PHASE10 | 2022-12-03 | 2023-02-24 | NANDE MAQUBELA | Floyd Mofokeng | 23000452 |  | 2023-05-09 |  | 2023-05-08 | 2023-11-16 | 222621.05 | 0 |  |  | C000084168 | 2998227.63 |  | 2343303.55 |  | 0 | 0 |  | 0 |  | 0
70000042 | Installation of New 60kVA Generator and | Installation of New 60kVA Generator and 15kVA UPS (UPS from Absa ex stock |  |  | Region 3 | Mpumalanga | 0 | 1000-70606-01 | Absa Kriel |  | 2022-07-01 |  |  | ALP-MP0005 | CLSD AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-10 |  | 0 |  | Approved | 2022-09-15 | 2022-09-15 | 695762.61 |  |  |  |  | 0 | CLOSED |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000043 | Installation of New 40kVA Generator and | Installation of New 40kVA Generator and 15kVA UPS (UPS Absa ex stock) |  |  | Region 3 | Mpumalanga | 77316X | 1000-70622-01 | Matsamo Plaza-Cnr R570 & R323 Rd-Matsamo |  | 2022-09-01 |  |  | ALP-MP0006 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-07-28 |  | 61624.1 |  | 100 | 2022-09-15 | 2022-09-15 | 708677.22 |  | {"MANDT":"111","REFERENCE":70000043,"ONEVIEW":"77316X","DATE01":"2022-06-23","DATE02":"2022-07-21","DATE03":"2022-07-28","DATE04":"2022-07-28","DATE05":"2022-09-01","DATE06":"2022-10-01","DATE07":"2022-10-22","DATE08":"2022-12-06","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-01","FORECAST_END":"2022-10-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjbG9zZWQ=","RATING":""} |  |  | C000063435 | PHASE11 | 2022-10-01 | 2022-10-22 | Siyanda Dlamini | Thea Spamers | 23000293 |  |  |  |  | 2023-01-24 | 616241.06 | 0 |  |  | C000063435 | 616241.06 |  | 61357.33 |  | 0 | 0 |  | 0 |  | 0
70000044 | Reinstatement | Reinstatement |  |  | Region 3 | Mpumalanga | 77446X | 1000-70628-01 | Blue Haze Shopping Centre-Main Rd-Hazyview |  | 2022-10-30 |  |  | ALP-MP0201 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-05 |  | 5244.17 |  | 100 | 2022-10-03 | 2022-10-03 | 0 |  |  |  |  | C000061921 | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000045 | Installation of New 60kVA Generator | Installation of New 60kVA Generator |  |  | Region 3 | Mpumalanga | 77446X | 1000-70628-01 | Blue Haze Shopping Centre-Main Rd-Hazyview |  | 2022-11-03 |  |  | ALP-MP0202 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-19 |  | 88757.69 |  | 100 | 2022-10-27 | 2022-10-27 | 1020713.46 |  | {"MANDT":"111","REFERENCE":70000045,"ONEVIEW":"77446X","DATE01":"2022-08-25","DATE02":"2022-09-22","DATE03":"2022-09-29","DATE04":"2022-09-29","DATE05":"2022-11-03","DATE06":"2022-12-03","DATE07":"2022-12-24","DATE08":"2023-02-07","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-03","FORECAST_END":"2022-12-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDb21wbGV0ZWQgYW5kIGNsb3NlZA==","RATING":""} |  |  | C000063436 | PHASE11 | 2022-12-03 | 2022-12-24 | NANDE MAQUBELA | Thea Spamers | 23000470 |  |  |  |  | 2023-01-24 | 887576.93 | 0 |  |  | C000063436 | 887576.93 | CIP2023XP | 88373.46 |  | 0 | 0 |  | 0 |  | 0
70000046 | Procurement of White Goods | Procurement of White Goods |  |  | National | National | Unknown | 1000-70027-01 | Various Sites | U | 2022-02-08 | 2022-12-30 |  | ALP-N00023 | CLSD BUDG ISBD ACPT AVAC RESA SETC: |  | false | true |  | Lorri-Anne Louis |  |  | 2022 |  | U |  | LOUISR | 2022-02-01 |  | 86956.92 |  | 100 | 2021-11-25 | 2022-01-25 | 1000000 |  | {"MANDT":"111","REFERENCE":70000046,"ONEVIEW":"Unknown","DATE01":"2021-11-30","DATE02":"2021-12-07","DATE03":"2021-12-28","DATE04":"2022-01-04","DATE05":"2022-01-25","DATE06":"2022-02-08","DATE07":"2022-12-14","DATE08":"2023-01-04","DATE09":"2023-07-15","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"608:7:21:7:21:14:309:21:192:0","PROGRESS":79,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-02-08","FORECAST_END":"2022-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmVnaW9uYWwgQlVMSyBwcm9qZWN0Lg==","RATING":""} |  |  | C000060800 | PHASE11 | 2022-02-08 | 2022-12-14 | LUCIA AMUNGA | Michael Maluleka | 23000547 | 2022-02-20 | 2022-02-26 |  |  | 2023-01-11 | 5731.49 | 0 |  |  | 2899452 | 869569.22 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000047 | Replacement of UPS Batteries | Replacement of UPS Batteries |  |  | National | National |  |  | Building not in our database |  | 2022-02-08 | 2022-12-30 |  | ALP-N00024 | REL BUDG AVAC RESA SETC: |  | false | true |  | Lorri-Anne Louis |  |  | 2022 |  | V |  | LOUISR | 2022-02-01 |  | 130434.78 |  | 100 | 2021-11-25 | 2021-11-25 | 1500000 |  | {"MANDT":"111","REFERENCE":70000047,"ONEVIEW":"","DATE01":"2021-11-30","DATE02":"2021-12-07","DATE03":"2021-12-28","DATE04":"2022-01-04","DATE05":"2022-01-25","DATE06":"2022-02-08","DATE07":"2022-12-30","DATE08":"2023-09-29","DATE09":"2023-09-29","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"577:7:21:7:21:14:325:273:0:0","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-02-08","FORECAST_END":"2022-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTAvMDcvMjAyMy0gUHJvamVjdHMgc3RpbGwgaW4gcHJvZ3Jlc3MgcGFydGlhbCBpbnZvaWNlcyBzdWJtaXR0ZWQgdG8gZmluYW5jZQo=","RATING":""} |  |  | CC000012334 | PHASE06 | 2022-02-08 | 2022-12-30 | LUCIA AMUNGA | Michael Maluleka | 0 | 2022-02-23 | 2022-02-25 |  |  |  | 1304347.83 | 0 |  |  | 2899453 | 1304347.83 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000048 | Energy Performance Certification | Energy Performance Certification at 33 buildings with a size of above 2000 square meters |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | U | 2022-03-11 | 2022-12-15 |  | ALP-N00025 | REL BUDG AVAC RESA SETC: |  | false | true |  | Joseph Bwowe |  |  | 2022 |  | F |  | LOUISR | 2022-02-22 |  | 126444.75 |  | 100 | 2021-11-18 | 2021-11-18 | 1454114.72 |  | {"MANDT":"111","REFERENCE":70000048,"ONEVIEW":"Various","DATE01":"2021-12-31","DATE02":"2022-01-07","DATE03":"2022-01-28","DATE04":"2022-02-04","DATE05":"2022-02-25","DATE06":"2022-03-11","DATE07":"2022-12-15","DATE08":"2023-10-31","DATE09":"2023-10-31","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"120:7:21:7:21:14:279:320:0:5","PROGRESS":87,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-11","FORECAST_END":"2022-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDQvMDkgLSBQcm9qZWN0IGluIHByb2dyZXNzClNpdGVzIENvbXBsZXRlZCAtIDIwClNpdGVzIHJlbWFpbmluZyAgLSAxNSAoaW5jbHVkaW5nIDEzIHZvbHVudGFyeSBjZXJ0aWZpY2F0aW9ucyk=","RATING":""} |  |  | 2903903 | PHASE08 | 2022-03-11 | 2022-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 1264447.58 | 0 |  |  | 2903903 | 1264447.58 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000049 | Corporate LED Lighting Rollout (2022) | LED Lighting Manufacturing, Supply and Installation at 5 National Absa Corporate Sites |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | U | 2022-03-03 | 2022-12-15 |  | ALP-N00026 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Jaca Kgomotso | rollover |  | 2022 |  | U |  | LOUISR | 2022-02-22 |  | 8477282.35 |  | 100 | 2022-02-03 | 2023-03-17 | 8477282.35 | BFM legal N/A | {"MANDT":"111","REFERENCE":70000049,"ONEVIEW":"Various Sites","DATE01":"2021-12-23","DATE02":"2021-12-30","DATE03":"2022-01-20","DATE04":"2022-01-27","DATE05":"2022-02-17","DATE06":"2022-05-26","DATE07":"2022-11-30","DATE08":"2022-12-21","DATE09":"2023-07-31","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"493:7:21:7:21:98:188:21:222:14","PROGRESS":87,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-05-26","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBzdGlsbCBpbiBwcm9ncmVzcy4gTEwtIDE4LzA3LzIwMjMtIEtnIHRvIHByb3ZpZGUgZmVlZGJhY2sg","RATING":""} |  |  | C000059962 | PHASE11 | 2022-05-26 | 2022-11-30 | JOSEPH BWOWE | Michael Maluleka | 0 | 2022-03-23 | 2022-03-28 |  |  | 2023-01-09 | 2315389.66 | 0 |  |  | 2913431 | 7371549.87 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000050 | Retail LED Lighting Rollout (2022) | LED Lighting Manufacturing, Supply and Installation at 16 National Absa Retail Branches |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | U | 2022-03-03 | 2022-12-15 |  | ALP-N00027 | REL BUDG AVAC RESA SETC: |  | false | true |  | Jaca Kgomotso | rollover |  | 2022 |  | U |  | LOUISR | 2022-02-22 |  | 10835311.01 |  | 100 | 2022-02-03 | 2022-02-03 | 10835311.01 |  | {"MANDT":"111","REFERENCE":70000050,"ONEVIEW":"Unknown","DATE01":"2021-12-23","DATE02":"2021-12-30","DATE03":"2022-01-20","DATE04":"2022-01-27","DATE05":"2022-02-17","DATE06":"2022-03-26","DATE07":"2022-07-31","DATE08":"2022-08-21","DATE09":"2022-12-31","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"585:7:21:7:21:37:127:21:132:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-26","FORECAST_END":"2022-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIEtnIHRvIHByb3ZpZGUgZmVlZGJhY2s=","RATING":"Low"} |  |  | C000059960 | PHASE10 | 2022-03-26 | 2022-07-31 | JOSEPH BWOWE | Michael Maluleka | 0 | 2022-03-23 | 2022-03-28 |  |  | 2023-01-09 | 309041.47 | 0 |  |  | 2913404 | 9422009.69 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000051 | Absa Retail Documentation | Absa Retail Documentation Compliance |  |  | National | National | Various | 1000-70027-01 | Various Sites | U | 2022-06-30 | 2022-12-14 |  | ALP-N00029 | REL BUDG AVAC RESA SETC: |  | false | true |  | Sibulele Gwangqa | rollover |  | 2022 |  | U |  | LOUISR | 2022-06-01 |  | 744429.56 |  | 100 | 2022-05-12 | 2022-05-19 | 8560940 |  | {"MANDT":"111","REFERENCE":70000051,"ONEVIEW":"Various","DATE01":"2022-04-21","DATE02":"2022-04-28","DATE03":"2022-05-19","DATE04":"2022-05-26","DATE05":"2022-06-16","DATE06":"2023-06-30","DATE07":"2023-12-14","DATE08":"2024-01-04","DATE09":"2024-02-18","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":0,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"313:7:21:7:21:379:167:21:45:10","PROGRESS":72,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIENvbXBsaWFuY2UgcHJvamVjdCBpcyBjb21wbGV0ZWQuIDEwLzA3LzIwMjMtIFByb2plY3RzIHN0aWxsIGluIHByb2dyZXNzIHBhcnRpYWwgaW52b2ljZXMgc3VibWl0dGVkIHRvIGZpbmFuY2UuIExMLSAxOC8wNy8yMDIzLSBQcm9qZWN0IHN0aWxsIGluIHByb2dyZXNzLgoK","RATING":""} |  |  | C000060068 | PHASE06 | 2023-06-30 | 2023-11-30 | LUCIA AMUNGA | Michael Maluleka | 23000443 | 2022-08-17 | 2022-09-08 |  |  | 2023-01-09 | 7444295.65 | 0 |  |  | C000036550 | 7444295.65 | CIP2023XP | 473621.59 |  | 0 | 0 |  | 0 |  | 0
70000052 | Retail Documentation Compliance Programm | Absa Retail Documentation Compliance Phase 3 Part 1. 124 Sites for remedial work on the Absa Retail Documentation Compliance Programme |  |  | National | National | Unknown | 1000-70027-01 | Various Sites | U | 2022-06-30 | 2023-12-14 |  | ALP-N00030 | REL BUDG AVAC RESA SETC: |  | false | true |  | Sibulele Gwangqa | rollover |  | 2022 |  | U |  | LOUISR | 2022-06-01 |  | 1824578.69 |  | 100 | 2022-05-12 | 2022-05-19 | 20982655 | Approved. | {"MANDT":"111","REFERENCE":70000052,"ONEVIEW":"Unknown","DATE01":"2022-04-21","DATE02":"2022-04-28","DATE03":"2022-05-19","DATE04":"2022-05-26","DATE05":"2022-06-16","DATE06":"2023-06-30","DATE07":"2023-11-30","DATE08":"2024-01-31","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"679:7:21:7:21:379:153:62:29:0","PROGRESS":73,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIENvbXBsaWFuY2UgcHJvamVjdCBpcyBjb21wbGV0ZWQuIDEwLzA3LzIwMjMtIFByb2plY3RzIHN0aWxsIGluIHByb2dyZXNzIHBhcnRpYWwgaW52b2ljZXMgc3VibWl0dGVkIHRvIGZpbmFuY2UuIExMLTE4LzA3LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3MuCkFTOiAwMi4vMDgvMjAyMyAtIFVwZGF0ZWQgY2FzaCBmbG93IGRhdGUgLkxMLSAwNC8wOS8yMDIzLSBQcm9qZWN0IHN0aWxsIGluIHByb2dyZXNzIHBhcnRpYWwgaW52b2ljZXMgYXJlIGJlaW5nIHN1Ym1pdHRlZC4KMjcvMDkvMjAyMywgTEEgLSBVcGRhdGVkIGNhc2ggZmxvdyBkYXRlLiBGaW5hbmNpYWwgcm9sbCBvdmVyLiA=","RATING":"Medium"} |  |  | C000060055 | PHASE06 | 2023-06-30 | 2023-11-30 | JOSEPH BWOWE | Michael Maluleka | 23000447 | 2022-08-02 | 2022-08-04 |  |  | 2023-01-09 | 13967409.97 | 0 |  |  | C000033787 | 18245786.96 | CIP2023XP | 1517910.52 |  | 0 | 0 |  | 0 |  | 0
70000053 | Absa Retail Documentation Compliance Pha | Absa Retail Documentation Compliance Phase 1 & 2 Council Submissions |  |  | National | National | Unknown | 1000-70027-01 | Various Sites | U | 2022-06-30 | 2022-12-15 |  | ALP-N00031 | REL BUDG AVAC RESA SETC: |  | false | true |  | Sibulele Gwangqa | rollover |  | 2022 |  | U |  | LOUISR | 2022-06-01 |  | 6897901.02 |  | 100 | 2022-05-12 | 2022-05-12 | 6897901.02 | Approved. | {"MANDT":"111","REFERENCE":70000053,"ONEVIEW":"Unknown","DATE01":"2022-04-21","DATE02":"2022-04-28","DATE03":"2022-05-19","DATE04":"2022-05-26","DATE05":"2022-06-16","DATE06":"2023-06-30","DATE07":"2023-11-30","DATE08":"2024-01-31","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"679:7:21:7:21:379:153:62:29:0","PROGRESS":73,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIGNvbXBsaWFuY2UgcHJvamVjdCBoYXMgYmVlbiBjb21wbGV0ZWQuIDEwLzA3LzIwMjMtIFByb2plY3RzIHN0aWxsIGluIHByb2dyZXNzIHBhcnRpYWwgaW52b2ljZXMgc3VibWl0dGVkIHRvIGZpbmFuY2UuIExMLSAxOC8wNy8yMDIzLSBQcm9qZWN0IHN0aWxsIGluIHByb2dyZXNzLiBMTC0gMDQvMDkvMjAyMy0gUHJvamVjdCBzdGlsbCBpbiBwcm9ncmVzcyBwYXJ0aWFsIGludm9pY2VzIGFyZSBiZWluZyBzdWJtaXR0ZWQuCjI3LzA5LzIwMjMsIExBIC0gVXBkYXRlZCBjYXNoIGZsb3cgZGF0ZS4gRmluYW5jaWFsIHJvbGwgb3Zlci4gCg==","RATING":""} |  |  | C000024645 | PHASE06 | 2023-06-30 | 2023-11-30 | JOSEPH BWOWE | Michael Maluleka | 0 | 2022-06-29 | 2022-07-01 |  |  | 2022-07-14 | 5998174.8 | 0 |  |  | C000024645 | 5998174.8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000054 | Green Star Existing Building Performance | Green Star Existing Building Performance & Interiors Certification at 18 Absa Retail Branches |  |  | Energy | Various | Various | 1000-70027-01 | Various Sites |  | 2022-06-10 | 2022-12-15 |  | ALP-N00032 | REL BUDG AVAC RESA SETC: |  | false | true |  | Jaca Kgomotso | rollover |  | 2022 |  | V |  | LOUISR | 2022-06-01 |  | 347064.6 |  | 100 | 2022-05-22 | 2022-05-22 | 3991243.1 |  | {"MANDT":"111","REFERENCE":70000054,"ONEVIEW":"Unknown","DATE01":"2022-04-01","DATE02":"2022-04-08","DATE03":"2022-04-29","DATE04":"2022-05-06","DATE05":"2022-05-27","DATE06":"2022-06-10","DATE07":"2022-08-01","DATE08":"2023-10-31","DATE09":"2023-11-17","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"699:7:21:7:21:14:52:456:17:25","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-10","FORECAST_END":"2022-08-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwgMTgvMDcvMjAyMy0gS2cgdG8gcHJvdmlkZSBmZWVkYmFjawoKT00gUHJvamVjdCBleGVjdXRpb24gaW4gcHJvZ3Jlc3MuIEV4cGVjdGVkIGZ1bGwgUEM6IDMxIE9jdG9iZXIgMjAyMw==","RATING":"Low"} |  |  | C000022917 | PHASE08 | 2022-06-10 | 2022-08-01 | LUCIA AMUNGA | Michael Maluleka | 23000459 | 2022-05-24 | 2022-05-25 |  |  | 2022-07-07 | 3470646.09 | 0 |  |  | C000022917 | 3470646.09 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000055 | EOL Replacement of UPS Batteries and x6 | EOL Replacement of UPS Batteries and x6 UPS Units from ex stock |  |  | National | National | Unknown | 1000-70027-01 | Unknown Building - not in our database | U | 2022-11-01 | 2022-12-15 |  | ALP-N00033 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Sibulele Gwangqa |  |  | 2022 |  | U |  | LOUISR | 2022-10-18 |  | 485560.61 |  | 100 | 2022-10-20 | 2022-10-20 | 5583947.06 |  | {"MANDT":"111","REFERENCE":70000055,"ONEVIEW":"Unknown","DATE01":"2022-08-23","DATE02":"2022-08-30","DATE03":"2022-09-20","DATE04":"2022-09-27","DATE05":"2022-10-18","DATE06":"2022-11-01","DATE07":"2022-12-15","DATE08":"2023-10-31","DATE09":"2023-10-11","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"403:7:21:7:21:14:44:320:-20:21","PROGRESS":89,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-01","FORECAST_END":"2022-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTAvMDcvMjAyMy0gUHJvamVjdHMgc3RpbGwgaW4gcHJvZ3Jlc3MgcGFydGlhbCBpbnZvaWNlcyBzdWJtaXR0ZWQgdG8gZmluYW5jZSBuZXcgUE8gd2FzIHJhaXNlZCBmb3IgbW9yZSBzdG9jayB0byBiZSBkZWxpdmVyZWQuCjEzLzA5LzIwMjMtIExhc3QgaW52b2ljZSBvZiByZWNlbnQgUE8gaGFkIGJlZW4gcmVjZWl2ZWQgUE9DIGluIHByb2dyZXNzIGF3YWl0aW5nIEVTTSB0byB1cGxvYWQgQXNzZXQgcmVnaXN0ZXIgZm9yIE1ob2xpIHRvIHRvIHNpZ24gb2ZmLgo=","RATING":"Medium"} |  |  | C000050049 | PHASE11 | 2022-11-01 | 2022-12-15 | LUCIA AMUNGA | Floyd Mofokeng | 0 | 2022-11-07 | 2022-11-11 |  |  |  | 4855606.13 | 0 |  |  | C000064372 | 4855606.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000056 | Replacement of UPS Batteries for Bulk PO | Replacement of UPS Batteries for Bulk PO |  |  | National | Various |  | 1000-70027-01 | Building not in our database |  | 2022-11-01 | 2022-12-15 |  | ALP-N00035 | REL BUDG AVAC: |  | false | true |  | Lucia Amunga |  |  | 2022 |  | Variou |  | LOUISR | 2022-11-01 |  | 65217.39 |  | Approved | 2022-10-20 | 2022-10-20 | 750000 |  |  |  |  | C000060051# | PHASE |  |  | LUCIA AMUNGA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-09 | 652173.91 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000057 | Upgrade of HVAC Systems | Upgrade of HVAC Systems |  |  | Region 2 | Western Cape | 78147X | 1000-70893-01 | Absa Swellendam |  | 2022-04-15 |  |  | ALP-WC0005 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-04 |  | 760500 |  | Approved | 2022-03-17 | 2022-03-17 | 757002.45 |  |  |  |  | C000019181 | CLOSED | 2022-04-15 | 2022-04-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000058 | Reinstatement | Reinstatement |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Absa Bridge park |  | 2022-04-29 | 2022-07-29 |  | ALP-WC0006 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-20 |  | 1374966.88 |  | Approved | 2022-05-17 | 2022-05-17 | 1374966.89 |  |  |  |  | C000022953 | CLOSED | 2022-04-29 | 2022-07-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000059 | Brackenfell Shopping Centre -Minor Works | Brackenfell Shopping Centre - Minor Works |  |  | Region 2 | Western Cape | 77848X | 1000-70862-01 | Absa Brackenfell | N | 2022-06-15 | 2022-07-29 |  | ALP-WC0007 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-04-22 |  | 630071.42 |  | 100 | 2022-05-26 | 2022-05-26 | 630071.42 |  | {"MANDT":"111","REFERENCE":70000059,"ONEVIEW":"77848X","DATE01":"2022-03-03","DATE02":"2022-03-10","DATE03":"2022-04-26","DATE04":"2022-05-26","DATE05":"2022-05-26","DATE06":"2022-11-19","DATE07":"2022-12-01","DATE08":"2022-12-13","DATE09":"2022-12-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:47:30:0:177:12:12:18:10","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-19","FORECAST_END":"2022-12-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgRGVjIEZpbmFsIFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZQ==","RATING":"Low"} |  |  | C000060071 | PHASE11 | 2022-11-19 | 2022-12-01 | Michael Maluleka | RODERICK NEVAY | 23000492 |  |  |  |  | 2023-01-09 | 439832.09 | 0 |  |  | C000027224 | 630071.42 | CIP2023XP | 49332.22 |  | 0 | 0 |  | 0 |  | 0
70000060 | Absa Vredenburg- Waterproofing and External | Absa Vredenburg - Waterproofing and External Refurbishment |  |  | Region 2 | Western Cape | 77722X | 1000-70852-01 | Absa Vredenburg-Main St-Vredenburg | N | 2023-04-21 | 2023-12-21 |  | ALP-WC0008 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | F |  | CEASARS | 2022-05-23 |  | 981530.67 |  | 100 | 2022-12-08 | 2022-12-08 | 981530.67 | Contingency utilised Balance available R15 120.51 Incl Vat | {"MANDT":"111","REFERENCE":70000060,"ONEVIEW":"77722X","DATE01":"2022-05-23","DATE02":"2022-05-30","DATE03":"2022-09-19","DATE04":"2022-11-01","DATE05":"2022-12-08","DATE06":"2023-04-11","DATE07":"2023-05-25","DATE08":"2023-06-05","DATE09":"2023-06-26","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"434:7:112:43:37:124:44:11:21:18","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-11","FORECAST_END":"2023-05-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBKdW5lIC0gRmluYWwgUE9DIFN1Ym1pdHRlZA==","RATING":"Low"} |  |  | C000073571 | PHASE11 | 2023-04-11 | 2023-05-25 | RODERICK NEVAY | Michael Maluleka | 23000473 |  |  |  |  | 2023-03-13 | 853504.93 | 0 |  |  | C000073571 | 853504.93 |  | 75231.01 |  | 0 | 0 |  | 0 |  | 0
70000061 | Swellendam - Minor Works | Swellendam - Minor Works |  |  | Region 2 | Western Cape | 78147X | 1000-70893-01 | Eskom Building-Voortrek St-Swellendam | N | 2022-10-19 | 2022-11-03 |  | ALP-WC0013 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-07-28 |  | 591851.63 |  | 100 | 2022-09-01 | 2022-09-01 | 591851.63 |  | {"MANDT":"111","REFERENCE":70000061,"ONEVIEW":"78147X","DATE01":"2022-07-14","DATE02":"2022-06-04","DATE03":"2022-07-21","DATE04":"2022-09-01","DATE05":"2022-09-01","DATE06":"2022-10-18","DATE07":"2022-11-03","DATE08":"2022-11-10","DATE09":"2022-12-25","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:-40:47:42:0:47:16:7:45:23","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-18","FORECAST_END":"2022-11-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTAgTm92IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZSA=","RATING":"Low"} |  |  | C000060059 | PHASE11 | 2022-10-18 | 2022-11-03 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-09 | 35576.42 | 0 |  |  | C000041395 | 514653.91 |  | 25930.63 |  | 0 | 0 |  | 0 |  | 0
70000062 | Bridge Park Bridgeway Century City - Reinstatement Dilaps - Phase 2 - 3rd Floor West | Bridge Park Bridgeway Century City - Reinstatement Dilaps - Phase 2 - 3rd Floor West |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2022-12-01 |  |  | ALP-WC0014 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-09-28 |  | 2455435.82 |  | 100 | 2022-11-29 | 2022-11-29 | 2455435.82 | Balance of contingency remaining is R 59 483.44 Incl Vat | {"MANDT":"111","REFERENCE":70000062,"ONEVIEW":"36225X","DATE01":"2022-08-22","DATE02":"2022-08-29","DATE03":"2022-11-02","DATE04":"2022-11-29","DATE05":"2022-11-29","DATE06":"2023-01-15","DATE07":"2023-05-08","DATE08":"2023-05-24","DATE09":"2023-07-08","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:65:27:0:47:113:16:45:5","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-15","FORECAST_END":"2023-05-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFBhcnQgNCBTdWJtaXR0ZWQgRmluYWwgMjQgTWF5IC0gUiA5MTMgOTczLjQzClBPQyBQYXJ0IDMgUE9DIFN1Ym1pdHRlZCAyNCBBcHJpbCAtIFIgODE1IDMwMC41NQpQT0MgUGFydCAyIFN1Ym1pdHRlZCA1IEFwcmlsIC0gUiA4MSA4MDYuMjkKUE9DIFBhcnQgMSBTdWJtaXR0ZWQgOSBKYW4gLSBSIDE5MiA4NjUuMzA=","RATING":"Low"} |  |  | C000063118 | PHASE11 | 2023-01-15 | 2023-05-08 | RODERICK NEVAY | Michael Maluleka | 23000456 |  |  |  |  | 2023-01-23 | 2135161.58 | 167708.96 |  |  | C000063118 | 1967452.62 |  | 212519.12 |  | 0 | 0 |  | 0 |  | 0
70000063 | Dilaps | Dilaps |  |  | Region 2 | Western Cape | 78094X | 1000-70879-01 | Heidelberg-Cnr Riebeeck & Krige St-Heidelberg | N | 2022-12-01 |  |  | ALP-WC0015 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-11-18 |  | 688867.54 |  | 100 | 2022-11-21 | 2022-11-21 | 688867.54 | Contingency Remaining R 46062.89 Incl Vat | {"MANDT":"111","REFERENCE":70000063,"ONEVIEW":"78094X","DATE01":"2022-09-22","DATE02":"2022-09-29","DATE03":"2022-10-20","DATE04":"2022-10-27","DATE05":"2022-11-17","DATE06":"2022-12-01","DATE07":"2023-02-15","DATE08":"2023-02-23","DATE09":"2023-04-09","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"220:7:21:7:21:14:76:8:45:8","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-01","FORECAST_END":"2023-02-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjMgRmViIGZpbmFsIFBPQyBTdWJtaXR0ZWQ=","RATING":"Low"} |  |  | C000063119 | PHASE11 | 2022-12-01 | 2023-02-15 | RODERICK NEVAY | Michael Maluleka | 23000482 |  |  |  |  | 2023-01-23 | 599015.24 | 48055.45 |  |  | C000063119 | 550959.79 |  | 56842.06 |  | 0 | 0 |  | 0 |  | 0
70000064 | New Water tank with booster pump and fil | New Water tank with booster pump and filtration systemAbsa Calvinia has no backup water supply system in place. The area is constantly experiencing water outages, whereby on some days it would extend to more than 5 days. During these water scarcity period, the branch is forced to free the staff members in order to comply with section 43 of the Occupational Health and Safety Act, 1993 Act No, 85 of 1993), stating that every employee must have access to drinking water and for sanitation in the workplace. This request seeks approval to install a 1500lt water tank which is the correct size to fit in the earmarked space, and also will be able to accommodate the number of staff for a maximum of 5 days of a water outage. A water filtration system will be installed in the tank for safety standards and a water pump system in order to maintain water pressure.Note: Supported by BFM Engineering.Scope of Work Supply and Installation of a 1500L water tank (1no) 2 x Big blue tripple filter system with carbon block Concrete base for the water tank, 2,00 x 2,00 M Anti Theft cage (with lock) The tank is positioned within Absa secured primise with lockable gate. Non return valve, 25mm Torentti spring loaded P/N 16 (16 BAR) & Fittings Polycop piping & fittings 20m depending on the tie in point Pump should be a 240 V A/C 0,75 A, pump with a pressure control A 30A isolator feeding the pump and control panel Electrical: a dedicated 20A breaker to be catered for in the main DB linked to the emergency power circuit. Allowance for COC Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test has been catered for Allowance for OHS file included |  |  | Region 3 | Northern Cape | 78015X | 1000-70869-01 | Absa Calvinia-Hoop St-Calvinia |  | 2021-03-31 |  |  | ASP-CR0122 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NGIDIN | 2021-03-10 |  | 7904.36 | Approved | 100 | 2022-11-10 | 2023-10-07 | 90900.16 |  | {"MANDT":"111","REFERENCE":70000064,"ONEVIEW":"78015X","DATE01":"2021-01-20","DATE02":"2021-02-17","DATE03":"2021-02-24","DATE04":"2021-02-24","DATE05":"2021-03-31","DATE06":"2021-04-30","DATE07":"2021-05-21","DATE08":"2021-07-05","DATE09":"2021-07-31","DATE10":"2021-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-04-30","FORECAST_END":"2021-05-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIFBPQyBwYWNrIHN1Ym1pdHRlZCBlbmQgTWF5IDIwMjMu","RATING":""} |  |  | C000063000 | PHASE11 | 2021-04-30 | 2021-05-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000550 |  |  |  |  | 2023-01-20 | 79043.62 | 0 |  |  | C000063000 | 79043.62 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000065 | External Minor Works - Absa Ladybrand (C | External Minor Works Absa Ladybrand (CIP 2022)At Absa Ladybrand, the last external refresh was done in 2015. The paintwork on the external structures deteriorated over time and requires to be repainted. That includes external walls, window frames, burglar guards, downpipes and gutters. Floor tiles in the ATM lobby deteriorated over time and requires to be replaced. In addition the branch requested to replace a portion of the lawn with pavement bricks. The refurbishment will enhance the look and feel of the branch. Note: Supported by CRES VP.Scope of works: Preparation of previously painted walls and apply new paint, one under coat and two final coat of Dulux West coast to the entire external walls (125m2) Prepare and paint windows, burglar guards and seals with one under coat and two final top coat of Dulux white metal oil base paint (105m2) Remove existing tiles and install new (600 x 600 mm signature grey floor tiles (21m2) Remove grass & flowers and install new pavement brick around the trees (18m2) Prepare and apply painting to existing palisade fencing & carports metal oil based paint (75m2) Provision made for security for the duration of project. |  |  | Region 3 | Free State |  | 1000-71556-01 | Building not in our database |  | 2022-06-01 | 2022-09-30 |  | ASP-CR0164 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | NGIDIN | 2021-05-12 |  | 350000 |  | 100 | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000060171 | IGNORE | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-09 | 63.5 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000066 | Installation of carport structures (CIP | Installation of carport structures (CIP 2022)This request seeks approval for the erection of a carport to accommodate x3 vehicle parking bays for staff members at Absa Trompsburg branch. The staff is currently parking their vehicles under trees at the back of the building and this exposes the vehicles to adverse weather conditions. Note: Approved by RIF. This project was prioritised and spend will be allocated from the corporate budget. Confirmation received that council approval is not required.Scope of works: Clear and level area identified for new carports. Excavate for carport support. (2,4m height) Install upright support and backfill using in situ concrete. Erect a carport for 3x vehicles at the back of the branch. Install IBR roof sheeting. (8,9m x6m) Compact , trim and level to final ground. |  |  | Region 3 | Free State | 79334X | 1000-71585-01 | Absa Trompsburg, 55 Voortrekker Street, Trompsburg |  | 2022-04-05 | 2022-05-20 |  | ASP-CR0197 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Freeho |  | NGIDIN | 2021-07-13 |  | 11215.49 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913269 | CLOSED | 2022-04-05 | 2022-05-20 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000067 | Supply outstanding items for the new RHO | Supply outstanding items for the new RHO BloemfonteinThis request seeks approval to provide items required at the new RHO building. The new building that the office is relocating to does not have all the items available and were not included in the Capital project. Note: Supported by CRES VP. Scope of works: Supply toilet brushes (x36) Supply key cabinet (x3) Supply tags (x700) Supply A4 perspex stands for meeting rooms (x20) Supply A4 poster frame (x24) |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Absa Bloemfontein RHODonald Murray Ave,Bloemfontein |  | 2021-10-27 | 2021-12-28 |  | ASP-CR0220 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mercy Ngidi |  |  | 2022 |  | Freeho |  | NGIDIN | 2021-09-30 |  | 1359.41 |  | Approved | 2022-06-23 | 2022-06-23 | 0 |  |  |  |  | C000023412 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000068 | Generator safety compliance upgrade | Generator safety compliance upgrade |  |  | Region 3 | Free State | 78908X |  | Absa Botshabelo Shopping Centre |  | 2022-01-11 | 2022-01-31 |  | ASP-CR0230 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-13 |  | 9212.94 |  | Approved | 2022-01-19 | 2022-01-19 | 0 |  |  |  |  | 2897114 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000069 | Replacement of teller chairs (2022 CIP)T | Replacement of teller chairs (2022 CIP)This request is for the replacement of the teller chairs at the Absa Vryburg Branch. The existing chairs are old and worn out and therefore requires to be replaced. Note: Project approved at RIF. The stores confirmed no stock available. OHS Approved spec as per acceptable standard.Scope of works: Supply and delivery of 4 x teller chairs Specification: (ST15.2) |  |  | Region 3 | North West | 77745X | 1000-71604-01 | Absa Vryburg,88 Market Street,Vryburg |  | 2022-02-28 | 2022-03-31 |  | ASP-CR0231 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-27 |  | 2008 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900290 | CLOSED | 2022-02-28 | 2022-03-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000070 | Minor Works- Absa Boitekong Mall (2022 C | Minor Works Absa Boitekong Mall (2022 CIP)Absa Boitekong has never been revamped since its inception in 2012. There was painting work conducted in 2018 to the banking hall and teller area however, the ATM room was excluded. The walls in the ATM room have visible surface defects and was therefore recommended to be repainted. In addition, the branch requires 10x new additional plastic customer chairs. Note: Project approved at RIF. The stores confirmed no stock available.Scope of works: Repainting walls in Absa grey colour in the ATM room (352sqm ) Supply of 10 x new customer chairs x10 (ST15.3) Covid 19 deep cleaning will be conducted upon project completion. Provision made for an additional security guard. |  |  | Region 3 | North West | 22485X | 1000-71245-01 | Absa Boitekong Mall,Cnr Thlou Street & R510,Rustenburg |  | 2022-02-28 |  |  | ASP-CR0232 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-27 |  | 4110.5 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900271 | CLOSED | 2022-02-28 | 2022-03-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000071 | Additional plug point for TV relocation. | Additional plug point for TV relocation.Absa Diamond Pavilion has a banking hall TV that is located where it does not serve the intended purpose nor add any value as the display is not visible to customers. A new electrical point is therefore required at the new identified location as part of the TV relocation.Note: Supported by Engineering.Scope of works: Supply and install 2 X electrical power points. Issue COC for the additional power point. TV relocation by others. No additional security guard required for the project. Touch point covid clean will be carried out upon project completion. |  |  | Region 3 | Northern Cape | 78575X | 1000-71352-01 | Absa Diamond Pavilion, Shop 88-89, Diamond Pavilion Shopping Mall, cnr Olivier and Mac Dougall Street, Kimberley |  | 2022-03-31 | 2022-04-29 |  | ASP-CR0233 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-01 |  | 218.98 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912263 | CLOSED | 2022-03-31 | 2022-04-29 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000072 | Replacement of an air conditioning unit | Replacement of an air conditioning unit and a drip tray installation |  |  | Region 3 | Free State | 79334X | 1000-71585-01 | Absa Trompsburg-Voortrekker St-Trompsburg |  | 2022-03-21 | 2022-04-21 |  | ASP-CR0235 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-02-10 |  | 5369.1 |  | 100 | 2022-03-10 | 2022-03-10 | 0 |  |  |  |  | C000059600# | IGNORE | 2022-03-21 | 2022-04-21 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-06 | 1413 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000073 | Replacement of vinyl tiles in ATM room | Replacement of vinyl tiles in ATM room (CIP 2022)Absa Calvinia has never had a revamp since it s inception . The vinyl tiling at the ATM room floor has scratches and require replacement. This request seeks approval to replace existing tiling with new. Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RIF Approval Received.Scope of works: Prep and replace vinyl tiles in ATM room (16m2) Covid 19 deep cleaning will be conducted upon project completion. Regional security manager confirmed that no project guarding required |  |  | Region 3 | Northern Cape | 78015X | 1000-70869-01 | Absa Calvinia, 20 Hoop Street, Calvinia |  | 2022-06-01 | 2022-06-30 |  | ASP-CR0237 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-16 |  | 2152.72 |  | Approved | 2022-05-18 | 2022-05-18 | 0 |  |  |  |  | C000013078 | CLOSED | 2022-06-01 | 2022-06-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000074 | Procurement of new chairs and a seater t | Procurement of new chairs and a seater table (CIP 2022)Absa Warrenton Branch has old and worn out chairs, and was requested by the planner that these be replaced with new. The request is for the supply and delivery of teller chairs, staff chairs, customer chairs, waiting area chairs, back of house chairs, meeting room chairs and a 4 seater table. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets. Support obtained from OHS for the spec of the chairs. Confirmation received from supplier that meeting room chairs are adjustable. Scope of works: Supply and deliver the following chairs:x4 Teller Chairs (ST 15/02)x4 Normal staff chairs (ST 15/01)x6 Customer chairs (S40B)x4 Waiting area plastic chairs (S40B) - Black/Grey x4 Back office chairs (S42A)x1 Table 4 Seater (T1.2) x7 Meeting room chairs (S41.1G) |  |  | Region 3 | Northern Cape | 21822X | 1000-71321-01 | Absa Warrenton, 54B Uys Street, Warrenton |  | 2022-03-07 | 2022-04-30 |  | ASP-CR0238 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-16 |  | 10601.01 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2907251 | CLOSED | 2022-03-07 | 2022-04-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000075 | Procurement of new chairs and a seater t | Procurement of new chairs and a seater table (CIP 2022)Absa Postmasburg branch has old and worn out chairs, and was requested by the planner that these be replaced with new. The request is for the supply and delivery of teller chairs, staff chairs, customer chairs, waiting area chairs, back of house chairs, meeting room chairs and a 4 seater table. . Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets. Support obtained from OHS for the spec of the chairs. Confirmation received from supplier that meeting room chairs are adjustable. Scope of Works: Supply and deliver the following chairs:x4 Teller Chairs (ST 15/02)x7 Normal staff chairs (ST 15/01)x8 Customer chairs (S40B)x7 Waiting area plastic chairs (S40B) - Black/Grey x4 Back office chairs (S42A)x1 Table 4 Seater (T1) x9 Meeting room chairs (S41.1G) |  |  | Region 3 | Northern Cape | 21312X | 1000-71316-01 | Absa Postmasburg, 7 Springbok Street, Postmasburg |  | 2022-03-07 | 2022-04-29 |  | ASP-CR0239 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-16 |  | 14086.7 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2907252 | CLOSED | 2022-03-07 | 2022-04-29 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000076 | Dilaps- Remove security Equipment | Dilaps Remove security Equipment |  |  | Region 3 | North West | 77852X | 1000-71301-01 | Absa Klerksdorp |  | 2022-03-15 |  |  | ASP-CR0240 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-04 |  | 593.2 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2906686 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000077 | COC to be issued | COC to be issued |  |  | Region 3 | Free State | 78989X | 1000-71565-01 | Absa Zastron |  | 2022-03-15 |  |  | ASP-CR0241 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-04 |  | 4497.63 |  | Approved | 2022-03-04 | 2022-03-04 | 0 |  |  |  |  | 2906687 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000078 | Installation of filtration system, pipe | Installation of filtration system, pipe rectification and galvanised steel cage.Absa Viljoenskroon has an existing 5000 litre water tank, with booster pump and pressure control unit. During water outages the branch does not have water as the water from the tank is pumped back into the municipal line leaving the branch without back up water. The pipe reticulation needs to be rectified by installing non return valves to ensure preservation of water already in the water tank and a bypass line needs to be catered for in the event of pump failure or in the event of tank maintenance to allow the branch to have water constantly. The branch further indicated that the water supplied by the municipality is for both drinking and sanitary use. The water has unpleasant taste, the worst usually being immediately after water has been restored following a disruption to supply. The branch therefore opted to purchasing of bottled water as a solution to the water quality challenge. The request is therefore to install a ( Big Blue) filtration system at the point of entry (POE) to the branch water reticulation systems. This type of treatment provides chemical free filtered water to all water points within the building.It has further been reported that there has been several incidents of pump theft and the recommendation was made to install a galvanised steel cage to safeguard the pump.Note: Supported by Engineering and prioritised by CRES. To be funded from CIP 2022 cancelled project budget allocated to Sannieshof Water tank was R90k.Scope of works: Remove paving and dig to expose existing pipes. Disconnect all the pipes from the tank to the branch. Connect a T coupling on the municipality line that will feed the tank and Absa branch. Install PVC piping and taking into consideration to install non return and stop valves before and after the Absa meter, water tank, pump (if installed after the tank no need to install before the pump) Install filtration system to the building (2 x Big Blue Sediment and Big Blue Carbon block filtration system). Secure the pump with galvanised steel cage. Test the reticulation, bury pipes and reinstate paving Provide schematic diagram of the improved reticulation. |  |  | Region 3 | Free State | 78481X | 1000-71540-01 | Absa Viljoenskroon, cnr Engelbrecht and Church Street, Viljoenskroon |  | 2022-03-25 | 2022-05-31 |  | ASP-CR0242 | CLSD BUDG AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2022 |  | L |  | CEASARS | 2022-03-11 |  | 2342.19 | Cancelled | 1 | 2022-03-29 | 2023-10-07 | 26935.25 |  | {"MANDT":"111","REFERENCE":70000078,"ONEVIEW":"78481X","DATE01":"2022-01-14","DATE02":"2022-01-21","DATE03":"2022-02-11","DATE04":"2022-02-18","DATE05":"2022-03-11","DATE06":"2022-03-25","DATE07":"2022-05-31","DATE08":"2022-06-21","DATE09":"2022-05-09","DATE10":"2022-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":1,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-25","FORECAST_END":"2022-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDYW5jZWxsZWQ=","RATING":""} |  |  | C000061736 | PHASE11 | 2022-03-25 | 2022-05-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-17 | 23421.96 | 0 |  |  | C000061736 | 23421.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000079 | Minor Works- Absa Nampo Park (CIP 2022) | Minor Works Absa Nampo Park (CIP 2022) Absa Nampo park was last revamped approximately ten years ago and the internal walls are still reflecting the old Absa wall paper and floor finishes in speckled tiles. The furniture has deteriorated over the years and requires to be replaced. It was therefore recommended that the internal walls be repainted with the new Absa lux colours and the floor tiles be replaced with the current VI floor tiles spec.Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets. Scope of Works: Remove wall paper and prepare walls to be repainted in Absa lux colours (385m2) Replace tiling at banking hall with Absa grey 600x600 porcelain tiles (27m2) Replace carpets in various areas with 500x500 belgotex equinox carpet tiles (101m2) Supply new chairs to replace worn out chairs (x4) Supply and install new VI internal signage in banking hall Refurbish wooden teller counters and varnish accordingly Security Services for the duration of project Advanced Covid Clean will be carried out at the end of the project. |  |  | Region 3 | Free State | 79033X | 1000-71568-01 | Absa Nampo Park, R30, Bothaville, Free State |  | 2022-03-18 | 2022-04-29 |  | ASP-CR0243 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-11 |  | 43279.16 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | C000018130 | CLOSED | 2022-03-18 | 2022-04-29 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000080 | Supply and install internal signage in t | Supply and install internal signage in the banking hall (CIP 2022)At Absa Waterfall Mall, the teller and customer areas do not have signage numbering (7 & 8). This request seeks approval to supply and install new signage to the areas identified.Note: Approved at RIF. Absa Design Approval obtained. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply and install burgandy red 702 vinyl cut out numbers Size 150mm high (X 2) Covid wipe down to be done on all touch points on completion. |  |  | Region 3 | North West | 76962X | 1000-71602-01 | Absa Waterfall Mall,1 Augrabies Avenue, Rustenburg |  | 2022-04-14 | 2022-05-31 |  | ASP-CR0244 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-25 |  | 247 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913280 | CLOSED | 2022-04-14 | 2022-05-31 | Floyd Mofokeng | SIYANDA DLAMINI | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000081 | Frosting to shopfront windows (CIP 2022) | Frosting to shopfront windows (CIP 2022)At Absa Trompsburg, one staff office window does not have frosting and the request is to install frosting on the window for privacy when engaging with staff. Additionally, there are other shopfronts in the banking hall which also do not have frosting thereby allowing sun rays to cause discomfort inside the branch. This request seeks approval to install frosting to the identified areas.Note: Approved at RIF. Absa Design Approval obtained. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Cut and apply frosted vinyl to indicated shopfront windows X 5 Covid wipe down to be done on all touch points on completion. |  |  | Region 3 | Free State | 79334X | 1000-71585-01 | Absa Trompsburg,55 Voortrekker Street,Trompsburg |  | 2022-04-14 | 2022-05-31 |  | ASP-CR0245 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-25 |  | 1187.5 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913204 | CLOSED | 2022-04-14 | 2022-05-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000082 | Supply and Install a customer helpline b | Supply and Install a customer helpline booth & internet kiosk (CIP 2022)Absa Theunhassen branch was build without an internet kiosk. The regional team identified a need to install an internet kiosk and a customer helpline booth for customer service, in line with the digital migration requirements. It was therefore recommended that these items be supplied and installed.Note: Spec approved by Absa design. Project approved at RIF. Engineering supported.Scope of Works: Install 1x wall mounted customer helpline booth. Install 1x internet kisok desk . Install online banking decal to new internet kiosk screen. Install 1x powerpole & issue COC . Standard Covid 19 wipe down conducted after project completion. |  |  | Region 3 | Free State | 79293X | 1000-71578-01 | Absa Theunissen,46 Van Heerden Street, Theunhassen |  | 2022-06-03 | 2022-06-30 |  | ASP-CR0246 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-25 |  | 4036.69 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912260 | CLOSED | 2022-06-03 | 2022-06-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000083 | Installation of a non-return valveThe Ab | Installation of a non return valveThe Absa Bank Mahikeng is a retail branch that has a ground and first floor linked to a 5000litre water tank connected to the municipality water network. It has been observed that water consumption in this building is very high and the water meter is constantly running. Upon investigation it was established that the high water consumption emanates from the installation method used during the coupling of the water tank into the municipality system. The absence of non return valves causes a constant flow of water through the meter as the pipe work loops back into the municipality system. The installation was done during the previous account and no records of the supplier could be traced. It is recommended that a non return valve be installed to regulate the flow of water through the reticulation pipework. Note: Supported by Engineering and prioritised by CRES. Council approval not required as the pump is in the LandLord building space. LL approval obtained. To be funded from CIP 2022 cancelled project budget allocated to Sannieshof Water tank was R90k.Scope of works: Carry out modification on the pipe that returns water to the municipal line To install a non return valve. (75mm) Supply all pipes and fittings to complete the work. |  |  | Region 3 | North West | 77725X | 1000-71297-01 | Absa Mahikeng, 12 Main Street, Mahikeng |  | 2022-02-15 | 2022-05-31 |  | ASP-CR0247 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-30 |  | 858.9 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913551 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000084 | Supply and install blinds to office wind | Supply and install blinds to office windowsThis request seeks approval to replace the existing blinds and install new to windows without blinds. The existing blinds were installed incorrectly 2 years ago to the underside of the ceiling. This method of installation is therefore causing the blinds to be unstable and can potentially break. In addition, some of the office windows have no blinds and the sun light is causing discomfort to the staff inside the branch. Note: RIF approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply and install brushed aluminium venecian blinds to all windows in offices on the 1st floor. (48m) Duration of the project is 1 day (during normal working hours). Manned Guarding Services for the duration of the project. Covid wipe down daily on all touch points and deep cleaning of the site will be done by contractor. |  |  | Region 3 | North West | 21941X | 1000-70917-01 | Absa Zeerust,Cnr Church & President Street,Zeerust |  | 2022-06-01 | 2022-09-30 |  | ASP-CR0248 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-31 |  | 7262.52 |  | Approved | 2022-05-04 | 2022-05-04 | 0 |  |  |  |  | C000025757 | CLOSED | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000085 | Alternative Structural Opinion | Alternative Structural Opinion |  |  | Region 3 | Northern Cape | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley |  | 2022-04-11 | 2022-06-30 |  | ASP-CR0252 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | CEASARS | 2022-04-07 |  | 8479 |  | 100 | 2022-04-25 | 2022-04-25 | 0 |  |  |  |  | C000067418 | IGNORE | 2022-04-11 | 2022-06-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-02-10 | 23645 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000086 | External Minor Works - Absa Brandfort (C | External Minor Works Absa Brandfort (CIP 2022)At Absa Brandfort, the previous external refresh was done in 2019. The paintwork on the external structures deteriorated over time and requires to be repainted. That includes external walls, carport, window frames, burglar guards, downpipes and gutters. Parking bay concrete pavement has also worn out. This request seeks approval to perform the listed refurbishment to enhance the look and feel of the branch.Note: Supported by CRES VP.Scope of works: Preparation of previously painted walls and apply new paint, one under coat and two final coat of Dulux West coast to the entire external walls (273m2) Prepare and paint windows, burglar guards and seals with one under coat and two final top coat of Dulux white metal oil base paint (124m2) Prepare and paint downpipes, gutters with one under coat and two final top coat of Dulux white metal oil base (55lm) and clean all gutters Replace the carports shade netting side covering only (20m2) Regravelling of the drive through to the parking bays with concrete stones (90m2) Repave the parking bay (15Mpa concrete) Lump sum item, (120m2) Repair of loose existing wire fence tighten and make good. (6m) Provision made for security for the duration of project. |  |  | Region 3 | Free State | 79333X | 1000-71584-01 | Absa Brandfort,51 Voortrekker Street,Brandfort |  | 2022-06-01 | 2022-09-30 |  | ASP-CR0253 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | CEASARS | 2022-04-07 |  | 30235.2 |  | Approved | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000019969 | CLOSED | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000087 | External Minor Works - Absa Virginia (CI | External Minor Works Absa Virginia (CIP 2022)At Absa Virginia, a last external building refresh was done in 2019. The paintwork on the external structures deteriorated over time and requires to be repainted. That includes external walls, window frames, burglar guards, downpipes, palisade fence and gutters. This request seeks approval to perform the listed refurbishment to enhance the look and feel of the branch.Note: Supported by CRES VPScope of works: Preparation of previously painted walls and apply new paint, one under coat and two final coat of Dulux West coast to the entire external walls (766m2) Prepare and paint windows, burglar guards and seals with one under coat and two final top coat of Dulux white metal oil base paint (135m2) Prepare and paint downpipes, gutters with one under coat and two final top coat of Dulux white metal oil base (84lm) and clean all gutters Sand and repaint existing steel palisade fencing 1,8m high (35m) Refurbishment of external drain pipes (12m) Provision made for security for the duration of project. |  |  | Region 3 | Free State | 79312X | 1000-71582-01 | Absa Virginia,32 Virginia Gardens,Virginia |  | 2022-08-26 | 2022-09-30 |  | ASP-CR0254 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | CEASARS | 2022-04-07 |  | 21514.23 |  | Approved | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000069881 | CLOSED | 2022-08-26 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-02-22 | 215142.31 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000088 | External Minor Works - Absa Bothaville ( | External Minor Works Absa Bothaville (CIP 2022)At Absa Bothaville, the last external refresh was done in 2016. The paintwork on the external structures deteriorated over time and requires to be repainted. That includes external walls, garmazine finish, window frames, burglar guards, downpipes and gutters. This request seeks approval to perform the listed refurbishment to enhance the look and feel of the branch.Note: Supported by CRES VPScope of works: Preparation of previously painted walls apply one under coat and two final coats Dulux WestPaint to the building externally and to repair the gamazine finished sections (705m2) Repair damaged rain water goods gutters and down pipes (8no) Paint external window frames and burglar bars with one under coat and two final coats of Dulux Old glory. (120m2) Supply and install Flock Reflector Bird Deterrent to at least six of the highest points on the building (6no) Provision made for additional security. |  |  | Region 3 | Free State | 79114X | 1000-71573-01 | Absa Bothaville-President St-Bothaville |  | 2022-06-01 | 2022-09-30 |  | ASP-CR0255 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2022 |  | F |  | CEASARS | 2022-04-08 |  | 30078.08 | Approved | 100 | 2022-04-26 | 2023-10-07 | 44580.11 |  | {"MANDT":"111","REFERENCE":70000088,"ONEVIEW":"79114X","DATE01":"2022-03-23","DATE02":"2022-03-30","DATE03":"2022-04-20","DATE04":"2022-04-27","DATE05":"2022-05-18","DATE06":"2022-06-01","DATE07":"2022-09-30","DATE08":"2022-10-21","DATE09":"2022-07-16","DATE10":"2022-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-01","FORECAST_END":"2022-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2Vk","RATING":""} |  |  | C000060170 | PHASE11 | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-31 | 38765.31 | 0 |  |  | C000019968 | 300780.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000089 | External Minor Works - Absa Odendaalsrus | External Minor Works Absa Odendaalsrus (CIP 2022)At Absa Odendaalsrus, the last external work refresh was done in 2017. The paintwork on the external structures deteriorated over time and requires to be repainted. That includes external walls, carport external, window frames, burglar guards downpipes and gutters. There is also a precast fence that is posing a hazard because it is unstable and could fall anytime. Additionally, there are x4 housing flats with worn out painting on the internal walls which requires to be repainted. This request seeks approval to perform the listed refurbishments to enhance the look and feel of the branch.Note: Supported by CRES VPScope of works: Preparation of previously painted walls and apply new paint, one under coat and two final coat of Dulux West coast to the entire external walls (676m2). Prepare and paint carports with metal oil based paint (63m2). Prepare and paint windows, burglar guards and seals with one under coat and two final top coat of Dulux white metal oil base paint (180m2). Prepare and paint downpipes, gutters with metal oil based paint & clean all gutters (64m2) . Remove and cartaway existing precast wall fence 1,8m high (7m). Neaten up poly prop pipes at back with new wall claps (35m). Sand and repaint palisade fencing with metal oil based paint (68m2). Preparation of previously painted walls and apply new paint, one under coat and. two final coat of Dulux West coast (335m2). Prepare and paint to the ceiling with white paint (25m2) . Supply and install and apply varnish wooded meranti skirting (30m). Provision made for security for the duration of project. |  |  | Region 3 | Free State | 79056X | 1000-71599-01 | Absa Odendaalsrus,53 Odendaal Street,Odendaalsrus |  | 2022-06-01 | 2022-09-30 |  | ASP-CR0257 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | CEASARS | 2022-04-18 |  | 33940.58 |  | Approved | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000019952 | CLOSED | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000090 | Signage Replacement At Absa Upington, th | Signage Replacement At Absa Upington, the shopfront decal has currently deteriorated over a period of time. Additionally, the existing dynoc vinyl in the ATM area has also deteriorated and is required to be replaced. This request seeks approval for the installation of new reversal shopfront decal in the inside of the branch and also to remove the existing dynoc vinyl from the tile walls by the ATM area . Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RIF Approval Received. Africa Security Clearance received. Artwork approval received from Absa Design.Scope of works: Supply and apply, and reverse apply new digital printed vinyl backed up with white size 2085 X 3430, 1 no Removal of existing shopfront decal and removal dynoc by the ATM area Security will not be required The site will be left clean on the outside upon completion, the branch cleaner will be require to do a touch point wipe down in the inside upon completion. |  |  | Region 3 | Northern Cape | 36271X | 1000-71336-01 | Absa Upington,28 Schroder Street,Upington |  | 2022-06-13 |  |  | ASP-CR0260 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-26 |  | 3646.41 |  | Approved | 2022-05-25 | 2022-05-25 | 0 |  |  |  |  | C000014904 | CLOSED | 2022-06-13 | 2022-07-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000091 | Power supply to external building signag | Power supply to external building signageAt Absa Preller Plein, the external building signage is not connected to the power supply. This request seeks approval to connect to the power supply of the branch.Note: RIF approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Landlord approval obtained.Scope of works: Wire Absa point and connect to isolator at the main DB 1no. COC will be issued on completion. Allowance for cleaning is not required since this work is done outside. |  |  | Region 3 | Free State | 79102X | 1000-71572-01 | Absa Preller Plein,Cnr Graaf Reinette & Dan Pienaar Street,Bloemfontein |  | 2022-06-13 |  |  | ASP-CR0261 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-28 |  | 4200.35 |  | Approved | 2022-05-04 | 2022-05-04 | 0 |  |  |  |  | C000019951 | CLOSED | 2022-06-13 | 2022-07-29 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000092 | Replacement of ceiling tiles in the Fron | Replacement of ceiling tiles in the Front of House (CIP 2022)Absa Orkney, the last refresh was done in 2018 which excluded the replacement of ceilings. The existing ceiling tiles in the front of house areas have deteriorated and are mismatched. This request seeks approval to replace with new. Note: RIF approval received. Supported by Engineering. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Site has been earmarked for LED replacement and will happen in conjuction with the replacement of the ceiling tiles.Scope of Work Remove old ceiling boards (1200 x 600mm) in the Front of house 343m2. (Banking hall, Tellers, Customer area, Enquiry area, Sales consultants, Branch managers office). Allow to cart away Skip waste. Allow to deinstall and reinstate the CCTV camera. Install new ceiling tiles (1200 x 600 mm) to existing ceiling grid in the Banking hall = 343m2. Allowance for enhance cleaning upon project completing. Allowance for extra security guard during the project 1 night. |  |  | Region 3 | North West | 77962X | 1000-71304-01 | Absa Orkney,59 Shakespear Avenue, Orkney |  | 2022-06-12 |  |  | ASP-CR0262 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-28 |  | 16103.8 |  | Approved | 2022-05-31 | 2022-05-31 | 0 |  |  |  |  | C000059838 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-09 | 12417.14 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000093 | Installation of CCTV Camera, De-install | Installation of CCTV Camera, De installation & Re installation of Cam VV System (VO )This is an additional request from Absa Security to add CCTV in the banking hall and also to remove and reinstate the VV system for the duration of the paintwork for the main project. Original approval of R 497 710,36 Incl VAT approved at CB09 dated 17 March 2022 for the Internal Finishes Refurbishment. VO amount required is R24 940,18 Incl VAT for the Installation of CCTV camera and removal and reinstatement of VV system during paintwork under the main project. The total cost amount for the project will be R522 650,54. Incl.VATNote: RIF approval received for the installation of CCTV camera. Once this request is approved, it will be noted at BTB as IFN. RBB Regional Approval Received. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Supply and install CCTV camera De installation of 5 Cam VV System Re installation of 5 Cam VV System |  |  | Region 3 | Free State | 79033X | 1000-71568-01 | Nampo Park-R30-Bothaville |  | 2022-05-12 |  |  | ASP-CR0263 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | CEASARS | 2022-04-29 |  | 2168.71 | Approved | 1 | 2022-05-04 | 2023-10-07 | 24940.18 |  | {"MANDT":"111","REFERENCE":70000093,"ONEVIEW":"79033X","DATE01":"2022-03-03","DATE02":"2022-03-10","DATE03":"2022-03-31","DATE04":"2022-04-07","DATE05":"2022-04-28","DATE06":"2022-05-12","DATE07":"2022-06-11","DATE08":"2022-07-02","DATE09":"2022-06-26","DATE10":"2022-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-05-12","FORECAST_END":"2022-06-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060166 | PHASE10 | 2022-05-12 | 2022-06-11 | SIYANDA DLAMINI | Juanita Van Coller | 0 |  |  |  |  | 2023-01-09 | 21687.11 | 0 |  |  | C000019966 | 21687.12 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000094 | Supply of chairs and a table, Installati | Supply of chairs and a table, Installation of Internet Kiosk and help line booth (CIP 2022)Absa Vrede branch was build without an internet kiosk. The regional team identified a need to install a internet kiosk and a customer help line booth to migrate clients to digital banking platforms. In addition, it was also requested to supply the branch with chairs and a table. Note: Approved at RIF. Floor plan updated. This project was prioritised by the region and spend will be allocated from the regional minor works budget. An Oasis request will be logged by Branch Support to install a network point.Scope of Works:Supply of chairs and a table and installation of IK and a Help line booth Staff chairs including covers (x6) Pause area (x4) Pause area table (x1) Visitors chair Upholstered A (x2) & B (x4) Internet kiosk and help line desk including the decal Floor plans for the IK position has been approved COC to be issued on completion. Allowance for enhance cleaning upon project completion. Additional security will not be required, email from Absa security is attached |  |  | Region 3 | Free State | 77122X | 1000-71531-01 | Absa Vrede-Church St-Vrede |  | 2022-03-26 |  |  | ASP-CR0264 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | CEASARS | 2022-04-29 |  | 12224.75 | Approved | 100 | 2022-06-23 | 2023-10-07 | 140584.67 |  | {"MANDT":"111","REFERENCE":70000094,"ONEVIEW":"77122X","DATE01":"2022-01-15","DATE02":"2022-01-22","DATE03":"2022-02-12","DATE04":"2022-02-19","DATE05":"2022-03-12","DATE06":"2022-03-26","DATE07":"2022-04-25","DATE08":"2022-05-16","DATE09":"2022-05-10","DATE10":"2022-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-26","FORECAST_END":"2022-04-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060365 | PHASE11 | 2022-03-26 | 2022-04-25 | Siyanda Dlamini | Juanita Van Coller | 0 |  |  |  |  | 2023-01-10 | 122247.54 | 0 |  |  | C000022940 | 122247.55 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000095 | Minor Works - Absa Villiers (Painting, S | Minor Works Absa Villiers (Painting, Signage, IK, Phone booth and Frosting) (CIP 2022)Absa Villiers branch was last revamped more than ten years ago and the painting of the internal walls are still reflecting the old Absa VI. The painting is peeling off from the walls and requires to be repainted. The internal signage is not aligned with the new Absa requirements and still reflecting the old Absa VI. The shopfront of the office facing the branch entrance is experiencing sun light discomfort and security concern as it does not have frosting. In addition, the branch also requires an Internet Kiosk and a telephone booth in support of retail business to migrate clients to digital banking platforms. This request seeks approval to paint the entire branch with the new Absa colours,install internal signage and an internet kiosk with a telephone booth. The upgrade of the required minor works to be conducted will enhance the look and feel of the branch.Note: RIF approval received. Artwork approved by Absa Design. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Prepare & paint wall for entire branch 710 sqm Prepare & paint internal walls in new Absa colours 118sqm Supply & install new internal signage (Signage Approved) Install frosting in on consultant window (Frosting approved) Install IK and help line booth (Permission to proceed received) Supply & install electrical pole & issue COC Supply & install wall mounted both Project security allowed in cost Provision for a after project cleaning & wipe down |  |  | Region 3 | Free State | 78810X | 1000-71554-01 | Absa Villiers,24B Main Street Street, Free State |  | 2022-03-17 |  |  | ASP-CR0265 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | CEASARS | 2022-05-03 |  | 25602.97 | Approved | 100 | 2022-05-25 | 2023-10-07 | 20298.77 |  | {"MANDT":"111","REFERENCE":70000095,"ONEVIEW":"78810X","DATE01":"2022-01-06","DATE02":"2022-01-13","DATE03":"2022-02-03","DATE04":"2022-02-10","DATE05":"2022-03-03","DATE06":"2022-03-17","DATE07":"2022-04-16","DATE08":"2022-05-07","DATE09":"2022-05-01","DATE10":"2022-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-17","FORECAST_END":"2022-04-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000059719 | PHASE11 | 2022-03-17 | 2022-04-16 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-06 | 17651.1 | 0 |  |  | C000014903 | 256029.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000096 | Minor works: Absa Sannieshof (CIP 2022) | Minor works: Absa Sannieshof (CIP 2022)Absa Sannieshof branch had last received the internal refresh in 2020 which did not touch the entire branch full scope. Currently, the front of house ceiling boards have deteriorated. Male and Female bathrooms also still hold old visual identity. This request seeks approval to carryout the above listed work so to enhance the branch s look an feel. Additionally, there is an approved request to add LED lighting onto this project, the cost which shall come from LED national budget. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. The LED lights replacement will take place in conjunction with the minor works project.Cost breakdown:Cost Allocated for Minor Works: R 140 632,15 incl.VAT (To be allocated against CIP PR/3/13)Installation of LED Lights : R 319 862,86 incl.VAT (To be allocated against CIP PR/2/03)Total project cost: R 460 495,01 incl.VATScope of Works Remove and replace with new ceiling boards 1200 x 600mm in the FOH (91m2) Allow to remove and reinstate security equipment (1 item) Gents: Remove and replace with new urinal complete with fittings (x1) Gents & Ladies: Remove and replace toilet cisten and fitting with new (x2) Gents & Ladies: Install new aluminium venetian window blinds 1m height (7m) Gents & Ladies: Remove existing vinyl floor tile and replace with new 600 x 600mm Absa grey porcelain tile (18m2) Gents & Ladies: Prepare and paint to walls, white above the floor tile (40m2) Gents & Ladies: Paint to door, Absa grey (X5) Ladies: Remove old wash hand basin and replace with new, complete with fittings (x1) Allowance for LED light installation as per the national roll out. Provide cleaning services upon completion of project. Provide Security Services for the duration of project. |  |  | Region 3 | Free State | 77996X | 1000-71305-01 | Sannieshof-Spoor St-Sannieshof |  | 2022-07-01 |  |  | ASP-CR0267 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | CEASARS | 2022-05-03 |  | 12228.88 | Approved | 1 | 2022-08-19 | 2023-10-07 | 140632.13 |  | {"MANDT":"111","REFERENCE":70000096,"ONEVIEW":"77996X","DATE01":"2022-04-22","DATE02":"2022-05-20","DATE03":"2022-05-27","DATE04":"2022-05-27","DATE05":"2022-07-01","DATE06":"2022-07-31","DATE07":"2022-08-21","DATE08":"2022-10-05","DATE09":"2022-10-31","DATE10":"2022-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-31","FORECAST_END":"2022-08-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000061147 | PHASE11 | 2022-07-31 | 2022-08-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000557 |  |  |  |  | 2023-01-13 | 122288.81 | 0 |  |  | C000032852 | 122288.82 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000097 | Walk- off Mats at Main Entrance (CIP 202 | Walk off Mats at Main Entrance (CIP 2022)There is currently no entrance walk off mat at Absa Welkom branch. The branch requested that a new recessed walk off mat be installed at the entrance.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works Cut into the existing floor tiles and prepare the floor to create a suitable recessed floor space to accommodate a new walk off mat. (4,6m2) Supply and Install Matco: Trioscape grey walk off mat to be fitted into a new recessed space opening ( 2300 x 2000mm) Supply and install aluminium angle around the floor edges (9m) Allow for security services Allow for project cleaning upon completion |  |  | Region 3 | Free State | 78607X | 1000-71545-01 | Absa WelkomCnr Ryk and Elizabeth StreetWelkom |  | 2022-07-01 |  |  | ASP-CR0268 | CLSD BUDG AVAC RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-03 |  | 6750.68 |  | Approved | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000037353 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000098 | Installation of aircon steel cageAt Absa | Installation of aircon steel cageAt Absa Parys branch, the aircon servicing the ATM room has been vandalised and stolen twice in the last two months. The last incident took place on the 9th March 2022. The forced entry was gained through a gate which had to be vandalised, the aircon seemed to be the target as it was vandalised beyond repair. This request seek approval to install a new aircon cage in order to prevent future incidents.Note: The replacement of aircon and the repair of the broken steel gate have been addressed via insurance claim (Reference WO no. 409121164). Africa Security confirmed the Scope/Spec.Scope of works: Supply and install a steel cage with a lock (1no) Anti rust paint to the cage |  |  | Region 3 | Free State | 78350X | 1000-71537-01 | Absa Parys,Cnr Middel & Kerk Street, Parys |  | 2022-06-01 |  |  | ASP-CR0269 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-04 |  | 660.54 |  | Approved | 2022-05-25 | 2022-05-25 | 0 |  |  |  |  | C000014896 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000099 | External refurbishment and Waterproofing | External refurbishment and Waterproofing (CIP 2022)Absa Reitz is an owned building. This request seeks approval to refurbish the external infrastructures of the building. Currently, paintwork of the external structures has worn out. Listed are the following external infrastructures which includes the concrete drain galley, waterproofing to the cantilever slab, paintwork to walls, window frames, burglar guards downpipes and gutters. This request seeks approval to refurbish the listed defects to enhance the look and feel of the branch.Note: Approved by CRES VP. Supported by BFM Engineering.Scope of Works Painting to external walls 20m2 Painting to gutters and rain water downpipes (x1) Waterpoofing to roof cantiliver slab (12m2) Painting to window frames and steel door frames (x1) Install weather strip on doors (x1) Painting to boundary walls (5m2) Repair concrete pedestal around the drain pipe with cement mortar (x1 item) Spray paint to man trap door frame, on the outside (x1) Replace external ceiling boards 5m2 Cut and remove trees (x5) Extend Aircon drain pipe 3.2m Allowance for project security |  |  | Region 3 | Free State | 78402X | 1000-71538-01 | Absa Reitz-Church St-Reitz |  | 2022-08-01 | 2022-09-30 |  | ASP-CR0270 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | CEASARS | 2022-05-09 |  | 20635.5 |  | 100 | 2022-09-22 | 2022-09-22 | 237308.27 |  | {"MANDT":"111","REFERENCE":70000099,"ONEVIEW":"78402X","DATE01":"2022-05-23","DATE02":"2022-06-20","DATE03":"2022-06-27","DATE04":"2022-06-27","DATE05":"2022-08-01","DATE06":"2022-09-30","DATE07":"2022-10-21","DATE08":"2022-12-05","DATE09":"2022-12-31","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-30","FORECAST_END":"2022-10-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000061787 | PHASE11 | 2022-09-30 | 2022-10-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000308 |  |  |  |  | 2023-01-17 | 206355.02 | 0 |  |  | C000061787 | 206355.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000100 | External Minor Works -Absa Heilbron (CIP | External Minor Works Absa Heilbron (CIP 2022)Absa Heilbron branch is an owned building. This request seeks approval to refurbish the external infrastructures of the building. Currently, the paintwork of the external structures deteriorated over a period of time. The following areas that requires refurbishment includes the painting of carport, pressure cleaning of wall tiles, paintwork to walls, paint to window frames, paint to burglar guards downpipes and gutters, paint to steel handrails, replacement of anti slip aluminium nosing strip, painting to external step and parking gate. This request seeks approval to refurbish the listed defects in order to bring the building back to it s good look and feel.Note: Approved by CRES VP. Scope of Works Painting to external walls 45m2 Replacement and paint of fascia boards 5m Painting to gutters and rain water downpipes (x1) Allow to clean the wall and paint 21m2 Painting to window frames and steel door frames (x1) Pressure cleaning of wall tile (include the scaffolding 4509m2 Painting to steel handrails Paint access ramp 2m2 Anti slip aluminium nosing strip 500mm (x3) Paint to external steps 1.28m2 Paint to carport (x1) Paint to parking gate (x1) Neatening of pipes and cable on the wall (x1) Cleaning of drainage system at the carport Allowance for project security |  |  | Region 3 | Free State | 78854X | 1000-71557-01 | Absa Heilbron-Kerk St-Heilbron |  | 2022-07-01 |  |  | ASP-CR0271 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | CEASARS | 2022-05-10 |  | 26784.28 | Approved | 100 | 2022-09-22 | 2023-10-07 | 308019.24 |  | {"MANDT":"111","REFERENCE":70000100,"ONEVIEW":"78854X","DATE01":"2022-04-22","DATE02":"2022-04-29","DATE03":"2022-05-20","DATE04":"2022-05-27","DATE05":"2022-06-17","DATE06":"2022-11-14","DATE07":"2023-02-15","DATE08":"2023-02-16","DATE09":"2023-02-22","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"131:7:21:7:21:150:93:1:6:16","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-14","FORECAST_END":"2023-02-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLgo=","RATING":""} |  |  | C000061786 | PHASE11 | 2022-11-14 | 2023-02-15 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-17 | 267842.82 | 0 |  |  | C000061786 | 267842.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000101 | Signage Replacement At Absa The Walk Sho | Signage Replacement At Absa The Walk Shopping Centre, there are two Absa external signage, first one is suspended signange from the passage ceiling of the building and the second one is on the pylon in the parking area. The back print of the signage on the passage does not align with new Absa logo, and the vinyl of the signage by the parking area has faded and deteriorated. This request seeks approval to exchange the back print on the suspended sign in the passage and also to change the vinyl on the signage at the pylon in the parking area. Note: RIF approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Removal of existing vinyl on the pylon and application of the new vinyl. Supply of new backprint 440 x 1400mm (2no) |  |  | Region 3 | Free State | 78830X | 1000-71555-01 | Absa Langenhoven,The Walk Shopping Centre,Cnr Jan Spies & Maretha Maartens Road, Bloemfontein |  | 2022-06-12 |  |  | ASP-CR0273 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | CEASARS | 2022-05-10 |  | 582.46 | Approved | 100 | 2022-05-25 | 2023-10-07 | 6698.29 |  | {"MANDT":"111","REFERENCE":70000101,"ONEVIEW":"78830X","DATE01":"2022-04-03","DATE02":"2022-04-10","DATE03":"2022-05-01","DATE04":"2022-05-08","DATE05":"2022-05-29","DATE06":"2022-06-12","DATE07":"2022-07-12","DATE08":"2022-08-02","DATE09":"2022-07-27","DATE10":"2022-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-12","FORECAST_END":"2022-07-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000062064 | PHASE11 | 2022-06-12 | 2022-07-12 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-18 | 5824.6 | 0 |  |  | C000062064 | 5824.6 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000102 | Supply and installation of Customer Inte | Supply and installation of Customer Internet Kiosk (CIP 2022)Absa Marquard Hinterland branch was build without an internet kiosk. The regional team identified a need to install an internet kiosk and a customer helpline booth for customer service, in line with the digital migration requirements. It was therefore recommended that these items be supplied and installed. Note: Updated drawing received from Absa design. RIF approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. The oasis request will be logged and work will happen in conjuction. Chair will be provided from stores.Scope of Work Install 1x internet kiosk desk Install 1x power pole & issue COC Supply 1x chair Standard Covid 19 wipe down conducted after project completion by the branch cleaner. |  |  | Region 3 | Free State | 78633X | 1000-71547-01 | Hinterland-Van Der Walt St-Marquard |  | 2022-06-09 |  |  | ASP-CR0274 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | NOMNGANGAL | 2022-05-18 |  | 3335.77 | Approved | 100 | 2022-06-23 | 2023-10-07 | 38361.34 |  | {"MANDT":"111","REFERENCE":70000102,"ONEVIEW":"78633X","DATE01":"2022-03-31","DATE02":"2022-04-07","DATE03":"2022-04-28","DATE04":"2022-05-05","DATE05":"2022-05-26","DATE06":"2022-06-09","DATE07":"2022-07-09","DATE08":"2022-07-30","DATE09":"2022-07-24","DATE10":"2022-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-09","FORECAST_END":"2022-07-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060364 | PHASE11 | 2022-06-09 | 2022-07-09 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-10 | 33357.69 | 0 |  |  | C000022942 | 33357.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000104 | Installation of new stand to the Chiller | Installation of new stand to the Chiller (CIP 2022)This request seeks approval for the installation of a new stand to the chiller. The landlord needs to waterproof the roof to remedy the roof leaks on rainy days. There is a McQuary air cooled chiller on the roof that belongs to Absa where the waterproofing needs to be done. The challenge is that the chiller unit has been mounted directly on the roof slab with no clearance underneath. The request is to mount the chiller unit on a permanent stand to make way for the waterproofing and for future maintenance purposes. The chiller unit will be decommissioned, as part of the stand installation process. A 600mm high stand will be installed, then the chiller recommissioned under the supervision of Daiken specialist. Note: Method statement supported by BFM & CRES Engineering.Scope of Works:. Decommission existing chiller Rigg off temporarily to allow for stand installation Supply and install 600mm high galvanized steel stand (with earthing) Put Back the chiller on new stand using a crane (x1) Complete modification of chilled water piping and insulation Chiller to be recommissioned by Vendor and OEM for sign off purposes. No additional security required |  |  | Region 3 | Free State | 78607X | 1000-71545-01 | Welkom-Cnr Ryk & Elizabeth St-Welkom |  |  | 2022-07-22 |  | ASP-CR0281 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-05-23 |  | 9642.88 | Approved | 100 | 2022-09-22 | 2023-10-07 | 110893.19 |  | {"MANDT":"111","REFERENCE":70000104,"ONEVIEW":"78607X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"2022-07-22","DATE07":"2022-08-12","DATE08":"2022-09-02","DATE09":"2022-10-17","DATE10":"2022-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-22","FORECAST_END":"2022-08-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000061655 | PHASE11 | 2022-07-22 | 2022-08-12 | Siyanda Dlamini | Floyd Mofokeng | 23000539 |  |  |  |  | 2023-01-16 | 96428.86 | 0 |  |  | C000061655 | 96428.86 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000105 | New Water tank with booster pump and fil | New Water tank with booster pump and filtration systemAbsa Hennenman is a freehold retail branch in the Northern Cape province. The area is constantly experiencing water outages, whereby on some days it would extend to more than 5 days. During these water scarcity periods, the branch is forced to free the staff members in order to comply with section 43 of the Occupational Health and Safety Act, 1993 Act No, 85 of 1993), stating that every employee must have access to drinking water and for sanitation in the workplace. This request seeks approval to install a 1500lt water tank which is the correct size to fit in the earmarked space, and also will be able to accommodate the number of staff for a maximum of 5 days of a water outage. A water filtration system will be installed in the tank for safety standards and a water pump system in order to maintain water pressure.Note: Supported by BFM EngineeringScope of Work Supply and Installation of a 1500L water tank (x1) Big blue 2 stage filtration system (x1) Concrete base for the water tank, 3,00m x 3,00m x 75mm plinth Pump 240V A/C, 075A with pressure control incl steel cage housing Non return valve, 25mm Torentti spring loaded P/N 16 (16 BAR) & Fittings Polycop piping & fittings 20m depending on the tie in point Pump should be a 240 V A/C 0,75 A, pump with a pressure control A 30A isolator feeding the pump and control panel Electrical: a dedicated 20A breaker to be catered for in the main DB linked to the emergency power circuit. Allowance for COC Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test has been catered for Allowance for OHS file included |  |  | Region 3 | Free State | 78855X | 1000-71558-01 | Absa Hennenman-Kerk St-Hennenman |  | 2022-07-14 |  |  | ASP-CR0298 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | NOMNGANGAL | 2022-06-17 |  | 6878.36 |  | 100 | 2022-11-10 | 2022-11-10 | 0 |  |  |  |  | C000063001 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 68783.62 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000106 | Dilaps | Dilaps |  |  | Region 3 | North West | 77057X | 1000-71282-01 | Absa Burger Street-Cnr Nelson Mandela & Beyers Naude St-Rustenburg |  | 2022-07-14 | 2022-12-15 |  | ASP-CR0299 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-06-22 |  | 32415.31 |  | 100 | 2022-06-27 | 2022-06-27 | 0 |  |  |  |  | C000061818 | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-17 | 188795.42 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000107 | Replacement of shopfront welcome decalAb | Replacement of shopfront welcome decalAbsa Diamond Pavillion, the transaction volume in the mall is picking up after 09h00 with the peak between 10h00 and 12h00. This request seeks approval to replace welcome time by amending Saturday opening hours from 10h00 to 12h00.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Removal of existing welcome decal Supply and install new decal |  |  | Region 3 | Northern Cape | 78575X | 1000-71352-01 | Absa Diamond Pavillion Shop 88-89, Diamond Pavilion Shopping Mall, cnr Olivier and Mac Dougall Street |  | 2022-07-28 |  |  | ASP-CR0301 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-06-27 |  | 141.65 |  | Approved | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000030692 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000108 | Remove deteriorated Dynoc vinyl and repl | Remove deteriorated Dynoc vinyl and replace with new The walls in the ATM at Absa Mmabatho Crossing has dynoc vinyl which is currently deteriorated and compromising the Absa Brand. This request seeks approval to remove and replace the existing dynoc vinyl. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing dynoc vinyl from the walls and replace with new (4m2). |  |  | Region 3 | North West | 22197X | 1000-71243-01 | Absa Mmabatho Crossing,Shop 35A, cnr Nelson Mandela Drive and Sekame Street |  | 2022-07-28 |  |  | ASP-CR0302 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-06-29 |  | 1464.19 |  | Approved | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000031014 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000109 | External Refurb- Provide additional x3 s | External Refurb Provide additional x3 shifts for the project security guard (VO)This request seeks approval for the variation order amount of R2 437,46 incl.VAT. This is an additional request to provide x3 more shifts for the Fidelity security guard, which had to continue guarding the project beyond the initial order.Original approval of R390 316,69 incl. VAT approved at CB15 dated 26 April 2022 for the External Minor works.VO amount required is R2 437,46 incl. VAT for the allocation of a guard. Total cost amount for the project will be R392 754,15. incl. VAT Note: Approved by CRES VP & RBB. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Allowance of security service at Absa Odendaalsrus x 3days |  |  | Region 3 | Free State | 79056X | 1000-71599-01 | Absa Odendaalsrus53 Odendaal StreetFree State |  |  | 2022-07-04 |  | ASP-CR0304 | CLSD ISBD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | NOMNGANGAL | 2022-07-04 |  | 211.95 |  | 100 | 2022-08-04 | 2022-08-04 | 2437.46 |  | {"MANDT":"111","REFERENCE":70000109,"ONEVIEW":"79056X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"0000-00-00","DATE07":"2022-07-04","DATE08":"2022-07-25","DATE09":"2022-09-08","DATE10":"2022-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"0000-00-00","FORECAST_END":"2022-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000030417 | PHASE11 |  | 2022-07-04 | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 2119.53 | 0 |  |  | C000030417 | 2119.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000110 | Installation of UV vinyl frosting to blo | Installation of UV vinyl frosting to block out UV sunlightThis request seeks approval for the installation of UV vinyl frosting at Absa Trompsburg to block out UV sunlight. There was a project recently completed, whereby window frosting was installed onto identified areas to address the privacy of staff and customers inside the branch. Upon project completion, the branch realised that not only was the privacy the only concern but also the sun light which is causing discomfort. This request seeks approval to apply a UV protection fronting to identified windows.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply, cut and install the UV Vinyl frosting to the shopfront (x8) |  |  | Region 3 | Free State | 79334X | 1000-71585-01 | Absa Trompsburg-Voortrekker St-Trompsburg |  |  | 2022-07-04 |  | ASP-CR0305 | REL BUDG AVAC SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | F |  | NOMNGANGAL | 2022-07-04 |  | 1635.5 | Approved | 1 | 2022-08-04 | 2023-10-07 | 18808.24 |  | {"MANDT":"111","REFERENCE":70000110,"ONEVIEW":"79334X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"2022-07-04","DATE07":"2022-07-25","DATE08":"2022-08-15","DATE09":"2022-09-29","DATE10":"2022-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-04","FORECAST_END":"2022-07-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDYW5jZWxsZWQu","RATING":""} |  |  | C000061021 | PHASE10 | 2022-07-04 | 2022-07-25 | Siyanda Dlamini | floyd mofokeng | 23000613 |  |  |  |  | 2023-01-12 | 16354.99 | 0 |  |  | C000030793 | 16355 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000111 | Dilaps | Dilaps |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein |  | 2022-11-10 | 2022-11-24 |  | ASP-CR0307 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | NOMNGANGAL | 2022-07-11 |  | 24771.12 |  | 100 | 2022-08-15 | 2022-08-15 | 0 |  |  |  |  | C000031552 | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000112 | Replacement of ATM Signage Absa Hartswat | Replacement of ATM Signage Absa Hartswater ATM canopy s existing vinyl has faded. This request seeks approval to remove and replace with new.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Remove existing ATM redband approx 4,6m long and replace with new |  |  | Region 3 | Northern Cape | 78684X | 1000-71610-01 | Absa Hartswater29 DF Malan StreetHartwatser |  | 2022-09-29 | 2022-09-29 |  | ASP-CR0309 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-07-11 |  | 1734.46 | Approved | 100 | 2022-08-04 | 2023-10-07 | 19946.36 |  | {"MANDT":"111","REFERENCE":70000112,"ONEVIEW":"78684X","DATE01":"2022-07-21","DATE02":"2022-07-28","DATE03":"2022-08-18","DATE04":"2022-08-25","DATE05":"2022-09-15","DATE06":"2022-09-29","DATE07":"2022-09-29","DATE08":"2022-10-20","DATE09":"2022-11-13","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-29","FORECAST_END":"2022-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060658 | PHASE11 | 2022-09-29 | 2022-09-29 | Siyanda Dlamini | floyd mofokeng | 0 |  |  |  |  | 2023-01-11 | 17344.66 | 0 |  |  | C000030640 | 17344.67 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000113 | Replacement of Earthing Cable (19991231c | Replacement of Earthing Cable (19991231ctive Insurance)The earthing cables for HVAC on the roof were stolen. Approval was granted for the supplier to replace all stolen earthing cables. A purchase order was issued out to the supplier who is still awaiting for the material.Note: Supported by BFM Engineering. Work Order Number : 409481556, PO number: 4500746907, Work completed 2022/08/29 and invoice captured on the 2022/10/10. INSOG insurance process followed. Scope of works To supply and replace the stolen earthing cables. Issue COC on completion. |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Absa Bloemfontein Forum19 Donald Murray AveBloemfontein |  | 2022-07-21 | 2022-07-28 |  | ASP-CR0310 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-07-12 |  | 4352.34 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000063005# | CLOSED |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 43523.4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000114 | Installation of plug point in the ATM ro | Installation of plug point in the ATM roomAbsa Hennenman ATM room does not have a plug point to power the Note Counting Machine. Currently, the staff uses an extension cable for power connection. This request seeks an approval to install a power plug inside the ATM Room.Note: Supported by RBB.Scope of Works Supply & install dedicated and normal plug in the ATM room. Issue COC upon completion. |  |  | Region 3 | Free State | 78855X | 1000-71558-01 | Absa Hennenman-Kerk St-Hennenman |  | 2022-11-03 | 2022-11-30 |  | ASP-CR0312 | REL BUDG AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-07-21 |  | 227.34 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000030795 | IGNORE |  |  | Siyanda Dlamini | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000115 | Installation of additional plugs for the | Installation of additional plugs for the security key padAt Absa Bothaville, there has been an upgrade to access keypads for the doors leading to the back office area. These new keypads only operates on electric power. This request seeks approval to install x2 dedicated plugs in the ceiling void.Note: Supported by RBB.Scope of Works Supply and install dedicated power point, 20 AMP CBI breaker x 1item Issue COC upon completion No need for security, project to be carried out during banking operational hours |  |  | Region 3 | Free State | 79114X | 1000-71573-01 | Absa Bothaville-President St-Bothaville |  | 2022-09-22 |  |  | ASP-CR0313 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-07-21 |  | 573.15 |  | 100 | 2022-08-04 | 2022-08-04 | 6591.23 |  | {"MANDT":"111","REFERENCE":70000115,"ONEVIEW":"79114X","DATE01":"2022-07-14","DATE02":"2022-07-21","DATE03":"2022-08-11","DATE04":"2022-08-18","DATE05":"2022-09-08","DATE06":"2022-09-22","DATE07":"2022-10-22","DATE08":"2022-11-12","DATE09":"2022-11-06","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-22","FORECAST_END":"2022-10-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000030794 | PHASE11 | 2022-09-22 | 2022-10-22 | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 5731.5 | 0 |  |  | C000030794 | 5731.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000116 | Supply outstanding items for the new Blo | Supply outstanding items for the new Bloemfontein Forum (VO)This request seeks approval for additional funds against the previous request approved at CB23 for the amount of R 15 633,31 including VAT due to the amended specifications of the cabinets. The new value has now increased to R 19 608.22 including VAT. The variation order required is R 4 542.86 including VAT for the supply of steel cabinets. The previous specifications was quoted for wooden cabinets.Original request: This request seeks approval to provide items required at the new Forum building. The new building that the office is relocating to does not have all the items available and were not included in the Capital project. Note: Supported by CRES VP. Scope of works: Supply steel cabinet (x3) |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Absa Bloemfontein Forum19 Donald Murray Ave,Bloemfontein |  | 2022-07-28 | 2022-07-28 |  | ASP-CR0314 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Freeho |  | NOMNGANGAL | 2022-07-22 |  | 395 |  | Approved | 2022-07-21 | 2022-07-21 | 0 |  |  |  |  | C000028132 | CLOSED |  |  | Siyanda Dlamini | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000117 | Minor Works | Minor Works |  |  | Region 3 | 0 | 0 | 1000-71347-01 | Absa Jan Kempdorp |  | 2022-11-03 | 2022-11-24 |  | ASP-CR0315 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-07-25 |  | 0 |  | Approved | 2022-11-10 | 2022-11-10 | 1158119.11 |  |  |  |  | 0 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000118 | Minor Works - Absa KathuAbsa Kathu last | Minor Works Absa KathuAbsa Kathu last had a minor refresh in 2016. Currently in the kitchen, the cupboard units has worn out including the wall ceramic tiles and floor vinyl tiles. The back of house requires a pause area table, staff and waiting area chairs including a x4 drawer lockable cabinet. This request seeks approval for the upgrade of the areas identified to enhance the look and feel of the branch.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply waiting area chairs (x 6) Supply staff chairs (x5) Supply pause area table (x1) Supply pause area chairs (x4) Supply lockable 4 drawer cabinet (x1) Strip and replace kitchen cupboard including double zinc (x1) Kitchen: remove and replace with metro white wall tile (22m2) Kitchen: replace with new vinyl tiles (6m2) Kitchen: prepare and paint wall with Absa grey (20m2) Allowance for project security only after banking hours |  |  | Region 3 | Northern Cape | 21345X | 1000-71317-01 | Kathu-Rietbok St-Kathu |  | 2022-11-10 |  |  | ASP-CR0317 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-01 |  | 15852.27 | Approved | 100 | 2022-08-04 | 2023-10-07 | 79040.65 |  | {"MANDT":"111","REFERENCE":70000118,"ONEVIEW":"21345X","DATE01":"2022-09-01","DATE02":"2022-09-08","DATE03":"2022-09-29","DATE04":"2022-10-06","DATE05":"2022-10-27","DATE06":"2022-11-10","DATE07":"2022-12-10","DATE08":"2022-12-31","DATE09":"2022-12-25","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-10","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060734 | PHASE11 | 2022-11-10 | 2022-12-10 | Siyanda Dlamini | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-11 | 68731 | 0 |  |  | C000030728 | 158522.79 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000119 | Replacement of furniture, vinyl tiles an | Replacement of furniture, vinyl tiles and a lockable drawer cabinet (CIP 2022)Absa Carnarvon were last revamped in 2021 when an additional ATM was installed. Currently, the branch needs waiting area chairs , pause area chairs and a table for the pause area.The floor vinyl tiles in the back office has worn out and requires to be replaced. In addition, a request has been made to provide a lockable drawer cabinet. Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Suppy waiting area chairs (x6) Supply pause area table (x1) Supply pause area chair (x4) Supply staff chairs (x5) Supply lockable drawer cabinet x 1item Remove and replace vinyl floor tile in the back of house x 100m2 Allowance for the project cleaners upon completion No need for the project security, by RSM |  |  | Region 3 | Northern Cape | 79297X | 1000-71360-01 | Absa Carnarvon-Cnr Victoria & Van Riebeeck St-Carnarvon |  | 2022-11-10 |  |  | ASP-CR0318 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-01 |  | 22346.23 | Approved | 100 | 2022-08-04 | 2023-10-07 | 94546.34 |  | {"MANDT":"111","REFERENCE":70000119,"ONEVIEW":"79297X","DATE01":"2022-09-01","DATE02":"2022-09-08","DATE03":"2022-09-29","DATE04":"2022-10-06","DATE05":"2022-10-27","DATE06":"2022-11-10","DATE07":"2022-12-10","DATE08":"2022-12-31","DATE09":"2022-12-25","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-10","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060627 | PHASE11 | 2022-11-10 | 2022-12-10 | Siyanda Dlamini | floyd mofokeng | 0 |  |  |  |  | 2023-01-11 | 82214.21 | 0 |  |  | C000030419 | 223462.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000120 | Replacement of furniture and refurbishme | Replacement of furniture and refurbishment of countertopAbsa Hopetown never had a branch refresh since inception. Currently, the chairs for staff, tellers, boardrooms and waiting area have worn out. The teller area counter top has faded and requires to be refurbished. This request seeks approval to replace the chairs and refurbish the cherrywood counter tops and apply x3 coat polyurethane.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply staff chairs (x4) Supply teller chairs (x3) Supply boardroom chairs (x5) Supply waiting area chairs (x7) Sand down existing cherrywood counter tops and apply 3 coat polyurethane (x3) Allowance for project security outside banking hours only |  |  | Region 3 | Northern Cape | 78645X | 1000-71353-01 | Hopetown-Cnr Widd & Kerk St-Hopetown |  | 2022-11-10 |  |  | ASP-CR0319 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-01 |  | 15078.84 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000060733 | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-11 | 106716.81 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000121 | Minor Works - Absa KurumanAbsa Kuruman l | Minor Works Absa KurumanAbsa Kuruman last had a revamp in 2016. Currently, the carpet in the customer service and bulk teller cubicle areas is worn out and deteriorated over a period of time. The main entrance outside the branch is exposed to motor vehicles potentially driving into the branch and as a preventative measure the recommendation was made to install concrete bollards. This request seeks approval to carry out the above listed items.Note: Approved by RIF. BFM Engineering supported. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing carpet and replace with 500 x 500 mm Belgoted hard graft shaded carpet in the customer service and bulk teller cubicle area(70m2) Supply and install concrete bollards (Minister bollard, 250mm dia. 1200mm height, 137kg weight) (x6) Project security not required. Allowance for project cleaning upon completion |  |  | Region 3 | Northern Cape | 78504X | 1000-71350-01 | Kuruman-Cnr Hoof & Livingstone Rd-Kuruman |  | 2022-11-03 |  |  | ASP-CR0320 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-01 |  | 12155.33 | Approved | 100 | 2022-08-04 | 2023-10-07 | 30232.55 |  | {"MANDT":"111","REFERENCE":70000121,"ONEVIEW":"78504X","DATE01":"2022-08-25","DATE02":"2022-09-01","DATE03":"2022-09-22","DATE04":"2022-09-29","DATE05":"2022-10-20","DATE06":"2022-11-03","DATE07":"2022-12-03","DATE08":"2022-12-24","DATE09":"2022-12-18","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-03","FORECAST_END":"2022-12-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCB3b3JrIGNvbXBsZXRlZCBhbmQgaW52b2ljZWQ=","RATING":""} |  |  | C000060656 | PHASE11 | 2022-11-03 | 2022-12-03 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-08-31 | 26289.17 | 0 |  |  | C000030420 | 121553.35 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000122 | Replacement of furniture (CIP 2022)At Ab | Replacement of furniture (CIP 2022)At Absa Thaba Nchu, the current chairs are old and deteriorated over a period of time, and requires to be replaced. In addition, a request was made to provide a table and x4 chairs for the pause area. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Canteen table and chairs will be provided from Absa Stores.Scope of Works Supply of waiting benches 240mm L, S13A (x2) Supply of canteen table from Absa stores (x1) Supply of canteen chairs from Absa stores (x4) |  |  | Region 3 | Free State | 78975X | 1000-71563-01 | Thaba Nchu-Market St-Thaba Nchu |  | 2022-11-10 |  |  | ASP-CR0322 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-23 |  | 2105.47 | Approved | 100 | 2022-09-08 | 2023-10-07 | 24213.01 |  |  |  |  | C000061765 | PHASE11 | 2022-12-10 | 2022-12-31 | NANDE MAQUBELA | Floyd Mofokeng | 23000606 |  |  |  |  | 2023-01-17 | 27844.96 | 0 |  |  | C000061765 | 21054.79 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000123 | Remove existing reception desk and insta | Remove existing reception desk and install new brave reception desk (CIP 2022)This request seeks approval to remove the existing reception desk with the platform. It was reported that it is causing a tripping hazard for staff members. The desk will be replaced with a new brave reception desk which does not require a platform.Note: Approved at RIF. Absa Design layout of the new brave reception desk has been issued and approved. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works Remove the existing reception platform(covered in carpet) and cartaway (x1) Supply and install new brave reception desk (x1) Prepare and repaint the yellow wall, Absa spec (8,1m2) Repair floor tile (x1) Move the reception desk from Preller Plein to Botshabelo (x1) Remove and make safe existing power underneath the existing desk (x1) Allowance for COC on completion Allowance for project security Supply consultant chair for the new brave reception desk (x1) |  |  | Region 3 | Free State | 79102X | 1000-71572-01 | Preller Plein-Cnr Graaff Reinette & Dan Pienaar St-Bloemfontein |  | 2022-11-10 |  |  | ASP-CR0323 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-23 |  | 4135.2 | Approved | 100 | 2022-09-08 | 2023-10-07 | 47554.89 |  | {"MANDT":"111","REFERENCE":70000123,"ONEVIEW":"79102X","DATE01":"2022-09-01","DATE02":"2022-09-08","DATE03":"2022-09-29","DATE04":"2022-10-06","DATE05":"2022-10-27","DATE06":"2022-11-10","DATE07":"2022-12-10","DATE08":"2022-12-31","DATE09":"2022-12-25","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-10","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000062136 | PHASE11 | 2022-11-10 | 2022-12-10 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-18 | 41352.08 | 0 |  |  | C000062136 | 41352.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000124 | Conduct a full due diligence, manufactur | Conduct a full due diligence, manufacture supply and installation of LED Lighting (Item for noting)This request seeks approval to conduct a due diligence, manufacture, supply and install LED lighting at Absa Sannieshof. As part of the minor works project that is underway at Absa Sannieshof and energy efficiency drive for the bank, it has been identified that the lighting onsite are outdated with inefficient technology. The replacement of lighting with LED is will align to Absa s Energy Management and Environmental Sustainability Strategy which entails a phased roll out of energy saving technology and human behavioural interventions across the portfolio nationally. The lighting replacement is scoped to achieve substantial energy savings, related electricity cost and carbon emissions savings by replacing existing lighting less energy efficient lights with sustainable lighting solutions based on LED technology, which also complies with the OHS Act lux level requirements. The warranty period on all the fittings is 5 years.Note: Supported by BFM Energy. Project will be funded from the cancelled National Bathroom Efficiency CIP 2022 project budgeted amount R703k incl.VAT. Approved Out of Cycle by CRES Engineering on 22/08/2022. Scope of Works:. Conduct a full lighting due diligence. Provide lighting designs based on approved LED lighting specification, simulation showing the achieved lux levels based on the proposed designs, energy savings calculations and cost benefit analysis. BOQ for the proposed design including as built lighting layout drawings. Manufacture , supply and install LED luminaires as per the designs . On completion, test commission and issue close out report, Issue as built drawings, technical specifications; and Inspect and sign off the installation to ensure that lux levels are compliant with legislation. |  |  | Region 3 | North West | 77996X | 1000-71305-01 | Absa Sannieshof21A Spoor St,Sannieshof |  | 2022-10-21 |  |  | ASP-CR0324 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-23 |  | 27814.16 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000061019 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-12 | 43452.82 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000125 | Supply of internal signage infillsAbsa W | Supply of internal signage infillsAbsa Wilkoppies branch requested to change the signage infills for two offices. The semi private office consultant sign needs to be replaced with a customer service infill. In addition, the private office consultant sign needs to be replaced with an interview office infill. These infills will be a supply only by the vendor and the branch has confirmed to do the installation.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply of inserts for the customer service area and interview office (x2) |  |  | Region 3 | North West | 77150X | 1000-71287-01 | Austin Crossing Centre-Cnr Austin & Ametis St-Klerksdorp |  | 2022-10-21 | 2022-12-01 |  | ASP-CR0325 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-24 |  | 56.77 |  | 100 | 2022-10-20 | 2022-10-20 | 0 |  |  |  |  | C000062347# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-18 | 567.74 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000126 | Replacement of furniture (CIP 2022)At A | Replacement of furniture (CIP 2022)At Absa Prieska, the current chairs for staff and customers deteriorated over a period of time and requires to be replaced. The branch had a minor refresh in 2019, however the chairs were not part of the scope. This request seeks approval to supply the branch with new chairs for the staff and customer service areas.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works Supply of staff chairs (ST15,01) (x5) Supply of waiting bench (AB S29B) (x2) Supply of visitors chair (x8) |  |  | Region 3 | Northern Cape | 21676X | 1000-71318-01 | Prieska-Cnr Main & Kerk St-Prieska |  | 2022-11-10 | 2022-12-01 |  | ASP-CR0326 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-24 |  | 7102.27 |  | 100 | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000037350 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000127 | Replacement of two condensing units (Ret | Replacement of two condensing units (19991231ctive)The aircons servicing the ATM room were vandalised and stolen twice in the last few months. The first incident took place on the 9th March 2022 ,WO 409109255 for R32 853.35 VAT inclusive and the 2nd incident took place on the 13 July 2022 WO 409500620 for R19 268.54 VAT inclusive. Both incidents took place before the steel cage was replaced. A new steel cage was installed in order to prevent future incidents. (PO issued: 4500743733).Note: Approved by Cres Engineering. These requests are for noting as work was completed as INSOG requests on the 21 July 2022, purchase order 4500750870.Cost breakdown:Steel Cage: R 7 596,31 incl.VAT (Approved at CB19) First Incident: R 32 853,35 incl.VAT (Insurance process) Second Incident: R 19 268,54 Incl.VAT (Insurance process) Total Cost: R 59 718,20 incl.VATScope of Works: Install new condensing unit at high level (x2) Install new refrigeration piping Replacement of brackets for outdoor unit |  |  | Region 3 | Free State | 78350X | 1000-71537-01 | Absa ParysCnr Middel and Kerk StreetParys |  | 2022-09-08 | 2022-09-08 |  | ASP-CR0328 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-30 |  | 4532.33 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000034718 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000128 | Minor Works - Absa Phokeng Mall (CIP 202 | Minor Works Absa Phokeng Mall (CIP 2022)Absa Phokeng were last refreshed in 2018. Over time the ceiling tiles in the banking hall have deteriorated, and the bulkhead paintwork is wearing off. Paintwork to the internal walls including the doors and frames have worn out. The identified areas that requires to be refreshed is as follows; the vinyl floor tiles in the bathrooms and store room, and replace worn out kitchen units with new. In addition, the branch requested that a walkoff mat be installed at the entrance. This request seeks approval to carry out the above listed defects in order to refresh the look and feel of the branch.Note: Approved by RIF and supported by BFM Eng. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Installation of LED Lights is not part of this year s National Roll Out Program and will be provisioned for in 2023. A small portion of the ceiling will be touched in the back of house area.Scope of Works Remove deteriorated ceiling tiles and replace with new Georgian Armstrong 600x1200mm, ceiling tiles (22m2) Strip and remove vinyl tiles in kitchen and bathroom and replace with new Floorworx Floorflex vinyl tiles (15m2) Remove existing kitchen unit and replace with new as specified Remove existing skirting and replace with new (150 lm) Prepare and paint plasterboard bulkheads (15m2) Supply and install new bump rail behind teller chairs (3,6m) Prepare and paint all internal walls (590m2) Supply new Belgotex Trioscape walk off mat Project cleaning upon completion Allowance for security guarding for project duration |  |  | Region 3 | Free State | 78032X | 1000-71306-01 | Phokeng Mall-Main Rd-Rustenburg |  | 2022-10-03 | 2022-10-06 |  | ASP-CR0329 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-12 |  | 20784.34 |  | 100 | 2022-09-15 | 2022-09-15 | 239019.91 |  | {"MANDT":"111","REFERENCE":70000128,"ONEVIEW":"78032X","DATE01":"2022-07-25","DATE02":"2022-08-01","DATE03":"2022-08-22","DATE04":"2022-08-29","DATE05":"2022-09-19","DATE06":"2022-10-03","DATE07":"2022-10-06","DATE08":"2022-10-27","DATE09":"2022-11-17","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-03","FORECAST_END":"2022-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000038411 | PHASE11 | 2022-10-03 | 2022-10-06 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 207843.4 | 0 |  |  | C000038411 | 207843.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000129 | External RefurbishmentAbsa Tlhabane is a | External RefurbishmentAbsa Tlhabane is a demountable branch and was last refreshed in 2019, and over time the external paint has worn out. The paint on the palisade fence has also faded and in some areas, starting to rust. The patio is covered with floor tiles which deteriorated over a period of time and requires to be refreshed. The external projecting sign is also broken beyond repair and needs to be replaced. This request seeks approval to carry out the above listed defects to enhance the look and feel of the branch.Note: Approved at RIF. Supported by BFM Eng. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Remove existing external floor tiles and replace with new 600x600mm grey porcelain tiles (176m2) Prepare and paint all external surfaces of demountable structure as specified (218m2) Prepare and paint palisade fence (385m2) Prepare and paint gutters and downpipes (80 lm) Prepare and paint access ramp handrails Removal of existing projecting sign and replacement of 600mm (ex stock) projecting sign including electrical connection (already power to the existing sign) |  |  | Region 3 | Free State | 78556X | 1000-71311-01 | Absa TlhabaneCnr Motsatsi & Makheni StreetTlhabane |  | 2022-10-03 | 2022-10-06 |  | ASP-CR0330 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-12 |  | 28471.64 |  | Approved | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000038402 | CLOSED |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000130 | Dilaps | Dilaps |  |  | Region 3 | Limpopo | 77057X | 1000-71282-01 | Absa Burger Street |  | 2022-10-06 | 2022-10-06 |  | ASP-CR0333 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-12 |  | 20311.99 |  | Approved | 2022-10-19 | 2022-10-19 | 0 |  |  |  |  | C000062132# | CLOSED |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-18 | 28105.07 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000131 | UPS Battery Replacement and Air Conditio | UPS Battery Replacement and Air Conditioning UnitAbsa Warden has a standby 30kVA John Deere generator and a 3kVA JNET UPS.This scope is for a UPS size upgrade so that critical load can be supported such as ATMs, Tellers, cash counting machines, treasury, customer service and consultant. During power failure/outage, power to the above mentioned equipment switches off immediately because they are not connected to the UPS. This UPS battery is housed in a non ventilated room and this resulted to an aircon being recommended. This request seeks an approval to replace the UPS and install a midwall split unit aircon. Note: Supported by BFM Engineering. The disposal certificate for the UPS batteries is to be supplied.Scope of Works Decommission and removed failed UPS batteries Supply, install and commision of the UPS Disposal of UPS and certificate to be supplied Supply and install new Samsung 18000 BTU AR18BSHG inverter midwall split unit (x1) Issue the COC after connecting power to the new aircon UPS power installation including COC Allowance for the project guard |  |  | Region 3 | Free State | 79096X | 1000-71571-01 | Absa Warden-Piet Retief St-Warden |  | 2022-10-20 |  |  | ASP-CR0334 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-16 |  | 9953.85 | Approved | 100 | 2022-10-05 | 2023-10-07 | 114469.36 | . | {"MANDT":"111","REFERENCE":70000131,"ONEVIEW":"79096X","DATE01":"2022-08-11","DATE02":"2022-09-08","DATE03":"2022-09-15","DATE04":"2022-09-15","DATE05":"2022-10-20","DATE06":"2022-11-19","DATE07":"2022-12-10","DATE08":"2023-01-24","DATE09":"2023-01-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-19","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000066707 | PHASE11 | 2022-11-19 | 2022-12-10 | NANDE MAQUBELA | floyd mofokeng | 23000387 |  |  |  |  | 2023-02-08 | 99538.57 | 0 |  |  | C000043155 | 99538.57 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000132 | Supply and installation of frosting on s | Supply and installation of frosting on shopfrontThis request seeks approval to install frosting on the shopfront. The internet kiosk was installed and completed in August 2022, however upon completion, the RBB team identified a privacy risk where the internet kiosk is positioned. The recommendation was to install frosting on the shopfront for privacy purposes. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and install new frosting to shopfront (x1) |  |  | Region 3 | Free State | 77122X | 1000-71531-01 | Absa Vrede-Church St-Vrede |  | 2022-10-10 |  |  | ASP-CR0336 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-28 |  | 1360.96 |  | 100 | 2022-10-20 | 2022-10-20 | 0 |  |  |  |  | C000062350# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-18 | 13609.63 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000133 | Replacement of UPS The Branch complaine | Replacement of UPS The Branch complained about the UPS being offline during a power outage/load shedding. The UPS has an internal PC board that is faulty and currently on bypass. The PC board needs to be replaced as spares are obsolete therefore cannot be repaired nor serviced. This request seeks approval to replace the UPS to avoid unplanned business interruptions. There are 15kVA Sentryum 3 Phase UPS s that has already been purchased by Absa and kept in store, one of these UPS will be installed at the branch. The cost is for delivery and commission a 3 phase 15kVA UPS. This work will be carried out by an OEM Vendor. Note: Supported by BFM Engineering. The disposal certificate for the UPS is to be supplied. The travel cost had a significant impact on the overall project cost.Scope of Works Decommission and remove failed UPS Deliver, install and commission 15kVA Sentryum UPS, commissioning data with proof of completion form. Disposal of UPS and certificate to be supplied. The electrical installation of a 3 phase 15kVA UPS and tie in to the current reticulation Certificate of Compliance |  |  | Region 3 | Free State | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies |  | 2022-09-30 |  |  | ASP-CR0337 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-28 |  | 3852.91 |  | 100 | 2022-10-05 | 2022-10-05 | 0 |  |  |  |  | C000081934# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-26 | 38529.1 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000134 | Suppy and installation of 2x trellidor s | Suppy and installation of 2x trellidor sliding gatesThis request seeks approval for the supply and installation of 2x trellidor sliding gates. There has been incidents at the branch where staff found vagrants sleeping in the entrance lobby of the branch in the mornings. The recommendation was made to install trellidor sliding gates as a preventative measure.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. AFS support obtained. Scope of Work Supply and install trellidor sliding gate (3.0 x 2.9m ) (x1) Supply and install trellidor sliding gate (4.14 x 2.9m) (x1) |  |  | Region 3 | Northern Cape | 78684X | 1000-71610-01 | Absa Hartswater29 DF Malan StreetHartswater |  | 2022-10-20 |  |  | ASP-CR0338 | CLSD BUDG AVAC RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-03 |  | 4523.8 | Approved | 100 | 2022-10-20 | 2023-10-07 | 52023.7 |  | {"MANDT":"111","REFERENCE":70000134,"ONEVIEW":"78684X","DATE01":"2022-08-11","DATE02":"2022-08-18","DATE03":"2022-09-08","DATE04":"2022-09-15","DATE05":"2022-10-06","DATE06":"2022-10-20","DATE07":"2022-11-19","DATE08":"2022-12-10","DATE09":"2022-12-04","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-20","FORECAST_END":"2022-11-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000044814 | PHASE11 | 2022-10-20 | 2022-11-19 | NANDE MAQUBELA | floyd mofokeng | 23000579 | [5 empty] | 45238 | 0 |  |  | C000044814 | 45238 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000135 | Dilaps -VO | Dilaps VO |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Absa Bloemfontein RHO |  | 2022-10-20 |  |  | ASP-CR0339 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-11 |  | 406.8 |  | Approved | 2022-10-12 | 2022-10-12 | 0 |  |  |  |  | C000042963 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000136 | Installation of a suspended external and | Installation of a suspended external and internal signageThe suspended Absa signage in the branch passage has worn out and needs replacement. There are also two areas inside the branch that needs internal signages to be installed which are customer service and consultant signage. This request seeks approval for the installation of the items listed above. Note: Approved at RIF. Supported by BFM Eng. Artwork approvals obtained. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works Repair and paint lightbox on affected area Supply the suspended sign backing print 400 x 1450mm Supply suspended sign front transluscent print 440 x 1450mm Supply the customer service and consultant internal signage |  |  | Region 3 | Free State | 78830X | 1000-71555-01 | Absa LangenhovenparkShop 16, Dynarc Walk CentreJan Spies AvenueLangenhovenpark |  | 2022-10-14 | 2022-10-17 |  | ASP-CR0340 | CLSD BUDG AVAC RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-13 |  | 1540.93 |  | Approved | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000038405 | CLOSED |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000137 | Installation of ATM CanopyAt Absa Calvin | Installation of ATM CanopyAt Absa Calvinia, there are two ATM s facing the sun during the day. The customers have complained that they are unable to read the screen while doing their banking transactions at the ATM s. This request seeks approval to supply and install an ATM Canopy as per Absa specifications.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and install (7800w x 2750h) aluminium underdeck patio cover canopy over ATM s (x1) De installation of the existing sun screens. (x2) |  |  | Region 3 | Northern Cape | 78015X | 1000-70869-01 | Absa Calvinia20 Hoop StreetCalvinia |  | 2022-10-28 | 2022-11-30 |  | ASP-CR0342 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-19 |  | 8450.88 | Approved | 100 | 2022-10-27 | 2023-10-07 | 97185.22 |  | {"MANDT":"111","REFERENCE":70000137,"ONEVIEW":"78015X","DATE01":"2022-08-19","DATE02":"2022-08-26","DATE03":"2022-09-16","DATE04":"2022-09-23","DATE05":"2022-10-14","DATE06":"2022-10-28","DATE07":"2022-11-30","DATE08":"2022-12-21","DATE09":"2022-12-12","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-28","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000062728 | PHASE11 | 2022-10-28 | 2022-11-30 | NANDE MAQUBELA | Floyd Mofokeng | 23000544 |  |  |  |  | 2023-01-20 | 84508.89 | 0 |  |  | C000062728 | 84508.89 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000138 | Replacement of JACE Controller | Replacement of JACE Controller |  |  | Region 3 | North West | 22195X | 1000-71242-01 | Absa Mooi River |  | 2022-10-27 |  |  | ASP-CR0343 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-21 |  | 4594.15 |  | Approved | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062788 | CLOSED |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 45941.55 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000139 | Replacement of UPS and batteriesA preven | Replacement of UPS and batteriesA preventative Planned Maintenance was carried out in September on the UPS and according to the report the following needs to be replaced: Power supply, battery charger card, capacitors, fans, inverter IGBT s, batteries, and rectifier contactor. The cost associated with the replacement was established to be too high, considering that the UPS is old. This request seeks approval for the replacement of the current UPS and batteries onsite with one of the 15kVA UPS from Absa stock. Note: Supported by BFM Engineering. The request for delivery and commission of a 3 phase 15KVA UPS at a cost of R14 000,10 incl VAT, and to disconnect the old UPS and connection of new UPS at R4 298.76 incl. VAT Scope of Work Supply and install UPS 15kVA Supply and install Elite VRLA 7a/h (sealed) high rate AGM UPS batteries Disposal of old items and certificate to be supplied. |  |  | Region 3 | North West | 22229X | 1000-71244-01 | Absa Britz MallCnr Hendrik Verwoerd DR and Maple Ridge AveBritz |  | 2022-11-03 |  |  | ASP-CR0344 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-26 |  | 1591.2 | Approved | 100 | 2022-11-02 | 2023-10-07 | 18298.86 |  | {"MANDT":"111","REFERENCE":70000139,"ONEVIEW":"22229X","DATE01":"2022-08-25","DATE02":"2022-09-01","DATE03":"2022-09-22","DATE04":"2022-09-29","DATE05":"2022-10-20","DATE06":"2022-11-03","DATE07":"2022-12-03","DATE08":"2022-12-24","DATE09":"2022-12-18","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-03","FORECAST_END":"2022-12-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000062397 | PHASE11 | 2022-11-03 | 2022-12-03 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-19 | 15912.05 | 0 |  |  | C000062397 | 15912.05 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000140 | Replacement of the existing 4000L water | Replacement of the existing 4000L water tank with a new 2500L tank and installation of a new filtration system A 4000 litre water tank with a booster pump and pressure control device is already present at Absa Phuthadithjaba. Based on the existing staff in the branch, the recommendation was made to reduce the existing size of the water tank. The local municipality is currently experiencing water problems, with the majority of its supplies being dirty and unfit for consumption. The current 4000L water tank will be decommissioned and replaced with a 2500L water tank. A water filtration system will be installed in the tank for safety standards and a water pump system in order to maintain water pressure. Note: Supported by BFM Engineering. Scope of Work Supply (x3) Big blue Filters with (x2) sediment and (x1) carbon block. Non return valve, 25mm Torentti spring loaded P/N 16 (16 BAR) & Fittings. Allowance for additional security during the installation of the filtration system. Six Monthly services for the pump, tank disinfection, filter change, legionella, and portability test has been catered for. No electrical work is affected therefore no COC is required. |  |  | Region 3 | Free State | 78615X |  | Phuthaditjhaba Shopping Centre-Cnr Setai & Motloung St-Phuthaditjhaba |  | 2022-11-03 | 2022-11-30 |  | ASP-CR0348 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Liso Jordan |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-31 |  | 7106.53 | Approved | 100 | 2022-11-17 | 2023-10-07 | 81725.14 |  | {"MANDT":"111","REFERENCE":70000140,"ONEVIEW":"78615X","DATE01":"2022-08-25","DATE02":"2022-09-22","DATE03":"2022-09-29","DATE04":"2022-09-29","DATE05":"2022-11-03","DATE06":"2022-11-30","DATE07":"2022-12-21","DATE08":"2023-02-04","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-30","FORECAST_END":"2022-12-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2Vk","RATING":""} |  |  | C000063117 | PHASE11 | 2022-11-30 | 2022-12-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000558 |  |  |  |  | 2023-08-31 | 71065.34 | 0 |  |  | C000063117 | 71065.34 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000141 | Generator load testing Absa Virginia has | Generator load testing Absa Virginia has a 275KVA 220kW standby generator installed that feeds the branch ground and first floor. It has been discovered that the generator consumes a lot of oil and this was investigated. According to the findings, this is due to oversized generator. Over sizing a generator eventually causes glazing. It is recommended that a dummy load test should be done to safe guard the engine and also confirm if there isnt any other issues with the diesel engine and this request seeks approval for that particular purpose. Note: Supported by BFM EngineeringScope Work Supply generator load testing. |  |  | Region 3 | Free State | 79312X | 1000-71582-01 | Absa Virginia-Virginia Gardens-Virginia |  | 2022-11-30 |  |  | ASP-CR0354 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | MOKOENAM2 | 2022-11-09 |  | 4491.1 | Approved | 100 | 2022-11-17 | 2023-10-07 | 51647.65 |  | {"MANDT":"111","REFERENCE":70000141,"ONEVIEW":"79312X","DATE01":"2022-09-21","DATE02":"2022-09-28","DATE03":"2022-10-19","DATE04":"2022-10-26","DATE05":"2022-11-16","DATE06":"2022-11-30","DATE07":"2022-12-30","DATE08":"2023-01-20","DATE09":"2023-01-14","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-30","FORECAST_END":"2022-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000063116 | PHASE11 | 2022-11-30 | 2022-12-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-23 | 44911 | 0 |  |  | C000063116 | 44911 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000142 | Generator exhaust modificationThis reque | Generator exhaust modificationThis request seeks approval to modify the existing generator exhaust. Rustenburg Plaza branch has a 180kVA Cummins generator that was installed in 2008. The Landlord has requested Absa to do a generator exhaust modification as the existing generator s exhaust pipe is directly blowing onto the Landlord s bullnose leaving a soet stain on the wall. A due diligence was done in order for suppliers to modify the generator exhaust. The proposed schematic drawing has the landlord s approval. Note: Supported by BFM Engineering. LL approval obtained.Scope of Work Extend the exhaust with stainless steel pipe (10m). Supply longer wall brackets that will support the exhaust pipe away from the bullnose. Use 114mm seal clamps. (x8) |  |  | Region 3 | North West |  |  | Building not in our database |  | 2022-12-02 | 2022-12-30 |  | ASP-CR0355 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | MOKOENAM2 | 2022-11-13 |  | 4348.62 |  | 100 | 2022-11-17 | 2022-11-17 | 0 |  |  |  |  | C000063102# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-23 | 43486.25 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000143 | ATM Sunscreens: Absa CarnavonAt Absa Car | ATM Sunscreens: Absa CarnavonAt Absa Carnavon the clients have complained about the sun glare on the ATM screens. The suggestion was that the three sunscreens should be linked to one another by adding small sunscreen panels in the open areas between the already installed sunscreens. The sunscreens need to be repostioned to ensure that there are no gaps between the sunscreens and the canopy. The branch also complaint about the sun glare on the screens. This request seeks approval to add the requested sunscreens, reposition existing screens and apply tinting to prevent sun glare.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Support obtained from Alternative Channels to proceed with this request. Scope of Work De installation of existing canopy & screens (x3) Linking of new additional sunscreen pannels (x3) Re installation of linked sunscreen pannels (x3) Re positioning of the new installation. Application of additional tinting to new installation unit. |  |  | Region 3 | Northern Cape | 79297X | 1000-71360-01 | Absa Carnarvon-Cnr Victoria & Van Riebeeck St-Carnarvon |  | 2022-12-02 | 2022-12-30 |  | ASP-CR0356 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | MOKOENAM2 | 2022-11-13 |  | 3480.68 |  | 100 | 2022-11-24 | 2022-11-24 | 0 |  |  |  |  | C000062395# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-19 | 34806.84 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000144 | New Water tank with booster pump and fil | New Water tank with booster pump and filtration system Absa Sannieshof, is a lease retail branch in North West province. The area is constantly experiencing water outages, whereby on some days it would extend to more than 5 days. During these water scarcity periods, the branch is forced to free the staff members in order to comply with section 43 of the Occupational Health and Safety Act, 1993 Act No, 85 of 1993), stating that every employee must have access to drinking water and for sanitation in the workplace. This request seeks approval to install a 1000lt water tank which is the correct size to fit in the earmarked space, and also will be able to accommodate the number of staff for a maximum of 5 days of a water outage. A water filtration system will be installed in the tank for safety standards and a water pump system in order to maintain water pressure.Note: Supported by BFM Engineering.Scope of Work Supply and Installation of a 1000L water tank (x1) 2 x Big blue tripple filter system with carbon block (x1) Concrete base for the water tank Anti Theft cage (with lock) Non return valve Polycop piping &fittings Power point & Sub DB Allowance for COC Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test has been catered for Allowance for OHS file included |  |  | Region 3 | North West | 77996X | 1000-71305-01 | Sannieshof-Spoor St-Sannieshof |  | 2022-11-30 | 2022-12-22 |  | ASP-CR0357 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-16 |  | 7110.35 |  | 100 | 2022-11-10 | 2022-11-10 | 0 |  |  |  |  | C000063012 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 71103.51 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000145 | Electrical work - Convert the dedicated | Electrical work Convert the dedicated DB into "UPS DB 2"At this branch, the ATMs are not connected to the UPS DB. The servers, tellers, security cameras etc are all connected to normal plugs, hence these experience an intermittent outage during load shedding, due to the change over. This project scope is to connect these critical circuits to UPS DB 2 to make sure that all the necessary circuits are under the UPS. This will include load balancing. The UPS is currently loaded at 10%.Note: Supported by BFM Engineering. Cost to perform work is based on location.Scope of Works Convert the dedicated DB into the "UPS DB 2" Move plugs from normal plugs to dedicated/UPS plugs COC to be issued on completion |  |  | Region 3 | Northern Cape | 79329X | 1000-71361-01 | De Aar-Voortrekker St-De Aar |  | 2022-11-18 | 2022-12-20 |  | ASP-CR0359 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-11-16 |  | 1554.43 | Approved | 100 | 2022-11-24 | 2023-10-07 | 17875.95 |  | {"MANDT":"111","REFERENCE":70000145,"ONEVIEW":"79329X","DATE01":"2022-09-09","DATE02":"2022-09-16","DATE03":"2022-10-07","DATE04":"2022-10-14","DATE05":"2022-11-04","DATE06":"2022-11-18","DATE07":"2022-12-20","DATE08":"2023-01-10","DATE09":"2023-01-02","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-18","FORECAST_END":"2022-12-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000062394 | PHASE11 | 2022-11-18 | 2022-12-20 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-19 | 15544.3 | 0 |  |  | C000062394 | 15544.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000146 | Minor Works: Absa Wilkoppies (CIP 2022)A | Minor Works: Absa Wilkoppies (CIP 2022)Absa Wilkoppies internet kiosk current position does not offer privacy to the clients. The designated internet kiosk position has a partition wall that needs to be demolished in order to make space for the internet kiosk desk. This will include the installation of a bumper rail. Lastly, the branch requires two additional seating benches and two more retractable queue rails. This request seeks approval to carry out the above listed items.Note: Approved by RIF. This project was prioritized by the region and spend will be allocated from the regional minor works budget. Updated floor plan obtained. Scope of Work Supply and install 1.5m black upvc bumper rail to the affected wall and adjust the height to align with chair touch points Demolish an existing 90mm partitional wall and make good (x1) Supply and delivery of S29B benches (x2) Relocation of existing powerpole Decommission and commission internet kiosk powerpoint from old to a new position. Provision for project security guard |  |  | Region 3 | North West | Unknown | 1000-71287-01 | Unknown Building - not in our database |  | 2022-11-30 |  |  | ASP-CR0367 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-11-29 |  | 6003.88 |  | 100 | 2022-10-27 | 2022-10-27 | 69044.63 | 08.08.2023 FM there is savings value in the project. 7997.13 | {"MANDT":"111","REFERENCE":70000146,"ONEVIEW":"Unknown","DATE01":"2022-09-21","DATE02":"2022-09-28","DATE03":"2022-10-19","DATE04":"2022-10-26","DATE05":"2022-11-16","DATE06":"2022-11-30","DATE07":"2022-12-30","DATE08":"2023-01-20","DATE09":"2023-01-14","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-30","FORECAST_END":"2022-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQ=","RATING":""} |  |  | C000046450 | PHASE11 | 2022-11-30 | 2022-12-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-31 | 60038.81 | 0 |  |  | C000046450 | 60038.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000147 | Ceiling tile replacement and LED Absa Gr | Ceilings tile replacement and LED Absa Greenfields was refreshed. The ceiling tiles are mismatched and the original specification is no longer available. The request is to replace the ceiling tiles throughout the branch and in addition to install new LED lighting. Note: Approved at RIF. BFM Engineering and FM support received. RBB has agreed to fund the LED s from the minor works budget. Cost Breakdown:LED Lights Replacement @ R356 394.36 incl. VAT Ceiling Tiles @ R135 845.62 incl. VATTotal Cost: R 492 239.98 incl.VATScope of works: Remove existing ceiling tiles (240sqm) Supply and install ceiling tiles with new specification 1200x600mm ceiling tiles (240sqm) Paint bulkhead and ATM lobby ceiling (75sqm) Remove and reinstall security equipment 600x1200mm LED Panel Luminaire (60W, 4000K) x 20 600x1200mm LED Panel Luminaire (60W, 4000K) Emergency x 15 LED COB Downlight (10W, 4000K) x 27 LED COB Downlight (10W, 4000K) Emergency x 6 600x600mm LED Panel Luminaire (40W, 4000K) x 2 Update drawings to reflect the newly installed LED lights Deep clean after project completion Security guarding during project duration | V1cwMVYyTXlTa1JSVkRCbklBPT0g | m | Region 2 | Eastern Cape | 79189X | 1000-71468-01 | Settlers Square Greenfields-Cnr Settlers Way & Cloverley Rd-East London | N | 2021-02-26 | 2021-06-30 |  | ASP-EC0122 | CLSD BUDG AVAC RESA SETC: | SAPMT | false | false | null | Laxine Maliffe | na | null | 0 |  | L |  | CEASARS | 2021-02-26 |  | 492239.98 |  | 100 | 2022-10-13 | 2022-10-13 | 492239.98 |  | {"MANDT":"111","REFERENCE":70000147,"ONEVIEW":"79189X","DATE01":"2020-12-18","DATE02":"2020-12-25","DATE03":"2021-01-15","DATE04":"2021-01-22","DATE05":"2021-02-12","DATE06":"2022-11-18","DATE07":"2022-12-10","DATE08":"2023-02-15","DATE09":"2023-04-01","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"802:7:21:7:21:644:22:67:45:14","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-18","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgRmViIEZpbmFsIFBPQyBQYWNrIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Low"} |  |  | C000062124 | PHASE11 | 2022-11-18 | 2022-12-10 | RODERICK NEVAY | Nokuthula Manzini | 23000494 |  |  |  |  | 2023-01-18 | 428034.76 | 287634.5 |  |  | C000062124 | 140400.26 | CIP2023XP | 7564.61 |  | 0 | 0 |  | 0 |  | 0
70000148 | Removal of reception desk (CIP 2022)Abs | Removal of reception desk (CIP 2022)Absa Knysna has a client call system which was managed by the branch hostess since its installation when the branch was revamped in 2015. The existing call system in the branch is no longer in use and the request is for the call system to be removed along with the reception desk upon which it was installed.Note: Engineering support received and RBB Regional approval on proposed cost received. Scope of Works: Remove call system equipment from reception desk Remove and dispose the reception desk Submit disposal certificate for the desk Covid 19 wipe down on all touch points |  |  | Region 2 | Eastern Cape | 77262X | 1000-70816-01 | Absa Garden Route Centre, Cnr Gray & Main Street, Knysna |  | 2022-03-10 | 2022-03-10 |  | ASP-EC0182 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 6603.78 |  | Approved | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904557 | CLOSED | 2022-03-10 | 2022-03-10 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000149 | New Signage (2022 CIP)As a precautionary | New Signage (2022 CIP)As a precautionary measure it was requested that precautionary warning signs are installed at Absa Middelburg. This request was raised after the Local Municipality has started road works in front of the branch. To highlight the slippery surfaces around the branch as a result of the roadworks it has been recommended that signs be installed to highlight the risk to the staff and clients.Note: Artwork approved, Bidvest Engineering supported, Cost approved by RBB RM. CRES OHS support obtained.Scope of Works: Supply 2 x Disclaimer Signs Slippery When Wet . |  |  | Region 2 | Eastern Cape | 76589X | 1000-71014-01 | Absa Middelburg, 23 Van Reenen Street, Middelburg |  | 2022-02-14 | 2022-02-28 |  | ASP-EC0183 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 1899.8 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2901594 | CLOSED | 2022-02-14 | 2022-02-28 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000150 | Replacement of external signageAbsa Plet | Replacement of external signageAbsa Plettenberg Bay was revamped in 2018 and the current signage was installed during the revamp. The current signage is showing signs of rust, further to this when it rains water gathers in the ribbon portion of the sign and this water drips down onto clients standing in the queue outside the branch waiting to transact. The request was to replace the ribbon sign however Absa Design was engaged and it was recommended to replace the existing ribbon sign with a fascia sign. Note: RBB regional approval; Bidvest Engineering support received; Artwork approval received and Landlord approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Remove existing ribbon sign and make good Install refurbished 2000 x 2000mm illuminated facia sign Connect sign to existing power Paint where sign has been removed Covid wipe down by contractor. |  |  | Region 2 | Eastern Cape | 77723X | 1000-71034-01 | Absa Plettenberg Bay, Sun Centre Development, 23 Main Street, Plettenberg Bay |  | 2022-03-30 | 2022-04-29 |  | ASP-EC0184 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 42631.37 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2910290 | CLOSED | 2022-03-30 | 2022-04-29 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000151 | Replacement of Brochure Holders (CIP 20 | Replacement of Brochure Holders (CIP 2022) |  |  | Region 2 | Eastern Cape | 78801X | 1000-71054-01 | Absa Queenstown |  | 2022-02-22 | 2022-03-31 |  | ASP-EC0185 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 23971.75 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2902832 | CLOSED | 2022-02-22 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000152 | Power point installation | Power point installation |  |  | Region 2 | Eastern Cape | 37159X | 1000-70797-01 | Absa Riversdale (Adhoc) |  | 2022-02-22 | 2022-03-23 |  | ASP-EC0186 | CLSD PCNF BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 13500 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2906852 | CLOSED | 2022-02-22 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000153 | Minor Works- Absa Vincent Office Park (C | Minor Works Absa Vincent Office Park (CIP 2022) |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Absa Vincent Office Park |  | 2022-02-22 | 2022-03-29 |  | ASP-EC0187 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 36226.76 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2902834 | CLOSED | 2022-02-22 | 2022-03-29 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000154 | Minor Works - Absa Despatch (CIP 2022)Ab | Minor Works Absa Despatch (CIP 2022)Absa Despatch had minor works done in 2020 which excluded the existing entrance ramp and external signage. This ramp has a rubberized surface that has deteriorated over time. The request is to rebuild and resurface the ramp utilising a new non slip finish along with new handrails. In addition, Absa has requested the replacement of the existing fascia sign with a projecting sign as the existing sign is not visible when approaching the branch. Furthermore, Africa Security requested the ATM wall facing the client area is to be upgraded to the new specification meta wall. Lastly, a Hydroboil and inline filters with replacement cartridges will be installed due to the metros water condition. Note: Landlord approval received; Engineering support received; Artwork approval received; Bidvest OHS support; Absa OHS support. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Refurbish and resurface existing ramp (clay pavers as per Landlord approval) Supply and install hand railings Re route rain water gutter pipe at ATM area. Remove existing external fascia sign 2000x2000mm and set aside to reuse Install new ribbon signage size: 800mm High x 14m Install new double sided projecting sign size: 1500 x 1500mm Paint facade where existing sign is to be removed 25sqm. Deinstall and reinstall 3 x ATM profiles Build new Absa spec front cubicle steel lined wall 13sqm Existing electrical to be reused / repositioned in ATM area COC to be issued on completion. Removal of existing geyser and installation of new 5L Hydroboil incl. inline filters and supply of 2 replacement cartridges. Existing electrical point to be utilised. |  |  | Region 2 | Eastern Cape | 76549X | 1000-71459-01 | Absa Despatch,32B Main Street, Despatch |  | 2022-03-07 | 2022-03-31 |  | ASP-EC0189 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 337260.8 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | C000062055 | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-18 | 4984.28 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000155 | Replacement of walk-off mats (CIP 2022) | Replacement of walk off mats (CIP 2022) |  |  | Region 2 | Eastern Cape | 36281X | 1000-70990-01 | Absa Libode Shopping Centre |  | 2022-03-07 | 2022-03-31 |  | ASP-EC0190 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 4698.85 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2902841 | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000156 | Replacement of HVAC unit in banking hall | Replacement of HVAC unit in banking hall (2022 CIP) |  |  | Region 2 | Eastern Cape | 79189X | 1000-71468-01 | Absa Greenfields |  | 2022-03-07 | 2022-03-31 |  | ASP-EC0194 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 231000 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900483 | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000157 | Supply and installation of new HVAC unit | Supply and installation of new HVAC unit in teller area (Ad Hoc Request) |  |  | Region 2 | Eastern Cape | 77747X | 1000-70855-01 | Absa Mossel Bay |  | 2022-03-07 | 2022-03-31 |  | ASP-EC0195 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-01-19 |  | 51584.05 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900484 | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000158 | Intelcab UPS Battery Replacement (Item f | Intelcab UPS Battery Replacement (Item for noting) (2021 Accrual) |  |  | Region 2 | Eastern Cape | 77686X | 1000-71032-01 | Absa Walmer Park Shopping Centre |  | 2021-07-13 | 2021-07-30 |  | ASP-EC0196 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-24 |  | 23886.65 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900485 | CLOSED | 2021-07-13 | 2021-07-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000159 | Intelcab UPS Battery Replacement (Item f | Intelcab UPS Battery Replacement (Item for noting) (2021 Accrual) |  |  | Region 2 | Eastern Cape | 36267X | 1000-70989-01 | Absa Bhisho |  | 2021-11-05 | 2021-11-05 |  | ASP-EC0197 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-21 |  | 23886.65 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900403 | CLOSED | 2021-11-05 | 2021-11-05 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000160 | Professional Fees- Structural Crack (CIP | Professional Fees Structural Crack (CIP 2022) |  |  | Region 2 | Eastern Cape | 20952X | 1000-70922-01 | Absa 60 Sutherland Street |  | 2022-03-15 | 2022-05-31 |  | ASP-EC0198 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-02-01 |  | 447677.66 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | C000017792 | CLOSED | 2022-03-15 | 2022-05-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000161 | Professional Fees- Structural Crack (CIP | Professional Fees Structural Crack (CIP 2022) |  |  | Region 2 | Eastern Cape | 20952X |  | Absa 60 Sutherland Street |  | 2022-05-16 | 2022-06-10 |  | ASP-EC0198 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  |  |  |  | 0 |  | Approved | 2022-04-20 | 2022-04-20 | 0 |  |  |  |  | C000017792 | CLOSED |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000162 | New walk-off mat (CIP 2022)Absa Aliwal N | New walk off mat (CIP 2022)Absa Aliwal North currently has a loose red walk off mat that can no longer be cleaned effectively. The request is to install a drop in new specification walk off mat.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Remove floor tiles in front of revolving door in the branch - 1500x1200mm Create drop in for walk off mat Supply Matco: Trioscape grey walk off mat - 1500x1200mm Allow for the above works to be conducted after hours to avoid foot traffic. |  |  | Region 2 | Eastern Cape | 79209X | 1000-71060-01 | Absa Aliwal North, 47 Somerset Street, Aliwal North |  | 2022-06-01 | 2022-11-25 |  | ASP-EC0199 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | CEASARS | 2022-02-07 |  | 19227.28 |  | 100 | 2022-08-04 | 2022-08-04 | 19227.28 |  | {"MANDT":"111","REFERENCE":70000162,"ONEVIEW":"79209X","DATE01":"2022-03-23","DATE02":"2022-04-28","DATE03":"2022-07-20","DATE04":"2022-07-27","DATE05":"2022-08-04","DATE06":"2022-11-24","DATE07":"2022-11-25","DATE08":"2022-12-16","DATE09":"2023-01-30","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-24","FORECAST_END":"2022-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000060589 | PHASE11 | 2022-11-24 | 2022-11-25 | RODERICK NEVAY | Juanita van Coller | 23000611 |  |  |  |  | 2023-01-11 | 16719.36 | 12629.05 |  |  | C000030638 | 4090.32 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000163 | Installation of TrellidoorThe entrance l | Installation of TrellidoorThe entrance lobby at Absa Ntabankulu has become a home to vagrants after hours. The vagrants are also soiling the area overnight which is creating a hazard / unpleasant environment when staff arrive in the morning. It was requested that a trellidoor be installed to close off this area to prevent vagrants from accessing it after hours. AFS has placed a guard in the interim.Note: RBB cost approval received; Engineering support received; AFS support received and Landlord approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply and install centre opening, white Trellidoor with slam lock, 3930mm x 2430mm at the maximum dimensions. Recess floor for Trellidoor track. Covid wipe down by contractor. |  |  | Region 2 | Eastern Cape | 20949X | 1000-70921-01 | Absa Ntabankulu, 129 Main Street, Ntabankulu |  | 2022-03-21 | 2022-04-29 |  | ASP-EC0203 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-16 |  | 51338.76 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2910275 | CLOSED | 2022-03-21 | 2022-04-29 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000164 | Replacement of HVAC units | Replacement of HVAC units |  |  | Region 2 | Eastern Cape | 79244X | 1000-71469-01 | Absa East London, 85 Oxford Street |  | 2022-04-04 | 2022-04-30 |  | ASP-EC0204 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-18 |  | 399500 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2906850 | CLOSED | 2020-04-04 | 2022-04-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000165 | Reinstatement | Reinstatement |  |  | Region 2 | Eastern Cape | 76928X | 1000-71021-01 | Summerstrand Village-8th Ave-Port Elizabeth | N | 2022-03-22 | 2022-11-28 |  | ASP-EC0206 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-03-02 |  | 426251.02 |  | 100 | 2022-10-13 | 2022-10-13 | 426251.02 |  | {"MANDT":"111","REFERENCE":70000165,"ONEVIEW":"76928X","DATE01":"2022-01-11","DATE02":"2022-06-28","DATE03":"2022-10-10","DATE04":"2022-10-13","DATE05":"2022-10-13","DATE06":"2022-10-18","DATE07":"2022-11-30","DATE08":"2023-03-06","DATE09":"2023-04-20","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"413:168:104:3:0:5:43:96:45:24","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-18","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBNYXIgLSBGaW5hbCBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000043383 | PHASE11 | 2022-10-18 | 2022-11-30 | RODERICK NEVAY | Juanita van Coller | 23000499 | [5 empty] | 69172.46 | 301480.58 |  |  | C000043383 | 69172.46 |  | 38695.55 |  | 0 | 0 |  | 0 |  | 0
70000166 | Procurement of visitor chairsThe Absa 10 | Procurement of visitor chairsThe Absa 106 York Street George branch was revamped in 2015 and received minor works in 2021. The branch had fabric waiting area chairs but were removed as part of the Covid 19 Regulations. The branch utilised the pause area chairs for client seating,however most of these chairs had since been damaged and cannot be repaired. It was therefore recommended that these chairs be replaced with new chairs. Note: RBB cost approval received & Engineering support received. As per Absa design approved spec. This project was prioritised by the region and spend will be allocated from the regional minor works budget. No chairs are available in store.Scope of works: 20 x Visitor Chairs Upholstered and plastic wrapped (approximately 10 week lead time) Destruction of 10 x plastic chairs. |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street, George |  | 2022-04-29 | 2022-05-31 |  | ASP-EC0207 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-11 |  | 115368.93 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912255 | CLOSED | 2022-04-29 | 2022-05-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000167 | Bi Directional Drop Safe | Bi Directional Drop Safe |  |  | Region 2 | Eastern Cape | 78501X | 1000-71048-01 | Absa Butterworth |  | 2022-05-01 | 2022-06-30 |  | ASP-EC0208 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-24 |  | 113897.54 |  | Approved | 2022-06-20 | 2022-06-20 | 0 |  |  |  |  | C000061210 | CLOSED | 2022-05-01 | 2022-06-30 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-13 | 26810.62 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000168 | Rerouting of water supply pipeAbsa Dutyw | Rerouting of water supply pipeAbsa Dutywa water tank was installed in 2021. The feed from the water tank to the branch was tampered with on several occasions. The contractor previously reconnected the piping, tested the pressure and the connection thereafter. At the beginning of March, the branch advised that the water supply from the tank has stopped once again. After investigations it was recommended by Engineering to reroute the water pipe directly from the water tank to the branch and bypass the centres water connections to prevent further tampering.Note: Supported by Engineering.To be funded from CIP 2022 cancelled project budget allocated to Atlantis Generator was R629k.Scope of works: Decommission existing water pipe connection to the branch Install a new dedicated water connection from the water tank to the branch 22mm composite pressure pipe 60meters Pressure test to be done on completion of the installation. |  |  | Region 2 | Eastern Cape | 35033X | 1000-70958-01 | Absa Dutywa Central Square,Richardson Road,Idutywa |  | 2022-05-01 | 2022-06-30 |  | ASP-EC0210 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-24 |  | 31522.04 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2912883 | CLOSED | 2022-05-01 | 2022-06-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000169 | Replacement of external floor tilesAbsa | Replacement of external floor tilesAbsa Alexandria branch external floor finishes reflect the old Corporate Identity. RBB has requested for the entire external floors to be retiled and replaced with the current non slip specification.Note: RIF support received, this project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Remove all existing external floor tiles starting from the entrance to the branch ending at the ATM area (40sqm) Supply and install new floor tiles starting from the entrance to the branch ending at the ATM area as per Absa spec NON SLIP (40sqm) Supply and install aluminium edge trim (40m) |  |  | Region 2 | Eastern Cape | 76600X | 1000-71015-01 | Absa Alexandria,Cnr Voortrekker & Krog Street,Alexandria |  | 2022-07-01 | 2022-09-30 |  | ASP-EC0212 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-08 |  | 51573.5 |  | Approved | 2022-05-31 | 2022-05-31 | 0 |  |  |  |  | C000062396 | CLOSED | 2022-07-01 | 2022-09-30 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-19 | 3990 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000170 | Replacement of forex signThe vinyl on th | Replacement of forex signThe vinyl on the external Foreign Exchange sign at Absa Somerset East has been vandalised. Absa Design has recommended for the existing sign to be replaced with a more durable sign. Note: RIF support received, this project was prioritised by the region and spend will be allocated from the regional minor works budget. Artwork approved by RBB Design.Scope of works: Remove exiting sign. Supply and install new non illuminated bent up acm/aluminium panel with vinyl decoration and laminated with clear vinyl size: 800 x 600. |  |  | Region 2 | Eastern Cape | 76426X | 1000-71008-01 | Absa Somerset East,57 Njoli Street,Somerset East |  | 2022-07-01 | 2022-09-30 |  | ASP-EC0213 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-08 |  | 8486.31 |  | Approved | 2022-05-31 | 2022-05-31 | 0 |  |  |  |  | C000025395 | CLOSED | 2022-07-01 | 2022-09-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000171 | Dry Wall + New ITAS Door | Dry Wall + New ITAS Door |  |  | Region 2 | Eastern Cape | 78801X | 1000-71054-01 | Absa Queenstown - Hexagon |  | 2022-07-01 | 2022-09-30 |  | ASP-EC0215 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-08 |  | 210496.83 |  | Approved | 2022-06-20 | 2022-06-20 | 0 |  |  |  |  | C000061216# | CLOSED | 2022-07-01 | 2022-09-30 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-13 | 18253.61 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000172 | Enhancement of Security in ATM areaThere | Enhancement of Security in ATM areaThere was an incident at Absa Cofimvaba with an attempted attack on the ATM s. Absa Africa Security has requested enhancements are made to the ATM room/lobby. The enhancements include the construction of a new specification metal wall and the installation of expanded mesh below the ceiling in the ATM Room.Note: Approved at RIF. Engineering, AFS and FM support received. As confirmed at RIF, please note that Africa Security has indicated that their 2022 budget is depleted and that RBB has undertaken the decision to avail budget to execute this upgrade.Scope of works: Deinstall and Reinstall 4x ATM profiles Build new Absa spec front cubicle steel lined wall (26sqm) Supply and install wall tiles - 14sqm Rebuild Server room wall in new Absa spec steel lined wall - 9sqm Paint ATM cubicle - 150sqm Supply and install mesh above ceiling in ATM cubicle - 30sqm Build new Absa spec front cubicle steel lined wall 13m2 Supply and install floor tiles in ATM cubicle - 30sqm Skim and paint ceiling in ATM lobby - 30sqm Paint ceiling in ATM lobby - 60sqm Electrical COC to be supplied for all electrical works Security guard services to be utilised |  |  | Region 2 | Eastern Cape | 78540X | 1000-71049-01 | Absa Cofimvaba,Cnr Market & Main Street, Cofimvaba |  | 2022-07-01 | 2022-09-30 |  | ASP-EC0216 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-04-28 |  | 469788.49 |  | 100 | 2022-10-13 | 2022-10-13 | 469788.49 |  | {"MANDT":"111","REFERENCE":70000172,"ONEVIEW":"78540X","DATE01":"2022-04-22","DATE02":"2022-04-26","DATE03":"2022-07-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-11-07","DATE07":"2022-11-25","DATE08":"2022-12-06","DATE09":"2022-12-30","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"131:4:79:69:21:26:18:11:24:16","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-07","FORECAST_END":"2022-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBEZWMgUE9DIFN1Ym1pdHRlZCA=","RATING":"Low"} |  |  | C000062140 | PHASE11 | 2022-11-07 | 2022-11-25 | RODERICK NEVAY | Juanita van Coller | 23000495 |  |  |  |  | 2023-01-18 | 408511.73 | 275703.76 |  |  | C000044053 | 132807.97 | CIP2023XP | 28606.43 |  | 0 | 0 |  | 0 |  | 0
70000173 | Waterproofing - Absa Somerset East (CIP | Waterproofing Absa Somerset East (CIP 2022)Absa Somerset East has experienced various roof leaks over time. Reactive maintenance and patchwork has been done, however due to the wear and tear of the original waterproofing the request has been made that the waterproofing is redone where affected and a warranty be provided. It is recommended that the existing waterproofing is redone on the entire roof and the resultant damages be repaired as part of the project.Note: Project is part of the prioritised Waterproofing projects for CIP 2022. Workmanship warranty for 1 year and product warranty for 10 years. Scope of works:(1) Concrete Roof 76sqm Remove and repair existing Torch On Power wash existing Torch On Reseal all joints where Torch On was removed Clean gutters (30Lm) Repair leaking aircon drain pipe Prep and paint roof with liquid rubber(2) Corrugated/IBR Roof 432sqm Power wash corrugated roof Repair leaks on roof Clean box gutters and parapets 60m x 1.2m (72sqm) Prep and paint box gutters and parapets (60sqm) Close and seal aircon drain pipes and condenser pipe holes Prep and paint roof with liquid rubber (3) Side Alley: Treat, damp seal and paint walls (55sqm) Unblock drain(4) Online Banking Area: Install single skinned moisture drywall in Online banking area (19.2sqm) Skim, prep and paint wall (20sqm)(5) Ground floor Consultants Office: Treat, damp seal and paint wall (12sqm)(6) Teller Area: Replace 8x ceiling tiles(7) Kitchen Area: Treat, damp seal and paint wall (8sqm) Replace damaged kitchen cupboard skirting (8) First Floor Boardroom: Treat and damp seal wall (14sqm) Prep and paint wall (62sqm)(9) First Floor Storeroom: Treat, damp seal and paint wall (45sqm) |  |  | Region 2 | Eastern Cape | 76426X | 1000-71008-01 | Absa Somerset East, 57 Njoli Street, Somerset East |  | 2022-09-01 | 2022-09-30 |  | ASP-EC0217 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-05-09 |  | 313200 |  | Approved | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000017761 | CLOSED | 2022-09-01 | 2022-09-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000174 | Waterproofing - Absa Graaff-Reinet (CIP | Waterproofing Absa Graaff Reinet (CIP 2022)Absa Graaff Reinet has experienced various roof leaks over time. Reactive maintenance and patchwork has been done, however due to the wear and tear of the original waterproofing the request has been made that the waterproofing is redone where affected and a warranty be provided. It is recommended that the existing waterproofing is redone on the entire roof and the resultant damages be repaired. As part of the project the existing roof top recreational area will also be demolished.Note: Project is part of the prioritised Waterproofing projects for CIP 2022. Workmanship warranty for 1 year and product warranty for 10 years. Scope of works:(1) Concrete Roof 249sqm Power wash existing Torch On Clean gutters (35Lm) Prep and paint roof with liquid rubber (2) Corrugated/IBR Roof 390sqm Power wash corrugated areas Clean box gutters and parapets 60m x 1m (60sqm) Prep and paint box gutters and parapets (60sqm) Prep and paint roof with liquid rubber (3) Roof Top Recreational Area Remove benches (9Lm) Demolish braai area (2.5sqm) Prepare and paint external hair line cracks (150sqm) |  |  | Region 2 | Eastern Cape | 76442X | 1000-71458-01 | Absa Graaff-Reinet,5 Church Street,Graaff-Reinet |  | 2022-09-01 | 2022-09-30 |  | ASP-EC0218 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-05-09 |  | 268300 |  | Approved | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000017760 | CLOSED | 2022-09-01 | 2022-09-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000175 | Waterproofing - Absa George (CIP 2022)Ab | Waterproofing Absa George (CIP 2022)Absa 106 York Street George has experienced minor roof leaks over time. Reactive maintenance and patchwork has been done, however due to the wear and tear of the original waterproofing the request has been made that the waterproofing is redone where affected and a warranty be provided. It is recommended that the existing waterproofing is redone on the entire roof and the resultant damages be repaired as part of the project.Note: Project is part of the prioritised Waterproofing projects for CIP 2022. Workmanship warranty for 1 year and product warranty for 10 years. Scope of works:(1) Concrete Flat Roof 106sqm Power wash existing Torch On Prep and paint roof with liquid rubber Clean full bore Prep and paint parapet wall with liquid rubber (192Lm)(2) Kliplock Roof 740sqm Power wash Kliplock areas Prep and paint roof with liquid rubber Clean gutters (22sqm) Prep and paint parapets (81Lm)(3) Corrugated/IBR Pitch Roof 138sqm Power wash Corrugated areas Prep and paint roof with liquid rubber Clean gutters (32sqm) |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa George,106 York Street, George |  | 2022-09-01 | 2022-09-30 |  | ASP-EC0219 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-05-09 |  | 453500 |  | Approved | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000017762 | CLOSED | 2022-09-01 | 2022-09-30 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000176 | Bi Directional Drop Safe | Bi Directional Drop Safe |  |  | Region 2 | Eastern Cape | 78953X | 1000-71060-01 | Absa Mount Frere |  | 2022-07-01 | 2022-09-30 |  | ASP-EC0221 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-26 |  | 134332.82 |  | Approved | 2022-06-20 | 2022-06-20 | 0 |  |  |  |  | C000019932 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000177 | Connection of ITAS door to UPSAfrica Sec | Connection of ITAS door to UPSAfrica Security has requested for a dedicated (red) plug to be installed at Absa Plettenberg Bay s ITAS Small foot Mantrap door leading to the Teller Area. The plug is to be connected to the 10kVA Intel Cab UPS in order to supply constant power to the door during prolonged power outages. The current Load is at 23% and projected load to be 24%.Note: Supported by RBB and Africa Security. Project will be funded from the EOL various UPS batteries round trip in EC.Scope of works 1 x 20AMP Circuit Breaker 1 x dedicated red plug 45 meters cable Electrical COC to be provided upon completion Covid wipe down by contractor. |  |  | Region 2 | Eastern Cape | 0 | 1000-71034-01 | Absa Plettenberg Bay, 23 Main Street, Plettenberg Bay |  | 2022-08-01 | 2022-09-30 |  | ASP-EC0222 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-06-03 |  | 5870.64 | Approved at CB/BTB |  | 2022-06-30 | 2023-02-09 | 77913.65 | Approved |  |  |  | C000067805 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-02-13 | 67751 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000178 | Installation of blinds (CIP 2022)In Dece | Installation of blinds (CIP 2022)In December 2020 Absa Riversdale underwent a minor refresh whereby vinyl was installed on the ground floor windows in the waiting area. In March 2022 an Online Banking desk was installed in the waiting area, however the vinyl that was installed on the windows in 2020 only provides limited privacy. The branch is located in a busy street, when transacting on the Online Banking computer the public is in view of client information. The branch manager has requested for blinds to be installed over the vinyl to allow the client more privacy.Note: Supported by Bidvest Engineering & RBB. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Supply and install 2 x 25mm brushed aluminium venetian blinds on ground floor: Window 1: 1570mm x 2400mm Window 2: 1590mm x 2400mm |  |  | Region 2 | Eastern Cape | 37159X | 1000-70797-01 | Absa Riversdale,Cnr Church & Dixon Streets,Riversdale |  | 2022-08-01 | 2022-09-30 |  | ASP-EC0223 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-06-03 |  | 3099.26 |  | Approved | 2022-07-14 | 2022-07-14 | 0 |  |  |  |  | C000026179 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000179 | Closing off of Teller areaAbsa Kempston | Closing off of Teller areaAbsa Kempston Road was last refreshed in 2019. The teller staff complement decreased and Business requested to close off the teller area. It was therefore recommended by Business that the clients only utilise the existing 2 Bulk Tellers for all cash related banking transactions. Note: RBB and Engineering support received. Updated floor plan pending Absa Design approval. This project was prioritised by the region and spend will be allocated from the regional minor works CIP 2022 budget. Scope of works: Close Tellers 1 6 with a single skimmed dry wall (15Lm) Install Alu Skirting (15Lm) Prep and Paint wall to spec (40.5sqm) Remove 3x poster frames in Teller area and reinstall on new dry wall Remove 1x Bulk Teller suspended sign Remove 1x Teller suspended sign and reinstall where Bulk Teller sign was removed Reposition mobile Q Rails |  |  | Region 2 | Eastern Cape | 76390X | 1000-71006-01 | Absa Kempston Road,208 Kempston Road,Port Elizabeth |  | 2022-08-01 | 2022-09-30 |  | ASP-EC0224 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-06-09 |  | 27827.12 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | C000031517 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000180 | Dilaps | Dilaps |  |  | Region 2 | Eastern Cape | 20952X | 1000-70922-01 | Absa 60 Sutherland Street |  | 2022-06-17 | 2022-09-30 |  | ASP-EC0226 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-06-13 |  | 21418.75 |  | Approved | 2022-06-22 | 2022-06-22 | 0 |  |  |  |  | C000021187 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000181 | Dilaps Electrical COC | Dilaps Electrical COC |  |  | Region 2 | Eastern Cape | 0 | 1000-71015-01 | Absa Alexandria,Cnr Voortrekker & Krog Street,Alexandria |  | 2022-08-01 | 2022-10-31 |  | ASP-EC0227 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-06-23 |  | 11323.5 |  | Approved | 2022-07-25 | 2022-07-25 | 0 |  |  |  |  | C000027225 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000182 | Dilaps | Dilaps |  |  | Region 2 | Eastern Cape | 20952X | 1000-70922-01 | Absa 60 Sutherland Street |  | 2022-07-07 | 2022-07-31 |  | ASP-EC0228 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-06-29 |  | 107528.8 |  | Approved | 2022-07-01 | 2022-07-01 | 0 |  |  |  |  | C000022952 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000183 | HVAC upgrade Absa Jeffreys Bay was ident | HVAC upgrade Absa Jeffreys Bay was identified for a minor works project in 2022. During the DD that was conducted it was detected that the branch has no functional fresh air intakes. The solution proposed is to install new ducted hide away units with the addition of fresh air intakes in order to meet the required standards.Note: Supported by Engineering & RBB. The design has been optimised for environmental considerations and the equipment is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. This project will be funded from cancelled EOL HVAC projects. Scope of works: Remove all existing ducted hide away HVAC units Supply and install 5x 36 000btu York ducted hide away units Utilise existing ducting & install additional ducting and diffusers (x20) Supply and install inline fans (x7) for fresh air with exterior louvers (x7) and filters (x7) Replace existing refrigerant piping and cabling Anti corrosion treatment all units Supply and install electrical power points Electrical COC to be issued Gas & Equipment Disposal certificates will be supplied.Leadtime 12 working days and Programme 3 weeks. |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | Absa Jeffreys Bay ,The Nautilus Builiding, Da Gama Rd , Jeffreys Bay |  | 2022-08-15 | 2022-10-27 |  | ASP-EC0229 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-07-05 |  | 496653 |  | Approved | 2022-07-07 | 2022-07-07 | 0 |  |  |  |  | C000023825 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000184 | Replacement of HVAC Unit The HVAC unit s | Replacement of HVAC Unit The HVAC unit serving the banking hall and offices on the ground floor at Absa Cradock was installed in 2005. The unit is not cooling due to the outdoor compressor that is faulty. Due to the age of the unit the parts are no longer available to repair the unit and thus needs to be replaced.Note: Supported by Engineering. The design is based on a like for like replacement for environmental considerations and the equipment is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. Scope of works: Remove existing faulty unit including refrigerant piping and cabling Supply and install new Samsung Hide Away 85 000btu Inverter unit including refrigerant copper piping and cabling Manufacture ducting for the supply air and return air to fit onto the existing ducting installed Test run and commission new HVAC unit 12 Months maintenance of new unit is included and scheduled for every 3 months 3 Minor and 1 Major Dispose of old unit and supply a disposal certificate. |  |  | Region 2 | Eastern Cape | 76934X | 1000-71022-01 | Absa Cradock,42 Adderley Street,Cradock |  | 2022-09-19 | 2022-09-30 |  | ASP-EC0230 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-07-19 |  | 147000 |  | Approved | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000029880 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000185 | Installation of blindsAbsa 60 Sutherland | Installation of blindsAbsa 60 Sutherland was revamped in 2021. The consultants are situated on the Mezzanine floor and at midday the sun s glare on the PC screens makes it difficult for the staff member to read. Business requested for blinds to be installed behind the consultants desks.Note: RBB and ENG support received. This project was prioritised by the region and spend will be allocated from the regional minor works CIP 2022 budget. Scope of works: Supply and install 5x 25mm brushed aluminium venetian blinds on the Mezzanine floor behind the Consultants desks. Measurement per window: 960 x 1310 mm |  |  | Region 2 | Eastern Cape | 20952X | 1000-70922-01 | Absa 60 Sutherland Street,60 Sutherland Street,Mthatha |  | 2022-09-30 | 2022-10-31 |  | ASP-EC0231 | CLSD BUDG AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-07-27 |  | 12644.25 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | C000031518 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000186 | HVAC ReplacementThe HVAC unit in the Bra | HVAC ReplacementThe HVAC unit in the Branch Administrator s office at Absa Mossel Bay was installed in 2016 and is no longer operational. Various attempts to repairs the unit have been unsuccessful. The compressor, internal PC board and external PC boards were damaged due to load shedding and power surges. The request is for the replacement of this HVAC unit and installation of appropriate type 3 surge protection.Note: The design is based on the existing, the equipment to be installed is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. Like for like replacement, no GMP impact after warranty period.Scope of works: Remove existing unit Install 1x Carrier 36000BTU under ceiling Invertor AC unit Unit Bluechem treated Supply new ducting, piping, cable and bracket Type 3 surge protection Issue of Electrical COC on completion Disposal certificate to be issued |  |  | Region 2 | Eastern Cape | 77747X | 1000-70855-01 | Absa Mossel Bay-Marsh St-Mossel Bay | N | 2022-09-13 | 2022-09-30 |  | ASP-EC0232 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | CEASARS | 2022-07-27 |  | 71628.38 |  | 100 | 2022-08-25 | 2022-08-25 | 71628.38 |  | {"MANDT":"111","REFERENCE":70000186,"ONEVIEW":"77747X","DATE01":"2022-07-05","DATE02":"2022-07-22","DATE03":"2022-08-12","DATE04":"2022-08-19","DATE05":"2022-08-25","DATE06":"2022-10-14","DATE07":"2022-11-12","DATE08":"2022-12-06","DATE09":"2022-12-13","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"118:17:21:7:6:50:29:24:7:3","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-14","FORECAST_END":"2022-11-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDYgRGVjIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000061150 | PHASE11 | 2022-10-14 | 2022-11-12 | RODERICK NEVAY | Juanita van Coller | 23000566 |  |  |  |  | 2023-01-13 | 62285.54 | 0 |  |  | C000033788 | 62285.55 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000187 | Replacement of x3 Garage doorsAbsa Graaf | Replacement of x3 Garage doorsAbsa Graaff Reinets garage doors are approximately 20 years old. Due to the wear and tear over the years the doors are jamming when opening and closing and various attempts to repair the slats and guides have been unsuccessful. The garage motors were replaced in 2019. The request is for the replacement of the 3x garage doors.Note: The design is based on like for like replacement. Engineering support received. Corp CIP funding available to cover the costs due to savings/underspend on other Corp projects in the region.Scope of works: Remove existing garage doors Install 3x industrial garage doors powder coated galvanized slats with open vents 2x 4326(w) x 2400(h)mm 1x 4711(w) x 2400(h)mm Refit existing garage motors onto new doors Issue disposal certificate |  |  | Region 2 | Eastern Cape | 76442X | 1000-71458-01 | Absa Graaff-Reinet,5 Church Street, Graaff-Reinet |  | 2022-09-30 | 2022-10-31 |  | ASP-EC0234 | CLSD BUDG AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-08-01 |  | 137873.2 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000061020 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-12 | 4521.73 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000188 | ATM lobby and External signage upgrade ( | ATM lobby and External signage upgrade (CIP 2022)Absa Mqanduli had minor works completed in April 2022 however, the ATM lobby area was not included in the scope of works. The client has requested to replace the floor tiles with non slip tiles to match existing internal floor finishes. Furthermore, the branch is situated in the main road however the existing signage is not visible to clients when passing the branch. The request is for a larger more visible external sign to be installed. Note: Approved at RIF. Artwork approval received. Landlord approval obtained. BFM Engineering support. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Replace floor tiles with new non slip signature grey 600x600mm tiles (20m2) Prepare and paint ATM lobby ceiling white (20m2) Supply and install refurbished 7000x1800mm non illuminated external sign |  |  | Region 2 | Eastern Cape | 78937X | 1000-71058-01 | Absa Mqanduli, Main Street, Mqanduli |  | 2022-10-31 | 2022-10-31 |  | ASP-EC0235 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-08-05 |  | 57699.37 |  | 100 | 2022-09-22 | 2022-09-22 | 57699.37 |  | {"MANDT":"111","REFERENCE":70000188,"ONEVIEW":"78937X","DATE01":"2022-08-22","DATE02":"2022-08-03","DATE03":"2022-09-13","DATE04":"2022-09-22","DATE05":"2022-09-24","DATE06":"2022-10-13","DATE07":"2022-11-12","DATE08":"2022-11-21","DATE09":"2022-12-15","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"131:-19:41:9:2:19:30:9:24:16","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-13","FORECAST_END":"2022-11-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgTm92IC0gUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":""} |  |  | C000061645 | PHASE11 | 2022-10-13 | 2022-11-12 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-01-16 | 10695.65 | 0 |  |  | C000039618 | 50173.36 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000189 | UPS ReplacementAbsa Greenacres branch ha | UPS ReplacementAbsa Greenacres branch has an Intelcab cabinet which was installed in September 2016 with a APC SRT 10kVA UPS. As per the service report the UPS has failed and requirement is for it to be replaced. In order to mitigate the risk a loan unit has been installed. The recommendation is to install an Eaton rack mounted UPS unit.Note: Funded from Engineering Retail Electrical using CIP for EOL UPS sites that were not done as per below: i.e. Budget Allocated from EOL UPS replacements that were Cancelled as Completed or no UPS on Site Engcobo, Malcomess Park, Port Alfred, Greenfields, Somerset East (R25 K Each) - R125k. Scope of works: Remove existing loan UPS Install new Eaton 9SX 1100i Power Module including Rail Kit & Network Card Install new Eaton Maintenance Bypass Panel Configuration and commissioning. |  |  | Region 2 | Eastern Cape | 77836X | 1000-71461-01 | Absa Greenacres Shopping Centre, 1 Ring Road, Port Elizabeth |  | 2022-09-30 | 2022-10-31 |  | ASP-EC0236 | CLSD BUDG AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-05 |  | 122518.37 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000033647 | CLOSED |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000190 | Additional Plug PointsThe Absa 106 York | Additional Plug PointsThe Absa 106 York Street George branch was revamped in 2015 and received minor works in 2021. The branch requested for additional plug points at teller 5, 6 and 7. At teller 5 the request is for a red plug point for the PC, tellers 6 and 7 require 2 additional plug points to accommodate both the new note counters and the ID buddy s.Note: Supported by BFM Eng via signed PRF Funded from previous underspend from Riversdale IK plugs ASP EC0186.Scope of works: Install 1 x dedicated plug (red) at teller 5 Install 4 x plugs at tellers 6 and 7 2 x white plugs 2 x Europlugs Install power trunking and cabling Connect to existing circuit Issue of Electrical COC on completion. |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street,George |  | 2022-09-08 | 2022-10-31 |  | ASP-EC0244 | CLSD BUDG AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-17 |  | 4500 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000033648 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000191 | Repairs to vandalised fence (19991231ct | Repairs to vandalised fence (19991231ctive)This request seeks 19991231ctive approval for the repairs to the vandalised fence at Absa Uniondale. The fence were vandalised on the premises whereby vagrants tramped and damaged it. Note: Work were done via INSOG as an Insurance claim. Ref WO no.409515547, Notification no. 303690617 and Supplier PO 4500750473 issued. Work completed on 29/07/2022.Scope of works: Removal of damaged fence Installation of new poles 2.1m 80 100mm = 15no 1.8m 100 120mm = 6no Erect new fence wire mesh 1.2m x 75mm x 50mm = 1no Wire steel L/V 2.0mm 50kg Wire Bind L/V 4.0mm 5kg No 8 Wire Bind L/V 2.5mm 5kg No 12 Wire Bind L/V 1.6mm 5kg No 16 |  |  | Region 2 | Eastern Cape | 78140X | 1000-71039-01 | Absa Uniondale,40 Voortrekker Street,Uniondale |  | 2022-09-15 | 2022-12-31 |  | ASP-EC0247 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-31 |  | 23592.25 |  | Approved | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000037145 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000192 | Installation of 2500L Water tank (CIP 20 | Installation of 2500L Water tank (CIP 2022)Eastern Cape is experiencing a water crisis and supply is intermittent. The landlord of Absa 51 Govan Mbeki is unable to supply grey water and as such, the branch does not have suitable storage facilities for grey water other than 1 x wheelie bin (200 litres). The landlord had 1 x water tank on the roof supplying the building, but over time the unit became inoperable and have since perished. The local municipality supply is very erratic and sometimes leaves the branch for days without running water. Recommendation has been received from Engineering to install a water tank in the basement to supply Absa with water. Note: Landlord approval for the installation and for the parking bay received. Recommendation for a 2500L water tank is based on the below ROD guidelines which determines the water tank size:16 people at the branch = 16ppl x 25ltr per person per day = 400 ltrThis ration at 5 days = 400ltr x 5 days = 2000ltrWith a safety factor of 10% = 2000ltr x 10% = 2200ltrScope of works: Supply and install 1x Eco Tank 2500 Litre Vertical, Biofilm lined, UV resistant Supply and install 1x Jetcom booster pump with pressure switch DAB 0.75kw Install steel cage for water pump. Install Big Blue 3 Stage filter system including replacement sediment filter Install 2.5m x 5m fence with 1m lockable pedestrian gate Electrical point with 20 amp breaker Electrical COC |  |  | Region 2 | Eastern Cape | 22165X | 1000-70940-01 | Absa 51 Govan Mbeki Ave Building, Port Elizabeth |  | 2022-10-10 | 2022-10-31 |  | ASP-EC0248 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-31 |  | 100000 |  | Approved | 2022-10-05 | 2022-10-05 | 0 |  |  |  |  | C000062053 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-18 | 434.78 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000193 | HVAC Layout DrawingsAbsa Jeffreys Bay HV | HVAC Layout DrawingsAbsa Jeffreys Bay HVAC installation was delayed as the coinciding Absa RBB PMO project was delayed in August due to Council issues with the required approvals. The Council has nothing on record for the building or branch of the previous builds. In order to proceed, the Council requires drawings of the existing layouts and the proposed layouts to be endorsed by an engineer as part of the submission. The scope of the HVAC project is to provide As Built HVAC drawings at the completion of the project of the new HVAC layout including the fresh air component that is being added.Note: The request is to supply the additional HVAC drawings of the current layouts which are to be endorse by engineer as required by the Council.Scope of works: Supply HVAC drawings of the existing layout with an engineers endorsement Submit a signed form by an engineer |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | Absa The Nautilus Building, Da Gama Road, Jeffreys Bay |  | 2022-10-10 | 2022-10-31 |  | ASP-EC0249 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-31 |  | 625 |  | Approved | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000037986 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000194 | Replacement of Brochure Holder InsertsTh | Replacement of Brochure Holder InsertsThe Vista brochure holder perspex inserts at Absa 106 York Street George are damaged and need to be replaced at the following locations: 1 x 1st floor at Business Bank; 2 x RIB on ground floor and 3 x client waiting area on ground floor at Customer Service and Consultants.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Approved by Bidvest Engineering and Absa Design. Scope of Work Remove and replace Perspex Pocket Holders in existing brochure holders.(x5) |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street, George |  | 2022-11-01 |  |  | ASP-EC0251 | CLSD BUDG AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-09-12 |  | 16853.25 |  | Approved | 2022-10-05 | 2022-10-05 | 0 |  |  |  |  | C000042170 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000195 | Replacement of Operating Hour decalAbsa | Replacement of Operating Hour decalAbsa Oudtshoorn was revamped/relocated in 2021. Their banking hours has since changed on Saturdays and the decal need to be replaced.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB approved cost, Design approved by Planner and Absa Design, Branch Manager and Engineering support received.Scope of Work Remove the existing decal and replace with new. |  |  | Region 2 | Eastern Cape | 37146X | 1000-70907-01 | Absa 48B High Street,Oudtshoorn |  | 2022-10-01 | 2022-10-28 |  | ASP-EC0252 | CLSD BUDG AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-09-12 |  | 583.33 |  | Approved | 2022-10-05 | 2022-10-05 | 0 |  |  |  |  | C000042167 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000196 | Connection of essential equipment UPS (C | Connection of essential equipment UPS (CIP 2022)Absa Despatch has a 20KVA UPS with a backup generator, the UPS has a current load of 14%. During a site audit, it was discovered that the 3x ATM s, 3x Tellers, 2x Customer Services and 6x Offices were not connected to the uninterrupted power supply (UPS). Not being connected to the UPS power supply causes extended interruptions during power outages. RBB has requested that the equipment is to be connected to eliminate down time during power interruptions. Note: The load calculated post the connection of the equipment would not exceed 35%. Scope of works: Connect 3x Tellers, 2x Customer Services, 6x Offices 3x ATM s on dedicated socket outlets onto existing UPS Issue of Electrical COC |  |  | Region 2 | Eastern Cape | 76549X | 1000-71459-01 | Absa Despatch-Main St-Despatch | N | 2022-12-01 | 2022-12-31 |  | ASP-EC0253 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-09-16 |  | 9481.63 |  | 100 | 2022-10-05 | 2022-10-05 | 9481.63 |  | {"MANDT":"111","REFERENCE":70000196,"ONEVIEW":"76549X","DATE01":"2022-09-22","DATE02":"2022-09-29","DATE03":"2022-10-20","DATE04":"2022-10-27","DATE05":"2022-10-06","DATE06":"2022-10-15","DATE07":"2023-02-09","DATE08":"2023-02-28","DATE09":"2023-03-31","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"220:7:21:7:-21:9:117:19:31:11","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-15","FORECAST_END":"2023-02-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjggRmViIC0gUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":""} |  |  | C000061964 | PHASE11 | 2022-10-15 | 2023-02-09 | RODERICK NEVAY | Juanita van Coller | 23000624 |  |  |  |  | 2023-01-17 | 8244.89 | 0 |  |  | C000042120 | 8244.89 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000197 | Absa Alexandria - Dilaps | Absa Alexandria - Dilaps - COC required |  |  | Region 2 | Eastern Cape | 76600X | 1000-71015-01 | Absa Alexandria | N | 2022-11-01 | 2022-12-01 |  | ASP-EC0254 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | CEASARS | 2022-09-16 |  | 18684.25 |  | 100 | 2022-09-19 | 2022-09-19 | 18684.25 |  | {"MANDT":"111","REFERENCE":70000197,"ONEVIEW":"76600X","DATE01":"2022-08-23","DATE02":"2022-08-30","DATE03":"2022-09-12","DATE04":"2022-09-19","DATE05":"2022-09-19","DATE06":"2022-11-11","DATE07":"2022-11-12","DATE08":"2022-12-02","DATE09":"2022-12-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"130:7:13:7:0:53:1:20:29:15","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-11","FORECAST_END":"2022-11-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MiBEZWMgRmluYWwgUE9DIFN1Ym1pdHRlZA==","RATING":""} |  |  | C000061641 | PHASE11 | 2022-11-11 | 2022-11-12 | RODERICK NEVAY | Juanita van Coller | 23000614 |  |  |  |  | 2023-01-16 | 16247.17 | 16247.17 |  |  | C000038744 | 956.52 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000198 | Replace HVAC Compressor (Item for Noting | Replace HVAC Compressor (Item for Noting)Absa George HVAC compressor servicing the first floor of the branch was damaged during load shedding due to a suspected power surge. The request is to replace the damaged HVAC compressor and to install surge protection. In addition, the replacement of damaged remotes for the VRV system.Note: Out of Cycle request supported by CRES Engineering on 27th Oct 2022. Scope of works: Supply and install 1x Mitsubishi R69 070 478 Compressor Supply 3x Wired remote controllers Supply and install 1x 3 phase surge arrester Electrical COC submission Disposal certificate to be issued on completion. |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street-York St-George | N | 2022-11-12 | 2022-11-12 |  | ASP-EC0261 | CLSD PCNF BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | CEASARS | 2022-10-26 |  | 68544.03 |  | 100 | 2022-10-27 | 2022-10-27 | 68544.03 |  | {"MANDT":"111","REFERENCE":70000198,"ONEVIEW":"79394X","DATE01":"2022-09-03","DATE02":"2022-09-10","DATE03":"2022-10-26","DATE04":"2022-10-27","DATE05":"2022-10-27","DATE06":"2022-11-08","DATE07":"2022-11-08","DATE08":"2023-02-15","DATE09":"2023-04-15","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"150:7:46:1:0:12:0:99:59:21","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-08","FORECAST_END":"2022-11-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgRmViIFBPQyBwYWNrIHN1Ym1pdHRlZCB0byBmaW5hbmNl","RATING":"Low"} |  |  | C000062483 | PHASE11 | 2022-11-08 | 2022-11-08 | RODERICK NEVAY | Juanita van Coller | 23000572 |  |  |  |  | 2023-01-19 | 59603.5 | 0 |  |  | C000045997 | 59603.5 | CIP2023XP | 6231.28 |  | 0 | 0 |  | 0 |  | 0
70000199 | Repairs to damaged walkway (19991231ctiv | Repairs to damaged walkway (19991231ctive Insurance)Absa Alexandria had an incident whereby a car accidentally drove into the walkway of the branch entrance. The rails and stairs were extensively damaged. The area was cordoned off to prevent potential OHS risks. Accidental damage was reported to Absa Africa Security and Absa Operations. Note: A Reactive Call was logged for remedial works which was completed on 29 September 2022. Reference WO no. 409664432, Notification no. 303730951 and PO no. 4500762269. INSOG insurance process followed. Scope of works:Work included replacement of tiles, flooring, rails, galvanizing and securing the area: Galvanised steelworks pre manufactured New signature Grey Matt Ecotec Hardbody anti slip tiles (50sqm) Rails |  |  | Region 2 | Eastern Cape | 76600X | 1000-71015-01 | Absa Alexandria,Cnr Voortrekker & Krog Streets,Alexandria |  | 2022-09-29 | 2022-09-29 |  | ASP-EC0263 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Freeho |  | CEASARS | 2022-10-28 |  | 1984.5 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000047955 | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000200 | Replacement of Internal Directory Signag | Replacement of Internal Directory Signage (Item for noting)This request seeks approval for the replacement of internal directional signage indicating the location of the Private Bank area. Absa Private Bank were consolidated into the Absa Regional Office space from the ground floor to the 2nd floor in Absa Moffett Office Park. The lift lobby signage was not updated indicating the location of the Private Bank on the 2nd floor and requires to be updated. This request is to update the signage in the 8 lift lobbies at Absa Moffett Office Park.Note: Supported by CRES VP and Artwork approval obtained. Planned completion date scheduled for 01/12/2022. Approved Out of Cycle on 18/11/2022.Scope of works: Remove existing Absa Signage Supply and install new vinyl decals to the 8 x directory boards in the lift lobbys from the Basement to the 3rd floor. (x8) |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2022-12-01 | 2022-12-31 |  | ASP-EC0265 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-11-17 |  | 3157.67 |  | 100 | 2022-11-18 | 2022-11-18 | 3157.67 |  | {"MANDT":"111","REFERENCE":70000200,"ONEVIEW":"22937X","DATE01":"2022-09-22","DATE02":"2022-09-29","DATE03":"2022-10-20","DATE04":"2022-10-27","DATE05":"2022-11-17","DATE06":"2022-12-05","DATE07":"2022-12-08","DATE08":"2022-12-30","DATE09":"2023-02-06","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"159:7:21:7:21:18:3:22:38:0","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-05","FORECAST_END":"2022-12-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000063104 | PHASE11 | 2022-12-08 | 2022-12-08 | RODERICK NEVAY | Juanita van Coller | 23000633 |  |  |  |  | 2023-01-23 | 2745.8 | 0 |  |  | C000063104 | 2745.8 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000201 | Gate Motor Replacement | Gate Motor Replacement |  |  | Region 2 | Eastern Cape |  | 1000-70855-01 | Building not in our database |  | 2023-01-15 | 2023-03-31 |  | ASP-EC0267 | REL BUDG AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-12-02 |  | 0 |  | Approved | 2022-12-19 | 2022-12-19 | 0 |  |  |  |  | C000066363 | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-02-02 | 11550.89 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000202 | Pretoria Campus Due Diligence - Waterproofing | Evaluation & specification for deteriorated roof waterproofing on Blocks A & C (Phase 1) Evaluation & specification for Block A windows and frames (Phase 1) Associated Engineering Professional Services and Bill of Quantities (Phase 1) Documentation and Procurement (Phase 1) Contract Administration and Inspection (Phase 2 - Construction phase) Site supervision and Final sign-off (Phase 2) |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2022-01-30 | 2022-05-31 |  | ASP-GN0111 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2021-10-28 |  | 23268.46 |  | 100 | 2021-11-18 | 2021-11-18 | 267587.33 |  | {"MANDT":"111","REFERENCE":70000202,"ONEVIEW":"22491X","DATE01":"2021-11-21","DATE02":"2021-11-28","DATE03":"2021-12-19","DATE04":"2021-12-26","DATE05":"2022-01-16","DATE06":"2022-04-15","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"495:7:21:7:21:89:380:21:45:5","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-04-15","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | 2913414 | PHASE11 | 2022-04-15 | 2023-04-30 | PRESHANE MUNTHREE | Obakeng Phuti | 23000512 | [5 empty] | 232684.63 | 0 |  |  | 2913414 | 232684.63 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000203 | 2nd floor-Closure | 2nd floor Closure |  |  | Region 1 | Gauteng South | 78531X | 1000-70416-01 | Absa Hillcrest Office Park |  | 2021-11-04 | 2022-03-31 |  | ASP-GN0113 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  | Leaseh |  | GAMIETR | 2021-11-04 |  | 26330.64 |  | Approved | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904656 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000204 | Variation Order for DRUPS (Diesel Rotary | Variation Order for DRUPS (Diesel Rotary UPS) Replacement of Rotor & Accumulator shaft of KS1A |  |  | Region 1 | Gauteng South | 36110X | 1000-70183-01 | Absa Samrand Data Centre |  | 2022-01-21 | 2022-02-28 |  | ASP-GN0122 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-24 |  | 7578.26 |  | Approved | 2022-01-25 | 2022-01-25 | 0 |  |  |  |  | 2900626 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000205 | Enclosed storage facilities for Branch o | Enclosed storage facilities for Branch on the Move Vehicles. (Ad Hoc Request) |  |  | Region 1 | Gauteng South | 22491X | 1000-70065-01 | Absa Pretoria Campus |  | 2022-01-21 | 2022-03-31 |  | ASP-GN0124 | CLSD ISBD AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-01-31 |  | 7979.81 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2902275 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000206 | Samrand Replacement of Fuel Control PLC (Program | Supply and Install: Ã¢ÂÂ¢ SIMATIC HMI, KTP400 Basic, Basic Panel, Key/touch operation, 4" Ã¢ÂÂ¢ SIMATIC S7-1200, CPU 1214C, compact CPU, DC/DC/relay Ã¢ÂÂ¢ SIMATIC S7-1200, analogue I/O SM 1234, 4 AI/2 AO, +/-10 V, 14-bit resolution or 0 (4)-20mA, 13-bit resolution Ã¢ÂÂ¢ SIMATIC S7-1200, Communication Board CB 1241, RS485, terminal block, supports Freeport |  |  | Region 1 | Gauteng North | 36110X | 1000-70183-01 | Samrand Data Centre-Waterloo Rd-Centurion | N | 2022-01-03 | 2022-08-31 |  | ASP-GN0125 | CLSD CNF BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-01-31 |  | 91767.85 |  | 100 | 2022-02-03 | 2022-02-03 | 91767.85 |  | {"MANDT":"111","REFERENCE":70000206,"ONEVIEW":"36110X","DATE01":"2021-10-25","DATE02":"2021-11-01","DATE03":"2021-11-22","DATE04":"2021-11-29","DATE05":"2021-12-20","DATE06":"2023-02-28","DATE07":"2023-02-28","DATE08":"2023-04-20","DATE09":"2023-05-05","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-28","FORECAST_END":"2023-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | 2902275 | PHASE11 | 2023-02-28 | 2023-02-28 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000549 | [5 empty] | 79798.13 | 0 |  |  | 2902275 | 79798.13 | CIP2023XP | 8342.53 |  | 0 | 0 |  | 0 |  | 0
70000207 | Replace Carpets throughout the branch an | Replace Carpets throughout the branch and install bumper rails in the consultants offices (CIP 2022).At Absa Lilian Ngoyi, the current carpet is over 5 years old and has deteriorated over time. This request seek approval to remove and replace carpet tiles in various affected areas which are at the teller, management, customer service, back of house office, treasury, bulk teller, financial advisor and sales consultants areas. In addition to the above, the office chairs are scratching the wall which was recently painted and it was therefore recommend to install bumper rails as a preventative measure.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Remove existing Carpet tiles Supply and install 500 x 500mm Belgotex hard graft shaded carpet tile (221m2) Supply and install 6x 1.5m bumper rails to consultants office. Security guard to be provided for the duration of project. Allowance made for enhance cleaning upon project completion Work will be conducted over 6 nights (after Hours), which includes 6 weekdays & 1 weekend. |  |  | Region 1 | Gauteng North | 22896X | 1000-70079-01 | Absa Lilian Ngoyi, 230 Lilian Ngoyi Street, Pretoria |  | 2022-01-29 | 2022-03-31 |  | ASP-GN0128 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-02-15 |  | 20446.98 | Approved | 100 | 2022-03-29 | 2023-10-07 | 20671.61 |  | {"MANDT":"111","REFERENCE":70000207,"ONEVIEW":"22896X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-01-29","DATE07":"2022-03-31","DATE08":"2022-04-21","DATE09":"2022-03-15","DATE10":"2022-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-29","FORECAST_END":"2022-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062005 | PHASE11 | 2022-07-15 | 2022-08-01 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-18 | 23772.35 | 0 |  |  | 2913429 | 204469.85 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000208 | Installation of a new power pole | Installation of a new power pole |  |  | Region 1 | Gauteng North | 78058X | 1000-70387-01 | Absa Rayton |  | 2022-02-15 | 2022-05-30 |  | ASP-GN0129 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-21 |  | 1106.36 |  | Approved | 2022-03-10 | 2022-03-10 | 0 |  |  |  |  | 2908622 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000209 | Floor tile replacement in Banking Hall & | Floor tile replacement in Banking Hall & ATM Lobby (CIP 2022)At Absa Kolonnade branch, there is a request to remove and replace the floor tiles in the banking hall and ATM lobby. The current floor tiles still reflect the old Absa image. The proposed refresh will enhance the branch s look and feel. Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets. Scope of Works: Removal of old tiles (250m2). Careful removal of q rails and re installation. Installation of new Absa spec tiles, 600 x 600mm Signature Grey Porcelain (250m2). Security Services for duration of project. Covid 19 deep cleaning required upon completion of the project. After hours work and full weekend work. |  |  | Region 1 | Gauteng North | 76649X | 1000-70303-01 | Absa Kolonnade, Shop U4-5, Kolonnade Centre, Zambezi Drive, Kolonnade Shopping Centre, Pretoria |  | 2021-01-29 | 2022-04-30 |  | ASP-GN0130 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-28 |  | 100000 | Approved |  | 2022-03-03 | 2023-10-07 | 2876 |  |  |  |  | C000062065 | PHASE11 | 2021-01-29 | 2022-04-30 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-18 | 2500.87 | 0 |  |  | 2907255 | 195259.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000210 | Installation of Walk off Mat (CIP 2022)A | Installation of Walk off Mat (CIP 2022)At Absa Olievenhoutbosch branch, there is no walk off mat at the entrance and this leads to the floor tiles getting dirty and muddy particularly during the rainy season. The request is for the installation of a walk off mat to ensure the floors are kept clean and tidy.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets. Scope of Works: Install matco trioscape grey walk off mat (2m x 1m). Lines to run horizontally to entrance of store. Covid wipe down. |  |  | Region 1 | Gauteng North |  |  | Building not in our database |  | 2021-01-29 |  |  | ASP-GN0131 | CRTD: |  | false | false |  |  |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-28 |  | 30000 |  | 100 | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2907254 | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000211 | Create access hatches in plastered ceili | Create access hatches in plastered ceilings (CIP 2022) This request seeks approval for the installation of access hatches/trap doors on plastered ceilings in various areas at Absa Pretoria Campus. This is to allow engineering access into the ceiling void for maintenance purposes.Note: Approved by CRES. Supported by Engineering.Scope of works: To install 7 x 600 x 600 mm access hatches / trap doors on plastered ceilings in the following areas:2 x 600 x 600 mm - Block C Third Floor Boardroom 3.022 x 600 x 600 mm Block C Second Floor Pause Area1 x 600 x 600 mm Block C First Floor Pause Area1 x 600 x 600 mm Block B Ground Floor Pause Area1 x 600 x 600 mm Block G Office Pause Area Work areas to be sectioned off as work will take place during operational hours Allowance for security for duration of the works On site cleaners to do wipe down on touch points on completion. Project duration 3 working days. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M, 270 Maggs Street, Pretoria |  | 2022-01-29 | 2022-07-30 |  | ASP-GN0132 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Manuella Nyakudarika |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-22 |  | 100000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912394 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000212 | Supply of Benches and Printed Customer S | Supply of Benches and Printed Customer Services Numbers (CIP 2022) At Absa Hercules, there is a request to obtain benches for the branch and install printed customer service numbers. Currently the branch does not have enough seating for customers and require four waiting area benches. The customer service counters require printed numbering to be installed onto the existing frames to assist in directing customers to the correct counter. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works: Supply 4 x S13A Waiting Bench with Colour Inserts 2400mm(L) Supply and Install on existing frames 1 4 Customer Services numbers (Passion Red) - 1/ 2/ 3/ 4 Security Guard to be provided for duration of the project. Wipe down to be done on completion of project. |  |  | Region 1 | Gauteng North | 21228X | 1000-70018-01 | Absa Hercules, cnr Van der Hoff and Alter Street, Pretoria |  | 2021-01-29 | 2022-05-31 |  | ASP-GN0133 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 3086.43 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913261 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000213 | Supply of benches (CIP 2022)At Absa Pick | Supply of benches (CIP 2022)At Absa Pick & Pay Centre Soshanguve, there is a request to obtain benches for the branch. The branch currently does not have sufficient seating for their customers and would require x5 additional waiting area benches.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Benches as per RBB spec.Scope of Works: Supply:5 x S13A Waiting Bench with Colour Inserts 2400mm(L)6 8 week leadtime |  |  | Region 1 | Gauteng South | 22606X | 1000-70067-01 | Absa Pick & Pay Centre Soshanguve, |  | 2022-02-15 | 2022-05-31 |  | ASP-GN0134 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 3312.02 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913264 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000214 | Minor Works- Absa Monument Road (CIP 202 | Minor Works Absa Monument Road (CIP 2022)At Absa Monument Park branch, there is a request to do minor works in the branch. The walls in the branch have picked up marks over time and would need to be repainted. The branch also requested for protective plastic covering to be installed on the couches. Furthermore, additional benches for customer seating have been requested. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgetScope of Works: Prep and paint selected walls Grey: Toilet Lobby Area/ Pause Area/ Consultants Offices (x4)/ Storeroom/ Wall by front entrance close to enquiries desk - Approx. 275sqm Prep and paint walls Orange: Pause Area Wall against storeroom - Approx. 15sqm Prep and paint walls Purple (Currently walls are orange) - Wall by check in desk/ walls by tellers where TV is mounted front and back (x2)/ Wall in BA office - Approx. 34 sqm Prep and paint Grey and White - Tellers Desk (x3)/ Customers Services Desk (x4) - Approx. 14sqm Bolt shelves to wall in Storeroom 7 x Supply S13A Waiting Bench with Colour Inserts 2400mm (L) Install plastic (PVC) covering on:4 x large couches2 x medium couches2 x small couches2 x small backboard2 x large backboard Work will take place during normal working hours. Security Guard to be provided for duration of the project. Cleaner will assist with project activities. |  |  | Region 1 | Gauteng North | 77976X | 1000-70385-01 | Absa Monument Park, Shop 67, Monument Centre, Skilpad Avenue, Pretoria |  | 2022-01-29 | 2022-07-31 |  | ASP-GN0135 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 10776.03 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913265 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000215 | Cover existing 28 single seater chairs w | Cover existing 28 single seater chairs with PVC plasticDue to the ongoing Covid 19 pandemic and cleaning restrictions on fabric furniture, a request has been made to cover existing material with PVC plastic. This will allow for ease of cleaning and to add more seating for the clients by the consultants desks as they are currently making use of the pause area plastic chairs. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgetScope of Works: Collect the existing fabric furniture (X 28 single seated customer service chairs) Cover the furniture with PVC and return them to the branch. Lead time: 2 3 working days |  |  | Region 1 | Gauteng North | 77036X | 1000-70346-01 | Absa Hatfield, Shop 10, Hatfield Plaza, 1122 Burnett Street, Pretoria |  | 2022-01-29 | 2022-05-31 |  | ASP-GN0136 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 1820.04 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913263 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000216 | Cover 4 single couches with PVC & Insta | Cover 4 single couches with PVC & Install PVC bumper rails (CIP 2022)Due to the ongoing Covid 19 pandemic and the difficulty in cleaning and disinfecting fabric furniture, a request has been made to cover the existing fabric furniture in the banking hall with PVC. This will allow for ease of cleaning and make more seating available for clients as they wait to be served.In addition, the walls in the forex and customer areas requires bumper rails as the chairs and office equipment are damaging the walls. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works: Collect the existing fabric furniture (X2 single red bucket couches & X2 single yellow bucket couches) Cover the furniture with PVC and return them to the branch. Lead time: 2 3 working days Supply and install bumper rails with stopends in forex and customer areas. Make good walls where new bumper rails are being installed. Work will be completed in 1 day, Saturday after business hours. AFS confirmed additional security is not required. |  |  | Region 1 | Gauteng North | 76422X | 1000-70249-01 | Absa Brooklyn Main,Shop 305, Brooklyn Mall, cnr Fehrsen and Veale Street, Pretoria |  | 2022-01-29 | 2022-05-31 |  | ASP-GN0137 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 1308.25 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913262 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000217 | Insurance - Replacement of furniture and | Insurance Replacement of furniture and ceiling boards (Item for Noting)At Absa Lilian Ngoyi, the Branch experienced flooding last year in November due to water which was coming from a floor above. The cause of this was a Chiller plant pipe which had burst. The damage caused by this incident is a few ceiling tiles and some furniture which needs to be replaced.Note: Approved at RIF. This request was processed via INSOG Insurance. Scope of Works: Replace existing ceiling tiles ( x 40no) Supply Furniture: Back Office Workstation (1450mm) x 3 Table Leg x 6 Private Desk Pedestal only x 2 Cap 9 Unit 1800mm(h) White x 1 Semi Private Desk RHS x 1 Sales & Services Plinth x 1 Dual Lock Cabinet x 1 No allowance made for security, this project will occur simultaneously with a Carpet replacement project |  |  | Region 1 | Gauteng North | 22896X | 1000-70079-01 | Absa Lilian Ngoyi, 230 Lilian Ngoyi Street, Pretoria |  | 2022-02-15 | 2022-05-31 |  | ASP-GN0138 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-03-29 |  | 5715.71 | Approved | 100 | 2022-03-29 | 2023-10-07 | 65730.72 |  | {"MANDT":"111","REFERENCE":70000217,"ONEVIEW":"22896X","DATE01":"2021-12-07","DATE02":"2021-12-14","DATE03":"2022-01-04","DATE04":"2022-01-11","DATE05":"2022-02-01","DATE06":"2022-02-15","DATE07":"2022-05-31","DATE08":"2022-06-21","DATE09":"2022-04-01","DATE10":"2022-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-02-15","FORECAST_END":"2022-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061757 | PHASE11 | 2022-02-15 | 2022-05-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-17 | 75590.33 | 0 |  |  | 2913426 | 57157.15 |  | 3072.89 |  | 0 | 0 |  | 0 |  | 0
70000218 | Supply and install new 6 x High Teller C | Supply and install new 6 x High Teller Chairs (CIP 2022)The current chairs are damaged, and the wheels and back supports are worn out posing a potential OHS risk to the staff. The tellers have now resorted to rather standing. The long periods of standing is affecting their backs /health, and there is a risk of falling and injury if they continue using these chairs.Note: Approved at RIF . Supported by OHS. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Chairs as per RBB spec. No stock available in stores.Scope of Works: Supply and install new 6 x High Teller Chairs: Black Nylon Mercury Base & Castors Draughtsman s Height Adjustment Chrome Footing Syncho Mechanism Pivot with Lumbar support including Clear cover Slip On plastic for easy wipe down when cleaning. Seat: Vulcan Slate (No arms) |  |  | Region 1 | Gauteng North | 20955X | 1000-70006-01 | Absa The Grove, Shop L68-L69, The Grove Mall, cnr Simon Vermooten and Lynnwood Road, Pretoria |  | 2022-03-29 | 2022-05-31 |  | ASP-GN0139 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-30 |  | 3029.39 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913427 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000219 | Central City Construction of new office & boardroom | Construction of new office & boardroomThis request seeks approval to sub divide the existing boardroom in order to include the relationship banker s office at Absa Central City. A new drywall will be constructed to divide the spaces and a new door will be installed to access the boardroom, and the existing door will be repositioned for the relationship banker office. In addition, a new HVAC midwall split unit will be installed in the relationship banker s office with access control for the new office. Note : Approved at RIF.This project was prioritised by the region and spend will be allocated from the regional minor works budget. Supported by Absa Security and BFM Eng. Updated floor plan received. GMP Cost Impact included.Scope of Work Install drywall to create new office by separating the boardroom. Prep and paint grey with new matching Aluminium skirtings. Supply and install new glass doors to match existing to Boardroom as well as adjacent private office (replace wooden door). Install Relationship Banker Sign for new office & frost 2 new glass doors. Relocate existing aircon cassette unit into new boardroom and service with new return air grill. Supply and Install a wall mounted split AC unit new office with drainage pump and new return air grill. Supply and install isolator in ceiling for AC unit. Relocate plug point on wall to accommodate new door. Supply power points in new office, boardroom & furniture with COC. Relocate projector and projector screen into new boardroom. Prep and paint existing walls within grey and lux (match existing colours on walls) 20sqm. Install carpet tiles where required (match existing carpets) 5sqm. Security Guarding provided for the duration of project. Work to be done after hours for duration of 5 days. |  |  | Region 1 | Gauteng North | 76439X | 1000-70253-01 | Central City Shopping Centre-Central Rd-Mabopane | N | 2022-03-24 | 2023-02-28 |  | ASP-GN0140 | REL BUDG AVAC RESA SETC: |  | R | false |  | Njabulo Ngubane |  |  | 2022 |  | L |  | GAMIETR | 2022-04-01 |  | 14954.5 | Approved | 100 | 2022-09-22 | 2023-10-07 | 171976.85 |  | {"MANDT":"111","REFERENCE":70000219,"ONEVIEW":"76439X","DATE01":"2022-01-13","DATE02":"2022-01-20","DATE03":"2022-02-10","DATE04":"2022-02-17","DATE05":"2022-03-10","DATE06":"2022-12-01","DATE07":"2023-03-17","DATE08":"2023-03-17","DATE09":"2023-03-27","DATE10":"2023-03-31","DATE11":"2023-03-27","DATE12":"2023-03-27","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-01","FORECAST_END":"2023-03-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMi8yMDogRm9sbG93IHVwIGZvciBzaWduYXR1cmUgd2l0aCBMdWNpdXMu","RATING":""} |  |  | C000061686 | PHASE08 | 2022-12-01 | 2023-03-17 | PRESHANE MUNTHREE | Obakeng Phuti | 23000523 |  |  |  |  | 2023-01-17 | 171976.85 | 0 |  |  | C0039621 | 149545.09 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000220 | Dilaps | Dilaps |  |  | Region 1 | Gauteng North | 78793X | 1000-70436-01 | Nigel-Cnr Hendrik Verwoerd & 2nd Ave-Nigel |  | 2021-01-29 | 2022-06-30 |  | ASP-GN0141 | REL BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-05-11 |  | 2050.6 |  | 100 | 2022-05-12 | 2022-05-12 | 0 |  |  |  |  | C000059843 | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-09 | 17137.2 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000221 | Install upholstery on existing desk side | Install upholstery on existing desk side screens and collaborative high partitions (CIP 2022)This request seeks approval to re upholster the desk side screens and collaborative high partitions at Absa Pretoria Campus. The existing side screens and collaborative high partitions which were installed in 2018 are deteriorated and still in the old Barclays (Blue) colour. The request was made to reupholster the desk side screens and collaborative high partitions with the new approved Absa colours and specifications. Note: Awaiting CRES approval. Budgeted amount on CIP 2022 R1,5MScope of works: Remove existing blue fabric and cover with new approved Absa specified materials back to back. Supply & install new: 70 x desk side screens to be re upholstered with weavers world vulcan fire.(Block A,B,C & J) 16 x collaborative high partitions (back to back) to be re upholstered with weavers world vulcan fire, vulcan roux & vulcan captivate. (Block A & C pause area) All partitions will be removed, and work will be done off site with a x3 week lead time on materials. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus, Block A - M, 270 Maggs Street, Pretoria |  | 2022-01-29 | 2022-10-31 |  | ASP-GN0142 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-16 |  | 1565250 |  | Approved | 2022-05-18 | 2022-05-18 | 0 |  |  |  |  | C000059716 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-06 | 38521.59 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000222 | Supply and install new x4 (sets) of kitc | Supply and install new x4 (sets) of kitchen cupboards at Block A pause areas (CIP 2022)The kitchen units were installed in 2008, have deteriorated over time and require complete replacement. This work will improve the look and feel of these high traffic pause areas. The original request (as part of CIP 2022) was to redo all the kitchen cupboards in the various pause areas, however the scope was reduced to only install new kitchen cupboards at block A pause areas. Note: Awaiting CRES approval. Budgeted amount on CIP 2022 R1,5M.Scope of works: Remove X 4 (sets) old kitchen units as identified on site and cart away. Supply and install 4 (sets/ 2,1m) of new kitchen units in white melamine veneer with reused sink bowl. Fabrication of kitchen units will be done off site and installed on site on weekend. Work will be completed within a week. Onsite security will be utilised. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M, 270 Maggs Street, Pretoria |  | 2021-01-29 | 2022-08-31 |  | ASP-GN0143 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-16 |  | 1314750 | Approved | 100 | 2022-05-18 | 2023-10-07 | 170239 |  |  |  |  | C000061741 | PHASE11 | 2021-01-29 | 2022-08-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-17 | 170239 | 0 |  |  | C000014840 | 148033.91 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000223 | Supply and deliver teller and office cha | Supply and deliver teller and office chairs Absa Tshwane Market is a small branch which has not been revamped in the in recent years, the chairs in the branch are old, worn and not ergonomic friendly. The teller counters are high hence there is a need for high rise teller chairs to be provided.Note: Approved at RIF. Supported by OHS. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply, install and deliver the following : 5 X High rise Teller chairs with wheels with Clear Cover Slip On Plastic 3 X Office chairs with arm rests with Clear Cover Slip On Plastic |  |  | Region 1 | Gauteng North | 76514X | 1000-71384-01 | Absa Tshwane Fresh Market, Hall A, D F Malan Drive, Pretoria |  | 2022-05-27 | 2022-07-31 |  | ASP-GN0146 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-05-30 |  | 4016 | Approved | 100 | 2022-05-31 | 2023-10-07 | 46184 |  |  |  |  | C000060095 | PHASE11 | 2022-07-15 | 2022-08-15 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-09 | 46184 | 0 |  |  | C000021170 | 40160 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000224 | Provide 4 x Mobile Generators for MV Ser | Provide 4 x Mobile Generators for MV Service. Absa Pretoria Campus is a call centre consisting of x11 building blocks A M. The Campus has x4 substations with Medium Voltage (MV) equipment installed with an annual service due in May 2022. To ensure the Campus operates during the services, the 4 X mobile generators are required to provide power for the 2 (two) days of the scheduled service.Note: Approved by CRES, supported by BFM Eng. Project to be funded from the cancelled insulation film on windows @PTA. Budgeted Amount: R 499KScope of works: Delivery and collection of 4 x mobile generators Fuel Fill generators Supply cables and connect generator Test run generators as per MV Service Method Statement. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus, 270 Maggs Street, Pretoria |  | 2022-05-27 | 2022-12-15 |  | ASP-GN0147 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-30 |  | 18733.47 | Approved | 100 | 2022-05-25 | 2023-10-07 | 215434.93 |  |  |  |  | C000059708 | PHASE11 | 2022-05-27 | 2022-12-15 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-06 | 215434.93 | 0 |  |  | C000014894 | 187334.73 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000225 | Pretoria Campus Replacement of wool rugs to reception ar | Replacement of wool rugs to reception areas at Absa Pretoria Campus building A, B and C. (CIP 2022)This request seeks approval for the wool rugs in the reception area. The carpets have worn out over time and cannot be restored. This request is to replace the rugs with durable, easily cleanable rugs. The carpet tile and rug options were presented and a 80% wool /20% rug was slected. Note: Final patterns to be approved by Absa prior to manufacturing. No GMP Cost Impact.Scope of works: Supply, deliver and install 7 x reception rugs in block A, B and C. 3 X (2400mm x 3600mm) Rugs in Block A 1 X (3200mm x 1600mm) Rug in Block A North Reception Semi Circle 1 X (6000mm x 2000mm) Rug in Block B 2 X (3200mm x 1600mm) Rug in Block C Semi Circle Rugs to be delivered and layed during operational hours with no disruption to employees. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2022-06-23 | 2022-12-15 |  | ASP-GN0148 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | LOUISR | 2022-06-15 |  | 134732.71 | Approved | 100 | 2022-06-23 | 2023-10-07 | 154942.62 |  | {"MANDT":"111","REFERENCE":70000225,"ONEVIEW":"22491X","DATE01":"2022-04-14","DATE02":"2022-04-21","DATE03":"2022-05-12","DATE04":"2022-05-19","DATE05":"2022-06-09","DATE06":"2022-10-21","DATE07":"2022-10-28","DATE08":"2023-02-28","DATE09":"2023-04-14","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"261:7:21:7:21:134:7:123:45:5","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-21","FORECAST_END":"2022-10-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | c000021148 | PHASE11 | 2022-10-21 | 2022-10-28 | PRESHANE MUNTHREE | Obakeng Phuti | 23000525 |  |  |  |  | 2022-06-29 | 154942.62 | 0 |  |  | c000021148 | 134732.71 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000226 | Minor Works- Absa The Grove Mall (CIP 20 | Minor Works Absa The Grove Mall (CIP 2022)Absa The Grove has not had a refresh since 2016 and a request was made to upgrade the Banking Hall. The current tiles are the old spec which is mismatched, deteriorated and needs to be replaced with the new Absa tile specification. The queue rails need to be removed and replaced with benches in the area for client seating. Some walls, doors and frames need to be painted as it is in the old Absa Spec. The teller area walls have damaged due to the opening of safe doors, it needs to be repaired and heavy duty door stoppers need to be added to prevent future damage. Note: Approved by RIF, This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Remove existing old floor tiles including tile fix and replace with Absa new specification (400 sqm) Remove old Q rails and cart away (new). Prepare and paint banking hall walls, Teller area and back office walls (total 400 sqm) and 10 door frames including doors as per Absa spec brand colours Supply and install new bumper rails in the Banking Hall Supply and install 2 x heavy duty door stopper in the Teller area door Supply and install 10 x new benches (Absa spec) Baker street Onsite cleaning staff to be used when project is completed. Work will be completed in 12 days consecutive nights after hours which includes two weekends. |  |  | Region 1 | Gauteng North | 20955X | 1000-70006-01 | The Grove Mall-Cnr Simon Vermooten & Lynwood Rd-Pretoria |  | 2022-07-30 | 2022-09-30 |  | ASP-GN0149 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-06-24 |  | 15578.84 |  | 100 | 2022-07-21 | 2022-07-21 | 0 |  |  |  |  | C000060361 | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-10 | 155788.45 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000227 | Minor Works- Absa Mall of AfricaThe expa | Minor Works Absa Mall of AfricaThe expansion joints throughout the branch need to be replaced, the current condition has deteriorated over a period of time. This has affected the carpeting, floor, wall tiles throughout the front and backhouse of the branch. In addition, there is a request from the branch to install bumper rails in the customer service and consultants area, this is due to the employees chairs continuously damaging the walls.Note : Approved at RIF. Supported by ENG. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing timber floor tiles and replace with new 600 x 600mm signature Grey 198 SQM Remove carpets and replace with new 500 x 500mm Belgotex Hard Graft carpet 120 SQM Remove vinyl floor tiles and replace with new 300 x 300mm semi flex vinyl tile 30 SQM Remove wall tiles where expansion joints are identified and replace with white ceramic wall tiles 30 SQM Repair and replace expansion joints Prepare and level floor surface Install M Trim anodized 15mm high aluminium straight edge trim. Install in areas where different floor tiles meet Install 76mm Aluminium skirting in all areas vinyl flooring and carpet tiles is used. Allowance for 100mm skirting to match floor tiles Supply & install bumper rails X 3 Project Cleaning Services Material Leadtime 2 to 3 Weeks Work will be done during the week Mon Sun 8:00 to 17:00. The vendor may also have to work during evenings depending on the centre managements requirements, for work to be completed sooner the branch may have to close for the project duration of 7 days |  |  | Region 1 | Gauteng North | 36105X | 1000-70182-01 | Absa Mall of Africa, Shop 1043, Mall of Africa, cnr Magwa and Karkloof Crescent, Midrand |  | 2021-01-29 | 2022-10-30 |  | ASP-GN0150 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-06-24 |  | 50000 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000061214 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-13 | 38488.73 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000228 | Installation of PA System (CIP 2022)Duri | Installation of PA System (CIP 2022)During a planned evacuation in 2019, The campus hired a sound system, which allowed for audibility (Block A Assembly Point) during the evacuation. A concern however was raised, that should an unplanned evacuation take place, our current loudhailers will not be sufficient, to cater for the large crowds. It is not a legal requirement to have a PA System fitted on site, however all instructions must be auditable during an emergency hence the request from OHS install load hailers with a focus on the Emergency Assembly points. This is request is to install loud hailers to the external areas of the campus to ensure audibility at assembly points.Note: BFM OHS approval obtained. Scope of Work Supply, delivery and installation of a PA System to ensure audibility to external areas. Supply and install 20 x Loud Horns with focus to Assembly Point outside Block A, B and C. Supply Mixer AMPS. Supply Wireless Microphone handheld Supply 2 x handheld wireless microphones Provide drawing of placement of Loud Horns on campus Provide a security guard for duration of project. Work will take place during normal working hours on a weekends. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2022-01-29 | 2022-09-30 |  | ASP-GN0151 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-14 |  | 2005000 | Approved | 100 | 2022-07-21 | 2023-10-07 | 350523.37 |  |  |  |  | C000060356 | PHASE11 | 2022-08-27 | 2022-10-07 | PRESHANE MUNTHREE | Obakeng Phuti | 23000505 |  |  |  |  | 2023-01-10 | 47711.12 | 263315 |  |  | C000060356 | 41487.93 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000229 | Connect the existing | Connect the existing ATM to Emergency DB in the branch linked to LL GeneratorDue to frequent loadshedding in the area the branch is experiencing a loss in business due to existing ATMs not being operational during loadshedding, a request was made by business support to add the 2 x ATMs to the branch s already available emergency board on the LL generator to prevent loss of business.Absa Olievenhout Plaza doesnt have a stand alone back up generator and the landlord gave the branch 40% capacity (32A of 80A) of their generator power for the lights & two plugs. During the investigation it was found that the branch is currently using 3A of the 32A given by the landlord and the current load of the two ATMs that need to be linked to landlord generator is 5A.Note: Alternative Channels approval obtained to link remote ATM s. LL approval obtained. RBB approval obtained.Scope of works: Relocate the circuits feeding the ATMs and the server from normal power section to the emergency section of the distribution board in the branch. Issue COC on completion. Update legend card. Work to be done after the branch operational hours. Security to be provided for duration of works. |  |  | Region 1 | Gauteng North | 78319X | 1000-70195-01 | Olievenhoutbosch Plaza | N | 2022-07-29 | 2022-09-30 |  | ASP-GN0152 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-07-18 |  | 623.1 | Approved | 100 | 2022-07-21 | 2023-10-07 | 7165.73 |  | {"MANDT":"111","REFERENCE":70000229,"ONEVIEW":"78319X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-09-20","DATE07":"2022-09-20","DATE08":"2022-10-11","DATE09":"2022-11-25","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"315:7:21:7:21:67:0:21:45:5","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-20","FORECAST_END":"2022-09-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060427 | PHASE11 | 2022-09-20 | 2022-09-20 | PRESHANE MUNTHREE | Obakeng Phuti | 23000626 |  |  |  |  | 2023-01-10 | 8240.59 | 0 |  |  | C000060427 | 6231.08 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000230 | Repair cupboards on ground and first flo | Repair cupboards on ground and first floor kitchensAt Absa Quagga Centre, there is a request to repair the cupboards on the ground and first floor kitchens. The kitchen cupboards have deteriorated over time and require repair work to ensure there is a uniform look and feel in the kitchen.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Replace kickplates and services doors in both kitchens; Replace 1 shelve in cupboard under sink in ground floor kitchen; Replace 1 shelve in bottom cupboard in first floor kitchen; Replace the upright that cupboard door is fixed to under the sink in ground floor kitchen; Install edging on doors under sink in ground floor kitchen; Security Guarding Services to be provided for duration of the project Project cleaning on completion Work will take place during normal working hours on weekdays |  |  | Region 1 | Gauteng North | 77315X | 1000-71396-01 | Absa Quagga Centre, Shop 1, Quagga Centre, cnr Quagga Road and Court Street, Pretoria |  | 2022-07-29 | 2022-09-30 |  | ASP-GN0153 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-08 |  | 1389.14 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | C000031479 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000231 | Closure VO | Closure VO |  |  | Region 1 | Gauteng North | 36233X | 1000-70194-01 | Menlyn Maine Central Square-Cnr Aramist & Corobay Ave-Waterkloof Glen |  | 2022-07-29 | 2022-10-31 |  | ASP-GN0154 | REL BUDG AVAC SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-16 |  | 1710.58 |  | 100 | 2022-08-03 | 2022-08-03 | 0 |  |  |  |  | C000061040# | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-12 | 17105.81 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000232 | Supply 2 x large tube system capsule can | Supply 2 x large tube system capsule canistersAt Absa Hatfield the ATM Room is situated on the other side of the treasury room, and the branch utilises the tube system to transfer money to the ATM room. The current canisters are too small, and a request was made to supply two larger capsules canister for the ATM Custodian to transfer money efficiently alleviate any risk for the branch.Note: Supported by CRES VP. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply 2 x Large tube system capsule canisters. |  |  | Region 1 | Gauteng North | 77036X | 1000-70346-01 | Hatfield Mall-Burnett St-Hatfield | N | 2022-08-22 | 2022-10-31 |  | ASP-GN0155 | CLSD CNF BUDG AVAC RESA SETC: |  | R | false |  | Roegshana Gamiet |  |  | 2022 |  | L |  | GAMIETR | 2022-08-22 |  | 5363.89 | Approved | 100 | 2022-08-25 | 2023-10-07 | 5363.88 |  | {"MANDT":"111","REFERENCE":70000232,"ONEVIEW":"77036X","DATE01":"2022-06-13","DATE02":"2022-06-20","DATE03":"2022-07-11","DATE04":"2022-07-18","DATE05":"2022-08-08","DATE06":"2022-09-01","DATE07":"2022-09-30","DATE08":"2022-10-21","DATE09":"2022-12-05","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"291:7:21:7:21:24:29:21:45:5","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-01","FORECAST_END":"2022-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061207 | PHASE11 | 2022-09-18 | 2022-10-10 | PRESHANE MUNTHREE | Obakeng Phuti | 23000629 |  |  |  |  | 2023-01-13 | 5363.88 | 0 |  |  | C000061207 | 4664.25 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000233 | Install space saver drop safe This reque | Install space saver drop safe This request is to install a space saver drop safe between Treasury and the ATM s at the Absa Thabo Sehume Branch. The walls in the branch are to be remedied to ensure a uniform look and feel after installation of the space saver drop safe.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Floor plans updated. Scope of Work Supply, deliver and install space saver drop safe (FPR24SS) Prep and paint all walls in the ATM room Treasury to match existing wall colours. Security Guarding Services to be provided for duration of the project Work will take place during normal working hours on weekends Lead time for safe is 6 8 weeks |  |  | Region 1 | Gauteng North | 70652X | 1000-71377-01 | Delta House-Pretorius St-Pretoria |  | 2022-08-22 | 2022-10-31 |  | ASP-GN0156 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-22 |  | 3486.06 | Approved | 100 | 2022-08-25 | 2023-10-07 | 40089.69 |  |  |  |  | C000061203 | PHASE11 | 2022-08-22 | 2022-10-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-13 | 53018.61 | 0 |  |  | C000061203 | 34860.61 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000234 | Camera inspection in the existing main s | Camera inspection in the existing main sewer line (CIP 2022)At Absa Pretoria Campus a request was made for the building of a new manhole in a 100 meter sewer pipe that always experiences sewer blockages especially in winter times and has escalated maintenance costs in this regard. This cost is for a camera inspection to be conducted and a recommendation report submitted to determine the best resolution to address this problem, and to relieve the pressure on the main sewer line.Note : Supported by BFM Eng. The allocated CIP budget for this project is R100k. Scope of Work Drain all manholes linked in the main line in prep for camera inspection. Conduct camera inspections in the main sewer line. Submit report Submit cost based on report findings. Work to be done during normal working hours and completed in two weeks. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2021-01-29 | 2022-10-31 |  | ASP-GN0157 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-29 |  | 100000 |  | 100 | 2022-09-01 | 2022-09-01 | 0 |  |  |  |  | C000061198 | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-13 | 12378.39 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000235 | Attlyn Branch Close off 2 X tellers with blinds. Absa | Close off 2 X tellers with blinds. Absa Atteridgeville branch receive complaints from customers due to open teller stations with no tellers during off peak operation times. This request is to install adjustable venetian aluminium blinds which can be opened and closed to suit daily operations. Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. As per Absa Design Base Line Specifications.Scope of Work Install blinds X 2 Teller Counters (Counter 5 and 6 ) 1460mm X 1100mm 50mm Venetian Aluminium blinds Works duration to be maximum 3 Hours to install. Works to take place on a weekend after branch operational hours (Closes at 11h00). Project Cleaning service to be done by branch cleaner. Security to be provided for duration of the installation. |  |  | Region 1 | Gauteng North | 78585X | 1000-70422-01 | Attlyn Shopping Centre-Cnr Phudufudu, Khoza & Umkhombe St-Atteridgeville | N | 2022-07-15 | 2022-10-31 |  | ASP-GN0158 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-08-29 |  | 776.68 | Approved | 100 | 2022-09-01 | 2023-10-07 | 8931.85 |  | {"MANDT":"111","REFERENCE":70000235,"ONEVIEW":"78585X","DATE01":"2022-05-06","DATE02":"2022-05-13","DATE03":"2022-06-03","DATE04":"2022-06-10","DATE05":"2022-07-01","DATE06":"2022-07-15","DATE07":"2022-10-31","DATE08":"2022-11-21","DATE09":"2022-08-29","DATE10":"2022-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-15","FORECAST_END":"2022-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061202 | PHASE11 | 2022-07-15 | 2022-10-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-13 | 8931.85 | 0 |  |  | C0035931-2 | 7766.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000236 | Install Push Bar EVAC doors (19991231cti | Install Push Bar EVAC doors (19991231ctive)During a walkabout with the LL Fire marshal it was noticed that the x2 evac doors are not compliant and a request was made to install thumb locks however, Africa Security recommended that push bars be installed. Due to both doors not being compliant the LL can t obtain his fire clearance certificate as a result of this Absa CRES requested that it should be done urgently to assist with LL compliance documentation. The existing x2 doors will be used and only push bars will be added to the front of house and back of house EVAC doorsNote : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Work was completed on 15 July 2022 via INSOG process. Scope of Work Supply and install emergency push bars (X2). |  |  | Region 1 | Gauteng North | 77976X | 1000-70385-01 | Monument Park Shopping Centre-Skilpad Rd-Pretoria |  | 2022-07-29 | 2022-10-31 |  | ASP-GN0159 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-09-05 |  | 1188.71 | Approved | 100 | 2022-09-08 | 2023-10-07 | 13670.25 |  |  |  |  | C000061321 | PHASE11 | 2022-07-20 | 2022-07-29 | PRESHANE MUNTHREE | Obakeng Phuti | 23000619 |  |  |  |  | 2023-01-13 | 13670.25 | 0 |  |  | C000061321 | 11887.18 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000237 | Close off of 4 x tellers countersAbsa Ke | Close off of 4 x tellers countersAbsa Key West retail branch has received complaints from customers due to open transparent teller stations with no tellers during off peak operation times. It has been agreed that all four retail teller counters be enclosed with a dry wall. Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Updated floor plan received. Supported by BFM Eng. Scope of Work Enclosure of four tellers with dry wall. Removal of TV screen and store. Changing of teller signage from tellers to teller. Security to be provided for duration of project Material Leadtime: + 1 week(s). Work to be done at night weekdays and will take 4 nights |  |  | Region 1 | Gauteng North | 22890X | 1000-70077-01 | Absa Key West, Shop 80, Key West Shopping Centre, cnr Paardekraal Drive (R28) and Viljoen Street, Krugersdorp |  | 2022-07-29 | 2022-10-31 |  | ASP-GN0160 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-09-19 |  | 2007.5 | Approved | 100 | 2022-09-22 | 2023-10-07 | 8130.5 |  | {"MANDT":"111","REFERENCE":70000237,"ONEVIEW":"22890X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-07-29","DATE07":"2022-10-31","DATE08":"2022-11-21","DATE09":"2022-09-12","DATE10":"2022-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-29","FORECAST_END":"2022-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061654 | PHASE11 | 2022-07-29 | 2022-10-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-16 | 8130.5 | 0 |  |  | C0039622 | 20075 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000238 | Supply 4 x queue rails and 2 x S29A benc | Supply 4 x queue rails and 2 x S29A benchesSince the Covid protocols have been lifted, there is an overflow of clients into the branch. Due to the lack of benches and queue rails, this negatively impacts the flow of services in the branch. There is a need for new 4 x queuing rails and 2 x waiting benches in the branch to manage the flow of clients within the branch and improve current operations. Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Work Supply, deliver and position Q Rails Black Gen VI Free standing.(x4) Supply, deliver and position of 2 x Bench A Purple Backrest and Red Seat (S29A) with 2 x Bench Connector Armrest. Allowance for security guarding service. 7 9 week lead time on benches. To be delivered and placed after operational hours |  |  | Region 1 | Gauteng North | 76680X | 1000-70310-01 | Northpark Mall Shopping Centre-Cnr Rachel De Beer & Burger St-Pretoria |  | 2022-07-15 | 2022-11-30 |  | ASP-GN0162 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-09-26 |  | 3130.51 | Approved | 100 | 2022-09-28 | 2023-10-07 | 36000.9 |  | {"MANDT":"111","REFERENCE":70000238,"ONEVIEW":"76680X","DATE01":"2022-05-06","DATE02":"2022-05-13","DATE03":"2022-06-03","DATE04":"2022-06-10","DATE05":"2022-07-01","DATE06":"2023-02-20","DATE07":"2023-03-30","DATE08":"2023-04-20","DATE09":"2023-06-04","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"178:7:21:7:21:234:38:21:45:28","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-20","FORECAST_END":"2023-03-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000061972 | PHASE11 | 2023-02-20 | 2023-03-30 | PRESHANE MUNTHREE | Obakeng Phuti | 23000594 |  |  |  |  | 2023-01-17 | 41401.04 | 0 |  |  | C0041191 | 31305.13 | CIP2023XP | 3145.54 |  | 0 | 0 |  | 0 |  | 0
70000239 | Replace and supply new frosting for the | Replace and supply new frosting for the branchA request has been made to replace the vinyl frosting on the following areas, revolving door and staff entrance door. The window panel above the entrance door and the one side of the shopfront currently have no frosting and require new frosting to be installed to match the existing. Supply new banking hour decal as well.Note : Approved at RIF. The supplier will use scaffolding to work at heights. Supported by OHS. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Replace frosting on the following areas revolving door and staff entrance door Supply new frosting on one side of shopfront and glass panel above entrance door Supply new banking hour decal. Supply and install new push, pull and safety pattern signage. Security guard for the duration of the works. Work will be carried out after normal working hours for two days. |  |  | Region 1 | Gauteng North | 21242X | 1000-70020-01 | Silverton-De Boulevard St-Pretoria |  | 2022-09-26 | 2022-11-30 |  | ASP-GN0163 | REL CNF BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-10-20 |  | 3129.78 | Approved | 100 | 2022-10-27 | 2023-10-07 | 35992.48 |  | {"MANDT":"111","REFERENCE":70000239,"ONEVIEW":"21242X","DATE01":"2022-07-18","DATE02":"2022-07-25","DATE03":"2022-08-15","DATE04":"2022-08-22","DATE05":"2022-09-12","DATE06":"2022-11-29","DATE07":"2022-11-29","DATE08":"2022-12-20","DATE09":"2023-02-03","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-29","FORECAST_END":"2022-11-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"VGVzdCBub3RlIDI3LTA5","RATING":""} |  |  | C000124774 | PHASE11 | 2022-11-29 | 2022-11-29 | PRESHANE MUNTHREE | Obakeng Phuti | 23000595 |  |  |  |  | 2023-11-20 | 5547.81 | 29733.46 |  |  | C000149509 | 1564.35 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000240 | Install a solid door with a view panelTh | Install a solid door with a view panelThis request seeks approval to install a solid door with a view panel between customer service and staff pause areas. The existing door does not have a view panel resulting in the staff members constantly bumping each other. This was raised as an OHS risk as it s not visible when someone is behind the door entering or exiting this area. Note: Supported by CRES VP. Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. BFM Eng and OHS support obtained.Scope of works: Remove existing door (x1) Supply and install new solid with a view panel (x1) Replacing damaged lock. Supply and fit iron Installation will be done during normal working hours. Material Leadtime: + 10 12 days. |  |  | Region 1 | Gauteng North | 76677X | 1000-70308-01 | Wonderpark Shopping Centre-Cnr Heinrich Ave & Brits Rd-Pretoria |  | 2022-09-26 | 2022-12-31 |  | ASP-GN0164 | REL BUDG AVAC SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-10-20 |  | 0 |  | 100 | 2022-12-01 | 2022-12-01 | 0 |  |  |  |  | C000079641# | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-04-14 | 10518.7 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000241 | Minor Works - Absa The Grove MallThe las | Minor Works Absa The Grove MallThe last revamp at Absa The Grove was done in 2021, this was for the redesign of the shopfront area and did not include the upgrading of the banking hall. The current tiles are the old spec which is mismatched, deteriorated and needs to be replaced with the new Absa tile specification. The queue rails need to be removed and replaced with benches in the area for client seating. Some walls, doors and frames at the teller area and back office need to be painted as it is still reflecting the old Absa specifications. The teller area walls are deface due to the opening of safe doors and needs to be repaired and heavy duty door stoppers need to be installed to prevent future dents and scratches.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing old floor tiles including tile fix (300 sqm) Remove old Q rails and cart away Supply and install new (300 sqm)floor tiles as per Absa new specification Prepare and paint banking hall walls, Teller area and back office walls (total 400 sqm) and 10 door frames including doors as per Absa spec brand colours Supply and install new bumper rails in the Banking Hall Supply and install 2 x heavy duty door stopper in the Teller area door Supply and install 10 x new benches (Absa spec) Baker street Onsite cleaning staff to be used when project is completed. Work will be completed in 12 days consecutive nights after hours which includes two weekends. |  |  | Region 1 | Gauteng North | 20955X | 1000-70006-01 | The Grove Mall-Cnr Simon Vermooten & Lynwood Rd-Pretoria |  | 2022-07-07 | 2022-11-30 |  | ASP-GN0166 | CLSD BUDG ACPT RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-11-03 |  | 25198.56 | Approved | 100 | 2022-10-27 | 2023-10-07 | 289783.47 |  | {"MANDT":"111","REFERENCE":70000241,"ONEVIEW":"20955X","DATE01":"2022-04-28","DATE02":"2022-05-05","DATE03":"2022-05-26","DATE04":"2022-06-02","DATE05":"2022-06-23","DATE06":"2023-01-31","DATE07":"2023-02-17","DATE08":"2023-03-10","DATE09":"2023-04-24","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-31","FORECAST_END":"2023-02-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCB0byBiZSBwYXJ0aWFsbHkgaW52b2ljZSBmb3Igb25seSBiZW5jaGVzIHRoYXQgd2VyZSBkZWxpdmVyZWQgcHJvamVjdCB3YXMgcHV0IG9uIGhvbGQgdG8gYmUgZG9uZSB0aHJvdWdoIFBNTy4=","RATING":""} |  |  | C000062748 | PHASE11 | 2023-01-31 | 2023-02-17 | PRESHANE MUNTHREE | Obakeng Phuti | 23000511 |  |  |  |  | 2023-01-20 | 289783.47 | 0 |  |  | C0046536-2 | 251985.63 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000242 | Replace PC boards for condensor units ( | Replace PC boards for condensor units (19991231ctive Insurance) The VRV outdoor units in Absa Silverton have been vandalised for PC board theft, this was picked up when the branch discovered the unreliable air supply and inaccurate logs in the BMS. Contractor was dispatched to site for investigating the BMS error code and discover the root cause being the missing PC board. Note : Work was completed June 2022. INSOG insurance process followed : 303635714 W/O 409397809.Scope of works: Clean outdoor units coils and electronic compartments. (x2) Check all communication cables and refrigeration piping between indoor units and outdoor units. Replace all the PCB s on the slave outdoor unit. (x5) Execute the wiring and piping test on the system and monitor operation. Check power supply circuit breakers and isolators for hot connections. |  |  | Region 1 | Gauteng North |  |  | Building not in our database |  | 2022-10-31 |  |  | ASP-GN0167 | CRTD: |  | false | false |  |  |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-11 |  | 0 |  | 100 | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000063010 | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-01-20 | 76064.84 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000243 | Minor Works - Absa KolonnadeIt was reque | Minor Works Absa KolonnadeIt was requested that the treasury room be reconfigured to create additional space. This calls for shortening one of the room s walls and constructing a new meta wall to fit the new layout. The bulk teller and two of the current safes will also need to be removed and replaced with a worktop (existing chair to be re used). Affected existing walls, floors and ceilings will be made good. The cameras will be relocated in accordance with the Absa Security. Diffusers and fire sprinklers will be reconfigured by the landlord s suppliers in accordance to their recommendations and approved by BFM engineering.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Updated floorplan received. AFS support obtained. No impact to existing fire sprinklers, additional added. LL Fire Consultant confirmed no council submission required. ESM advised that there is no GMP cost for sprinkler heads. The system belongs to the landlord and is being serviced by LL. Scope of Work Remove bulker teller, reduce wall length and Install new meta wall. Make good all affected walls, floor finishes and ceilings. Install a new desk and re use existing chair. Reposition plug, supply and install electrical outlet to new desk. Supply and install two 600 x 600 LED Cool White lights as per specifications from Utilities Provide electrical COC. Install trunking for network cabling. Install two new diffusers and relocate one diffuser. Install two new sprinklers and replace one sprinkler. Repositioning of cameras as per Absa security. Remove 2 of 3 safes, move the 3rd safe and coin cage to a new position. Security guard to be provided for duration of works. Project cleaning to take place after project completion. Work will be carried out after normal hours for a duration of 10 days. (Material Leadtime: + 5 days.) |  |  | Region 1 | Gauteng North | 76649X | 1000-70303-01 | Kolonnade Shopping Centre-Sefako Makgatho Dr-Pretoria |  | 2022-11-15 | 2022-12-31 |  | ASP-GN0168 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-11-18 |  | 12297.61 | Approved | 100 | 2022-11-10 | 2023-10-07 | 141422.54 |  | {"MANDT":"111","REFERENCE":70000243,"ONEVIEW":"76649X","DATE01":"2022-09-06","DATE02":"2022-09-13","DATE03":"2022-10-04","DATE04":"2022-10-11","DATE05":"2022-11-01","DATE06":"2023-02-21","DATE07":"2023-02-24","DATE08":"2023-02-26","DATE09":"2023-05-06","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"236:7:21:7:21:112:3:2:69:1","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-21","FORECAST_END":"2023-02-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000063101 | PHASE11 | 2023-02-21 | 2023-02-24 | PRESHANE MUNTHREE | Obakeng Phuti | 23000527 |  |  |  |  | 2023-01-23 | 141422.54 | 0 |  |  | C000050832 | 122976.12 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000244 | Procurement of catering equipment for th | Procurement of catering equipment for the lite bite area (CIP 2022)This request seeks approval to procure catering equipment that is required for the restaurant at Absa Menlyn Maine. Due to the operational requirements, a request was made to procure an ice machine maker, hamilton beach blender with muffler and a small popcorn machine to cater for the needs of the employees. Note: Approved CRES VP. As per the agreement, there is a responsibility of 100% to be paid by Absa for the new services being offered. This project was supported in terms of allocation for 2022 and it is not part of the Capital project.Scope of works: Supply of catering equipment as listed below: Ice Make 28kg /24hr x 1 @ R23 085,00 excl.VAT Hamilton Beach Blender with Muffler x 1 @ R29 545,00 excl.VAT Small Popcorn Machine x 1 @R4 805,00 excl.VAT |  |  | Region 1 | Gauteng North | 36233X | 1000-70194-01 | Menlyn Maine Central Square-Cnr Aramist & Corobay Ave-Waterkloof Glen |  | 2022-11-20 | 2022-12-31 |  | ASP-GN0169 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-21 |  | 5743.5 |  | 100 | 2022-11-17 | 2022-11-17 | 0 |  |  |  |  | C000062516# | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-19 | 57435 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000245 | Installation of 250 new Alpha Logic desk | Installation of 250 new Alpha Logic desk plugs Phase 1A request was made to replace the Alpha desk plugs at various desk. The plugs have been vandalised and require to be replaced. Note: Supported by BFM Engineering. Supplier is closed and an order will only be made next after the issuing of the PO.Scope of Work Supply and deliver 250 Alpha logic desk plugs. Delivery will be conducted during normal working hours. Material lead time: 4 6 weeks. On site timeline: 1 Day. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2022-11-20 | 2023-01-31 |  | ASP-GN0172 | REL BUDG SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-21 |  | 30603.69 |  | 100 | 2022-11-24 | 2022-11-24 | 0 |  |  |  |  | C000053023 | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000246 | Irene Mall Installation of Man Trap | Installation of new single mantrap door A request has been made to replace the currently installed automated sliding door at the entrance of the branch. There is currently a primary project underway, however this request was not part of the original scope of work. The current door is malfunctioning due to load shedding and a high volume of clients are entering and exiting the branch. This is posing a security risk to the branch as the current door malfunctions and requires a technician in order for the door to be closed.Note: Approved at RIF. AFS and LL approval obtained. Updated floor plan obtained. This project was prioritised by the region and spend will be allocated from the regional minor works budget. The intention is to run this project in parallel with the current primary project running at the branch, however there is clarity required around the colour of the door. Supplier advised that the colour available is Texture Silver and it does not match existing shopfront and requires approval. If the colour is not approved by the landlord and respective party, there will be a delay leading to the project having to run next year in Q1 2023. Scope of works: Removal of existing door and carpet. Installation of new single mantrap door (x1) Levelling of floor surfaces. Tiling (5.4sqm) and painting affected areas. Installation of a new walk off mat. Final finishes around unit. Install 15Amp power points above equipment. COC to be issued on completion. Work will be carried during normal working hours for 5 days. Security guard for the duration of the works. Material Leadtime (ITAS door): 6 8 weeks. |  |  | Region 1 | Gauteng North | 21273X | 1000-70022-01 | Irene Mall-Cnr Nellmapius & Van Ryneveldt Rd-Centurion | N | 2022-10-26 | 2022-12-31 |  | ASP-GN0173 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-11-23 |  | 204979.59 | Approved | 100 | 2022-11-24 | 2023-10-07 | 215124.57 |  | {"MANDT":"111","REFERENCE":70000246,"ONEVIEW":"21273X","DATE01":"2022-08-17","DATE02":"2022-08-24","DATE03":"2022-09-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-12-03","DATE07":"2022-12-10","DATE08":"2022-12-31","DATE09":"2023-02-14","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"226:7:21:7:21:52:7:21:45:24","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-03","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000052675 | PHASE11 | 2022-12-03 | 2022-12-10 | PRESHANE MUNTHREE | Obakeng Phuti | 23000233 |  |  |  |  | 2023-02-07 | 215124.57 | 0 |  |  | C000062488 | 187064.84 | CIP2023XP | 18445.42 |  | 0 | 0 |  | 0 |  | 0
70000247 | Wonderpark Replacement of underground waste pipes | Replacement of underground waste pipesA request has been made for faulty male and female toilets that are next to each other to be repaired. When one toilet is flushed, waste runs in to the toilet next door. The current installation has a straight pipe running along each toilet in the wall, this pipe is on the same height as the toilets. each toilet outlet is jointed to this pipe with T junctions, and this is not a compliant way of installing the drains hence waste runs on the toilet next door when the other toilet is flushed. The toilet s pipework will need to be re done. This will entail removing the toilets pans, breaking the floor, running the main pipe at a lower level as the toilet, run new pipes from the toilet with elbows running down and then joining each toilet with a J junction to the new main pipe. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. LL approval obtained. BFM Engineering Support obtained. The branch has agreed to use the mall s toilets for the duration of works as the toilets will not be operational. Scope of works: Remove existing toilet pans. Digg and replace pipes. Install new toilet pans.(x3) Patch, retile and make good affected areas. Installation will be done after normal working hours for 4 nights. One security guard for the duration of the Installation. Material Leadtime: + 2 day. |  |  | Region 1 | Gauteng North | 76677X | 1000-70308-01 | Wonderpark Shopping Centre-Cnr Heinrich Ave & Brits Rd-Pretoria | N | 2022-11-23 | 2023-02-28 |  | ASP-GN0174 | CLSD BUDG ISBD AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-11-24 |  | 79299.15 | Approved | 100 | 2022-11-24 | 2023-10-07 | 79299.15 |  | {"MANDT":"111","REFERENCE":70000247,"ONEVIEW":"76677X","DATE01":"2022-09-14","DATE02":"2022-09-21","DATE03":"2022-10-12","DATE04":"2022-10-19","DATE05":"2022-11-09","DATE06":"2023-03-01","DATE07":"2023-03-05","DATE08":"2023-05-05","DATE09":"2023-05-15","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"198:7:21:7:21:112:4:61:10:0","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-01","FORECAST_END":"2023-03-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000066679 | PHASE11 | 2023-03-01 | 2023-03-05 | PRESHANE MUNTHREE | Obakeng Phuti | 23000561 |  |  |  |  | 2023-02-08 | 79299.15 | 0 |  |  | C000062484 | 68955.78 | CIP2023XP | 7061.74 |  | 0 | 0 |  | 0 |  | 0
70000248 | Replacement of Envirocabinet (UPS) Batte | Replacement of Envirocabinet (UPS) Batteries |  |  | Region 1 | Gauteng South | 78283X | 1000-70398-01 | Absa 105 East Rand Mall |  | 2022-01-12 | 2022-01-31 |  | ASP-GS0408 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-20 |  | 2284.81 |  | Approved | 2022-01-19 | 2022-01-19 | 0 |  |  |  |  | 2897124 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000249 | Waterproofing Professional Consultants | Waterproofing Professional Consultants Fees |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2020-06-30 | 2022-05-31 |  | ASP-GS0409 | REL BUDG AVAC RESA SETC: |  | R | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-01-21 |  | 316162.44 |  | 100 | 2021-11-18 | 2021-11-18 | 316162.44 |  |  |  |  | 2913402 | PHASE11 | 2022-05-15 | 2022-12-15 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000507 | [5 empty] | 274923.86 | 0 |  |  | 2913402 | 274923.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000250 | Removal of the UPS | Removal of the UPS |  |  | Region 1 | Gauteng South | 35028X | 1000-70082-01 | Absa Thabong |  | 2022-01-25 | 2022-02-28 |  | ASP-GS0410 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-25 |  | 321.4 |  | Approved | 2022-01-21 | 2022-01-21 | 0 |  |  |  |  | 2897635 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000251 | Supply and Install Wash Trough Basin (Ad | Supply and Install Wash Trough Basin (Ad Hoc Request) |  |  | Region 1 | Gauteng South | 21335X | 1000-71363-01 | Absa 270 Republic Road, 270 Republic Road, Randburg |  | 2022-01-21 | 2022-03-31 |  | ASP-GS0411 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-01-31 |  | 1916.01 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900627 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000252 | Replacement of leaking geyser (Item for | Replacement of leaking geyser (Item for noting) (Ad Hoc Request)This request is an item for noting for the replacement of the geyser. The geyser was leaking and needed to be replaced at Absa Meyerton branch. Due to the OHS risk the geyser was replaced through INSOG process. Note: Approved by CRES. Work completed on the 14 January 2022. The damaged geyser was disposed off via the FM disposal process.Scope of Works: Supply and fit 10 litre Prisma Geyser. |  |  | Region 1 | Gauteng South | 77636X | 1000-70376-01 | Absa Meyerton, 15C Loch Street,Meyerton |  | 2022-01-28 | 2022-03-31 |  | ASP-GS0412 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-31 |  | 408.76 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2902125 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000253 | Replacement of the Gate Motor (Item for | Replacement of the Gate Motor (Item for noting) (Ad Hoc Request) |  |  | Region 1 | Gauteng South | 76438X | 1000-70252-01 | Absa Central Avenue,16A Central Avenue, Kempton Park |  | 2022-01-28 | 2022-09-30 |  | ASP-GS0416 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-01-31 |  | 1080.3 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900614 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000254 | Installation of plugs points near fire e | Installation of plugs points near fire escape doors.(Ad Hoc Request) |  |  | Region 1 | Gauteng South | 37140X | 1000-71710-01 | Absa Gilloolys View |  | 2022-01-28 | 2022-02-28 |  | ASP-GS0417 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-31 |  | 756.28 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900613 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000255 | Re-upholster Equinox furniture (Ad Hoc R | Re upholster Equinox furniture (Ad Hoc Request) |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Absa Alice Lane North |  | 2022-02-03 | 2022-03-31 |  | ASP-GS0418 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 18115.03 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2902115 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000256 | Replacement of earth cables (2021 Accrua | Replacement of earth cables (2021 Accrual Item for Noting) |  |  | Region 1 | Gauteng South | 78946X | 1000-71416-01 | Absa Towers East, 170 Main Street, Johannesburg |  | 2022-02-03 | 2022-04-30 |  | ASP-GS0419 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-02-07 |  | 15050.74 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2902126 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000257 | Generator ReplacementThe water pump impe | Generator ReplacementThe water pump impeller on the existing generator disintegrated , and the fragments remain inside the water space within the engine block. Although a new water pump was installed the service provider is concerned that the impeller fragments may move into the new impeller causing further damage. Instruction was given by Absa CRES Engineering to keep the generator switched off to prevent further possible damage to the engine. This request is to replace the existing 200KVA generator with a new 80 KVA. Load analysis was conducted at the branch by BFM Engineering in consultation with Absa CRES Engineering and it was determined that an 80KVA will supply adequate power for the load. The existing 200KVA generator is to be decommissioned and transported to Diesel Electric storage pending Absa directive of reconditioning the unit. The existing infrastructure consisting of the bund wall, palisade fence and cables are to be reused.Note: CRES VP Supported. Supported by Engineering. RIF Approval obtained.Scope of works: Supply, delivery, installation & commissioning of a 400V, 80 KVA SDMO J88 John Deere generator set with 125A Automatic Transfer Switch. All the existing cables, bund wall and palisade fencing to be re used Factory Acceptance Test Provide a COC Generator fuel first fill Site Acceptance Test 6 (six) and 12 (Twelve ) month Service Level Agreement included. Work to be done over a weekend when the Branch closes on a Saturday and continue Sunday. Security officer not allowed for as the area where the generator is to be installed is considered safe and the gate keys must be obtained from Centre Management. There is a lead time is estimate 7 weeks post order |  |  | Region 1 | Gauteng South | 78551X | 1000-70418-01 | Greenstone Shopping Centre-Stoneridge Dr-Edenvale |  | 2022-02-09 | 2022-08-31 |  | ASP-GS0420 | REL CNF BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-02-09 |  | 40934.3 | Approved | 100 | 2022-07-07 | 2023-10-07 | 388905.7 |  | {"MANDT":"111","REFERENCE":70000257,"ONEVIEW":"78551X","DATE01":"2021-12-01","DATE02":"2021-12-08","DATE03":"2021-12-29","DATE04":"2022-01-05","DATE05":"2022-01-26","DATE06":"2022-09-14","DATE07":"2022-09-30","DATE08":"2022-10-21","DATE09":"2022-12-05","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"485:7:21:7:21:231:16:21:45:5","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-14","FORECAST_END":"2022-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060375 | PHASE09 | 2022-09-14 | 2022-12-22 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000503 |  |  |  |  | 2023-01-10 | 388905.7 | 0 |  |  | C000060375 | 409343.07 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000258 | Install Additional Power Points (CIP 202 | Install Additional Power Points (CIP 2022) |  |  | Region 1 | Gauteng South | 78451X | 1000-70406-01 | Absa 8 Top Road |  | 2021-01-29 | 2022-03-31 |  | ASP-GS0423 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-11 |  | 1875.79 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2902842 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000259 | Installation of dedicated and normal pow | Installation of dedicated and normal power for the ATM, workstation (CIP 2022)The branch has taken over the servicing of the ATM s and require a workstation with a printer and a telephone to be installed. A power source is required for the equipment to be operational. Note: Approved by CRES, Engineering support received.Scope of works:Installation of: 1 X red double plug, 1 X white double plug 1 X 4 X 4 blank plate Twin & earth cable with conduit Work to take approx. 6 hours Prep work to take place during operational hours and area will be sectioned off. Any power disruptions will be after the branch operational hours. Work to be done on a weekday. Security guard allowance made for 1 x Saturday shift Branch cleaner onsite to do covid wipe down. |  |  | Region 1 | Gauteng South | 79059X | 1000-70442-01 | Absa Maponya Mall, Maponya Mall, 2127 Chris Hani Road, Soweto |  | 2022-01-29 | 2022-08-31 |  | ASP-GS0424 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-11 |  | 526.53 |  | Approved | 2022-05-18 | 2022-05-18 | 0 |  |  |  |  | C000027367 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000260 | Closure | Closure |  |  | Region 1 | Gauteng South | 22346X | 1000-70055-01 | Absa Northgate |  | 2021-01-29 | 2022-03-31 |  | ASP-GS0430 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-25 |  | 10141.48 |  | Approved | 2022-02-25 | 2022-02-25 | 0 |  |  |  |  | 2904921 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000261 | Minor Works - Absa Alberton Branch (CIP | Minor Works Absa Alberton Branch (CIP 2022)At Absa Alberton branch, there is a request for minor works required to optimise the space in the teller area. It was therefore recommended to close off one section of the teller counters to create a more cohesive client experience and allow the streamlining of teller and customer services. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets, supported by BFM Eng. Scope of Works: Supply and install new dry wall partitions to enclose counters 11 to 20 2700mm high (44sqm) Supply and install new aluminium skirting 100mm high (16m) Supply paint and paint new dry wall (88sqm) Supply paint and paint ceiling down stand (24sqm) Supply and build new double brick wall to close CAD Area (5sqm) and plaster (10sqm) Supply and paint the double brick walls (58sqm) and supply and install new aluminium skirting 100mm (3m) Supply paint and paint doors x 2 doors Remove existing queue rails and uplift existing floor tiles (95sqm) Remove existing shop fitted alien walls (2 walls) Alien wall 1 space Supply and install new floor tiles (like for like) (95sqm) Alien wall 2 space Supply and install new floor tiles (like for like) (54sqm) Repair 2 bulkheads and supply paint (62 sqm) Electrical remove and make safe power points and provide COC (2 points) Remove existing help line cubicle x 1 and supply paint and paint Walls (17sqm) Remove existing formica cladding and supply and install new cladding (20m) Enhanced Cleaning Work to be conducted on 4 weekends after close of business . Security allowance made for the full duration of the weekend work. |  |  | Region 1 | Gauteng South | 79331X | 1000-70447-01 | Absa Alberton, 24 Voortrekker Street, Alberton |  | 2022-01-29 | 2022-03-31 |  | ASP-GS0431 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | GAMIETR | 2022-02-28 |  | 25425.82 | Approved | 100 | 2022-03-03 | 2023-10-07 | 20336.6 |  | {"MANDT":"111","REFERENCE":70000261,"ONEVIEW":"79331X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-01-29","DATE07":"2022-03-31","DATE08":"2022-04-21","DATE09":"2022-03-15","DATE10":"2022-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-29","FORECAST_END":"2022-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062063 | PHASE11 | 2022-01-29 | 2022-03-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-18 | 23387.09 | 0 |  |  | 2907253 | 254258.23 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000262 | Supply and install 2 X new IT Power Dist | Supply and install 2 X new IT Power Distribution Units (PDUs) (19991231ctive) |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North |  | 2022-06-01 | 2022-06-24 |  | ASP-GS0432 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | (Non PM) |  |  | 2022 |  | F |  | GAMIETR | 2022-02-28 |  | 2575.89 |  | 100 | 2022-03-17 | 2022-03-17 | 25758.98 |  | {"MANDT":"111","REFERENCE":70000262,"ONEVIEW":"77381X","DATE01":"2022-03-23","DATE02":"2022-03-30","DATE03":"2022-04-20","DATE04":"2022-04-27","DATE05":"2022-05-18","DATE06":"2022-06-01","DATE07":"2022-06-24","DATE08":"2022-07-15","DATE09":"2022-07-16","DATE10":"2022-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-01","FORECAST_END":"2022-06-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000061812 | PHASE11 | 2022-06-01 | 2022-06-24 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 25758.93 | 0 |  |  | C000014772 | 25758.93 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000263 | Install Automated Sliding Door | Install Automated Sliding Door |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North |  | 2021-01-29 | 2022-05-31 |  | ASP-GS0434 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-13 |  | 9797.05 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2911936 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000264 | Closure | Closure |  |  | Region 1 | Gauteng South | 36100X | 1000-70179-01 | Absa Verdi |  | 2021-01-29 | 2022-04-30 |  | ASP-GS0436 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-14 |  | 16082 |  | Approved | 2022-03-15 | 2022-03-15 | 0 |  |  |  |  | 2909263 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000265 | Tiling and painting of Equinox areaThe e | Tiling and painting of Equinox areaThe equinox area at Alice Lane has not received a refresh in over five years. This request seeks the approval to remove the existing peeling wallpaper, paint walls and doors according to specification provided. In addition, the wall behind the servery areas within the equinox space need to be tiled. Note : Approved by CRES. This project was supported in terms of allocation for 2022 and it is not part of Capital project.Scope of works: Remove wallpaper from walls 35m2. Remove wallpaper from doors no. 4. Prepare and paint walls with Dulux trade diamond eggshell, silver quill 35m2. Prepare and paint doors with Dulux trade diamond eggshell, silver quill no. 4. Supply and install 300 x 100mm Red Glass Metro tiles behind servery areas 14m2. Enhanced cleaning provided after work is completed. Security services provided for the duration of the project Lead time for the Red metro tiles: 5 10 working days Duration of work: 4 days. Work will be done during normal working hours for 4 days including weekend. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Absa Alice Lane North (Equinox), 15 Alice Lane, Sandton |  | 2021-01-29 | 2022-04-30 |  | ASP-GS0438 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-22 |  | 4423.6 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912388 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000266 | Minor Works - Absa NorthmeadThere is a r | Minor Works Absa NorthmeadThere is a request to do minor works at Absa Northmead branch. As part of the minor works, the carpets in the branch will be replaced with the new spec carpets excluding the teller area, painting of selected walls in the kitchen, storeroom and back office areas, except for the purple walls. A bumper rail will also be installed on the selected wall in the area between the server/ATM room and front of house offices). This improvement will enhance the look and feel of the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Replace carpets in branch with new spec carpets (130 m2; Carpet Spec Belgotex Accelerate Boost) Prep and paint selected walls in the branch as per existing orange and grey colours ( kitchen,storeroom walls & back office walls) ( 258 m2) Install 1 X PVC bumper rail on selected wall between the server/ATM room. Security to be provided for duration of project. Wipe down to be done on completion of project Supplier to work during normal working hours from Monday to Friday. Project duration is approximately x3 weeks. |  |  | Region 1 | Gauteng South | 36244X | 1000-70196-01 | Absa Northmead Square,Shop F10-14, Northmead Square, cnr O Reilly Merry Street and 14th Avenue, Northmead Square |  | 2022-01-29 | 2022-05-31 |  | ASP-GS0439 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 14898.32 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913268 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000267 | Install bumper rails in banking hall (CI | Install bumper rails in banking hall (CIP 2022)At Absa Eastrand Mall, the walls behind the teller area requires bumper rails. The chairs being used by the tellers are scratching the walls and it was therefore requested to install bumper rails to protect the walls. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Supply and Install PVC bumper rails. Make good walls where new bumper rails are being installed. Work will be completed in 1/2 day Saturday after business hours. Security Guard to be provided for duration of the project. |  |  | Region 1 | Gauteng South | 78283X | 1000-70398-01 | Absa 105 East Rand Mall, Shop 103 and 105, East Rand Mall, cnr Rietfontein (M21) and Bental Road, Boksburg |  | 2021-01-29 | 2022-05-31 |  | ASP-GS0440 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 20000 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913266 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000268 | Supply and installation of 3 x tilting p | Supply and installation of 3 x tilting pans (CIP 2022)This request seeks approval to procure catering equipment. At Absa Towers West,the current tilting pans in the upper ground kitchen are rusted and need to be repaired regularly. The recommendation was made to replace the x3 tilting pans with new items.Note : Approved by CRES.Scope of works: Supply and Install 3 x Tilting Pans (with tap and gas). Provide Gas COC Security guarding services for duration of project. Enhanced cleaning Services to be provided on completion of project. Work will take after working hours on weekdays and normal working hours on weekends. 24 Month warranty on tilting pans |  |  | Region 1 | Gauteng South | 77381X | 1000-70027-01 | Absa Towers West, 15 Troy Street, Johannesburg |  | 2022-03-29 | 2022-07-31 |  | ASP-GS0441 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-29 |  | 21734.32 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912387 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000269 | Installation of frosting on glass panels | Installation of frosting on glass panelsThis request is to install frosting at the unused entrance adjacent to the teller area. The entrance door and glass panels needs to be frosted for privacy purposes. Note: Approved at RIF and Absa Design. Supported by AFS. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Supply and install new frosted vinyl and safety patterns for glass panel on the left of the ITAS glass doors when standing from inside the branch Install new frosted vinyl with safety pattern and new banking hour decal on ITAS door that has the current banking hour decal. Security guard to be provided for the duration of project. Wipe down to be done on completion of project. Work will take place during normal working hours for 2 days. |  |  | Region 1 | Gauteng South | 35039X | 1000-70084-01 | Absa Campus Square, Shop F05, Campus Square, cnr Kingsway and University Street, Auckland Park |  | 2022-03-29 | 2022-05-31 |  | ASP-GS0442 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-30 |  | 1079.09 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913428 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000270 | 3 Phase Power installation for Shwarma M | 3 Phase Power installation for Shwarma Machine (Item for noting)A shwarma machine was moved from Alice Lane South and installed at Alice Lane North kitchen. The current location where the machine has been placed has no 3 phase plug and this request is to install a plug.Note: Supported by Engineering. To be funded from CIP 2022 cancelled project budget allocated to Towers West Cracks was R60k. Approved OOC on 31 March 2022.Scope of works: Install of 3 phase plug in the kitchen area (ground floor). Supply & install 6mm x 4 core norsk cable. Supply & install 6mm x2 core norsk terminations. Supply & install 40Amp T/PABB circuit breaker. COC to be provided on completion. |  |  | Region 1 | Gauteng South | 77656X | 1000-71397-01 | Absa Alice Lane North, 15 Alice Lane, Sandton |  | 2022-03-29 | 2022-04-01 |  | ASP-GS0443 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-31 |  | 634.64 |  | Approved | 2022-04-07 | 2022-04-07 | 0 |  |  |  |  | 2913799 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000271 | Fochville Waterproofing - Fochville (Ope | Fochville Waterproofing Fochville (Opex Budget) |  |  | Region 1 | Gauteng South | 77647X | 1000-71296-01 | Absa Fochville-Losberg Ave-Fochville |  | 2021-01-29 | 2022-07-29 |  | ASP-GS0444 | REL CNF BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-04-11 |  | 150000 |  | 100 | 2022-04-11 | 2022-04-11 | 11057.1 |  | {"MANDT":"111","REFERENCE":70000271,"ONEVIEW":"77647X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2022-09-30","DATE07":"2022-09-30","DATE08":"2022-10-21","DATE09":"2022-12-05","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"861:7:21:7:21:623:0:21:45:5","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-30","FORECAST_END":"2022-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000015879 | PHASE10 | 2022-09-30 | 2022-09-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000623 | [5 empty] | 9614.87 | 0 |  |  | C000015879 | 9614.87 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000272 | Canteen Deck Assessment Professional Fee | Canteen Deck Assessment Professional Fees (CIP 2022)The canteen deck at Absa Pretoria Campus Block E is currently 7 years old and has deteriorated over time. The floor panels are made of composite plastic which resembles wood, a number of these panels have weathered due to age and have weakened as a result. There is hollow void beneath these floor panels an assessment of the structure is requested to determine whether the deck can be repaired, or a full replacement is required. In addition, the timber structure beneath the floor panels needs to be assessed as well.Note : Approved by CRES. Scope of works: Assess the current deck at Block E , its timber structure , joints and floor panels on site. Provide a full report on the structural elements and recommendations. |  |  | Region 1 | Gauteng South | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2021-01-29 |  |  | ASP-GS0445 | CRTD BUDG AVAC: |  | false | false |  | << To be Determined >> |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-04-11 |  | 1497960 |  | 100 | 2022-04-13 | 2022-04-13 | 0 |  |  |  |  | QWARI | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000273 | Supply and Install 2 x Roller Shutter Do | Supply and Install 2 x Roller Shutter Doors (CIP 2022)This request seeks approval to replace two roller shutter doors by the Polly Street entrance. The roller shutter doors require replacement as they have deteriorated over time and there are times when the doors get stuck whilst opening and closing. New motors for these roller shutter doors will also need be installed. The height restriction poles at the entrance of the roller shutter doors will need to be refurbished. The chains holding up the height restriction poles will need to be replaced.Note: Approval obtained from AFS. Scope of Works: Remove existing 2 x roller shutter doors with motors Install 2 x new galvanized roller shutter doors with new motors (380v motor) Refurbish 4 x height restriction poles Replace chains for 4 x height restriction poles Security guarding services to be provided for duration of project COC to be provided on completion of installation. Store slats for one roller shutter door on site, and dispose of other old slats Roller shutter doors to be serviced 4 times per year. (Work to take place during normal working hours on weekdays) Work will take place on Weekends from 8am to 5pm. Project will take approximately 6 days to complete onsite. On site engineering team to provide storage space at the Absa Towers North Building for old motors and slats to be kept as attic stock Lead times 10 to 15 working days. Services for roller shutter doors: 4x times for the 1st year. |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North,180 Commissioner Street, Johannesburg CBD |  | 2022-01-29 | 2022-06-30 |  | ASP-GS0446 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-04-11 |  | 752700 |  | Approved | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000014906 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000274 | Replacement of a broken kitchen stove (C | Replacement of a broken kitchen stove (CIP 2022)The gas stove in the restaurant at 15 Alice Lane Campus has reached end of life and had over 8 years life span of service. Numerous calls were logged to repair the gas stove but is now beyond repair. This request seeks an approval to replace this gas stove. Note : Approved by CRES. Supported by Catering. Old stove will be disposed of by the supplier delivering the new one. Scope of works: Supply and install : Vision Char Broiler CG2 600X600X300 1 13,600.00 13,600.00 x 1No , Dimensions: 800 x 600 x 300mm High, Gas Consumption: 45000 KJ/HR. Gas COC to be provided. Costs to dispose of current stove is included. Covid wipe down to be done on all touch points on completion. In house security to be provided. |  |  | Region 1 | Gauteng South | 70656X | 1000-71371-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-04-11 | 2022-05-31 |  | ASP-GS0447 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-04-14 |  | 2972.44 | Approved | 100 | 2022-04-13 | 2023-10-07 | 30668.2 |  | {"MANDT":"111","REFERENCE":70000274,"ONEVIEW":"70656X","DATE01":"2022-01-31","DATE02":"2022-02-07","DATE03":"2022-02-28","DATE04":"2022-03-07","DATE05":"2022-03-28","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079211 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000596 |  |  |  |  | 2023-04-12 | 35268.43 | 0 |  |  | C000015399 | 29724.48 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000275 | Replace wallpaper in the boardrooms (CIP | Replace wallpaper in the boardrooms (CIP 2022)This request seeks approval to replace the wallpaper in three boardrooms at Clearwater Office Park. The wallpapers deteriorated over time and are peeling off the walls. The wallpaper requires to be stripped and replaced with new. Note : Approved by CRES. Wallpaper specification approved by Absa Design.Scope of Works: Changing the wallpaper in Boardrooms GO4 ,G10 and G105. To strip the existing wallpaper, repair and prepare wall for new installation. Print, cut and install new wallpaper as per Absa approved artwork. Size 4810 x 2580mm Inhouse security to be provided for duration of the project Inhouse cleaner to do touchpoints cleaning on completion of the installation. |  |  | Region 1 | Gauteng South | 77174X | 1000-70352-01 | Absa Clearwater Office Park, Cnr Christiaan de Wet Rd & Millennium Blvd, Roodepoort |  | 2021-01-29 | 2022-09-30 |  | ASP-GS0449 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-04-19 |  | 20000 |  | Approved | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000059721# | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-06 | 1755.55 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000276 | Supply wheelchairs to all branches (CIP | Supply wheelchairs to all branches (CIP 2022)There is a requirement from group OHS to provide wheelchairs to all branches. This request is to supply 86 wheelchairs to the various branches who do not have wheelchairs on site.Note : Approved by CRES. Scope of Works: Supply 86 X wheelchairs (Various Sites). Delivery included in the cost. |  |  | Special Projects | National | Various | 1000-70027-01 | National Various Sites (86 Branches) |  | 2022-04-19 | 2022-06-30 |  | ASP-GS0450 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Roegshana Gamiet |  |  | 2022 |  | Variou |  | GAMIETR | 2022-04-26 |  | 22016 |  | Approved | 2022-04-13 | 2022-04-13 | 0 |  |  |  |  | C000014887 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000277 | Dilaps | Dilaps |  |  | Region 1 | Gauteng South | 78793X | 1000-70436-01 | Absa Nigel |  | 2022-06-30 | 2022-12-15 |  | ASP-GS0451 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-05-13 |  | 3498.11 |  | Approved | 2022-05-13 | 2022-05-13 | 0 |  |  |  |  | C000018455 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000278 | Reupholstery of the benches in the lekgo | Reupholstery of the benches in the lekgotlas and the canteen (CIP 2022)The seating benches at the Absa Call Centre Auckland lekgotlas and canteen were last reupholstered over 8 years ago. The benches deteriorated over a period of time and are subject to wear and tear. The PU cover is torn and chipping off the frame and therefore requires to be stripped and reupholstered in the colours that match the existing. Note: Approved by CRES.Scope of works: Uplift and strip the seats in the lekgotlas and the canteen. Reupholster seats in weavers world ranger per colour offsite. Return reupholstered seats and install on frames. 5 Year guarantee on workmanship on seats. Seats to be collected and returned from site therefore no security and enhanced cleaning required. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-01-29 | 2022-07-31 |  | ASP-GS0452 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | GAMIETR | 2022-05-16 |  | 200000 | Approved | 100 | 2022-05-12 | 2023-10-07 | 115894.85 |  | {"MANDT":"111","REFERENCE":70000278,"ONEVIEW":"76849X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZS4=","RATING":"Low"} |  |  | C000090805 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000537 |  |  |  |  | 2023-06-09 | 176261.58 | 0 |  |  | C000014841 | 100778.13 | CIP2023XP | 8127.05 |  | 0 | 0 |  | 0 |  | 0
70000279 | Extension of existing exhaust (CIP 2022 | Extension of existing exhaust (CIP 2022)The request is to extend and bend away the existing exhaust from the office window area due to noise and smoke. Currently during power outages when the generator is in use, smoke and noise enters the adjacent office windows and this request seeks to address this issue. Note: Approved by CRES, Engineering support received.Scope of works: Extend generator exhaust as per assessment away from the position of the office windows. |  |  | Region 1 | Gauteng South | 77381X | 1000-70241-01 | Absa Carletonville, 69 Annan Road, Carletonville |  | 2021-01-29 | 2022-08-31 |  | ASP-GS0453 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2022-05-16 |  | 98380.2 |  | 100 | 2022-05-18 | 2022-05-18 | 29699.59 |  | {"MANDT":"111","REFERENCE":70000279,"ONEVIEW":"77381X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2021-01-29","DATE07":"2022-08-31","DATE08":"2022-09-21","DATE09":"2021-03-15","DATE10":"2021-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-01-29","FORECAST_END":"2022-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061728 | PHASE11 | 2021-01-29 | 2022-08-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 29669.59 | 0 |  |  | C000014835 | 29669.59 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000280 | Camera Inspection of Sewer Line/Drainage | Camera Inspection of Sewer Line/Drainage Pipes (CIP 2022)This request seeks approval for the preparation to conduct remedial work for the sewer line piping at Absa Towers North. A site walkabout were conducted with the Head of CRES Engineering and the Engineering Services Manager for an asessment. It was therefore recommended by Engineering that a camera inspection be conducted in selected sewer line/ drainage pipes, to determine the cause of the blockages.Note: Obtained CRES Approval. Scope of works: Camera inspections to be done in following areas: Pipes in kitchen canteen that runs to the Euromarket Pipes in recycling bay to basement 1 Pipes in lower ground guest bathrooms to basement 1 Provide report with findings Enhanced Cleaning to be done on completion Security Guarding Services to be provided for duration of project. Work will take place on weekends from 8am to 5pm |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North, 180 Commissioner Street, Johannesburg |  | 2022-01-29 | 2022-07-31 |  | ASP-GS0454 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-16 |  | 858.97 |  | Approved | 2022-05-18 | 2022-05-18 | 0 |  |  |  |  | C000014837 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000281 | Conversion of two offices into one offic | Conversion of two offices into one office (Busi)ness Cost Centre:9380This request seeks approval to combine two offices into one office on level 2 at Absa 268 Republic Road, Block B. Selected drywalls will be demolished, and new drywalls will be installed. The plug points on the current drywalls will be relocated to the existing power skirtings. New carpets will be installed in the office and the ceiling tiles which will be affected during project activities,will be replaced. In addition, a smoke detector will be removed as per recommendation from CRES Engineering that only one smoke detector is required in the office.Note: Supported by CRES VP and Engineering. Support received from Absa design. This cost to be allocated against cost centre: 9380.Scope of works: Demolish existing drywalls Install new drywalls Prep and paint new drywalls and repaint existing walls- match existing wall colours (approx. 111m2) Replace damaged ceiling tiles, and Ts - When removing drywalls existing ceiling tiles will be damaged. Install silver aluminium strip skirting to match existing skirting in office Replace old carpets with New Belgotex Absa "Custom X 001 Cirrus -Nimbus" Charcoal Grey 1m x 25cm, carpet spec (approx. 50m2) Plug sockets to be repositioned onto the existing power skirtings Reuse existing door Provide electrical COC Remove x1 smoke detector Relocate Data Cables to existing power skirting Enhanced Cleaning Services at the end of the project Security Guarding Services to be provided for duration of project Work will take place on weekends from 8am to 5pm |  |  | Region 1 | Gauteng South | 21334X | 1000-70026-01 | Absa 268 Republic RoadBlock A,B &CRandburg |  | 2022-05-11 | 2022-06-30 |  | ASP-GS0455 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-17 |  | 8290 |  | Approved | 2022-05-12 | 2022-05-12 | 0 |  |  |  |  | C000021167 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000282 | Furniture Request for CEO Office - x8 H | Furniture Request for CEO Office x8 High Back Chairs and x2 Trium Coffee Tables This request seeks approval to supply high back chairs and coffee tables for the CEO s office on the 8th floor. Note: Approved by CRES. Project to be funded from the deferred ATN Carpet project with a budget of R16.8M.Scope of works: Spectre Cocoon High Back Chair : 8 x (740W x 810D x 1130H), Fully Upholstered with headrest in weavers world opulence ( Colour To Be Specified), & Height adjustable polished aluminium swivel base. Trium Coffee Table : 2 x (1000O x 450H), 22mm Black Melamine Top with a matching impact edge, & metal frame DTM Colour Black |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West, 15 Troye Street, Johannesburg |  | 2022-05-19 | 2022-07-30 |  | ASP-GS0456 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-19 |  | 15508.8 |  | Approved | 2022-05-12 | 2022-05-12 | 0 |  |  |  |  | C000014830 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000283 | Kitchen Retiling :The kitchen area at Al | Kitchen Retiling :The kitchen area at Alice Lane North has not received a refresh since the inception of the building. This request seeks the approval to remove the existing deteriorated wall / floor tiles and replace with new approved tiles according to specification provided. In addition, the project shall require the existing catering equipment to be removed, stored and reinstalled upon completion of the tiling. Further, the building will require the hiring of casual employees to assist with catering which will ensure that food can be moved between the campus buildings during the refresh period. Note: CRES approval obtained.Scope of works: Removal of wall tiles and cartaway 65sqm Prepare surface, supply and install 300 x 600mm wall tiles (Spec: Apex white ceramic gloss finish LGAB07BLSP) 65sqm Remove floor tiles and cartaway 153sqm Apply Self Level Screed on Floors 153sqm Prepare surface on floors, supply and install 300x300mm floor tiles (Spec: Thar textured R11 silver LGAB05BLSP) 153sqm Hiring of Casual Employees for catering. Security to be provided for duration of project Covid 19 Deep Cleaning to be done on completion Material Leadtime 2 to 3 Weeks Work will be taking place during the evenings normal week days, weekends during the day and evening when necessary. Fire Fighting Equipment will remain in original positions vacinity to not affect fire rational design. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-05-19 | 2022-07-31 |  | ASP-GS0457 | REL CNF BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-05-23 |  | 21975.58 |  | 100 | 2022-05-25 | 2022-05-25 | 0 |  |  |  |  | C000124731 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-11-20 | 19912.59 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000284 | Waterproofing, Remedial Works & Replace | Waterproofing, Remedial Works & Replace Gutter Box 19991231ctiveAt Absa Meadowdale, there was a waterproofing project conducted in 2021, however the replacement of the gutter box was not part of the waterproofing project. The existing gutter box is worn out and not re routing rainwater to the drain and therefore required to be replaced with a new gutter box. Remedial work had to be conducted in conjuction with the replacement of the gutter box. Note: Approved by CRES, Work was completed as INSOG request on the 3 March 2022.Scope of works: Replace gutter box on the roof by reception area; Waterproof kitchen area admin building parapet walls; Repair leaks occurring above ceiling panels at ventilation grills; Repair leaks related to trunking/cables going through the wall; Replace vertical sheets on roof; Inspection of repairs and replacement; Serviced Smoke Ventilation system and replacing fusible links on the roof |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Absa Highlands Warehouse Meadowdale, |  | 2022-05-19 | 2022-12-15 |  | ASP-GS0458 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-23 |  | 18567.09 |  | Approved | 2022-05-25 | 2022-05-25 | 0 |  |  |  |  | C000014895 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000285 | Voltage Harmonic SurveyAt Absa Auckland | Voltage Harmonic SurveyAt Absa Auckland Park, the electronic systems (i.e. splits units pc boards, FCUs controllers, chiller pc boards and compressors) are currently failing. A power quality analysis survey had been done and indicated that the electronic systems failure is due to excessive voltage harmonics, which is fluctuations in voltage sine waves supplying the equipment. A voltage harmonic survey on the A supply panel and B supply panel in the LT room will be done to obtain readings for 1 week which will identify the harmonics causing the problem. Note: Approved by CRES. Project to be funded from the cancelled insulation film on windows @PTA. Budgeted Amount: R 499K.Scope of works: Conduct a Voltage Harmonic Survey for one week in the A and B supply panel in the LT room. Work will take place during normal working hours on weekdays. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Auckland Park Call Centre, 9 Lothbury Road, Auckland Park |  | 2022-05-19 | 2022-12-15 |  | ASP-GS0459 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-23 |  | 1332.1 |  | Approved | 2022-05-25 | 2022-05-25 | 0 |  |  |  |  | C000014893 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000286 | Installation of blinds (CIP 2022)At Abs | Installation of blinds (CIP 2022)At Absa Auckland Park, there is a request to replace the blinds on the Mezzanine and Ground level floors. The current blinds are old and have deteriorated over time due to exposure to sunlight and heat. Plain frosting will be installed on all small glass panels above fire evacuation doors. In addition, there is currently a drywall with blinds installed behind it on the ground floor which will be removed and a new drywall will be reinstalled with the new blinds. Note: Approved by CRES VP. Supported by BFM Engineering & OHS. Allocated budget R300 000,00. This project has been prioritised and will be funded from the CIP 2022 budget. Scope of works: Remove existing blinds on the Ground and Mezzanine Floors Install new spec blinds (50mm Venetian Aluminium Blinds) on Ground and Mezzanine Floors Install plain frosting on all small glass walls above fire evacuation doors on the Ground and Mezzanine Floors. Remove existing drywall and install new blinds on ground floor Install new drywall on Ground Floor after new blinds are installed. Prep and paint new drywall on Ground Floor Enhanced cleaning Services to be provided on completion of project. Security Guarding Services to be provided for duration of the project Work will take place on weekends Manufacture Lead time approximately 21 days |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Auckland Park Call Centre,9 Lothbury Road, Auckland Park |  | 2022-01-29 | 2022-07-31 |  | ASP-GS0460 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-29 |  | 300000 |  | Approved | 2022-05-31 | 2022-05-31 | 0 |  |  |  |  | C000019963 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000287 | Supply and install copper busbars - (Ret | Supply and install copper busbars (19991231ctive)Quadrum Office Park main incomer breaker had multiple power cables terminated into one terminal, due to this incorrect termination it was found that there was a hot spot and burnt cables on both the main incomer breaker and change over panel. It was recommended by the electrical supplier that new copper termination busbars be installed, redo the cable termination on the breaker and change over panel. Note: Approved by CRES. Work was done INSOG Request on the 13 March 2022. Project to be funded from the cancelled Pretoria Campus Install insulation film on windows project. Budgeted Amount R499k.Scope of works: Supply and install busbars on circuit breakers to reduce overheating on cable termination. |  |  | Region 1 | Gauteng South | 21332X | 1000-70025-01 | Absa Quadrum Office Park, Constantia Blvd, Roodepoort |  | 2022-03-01 | 2022-08-31 |  | ASP-GS0461 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-30 |  | 2895 |  | Approved | 2022-06-02 | 2022-06-02 | 0 |  |  |  |  | C000021190 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000288 | Supply and Installation of a new inverte | Supply and Installation of a new inverter airconditioning unitThe Aircon unit at Absa Highlands Warehouse was installed in 2013 and has been running for 9 years. The unit has a worn out bracket and bush which the manufacturer has confirmed are parts that cannot be supplied hence the unit is beyond repair. The R22 refrigerant gas used on the unit is in the process of being phased out because of its ozone depletion potential. There is need to install a new inverter unit that not only is environmentally friendly but also has energy serving technology.Note: Approved by CRES, supported by BFM Eng. The design has been optimised for environmental considerations and the equipment is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. Project to be funded from the cancelled Pretoria Campus Install insulation film on windows project. Budgeted Amount R499k.Scope of works: Decommissioning and removing of an old unit. Supply, deliver, installation and commissioning of a new Gree Ducted BTU inverter air conditioning unit. Issue COC. Work to take place during operational hours. Gas & Equipment Disposal certificates will be supplied. Cleaning touch points to be done by supplier. Security guarding service to be provided for the two day installation. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-05-27 | 2022-07-31 |  | ASP-GS0462 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-30 |  | 5790.77 |  | 100 | 2022-06-02 | 2022-06-02 | 0 |  |  |  |  | C000060090 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 57907.77 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000289 | Scanning for critical infrastructure - ( | Scanning for critical infrastructure (Item for noting)At Absa Republic Road, there is a water leak experienced by the guard house at the entrance of 270 Republic Road. An excavation will take place to repair the water leak. However, prior to the excavation taking place scanning on the ground level is required to ensure that there is no critical infrastructure where the excavation will take place.Note: Approved by CRES, supported by BFM Eng. Approved Out of Cycle by CRES ENG on 31 May 2022.Scope of works: Scanning on ground level by the guard house at 270 Republic Road. |  |  | Region 1 | Gauteng South | 21334X | 1000-70026-01 | Absa 268 Republic Road, 268 Republic Road, Randburg |  | 2022-05-27 |  |  | ASP-GS0463 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-30 |  | 1265 |  | Approved | 2022-06-02 | 2022-06-02 | 0 |  |  |  |  | C000014901 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000290 | LED Replacement - Phase 1 CanteenThe lig | LED Replacement Phase 1 CanteenThe lights at Absa Towers West, including the canteen area were installed in 2017 and are now discolouring (turning yellow) as it has reached its 5 year life span. The canteen has recently re opened and since employees are starting to come back into the building, this request for the canteen will be prioritised as phase 1 of the ATW LED replacement project and the entire building will form phase 2 of the LED project to follow. The canteen has 190 LED lights to be replaced with an approximate area of 250 sqm.Note: Approved by CRES and supported by BFM Energy. Project to be funded from the cancelled Auckland Park Call Centre & Ridgeside HVAC optimisation through Cryogen project. Budgeted amount is R925k.Scope of works: Supply and install 75 X LED Panel 36W 600X600 90 100LUM 50000H WXX430/3CCT Supply and install 15 X LED Panel 60W 600X1200 90 100LUM 50000H WXX460/3CCT Supply and install 100 X D/L 10W Non Dim 954LM 120D 4000K WHT TLQ105 Once off Covid Clean on completion of installation. Security guard to be provided for duration of project. Work to take place on weekdays and weekends after operational hours |  |  | Region 1 | Gauteng South | 21526X | 1000-71364-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-05-27 | 2022-12-15 |  | ASP-GS0465 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-05-30 |  | 32700.61 | Approved | 100 | 2022-05-25 | 2023-10-07 | 60313.06 |  |  |  |  | C000059703 | PHASE11 | 2022-06-28 | 2022-07-01 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000608 |  |  |  |  | 2023-01-06 | 60313.06 | 0 |  |  | C000014892 | 327006.14 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000291 | Removal of existing 200KVA Generator | Removal of existing 200KVA Generator |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2022-05-27 |  |  | ASP-GS0466 | CRTD: |  | false | false |  |  |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-05-31 |  | 0 |  | 100 | 2022-04-20 | 2022-04-20 | 0 |  |  |  |  | C000014836 | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000292 | Polish exterior granite wall tiles (CIP | Polish exterior granite wall tiles (CIP 2022)At Absa Towers North, there is a request to polish the exterior granite wall tiles around the building. Some of the granite wall tiles around the building are severely cracked and broken. These tiles are old and deteriorated over time and require polishing, and the cracked granite wall tiles will be filled with granite filler. The polishing of the granite tiles will enhance the look and feel off the building.Note: Approved by CRES VP. CRES OHS approval obtained.Scope of Work Clean exterior granite wall tiles (Approx. 1750sqm); Polish exterior granite wall tiles with buffering machine (Approx. 1750sqm); Apply filler on selected cracked granite wall tiles (Note. The tiles that are severely damaged will not be able to receive filler); Scaffolding to be installed onsite to conduct activities; Work will take place during normal working hours on weekdays Project Duration Approx. 25 days |  |  | Region 1 | Gauteng North | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2022-06-15 | 2022-12-15 |  | ASP-GS0467 | REL BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | LOUISR | 2022-06-06 |  | 26856.76 | Approved | 100 | 2022-09-28 | 2023-10-07 | 308852.76 |  | {"MANDT":"111","REFERENCE":70000292,"ONEVIEW":"77381X","DATE01":"2022-04-06","DATE02":"2022-04-13","DATE03":"2022-05-04","DATE04":"2022-05-11","DATE05":"2022-06-01","DATE06":"2022-06-15","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-15","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000041065 | PHASE10 | 2023-08-15 | 2023-10-18 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000508 | [5 empty] | 308852.76 | 0 |  |  | C000041065 | 268567.62 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000293 | Carpet Replacement and Painting Walls in | Carpet Replacement and Painting Walls in Entire Branch (CIP 2022)Absa Fochville branch was last refreshed in 2017, the carpets and paint has deteriorated over time. The front office was the only area refreshed at the time; the back of house was not included. This request is for the repainting the walls and replacement of carpets as the paint is peeling and the carpets are worn out in these areas. This is an operational requirement to enhance the look and feel of the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Lift existing Berber point carpet including adhesive (265m2). Supply and install new Belgotex Accelerate Solid Boost carpet tiles (291,5m2). Paint existing dry walling (Absa Grey, 588m2). Paint existing perimeter walls (Absa Grey, 345m2). Prestige to conduct once off Covid clean on completion. Security to be provided for the duration of the project for the work weekdays and weekends. Work to take place 12 weekdays and 2 weekends O8h00 to 17h00 shifts with front of housework done after branch operational hours. |  |  | Region 1 | Gauteng South | 77647X | 1000-71296-01 | Absa Fochville-Losberg Ave-Fochville |  | 2022-06-15 | 2022-12-15 |  | ASP-GS0468 | REL BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-06-06 |  | 28864.01 |  | 100 | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000060173# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 44965.14 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000294 | Close off Teller CountersAbsa Boksburg b | Close off Teller CountersAbsa Boksburg branch has requested for the installation of blinds at tellers that are currently unused due to operational reasons. This request shall assist the branch in closing and opening tellers depending on how busy the branch is.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply and fit new 50mm aluminium venetian Blinds at Teller 1,5,7 (3No) Enhanced Cleaning to be done on completion of project. Security Guard to be provided for duration of project Work will take place during normal working hours 2 weeks lead time on material and 1 day for installation |  |  | Region 1 | Gauteng South | 76384X | 1000-70238-01 | Absa Boksburg, cnr Burger and Commissioner Streets, Boksburg |  | 2022-06-15 | 2022-12-15 |  | ASP-GS0469 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-06-06 |  | 1427.46 |  | Approved | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000063013 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 3603.54 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000295 | Painting | Painting |  |  | Region 1 | Gauteng South | 37039X | 1000-70208-01 | Absa 190 Commissioner St-Commissioner St-Johannesburg |  | 2022-06-30 | 2022-12-15 |  | ASP-GS0470 | CRTD AVAC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | 0 |  | LOUISR | 2022-06-10 |  | 0 |  | 100 | 2022-06-10 | 2022-06-10 | 0 |  |  |  |  | C000018458 | IGNORE |  |  | PRESHANE MUNTHREE |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000296 | Remove blinds and install frosting (CIP | Remove blinds and install frosting (CIP 2022)At Absa Trade Route Mall, there is a request to remove the blinds and install frosting. The blinds in the branch are old and have deteriorated over time. These blinds will be removed and frosting will be installed.Note: Supported by CRES VP.Scope of works: Removal of blinds in the banking hall by shopfront which faces outside (by the office situated by the shopfront); Install frosting on windows where blinds had been removed; Enhanced cleaning; Provision of security guarding services Note: Work will take place during normal working hours on weekdays. |  |  | Region 1 | Gauteng South | 77216X | 1000-70356-01 | Absa Trade Route Mall, Cnr K43 & Nirvana dr, Lenasia |  | 2022-06-30 | 2022-12-15 |  | ASP-GS0471 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-06-13 |  | 50000 |  | Approved | 2022-06-15 | 2022-06-15 | 0 |  |  |  |  | C000023841 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000297 | Seal holes, flatten bolts and new tiles | Seal holes, flatten bolts and new tiles in the ATM area.The ATM at Absa Meyerton branch was removed and a request was made to seal the holes, flatten the bolts in the ground and install new floor tiles to to match the existing tiles.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing floor tiles. Grind the 8 no off bolts from the floor Seal holes with pavelite and make good Install 10 new floor tiles to cover the remediated area (Closest Match). Security will be provided duration of project. Work will be completed in one weekend, Saturday after the branch closes for trading. |  |  | Region 1 | Gauteng South | 77636X | 1000-70376-01 | Absa Meyerton-Loch St-Meyerton |  | 2022-06-30 | 2022-12-15 |  | ASP-GS0472 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | LOUISR | 2022-06-13 |  | 460 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000060660 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-11 | 4599.99 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000298 | Minor Works - Absa Birch Acres Mall (CIP | Minor Works Absa Birch Acres Mall (CIP 2022)Absa Birch Acres Mall has not received a major revamp since 2010. The carpets and tiles throughout the branch have deteriorated over time and a request was made to upgrade the tiling and carpeting with the new Absa specification. In addition, there is a request for benches to replace the existing que rail system in the banking hall. Further, the ATM que rail shall be repositioned to avoid congestion. Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing carpets and replace with new 500 x 500 Belgotex Hard graft shaded carpet tiles (139sqm) Remove existing tiles and replace with new 600 x 600 porcelain floor tiles (Signature grey matt) (139sqm) Remove existing vinyl floor and replace with new vinyl floorworx floorflex semi flexible vinyl floor tiles 300 x 300 (43sqm) Remove existing que rails and reposition (x1) Repair floors where necessary and apply self levelling screed (x1) Supply and install vinyl floorworx floorflex semi flexible vinyl floor tiles 300 x 300 (43sqm) Allow for aluminium edge trims where necessary (x1) Supply and Delivery of benches (x6) Project Cleaning Services Security Guard (14 Shifts) to be provided for duration of project.Material Leadtime: 2 3 weeks. Timeline: 14 Days Day or Night Depending on Centre Management. Branch will be required to close to ensure the project is completed on time |  |  | Region 1 | Gauteng North | 21330X | 1000-70024-01 | Birch Acres Mall-Cnr Andrew Mapheto Dr & Isimuku St-Tembisa | N | 2022-06-23 | 2022-09-15 |  | ASP-GS0473 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | LOUISR | 2022-06-13 |  | 26344.7 | Approved | 100 | 2022-08-04 | 2023-10-07 | 302964.11 |  | {"MANDT":"111","REFERENCE":70000298,"ONEVIEW":"21330X","DATE01":"2022-04-14","DATE02":"2022-04-21","DATE03":"2022-05-12","DATE04":"2022-05-19","DATE05":"2022-06-09","DATE06":"2023-01-02","DATE07":"2023-04-03","DATE08":"2023-07-31","DATE09":"2023-09-14","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"717:7:21:7:21:207:91:119:45:5","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-02","FORECAST_END":"2023-04-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZS4=","RATING":"Medium"} |  |  | C000060634 | PHASE09 | 2023-01-02 | 2023-04-03 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000509 |  |  |  |  | 2023-01-11 | 348408.73 | 0 |  |  | C000030624 | 263447.06 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000299 | Replace external branch | Replace external branch window decal with new Absa spec (CIP 2022)Due to extreme weather and sun reflecting on the windows most of the day, some of the decals are lifting up and further damage occurs by passers by. These decals were partially replaced is 2021 but damage has since recurred. Note : CRES VP Supported. Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Work Remove all existing external decals from windows (match existing decals). Supply and Install new Absa spec decal on the inside of the branch against the windows to minimise peeling off from direct sunlight. Work will be done during working hours and will be completed in 3 days and will not interfere with day to day operations of the branch. |  | l | Region 1 | Gauteng South | 77381X | 1000-76115-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2023-01-28 | 2023-02-08 |  | ASP-GS0474 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Athi Magqashela |  |  | 2022 |  | F |  | LOUISR | 2022-06-13 |  | 89540.29 | Cost Board | 100 | 2022-11-01 | 2022-11-01 | 89540.29 |  | {"MANDT":"111","REFERENCE":70000299,"ONEVIEW":"77381X","DATE01":"2022-04-14","DATE02":"2022-04-21","DATE03":"2022-05-12","DATE04":"2022-05-19","DATE05":"2022-06-09","DATE06":"2022-01-01","DATE07":"2022-12-07","DATE08":"2022-12-28","DATE09":"2022-12-13","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"351:7:21:7:21:-159:340:21:-15:44","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2022-12-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000072301 | PHASE11 | 2023-02-13 | 2023-02-28 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000554 | 2023-01-19 | 2023-02-06 |  |  | 2023-03-07 | 74742.02 | 0 |  |  | C000023840 | 77861.12 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000300 | Close off 4 X tellers with blinds.Absa T | Close off 4 X tellers with blinds.Absa The Boulders retail branch has received complaints from customers due to open transparent teller stations with no tellers during off peak operation times. This request is to install adjustable venetian aluminium blinds (Absa Design Base Line Spec) which can be opened and closed to suit daily operations. Note: Approved by RIF, This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Supply , deliver and install 1460mm X 1100mm 50mm Venetian Aluminium blinds 4 x Teller Counters (Counter 2,3,5,6) Works duration to be maximum 3 Hours to install. Works to take place during operational hours with noise kept at a minimal. Cleaning touch points to be arranged with branch cleaner. Security to be provided for duration of the installation. |  |  | Region 1 | Gauteng North | 36250X | 1000-70197-01 | Absa Midrand, Boulders Shopping Centre, cnr Old Pretoria Road and Alexandra Avenue, Midrand |  | 2022-06-23 | 2022-12-15 |  | ASP-GS0475 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-06-13 |  | 750.71 |  | Approved | 2022-06-30 | 2022-06-30 | 0 |  |  |  |  | C000022950 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000301 | Close off x8 teller counters with blinds | Close off x8 teller counters with blinds. (CIP 2022)The Absa Horison retail branch has received complaints from customers due to open transparent teller stations with no tellers during off peak operation times. This request is to install adjustable venetian aluminium blinds which can be opened and closed to suit daily operations.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply , deliver and install x8 1460mm X 1100mm 50mm Venetian Aluminum blinds 3 x Bulk Tellers 5x Teller Counters (Counter 2,3,4,5,6) Works duration is approximatley 3 Hours to install Works to take place on a weekend after branch opertional hours (Branch closes at 11h00). Cleaning touch points to be arranged with branch cleaner Security to be provided for duration of the installation. |  |  | Region 1 | Gauteng South | 76458X | 1000-71379-01 | Horison Park-Ontdekkers Rd-Roodepoort |  | 2022-06-23 | 2022-12-15 |  | ASP-GS0476 | CLSD CNF BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | LOUISR | 2022-06-13 |  | 1551.45 | Approved | 100 | 2022-06-23 | 2023-10-07 | 2411.73 |  |  |  |  | C000060108 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000635 |  |  |  |  | 2023-01-09 | 2411.73 | 0 |  |  | C000021150 | 15514.55 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000302 | Supply and install new internal and exte | Supply and install new internal and external building signage (CIP 2022)At Absa Bedford Centre, there is a request to install internal and external signage, there is no external building signage in entrance 1 of the mall and no internal signage in the sales consultant s offices. This request seeks approval to have both internal and external signage installed.Note : Approved at RIF and CRES VP. Supported by BFM ENG. This project was prioritised by the region and spend will be allocated from the regional minor works budget. LL approval obtained. Scope of Work Supply and install 1 x external building signage (Size 1400mm x 1000mm x 1 no off) including luminating electrical connections Supply and install internal signage (x 3 no entry, x 2 sales consultant, x 1 push/pull no entry decal set) Lead time on signage: 10 working days Allow for security guard Site to be left clean upon completion for external building signage. Work will be done in 2 week days during the day, and will not impact business operations, this has been arranged with the branch as well. |  |  | Region 1 | Gauteng South | 76582X | 1000-70292-01 | Bedford Centre-Cnr Smith & Van Der Linde Rd-Bedfordview |  | 2022-06-23 | 2022-12-15 |  | ASP-GS0477 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  | L |  | LOUISR | 2022-06-13 |  | 4685.2 | Approved | 100 | 2022-08-04 | 2023-10-07 | 53879.79 |  | {"MANDT":"111","REFERENCE":70000302,"ONEVIEW":"76582X","DATE01":"2022-04-14","DATE02":"2022-04-21","DATE03":"2022-05-12","DATE04":"2022-05-19","DATE05":"2022-06-09","DATE06":"2022-09-30","DATE07":"2022-10-30","DATE08":"2022-11-20","DATE09":"2023-01-04","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"320:7:21:7:21:113:30:21:45:9","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-30","FORECAST_END":"2022-10-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060657 | PHASE11 | 2022-09-30 | 2022-10-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000577 |  |  |  |  | 2023-01-11 | 46851.99 | 0 |  |  | C000030639 | 46852 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000303 | Comprehensive assessment of entire roofT | Comprehensive assessment of entire roofThe Absa Towers West glass roof was installed at the inception of the building in 2010. The installation was done by a company which has since closed down. Some glass roof panels in this area were replaced however further water leaks resurfaced. This request is to appoint an independent glass roof consultant to conduct a thorough conditional assessment of the glass roof and investigate the root cause of the current leaks. Note: Project to be funded from a portion of Auckland Park Lower ground slab flooring insulation budget amount (R7,9M)Scope of Work Conduct a thorough conditional assessment of the glass roof (Approx. 1260 sqm) Investigate the root cause of the current leaks Investigate and confirm the type of installed skylight, its lifespan and relation to NBR requirements Submit recommendations on above investigation including the following Variation in appearance of glazing Condensation Glass cracking Leaks Provide conclusions with these recommendations refrenced to applicable standards. |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West, 15 Troye street, Johannesburg |  | 2022-06-30 | 2022-12-15 |  | ASP-GS0479 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | LOUISR | 2022-06-14 |  | 7992.38 |  | Approved | 2022-06-30 | 2022-06-30 | 0 |  |  |  |  | C000060368 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-10 | 7265.8 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000304 | Installation of BlindsThis request seeks | Installation of BlindsThis request seeks approval for the installation of blinds at 15 Alice Lane South Campus in G.27 which is utilized by Absa CRO. This office is currently situated behind a smoking area and walkaway, and does not have privacy as employees have a full view into the office. The recommendation was made to replace aluminum blinds with blockout blinds. Note: Supported by CRES VP.Scope of works: Remove existing blinds. Install new blockout roller blinds 1105x3255mm (x1) Install new blockout roller blinds 1215x3255mm (x2) Install new blockout roller blinds 1215x3255mm (x1) Enhanced Cleaning Security to be provided by in house security. Material leadtime 2 3 weeks. Execution timeframe 1 Day (evening) |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2022-06-23 | 2022-12-15 |  | ASP-GS0480 | REL BUDG AVAC SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-06-14 |  | 1500.1 |  | 100 | 2022-06-15 | 2022-06-15 | 0 |  |  |  |  | C000060094# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 15000.99 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000305 | Dilaps | Dilaps |  |  | Region 1 | Gauteng North | NGA_54001 | 1000-64538-01 | Sinoville-- |  | 2022-07-29 | 2022-12-15 |  | ASP-GS0482 | REL BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-06-15 |  | 16138.46 |  | 100 | 2022-06-10 | 2022-06-10 | 0 |  |  |  |  | C000018582 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000306 | Temperature difference assessment (CIP | Temperature difference assessment (CIP 2022)The Auckland Park Call Centre lower ground floor slab was initially designed for car parking and was later converted into office space without enhancing the floor slab. There is a car parking area underneath the slab with open walls and diffusers which are situated on the ceiling, so when temperature increase, the employees feel cold underneath their feet and hot on their upper bodies. The recommendation was made to conduct an assessment and provide a suitable solution. Scope of WorkProvide Assessment Report with the following; Details of the methods used to investigate the temperature differences between the ground floor and ceiling throughout the office. Document all findings of investigation and to provide a permanent solution. Conclusions drawn from investigation. Recommendations - Provide BOQ/BOM for RFQ. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-06-22 | 2022-08-31 |  | ASP-GS0484 | REL BUDG AVAC SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | GAMIETR | 2022-06-22 |  | 7125.16 |  | 100 | 2022-06-15 | 2022-06-15 | 81939.37 |  | {"MANDT":"111","REFERENCE":70000306,"ONEVIEW":"76849X","DATE01":"2022-04-13","DATE02":"2022-04-20","DATE03":"2022-05-11","DATE04":"2022-05-18","DATE05":"2022-06-08","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000124732 | PHASE10 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000556 |  |  |  |  | 2023-11-20 | 71251.63 | 0 |  |  | C000021189 | 71251.64 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000307 | Minor Works -Absa Nicolway (CIP 2022)The | Minor Works Absa Nicolway (CIP 2022)The last major refurbishment at Absa Nicolway was in 2017, and since then the branch has not received an upgrade. The current state of the branch does not align with the new Absa RBB look and feel. This paper seeks approval to provide sales, customer service desks, create a branch managers office, remove existing wallpaper, paint the front and back of house and ensure the current HVAC system is altered to accommodate the new branch managers office. In addition, there has been a request to provide an online OMNI pod at the front of house.Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Supported by BFM Eng . Updated floor plan obtained.Scope of Work Paint walls BOH and FOH 190sqm Strip wallpaper on Managers Side 32sqm Skim wall where wallpaper is stripped to achieve a smooth finish 32sqm Supply and install Clip 44 shopfront and single height door in 8.38 Pvb/ns Glass and provide Glazing COC ( X1) Allowance to move directional signage and other signage Provide required furniture from Absa stores as per the design Supply and deliver rug for reception area (X1) Take onsite existing furniture to stores HVAC alteration Supply and installation of the new OMNI POD. Electrical requirements for power and network for all desks from stores, including the new OMNI POD, additional lighting with an electrical coc. Issue of a COC on completion. Security for the project duration 14 Days |  |  | Region 1 | Gauteng South | 36213X | 1000-70187-01 | Absa Nicolway - 2 Self-Service Outlet, Shop L48, Nicolway Bryanston, cnr William Nicol Drive and Wedgewood, Sandton |  | 2022-07-30 | 2022-09-30 |  | ASP-GS0486 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-06-22 |  | 25657.5 |  | Approved | 2022-07-27 | 2022-07-27 | 0 |  |  |  |  | C000028358 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000308 | Install Halo LED UnitsAt Absa Quadrum, t | Install Halo LED UnitsAt Absa Quadrum, there is a request to install two Halo LED Units in the supply duct of the 2 x 45 000 BTU hideaways of the second floor South wing. The Halo LED Units will produce a friendly oxidant when the air passes around the device and this friendly oxidant will eliminate bacterias, and viruses in the air. A lab test will be conducted prior to the installation, and another lab test will be done after the installation to determine the effectiveness of the Halo LED Units. Note : Project funded from deferred National corprate energy allowance. (R4,8M) Install Halo LED Units x 2 Conduct lab tests before and after installation; Provide report with findings Work will take place on weekends from 8am to 5pm |  |  | Region 1 | Gauteng South | 21332X | 1000-70025-01 | Quadrum Office Park-Constantia Blvd-Roodepoort |  | 2022-07-07 | 2022-08-31 |  | ASP-GS0487 | REL BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-06-22 |  | 4614.5 | Approved | 100 | 2022-06-30 | 2023-10-07 | 53066.74 |  | {"MANDT":"111","REFERENCE":70000308,"ONEVIEW":"21332X","DATE01":"2022-04-28","DATE02":"2022-05-05","DATE03":"2022-05-26","DATE04":"2022-06-02","DATE05":"2022-06-23","DATE06":"2022-07-30","DATE07":"2022-09-30","DATE08":"2022-10-21","DATE09":"2022-12-05","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"428:7:21:7:21:37:62:21:45:21","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-30","FORECAST_END":"2022-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060374 | PHASE11 | 2023-03-15 | 2023-04-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000578 |  |  |  |  | 2023-01-10 | 61026.75 | 0 |  |  | C000024800 | 46145 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000309 | Replace Unsteady Raised Flooring - Phase | Replace Unsteady Raised Flooring Phase 1 Professional Fees (CIP 2022)This request seeks approval to appoint a consultant to conduct an assessment on the current condition of the raised floors at Absa Towers North in the call centre. The raised floor has become unsteady due to the high volume of people using the third and fourth floor call centre. It was identified that the floor tiles had become bent at the corners of the tile which rests on the support structure. The bent corners of the floor tiles are believed to be the cause for the unsteady raised floors. A consultant will need to be appointed to investigate the raised flooring from floors 1 to 6.Scope of Work Investigate all raised flooring from floors 1 to 6 Provide report with pictures, findings, recommendations, and Bill of Quantities for the replacement of raised flooring Work will take place on weekends (8am to 5pm). Supplier will clean up during project activities if required. |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2021-01-29 | 2022-09-30 |  | ASP-GS0488 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-06-24 |  | 2506250 |  | 100 | 2022-07-27 | 2022-07-27 | 0 |  |  |  |  | C000060509 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-10 | 101606.18 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000310 | Replace CRAC Units - Professional Fees ( | Replace CRAC Units Professional Fees (Phase1) |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-06-30 | 2022-07-31 |  | ASP-GS0489 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-06-27 |  | 22952.36 |  | 100 | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000061146# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-13 | 229523.66 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000311 | Supply and install UPS power plugs (Retr | Supply and install UPS power plugs (19991231ctive)Room 5.15 in Absa Towers North is dedicated to being a Microsoft Teams meeting room. The MS Teams equipment that needs to be installed and must be connected to the UPS power. IT has requested for the supply and installation of UPS power in the ceiling void and floor void to power up the screens and equipment.Note : Supported by Engineering. Work was completed on the 19th March 2022.Scope of works: Supply and install 2.5mm surfix 3 core 45 50m meters Supply and Install UPS dedicated sockets with boxes Standard Supply and install connection consumables Supply and install M9F22103 Schneider Electric CB 1phase Wire reticulation within concealed ceiling from DB s to end points Power supply & ground earthing of new installation Supply service Electrical COC for new installation |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North, 180 Commissioner Street, Johannesburg |  | 2022-03-01 | 2022-08-31 |  | ASP-GS0490 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-06-29 |  | 1428.35 |  | Approved | 2022-04-07 | 2022-04-07 | 0 |  |  |  |  | C000022944 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000312 | Repair Artwork StandsThis request seeks | Repair Artwork StandsThis request seeks approval to repair the artwork stands at Absa Towers Main in the art gallery, which have deteriorated and require repair work. Aluminium flat strips and edging will be installed on all stands as a protective measure. The deteriorated surfaces of the stands will be repaired, made good and all holes will be filled.Note: CRES Approval obtained.Scope of Work Install aluminium flat strips on all painting stands/ frames (edges, top, and bottom). Install aluminium edging strips for handles on all painting stands/ frames. Repair damaged surfaces on all painting stands/ frames, prep and paint. Close holes (screw openings) on all painting stands/ frames, prep and paint. Onsite security and cleaning to be utilised. Work will take place during on normal working hours on week days and weekends. |  |  | Region 1 | Gauteng South | 78944X | 1000-71415-01 | Absa Towers Main, 160 Main Street, Johannesburg |  | 2022-07-29 | 2022-08-31 |  | ASP-GS0491 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-04 |  | 3255.45 |  | Approved | 2022-07-07 | 2022-07-07 | 0 |  |  |  |  | C000024790 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000313 | Water Leak Remedial Work (Item for notin | Water Leak Remedial Work (Item for noting)There is high water consumption experienced at the Absa 268 and 270 Republic Road building. Inspections had been conducted onsite, and it was found that there is a water leak on a pipe by the manhole at the guard house located near the gates. Scanning had taken place to confirm that no services are in the area where the repair work is required. The repair work will assist in reducing the high water consumption experienced at the building.Note : Approved by CRES, supported by BFM Eng. Approved Out of Cycle by CRES Engineering on 07/07/2022Scope of Work Excavate to expose the burst pipe next to the manhole by the main gate Supply pipes and fittings to repair the burst pipe Back fill and re build the manhole Re pave afterwards Work will take place during normal working hours on weekends During project activities there will be no water available for building users. Comms will be sent out to inform building users. |  |  | Region 1 | Gauteng South | 21335X | 1000-70026-01 | Absa 268 Republic Road, 268 Republic Road, Randburg |  | 2022-07-29 | 2022-08-31 |  | ASP-GS0492 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-08 |  | 4298.85 |  | Approved | 2022-07-14 | 2022-07-14 | 0 |  |  |  |  | C000023854 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000314 | Removal of UPS (19991231ctive) | Removal of UPS (19991231ctive) |  |  | Region 1 | Gauteng South | 22226X | 1000-71367-01 | Absa Chris Hani |  | 2022-03-01 | 2022-08-31 |  | ASP-GS0493 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-12 |  | 231.59 |  | Approved | 2022-07-11 | 2022-07-11 | 0 |  |  |  |  | C000024802 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000315 | Upgrade UG Cubicle Stainless steel balus | Upgrade UG Cubicle Stainless steel balustrade railingThe area with cubicles on the UG which was previously occupied by RBB Home loans must be changed for people to utilize and book through the condeco system. People are not booking and using gaps between the existing handrails to access these cubicles. This request is to install matching stainless steel balustrades within the gaps to control access. In this way using the designated entrance with a ticket will be enforced.Note: CRES VP approval obtained.Scope of Work Install 1 x 1200 X 1000 mm stainless steel balustrade rail to match existing 2 x 2300 X 1000 mm stainless steel balustrade supplied and fitted 1 x 2000 X 1000 mm stainless steel balustrade supplied and fitted 1 x 3000 X 1000 mm stainless steel balustrade supplied and fitted Install new LED light bulbs in existing light pendants to improve lighting in the booths Work will be done on one weekend Saturday & Sunday Electrical work to be done by in house by Bidvest engineering |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West, 15 Troye Street, Johannesburg |  | 2022-07-29 | 2022-09-30 |  | ASP-GS0494 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-14 |  | 4477 |  | Approved | 2022-07-21 | 2022-07-21 | 0 |  |  |  |  | C000027647 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000316 | Close off selected counters with blindsA | Close off selected counters with blindsAt Absa Florida Branch, there are seven counters which were identified and closed off for operational reasons. A request was made to close off these selected counters with blinds.Note: Approved by RIF, This project was prioritised by the region and spend will be allocated from the regional minor works.Scope of Work Supply and install new blinds 50mm Venetian Aluminium Blinds for the following counters: 2 x Bulk Counters 5 x Tellers Counters (Counters 1,3,5,7,8) Security Guarding Services to be provided for duration of project. Work will take place during normal working hours during weekdays Approx. 3 days |  |  | Region 1 | Gauteng South | 22379X | 1000-70060-01 | 20 Goldman Street Florida-Goldman St-Johannesburg |  | 2022-06-30 | 2022-09-30 |  | ASP-GS0495 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-15 |  | 1862.35 |  | 100 | 2022-07-21 | 2022-07-21 | 0 |  |  |  |  | C000060360 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-10 | 18623.5 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000317 | Supply and Installation of a new inverte | Supply and Installation of a new inverter airconditioning unit The Aircon unit at Absa Highlands Warehouse was installed in 2013 and has been running for 9 years. The unit has a worn out bracket and bush which the manufacturer has confirmed are parts that cannot be supplied hence the unit is beyond repair.The unit uses R22 refrigerant gas which is in the process of being phased out because of its ozone depletion potential. There is need to install a new inverter unit that not only is environmentally friendly but also has energy serving technology.Note: Supported by CRES.Scope of works: Decommissioning and removing of an old unit. Supply, deliver, installation and commissioning of a new inverter air conditioning unit. (AC160JNMDEH 60000BTU Hide Away Inverter Samsung ) Issue COC on completion. Work to take place after operational hours weekdays 17h00 18h00, Saturday from 13h00 and Sundays anytime. Cleaning touch points to be done by supplier. Security guarding service to be provided for the two day installation. Programme: Work will be completed over 7 consecutive days (normal hours). |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-06-20 | 2022-09-30 |  | ASP-GS0496 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-15 |  | 8272.46 | Approved | 100 | 2022-08-11 | 2023-10-07 | 95133.35 |  |  |  |  | C000060842 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000546 |  |  |  |  | 2023-01-12 | 95133.35 | 0 |  |  | C000031480 | 82724.66 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000318 | Walk-off mats at Absa Towers West, Tower | Walk off mats at Absa Towers West, Towers North and Alice Lane for Shoe cobbler and shine.Absa has a shoeshine and cobbler in each of their corporate buildings with walk off mats. This request is for the replacement of the existing walk off mats which have deteriorated and worn out over a period of time.Note: CRES VP approval obtained.Scope of Work Supply and install Teddy Colour 2,8 x 1,m walk off mats x 6 Once Off purchase (two per site). |  |  | Region 1 | Gauteng South | Various | 1000-70027-01 | Absa Various Sites (Absa Towers West, Towers North and Alice Lane) |  | 2022-07-29 | 2022-09-30 |  | ASP-GS0497 | CLSD CNF BUDG AVAC RESA SETC: |  | false | true |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-18 |  | 2872.4 | Approved | 100 | 2022-07-21 | 2023-10-07 | 33032.59 |  |  |  |  | C000060359 | PHASE11 | 2022-07-29 | 2022-09-30 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-10 | 33032.59 | 0 |  |  | C000027649 | 28724 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000319 | Remove two Midwall split unit and replac | Remove two Midwall split unit and replace with one new Midwall Split Unit in the ATM room The branch reported that the two 24 000 BTU Mid wall Split units were inoperative, it was affected by loadshedding. Service providers were requested to investigate the problem and have reported that the compressors, fan motors and PC Boards on the Daikin units were all defective. This request is to supply x1 new 24 000 BTU Mid wall split unit and make good the area. In addition, a surge protection device (QKL/QFL spec attached) to be installed on the unit.Note: Supported by BFM Engineering. The design is based on the existing, the equipment to be installed is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. GMP Cost Impact will be reduced.Scope of works: Decommission the aircon units in the Absa Alberton ATM Room. Remove and transport the aircon units off site, provide safe disposal certificate. Install new 1 x Samsung AR4500 Inverter 24 000BTU Mid Wall Split unit and test for operation. Drain Pump Power supply to the aircon unit ( Tap electrical connection from existing Distribution Board). Issue COC on completion. Allowance for R410 Refrigerant. 1 x QKL/QFL Surge Arresters. Replacement of unit therefore maintenance structure and costing are already captured. Make good the area (Patch and paint etc). Security Guard provided for the duration of the project. Work to be done after branch operational hours. |  |  | Region 1 | Gauteng South | 79331X | 1000-70447-01 | Absa Voortrekker Street Alberton-Voortrekker St-Alberton |  | 2022-07-18 | 2022-10-31 |  | ASP-GS0498 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-18 |  | 4093.43 | Approved | 100 | 2022-09-08 | 2023-10-07 | 47074.54 |  |  |  |  | C000061312 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000583 |  |  |  |  | 2023-01-13 | 47074.54 | 0 |  |  | C000037144 | 40934.39 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000320 | Install new screen with video conferenci | Install new screen with video conferencing At Absa Clearwater Office Park, there is a request to install a new screen with video conferencing. The walls for the new screen will also need to be reinforced to hold the weight of the new screen that will be installed. Note: Awaiting CRES Approval. Absa to log a call with IT Master for network cables/MS Teams post installation.Scope of Works Install new screen with video conferencing; Provide power and Issue COC; Reinforce dry wall where new screen will be installed; Security Guarding Services to be provided for duration of project |  |  | Region 1 | Gauteng South | 77174X | 1000-70352-01 | Absa Clearwater Office Park,Cnr Christiaan de Wet Rd & Millennium Blvd, Roodepoort |  | 2022-07-18 | 2022-10-31 |  | ASP-GS0499 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-18 |  | 12551.37 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000061199 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-13 | 15292.74 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000321 | Install 2 X glass writeable walls on the | Install 2 X glass writeable walls on the second floor at Alice Lane NorthThis request seeks approval to install 2x glass writable walls on the second floor at Alice Lane North. This room was originally a quiet room (SF29) and was later converted to an office space. This request is by the client to install writeable walls as its a requirement for BAU daily operations.Note: CRES VP approval obtained. Cost to be allocated against cost centre: SA600714.Scope of works: Install 1 x ( 790mm x 900mm ) new glass writeable board to the existing wall Install 1 x ( 480mm x 900mm ) new glass writeable board to the existing wall Security guarding service to be provided for duration of installation Work to take place after operational hours |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-07-29 | 2022-09-30 |  | ASP-GS0501 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-18 |  | 1081.94 | Approved | 100 | 2022-07-21 | 2023-10-07 | 12442.34 |  |  |  |  | C000060673 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Michael Maluleka | 23000621 |  |  |  |  | 2023-01-11 | 12442.34 | 0 |  |  | C000027650 | 10819.44 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000322 | Installation of Space Saver Safe (CIP 20 | Installation of Space Saver Safe (CIP 2022)At Absa Jorrisen Branch, there is a request to install a space saver safe between the ATM and Bulker Teller Rooms. The walls in the ATM and Bulk Teller rooms will also be painted to ensure a uniform look and feel after installation of the space saver safe.Note: RBB, Africa Security and Engineering supported this request. This project was prioritised by the region and spend will be allocated from the regional minor works. Updated floor plan obtained.Scope of Work Supply space saver safe Install space saver on wall as indicated on drawing Prep and paint all walls in the ATM room and Bulk Teller room (match existing wall colours) Move coin cage to the side wall. (out of the way - as indicated on drawing) Security Guarding Services Work will take place during normal working hours on weekends. Lead time for safe is 6 8 weeks |  |  | Region 1 | Gauteng South | 77563X | 1000-70375-01 | Absa Jorrisen Place,66 Jorrisen Place, cnr Bertha and Jorrisen Streets,Johannesburg |  | 2022-06-15 | 2022-08-31 |  | ASP-GS0502 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-18 |  | 5516.01 |  | Approved | 2022-07-14 | 2022-07-14 | 0 |  |  |  |  | C000026181 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000323 | Removal of dividing IBR wall (CIP 2022)T | Removal of dividing IBR wall (CIP 2022)This request seeks approval to expand the storage space at Absa Lea Glen Stores. The existing divider of the IBR wall between the two stores will be removed to expand the storage space. Note: Approved by CRES VP.Scope of Work Dismantle and remove existing 1 x IBR wall between two stores. Removed IBR Sheeting to be left on site. Make good walls where IBR sheet was removed Security to be provided for the duration of the project. Work to be done during operation hours with minimum disruption to stores. |  |  | Region 1 | Gauteng South | 76949X | 1000-70344-01 | Lea Glen-Amanda Ave Lea Glen-Florida | N | 2022-07-15 | 2022-08-31 |  | ASP-GS0503 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | L | 2025-01-30 | GAMIETR | 2022-07-18 |  | 3216.47 |  | 100 | 2022-07-14 | 2022-07-14 | 3216.47 |  | {"MANDT":"111","REFERENCE":70000323,"ONEVIEW":"76949X","DATE01":"2022-05-06","DATE02":"2022-05-13","DATE03":"2022-06-03","DATE04":"2022-06-10","DATE05":"2022-07-01","DATE06":"2022-07-15","DATE07":"2022-08-31","DATE08":"2022-09-21","DATE09":"2022-11-05","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-15","FORECAST_END":"2022-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000060425 | PHASE11 | 2022-07-15 | 2022-08-31 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000095 |  |  |  |  | 2023-01-10 | 2796.93 | 0 |  |  | C000026183 | 2796.94 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000324 | Dilaps | Dilaps |  |  | Region 1 | Gauteng South | 77470X | 1000-70369-01 | Vanderbijlpark-FW Beyers St-Vanderbijlpark |  | 2021-01-29 | 2022-08-31 |  | ASP-GS0504 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-07-19 |  | 5523.28 |  | 100 | 2022-07-19 | 2022-07-19 | 63517.79 |  | {"MANDT":"111","REFERENCE":70000324,"ONEVIEW":"77470X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000061817 | PHASE10 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000573 |  |  |  |  | 2023-01-17 | 55232.86 | 0 |  |  | C000026178 | 55232.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000325 | Installation of exterior window decalsTh | Installation of exterior window decalsThis request seeks approval to install exterior window decals from Wiesenhof restaurant up t o the main entrance at Absa Towers North. Due to extreme weather and sun reflecting on the windows some of the decals are lifting and deterioarated over a period of time. The recommendation was made to cover up the windows with an Absa branded decal as most of the space in the building is vacant. Note: Approved by CRES VP.Scope of Work Strip 30 sqm of existing vinyl clean and prepare for new Supply and Install 132 sqm of vinyl print cut and laminate on the glass window. |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2022-07-18 | 2022-08-31 |  | ASP-GS0505 | REL CNF BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-19 |  | 9571.95 |  | 100 | 2022-07-14 | 2022-07-14 | 0 |  |  |  |  | C000060346 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-10 | 2119.53 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000326 | Dilaps | Dilaps |  |  | Region 1 | Gauteng South | 77172X | 1000-70351-01 | Evaton Mall-Cnr Golden Highway & Easton Rd-Sebokeng |  | 2021-01-29 | 2022-08-31 |  | ASP-GS0506 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-07-20 |  | 288.55 |  | 100 | 2022-07-21 | 2022-07-21 | 3318.42 |  | {"MANDT":"111","REFERENCE":70000326,"ONEVIEW":"77172X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Medium"} |  |  | C000026790 | PHASE10 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000632 | [5 empty] | 2885.58 | 0 |  |  | C000026790 | 2885.58 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000327 | Replace banking hour decal The DHA has n | Replace banking hour decal The DHA has not been operational since the branch was revamped in 2020. This request is to replace the current DHA decal with a blank decal as it causes customer complaints due to the non operational service. Note: Approved by RIF and Absa Design. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Remove existing Trading hour decal. Application of new blank Decal. Security guarding service allowance for the duration of the project. |  |  | Region 1 | Gauteng South | 78551X | 1000-70418-01 | Absa Greenstone Mall, Shop L065, Greenstone Shopping Centre, cnr Blackrock Street and Stoneridge Drive, Modderfontein |  | 2022-07-29 | 2022-09-30 |  | ASP-GS0507 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-25 |  | 569.32 | Approved | 100 | 2022-07-27 | 2023-10-07 | 6547.21 |  |  |  |  | C000060623 | PHASE11 | 2022-07-29 | 2022-09-30 | PRESHANE MUNTHREE | Buhle Qwabe | 23000627 |  |  |  |  | 2023-01-11 | 6547.21 | 0 |  |  | C000028397 | 5693.24 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000328 | Replacement diffusers and wall controlle | Replacement diffusers and wall controllers in the Forex area (19991231ctive)Absa Cresta Mall was revamped in July 2021 and the Forex department aircon at the back office was designed to share aircon settings with the front office, which affects the back office when temperatures at the front office is set. This type of aircon diffuser is a constant volume diffuser instead of a variable volume diffuser that has a capability to auto adjust as per settings. A request was made to conduct an assessment and the recommendation was that the constant air volume (CAV) diffusers be replaced with a variable air volume (VAV) diffusers with a dedicated controller.Note: Work was completed 15 March 2022. Approved by CRES.Scope of works: Supply and install the new diffusers and wall controller : 200DIA VAV 0,5kw Swirl (x3) 250DIA VAV 0,5kw Swirl (x2) 300DIA VAV 0,5kw Swirl (x1) Wall termostat (x5) Power pack (x6) 2.5mm x2 Earth Surfix White (Drum) 0.3/0.5kV to SABS 1411 (x50m) |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2022-07-29 |  |  | ASP-GS0508 | CRTD: |  | false | false |  |  |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-25 |  | 0 |  | 100 | 2022-07-27 | 2022-07-27 | 0 |  |  |  |  | C000060653 | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-01-11 | 52664.44 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000329 | COC Investigation and Remedial Work | COC Investigation and Remedial Work |  |  | Region 1 | Gauteng South | 77462X | 1000-71398-01 | Absa Kings |  | 2022-07-01 | 2022-08-31 |  | ASP-GS0509 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-07-27 |  | 4371.6 |  | Approved | 2022-07-27 | 2022-07-27 | 0 |  |  |  |  | C000061755 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 3900 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000330 | Remove ATM Doors 19991231ctive | Remove ATM Doors 19991231ctive |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2022-07-29 |  |  | ASP-GS0510 | CRTD: |  | false | false |  |  |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-07-27 |  | 0 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000060543 | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-01-11 | 3982.57 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000331 | Replacement of banking hour decalAt Absa | Replacement of banking hour decalAt Absa Mall@Carnival, there is a request to replace the banking hour decal. The existing banking hour decal does not have the correct banking hour details and will be replaced to indicate the correct hours of Saturdays 09:00 12:00.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and install new banking hour decal Work will take place during normal working hours during weekdays Approx. 3 days |  |  | Region 1 | Gauteng South | 21869X | 1000-70043-01 | Absa Carnival Mall, Shop 156-157, Mall @ Carnival, cnr Lavender Street and Rangeview Road, Brakpan |  | 2022-07-29 | 2022-10-31 |  | ASP-GS0515 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-07 |  | 305.62 |  | Approved | 2022-08-19 | 2022-08-19 | 0 |  |  |  |  | C000061088 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-12 | 277.83 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000332 | Install Branch Manager SignThis request | Install Branch Manager SignThis request seeks approval to install a branch manager sign as there is currently no sign. This sign will ensure that the branch manager s office is visible to the clients.Note : Approved by RIF. Artwork approved by Absa Design. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and Install Branch Manager Sign (120 X 300) Security Guarding Services to be provided for duration of the project. Work will take place during normal working hours |  |  | Region 1 | Gauteng South | 36244X | 1000-70196-01 | Absa Northmead Square, Shop F10-14, Northmead Square, cnr O Reilly Merry Street and 14th Avenue, Benoni |  | 2022-07-29 | 2022-10-31 |  | ASP-GS0516 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-08 |  | 147.84 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | C000031481 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000333 | Install new floor vinyl tilesAt Absa Mal | Install new floor vinyl tilesAt Absa Mall of the South, there is a request to install new floor vinyl tiles in the ATM room due to the current tiles being stained with ink. The floor had been cleaned however; it was not possible to remove the ink stains. New floor vinyl tiles will be installed to enhance the look and feel within the ATM room.Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Install new anti static floor vinyl tiles (12 sqm) Security Guarding Services to be provided for duration of project Project Cleaning Services Work will take place during normal working hours on weekdays |  |  | Region 1 | Gauteng South | 36101X | 1000-70180-01 | Absa Mall of the South, Shop G140, Mall of the South, cnr Swartkoppies Road and Kliprivier Drive, Johannesburg |  | 2022-07-30 | 2022-09-30 |  | ASP-GS0517 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-08 |  | 687.84 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | C000031482 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000334 | Install new floor vinyl tilesAt Absa Sou | Install new floor vinyl tilesAt Absa Southgate mall, there is a request to install new floor vinyl tiles in the ATM room due to the current tiles being stained with ink. The floor had been cleaned however; it was not possible to remove the ink stains. New floor vinyl tiles will be installed to enhance the look and feel within the ATM room.Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Install new anti static floor vinyl tiles (35 sqm) Security Guarding Services to be provided for duration of project Work will take place during normal working hours on weekdays |  |  | Region 1 | Gauteng South | 77326X | 1000-70365-01 | Southgate Mall-Cnr Rifle Range Rd & Columbine Ave-Mondeor |  | 2022-07-30 | 2022-09-30 |  | ASP-GS0518 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-08-08 |  | 1602.23 | Approved | 100 | 2022-08-11 | 2023-10-07 | 18425.68 |  | {"MANDT":"111","REFERENCE":70000334,"ONEVIEW":"77326X","DATE01":"2022-05-21","DATE02":"2022-05-28","DATE03":"2022-06-18","DATE04":"2022-06-25","DATE05":"2022-07-16","DATE06":"2022-07-30","DATE07":"2023-03-21","DATE08":"2023-04-11","DATE09":"2023-05-26","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-30","FORECAST_END":"2023-03-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061032 | PHASE08 | 2022-07-30 | 2023-03-21 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000615 |  |  |  |  | 2023-01-12 | 18425.68 | 0 |  |  | C000031483 | 16022.34 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000335 | Replace damaged HVAC units and control p | Replace damaged HVAC units and control panel (19991231ctive)The HVAC copper pipes were stolen. After the copper lines were repaired and units re gassed, four out of 7 units have mechanically ceased due to the condensors that were running without oil while copper lines were stolen .This could not be detected before repairs of the copper lines. Note: Supported by AFS. Work completed was completed in May 2022. The landlord proposed to install motion trigger cameras as temporary solution while they prepare to close the area with fencing. Insurance Claim Logged via INSOG Process.Scope of works: Decommission x3 Mitsubishi Condensers Units Remove and replace faulty compressors from condensers Clean refrigerant pipe lines vacuum systems to 500 microns Recharge System with refrigerant (R410) Gas. Issue Gas & Disposal Certificate on completion. Remove and replace faulty outdoor main PC board & recommission systems after repairs carried out. |  |  | Region 1 | Gauteng South | 76420X | 1000-70247-01 | Absa Eastgate, Shop L34A, Eastgate Shopping Centre, cnr Bradford and Nicol Road, Bedfordview |  | 2022-08-01 | 2022-12-31 |  | ASP-GS0519 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | L |  | GAMIETR | 2022-08-08 |  | 7870.7 | Approved |  | 2022-08-11 | 2023-10-07 | 90513.04 |  | {"MANDT":"111","REFERENCE":70000335,"ONEVIEW":"76420X","DATE01":"2022-05-23","DATE02":"2022-05-30","DATE03":"2022-06-20","DATE04":"2022-06-27","DATE05":"2022-07-18","DATE06":"2022-08-01","DATE07":"2022-12-31","DATE08":"2023-01-21","DATE09":"2022-09-15","DATE10":"2022-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-08-01","FORECAST_END":"2022-12-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000031519C000061041 | PHASE11 | 2022-08-01 | 2022-12-01 | PRESHANE MUNTHREE | Buhle Qwabe | 23000551 |  |  |  |  | 2023-01-12 | 78706.99 | 0 |  |  | C000031519 | 78707 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000336 | Replacement Server Room Midwall Split un | Replacement Server Room Midwall Split unit (19991231ctive)Absa Mall@Carnival, the HVAC unit in the server room has stopped working and a call was logged for the service provider to establish what the problem was. Upon investigation it was found that no surge protection was installed and as a result of this it affected the PC Boards on the outdoor unit as well as the compressor had failed. The unit was installed in 2011 and repairs was conducted on this unit twice before where the compressor failed. Due to the server room equipment running 24 hrs /7 days a week the work was completed via the INSOG process.Note : Work completed was completed 05 May 2021. Like for like replacement, No GMP Cost Impact.Cost breakdown: Installation of HVAC: R 31 339,32 Incl. VAT Installation of Surge Protectors : R 4 068,16 Incl. VAT Total project cost: R 35 407,48,01 Incl. VAT Scope of works: Remove existing outdoor unit Supply and install new 18,000 BTU Midwall unit for Server Room Inverter Supply and install new refrigeration piping, cable tray and drain piping. |  |  | Region 1 | Gauteng South | 21869X | 1000-70043-01 | Mall@Carnival-Cnr Airport & Heidelberg Rd-Brakpan |  | 2022-08-01 | 2022-10-31 |  | ASP-GS0520 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-08 |  | 3078.91 |  | 100 | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000061764 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 3537.53 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000337 | Install banking time decal (19991231ctiv | Install banking time decal (19991231ctive)The emergency exit door was replaced and the banking hour decal had to be installed on it. The work was done via the INSOG process and was completed in 22 April 2022.Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Install time decal on emergency exit door. |  |  | Region 1 | Gauteng South | 78727X | 1000-70433-01 | Absa Daveyton, Shop 57, Daveyton Mall, cnr Turton and Eisselen Street, Daveyton |  | 2022-04-07 | 2022-08-31 |  | ASP-GS0521 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leased |  | GAMIETR | 2022-08-10 |  | 292.13 |  | Approved | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000030575 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000338 | Installation of power points (19991231ct | Installation of power points (19991231ctive)This request seeks 19991231ctive approval for the installation of power points in the ceiling void for access control and BMS equipment in the Clown fish / Forensics room in the Data Centre.Scope of Work Install 2 X plug points in ceiling void for camera. Issue COC upon completion. |  |  | Region 1 | Gauteng South | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2022-07-30 | 2022-08-31 |  | ASP-GS0522 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-10 |  | 513.76 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000060740 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-11 | 5137.63 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000339 | Install 3 X Flood LightsThis request is | Install 3 X Flood LightsThis request is for the installation of x3 flood lights outside the Alice Lane North pump room following a break in incident. The official security report recommended the installation of lights in the blind spots to ensure a clear view for the cameras. Note: Supported by AFS and BFM Engineering.Scope of Work Supply and installation of 3 X Flood Lights (100 watts LED & motion sensor). COC to be provided. Security guarding service to be provided for duration of project. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-07-30 | 2022-10-31 |  | ASP-GS0524 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-22 |  | 2113.91 | Approved | 100 | 2022-09-15 | 2023-10-07 | 24310.01 |  |  |  |  | C000061525 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Michael Maluleka | 23000605 |  |  |  |  | 2023-01-16 | 24310.01 | 0 |  |  | C000038746 | 21139.14 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000340 | Transformer replacement earth cable (Ret | Transformer replacement earth cable (19991231ctive)At Absa Towers North the earth cable that earths the transformers was stolen. The cable was replaced with Kwena anti theft cable and by means of looping each transformer instead of wiring them in parallel. This request seeks approval to recover the cost due to this being done INSOG as it was an emergency.Note: Work was completed 17th August. INSOG approval in place. Scope of Work Supply Kwena Anti Theft Earth Conductor 20mm (100m). |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North, 180 Commissioner Street, Johannesburg |  | 2022-07-29 | 2022-08-31 |  | ASP-GS0525 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-22 |  | 7730.11 |  | Approved | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000037143 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000341 | Replacement of earth cable (19991231ctiv | Replacement of earth cable (19991231ctive) |  |  | Region 1 | Gauteng South | 37039X | 1000-70208-01 | Absa 190 Commissioner Street |  | 2022-07-30 | 2022-10-31 |  | ASP-GS0526 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-22 |  | 1379.5 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000034059 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000342 | Replacement of decal with updated trade | Replacement of decal with updated trade hours on shopfront Absa Oakfields has seen a decline in performance for the past 2 years and they didnt recover post lockdown. It was suggested that the branch must trade two Saturdays a month due to low feet on weekends. Due to this, the decal on the shopfront will have to be changed and reprinted to show the revised trade hours.Note: Approved at RIF, Absa design. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Replacing decal on shopfront. Material Leadtime: + 1 week(s). Timeline: 1 Day |  |  | Region 1 | Gauteng South | 79055X | 1000-71417-01 | Oakfields Shopping Centre-Cnr Oak & Hanekom St-Benoni |  | 2022-08-22 | 2022-10-31 |  | ASP-GS0527 | REL BUDG AVAC SETC: |  | false | false |  | << To be Determined >> |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-22 |  | 311.31 |  | 100 | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000034064 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000343 | Installation of space saver drop safe At | Installation of space saver drop safe At Absa Karaglen Branch a request was made to install a space saver safe between the ATM and Bulk Teller Rooms. The walls in the ATM and Bulk Teller rooms will also be painted to ensure a uniform look and feel after installation of the space saver safe. The space saver will be refurbished from existing stock.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. LL approval obtained. Floor plans updated. Scope of Work Full refurbishment of space saver from existing stock Delivery of space saver to site Break wall for space saver installation Prep and paint all walls in the ATM room and Bulk Teller room (match existing wall colours) Security guarding services to be provided for duration of project Work will take place during normal working hours on a weekend. Work to be completed in 2 days. |  |  | Region 1 | Gauteng South | 76642X | 1000-70300-01 | Karaglen Centre-Baker Rd-Edenvale |  | 2022-07-20 | 2022-10-31 |  | ASP-GS0528 | CLSD CNF BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-22 |  | 4261.51 | Approved | 100 | 2022-08-25 | 2023-10-07 | 49007.43 |  |  |  |  | C000061213 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000581 |  |  |  |  | 2023-01-13 | 49007.43 | 0 |  |  | C000034063 | 42615.17 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000344 | Replacing condenser fans and install sur | Replacing condenser fans and install surge protectors on chillers in Block M and H This request is for the replacement of the faulty chiller condensor fans in Block H and Block M at the Absa Pretoria Campus. The chiller condensor fans have been affected by a power surge based on assessment done on fans that were previously damaged as per the report. An additional request is to install surge protectors to prevent this from happening in future Note: Approved by CRES, Supported by Engineering. Work completed via INSOG process on 24 June 2022 in Block H for the chiller condensor, surge protectors still to be installed. Scope of Work Replacement of faulty chiller condenser fans: 2 X on chiller 4 and 1 X on Chiller 1 Block H. 1 X on chiller 4 and 1 X on Chiller 1 Block M Supply of Type 3/surge / 3ph/ 380V/ Schinder (x10) Issue of COC on completion |  |  | Region 1 | Gauteng South | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2022-08-01 | 2022-11-30 |  | ASP-GS0529 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-25 |  | 21457.43 | Approved | 100 | 2022-10-27 | 2023-10-07 | 246760.45 |  |  |  |  | C000062474 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000516 |  |  |  |  | 2023-01-19 | 246760.45 | 0 |  |  | C000045996 | 214574.3 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000345 | Removal of 200kVA & Install Temporary 10 | Removal of 200kVA & Install Temporary 100kVA generator (19991231ctive)At Absa Greenstone the current generator (200KVA ) is not working, the new generator that was approved under projects is currently under the manufacturing process until end of September 2022. This request is for Diesel Innovations to install a temporary generator and remove from on site.Note: Work was completed in July 2022 and done via INSOG approval process. Scope of Work To decommission and remove the existing 200kVA generator that is damaged and install a spare generator . To connect the 100KVA generator to the existing exhaust line. Align the temporary generator exhaust line to the existing exhaust line ( flexible pipe used and clamped on joints for coupling and airtight sealing ). Cost inclusive of rigging. |  |  | Region 1 | Gauteng South | 78551X | 1000-70418-01 | Greenstone Shopping Centre-Stoneridge Dr-Edenvale |  | 2022-07-29 | 2022-08-31 |  | ASP-GS0530 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-08-25 |  | 12035.5 | Approved | 100 | 2022-09-01 | 2023-10-07 | 138408.25 |  | {"MANDT":"111","REFERENCE":70000345,"ONEVIEW":"Unknown","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-07-29","DATE07":"2022-07-29","DATE08":"2023-01-23","DATE09":"2023-03-09","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"194:7:21:7:21:14:0:178:45:25","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-29","FORECAST_END":"2022-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Medium"} |  |  | C000050087 | PHASE11 | 2022-07-29 | 2022-07-29 | PRESHANE MUNTHREE | Buhle Qwabe | 23000528 | [5 empty] | 138408.25 | 0 |  |  | C000050087 | 120355 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000346 | 19991231ctive COC | 19991231ctive COC |  |  | Region 1 | Gauteng South | 78946X | 1000-71416-01 | Absa Towers East |  | 2022-08-01 | 2022-11-30 |  | ASP-GS0531 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-08-25 |  | 9385 |  | Approved | 2022-09-16 | 2022-09-16 | 0 |  |  |  |  | C000039291 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000347 | Replacement of 2 X Hydro taps and moving | Replacement of 2 X Hydro taps and moving of Traders area Hydro tap to Podium ground floor.The current hydro taps in the following areas, Podium Ground Floor (21843X) and the Alice Lane South(ALS) 3rd floor Executive Client Suites(35041X) are malfunctioning and require to be restarted constantly. This is an inconvenience, and a request was made to replace the 2 Hydro taps. The supplier was approached to fix the problem, but they have advised that the units have been discontinued and the replacement parts have become obsolete. It was also suggested that one Hydro tap from ALN 2nd floor Traders area (70656X) be relocated to Podium ground floor and replaced with a new Hydro tap with a sparkling option. Installation of the 3rd floor client suites tap will be on the existing drain system, however, should it prove to be conducive upon installation, the granite will be required to be cut.Maintenance Cost The CO2 Gas cartridge Pack of 2 R3040,00 ex VAT each and the lifespan is dependable on the usage. They are dispoable metal cartridges that are recyclable.The SLA on the system is every 6 months with a filter change or after 34 068 litres at R3680, although not applicable as similar units being replaced already accounted for . Cost BreakdownAbsa ALS 3rd Floor (35041X): R 97 363,99 Incl. VATAbsa ALN Traders (70656X) : R145 189,04 Incl. VATAbsa ALP (21843X) : R 10 890,45 Incl. VAT R253 443, 48 Incl. VAT(Installation, Security & Contingency cost distributed equally to 3 above)Note : Supported by CRES VP s. BFM ENG support obtained. Like for like replacements, no GMP Cost ImpactScope of Work Supply and install 2 x Hydro taps as follow: 2nd Floor Traders Area X1 Hydrotap G4 BCS(Hot, Cold and Sparkling) CO2 Gas Cylinder gives approximately 150 to 160 litres of sparkling water, equivalent to 750 glasses of sparkling water. 3rd Floor Executive Client Suites KitchenX1 Hydrotap G4 BC(Hot and Cold) 2610038. Decommission and re install existing Hydro tap as follows: Ground Floor Podium Pause areaX1 ZIP Hydro tap from 2nd floor traders area to Podium pause area. Replace BIC door with a ventilated door (2nd floor traders area) Image attached to BC. Installation of Electrical Points Issue COC certificate on completion Security guarding service to be provided for duration of project. |  |  | Region 1 | Gauteng South | 70656X | 1000-71371-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-08-22 | 2022-10-31 |  | ASP-GS0532 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-25 |  | 22038.56 | Approved | 100 | 2022-09-28 | 2023-10-07 | 253443.47 |  |  |  |  | C000041190 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Michael Maluleka | 23000514 | [5 empty] | 291459.99 | 0 |  |  | C000041190 | 220385.63 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000348 | Supply of tables for the outside deck ar | Supply of tables for the outside deck areaAt Absa Towers Main, there are only chairs on the outside deck area which require tables. This request is to obtain 4 x 6 seater tables which are durable to all weather conditions as these will be situated outside.Note: Supported by CRES VP. The design was supplied by and approved by Absa Design Team.Scope of works: Supply and Deliver 4 x 6 seater tables Lead Times: 6 8weeks |  |  | Region 1 | Gauteng South | 78944X | 1000-71415-01 | ABSA TOWERS MAIN-Main St-Johannesburg |  | 2022-07-29 | 2022-10-31 |  | ASP-GS0533 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-08-29 |  | 9418.35 | Approved | 100 | 2022-09-01 | 2023-10-07 | 108311.03 |  | {"MANDT":"111","REFERENCE":70000348,"ONEVIEW":"78944X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061206 | PHASE11 | 2022-10-01 | 2022-11-24 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000541 |  |  |  |  | 2023-01-13 | 124557.68 | 0 |  |  | C000035930 | 94183.51 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000349 | Install Vinyl frosting in two meeting ro | Install Vinyl frosting in two meeting rooms This request seeks approval for the installation of vinyl frosting in boardrooms GF65 and GF63 at Absa Alice Lane North. Being meeting rooms, there is a requirement for vinyl frosting to provide privacy.Note : Approved by CRES. Scope of Work Vinyl Design, manufacture, cut and install onto Glass (7.3 m), Office Windows Facing Canteen Office G.63 (7.3 m) Vinyl Design, manufacture, cut and Install onto Glass Office Windows Facing Canteen Office G.65 Security guarding service to be provided for duration of installation Work to take place on a weekend during the day |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-08-30 | 2022-11-30 |  | ASP-GS0534 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | L |  | GAMIETR | 2022-08-29 |  | 1720.35 |  | 100 | 2022-09-01 | 2022-09-01 | 19784.11 |  | {"MANDT":"111","REFERENCE":70000349,"ONEVIEW":"70656X","DATE01":"2022-06-21","DATE02":"2022-06-28","DATE03":"2022-07-19","DATE04":"2022-07-26","DATE05":"2022-08-16","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000043418 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000609 | [5 empty] | 17203.57 | 0 |  |  | C000043418 | 17203.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000350 | Dilaps & Reinstatement | Dilaps & Reinstatement |  |  | Region 1 | Gauteng South | 77264X | 1000-70360-01 | Absa Vereeniging |  | 2022-07-30 | 2022-09-30 |  | ASP-GS0535 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-08-31 |  | 9784.09 |  | Approved | 2022-09-01 | 2022-09-01 | 0 |  |  |  |  | C000061200# | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-13 | 18745.97 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000351 | Minor Works - Absa Lenasia (CIP 2022)At | Minor Works Absa Lenasia (CIP 2022)At Absa Lenasia, there is a request to replace the existing furniture and install new carpets. The counter in the customer service area will be replaced with x3 bench style sales desks, and x1 additional desk will also be installed by the consultants along with a power pole. The plinths inx5 offices at the front of the branch, and x4 in the customer service area will be replaced. The carpets in the front of the branch (x5 offices, customer services, and consultants) have deteriorated over time and requires to be replaced with new carpets. The ceiling tiles are mismatched and the recommendation was made to spray the tiles to enhance the look and feel of the branch.Note : Approved at RIF and Absa Design. Supported by BFM Eng. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Work Pick up x4 bench style sales desks and x9 plinths from Absa Stores at Lea Glen and transport to the Absa Lenasia branch. Install plinths in x5 offices at the front of the branch, and x4 in the customer service area. Install x4 bench style sales desks at the front of the branch as indicated on drawing. Install vinyl for x1 sales consultant desk, and on x3 customer services desks. Install power pole with 1 red and 1 normal plug points for additional desk. COC to be provided on completion. Remove existing flooring by the 5 offices in the front of the branch, customer services, and consultants. Install new carpet spec (Belgotex Hard Graft) in the 5 offices in the front of the branch, customer services, consultants, tellers, bulk teller, treasury area and at the back office (excluding kitchen and back interview room) Approx. 290sqm. Prep and paint wall where counter had been removed by customer services. Spray Ceiling Tiles White (excluding server room) Approx. 581sqm. Security guarding services to be provided for duration of the project. Project cleaning services at the end of the project. Work will be completed in two weeks which will include two weekends after working hours. |  |  | Region 1 | Gauteng South | 77329X | 1000-70367-01 | Absa Lenasia-Cnr Rose & Gemsbok Ave-Lenasia |  | 2022-07-29 | 2022-10-31 |  | ASP-GS0537 | CLSD CNF BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-09-05 |  | 25537.97 | Approved | 100 | 2022-09-08 | 2023-10-07 | 293686.66 |  | {"MANDT":"111","REFERENCE":70000351,"ONEVIEW":"77329X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061328 | PHASE11 | 2022-11-15 | 2022-11-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000510 |  |  |  |  | 2023-01-13 | 337739.66 | 0 |  |  | C000037141 | 255379.71 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000352 | Installation of a new raised toilet seat | Installation of a new raised toilet seat with lid (Block A)One of the employees at Absas Pretoria Campus underwent surgery requiring the usage of a raised toilet seat. The supply and installation of the toilet seat in Block A is urgently needed. An assessment was conducted and all medical documentation were submitted.Note: Supported by CRES OHS. Scope of works: Installation of a new raised toilet seat. Installation will be done during normal working hours. On site timeline: 1 Day. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2022-09-05 | 2022-10-31 |  | ASP-GS0539 | REL BUDG AVAC SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-09-09 |  | 337.34 |  | 100 | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000061522# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-16 | 3373.48 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000353 | Phase 1: Installing soundproofing above | Phase 1: Installing soundproofing above the ceiling and re install existing acoustic door Office 1.01 (19991231ctive) SA601903This request seeks 19991231ctive approval for the installation of soundproofing above the ceiling and one acoustic door. An urgent request was made to enhance the soundproofing in room 1.01 to function as an interim office at 15 Alice Lane South. The office were to be ready for occupancy on 05 September 2022 and therefore accelerated approval were required on the 31st August to commence with the work immediately. This is part of the compliance interim office solution.Note: Approved by CRES VP, BFM Engineering and Absa Design. Updated drawing received. Work completed on 05 September 2022. Scope of Work Remove existing ceiling panels and set aside for re use. Install new acoustic boards and re instate the ceiling panels. Remove and wrap existing solid door and set aside for re use in Project phase 2. Remove acoustic door from room 3.07 and install door in room 1.01. Timeline: 2 Nights. |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2022-09-05 | 2022-10-31 |  | ASP-GS0540 | REL BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-09-09 |  | 2538.46 |  | 100 | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000038844 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000354 | Supply and installation of Compressor on | Supply and installation of Compressor on Chiller 5 (Item for Noting)Absa Auckland Park chiller plant was installed on the inception of the building. In the past there has been a number of both mechanical and electrical failed compressors that have been replaced. One of the chiller 5 compressors on circuit 1 has also failed mechanically. Upon root cause investigation done by the chiller OEM it was noted that the previous chiller plant running methodology was incorrect and has caused this compressor to fail mechanically. A new chiller plant running methodology has since been implemented as agreed with the CRES Engineering team. Chiller 5 is currently operating at 50% capacity and the compressor replacement is required to ensure that Chiller 5 can operate at 100% capacity.Note: Supported by BFM Engineering. Approved Out of Cycle by CRES Engineering on 12/09/2022. Like for like replacement, No GMP Cost Impact.Scope of Work Supply and Install 1 x New Compressor on Chiller 5, Circuit 1; ( C1080625, Scroll ZP485KCE TWD 522 + Antivibration Mounts COD 8048911 TANDEM USE COD 8040746) Oil sample,Wearcheck (x1 of per compressor) Consumables (rods,rags,oxy,degreaser) Oil, ICI Emkarate RL 32,26.0 litres for two circuits, 13L per circuit (5.77kg compressor) Refrigerant (x6 bottles per circuit) Acid burnout/ High moisture filter dryer, C6020196 Filer Core Type ADKS 48 CU.IN.100% SET.MOL.X POE, 6 of Servicing,green coil cleaner Nitrogen Work will take place normal working hours from Monday to Friday, installation will take approximately x3 days Lead time x 2 weeks for equipment |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-05-27 | 2022-12-31 |  | ASP-GS0541 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-09-12 |  | 13882.05 |  | 100 | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000061528# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-16 | 138820.55 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000355 | Refurbishment of EZGO Electrical Golf Ca | Refurbishment of EZGO Electrical Golf Carts (x2)This request seeks approval for the refurbishment of golf carts at Absa Towers West. The current golf carts are approximately 4 years old and deteriorated over a period of time. The recommendation was made to refurbish the golf carts.Note: Supported by CRES VP.Cost Breakdown: Golf Cart (Chassis No.283521) = R 70 899,80 incl.VAT ( Lithium Battery Pack) + R 2 696,75 incl.VAT (Refurbishment) = (R 73 596,55 incl.VAT) Golf Cart (Chassis No.2836586) = R 70 899,80 incl.VAT ( Lithium Battery Pack) + R 1 909,00 incl.VAT (Refurbishment) = (R 72 808,80 incl.VAT) Total Cost: R 146 405,35 incl.VATScope of Works: Installation of golf cart hooter (x2) Consumables (x2) Collection and delivery of golf carts (x2) Clean and polish of golf carts (x2) Lithium Pack 48V 100AH with charger and battery meter (x2) |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West, 15 Troy StreetJohannesburg |  | 2022-09-13 | 2022-10-31 |  | ASP-GS0542 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-09-13 |  | 12730.9 |  | Approved | 2022-09-01 | 2022-09-01 | 0 |  |  |  |  | C000061527# | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-16 | 127309 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000356 | Minor Works - Absa FloridaThere is a pro | Minor Works Absa FloridaThere is a project request for minor works to be done at Absa Florida, spraying of all the ceiling tiles white and upgrade the kitchen. The ceiling tiles have deteriorated over time and would need to be sprayed white to enhance the look and feel of the branch. The kitchen is old and has not been upgraded previously. The kitchen would require an installation of new cupboards, painting of walls, replacements of floor tiles, and installation of a new hydroboil. Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Supported by BFM Eng. No GMP Cost impact.Scope of Work Replace floor tiles (8m2) Replace wall tiles (8m2) Install new cupboards; Prep and paint walls (30m2) Install new tap and 7,5 lt hydroboil; Spray Ceiling Tiles White on site (821m2) Security to be provided for duration of project. Work to be after hours and for duration of two weeks. |  |  | Region 1 | Gauteng South | 22379X | 1000-70060-01 | 20 Goldman Street Florida-Goldman St-Johannesburg |  | 2022-03-29 | 2022-10-31 |  | ASP-GS0544 | REL CNF BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-09-19 |  | 80000 | Approved | 100 | 2022-09-22 | 2023-10-07 | 176914.87 |  | {"MANDT":"111","REFERENCE":70000356,"ONEVIEW":"22379X","DATE01":"2022-01-18","DATE02":"2022-01-25","DATE03":"2022-02-15","DATE04":"2022-02-22","DATE05":"2022-03-15","DATE06":"2022-01-01","DATE07":"2023-04-04","DATE08":"2023-04-25","DATE09":"2023-06-09","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-04-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061650 | PHASE11 | 2022-01-01 | 2023-02-16 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000522 |  |  |  |  | 2023-01-16 | 203452.1 | 0 |  |  | C000039620 | 153839.02 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000357 | Supply, deliver and place walk-off mat a | Supply, deliver and place walk off mat at entrance lobbyThis request is for the supply of walk off mat as clients enter the lobby area before they can enter the branch itself, the area is tiled and the walk off mat is to be placed on top of the tiles. Currently there is no walk off mat at the branchs entrance lobby as such the carpets in the mantrap doors are being soiled and worn as this is a high traffic area.Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply, deliver and place walk off mat (12mm thick Grey Trio Scraper). Dimensions:2500mmx1400mm Mat to be placed in the morning before branch opens. |  |  | Region 1 | Gauteng South | 77470X | 1000-70369-01 | Absa Vanderbijlpark, Vesco Building, FW Beyers Street, Vanderbijlpark |  | 2022-08-30 | 2022-11-30 |  | ASP-GS0545 | CLSD PCNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-09-26 |  | 1417.81 | Approved | 100 | 2022-09-28 | 2023-10-07 | 16304.9 |  |  |  |  | C000041192 | PHASE11 | 2022-08-30 | 2022-11-30 | PRESHANE MUNTHREE | Buhle Qwabe | 23000618 | [5 empty] | 16304.9 | 0 |  |  | C000041192 | 14178.17 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000358 | Replacement of worn-out | Replacement of worn out lift main & governor cables (INSOG)During a recent routine maintenance, it was reported that the main and governor cables of shuttle lift A is showing signs of wearing out. Upon further investigation it was established that the detertioration was beyond a reasonable threshold therefore requiring change. As a precautionary measure the current lift has been isolated from usage pending the cable replacement. Note: Approved by CRES & Supported by BFM Engineering. Awaiting spares work not completed. Call logged via the INSOG Process.Scope of Work Sling lift cars and bump the counterweights. Supply and install 6 new 12mm main ropes, 75m each in length per lift. Supply and install 1 new 6mm governor rope, 47m each in length per lift. Remove the slings and counterweight bumping pole. Return the lifts into service. Security to be provided for duration of project. |  | h | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | Y | 2022-01-29 | 2022-11-30 |  | ASP-GS0547 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | F |  | GAMIETR | 2022-09-30 |  | 38933.4 | Cost Board | 100 | 2022-10-05 | 2022-10-05 | 38933.4 |  | {"MANDT":"111","REFERENCE":70000358,"ONEVIEW":"77381X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-01-01","DATE07":"2023-03-10","DATE08":"2023-03-31","DATE09":"2023-05-17","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"496:7:21:7:21:-14:433:21:47:5","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-03-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061970 | PHASE11 | 2022-01-01 | 2023-03-10 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000515 |  | 2023-03-17 |  | 2023-03-17 | 2023-01-17 | 219370.28 | 0 |  |  | C000042118 | 219370.28 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000359 | Supply new internal directional signageC | Supply new internal directional signageCustomers have expressed frustration over being lost at Absa Rosebank, the branch currently does not have directional signage indicating where to go. This request is for new internal directional signage.Note : Approved at RIF and Absa Design. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and deliver x1 new internal directional signage stand to branch. (620 X 300mm) Material lead time: + 1.5 week(s). Timeline: 1 day |  |  | Region 1 | Gauteng South | 36280X | 1000-70025-01 | Cradock Heights-Cradock Ave-Johannesburg |  | 2022-08-30 | 2022-11-30 |  | ASP-GS0548 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-09-30 |  | 652.09 | Approved | 100 | 2022-10-05 | 2023-10-07 | 7499.05 |  | {"MANDT":"111","REFERENCE":70000359,"ONEVIEW":"36280X","DATE01":"2022-06-21","DATE02":"2022-06-28","DATE03":"2022-07-19","DATE04":"2022-07-26","DATE05":"2022-08-16","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000042119 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000625 | [5 empty] | 7499.05 | 0 |  |  | C000042119 | 6520.91 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000360 | Replace Generator BatteriesAt Absa 270 R | Replace Generator BatteriesAt Absa 270 Republic Road, there are nine backup generators. These generators provide backup power to the critical equipment in 5 buildings (Block A, Block B, Block C, 270 Office towers, 270 data centre). The starter batteries have an average life span of 4 to 5 years however due to Absa service level agreement & the Critical Nature of the Data centre and offices, the client has requested that the batteries be changed on a yearly basis. Note: Approved by CRES, Supported by Engineering. Scope of Work Supply and install 16 Royal N150 150 ampere hour starter batteries and 14 Royal 1150K 105 ampere hour starter batteries. |  |  | Region 1 | Gauteng South | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2022-09-26 | 2022-11-30 |  | ASP-GS0549 | REL BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-09-30 |  | 11327.18 | Approved | 100 | 2022-10-27 | 2023-10-07 | 130262.57 |  | {"MANDT":"111","REFERENCE":70000360,"ONEVIEW":"21335X","DATE01":"2022-07-18","DATE02":"2022-07-25","DATE03":"2022-08-15","DATE04":"2022-08-22","DATE05":"2022-09-12","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062344 | PHASE09 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000532 |  |  |  |  | 2023-01-18 | 130262.57 | 0 |  |  | C000045993 | 113271.8 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000361 | Replace Generator BatteriesAbsa 12 Alice | Replace Generator BatteriesAbsa 12 Alice Lane North has 6 CAT generators positioned in the basement parking that use battery power for the Generator start up during load shedding & electricity interruptions. The starter batteries have an average life span of 4 to 5 years however due to Absa service level agreement & the Critical Nature of Alice lane North, the client has requested that the batteries be changed on a yearly basis.Note: Approved by CRES, Supported by Engineering. Scope of Work Supply and install 24 x 150 ampere hour , N150 Type Royal Batteries . |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-08-30 | 2022-11-30 |  | ASP-GS0550 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-09-30 |  | 11807.87 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062734# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 118078.73 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000362 | Replace Generator BatteriesAbsa Alice La | Replace Generator BatteriesAbsa Alice Lane South has 2 x Mitsubishi generators positioned in the basement parking that utilises battery power for the generator to start up during load shedding & electricity interruptions. The starter batteries have an average life span of 4 to 5 years however, due to Absa service level agreement & the critical nature of Alice Lane South, the client has requested that the batteries be changed on a yearly basis. Note: Approved by CRES, Supported by Engineering. Scope of Work Supply and install 16x102Amphere hour, N102 Type Deltec Batteries. |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2022-08-30 | 2022-11-30 |  | ASP-GS0551 | REL BUDG AVAC SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | L |  | GAMIETR | 2022-09-30 |  | 4717.54 | Approved | 100 | 2022-10-05 | 2023-10-07 | 54251.76 |  | {"MANDT":"111","REFERENCE":70000362,"ONEVIEW":"35041X","DATE01":"2022-06-21","DATE02":"2022-06-28","DATE03":"2022-07-19","DATE04":"2022-07-26","DATE05":"2022-08-16","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061965 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Michael Maluleka | 23000576 |  |  |  |  | 2023-01-17 | 54251.76 | 0 |  |  | C000042109 | 47175.44 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000363 | Replace Generator BatteriesHighlands War | Replace Generator BatteriesHighlands Warehouse Meadowdale has 1 Perkins and 1 Mitsubishi generators that utilises battery power for the Generator start up during load shedding & electricity interruptions. The starter batteries have an average life span of 4 to 5 years however, due to Absa service level agreement & the critical nature of Highlands Warehouse namely being a backup worksite, the client has requested that the batteries be changed on a yearly bases. Note: Approved by CRES, Supported by Engineering. Scope of Work Supply and install 6 x 105 ampere hour, 1150K Nut Type Royal Batteries. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-08-30 | 2022-11-30 |  | ASP-GS0552 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-09-30 |  | 1711.58 | Approved | 100 | 2022-10-05 | 2023-10-07 | 19683.24 |  | {"MANDT":"111","REFERENCE":70000363,"ONEVIEW":"37006X","DATE01":"2022-06-21","DATE02":"2022-06-28","DATE03":"2022-07-19","DATE04":"2022-07-26","DATE05":"2022-08-16","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061966 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000610 |  |  |  |  | 2023-01-17 | 19683.24 | 0 |  |  | C000042115 | 17115.86 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000364 | Relocation and supply of additional cant | Relocation and supply of additional canteen furnitureThere is a growing need for additional seating in the canteen area at Absa Towers West. This request is for the procurement of x6 additional tables and x6 benches as well as the relocation of high tables and chairs from the canteen area in Absa Towers North to canteen area in Absa Towers West, due to more staff returning to the building post covid lock down.Note: Supported by CRES VP. Scope of Work Supply and position 6 x New Rectangular Walnut Veneer top tables 1500mm x 800mm Supply and position 6 x New Walnut Veneer benches 1500x 450mm Leadtime on furniture delivery is 4 6 weeks Relocation 4 x high tables & 12 x highchairs from ATN to ATW Canteen inside seating area. Work to take place after hours Security guard to be provided for duration of project. |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-07-29 | 2022-11-30 |  | ASP-GS0553 | REL BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-10-07 |  | 30144.69 | Approved | 100 | 2022-10-13 | 2023-10-07 | 346663.97 |  | {"MANDT":"111","REFERENCE":70000364,"ONEVIEW":"21526X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062125 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000506 |  |  |  |  | 2023-01-18 | 346663.97 | 0 |  |  | C000043771 | 301446.93 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000365 | Supply of Alpha plugs on various deskThe | Supply of Alpha plugs on various deskThe staff are returning back to Auckland Park Call Centre and require functional plugs. It was found that the plugs socket modules at various desks were vandalised. This request is to replace 102 of these plug sockets modules.Scope of Work Supply of 102 X Alpha Plugs On site Engineering team to install the plugs. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-10-11 | 2022-11-30 |  | ASP-GS0554 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-10-23 |  | 14945.04 |  | 100 | 2022-10-20 | 2022-10-20 | 0 |  |  |  |  | C000062351 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-19 | 149450.4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000366 | Installation and integration of a new En | Installation and integration of a new Environmental Monitoring System(EMS)A new 300kVA UPS and a 800kVA generator were installed as part of a project in May 2021 at Absa Highlands Warehouse Meadowdale. The two systems were however not incorporated with any environment monitoring system. A request has been made for the installation and integration of a new SMS box and an environmental monitoring system to the new 300kVA UPS, generator and UPS room.Note: Approved by CRES, Eng supported. GMP Cost Impact updated. Scope of Work Install and integrate an environmental monitoring system to the UPS and generator. Work will be carried out durina normal working hours. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-10-14 | 2022-11-30 |  | ASP-GS0555 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-10-23 |  | 3970.64 | Approved | 100 | 2022-10-20 | 2023-10-07 | 45662.45 |  |  |  |  | C000062339 | PHASE11 | 2022-10-14 | 2022-11-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-18 | 45662.45 | 0 |  |  | C000044821 | 39706.48 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000367 | Installation of a New 12 000Btu/h Invert | Installation of a New 12 000Btu/h Inverter Midwall unit There is currently no aircon unit in the Absa Tsakane Mall ATM room. This request is to install a new 12 000Btu/h Inverter Midwall unit in the ATM room to allow for the to cooling for the ATM machinery. This will include the installation of a type 3 surge protection .Note: Approved by RIF and CRE and Supported BFM Eng. GMP Cost Impact included.Scope of Work Supply, delivery and installation of 1 x 12 000Btu/h Samsung Midwall Unit complete. Supply, delivery and Installation of pump out unit complete with drain. Installation of electrical supply circuit from main DB to AC Unit. Installation of surge protection type 3. Commissioning of System and issuing of COC. Security Guard to be provided for the duration of the project. Work to take place on a weekend after operational hours duration (16 hrs 2 days) Unit is in stock Max 1 week leadtime. |  |  | Region 1 | Gauteng South | 21857X | 1000-70041-01 | Tsakane Mall-Cnr Modjadji & Malandela St-Tsakane |  | 2022-10-14 | 2022-11-30 |  | ASP-GS0556 | REL BUDG AVAC SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-10-23 |  | -39439.49 | Approved at CB/BTB | 100 | 2022-10-20 | 2023-03-02 | -39439.49 | Approved |  |  |  | C000062141 | PHASE08 | 2022-10-14 | 2023-05-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000592 |  |  |  |  | 2023-01-18 | 39439.48 | 0 |  |  | C000044813 | 34295.2 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000368 | Re-Installing Intercom Cables to x2 Good | Re Installing Intercom Cables to x2 Goods LiftsThe goods lifts at Absa Towers North were upgraded approximately 2 years ago and during a recent evacuation drill it was identified that it is necessary to reconnect the old intercom system into the newly upgraded goods lifts to enable personnel on each floor to communicate with the goods lift operator. In case of an emergency/incident that requires evacuation the personnel and the firemen make use of the goods lift to access different floor levels, during this process communication using the intercom system is critical between the passengers and the operator of the goods lift. Note: Approved by CRES, Supported by Engineering.Scope of Work Installation of new cables for intercom systems to 2 x goods lift . Test and Commission Work will be carried out during normal working hours. Project cleaning services required after completion Material Leadtime: + 14 working days. Onsite timeline: 2 days. |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2022-10-14 | 2022-12-31 |  | ASP-GS0557 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2022 |  | F |  | GAMIETR | 2022-10-24 |  | 44773.34 |  | 100 | 2022-10-27 | 2022-10-27 | 44773.34 |  | {"MANDT":"111","REFERENCE":70000368,"ONEVIEW":"21526X","DATE01":"2022-08-05","DATE02":"2022-08-12","DATE03":"2022-09-02","DATE04":"2022-09-09","DATE05":"2022-09-30","DATE06":"2022-10-14","DATE07":"2022-12-31","DATE08":"2023-01-21","DATE09":"2023-03-07","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-14","FORECAST_END":"2022-12-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000046095 | PHASE11 | 2022-10-25 | 2023-01-27 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000588 |  |  |  |  | 2023-01-19 | 38933.34 | 0 |  |  | C000046095 | 38933.4 | CIP2023XP | 4070.1 |  | 0 | 0 |  | 0 |  | 0
70000369 | Supply and install the fire detection wi | Supply and install the fire detection with the evacuation trigger for block A,B and CAt Absa 268 Republic Road, there was a request to supply and install interface devices to automate the fire detection with the evacuation trigger for block A, B and C, currently the system is connected to the PA system at 270 Republic Road and that has since been decommissioned and the building upgrade will include an installation of a new PA system. It is also recommended to separate the 2 fire systems in order for the one at 268 Republic Road to run independently from that of 270 Republic Road for future purposes. Note: Approved by CRES, supported by BFM Eng. Scope of Work Install a Flush mounting RED analogue Call Point c/w EN54 marking [ZP785 3] X1 Install a Surface Mounting Box with Earth Connector RED. X1 PA System Programming Install a Series mini relay unit, mains switching [A51E 1] X6 Install s Surface box for A Series module, IP66 (4 single or 2 double) X 3 Install a Fire Retardant Cable 2 X 1mm.sq. PH30 100/100V per Meter X 100m Test and Commissioning Training on System Operation & Maintenance SFP11 Security guards will be required for the duration of the works. Work will be carried out during normal working hours for duration of 2 days Material Leadtime: + 2 working days. |  |  | Region 1 | Gauteng South | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2022-10-14 | 2022-11-30 |  | ASP-GS0558 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-10-24 |  | 2381.35 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062472# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-19 | 23813.57 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000370 | Adjust external ATM signage (19991231cti | Adjust external ATM signage (19991231ctive)A request was made to remove and adjust the ATM signage at the external ATM area as client kept hitting their heads on the signage. A call was logged via the INSOG process 303759283 409752136 PO 4500767502 for the work to be done immediately.Note : Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Work was complete on 30 September 2022Scope of Work Remove sign and investigate structure to lift sign higher. Repair & Repositioning ATM Sign on site |  |  | Region 1 | Gauteng South | 77203X | 1000-70355-01 | Absa Bracken City, Shop 4-5B, Bracken City Shopping Centre, cnr Rae Frankel and Hennie Alberts Street, Alberton |  | 2022-10-14 | 2022-12-31 |  | ASP-GS0559 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-10-24 |  | 533 | Approved | 100 | 2022-10-27 | 2023-10-07 | 6129.5 |  |  |  |  | C000062747 | PHASE11 | 2022-10-14 | 2022-12-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 6129.5 | 0 |  |  | C000046539 | 5330 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000371 | Install UPS plug for a digital whiteboar | Install UPS plug for a digital whiteboard A request has been made to install a UPS plug for a digital whiteboard in one of the Boardrooms. The reason for this request is that there is currently no plug where the board has been mounted.Note: Approved by CRES, Supported by Eng (Plug point is 50m from the nearest connection).Scope of Work Install new UPS plug and supply COC Work will be carried out on a weekend. Security guard for the duration of the works. Material Leadtime: + 5 days. |  |  | Region 1 | Gauteng South | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2022-10-26 | 2022-11-30 |  | ASP-GS0560 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | F |  | GAMIETR | 2022-10-27 |  | 1532.48 | Approved | 100 | 2022-10-27 | 2023-10-07 | 17623.61 |  | {"MANDT":"111","REFERENCE":70000371,"ONEVIEW":"21334X","DATE01":"2022-08-17","DATE02":"2022-08-24","DATE03":"2022-09-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062345 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000616 |  |  |  |  | 2023-01-18 | 20267.15 | 0 |  |  | C000045994 | 15324.88 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000372 | Scanning of the water reticulation syste | Scanning of the water reticulation systemThere is a water leak experienced by the guard house at the entrance of 270 Republic Road. An excavation will take place to repair the water leak. However, prior to the excavation taking place scanning on the ground level is required to ensure that there is no critical infrastructure where the excavation will take place.Note: Approved by CRES, Supported by Engineering. Scope of Work Scanning the existing water reticulation system: Scanning of possible water leaks to the existing water reticulation or there is a tie off Scanning of underground electrical conducts in preparation to set up for excavations where necessary. Test and Commissioning Security guard not required for the duration of the works. Work will be carried out during normal working hours for duration of two days. Material Leadtime: + 7 working days. |  |  | Region 1 | Gauteng South | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2022-10-28 | 2022-12-31 |  | ASP-GS0561 | CRTD: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-10-28 |  | 0 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | 0 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000373 | Highlands Warehouse Gate motor Anti thef | Installation of an anti theft bracket on gate motorA request has been made to install an anti theft bracket on the gate motor at the rear of the parking as a preventative measure. This is as a result of a recent security risk assessment conducted.Note: Approved by CRES VP. Scope of Work Supply and install new steel anti theft bracket over gate motor as per Absa Security requirement. Work will be carried out during normal working hours for 1 day. Material Leadtime: + 5 days. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-10-26 | 2022-11-30 |  | ASP-GS0562 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | F |  | GAMIETR | 2022-10-31 |  | 225.43 | Approved | 100 | 2022-10-27 | 2023-10-07 | 2592.45 |  | {"MANDT":"111","REFERENCE":70000373,"ONEVIEW":"37006X","DATE01":"2022-08-17","DATE02":"2022-08-24","DATE03":"2022-09-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062733 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000634 |  |  |  |  | 2023-01-20 | 2592.45 | 0 |  |  | C000046533 | 2254.3 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000374 | Vereeniging Dilaps - Phase 2 | Remove all loose furniture Data and telephone equipment All security equipment, the alarm and access control; Remove all Absa internal signage; Remove all hygiene equipment; Provide current certificate of compliance Security guard not required for the duration of the works. Work will be carried out during normal working hours for duration of 15 working days Project cleaning services required Material Leadtime: +-14 working days. |  |  | Region 1 | Gauteng South | 77264X | 1000-70360-01 | Vereeniging-Cnr Merriman Ave & Leslie St-Vereeniging | N | 2022-10-14 | 2022-12-31 |  | ASP-GS0563 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2022 |  | L |  | GAMIETR | 2022-11-02 |  | 43438.92 |  | 100 | 2022-11-25 | 2022-11-25 | 43438.92 |  | {"MANDT":"111","REFERENCE":70000374,"ONEVIEW":"77264X","DATE01":"2022-08-05","DATE02":"2022-08-12","DATE03":"2022-09-02","DATE04":"2022-09-09","DATE05":"2022-09-30","DATE06":"2022-10-31","DATE07":"2022-12-03","DATE08":"2022-12-24","DATE09":"2023-02-07","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"238:7:21:7:21:31:33:21:45:24","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-31","FORECAST_END":"2022-12-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000052735 | PHASE11 | 2022-10-31 | 2022-12-05 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000589 |  |  |  |  | 2023-01-19 | 37772.97 | 0 |  |  | C000052735 | 37772.97 |  | 3704.36 |  | 0 | 0 |  | 0 |  | 0
70000375 | Install vinyl on double glass door (Retr | Install vinyl on double glass door (19991231ctive) This request seeks 19991231ctive approval for the installation of vinyl frosting at the entrance of the building on the double door at Absa Clearwater Office Park. This will prevent clients from looking through the glass door and in addition, create a uniform look and feel when entering the building. Note: Work was completed via INSOG process on W/O 30330844 / 408191660. Scope of works: Supply and apply vinyl frosting on double door. |  |  | Region 1 | Gauteng South | 77174X | 1000-70352-01 | Absa Clearwater Office Park, Cnr Christiaan de Wet Rd & Millennium Blvd, Roodepoort |  | 2022-10-31 | 2022-10-31 |  | ASP-GS0564 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-02 |  | 213.1 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000047954 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000376 | Install contravision to ATM door glass p | Install contravision to ATM door glass panel At Absa Primrose the wooden door leading to the ATM room has a glass panel where clients can see when employees are loading the ATM machines, this poses a security risk. A request was made for the glass panel to be frosted with contravision to allow more privacy.Note : Approved at RIF and Absa CRES. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Apply contravision on approximately 300 x 300mm ATM door glass panel. Security Guard to be provided for the duration of project. Work to take place during normal working hours and 1 day to complete. |  |  | Region 1 | Gauteng South | 76610X | 1000-70297-01 | Primrose Mall-Randfontein Rd-Germiston |  | 2022-10-31 | 2022-12-31 |  | ASP-GS0565 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-11-02 |  | 412.56 | Approved | 100 | 2022-11-02 | 2023-10-07 | 4744.49 |  | {"MANDT":"111","REFERENCE":70000376,"ONEVIEW":"76610X","DATE01":"2022-08-22","DATE02":"2022-08-29","DATE03":"2022-09-19","DATE04":"2022-09-26","DATE05":"2022-10-17","DATE06":"2022-10-31","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-31","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062849 | PHASE11 | 2022-10-31 | 2023-05-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000630 |  |  |  |  | 2023-01-20 | 4744.49 | 0 |  |  | C000047956 | 4125.64 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000377 | Installation of x5 Red Plugs in the Bank | Installation of x5 Red Plugs in the Banking hall (19991231ctive) The branch requires x4 red plugs to be installed by customer services and x1 red plug by bulk cash teller. Business is being impacted when there is load shedding as the PC s switch off. Note : Work was completed on 12 October 2022 via the INSOG process: W/O 303783136 BFM PO 4500773415.Scope of works: Supply and install 2x 4 Red plugs and plates. Issue COC on completion. |  |  | Region 1 | Gauteng South | 77326X | 1000-70365-01 | Absa Southgate Mall, Shop L305-306, Southgate Mall, cnr Columbine Avenue (M68) and Rifle Range Road, Johannesburg |  | 2022-10-01 | 2022-10-31 |  | ASP-GS0566 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-02 |  | 279.16 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000050598 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000378 | Replace banking hour decal and desk stan | Replace banking hour decal and desk stands required (19991231ctive)A request was made to replace the Banking hour decal with new as the information requires to be updated. Supply of new A4 desk stands, these are needed display information for the client. A call was logged via the INSOG process 303782455Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Work was completed on 19 October 2022.Scope of Work Remove old decal, prepare surface and install new decal (x1) Desk stand to be supplied and delivered (x2) |  |  | Region 1 | Gauteng South | 36102X | 1000-70181-01 | Absa New Market, Shop 46-47, Mall at Newmarket, cnr Ring Road East and Voortrekker Road, Alberton |  | 2022-10-01 | 2022-12-31 |  | ASP-GS0569 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-02 |  | 479.62 | Approved | 100 | 2022-10-27 | 2023-10-07 | 5515.63 |  |  |  |  | C000062789 | PHASE11 | 2022-10-01 | 2022-12-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 6342.97 | 0 |  |  | C000047008 | 4796.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000379 | Replacement of burst geyser (19991231cti | Replacement of burst geyser (19991231ctive Insurance)The geyser at Absa Southgate Mall had burst and required immediate replacement. A call was logged via the INSOG process for the installation of a new geyser. Note : Supported by CRES VP. INSOG Insurance process followed. Work was completed 26 July. W/O 3033385 , PO 408305385,Scope of Work Supply and install 100 litre geyser. |  |  | Region 1 | Gauteng South | 77326X | 1000-70365-01 | Absa Southgate Mall, Cnr Rifle Range Rd & Columbine Ave, Mondeor |  | 2022-10-31 | 2022-12-31 |  | ASP-GS0570 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-04 |  | 891.9 | Approved | 100 | 2022-11-02 | 2023-10-07 | 10256.88 |  |  |  |  | C000062850 | PHASE11 | 2022-10-31 | 2022-12-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 11795.41 | 0 |  |  | C000047957 | 8919.03 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000380 | Floor tile replacement on external stair | Floor tile replacement on external staircase.The existing floor tiles on the external staircase at 270 Republic Road corporate building are cracked and have significantly deteriorated , the existing tiles specification cannot be replaced as there are no longer manufactured. The existing tiles are to be removed and a new Absa Spec tile is to be laid down with non slip strips . Note: Approved by CRES VP. Specification supported by Absa Design. On site security will be utilised for this project as work will happen on the outside of the building.Scope of Work Uplift existing floor tiles & tile fix 80m2 Cut and Fit New Tiles Lake Stone Grey ,size: 900 x 450mm 80m2 Grout and smooth finish of joints Fit non Slip Strip to Tile Treads Construct a small concrete ramp to level out with the tiles Remove rubble off site. Work will take place during normal working hours on weekends over 3 days |  |  | Region 1 | Gauteng South | 21335X | 1000-70026-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2022-10-26 | 2022-12-31 |  | ASP-GS0571 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 2022 |  | F |  | GAMIETR | 2022-11-07 |  | 6509.98 | Approved | 100 | 2022-11-10 | 2023-10-07 | 74864.83 |  | {"MANDT":"111","REFERENCE":70000380,"ONEVIEW":"21335X","DATE01":"2022-08-17","DATE02":"2022-08-24","DATE03":"2022-09-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-10-26","DATE07":"2023-03-22","DATE08":"2023-04-12","DATE09":"2023-05-27","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-26","FORECAST_END":"2023-03-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062997 | PHASE11 | 2022-10-26 | 2023-03-22 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000565 |  |  |  |  | 2023-01-20 | 74864.83 | 0 |  |  | C000049681 | 65099.85 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000381 | Supply of Alpha plugs on various desk Ph | Supply of Alpha plugs on various desk Phase 2Due to the restacking at Auckland Park Call Centre a request was made for all plugs to be checked and it was found that the plug socket modules at various desk were vandalised and need to be replaced. Phase 2 is for the replacement 278 of these plug sockets.Note: Approved by CRES. Supported by BFM Engineering.Scope of Work Supply and install Alpha Plugs (x278) On site engineering team to install the plugs. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-10-14 | 2022-12-31 |  | ASP-GS0572 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-07 |  | 40732.56 |  | 100 | 2022-11-10 | 2022-11-10 | 0 |  |  |  |  | C000050258 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000382 | Replace damaged raised floor panels at D | Replace damaged raised floor panels at Data Centre (19991231ctive) On the 5th March 2022 one of the technicians fell through the raised flooring at the data centre 1st floor white space at 270 Republic Road. An investigation was conducted as this could have lead to more staff being injured. A reactive call was logged to replace the damaged rasied floor panels. Note: Supported by BFM Engineering. Work was completed on the 05 April 2022. The work was completed via the INSOG process W/ O 409175134Scope of Work Systematically open each and every panel to visually identify cause of uneven floor or potential hazards Systematically open raised flooring, replaced damaged under structure if required, re glue under structure to the sub floor where other contractors have knocked them loose, replace damaged raised floor panels, snag and level access floor. |  |  | Region 1 | Gauteng South | 21335X | 1000-71363-01 | 270 Republic Road, 270 Republic Road, Randburg |  | 2022-10-31 | 2022-10-31 |  | ASP-GS0573 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-07 |  | 7787.5 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000049677 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000383 | Install x2 heat detectors at the recycli | Install x2 heat detectors at the recycling area (19991231ctive) A new in vessel composter was installed at the compactor area at Absa Towers North, however no heat sensors were installed above the unit. A request was made to install two heat detectors as part of compliance requirements. Note: Work was completed 04 May 2022 via the INSOG Process : 303578918 W/O 409177934 Scope of works: Install heat detectors (x2) |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2022-10-31 |  |  | ASP-GS0574 | CRTD: |  | false | false |  |  |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-07 |  | 0 |  | 100 | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000063016# | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-01-20 | 8665.05 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000384 | Install pendant lights at the coffee bar | Install pendant lights at the coffee bar (19991231ctive) The coffee bar collapsed in December 2021 at Absa Towers West and a request was made for the installation of new pendant lights as the previously ones were damaged when the coffee bar collapsed.Note: Work was completed on the 31 March 2022. Work was completed via the INSOG process 303570893 W/O 409161065 BFM PO 4500725241. Scope of Work Supply and install 400mmJG 12 CH Chrome 240v pendant lights (x5) |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West, 15 Troy Street, Johannesburg |  | 2022-10-31 | 2022-10-31 |  | ASP-GS0575 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-07 |  | 2815.48 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000050597 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000385 | Procurement of x3 soft serve machines fo | Procurement of x3 soft serve machines for the employee dining restaurants (CIP 2022)This request seeks approval to procure soft serve machines for x3 Absa Corporate Sites. Based on the operational requirements at Absa Alice Lane North, Absa Towers West and Absa 270 Republic Road a request was received to procure soft serve ice cream machines as an additional offering to employees. Note: Approved CRES VP. As per the agreement, there is a responsibility of 100% to be paid by Absa. The cost for each machine isR 43 642.50 incl.VAT.Scope of works: Supply of x3 Soft Servce Ice Cream Machines for various Absa Corporate Sites as listed below: Absa Alice Lane North Absa Towers West Absa 270 Republic Road |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-11-07 | 2022-12-31 |  | ASP-GS0580 | REL BUDG AVAC SETC: |  | false | true |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-10 |  | 11385 |  | 100 | 2022-11-10 | 2022-11-10 | 0 |  |  |  |  | C000062998 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 113850 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000386 | Install plugs for fridges (19991231ctive | Install plugs for fridges (19991231ctive) A request was made to install plugs for the fridges in the Wellness Centre Clinic at Absa 270 Republic Road.Note: Work was completed on the 06 August 2021. Work was completed via the INSOG process W/O 408376475 BFM PO 4500671260.Scope of Work Supply and install 4 X 4 normal plugs(x 2) Supply and install 4 X 4 wall box (x 1) |  |  | Region 1 | Gauteng South | 21335X | 1000-71363-01 | Absa 270 Republic Road, 270 Republic Road, Randburg |  | 2022-08-01 | 2022-12-31 |  | ASP-GS0581 | CLSD BUDG ACPT AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-11 |  | 247.56 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000049680 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000387 | Supply and install new Building Manageme | Supply and install new Building Management System (BMS) at Equinox CentreAt Alice Lane North Equinox centre, the BMS system has not been in operation since 2020. A decision was made not to remediate due to the BMS upgrade project. An assessment of the system was carried out by OEM. A new control system panel will be manufactured off site and will take 14 days to build ,install and commission.Scope of Work Supply and installation of smart controller with 320I/O point license Supply and installation of 24V power supply Supply and installation of 16 Digital Input Module Supply and installation of 8 Digital Output Module Supply and installation of 8 Universal Input, 6 Universal Output Module Supply and installation of panel revamp, rewiring and parts Supply and installation of Industrial 8 port switch in distribution panel Supply and installation of CAT5E Cable Installed Supply and installation of power cable for network panels System installation and commissioning Graphical generation Work will be done during normal working hours. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-10-14 | 2022-11-30 |  | ASP-GS0582 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-11-13 |  | 43466.68 |  | 100 | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000063011 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 434666.81 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000388 | Supply and Install new TV screen for int | Supply and Install new TV screen for internal client suitesA request was made to replace the current TV screen, which is currently faulty, the screen is powering on but the LCD is not working. This screen is utilised to guide clients to the correct boardrooms. An assessment was conducted, and it was recommended that the screen be replaced with new.Note: Scope of Work Supply and install new Samsung 50 Professional Display UHD, 24/7 Usage. |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-11-07 | 2022-12-31 |  | ASP-GS0583 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-13 |  | 1455.5 |  | 100 | 2022-11-10 | 2022-11-10 | 0 |  |  |  |  | C000062999 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 14555 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000389 | 268 Republic Rd Replacement of existing R22 hideaway uni | Replacement of existing R22 hideaway unit with an R410 (Item for noting)A request has been made to replace the current aircon unit in Block A Ground floor at the ATM lab. The unit was installed in the year 2000 and is no longer working. It has reached end of life and needs to be replaced with new similar 90 000 BTU unit. Note: Supported by BFM Eng. Approved Out of Cycle on Work completed on 13/11/2022. Gas & Equipment Disposal certificates will be supplied. No GMP Cost Impact. Scope of works: Replace existing R22 hideaway unit with an R410 (Dun ham Bush). Work will be carried out on a weekend. On site security guard will be utilised for the duration of the works. Material Leadtime: + 1 day. |  |  | Region 1 | Gauteng South | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg | N | 2022-11-07 | 2022-12-31 |  | ASP-GS0585 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | F |  | GAMIETR | 2022-11-15 |  | 17082.75 | Approved | 100 | 2022-11-17 | 2023-10-07 | 196451.69 |  | {"MANDT":"111","REFERENCE":70000389,"ONEVIEW":"21334X","DATE01":"2022-08-29","DATE02":"2022-09-05","DATE03":"2022-09-26","DATE04":"2022-10-03","DATE05":"2022-10-24","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-01-21","DATE09":"2023-03-31","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062515 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000520 |  |  |  |  | 2023-01-19 | 196451.69 | 0 |  |  | C000051185 | 170827.56 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000390 | Replace of external flood lights at Vil | Replace of external flood lights at Villa of Hope Childrens HomeA request was made to replace all the existing flood lights that are faulty and not working at the Villa of Hope Childrens Home. Note: Work scheduled to start on the 23/11/2022.Scope of works: Remove the existing floodlights (x35) Supply 100w LED Floodlights and provide warranty certificate (x35) Install poles and lights (x35) Hire Cherry picker (x1) |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-11-20 | 2022-12-15 |  | ASP-GS0588 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-21 |  | 6983.15 |  | 100 | 2022-11-24 | 2022-11-24 | 0 |  |  |  |  | C000053145 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000391 | Supply and install a cover for an existi | Supply and install a cover for an existing cat ladderThis request is for the supply and installation of a cover for the cat ladder onsite . As per the security risk assessment that was conducted, this will be a preventative measure from allowing anyone to gain access to the roof. Note: Supported by CRES VP. AFS support obtained. Supply and install a cover for the cat ladder (x1) Security guard not required for the duration of the works. Work will be carried out during normal working hours for duration of one day Material Leadtime: + 6 working days. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-11-23 | 2022-12-31 |  | ASP-GS0589 | REL BUDG AVAC SETC: |  | false | false |  | << To be Determined >> |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-11-24 |  | 1928.94 |  | 100 | 2022-11-24 | 2022-11-24 | 0 |  |  |  |  | C000066529 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-02-07 | 19289.49 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000392 | Clearwater O/P Installation of X 2 new s | Replacement of 2x new solid doors with view panelsThis request seeks approval to replace the existing two doors with new solid doors which include view panels. The existing doors in the passage leading to the ablutions do not have view panels, resulting in the staff constantly bumping into each other with the doors as its not visible whether someone is behind the door for an entry or exit.Note: Supported by CRES VP. BFM Eng and OHS support obtained. BFM ESM confirmed the airflow and the ventilation wont be affected.Scope of works: Remove existing doors (x2) Installation of x2 new solid doors with view panels. Installation will be done during normal working hours. Material Leadtime: + 10 12 days. |  |  | Region 1 | Gauteng South | 77174X | 1000-70352-01 | Clearwater Office Park Building 4-Millenium Rd-Strubensvalley |  | 2022-11-23 | 2022-12-31 |  | ASP-GS0590 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-11-28 |  | 1483.73 | Approved | 100 | 2022-12-01 | 2023-10-07 | 17063 |  | {"MANDT":"111","REFERENCE":70000392,"ONEVIEW":"77174X","DATE01":"2022-09-14","DATE02":"2022-09-21","DATE03":"2022-10-12","DATE04":"2022-10-19","DATE05":"2022-11-09","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-01-21","DATE09":"2023-03-31","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000074875 | PHASE11 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000617 |  |  |  |  | 2023-03-17 | 17063 | 0 |  |  | C000074875 | 14837.39 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000393 | Replacement of stolen cables at Villa o | Replacement of stolen cables at Villa of Hope Childrens HomeThis request seeks approval for the replacement of cabling. A request was made to replace all the existing flood lights that are faulty and not working at the Villa of Hope Childrens Home. During the replacement of the flood lights the supplier discovered that there was a missing cable near the boundary wall lights, which they assume was stolen. They will not be able to get all the lights working near the boundary wall without the cable being replaced. Note: Supported by CRES VP.Scope of works: Supply and install 2,5mm x2 core black norsk cable(x200) Supply and install 2,5mm x3 core black norsk cable (x10) |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-12-01 | 2022-12-31 |  | ASP-GS0591 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-12-01 |  | 861.2 |  | 100 | 2022-12-01 | 2022-12-01 | 0 |  |  |  |  | AWAIT PO | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000394 | WiFi infrastructure upgrade This request | WiFi infrastructure upgrade This request seeks approval to upgrade the WiFi infrastructure at Absa Auckland Park to support the call centre consolidation strategy and the CRES disposal strategy. The existing infrastructure will not be able to support the additional teams moving into the call centre at Auckland Park from Quadrum where a lease break will be exercised, and where Absa is planning on disposing of buildings at Towers North. Note: Supported by CRES VP. Absa Networks will provide the 40 x APs and CRES will pay for the labor, trunking, and related installation of cabling that will support the APs.Scope of works: Supply and install access points (x40) |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2022-12-01 |  |  | ASP-GS0592 | CRTD: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-12-01 |  | 0 |  | 100 | 2022-12-01 | 2022-12-01 | 0 |  |  |  |  | 0 | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000395 | Absa Durban City - Installation of autom | Absa Durban City Installation of automated roller shutter and trelli slam gates Absa Durban City has previously experienced a series of break in s. With the first incident occuring in August 2019, as a result a Meta wall was installed at the area where the burglary access was gained in order to mitigate this. In May 2021 and February 2022 two break ins occured where two TVs were stolen in both incidents simultaneously through the shopfront. The region approved a proposal of preventing further burglaries at the branch and enhance the security by installing an automated roller shutter door at the main entrance of the bank and trelli gates at the two shopfronts facing the street.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB and Absa Security have agreed to split the cost and they both will be funding this project as follows. Supported by Absa Finance.RBB: R 187 723,77 Africa Security: R 187 723,77Total Request: R 375 447,53Scope of Works: Supply and install 7800 mm x 3000 mm solid mix with perforated roller shutter door with an automated system and battery back up (3 Phase power supply) with overide chain for power outages. Issuing of COC for new electriacal motor power supply from DB. Supply and install new white Multiguard Pro with slam lock to shopfront along Consulting area 1 (7803mm x 3347mm) Supply and install new white Multiguard Pro to shopfront along Consulting area 2 (8700mm x 2707mm) Provision made for extra security Covid 19 deep clean to be conducted upon completion. |  |  | Region 3 | KwaZulu-Natal | 77987X | 1000-71206-01 | Absa Durban City,291 Anton Lembede Street,Durban |  | 2021-07-08 |  |  | ASP-KZ0098 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NGIDIN | 2021-07-07 |  | 32647.61 |  | Approved | 2022-06-15 | 2022-06-15 | 0 |  |  |  |  | C000022941 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000396 | Waterproofing | Waterproofing |  |  | Region 3 | KwaZulu-Natal | 76944X | 1000-71148-01 | Absa Port Shepstone |  | 2022-04-29 | 2022-05-31 |  | ASP-KZ0148 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-01-25 |  | 6025.27 |  | Approved | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2905352 | CLOSED | 2022-04-29 | 2022-05-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000397 | Demountable Disposal | Demountable Disposal |  |  | Region 3 | KwaZulu-Natal | 78700X | 1000-71227-01 | Absa Madadeni |  | 2022-02-09 | 2022-03-31 |  | ASP-KZ0150 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-10 |  | 42801.93 |  | Approved | 2022-02-11 | 2022-02-11 | 0 |  |  |  |  | 2901613 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000398 | Installation of blinds to close off 2x T | Installation of blinds to close off 2x Teller Counters (CIP 2022)Absa Stanger branch has a total of six teller counters. Due to Covid 19 social distancing regulations, two of these counters are no longer in use, and have been requested to be closed off. The request is to install blinds to close off the unused teller counters. Note: Approved at RIF. Scope of works: Supply & Install blinds to close off 2x teller counters. Branch cleaner to conduct wipe down |  |  | Region 3 | KwaZulu-Natal | 77928X | 1000-71201-01 | Whitehouse Centre-Chief Albert Luthuli St-Stanger |  | 2022-03-22 | 2022-04-29 |  | ASP-KZ0151 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-16 |  | 1883.36 |  | 100 | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2908780 | IGNORE | 2022-03-22 | 2022-04-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000399 | Minor Works - Absa Davenport (CIP 2022)A | Minor Works Absa Davenport (CIP 2022)Absa Davenport were last revamped in 2018. The painting in the branch has faded due to numerous electrical maintenances work conducted and the kitchen units have deteriorated over time, and requires to be refurbished. This request is to repaint the internal walls in the entire branh with the new lux colours, replace ceilings tiles, refurbishment of kitchens and a provide a full merchandising kit.Note: Approved by RIF. Scope of works: Repaint the branch in the new Absa colours. (1800sqm) Replace all the ceiling tiles in the backing hall including ATM lobby and make good the flush plastered ceiling in ATM lobby. (382sqm) Sand and varnish counter tops and make good the worn out tops including the steel counter tops. Install 5litre Hydroboil in both the kitchens. Refurbish the kitchens on the ground and first floor and to include replacement of the floor and wall tiles. (73sqm) Branch to receive full new merchandising kit. COC to be issued on completion. |  |  | Region 3 | KwaZulu-Natal | 77015X | 1000-71153-01 | Glenwood-Brand Rd-Berea |  | 2022-04-21 | 2022-05-31 |  | ASP-KZ0152 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-16 |  | 31845.71 |  | 100 | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | C000059658# | IGNORE | 2022-04-21 | 2022-05-31 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-06 | 63785.69 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000400 | Minor Works - Absa Overport City (CIP 20 | Minor Works Absa Overport City (CIP 2022)The Overport branch was last revamped in 2013 with no other minor works since the revamp. As a result, the look and feel of the branch needs to be refreshed. The request is for the installation of new carpets, painting of the entire branch with the new Absa colours, new skirting and providing a full new merchandising kit. Note: Approved at RIF.Scope of works: Painting walls throughout the branch (683 m2) Install new metal and wooden skirtings (271m) Provide full new merchandising kit Covid 19 deep clean upon completion of the works |  |  | Region 3 | KwaZulu-Natal | 77931X | 1000-71202-01 | The Atrium Overport City-Ridge Rd-Berea |  | 2022-02-18 | 2022-03-31 |  | ASP-KZ0153 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-21 |  | 18237.03 | Approved |  | 2022-02-24 | 2023-10-07 | 78364.23 |  |  |  |  | C000060355 | PHASE11 | 2022-02-18 | 2022-03-31 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-10 | 68142.81 | 0 |  |  | 2904920 | 182370.32 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000401 | Minor Works - Absa Durban City (CIP 2022 | Replacement of carpets |  |  | Region 3 | KwaZulu-Natal | 77987X | 1000-71206-01 | Absa 291 Anton Lembede Street-Anton Lembede St-Durban |  | 2022-02-18 | 2022-03-31 |  | ASP-KZ0154 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | GAMIETR | 2022-02-21 |  | 43104.16 | Approved |  | 2022-02-24 | 2023-10-07 | 17572.12 |  | {"MANDT":"111","REFERENCE":70000401,"ONEVIEW":"77987X","DATE01":"2021-12-10","DATE02":"2021-12-17","DATE03":"2022-01-07","DATE04":"2022-01-14","DATE05":"2022-02-04","DATE06":"2022-02-18","DATE07":"2022-03-31","DATE08":"2022-04-21","DATE09":"2022-04-04","DATE10":"2022-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-02-18","FORECAST_END":"2022-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000068847 | PHASE11 | 2022-02-18 | 2022-03-31 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-02-17 | 15280.1 | 0 |  |  | 2904909 | 431041.68 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000402 | Replenishment of operational equipment | Replenishment of operational equipment for pause area (CIP 2022) |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Absa Ridgeside Regional Office |  | 2022-03-15 | 2022-03-15 |  | ASP-KZ0155 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-02 |  | 612.3 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2910160 | CLOSED | 2022-03-15 | 2022-03-15 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000403 | Installation of air conditioning for Bul | Installation of air conditioning for Bulk Tellers, Treasury and ATM room (Ad Hoc Request) |  |  | Region 3 | KwaZulu-Natal | 20988X | 1000-70173-01 | Absa Galleria Mall |  | 2022-03-11 |  |  | ASP-KZ0156 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-03-09 |  | 15416.51 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2907840 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000404 | Installation of drop safe | Installation of a drop safe |  |  | Region 3 | KwaZulu-Natal | 36235X | 1000-71131-01 | Boardwalk Shopping Centre-Kruger Rand Rd-Richards Bay |  | 2022-06-09 |  |  | ASP-KZ0157 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | CEASARS | 2022-04-25 |  | 12702.11 | Approved |  | 2022-05-12 | 2023-10-07 | 47405.56 |  | {"MANDT":"111","REFERENCE":70000404,"ONEVIEW":"36235X","DATE01":"2022-03-31","DATE02":"2022-04-07","DATE03":"2022-04-28","DATE04":"2022-05-05","DATE05":"2022-05-26","DATE06":"2022-06-09","DATE07":"2022-07-09","DATE08":"2022-07-30","DATE09":"2022-07-24","DATE10":"2022-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-09","FORECAST_END":"2022-07-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061822 | PHASE11 | 2022-06-09 | 2022-07-09 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-17 | 41222.23 | 0 |  |  | C000013069 | 127021.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000405 | Installation of a through-the-wall (TTW) | Installation of a through the wall (TTW) drop safeThe Cornubia branch currently clears ATM deposits and loads cash before branch opening or when the branch closes. To ensure better and increased efficiency on branch serviced devices (ATM s & Cash Accepting) and deposits being cleared timeously, a through the wall (TTW) drop safe is required to be installed. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Floor plans updated and approved by Absa design.Scope of works: Cut opening into existing wall between ATM room & treasury (550mm x 1450mm). Install new space saver drop safe. Make good wall. Provision made for additional security. Covid 19 deep clean to be conducted upon completion. |  |  | Region 3 | KwaZulu-Natal | 36268X | 1000-71135-01 | Cornubia Shopping Mall-Cornubia Blvd-Mount Edgecombe |  | 2022-05-09 | 2022-06-30 |  | ASP-KZ0158 | REL BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-25 |  | 4876.14 |  | 100 | 2022-05-12 | 2022-05-12 | 0 |  |  |  |  | C000059599# | IGNORE | 2022-05-09 | 2022-06-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-06 | 12942.33 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000406 | Minor Works - Paulpietersburg Branch (CI | Minor Works Paulpietersburg Branch (CIP 2022)Absa Paulpietersburg branch had a minor refresh in 2018. This request seeks approval to upgrade the kitchen area including the male and female ablution facilities. In addition, the branch requested chairs to be supplied for the customers in the waiting area and to install a awning that will provide covering for customers while queueing at the ATM area. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Remove old kitchen units and cart away (2.1m long cupboard with sink). Remove old vinyl floor tiles and cart away (2.5sqm). Supply and install new FloorworX Floorflex semi flexible vinyl floor tiles 300 x 300 x 1.6mm thick in Moor Grey finish (Colour code :MF25020) (2.5sqm). Remove existing male and female ablutions devices and replace with new. Supply x10 waiting area chairs. Install ATM awning on front facade. Provision for security for duration of project. Enhanced Covid 19 cleaning upon project completion. |  |  | Region 3 | KwaZulu-Natal | 77511X | 1000-71177-01 | Absa 17 High Street-High St-Paulpietersburg |  | 2022-06-01 |  |  | ASP-KZ0159 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | CEASARS | 2022-04-28 |  | 35466.94 | Approved |  | 2022-04-13 | 2023-10-07 | 141352.99 |  | {"MANDT":"111","REFERENCE":70000406,"ONEVIEW":"77511X","DATE01":"2022-03-23","DATE02":"2022-03-30","DATE03":"2022-04-20","DATE04":"2022-04-27","DATE05":"2022-05-18","DATE06":"2022-06-01","DATE07":"2022-07-01","DATE08":"2023-02-24","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-01","FORECAST_END":"2022-07-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060125 | PHASE11 | 2022-06-01 | 2022-07-01 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-31 | 122915.64 | 0 |  |  | C000019950 | 354669.46 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000407 | Replacement of AC piping - Insurance cla | Replacement of AC piping Insurance claim (19991231ctive)On 11 November 2021, the branch situated at 291 Anton Lembede Street reported that their aircon was not operational and a call was logged to urgently attend to this matter as this posed an OHS risk. Upon further investigation it was identified that the aircon piping was stolen. The contractor was given the go ahead to commence with repair work and to order long lead time items (2 x refnet kits) this specific item was only available from the manufacturer and to be couriered from Johannesburg.Note: Supported by Engineering. Work was done via INSOG process. WO no: 409018395 & PO no: 4500716666. Supplier payment processed on 2022.03.11.Scope of works: Re instate refrigerant piping including the Refnet kits on Mitsubishi systems Perform pressure tests and evacuations Fit galvanised sheet metal covers for the refrigerant piping as an additional layer of security (18m of 1.2mm galvanised sheet metal & 50kg of R140 gas, x4 refnet kits, 25mm piping ) Replace blown power circuits and PCB s Test and commission system. |  |  | Region 3 | KwaZulu-Natal | 77987X | 1000-71206-01 | Absa 291 Anton Lembede Street-Anton Lembede St-Durban |  | 2022-05-12 |  |  | ASP-KZ0160 | REL BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-03 |  | 17120.62 |  | 100 | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000060167 | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-09 | 171206.24 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000408 | Dilaps- Removal of security items & sign | Dilaps Removal of security items & signage |  |  | Region 3 | KwaZulu-Natal | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg |  | 2022-06-01 |  |  | ASP-KZ0161 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-03 |  | 15546.66 |  | 100 | 2022-05-04 | 2022-05-04 | 0 |  |  |  |  | C000017952 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000409 | Installation of directional signageAbsa | Installation of directional signageAbsa Field street was revamped in 2019. With the revamp, the branch entrance was repositioned from Field street to West Street. The customers are unaware of the new position of the branch entrance and are under the assumption that the branch is closed. This request is to install directional signage onto the external wall in Field street to direct clients to the new entrance of the branch. Note: Approved at RIF and Absa Design. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works: Supply and install new directional signage onto external wall (500mm x 500mm) at the old branch entrance. |  |  | Region 3 | KwaZulu-Natal | 77449X | 1000-71174-01 | Absa Field Street, cnr Joe Slove and Dr Pixley Kaseme Street, Durban |  | 2022-06-01 |  |  | ASP-KZ0162 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-04 |  | 157.62 |  | Approved | 2022-04-13 | 2022-04-13 | 0 |  |  |  |  | C000019957 | CLOSED | 2022-06-01 | 2022-06-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000410 | Minor Works - Absa Port Edward (CIP 2022 | Minor Works Absa Port Edward (CIP 2022) The existing infrastructure at Absa Port Edward has not been improved since the inception of the branch. As a result over time the teller counter tops have faded with visible scratches and dents. The shopfront decals are further peeling off and need to be replaced with new Absa graphics. The branch has also requested the provision of movable storage shelves to cater for the storage of office supplies. This project will cover the refurbishment of the counter tops, replacement of the shopfront decals, and provision of storage shelves.Note: Approved at RIF. Artwork approval obtained. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Sand and varnish teller counter tops Supply and install (3) storage shelves (supplied by Absa approved furniture supplier) Remove existing shopfront decals and replace with new graphics (3,5 x 2,5m) Manned guarding services for the duration of the project. Covid 19 enhanced clean to be conducted upon completion. |  |  | Region 3 | KwaZulu-Natal | 77893X | 1000-71199-01 | Port Edward Mall-Owen Ellis Dr-Port Edward |  | 2022-06-30 |  |  | ASP-KZ0163 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | CEASARS | 2022-05-06 |  | 8996.89 |  | 100 | 2022-06-23 | 2022-06-23 | 0 |  |  |  |  | C000060093# | IGNORE | 2022-06-30 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-09 | 9913.93 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000411 | Installation of Blinds (CIP 2022)This re | Installation of Blinds (CIP 2022)This request seeks approval for the installation of blinds at Absa Emgangeni. Concerns have been raised by staff members and the branch manager who is experiencing sun glare at midday causing discomfort inside the branch. The branch requested that blinds be installed at the customer service area on the shopfront in order to block out the sun glare. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Blinds installation as per Absa design specification.Scope of Works Supply and install Corona blockout blinds at customer services shopfront area (5 x 7,2m) |  |  | Region 3 | KwaZulu-Natal |  |  | Building not in our database |  | 2022-06-01 |  |  | ASP-KZ0164 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-06 |  | 3962.02 |  | 100 | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000061386 | IGNORE | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-13 | 39620.19 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000412 | Minor Works - Absa Ithala Centre Manguzi | Minor Works Absa Ithala Centre Manguzi (CIP 2022)At Absa Manguzi branch, minor refreshes were made approximately 5 years ago, however no improvements to the floor finishes and ceilings were made since inception. The existing floor tiles in the banking hall are worn and faded with visible chipping and the carpets in the front and back offices are stained at places, and can no longer be easily cleaned. The ceiling tiles in the entire branch also need to be replaced due to visible wearing. The minor works will improve the look and feel of the branch for the benefit of staff and customers.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Supported by Engineering. The LED installation will happen in conjunction with the minor works. Scope of works: Strip existing floor tiles and replace with new as specified (190m2) Strip existing carpet tiles and replace with new as specified (62,5m2) Strip existing skirting and replace with new as specified (136m) Strip existing ceiling tiles and replace with new as specified (252,5m2) Manned guarding services for the duration of the project. Covid 19 enhanced clean to be conducted upon completion. |  |  | Region 3 | KwaZulu-Natal | 77685X | 1000-71188-01 | Ithala Centre Manguzi-Main Rd-Manguzi |  | 2022-08-28 |  |  | ASP-KZ0165 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-12 |  | 42179.92 | Approved |  | 2022-06-09 | 2023-10-07 | 485069.14 |  |  |  |  | C000060169 | PHASE11 | 2022-08-28 | 2022-09-27 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-01-09 | 421799.25 | 0 |  |  | C000020303 | 421799.26 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000413 | Installation of vision panels on canteen | Installation of vision panels on canteen swing doorsA risk assessment was conducted in 2021 at the Ridgeside building and it was identified that the absence of vision panels on the canteen swing doors is an OHS risk. The swing doors in the canteen open both ways, causing a risk for persons on both sides of the doors. Installing vision panels will minimise this risk. Note: Approved by CRES, Request supported by Eng & FM. Project to be funded from external minor works underspend projects.Scope of Works: Remove existing canteen swing doors. Create new openings on doors (300mm x 400mm). Install new vision panel to previously removed doors using natural anodized frame and 6.38mm Intrude ruffe glass. Re install swing doors. Covid wipe down to be done on all touch points on completion. |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Absa Ridgeside Regional Office, William Campbell Dr, Umhlanga |  | 2022-06-15 |  |  | ASP-KZ0166 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | CEASARS | 2022-05-12 |  | 943.27 |  | Approved | 2022-04-26 | 2022-04-26 | 0 |  |  |  |  | C000019949 | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000414 | Minor Works - Absa Ulundi (CIP 2022)Absa | Minor Works Absa Ulundi (CIP 2022)Absa Ulundi has not received a refresh and still reflects the old corporate image.The carpets are stained and have loose strands which poses an OHS risk. Some of the tiles are cracked and faded, and the walls need to be repainted with the new Absa colours. The kitchen cupboards deteriorated over a period of time and needs to be replaced, and a new hydroboil will be installed. In addition to the above, a request was made to provide a new merchandising kit. This refresh will enhance the look and feel of the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Updated floor plan received. Like for like replacement, No GMP Cost Impact for the installation of the hydroboil. Scope of Works Strip and discard existing carpet tiles and replace with new Belgotex Hard Graft 500x500mm carpet tiles (120m2) Strip and discard existing vinyl floor tiles and replace with new FloorworX Floorflex 300x300mm vinyl tiles (40m2) Strip and discard existing skirting and replace with new aluminium skirting (230m) Prepare and paint all internal walls with specified Absa colours (750m2) Replace existing kitchen cupbaords with new as specified Replace non operational hydroboil with a new 5L Hydroboil with filtration kit, including COC. Supply new merchandising kit to the branch Allowance for security guarding for project duration |  |  | Region 3 | KwaZulu-Natal | 77891X | 1000-71198-01 | Ulundi Shopping Centre-Princess Mbakayi St-Ulundi |  | 2022-07-01 |  |  | ASP-KZ0167 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | CEASARS | 2022-05-16 |  | 43123.05 | Approved |  | 2022-09-22 | 2023-10-07 | 495915.14 |  | {"MANDT":"111","REFERENCE":70000414,"ONEVIEW":"77891X","DATE01":"2022-04-22","DATE02":"2022-04-29","DATE03":"2022-05-20","DATE04":"2022-05-27","DATE05":"2022-06-17","DATE06":"2022-07-01","DATE07":"2023-02-28","DATE08":"2023-03-29","DATE09":"2023-04-17","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-01","FORECAST_END":"2023-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000061723 | PHASE11 | 2022-07-01 | 2023-02-28 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-31 | 431230.56 | 0 |  |  | C000061723 | 431230.56 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000415 | Installation of worktop in ATM roomAbsa | Installation of worktop in ATM roomAbsa Hillcrest has recently taken over the servicing of the ATM s and thus requires a worktop to be installed in the ATM room. The worktop will accommodate a note counter and PC for the purposes of cashing up and capturing of relevant data. Engineering considerations have been made in terms of the HVAC and lighting as follows:fresh air intakes into the ATM room to be introduced as per the required standards and lux levels were tested and found to be satisfactory. The room has four ATM s and a 18000BTU midwall split unit. Note: Approved at RIF, Supported by Engineering. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Reconfigure existing HVAC to introduce fresh air into ATM room. Supply and deliver 1200mm seated worktop. Install (x1) dedicated plugpoint. Issue COC on completion. Make good wall and paint to match existing (8m2). |  |  | Region 3 | KwaZulu-Natal | 77291X | 1000-71164-01 | Pick & Pay Christians Village-Cnr Old Main & Inanda Rd-Hillcrest |  | 2022-07-01 |  |  | ASP-KZ0168 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | CEASARS | 2022-05-16 |  | 2702.7 | Approved |  | 2022-10-20 | 2023-10-07 | 31081.11 |  |  |  |  | C000062335 | PHASE11 | 2022-07-31 | 2022-08-21 | SIYANDA DLAMINI | Juanita Van Coller | 23000600 |  |  |  |  | 2023-01-18 | 27027.05 | 0 |  |  | C000062335 | 27027.05 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000416 | Solar Hot Water Heater Replacement with | Solar Hot Water Heater Replacement with Heat Pump Item for notingAbsa Ridgeside Regional Office currently has (6) rooftop solar water heater panels that preheat water to (x3) vessels for the purpose of hot water supply. These rooftop panels were requested to be removed by the Ridgeside Management Association with immediate effect. Further to this, the space currently being occupied by these solar water heater panels take up space that has been allocated to the impending Solar PV project. This system is to be replaced with a 12kW Heat Pump to feed the (3) existing vessels. Note: Approved by CRES and supported by BFM Energy. Approved OOC by CRES Engineering on 20 May 2022. Project to be funded from the cancelled Auckland Park Call Centre & Ridgeside HVAC optimisation through Cryogen project. Budgeted amount is R925k. Scope of works: Safely decommission, remove and store onsite the existing solar water heaters from the roof (redundant piping loop included) Installation and commissioning of a heat pump (Model: ALLWH120R410 Alliance) Graphical Interface with BMS including measuring points and alarms Associated electrical works with COC |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Absa Ridgeside Regional Head Office, 90 William Campbell Drive, Umhlanga |  | 2022-06-01 |  |  | ASP-KZ0171 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | CEASARS | 2022-05-20 |  | 10019.98 | Approved |  | 2022-05-25 | 2023-10-07 | 115229.76 |  |  |  |  | C000060366 | PHASE11 | 2022-06-01 | 2022-07-01 | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-10 | 100199.79 | 0 |  |  | C00001995 | 100199.8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000417 | Dilaps - Removal of Furniture | Dilaps Removal of Furniture |  |  | Region 3 | KwaZulu-Natal |  | 1000-71221-01 | Building not in our database |  |  | 2022-06-10 |  | ASP-KZ0174 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-06-10 |  | 0 |  | 100 | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000018454 | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000418 | Comprehensive Water Assessment and Grey | Comprehensive Water Assessment and Grey Water Systems Due Diligence (CIP 2022)As part of the Absa 2030 Environmental Action Plan EAP targets we are aiming to reduce utility water consumption and increase self generation of water in our buildings. Our water reduction target for 2030 is 100 Megalitres (ML) as of 2021 we have only achieved a reduction of 14ML. We have in the past installed successful alternative water sources and grey water harvesting systems in some of our buildings which have yielded great results in sites such as the Auckland Park Campus, Absa Towers North and Absa Towers West. The appointmet of Bidvest Facilities Management and SEM Solutions is required to conduct a comprehensive water assessment and grey water harvesting systems due diligence at Absa Ridgeside Regional Office. This assessment will include a site visit, a feasibility assessment, a recommendation report and sign off. The due diligence outcome will be used in scoping and sourcing for a water solution that is feasible at the site. Scope of Work Conduct a site walkabout (the following to be provided to SEM: building layout, Council water billing accounts and water reticulation schematics) Evaluation of significant water usage Assessment of the water reticulation, Data collection site water usage, source and profiling, Due diligence report with findigs of audit, Proposed solutions with feasibilities and initiave priorities Expected cost of initiatives implementation and projects financial benefits |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Absa Ridgeside Regional Office,90 William Campbell Dr, Umhlanga |  | 2022-10-01 |  |  | ASP-KZ0175 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Freeho |  | NOMNGANGAL | 2022-06-21 |  | 8672.3 |  | Approved | 2022-06-15 | 2022-06-15 | 0 |  |  |  |  | C000019955 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000419 | Minor Works- Absa Shelly Beach (CIP 2022 | Minor Works Absa Shelly Beach (CIP 2022)Absa Shelly Beach has requested the addition of semi private cubicle to cater for additional space needed by the staff to consult with customers. The cubicle will be constructed to match the existing cubicles at the branch and an existing workstation will be removed to accommodate for this change. The configuration is open top and is not closed off at the front, therefore no requirement for the consideration of HVAC and lighting as the designated space is already aligned in this regard. In addition to the above, a request was made to install new carpets, relocate existing signage and omnipod, and supply and install furniture that will be obtained from the Absa stores. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Engineering support obtained and layout approved by Absa Design.Scope of Work Remove existing workstation Strip and discard existing porcelain tiles and replace with Belgotex carpet tiles (6,5m2) Relocate existing signage and gestures to new position further down the same wall Relocate omnipod to new position Supply and install matching panel to create semi private cubicle (2x2,5m) Prepare and paint rear wall of new cubicle (9m2) Supply (x1) desk, (x1) staff chair, (x2) visitor chairs to the office (furniture to be obtained from stores) |  |  | Region 3 | KwaZulu-Natal | 77417X | 1000-71171-01 | Shelly Beach-East St-Shelly Beach |  | 2022-07-14 |  |  | ASP-KZ0176 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-06-21 |  | 10498.28 | Approved |  | 2022-10-20 | 2023-10-07 | 120730.22 |  | {"MANDT":"111","REFERENCE":70000419,"ONEVIEW":"77417X","DATE01":"2022-05-05","DATE02":"2022-06-02","DATE03":"2022-06-09","DATE04":"2022-06-09","DATE05":"2022-07-14","DATE06":"2022-11-21","DATE07":"2022-12-05","DATE08":"2023-01-19","DATE09":"2023-02-01","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-21","FORECAST_END":"2022-12-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062332 | PHASE11 | 2022-11-21 | 2022-12-05 | Siyanda Dlamini | floyd mofokeng | 23000535 |  |  |  |  | 2023-08-31 | 104982.8 | 0 |  |  | C000062332 | 104982.8 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000420 | Dilaps | Dilaps |  |  | Region 3 | KwaZulu-Natal | 21052X | 1000-71074-01 | Absa Ladysmith |  | 2022-07-18 | 2022-09-29 |  | ASP-KZ0177 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-07-07 |  | 5493.24 |  | Approved | 2022-07-12 | 2022-07-12 | 0 |  |  |  |  | C000024797 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000421 | Dilaps | Dilaps |  |  | Region 3 | KwaZulu-Natal | 77539X | 1000-71180-01 | Absa Nongoma |  | 2022-11-10 |  |  | ASP-KZ0179 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-07-27 |  | 10359.41 |  | Approved | 2022-08-03 | 2022-08-03 | 0 |  |  |  |  | C000061825 | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 |  |  |  |  | 2023-01-17 | 66174.78 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000422 | Minor Works- Absa Galleria (CIP 2022)Ab | Minor Works Absa Galleria (CIP 2022)Absa Galleria is in need of an additional office cubicle for the purposes of serving clients and conducting interviews. There is currently one cubicle at the branch, which is insufficient for fulfilling all customer related needs. As part of the works, the existing HVAC will be aligned to cater for the new cubicle and the configuration matching the existing cubicle in the banking hall. This will entail installation of a diffuser and return air grilles, as well as a fire detector. Fresh air considerations were made and aligned as per standard requirements. In addition to the above, a request was made to install block out vinyl around the cubicle and shopfront, including the supply of a new office desk and chairs that will be obtained from the Absa stores. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Engineering support obtained and layout approved by Absa Design. GMP Cost Impact for fire detector included. Scope of Works Construct new glass cubicle including glass door to serve as office (3x3m) Alignment of HVAC to new office cubicle (installation of diffuser with electrical power provision and wall controller, return air grilles) Installation of plug points (x2) normal, (x2) dedicated and IT points. Install fire detector (x1) Install block out vinyl around cubicle and shopfront Supply new desk for office Supply (x1) staff chair and (x2) visitor chairs |  |  | Region 3 | KwaZulu-Natal | 20988X | 1000-71073-01 | Galleria-Cnr Moss Kolnick & Arbour Rd-Amanzimtoti |  | 2022-09-01 | 2022-09-01 |  | ASP-KZ0181 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-07-28 |  | 13060.53 | Approved |  | 2022-10-20 | 2023-10-07 | 150196.14 |  |  |  |  | C000062334 | PHASE11 | 2022-11-21 | 2022-11-25 | NANDE MAQUBELA | floyd mofokeng | 23000526 |  |  |  |  | 2023-01-18 | 130605.34 | 0 |  |  | C000062334 | 130605.34 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000423 | The Absa Vryheid branch has recently rel | The Absa Vryheid branch has recently relocated from an Absa owned building to a new leasehold site. BFM has restored the building to a white shell, and divided the space into two shops (project number ALP KZ0005) and CRES has secured a lease with a new tenant. As part of the handover and to ensure full compliance, an electrical COC for the entire building is a requirement. This request seeks the approval of the variation which will cater for the electrical COC. |  |  | Region 3 | KwaZulu-Natal | 0 | 1000-71614-01 | Absa Vryheid |  | 2022-08-25 | 2022-08-25 |  | ASP-KZ0182 | CLSD BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-19 |  | 5764 |  | Approved | 2022-08-15 | 2022-08-15 | 0 |  |  |  |  | C000032669 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000424 | New Office Cubicle and ATM Room Worktop | New Office Cubicle and ATM Room Worktop Absa Empangeni has requested a new office cubicle to be installed at the branch for the purpose of conducting private client interviews. The branch currently has existing open cubicles which offer little privacy. The new office cubicle will be prefabricated in order to match the existing look and feel. In addition, the branch has requested that an ATM room worktop be installed to create sufficient working space for the clearing of ATM deposits. Note: Approved at RIF. Supported by BFM Eng. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works: Remove existing cubicle partitions Supply and install new office cubicle in place of existing partitions Supply and install new ATM room worktop Provision made for additional project security |  |  | Region 3 | KwaZulu-Natal | 37109X | 1000-71708-01 | Empangeni 8 Smith Street |  | 2022-09-29 |  |  | ASP-KZ0183 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-22 |  | 17111.74 | Approved |  | 2022-08-19 | 2023-10-07 | 196785.06 |  |  |  |  | C000061039 | PHASE10 | 2023-06-02 | 2023-06-13 | NANDE MAQUBELA | Juanita van Coller | 23000519 |  |  |  |  | 2023-01-12 | 171117.44 | 0 |  |  | C000032666 | 171117.45 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000425 | Replacement of IntelCab UPS and Batterie | Replacement of IntelCab UPS and Batteries The existing unit were installed in 2018. A complaint was received from the branch about the UPS in the IntelCab being offline during load shedding. Intelcab was contacted and a technician was despatched to the branch. After testing, the UPS was found to be faulty. A loan UPS unit was installed and the existing was sent to the OEM for assements. As per the OEM multiple damages have occured to the UPS and as such cannot be repaired and requires replacement. Scope of Works Decommission and remove failed batteries. Supply and install 9PX/SX8 11 KVA and 11000 VA 200 250V Rack/Tower Supply and Install Eaton 11kVA UPS module (x1) Commission newly installed batteries and provide commissioning data with proof of completion form. Disposal of UPS & batteries and certificate to be supplied. |  |  | Region 3 | KwaZulu-Natal | 77417X | 1000-71171-01 | Absa Shelly BeachAbsa HouseEast StreetShelly Beach |  | 2022-09-01 | 2022-09-29 |  | ASP-KZ0186 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-08-25 |  | 9774.82 |  | 100 | 2022-08-25 | 2022-08-25 | 112410.46 |  | {"MANDT":"111","REFERENCE":70000425,"ONEVIEW":"77417X","DATE01":"2022-06-23","DATE02":"2022-06-30","DATE03":"2022-07-21","DATE04":"2022-07-28","DATE05":"2022-08-18","DATE06":"2022-09-01","DATE07":"2022-09-29","DATE08":"2022-10-20","DATE09":"2022-10-16","DATE10":"2022-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-01","FORECAST_END":"2022-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZQ==","RATING":""} |  |  | C000033641 | PHASE11 | 2022-09-01 | 2022-09-29 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 97748.23 | 0 |  |  | C000033641 | 97748.23 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000426 | Install New Banking Hour Decals (CIP 202 | Install New Banking Hour Decals (CIP 2022)At Absa Liberty Mall, recently changed their banking hours and the existing banking hours shopfront decal needs to be changed in order to reflect the new hours. The new hours take effect from 1 September 2022. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgetScope of Works Remove existing banking hour decals at the shopfront Supply and install new banking hour decals to the shopfront |  |  | Region 3 | KwaZulu-Natal | 77948X | 1000-71203-01 | Absa Liberty Mall PietermaritzburgShop 90 Liberty Midlands MallSanctuary RdPietermaritzburg |  | 2022-09-15 | 2022-09-15 |  | ASP-KZ0187 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-01 |  | 555.5 |  | 100 | 2022-09-08 | 2022-09-08 | 6388.25 |  | {"MANDT":"111","REFERENCE":70000426,"ONEVIEW":"77948X","DATE01":"2022-07-07","DATE02":"2022-07-14","DATE03":"2022-08-04","DATE04":"2022-08-11","DATE05":"2022-09-01","DATE06":"2022-09-15","DATE07":"2022-09-15","DATE08":"2022-10-06","DATE09":"2022-10-30","DATE10":"2022-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-15","FORECAST_END":"2022-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZQ==","RATING":""} |  |  | C000037352 | PHASE11 | 2022-09-15 | 2022-09-15 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 5555 | 0 |  |  | C000037352 | 5555 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000427 | Installation of worktop in ATM roomAbsa | Installation of worktop in ATM roomAbsa Bluff has recently taken over the servicing of the ATM s and thus requires a worktop to be installed in the ATM room. The worktop will accommodate a note counter and PC for the purposes of cashing up and capturing of relevant data. Engineering considerations have been made in terms of the HVAC and lighting as follows: fresh air intakes into the ATM room to be introduced as per the required standards and lux levels were tested and found to be satisfactory. The room has four ATM s and a 18000BTU midwall split unit. Note: Approved at RIF, Supported by Engineering. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Configure existing HVAC to introduce fresh air into ATM room. Supply and deliver 1200mm seated worktop. Install (x1) additional plugpoint . Issue COC on completion. Make good wall and paint to match existing 8m2. |  |  | Region 3 | KwaZulu-Natal | 77346X | 1000-71167-01 | Bluff Hillside Mall-Cnr Tara & Greys Inn Rd-Bluff |  | 2022-10-24 |  |  | ASP-KZ0190 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-12 |  | 2238.44 | Approved | 100 | 2022-10-20 | 2023-10-07 | 25742.11 |  | {"MANDT":"111","REFERENCE":70000427,"ONEVIEW":"77346X","DATE01":"2022-08-15","DATE02":"2022-09-12","DATE03":"2022-09-19","DATE04":"2022-09-19","DATE05":"2022-10-24","DATE06":"2022-11-23","DATE07":"2022-12-14","DATE08":"2023-01-28","DATE09":"2023-01-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-23","FORECAST_END":"2022-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZQ==","RATING":""} |  |  | C000062338 | PHASE10 | 2022-11-23 | 2022-12-14 | NANDE MAQUBELA | Juanita Van Coller | 23000604 |  |  |  |  | 2023-01-18 | 22384.44 | 0 |  |  | C000062338 | 22384.44 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000428 | Minor Works- Absa Davenport - Constructi | Minor Works Absa Davenport (VO)This request seeks the approval for the variation order amount of R 70 373.44 including VAT. This request is in order to refurbish the ground and first floor kitchens at Absa Davenport as part of the Minor Works project that is currently in progress, reference ASP KZ0152. The upgrade of the kitchens were originally not included in the scope of works for the minor works project, however the client requested that this upgrade form part the minor works project currently underway. The original amount of R 366 225,72 incl VAT was approved at CB05 for the minor works at the branch. The total VO amount required is R 70 373.44 incl. VAT and the total cost amount for the project will be R 436 599,16.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Strip and discard existing floor tiles, replace with new as specified (9m2) Strip and discard existing wall tiles, replace with new as specified (5m2) Strip and discard existing kitchen units, replace with new as specified Prepare and paint walls grey (27m2) Supply and install new 5L Hydroboil with plug point. Provide COC on completion. Covid 19 enhanced clean to be conducted upon completion. |  |  | Region 3 | KwaZulu-Natal | 77015X | 1000-71153-01 | Absa Davenport |  | 2022-10-06 |  |  | ASP-KZ0191 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-12 |  | 6119.42 | Approved |  | 2022-06-15 | 2023-10-07 | 70373.43 |  | {"MANDT":"111","REFERENCE":70000428,"ONEVIEW":"77015X","DATE01":"2022-07-28","DATE02":"2022-08-04","DATE03":"2022-08-25","DATE04":"2022-09-01","DATE05":"2022-09-22","DATE06":"2022-10-06","DATE07":"2022-11-05","DATE08":"2022-11-26","DATE09":"2022-11-20","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-06","FORECAST_END":"2022-11-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000062743 | PHASE11 | 2022-10-06 | 2022-11-05 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 61194.29 | 0 |  |  | C000062743 | 61194.29 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000429 | Dilaps | Dilaps |  |  | Region 3 | KwaZulu-Natal | 22338X | 1000-71093-01 | AVAF Trade Centre-Hunter St-Durban |  | 2022-10-20 |  |  | ASP-KZ0192 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-19 |  | 20054.25 |  | 100 | 2022-10-07 | 2022-10-07 | 17706.84 |  | {"MANDT":"111","REFERENCE":70000429,"ONEVIEW":"22338X","DATE01":"2022-08-11","DATE02":"2022-09-08","DATE03":"2022-09-15","DATE04":"2022-09-15","DATE05":"2022-10-20","DATE06":"2022-11-19","DATE07":"2022-12-10","DATE08":"2023-01-24","DATE09":"2023-01-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-19","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZQ==","RATING":""} |  |  | C000062123 | PHASE10 | 2022-11-19 | 2022-12-10 | NANDE MAQUBELA | Juanita van Coller | 23000518 |  |  |  |  | 2023-01-18 | 15397.25 | 0 |  |  | C000042630 | 200542.55 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000430 | Install lockable cupboard doors This req | Install lockable cupboard doors This request seeks approval to install lockable cupboard doors to the shelving in the storeroom. A request was made by the branch for the provision of storeroom space to store IT equipment. A stockroom on the third floor 3,30 was identified as suitable space for IT however, the room is a shared space utilised by various business units. In order to dedicate a portion of this space for IT Equipment, Merchant Services have agreed to share the space provided that doors and locks are installed to their shelving cupboards within their space. Note: Approved by Cres VP. This cost will be funded from the Absa IT cost centre. SA:600759Scope of Works Supply and install new wooden lockable cupboard doors to match existing (1000mm x 650mm). (x8) |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2022-10-27 | 2022-10-31 |  | ASP-KZ0193 | REL BUDG AVAC SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | F |  | NOMNGANGAL | 2022-10-03 |  | 1123 | Approved |  | 2022-10-13 | 2023-10-07 | 12914.5 |  |  |  |  | C000062341 | PHASE11 | 2022-11-22 | 2022-11-18 | NANDE MAQUBELA | Juanita Van Coller | 23000620 |  |  |  |  | 2023-01-18 | 11230 | 0 |  |  | C000062341 | 11230 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000431 | Installation of new banking hour decalsA | Installation of new banking hour decalsAbsa Bluff has recently changed their banking hours. As such, the existing banking hours shopfront decal needs to be changed in order to reflect the new hours for the benefit of customers. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Remove existing banking hour decals at the shopfront Supply and install new banking hour decals to the shopfront (1000mm x 700mm) |  |  | Region 3 | KwaZulu-Natal | 77346X | 1000-71167-01 | Bluff Hillside Mall-Cnr Tara & Greys Inn Rd-Bluff |  | 2022-11-04 |  |  | ASP-KZ0194 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-10 |  | 490.05 | Approved | 100 | 2022-10-13 | 2023-10-07 | 5635.58 |  | {"MANDT":"111","REFERENCE":70000431,"ONEVIEW":"77346X","DATE01":"2022-08-26","DATE02":"2022-09-02","DATE03":"2022-09-23","DATE04":"2022-09-30","DATE05":"2022-10-21","DATE06":"2022-11-04","DATE07":"2022-12-04","DATE08":"2022-12-25","DATE09":"2022-12-19","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-04","FORECAST_END":"2022-12-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZQ==","RATING":""} |  |  | C000062342 | PHASE11 | 2022-11-04 | 2022-12-04 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-18 | 4900.5 | 0 |  |  | C000062342 | 4900.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000432 | Supply of yellow wheelie bin (19991231ct | Supply of yellow wheelie bin (19991231ctive)After construction, the Cornubia branch did not receive a yellow bin for storage of grey water. Due to the current water shortage as a result of water restrictions implemented in the eThekwini municipality and various ongoing repairs, the branch often find itself without water. The procurement and placement of a wheelie bin will ensure that branch has at least 200 litres of grey water available in the event of water disruption.Note: Approved by Cres VP. Work Order No:409606778.Purchase Order: 4500757363.Work Completed: 2022/08/24.Invoice capture date: 2022/08/17Scope of Work Supply and deliver new wheelie bin (x1) 200 Litres |  |  | Region 3 | KwaZulu-Natal | 36268X | 1000-71135-01 | Absa Cornubia,Shop U68Cornubia Mall,Cnr Allamanda and Tecoma Rd |  | 2022-10-13 |  |  | ASP-KZ0196 | CLSD ISBD AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-11 |  | 0 |  | Approved | 2022-09-28 | 2022-09-28 | 0 |  |  |  |  | C000042941 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000433 | Supply of yellow wheelie bin (19991231ct | Supply of yellow wheelie bin (19991231ctive)After construction, the branch did not receive a yellow bin for storage of grey water. Due to the current water shortage as a result of water restrictions implemented in the eThekwini municipality and various ongoing repairs, the branch often find itself without water. The procurement and placement of a wheelie bin will ensure that branch has at least 200 litres of grey water available in the event of water disruption.Note: Approved by Cres VP. Work Order No:409606778.Purchase Order: 4500757362.Work Completed: 2022/08/24.Invoice capture date: 2022/09/01Scope of Work Supply of yellow wheelie bin (x1) 200 Litres |  |  | Region 3 | KwaZulu-Natal | 37169X |  | Absa Midway CrossingA225 NtuzumaMidway Crossing |  | 2022-10-13 |  |  | ASP-KZ0197 | CLSD ISBD AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-11 |  | 0 |  | Approved | 2022-09-28 | 2022-09-28 | 0 |  |  |  |  | C000042962 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000434 | Supply of yellow wheelie bin (19991231ct | Supply of yellow wheelie bin (19991231ctive)The Absa La Lucia branch did not receive a yellow bin for storage of grey water. Due to the current water shortage as a result of water restrictions implemented in the eThekwini municipality and various ongoing repairs, the branch often find itself without water. The procurement and placement of a wheelie bin will ensure that branch has at least 200 litres of grey water available in the event of water disruption.Note: Approved by Cres VP. Work Order No:409606793.Purchase Order: 4500757361. Work Completed: 2022/08/24.Invoice capture date: 2022/09/01Scope of Work Supply of yellow wheelie bin (x1) 200 Litres |  |  | Region 3 | KwaZulu-Natal | 76958X | 1000-71149-01 | Absa La Lucia,43 Armstrong AveLa Lucia |  | 2022-10-13 |  |  | ASP-KZ0198 | CLSD BUDG ISBD AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-11 |  | 180.4 | Approved |  | 2022-09-28 | 2023-10-07 | 2074.6 |  |  |  |  | C000061742 | PHASE11 | 2022-10-13 | 2022-11-12 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-17 | 1804 | 0 |  |  | C000061742 | 1804 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000435 | Supply of yellow wheelie bin (19991231ct | Supply of yellow wheelie bin (19991231ctive)After a revamp, the Absa Bluff branch did not receive a yellow bin for storage of grey water. Due to the current water shortage as a result of water restrictions implemented in the eThekwini municipality and various ongoing repairs, the branch often find itself without water. The procurement and placement of a wheelie bin will ensure that branch has at least 240 litres of grey water available in the event of water disruption.Note: Approved by Cres VP. Work Order No:409606806,Purchase Order: 4500757360, Work Completed: 2022/08/25,Invoice capture date: 2022/09/01Scope of Work Supply and deliver new wheelie bin (x1) 240 Litres |  |  | Region 3 | KwaZulu-Natal | 77346X | 1000-71167-01 | Absa Bluff,Hillside MallShop 32Cnr Tara and Olsen Road |  | 2022-10-13 | 2022-10-13 |  | ASP-KZ0199 | CLSD ISBD AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-11 |  | 0 |  | Approved | 2022-09-28 | 2022-09-28 | 0 |  |  |  |  | C000042964 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000436 | Removal of Internal and External Signage | Removal of Internal and External Signage (19991231ctive)The Landlord had scheduled demolition work in order to commence with the rebuild. The request was made to completely de brand the branch and to ensure signage was properly discarded. Note: Approved by Cres VP. Work Order No:408568964. Purchase Order: 4500685888. Work Completed: 2021/10/01. Invoice capture date: 2021/10/13Scope of Work Removal of all Absa branding. |  |  | Region 3 | KwaZulu-Natal | 21262X | 1000-71079-01 | Absa Bridge CityShop U39Cnr Nogwala and Phoenix RdBridge City Shopping Centre |  | 2022-10-13 | 2022-10-13 |  | ASP-KZ0200 | CLSD BUDG ISBD AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-11 |  | 0 |  | Approved | 2022-10-05 | 2022-10-05 | 0 |  |  |  |  | C000043690 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000437 | Drainage installationDuring the construc | Drainage installationDuring the construction of the Chatsworth branch, the ramp used for emergency exit was tiled in a way that creates a fall into the branch. This results in water entering the branch during rainy periods. This is a design/construction flaw that does not fall within the landlord space as the emergency exit door formed part of the branch build. Weather strips have proved to be unsuccessful and the solution is to install a drainage mechanism under the door which will act as a catchment, routing water away from the branch. Note: Approved at RIF. Supported by BFM Engineering. LL approval obtained. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Cut through tiles and remove section of concrete 450mm wide Supply and install purpose made mentis grid Suply and install 110mm UG pipe with outlet, including 90 degree elbow Make good floor upon completion |  |  | Region 3 | KwaZulu-Natal | 77567X | 1000-71183-01 | Chatsworth Centre-Joyhurst St-Chatsworth |  | 2022-10-28 | 2022-10-28 |  | ASP-KZ0201 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-13 |  | 28554.36 |  | 100 | 2022-10-27 | 2022-10-27 | 28554.36 | 08.08.2023 FM there is savings value into the project R695.65 | {"MANDT":"111","REFERENCE":70000437,"ONEVIEW":"77567X","DATE01":"2022-08-19","DATE02":"2022-09-16","DATE03":"2022-09-23","DATE04":"2022-09-23","DATE05":"2022-10-28","DATE06":"2022-10-28","DATE07":"2022-11-18","DATE08":"2023-01-02","DATE09":"2023-03-28","DATE10":"2023-04-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"217:28:7:0:35:0:21:45:85:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-28","FORECAST_END":"2022-11-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIFBPQyBwYWNrIHN1Ym1pdHRlZCB0byBGaW5hbmNlIG9uIDI0IE1hcmNoIDIwMjM=","RATING":""} |  |  | C000062745 | PHASE11 | 2022-10-28 | 2022-11-18 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-31 | 24829.88 | 0 |  |  | C000062745 | 24829.88 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000438 | Dilaps | Dilaps |  |  | Region 3 | KwaZulu-Natal | 77323X | 1000-71165-01 | Queensburgh Centre-Cnr Ridley Park & Old Main Rd-Queensburgh |  | 2022-10-24 | 2022-10-28 |  | ASP-KZ0202 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-19 |  | 1824.52 |  | 100 | 2022-10-18 | 2022-10-18 | 0 |  |  |  |  | C000062131# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-18 | 18245.29 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000439 | Installation of Worktop in ATM RoomAbsa | Installation of Worktop in ATM RoomAbsa Pavillion has recently taken over the servicing of the ATM s and thus requires a worktop to be installed in the ATM room. The worktop will accommodate a notecounter and PC for the purposes of cashing up and capturing of relevant data. Although the room currently has an 18000BTU midwall split unit, engineering indicated that fresh air supply into the room be catered for in order for compliance to be met. Considerations have thus been made in this regard. Lux levels were also tested and found to be compliant. Note: Approved by RIF. Supported by Engineering. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Introduction of fresh air into ATM room (installation of extractor fan and galvanised ducting) Install 1200mm seated worktop Install (x1) dedicated plugpoint Issue COC on completion Make good wall and paint to match existing (8m2) |  |  | Region 3 | KwaZulu-Natal | 77543X | 1000-71182-01 | The Pavillion Shopping Centre-Jack Martens Dr-Westville |  | 2022-10-28 | 2023-03-31 |  | ASP-KZ0203 | REL BUDG AVAC SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-19 |  | 4258.72 | Approved |  | 2022-10-27 | 2023-10-07 | 48975.35 |  |  |  |  | C000062739 | PHASE11 | 2022-11-13 | 2022-12-02 | NANDE MAQUBELA | Juanita Van Coller | 23000582 | [5 empty] | 42587.26 | 0 |  |  | C000062739 | 42587.26 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000440 | Dilaps | Dilaps |  |  | Region 3 | KwaZulu-Natal | 36214X | 1000-71130-01 | Gateway Theatre of Shopping-Palm Blvd-Umhlanga Ridge |  | 2022-11-10 |  |  | ASP-KZ0206 | REL BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-24 |  | 2246.22 |  | 100 | 2022-10-26 | 2022-10-26 | 0 |  |  |  |  | C000062739# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 42587.26 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000441 | Installation of burglar barsThe water ta | Installation of burglar barsThe water tank that supplies the branch at Absa Chatterton Road is situated on the outside of the branch along a main road. The water tank has been placed inside an open top enclosure with a lockable entrance door. Access into the space is still possible from the top of the enclosure and this has led to vandalism and the pump being stolen. In order to avoid the recurrence of this, the branch has requested that the area be further secured by installing burglar bars at the top of the enclosure to limit access into the space. Furthermore, the lock on the door will be secured to limit tampering. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and install burglar bar covering to top of Jojo tank enclsoure 25x25 mm frame with 10x10mm infills 110mm apart (hot dipped galvanised) Remove existing sheeting around door and install new, inclusive of barrel bolt cover (hot dip galvanised) |  |  | Region 3 | KwaZulu-Natal | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg |  | 2022-11-07 | 2022-11-11 |  | ASP-KZ0207 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-28 |  | 4467.32 | Approved |  | 2022-10-27 | 2023-10-07 | 51374.2 |  |  |  |  | C000062738 | PHASE11 | 2022-11-07 | 2022-11-11 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 44673.22 | 0 |  |  | C000062738 | 44673.22 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000442 | Painting of internal wallsThe Absa Ladys | Painting of internal wallsThe Absa Ladysmith branch is in need of new painting works to be implemented internally. The condition of the walls currently exhibits an uneven look, with patches of staining at places. In addition, the branch needs to reflect the new Absa colours in order to align to the current visual identity and improve overall look and feel for customer and staff.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Prepare and paint internal walls with new Absa colours (300m2) |  |  | Region 3 | KwaZulu-Natal | 21052X | 1000-71074-01 | 150 Murchison Street-Murchison St-Ladysmith |  | 2022-11-11 | 2022-11-15 |  | ASP-KZ0208 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-28 |  | 2709.78 | Approved |  | 2022-10-27 | 2023-10-07 | 31162.5 |  |  |  |  | C000062726 | PHASE11 | 2022-11-15 | 2022-12-06 | NANDE MAQUBELA | Floyd Mofokeng | 23000599 |  |  |  |  | 2023-01-20 | 27097.83 | 0 |  |  | C000062726 | 27097.83 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000443 | Supply of yellow wheelie bin (19991231ct | Supply of yellow wheelie bin (19991231ctive Insurance)During the July 2021 KZN riots the Branch was looted and the yellow wheelie bin was stolen. The branch was rebuilt and reopened in November 2021. During the April 2022 floods in KZN and the Municipal water infrastructure was severely damaged. It has now become a necessity to have a wheelie bin onsite to store water for when there is no water supply in the area.Note: Approved by Cres VP. Work Order No:409482152, Purchase Order:4500747055, Work Completed: 2022/07/22, Invoice capture date: 2022/10/11Scope of Work Supply and deliver new wheelie bin (x1) 240 Litres |  |  | Region 3 | KwaZulu-Natal | 77729X | 1000-71582-01 | Absa UmlaziShop V02Umlazi Mega City50 Mangosuthu Highway |  | 2022-10-27 |  |  | ASP-KZ0209 | CLSD BUDG AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-28 |  | 288.26 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000047855 | CLOSED |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000444 | Re-route of fresh air supply (19991231ct | Re route of fresh air supply (19991231ctive)The current fresh air supply grille to the branch is located in the service passage. When the adjoining tenant (Nandos) changes out or services their LP gas cylinders, the gas discharged from the lines is drawn through the Absa fresh air supply system and dispersed in the branch, posing an OHS risk. In order to alleviate this risk and preserve the quality of the fresh air supply into the branch, the fresh air intake will be moved to the side of the building. Note: Supported by BFM Engineering. Approved Out of Cycle on 10/11/2022. Work Completed on the 16/11/2022.Scope of Work Remove existing fresh air grille. Install new ducting sections, manufactured to suite configuration for recommended side intake position. |  |  | Region 3 | KwaZulu-Natal |  |  | Building not in our database |  | 2022-12-01 |  |  | ASP-KZ0211 | REL BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-09 |  | 1687.09 |  | 100 | 2022-11-24 | 2022-11-24 | 0 |  |  |  |  | C000063014# | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 16870.92 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000445 | Dilaps VO | Dilaps VO |  |  | Region 3 | KwaZulu-Natal |  |  | Building not in our database |  | 2022-11-30 | 2023-03-31 |  | ASP-KZ0214 | REL BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-16 |  | 4347.82 |  | 100 | 2022-11-16 | 2022-11-16 | 0 |  |  |  |  | C000063002 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 43478.26 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000446 | Dilaps | Dilaps |  |  | Region 3 | Limpopo | 76788X | 1000-70524-01 | Absa Modimolle |  | 2021-11-27 | 2021-12-31 |  | ASP-LP0105 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NGIDIN | 2021-11-27 |  | 4033.31 |  | Approved | 2022-03-02 | 2022-03-02 | 0 |  |  |  |  | 2906011 | CLOSED |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000447 | Installation of new 2500ltr water tank ( | Installation of new 2500ltr water tank (CIP 2022) |  |  | Region 3 | Mpumalanga |  | 1000-60722-01 | Building not in our database |  | 2021-12-06 | 2022-03-31 |  | ASP-LP0108 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2021-12-08 |  | 6299 |  | 100 | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | C000070259 | IGNORE |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 |  |  |  |  | 2023-02-24 | 62990 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000448 | Install bumper rail and replace ATM room | Install bumper rail and replace ATM room floor tiles (CIP 2022)Absa Thaba Mall was built in 2018 however it has an ATM room with vinyl floor tiles that are stained as a result of dye stain spillages and needs to be replaced. New bumper railing is also required on the side wall of one teller cubicle. Paint clean up to wall markings will be required before the bumper rail can be installed.Note: Approved at RIF.Scope of works: Prepare and paint wall area to the side of the teller where bumper rail is to be installed (15m2) Supply and install new bumper rail to the side wall of the teller counter. (1.5m) Supply and install floorworx floorflex semi flexible vinyl floor tiles 300 x 300 x 1.6mm thick. (7m2) Advanced covid clean to be carried out at the end of the project. Security Services for duration of project. |  |  | Region 3 | Limpopo | 37045X | 1000-70507-01 | Absa Thabazimbi, Shop 30B&33, Thaba Mall, Warmbad Weg (R510), Thabazimbi |  | 2022-02-01 | 2022-04-30 |  | ASP-LP0110 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 3533.49 |  | Approved | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904908 | CLOSED |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000449 | Minor Works - Absa Siyabuswa (CIP 2022)A | Minor Works Absa Siyabuswa (CIP 2022)Absa Siyabuswa was affected by fire in 2019 which originated from the butchery next to the branch. There after the repairs to the adjoining wall showed some hairline cracks on the plaster, potentially due to inadequate curing time before the plaster was painted. This started to show months later outside the defects liability period. To improve the aesthetics on final finishes the wall needs to be skeemed and repainted. In addition, all internal walls will require repainting with the new Absa lux colours to improve the look and feel of the branch. As part of this request selected areas will have ceiling tiles replaced with new. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets.Scope of works: Prepare and paint all previously painted walls in front and back of house areas with Absa lux colors. (625m2) Reception and pause area with Absa colour interior only. (120m2) Replace stained and darkened tiles in banking hall and ablution facilities with 1200x600 Georgian Armstrong ceiling tiles to match existing. (34m2) Advanced covid clean to be carried out at the end of the project. Security Services for duration of project. |  |  | Region 3 | Limpopo | 36259X | 1000-62572-01 | Absa Siyabuswa Mall, Shop 24, Siyabuswa Mall, Bongimfundo Road, Siyabuswa |  | 2022-02-01 | 2022-04-30 |  | ASP-LP0111 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 13282.67 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2907261 | CLOSED |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000450 | Minor Works - Absa Mookgopong (CIP 2022 | Minor Works Absa Mookgopong (CIP 2022).Absa Mookgopong kitchen units were installed in 2008 and have deteriorated over a period of time and require total replacement. The vinyl tiles in the ATM room are stained and require total replacement with new vinyl tiles. The above work will improve the look and feel of the branch. Note: Approved At RIF.Scope of works: Remove old kitchen units and cart away. (2.1m long cupboard with sink). Remove old vinyl floor tiles and cart away.(25m2) Supply and install new floorworX, floorflex semi flexible vinyl floor tiles 300 x 300 x 1.6mm (25m2). Supply and install new kitchen units in white melamine veneer with a single bowl sink, fitted into black counter top, complete with a mix tap, microwave unit slot above as per existing arrangement; bottom cabinet to have drawers and storage area for cutlery and to accommodate the existing Hydroboil unit. Total length of kitchen unit: Bottom 2.1m; Top 0.6m Covid 19 clean will be carried out at the end of the project. |  |  | Region 3 | Limpopo | 76711X | 1000-60884-01 | Absa Mookgophong, Earp Shopping Centre, Thabo Mbeki Street,Mookgophong |  | 2022-02-01 | 2022-04-30 |  | ASP-LP0112 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 5374.12 |  | Approved | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904912 | CLOSED |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000451 | Minor Works- Absa Mokopane (CIP 2022)Ab | Minor Works Absa Mokopane (CIP 2022)Absa Mokopane kitchen area was last revamped in 2018. The kitchen was fitted with wooden units which have currently deteriorated over time due to water seepage from the sink area. In addition to the above, the regional manager requested that the existing steel staff lockers be replaced with the multi coloured wooden lockers to align with the look and feel of the newer branches, install vinyl floor finishes in the kitchen and pause areas, and modular shelves in the store room to store cleaning material.Note: Approved at RIF.Scope of works: Supply and install new kitchen units in white melamine veneer with a single bowl sink, fitted into black counter top, complete with a mix tap, microwave unit slot and cupboard unit above, bottom cabinet to have drawers and storage area. Total length of kitchen unit: Bottom 3.0m; Top 3.8.0m Supply and install x21 staff multi colour lockers. Supply and install FloorworX Floorflex semi flexible vinyl floor tiles 300 x 300 x 1.6mm thick in Moor Grey finish (Colour code :MF2502),laid in FloorworX No.62 acrylic adhesive to kitchen and pause area (35m2) Provide single stack shelving to cleaners storeroom. Covid clean to be carried out at the end of the project. Security Services for duration of project. |  |  | Region 3 | Limpopo | 76721X | 1000-70668-01 | Mokopane-Thabo Mbeki St-Mokopane |  | 2022-02-01 | 2022-04-30 |  | ASP-LP0113 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 43443.77 |  | 100 | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904913 | IGNORE |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000452 | Minor Works - Absa Limpopo Mall (CIP 202 | Minor Works Absa Limpopo Mall (CIP 2022)Absa Limpopo Mall kitchen units were installed in 2014 and have deteriorated over a period of time and require total replacement. Further to that, the vinyl floor tiles to the pause are stained and requires to be replaced. This will improve the look and feel of the branch.Note: Approve At RIFScope of works: Remove old kitchen units and cart away. (5.3m long cupboards with a sink) Remove old vinyl floor tiles and cart away.(25sqm) Supply and install new FloorworX Floorflex semi flexible vinyl floor tiles (27sqm), 300 x 300 Supply and install new kitchen units in white melamine veneer with a single bowl sink, fittedt into black counter top, complete with a mix tap, microwave unit slot and cupboard unit above; bottom cabinet to have drawers and storage area for cutlery and to accommodate the existing Hydroboil unit. Total length of kitchen unit: Bottom 3.3m; Top 2.0m Covid 19 clean to be carried out at the end of the project. |  |  | Region 3 | Limpopo | 78979X | 1000-70547-01 | Limpopo Mall-Cnr Rissik, Market, Devenish & Kerk St-Polokwane |  | 2022-02-01 | 2022-04-30 |  | ASP-LP0114 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 6294.16 |  | 100 | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904922 | IGNORE |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000453 | Minor Works - Absa Elim Mall (CIP 2022)A | Minor Works Absa Elim Mall (CIP 2022)Absa Elim Mall was last refreshed in 2014. The existing wooden veneer inserts and cladding to walls in the banking hall, offices ATM area and teller areas are bulging due to high temperatures in the area. The bottom edges of the cladding are chipping out by customers kicking against the cladding while transacting or leaning against the walls. The recommendation is to replace all the veneer cladding and inserts with paint finish and to install ceramic tiles on the ATM area walls.Note: Approved at RIF.Scope of works: Remove all wooded veneer and cladding and cart away Prepare and paint all wall including walls previously cladded with wooden veneer. (659m2) Supply and paint customer focus walls in Absa Lux colours Supply and install 600x300 Absa grey porcelain tiles to wall around ATM facade. Covid 19 deep clean upon completion of project. Security Services for duration of project. |  |  | Region 3 | Limpopo | 35022X | 1000-60209-01 | Absa Elim , Shop 54, Elim Mall, R578 Main Road, Elim Mall |  | 2022-02-01 | 2022-04-30 |  | ASP-LP0115 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 15814.67 |  | Approved | 2022-02-24 | 2022-02-24 | 0 |  |  |  |  | 2904914 | CLOSED |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000454 | Painting of internal walls and Installat | Painting of internal walls and Installation of a push bar to emergency exit door (CIP 2022)Absa Bela Bela was last refreshed in 2014 and the existing internal walls are still reflecting the old Absa spec colours. This request is to repaint the internal walls in the customer focus areas with the new Absa lux colour to align with the latest Absa colour schemes. The repainting of the walls will enhance the look and feel of the branch.In addition, the fire exit door currently dont have a push bar and operates under lock and key with a break glass system. It was therefore recommended to install a new push bar to the emergency exit door as part of the compliance upgrade.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets, and the cost for the doors will be allocated against the compliance project.Scope of works: Painting to all internal walls and introduction of lux colours to customer focus areas.(835 m2) Supply and Install new push bar to emergency exit door. Touch Point clean to be carried out at the end of the project. Security Services for duration of project. |  |  | Region 3 | Limpopo | 76787X | 1000-70523-01 | Absa Bela- Bela, Bosveld Pick n Pay Centre, cnr Mark (R101) and Potgieter Road, Bela-Bela |  | 2022-03-30 | 2022-04-29 |  | ASP-LP0116 | CLSD BUDG ACPT AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 19136.94 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2907659 | CLOSED | 2022-03-30 | 2022-04-29 | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000455 | Supply and install staff lockers and a p | Supply and install staff lockers and a push bar to emergency exit door (CIP 2022)Absa Lephalale branch had a limited scope revamp in 2021, however the lockers for staff were not provided as part of the project. The employees currently do not have suitable storage space for their belongings during working hours. In addition, the fire exit door currently dont have a push bar and operates under lock and key with a break glass system. It was therefore recommended to install a new push bar to the emergency exit door as part of the compliance upgrade. This request seeks approval for the supply and installation of staff lockers and a new push bar to the emergency exit door.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budgets, and the cost for the doors will be allocated against the compliance project.Scope of works: Supply and install 21 X Multi colour staff lockers Supply and Install new push bar to emergency exit door. Touch Point clean to be carried out at the end of the installations Security Services for duration of project. |  |  | Region 3 | Limpopo | 76789X | 1000-70525-01 | Absa Lephalale, cnr Fox Odendaal and Plein street, Ellisras |  | 2022-03-30 | 2022-04-29 |  | ASP-LP0117 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-09 |  | 4120.84 |  | Approved | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 2907660 | CLOSED | 2022-03-30 | 2022-04-29 | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000456 | Minor Works - Absa Tubatse Crossing (CIP | Minor Works Absa Tubatse Crossing (CIP 2022)Absa Tubatse Crossing was built in 2015 and has since not received any refresh to internal finishes. The paint on the internal walls are scratched and stained, due to customers leaning against the walls. The following areas requires to be re painted,banking hall, customer service, cash areas, ATM room, entrance lobby, back office, bathrooms and store rooms. There are also cracked floor tiles at the pause and teller areas that need to be replaced. This refresh will enhance the look and feel of the branch.Note: RIF approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Paint to all internal walls introducing Absa Lux colours (621sqm) Paint to all painted doors to match existing (15sqm) Replace cracked tiles to pause area and tellers area (20sqm) Enhanced Covid clean at the end of the project The project will be carried out over a weekend and dedicated project security guard will be arranged. |  |  | Region 3 | Limpopo | 35151X | 1000-70488-01 | Tubatse Crossing-Cnr R37 & R555-Burgers Fort |  | 2022-06-02 | 2022-09-30 |  | ASP-LP0119 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-01 |  | 13937.68 |  | 100 | 2022-05-12 | 2022-05-12 | 0 |  |  |  |  | C000063004# | IGNORE | 2022-06-02 | 2022-09-30 | SIYANDA DLAMINI | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 23896.79 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000457 | Absa Lephalale - Sheltered Parking Bays | Absa Lephalale Sheltered Parking Bays (CIP 2022)The branch has existing sheltered staff parking and open parking for customers however, the staff parking available is inadequate to accommodate all staff vehicles therefore exposing the vehicles to inclement weather conditions. It has been proposed that (x6) public parking bays be installed with shelter structures and be converted into staff parking.Note: Supported by CRES VP and BFM ENG. Approved drawings obtained. Council approval obtained pending payment of municipality fees which are included in the request as part of the contractor bill.Scope of Works Excavate and cast concrete bases for the structural steel posts(x6) Erect new structural steel shelter over (x6) parking bays Supply and install powder coated IBR roof sheeting as covering Make good affected paved surfaces Provide traffic management services Settle all Municipality approval fees Structural Engineer to sign off on completion |  |  | Region 3 | Limpopo | 76789X | 1000-70525-01 | Absa Lephalale-Cnr Strydom & Fox Odendaal St-Lephalale |  | 2022-06-01 | 2022-09-30 |  | ASP-LP0120 | REL BUDG AVAC RESA: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Freeho |  | CEASARS | 2022-04-01 |  | 14490.39 |  | 100 | 2022-08-19 | 2022-08-19 | 0 |  |  |  |  | C000061012# | IGNORE | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Buhle Qwabe | 0 |  |  |  |  | 2023-01-12 | 144903.94 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000458 | Minor Works - Absa Kamaqhekeza (CIP 2022 | Minor Works Absa Kamaqhekeza (CIP 2022)Absa Kamaqhekeza was last refreshed in 2019 and the ceiling boards were not included in the refresh scope of work. The ceiling tiles have deteriorated and faded in colour over a period of time. The process to replace branch ceiling tiles will also require that all down lighters, fire detectors and security cameras mounted to ceiling tiles, be deinstalled and reinstalled onto the new ceiling boards. The ATM lobby has drop in ceiling tiles which are not ideal for use as external ATM area ceilings for branches and will therefore be upgraded to plaster board ceilings in line with Absa requirements for external ceilings. The ceramic tiles to the walls at the ATM lobby are delaminating and need to be replaced.Note: RIF approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. AFS support obtained. Supported by Engineering.Scope of works: Replacement of all branch ceiling boards with new (300sqm) Deinstallation of existing down lighters and install with LED down lighters (x45) Deinstallation and reinstallations of security cameras (x15) Deinstallation and reinstallation of fire detectors (x6) Replacement of drop in ceilings with plaster board ceilings at ATM lobby (24sqm) Replacement of wall tiles at ATM lobby (10sqm) Enhanced Covid clean to be carried out at the end of the project Project will be carried out over a weekend and dedicated project security will be arranged. |  |  | Region 3 | Mpumalanga | 77571X | 1000-70637-01 | Kamaqhekeza Plaza-Main Rd-Balfour |  | 2022-10-01 | 2022-11-30 |  | ASP-LP0121 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-04 |  | 19984.48 |  | 100 | 2022-05-12 | 2022-05-12 | 0 |  |  |  |  | C000124733 | IGNORE | 2022-10-01 | 2022-11-30 | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-11-20 | 74445.07 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000459 | Minor Works- Absa Tzaneen (CIP 2022)Absa | Minor Works Absa Tzaneen (CIP 2022)Absa Tzaneen High Volume Centre (HVC) was built in 2015 and has since not received any refresh to the wall and floor finishes. This is a cash handling facility with cash trollies and money bags being hauled across floors and often rubbing and bouncing against walls. These activities result in finishes dilapidating rapidly. All the carpets in offices, teller areas, and treasury need to be replaced. The ceramic tiles in the cash receiving area need to be replaced with high traffic tiles. The walls in the offices, teller and treasury areas need to be repainted. Aluminium trims are to be added to the wall corners along the trolley paths as a preventative measure to protect the wall from potential future damage.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Replace existing carpet to offices and teller areas (185m2). Paint all internal walls to offices, tellers and cash receiving areas to match existing (660m2). Replace damaged ceramic tiles in patches (10m2) Paint to all wooden doors to match existing (x13) Aluminium Trims to walls along cash movement routes.The work will be carried out over a weekend and dedicated project security will be arranged. |  |  | Region 3 | Limpopo | 76808X | 1000-70526-01 | Danie Joubert Street Tzaneen-Danie Joubert St Tzaneen Hotel-Tzaneen |  | 2022-08-01 |  |  | ASP-LP0122 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-09 |  | 28345.08 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000060728 | IGNORE | 2022-08-01 | 2022-09-30 | SIYANDA DLAMINI | Buhle Qwabe | 0 |  |  |  |  | 2023-01-11 | 31587.71 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000460 | Removal of Equipment: Deinstallation and | Removal of Equipment: Deinstallation and remove all internal and External signage, Deinstallation and removal of TVs, Deinstallation and removal of security equipment, Deinstallation and removal of safes,Deinstallation and removal of furniture including scrapping thereof. |  |  | Region 3 | Limpopo | 79124X | 1000-70554-01 | Absa Northam Plaza |  | 2022-08-01 | 2022-09-30 |  | ASP-LP0124 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-09 |  | 8494.79 |  | Approved | 2022-05-22 | 2022-05-22 | 0 |  |  |  |  | C000059841 | CLOSED | 2022-08-01 | 2022-09-30 | SIYANDA DLAMINI | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 8263.31 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000461 | Minor Works - Absa Senwabarwana (CIP 202 | Minor Works Absa Senwabarwana (CIP 2022)Absa Senwabarwana was last refreshed in 2020 and selected walls were painted with the new Absa Lux colours. The remainder of the walls in the banking hall, offices, cash areas, utility room, CIT delivery bay, back office, bathrooms and kitchens, ATM room and ATM lobby requires to be repainted as it has deteriorated over a period of time. In addition, the existing chairs for the customers and staff have also deteriorated and need to be replaced to enhance the look and feel of the branch. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Paint banking hall (396m2) Paint customers services area (54m2) Paint all offices (141m2) Paint ATM lobby and Utility room (32m2) Paint the Treasurery & ablution facilities (46m2) Paint CIT delivery area (18m2) Bench A purple back rest and red seat Replacement of chairs for the entire branch (x1) S29A Bench B orange backrest and pink seat (x1) S29B Omni POD chair upholstered in luxury poppy (x1) S32 Visitors chairs upholstered A (x2) S40A Visitors chairs upholstered B (x10) S40B Protective plastic cover over chairs (x13) SC1 8 bay staff locker unit (x1) F55 Net one mesh back operator chairs (x13) ST15.01 Standing teller chairs (x4) ST15.02 Tile Rugs (x12) Waiting area cofee table (x2) AB T14.1 Waiting area bench AB S13A Provision made for security services*There is a lead time of 6 8 weeks on all furniture orders. The Paint work will be carried out over the weekend. |  |  | Region 3 | Limpopo | 22539X | 1000-70473-01 | Blouberg Mall-Blouberg Rd-Bochum |  | 2022-07-01 |  |  | ASP-LP0125 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-16 |  | 43403.05 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000060801# | IGNORE |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 |  |  |  |  | 2023-01-11 | 75517.71 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000462 | Generator Exhaust ModificationThe Genera | Generator Exhaust ModificationThe Generator exhaust is currently blowing onto the landlord s wall leaving an unsightly stain. The landlord has escalated this threatening legal action. A site visit was conducted, and a modification agreed upon. Note: Supported by CRES Engineering. Scope of works Modify existing generator exhaust by making use of 90mm, 90 degree bend pipe and wall brackets, u bolt clamps and elbows. |  |  | Region 3 | Limpopo | 76787X | 1000-70523-01 | Bushveld Pick & Pay Centre-Cnr Mark & Potgieter St-Bela Bela |  | 2022-07-04 | 2022-07-05 |  | ASP-LP0127 | REL BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-06-16 |  | 1406.04 |  | 100 | 2022-06-23 | 2022-06-23 | 0 |  |  |  |  | C000060103 | IGNORE |  |  | Siyanda Dlamini | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 14060.47 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000463 | Replacement of furniture (CIP 2022)Absa | Replacement of furniture (CIP 2022)Absa Elim Mall was refreshed in April 2022, however the furniture in the branch were included in the scope of work. The current chairs in the customer and staff area has worn out and in a deteriorated condition. The request was made by regional management to replace the chairs to enhance the look and feel of the branch . Note : Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works:Supply and installation of new furniture pieces as follows: Pause Area Chairs red (x7) S42A 8 Bay Staff Locker Unit (x1) F56 NetOne Mesh Back Operators Chairs (x12) ST15/01 NetOne Standing Teller Chairs (x2) ST15/02 Visitors Chairs (x11) S40A & S40B Omni POD Chair (x1) S32 Waiting area coffee table Single (x 1) Waiting area staggered rug (x2) A1.3C* There is a lead time of 6 8 weeks on all furniture orders. |  |  | Region 3 | Limpopo | 35022X | 1000-70483-01 | Elim Mall-Cnr Giyani & Levubu Rd-Elim |  | 2022-09-01 | 2022-09-01 |  | ASP-LP0130 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-07-28 |  | 18016.69 |  | 100 | 2022-08-04 | 2022-08-04 | 207192.04 |  | {"MANDT":"111","REFERENCE":70000463,"ONEVIEW":"35022X","DATE01":"2022-06-23","DATE02":"2022-06-30","DATE03":"2022-07-21","DATE04":"2022-07-28","DATE05":"2022-08-18","DATE06":"2022-09-01","DATE07":"2022-09-01","DATE08":"2023-02-28","DATE09":"2023-03-31","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-01","FORECAST_END":"2022-09-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"cHJvamVjdCBjb21wbGV0ZWQgYW5kIGNsb3NlZA==","RATING":""} |  |  | C000030691 | PHASE11 | 2022-09-01 | 2022-09-01 | Siyanda Dlamini | Juanita van Coller | 0 |  |  |  |  | 2022-08-11 | 180166.99 | 0 |  |  | C000030691 | 180166.99 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000464 | Dilaps | Dilaps |  |  | Region 3 | Limpopo | 79124X | 1000-70554-01 | Northam Plaza-Cnr Rustenburg Rd & R510-Thabazimbi |  | 2022-09-08 | 2022-11-24 |  | ASP-LP0131 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-10 |  | 4335.77 |  | 100 | 2022-09-29 | 2022-09-29 | 0 |  |  |  |  | C000061971 | IGNORE |  |  | Siyanda Dlamini | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 43357.75 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000465 | Installation of electrical Surge Protect | Installation of electrical Surge Protection (19991231ctive)The branch and mall evacuated due to the facility being engulfed in smoke. Upon investigation, it was discovered that the primary winding of the indoor fan motor on the indoor unit had failed due to overheating and that this was the cause of the smoke. The indoor airconditioning unit had been extensively damaged which was replaced, it was therefore recommended that surge protection be installed urgently on the main Absa electrical distribution board to prevent further damage during such electrical anomalies. Note: Supported by BFM Engineering. INSOG Request approved by CRES Engineering. Work was completed as INSOG request on the 13 July 2022. Purchase Order 4500742501 was issued and the service was completed. (Insurance process followed)Scope of Works Supply and install Surge protection and lighting arrestors. |  |  | Region 3 | Limpopo | 76707X | 1000-70559-01 | Absa Ba-PhalaborwaShop 45 Eden SquareCnr Palm and President StreetPalaborwa |  | 2022-09-08 |  |  | ASP-LP0132 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-30 |  | 1300 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000034717 | CLOSED |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000466 | Install Bumper rail and Painting Absa Le | Install Bumper rail and Painting Absa Lephalale branch has offices that were not fitted with bumper rails as part of the original design. It has been observed over time that occasionally the client chairs rub against the walls resulting in consequential damage to wall surfaces. Bumper rails are therefore recommended as a solution to the wall damage caused by the chairs. This is being applied on a case by case basis as in the consultant office in this branch where customer chairs are the cause for severe damage to the wall they lean against. Some remedial paint work will also be required before installation of the bumper rail.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Prepare and paint affected wall in consultant office match existing (12m2) Supply and installation bumper rail (1,5m long) Final Clean to affected floor finishes No additional security required |  |  | Region 3 | Limpopo | 36103X | 1000-70666-01 | Lephalale Mall-Cnr Nelson Mandela Dr & Chris Hani Ave-Lephalale |  | 2022-10-20 | 2022-10-20 |  | ASP-LP0133 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 2536.62 |  | 100 | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039896 | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000467 | Replace cracked floor tiles and remediat | Replace cracked floor tiles and remediate ceiling boards at ATM Lobby.This request seeks approval for the replacement of the cracked floor tiles and remediate ceiling boards. The floor tiles are showing continuous cracks in various places due to misplaced joint strips. It is therefore required that the floor tiles be removed and be re laid to align the tile joints strips with the original concrete floor slab joint strips. This will include tiling within the pause area through to the ablution facilities area. In addition to the above, the plaster board ceilings at the ATM lobby are sagging and need to be rectified. This will require that the existing board be cut and finished to match existing.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. BFM Engineering Support obtained.Scope of Work Hack off ceramic floor tiles and tile joint strips in patches (42m2) Supply and installation of 330x330 ceramic floor tiles (42m2) Supply and installation of tile joint strips to align with concrete slab tile joints (40m) Remediate sagging plaster board ceilings at ATM lobby (2.5m2) Paint the entire plaster board ceilings to match existing (25m2) Final Clean to work area Provision has been made for a Project Guard for the duration of the project |  |  | Region 3 | Limpopo | 36251X | 1000-70667-01 | Absa Groblersdal Mall,Shop 6Groblersdal MallVan Riebeeck StreetGroblersdal |  | 2022-10-20 | 2022-10-20 |  | ASP-LP0134 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 9763.83 | Approved | 100 | 2022-09-22 | 2023-10-07 | 14246.22 |  |  |  |  | C000061734 | PHASE11 | 2022-10-20 | 2022-10-20 | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 14246.22 | 0 |  |  | C000039897 | 97638.32 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000468 | Refurbishment of ATM Lobby Floor, Wall a | Refurbishment of ATM Lobby Floor, Wall and Ceiling At Absa Mankweng branch, the ATM facilities lobby is located at a different location from the branch s premises. The ATM lobby has UPVC floor tiles and white painted perimeter walling including drop in ceiling boards that are badly stained, and requires to be refurbished. It has been recommended that the UPVC floor tiles be replaced with porcelain floor tiles for durability and the wall areas be tiled to a height of 2100mm for ease of maintenance and to prevent potential staining from customers leaning against the walls. The fading and stained ceilings will be painted with white PVA ceiling paint to restore their original aesthetics.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Hack off UPVC tiles to ATM lobby and cart away Supply and install 300x600 anti static floor porcelain tiles to wall to a height of 2100mm Supply and install 600x600 porcelain floor tiles Prepare and paint ceilings to ATM lobby in white PVA ceiling paint (75m2) Allowance for cleaning upon completion Allowance have been made for project security guard |  |  | Region 3 | Limpopo | 76781X | 1000-70520-01 | Absa MankwengShop E2Turfloop PlazaUniversity RoadMankweng |  | 2022-10-20 |  |  | ASP-LP0135 | CLSD BUDG ACPT AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 18253.66 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000061784 | CLOSED |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 29645.62 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000469 | Replacement of Teller Counters and paint | Replacement of Teller Counters and paint to wallsAbsa Malamulele was refreshed in 2018 however the two teller counters in the branch are still the standing teller module and present challenges to staff members of shorter stature. There are no seated teller counters in this branch. It has been recommended that the two standing teller counters be replaced with two new seated teller counters to accommodate both staff and customers with height challenges. Further to that the paint to adjacent walls to the tellers as well as the ATM room walls have deteriorated and need to also be refreshed. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Dismantle and cart away existing teller counters (x2) Supply and installation new seated teller counters (x2) Supply and installation Electrical and data power points to new teller counters Prepare and paint walls to tellers and ATM room Make good affected finishes Final cleaning upon completion of work Allowance has been made for a project guard |  |  | Region 3 | Limpopo | 76784X | 1000-70500-01 | Mangalani Shopping Centre-Cnr Giyani & Malamulele Rd-Malamulele |  | 2022-10-20 | 2022-10-20 |  | ASP-LP0136 | REL BUDG AVAC SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-09-16 |  | 22650.74 | Approved | 1 | 2022-10-05 | 2023-10-07 | 260483.61 |  |  |  |  | C000062054 | PHASE06 | 2022-10-20 | 2022-11-10 | NANDE MAQUBELA | Floyd Mofokeng | 23000513 |  |  |  |  | 2023-01-18 | 260483.61 | 0 |  |  | C000062054 | 226507.49 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000470 | Floor tiles and Paint to ATM Room and Ut | Floor tiles and Paint to ATM Room and Utility Room (CIP 2022)Absa Lephalale was refreshed in 2020 however the ATM room and server room wall and floor finishes were not included in the scope of work. The floor and wall finishes have deteriorated and need to be rejuvenated. It is recommended that the floor tiles and wall paint in both the ATM room and Utility room be redone to a fresh look. The project will take two days to complete and will be carried out over a weekend.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Absa IT Support obtained.Scope of Work Hack off upvc tiles in ATM room and Utility room and cart away. Supply and installation Upvc floor tiles to ATM room and Utility Rooms. Prepare and paint walls in ATM room and Utility room To match existing. Final clean to work area the end of the project. Provision has been made for project security guard. |  |  | Region 3 | Limpopo | 76789X | 1000-70525-01 | Absa Lephalale-Cnr Strydom & Fox Odendaal St-Lephalale |  | 2022-10-20 | 2022-10-20 |  | ASP-LP0137 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 7096.58 |  | 100 | 2022-10-05 | 2022-10-05 | 0 |  |  |  |  | C000061968 | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-17 | 70965.83 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000471 | Replacement of burnt Air conditioning Un | Replacement of burnt Air conditioning Unit and Installation of a surge protection (19991231ctive)The branch were required to evacuated the building due to the facility being covered in smoke. Upon investigation, it was discovered that the primary winding of the indoor fan motor on the indoor unit had failed due to overheating and that it was the source of the smoke. Based on these findings, it was found that due to the irregularity of power supplied by the Municipality recently, this contributed to the failing of the winding of the motor. The entire indoor unit was extensively damaged and required urgent replacement. A surge protection was installed urgently on the main Absa electrical distribution board to prevent further damages during such electrical anomalies. Note: Supported by BFM Engineering. The work was done via the INSOG process and insurance claim was logged : WO 409515590.Scope of Works Remove and replace existing air conditioning unit with a Dunham Bush 60 000 BTU inverter ducted air conditining unit. Install a 250A class 2 surge protection with fuses. Dispose off old unit and provide disposal certificate. |  |  | Region 3 | Limpopo | 76709X | 1000-70559-01 | Absa Ba -PhalaborwaShop 45Eden SquareCnr Palm Street and Nelson MandelaPhalaborwa |  | 2022-09-22 | 2022-09-23 |  | ASP-LP0141 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-23 |  | 4991.84 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039616 | CLOSED |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000472 | Replacement of Staff LockersAbsa Maake | Replacement of Staff LockersAbsa Maake Plaza staff lockers are old, broken, and cannot be repaired. It has been recommended that new staff lockers be provided to replace the old units.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and install (x8) compartment staff lockers |  |  | Region 3 | Limpopo | 22530X | 1000-70472-01 | Maake Plaza-Cnr R36 & Main Rd-Tzaneen |  | 2022-11-03 | 2022-11-30 |  | ASP-LP0143 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 1555.75 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062792 | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 15557.53 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000473 | Replacement of Staff LockersAbsa Mookgo | Replacement of Staff LockersAbsa Mookgopong staff lockers are old, broken and cannot be repaired. It has been recommended that new staff lockers be provided to replace the old units.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and install (x8) compartment staff lockers |  |  | Region 3 | Limpopo | 76711X | 1000-70516-01 | Earp Shopping Centre-Thabo Mbeki St-Polokwane |  | 2022-11-03 |  |  | ASP-LP0144 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 1102.88 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062724# | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 11028.81 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000474 | Upgrade to customer services modesty pan | Upgrade to customer services modesty panelsAbsa Mankweng customer service area has modesty panels that allow airflow underneath which is causing discomfort to staff members working at these service points during winter. It is recommended that the modesty panels at the customer service area be replaced with full drop modesty panels and install kick plates to the lower end of the modesty panels.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove exiting modesty panels and cart away (x3) Supply and install (x3) new full drop modesty panels with kick plates |  |  | Region 3 | Limpopo | 76781X | 1000-70520-01 | SSC Turfloop Plaza Mankweng-Cnr University St & Houtbosdorp Rd-Polokwane |  | 2022-11-03 | 2022-11-30 |  | ASP-LP0145 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 1183.95 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062720# | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 11839.56 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000475 | Installation of Signage to ATM LobbyAbsa | Installation of Signage to ATM LobbyAbsa Mankweng branch has an ATM facilities lobby that is located at a different location from the branch premises. The ATM lobby has no visibility from the street and it has been recommended that a projecting sign be installed at the entrance to the ATM lobby. The signage will also be connected to a power isolator.Note: Approved at RIF. Approved by Absa design. LL approval obtained . This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Work Install cantilevered lightbox 700 x 740mm COC to be issued on completion. No project security guard required (external work)Material Leadtime: 6 Weeks |  |  | Region 3 | Limpopo | 76781X | 1000-70520-01 | SSC Turfloop Plaza Mankweng-Cnr University St & Houtbosdorp Rd-Polokwane |  | 2022-11-30 | 2022-11-30 |  | ASP-LP0146 | REL BUDG AVAC RESA: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-02 |  | 3794.61 |  | 100 | 2022-11-24 | 2022-11-24 | 0 |  |  |  |  | C000062480 | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-19 | 37946.11 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000476 | Replacement of Graphic Signage to Shopfr | Replacement of Graphic Signage to ShopfrontAbsa Malamulele was refreshed in 2018 with lifestyle graphics applied to the shopfronts. The graphic printed signage to the shopfront has dilapidated and is peeling off and recommended to be replaced.Note: Approved at RIF. Approved by Absa design. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Like for like replacement.Scope of Work Hack off and cart away existing Lifestyle Graphics x 60m2 Install Lifestyle Graphics x 60m2 No project security guard required (external work)Material Leadtime: 6 Weeks |  |  | Region 3 | Limpopo | 76784X | 1000-70522-01 | Mangalani Shopping Centre-Cnr Giyani & Malamulele Rd-Malamulele |  | 2022-11-30 |  |  | ASP-LP0147 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-11-07 |  | 8092.8 | Approved | 100 | 2022-11-24 | 2023-10-07 | 93067.2 |  |  |  |  | C000062471 | PHASE11 | 2022-12-30 | 2023-01-20 | NANDE MAQUBELA | Buhle Qwabe | 23000548 |  |  |  |  | 2023-01-19 | 93067.2 | 0 |  |  | C000052738 | 80928 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000477 | Removal of Equipment | Removal of Equipment |  |  | Region 3 | Limpopo | 76717X | 1000-70518-01 | 76E Schoeman Street-Schoeman St-Polokwane |  | 2022-11-29 | 2022-12-08 |  | ASP-LP0148 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Freeho |  | NOMNGANGAL | 2022-11-22 |  | 7511.02 |  | 100 | 2022-12-14 | 2022-12-14 | 0 |  |  |  |  | C000059892 | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-09 | 75110.27 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000478 | New Water tank with booster pump and fil | New Water tank with booster pump and filtration system (CIP 2022)Absa Volksrust has no backup water supply system in place and during prolonged water disruptions, the yellow bin does not provide adequate water supply backup to meet the water demand for the branch. It has been recommended that a 1000 litre water tank with a suitable booster pump and a filtration system be installed as a backup supply to the branch. Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test to be catered for.Note: Supported by BFM Engineering. Scope of Work Construction of reinforced conrete base with bund walling for the water tank Supply and install 1000 litre black lined water tank Supply and install a booster pump complete with power requirements Provide all the necessary plumbing for the installation Commisioning of the system and issue of as built drawings Install a cage to secure the pump Supply and install palisade fencing complete with lockable gate Issue a COC for the new electrical installation. Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test has been catered for No additional security required. |  |  | Region 3 | Mpumalanga | 77566X | 1000-70636-01 | Absa Volksrust-Joubert St-Volksrust |  | 2022-06-01 | 2022-09-30 |  | ASP-MP0088 | REL BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NGIDIN | 2021-09-16 |  | 110000 | Approved | 100 | 2022-10-27 | 2023-10-07 | 61954.35 |  | {"MANDT":"111","REFERENCE":70000478,"ONEVIEW":"77566X","DATE01":"2022-03-23","DATE02":"2022-04-20","DATE03":"2022-04-27","DATE04":"2022-04-27","DATE05":"2022-06-01","DATE06":"2022-09-30","DATE07":"2022-10-21","DATE08":"2023-06-09","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-30","FORECAST_END":"2022-10-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHRvIGJlIHNoYXJlZCB3aXRoIGVuZ2luZWVyaW5nIGZvciBzaWduIG9mZiAgRVRBICAyMiBTZXB0CiAgSW52b2ljZXMgYW5kIHJlbGF0ZWQgc3VwcG9ydGluZyBkb2N1bWVudGF0aW9uIHJlcXVlc3RlZCBmcm9tIHN1cHBsaWVy","RATING":""} |  |  | C000062741 | PHASE09 | 2022-09-30 | 2022-10-21 | SIYANDA DLAMINI | Thea Spamers | 23000574 |  |  |  |  | 2023-01-20 | 53873.35 | 0 |  |  | C000149102 | 53873.35 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000479 | Minor Works - Absa Highveld Mall (CIP 20 | Minor Works Absa Highveld Mall (CIP 2022)Absa Highveld Mall ATM room currently do not have any direct link to the secure teller & treasury area. The branch utilizes an undercounter safe to safeguard cash needed for ATM loading during trading hours in the event the ATMs do run out of cash. It has been recommended that a drop safe previously removed from Absa Midcentral branch and currently at Universal ATM storage be installed at this branch as a link between the treasury and the ATM room, to facilitate efficient cash movement between the two areas. The existing BCTU and metal wall in the CIT receiving area will be deinstalled and repositioned to make way for the new drop safe. The existing undercounter safe in the ATM room will then be removed from site and sent back to storage. Note: Approved by RIF. The cost for the drop safe will be covered by AFS. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Cost breakdown:Cost Allocated to AFS: R 34 802.06 incl.VATInstallation of drop safe: R 78 795.64 incl.VATTotal project cost: R 113 597.70 incl.VATScope of Works Demolish existing metal wall in CIT delivery passage (x4lm) Deinstall BCTU in CIT passage and store for reuse (x1) Supply and install new metal wall in CIT passage as per plan (x 4lm) Create opening in new metal wall for the BCTU and reinstall BCTU. Create opening in existing ATM metal wall to fit new drop safe. Prepare and paint new and affected walls (35sqm) Make good affected floor and ceiling finishes to match existing (3sqm) Project to be carried out over a weekend and a dedicated project guard will be arranged. |  |  | Region 3 | Mpumalanga |  | 1000-70655-01 | Building not in our database |  | 2021-08-17 | 2021-12-31 |  | ASP-MP0091 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NGIDIN | 2021-09-22 |  | 2398.75 |  | 100 | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000061211 | IGNORE |  |  | SIYANDA DLAMINI | Thea Spamers | 0 |  |  |  |  | 2023-01-13 | 31775.79 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000480 | Dilaps | Dilaps |  |  | Region 3 | Mpumalanga | 35155X | 1000-70582-01 | Absa Checkers Mall Secunda |  | 2022-01-14 | 2022-01-31 |  | ASP-MP0095 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-01-19 |  | 1702 |  | Approved | 2022-02-21 | 2022-02-21 | 0 |  |  |  |  | 2903608 | CLOSED |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000481 | Minor Works - Absa Ilanga Mall (2022 CIP | Minor Works Absa Ilanga Mall (2022 CIP) Absa Ilanga Mall Branch was last refreshed more than five years ago. The carpets to banking hall, back office and teller areas have faded, and requires to be replaced. The painted walls in the entire branch need to be repainted in Absa Lux colours to enhance the look and feel of the branch. The afore mentioned refurbishment to floor and wall finishes will improve the general look and feel of the branch. Note: Round Robin approval obtained by RBB. Spec approved by Absa design.Scope of works: Remove existing carpet and cart away (250sqm). Prepare and repaint all walls in Absa lux colours (714sqm). Supply and install new belgotex equinox 500x500 carpet tiles (250sqm). Supply and install Trioscape walk off mat to rotabooth and reception area (12sqm). Covid clean to be carried out at the end of the project. |  |  | Region 3 | Mpumalanga | 22227X | 1000-63481-01 | Absa Ilanga Mall, Cnr Flamboyant & Bitterbessie Street, Nelspruit |  | 2022-02-03 | 2022-04-30 |  | ASP-MP0096 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 28941.12 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2904752 | CLOSED |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000482 | Paint internal walls of branch (2022 CIP | Paint internal walls of branch (2022 CIP) |  |  | Region 3 | Mpumalanga | 78542X | 1000-70653-01 | Absa Mall@Emba, Cnr Old Provincial & Embalenhle Rd, Embalenhle |  | 2022-02-03 | 2022-04-30 |  | ASP-MP0097 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-03 |  | 15735.42 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2908015 | CLOSED |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000483 | Dilaps | Dilaps |  |  | Region 3 | Mpumalanga | 78041X | 1000-70647-01 | Absa Midcentral |  | 2022-02-25 | 2022-03-31 |  | ASP-MP0098 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-02-25 |  | 4289.78 |  | Approved | 2022-02-25 | 2022-02-25 | 0 |  |  |  |  | 2905111 | CLOSED |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000484 | Replacement of waiting area chairs (CIP | Replacement of waiting area chairs (CIP 2022) |  |  | Region 3 | Mpumalanga | 22227X | 1000-70564-01 | Absa Ilanga Mall |  | 2022-04-04 | 2022-05-30 |  | ASP-MP0100 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-11 |  | 5504 |  | Approved | 2022-03-10 | 2022-03-10 | 0 |  |  |  |  | 2908654 | CLOSED | 2022-04-04 | 2022-05-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000485 | Installation of new Hydro taps to 1st Fl | Installation of new Hydro taps to 1st Floor and Second floor Kitchens (CIP 2022) |  |  | Region 3 | Mpumalanga | 77878X | 1000-70683-01 | Absa Square |  | 2022-03-14 | 2022-04-30 |  | ASP-MP0101 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-14 |  | 34380.89 |  | Approved | 2022-03-10 | 2022-03-10 | 0 |  |  |  |  | 2908637 | CLOSED | 2022-03-14 | 2022-04-30 | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000486 | Dilaps- Removal on Generator | Dilaps Removal on Generator |  |  | Region 3 | Mpumalanga | 78041X | 1000-70647-01 | Absa Midcentral VO |  | 2022-03-24 | 2022-12-15 |  | ASP-MP0102 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | LOUISR | 2022-03-16 |  | 5221.7 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2909883 | CLOSED |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000487 | Installation of roller shutter door to s | Installation of roller shutter door to staff entrance (CIP 2022)At Absa Carolina the staff entrance currently has no roller shutter door and only has a lockable gate manned by the branch security during the day. The branch security has been tasked to look after customers entering and exiting the branch as well as the ATM area which makes it difficult to effectively manage access control at the staff vehicles gate. It was therefore recommended that a motorized roller shutter door be installed at the staff entrance with remote controls that will be issued to staff members.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. AFS and Engineering support obtained.Scope of works: Supply and install 3100mm,3600mm roller door x1 Supply and install roller shutter door motor complete with electrical connection x1 Issue COC upon completion of installation Issue Staff remote controls x 3 No covid clean required, external work. No additional Security required |  |  | Region 3 | Mpumalanga | 78145X | 1000-70684-01 | Absa Carolina, 44F Voortrekker Street, Carolina |  | 2022-04-11 | 2022-05-31 |  | ASP-MP0103 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Freeho |  | GAMIETR | 2022-03-25 |  | 5710.43 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | C000063120 | CLOSED | 2022-04-11 | 2022-05-31 | SIYANDA DLAMINI | Thea Spamers | 0 |  |  |  |  | 2023-01-23 | 5472.1 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000488 | Upgrade of sales areaThis request seeks | Upgrade of sales areaThis request seeks approval for the upgrade of the sales area. Absa Nelspruit Plaza was built in 2017 as a cashless branch with only two sales desks and an internet kiosk. The internet kiosk is not generating the expected transaction volumes since installation and the region decided to have it replaced with an additional sales desk. The internet kiosk will be removed from the site to stores. In addition, the existing standard poster frames are not stable and requires to be replaced with A0 poster frames. Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Absa design approval obtained.Scope of works: Deinstallation and removal of existing internet kiosk (x1) Supply and installation of new sales desk complete with side screens (x1) Supply and install power to new desk COC to be issued on completion. Supply and install frosting to privacy screens (x2) Supply and install A0 poster frames to replace existing poster frames. (x2) Touch point covid clean will be carried out at the end of the project. No additional security will be required. |  |  | Region 3 | Mpumalanga | 37007X | 1000-70591-01 | Absa Nelspruit Plaza Sales and Service, Shop 22C, Nelspruit Plaza, cnr Henshall and Bester Street, Nelspruit |  | 2022-04-21 | 2022-05-31 |  | ASP-MP0104 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-03-25 |  | 4339.76 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912427 | CLOSED | 2022-04-21 | 2022-05-31 | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000489 | Minor Works - Absa Komatipoort (CIP 2022 | Minor Works Absa Komatipoort (CIP 2022)Absa Komatipoort was last refreshed in 2014 and the wall and floor finishes have deteriorated over a period of time. The ceramic tiles in the banking hall, ATM lobby, teller kitchen and ablution areas need to be replaced. The paint to walls in banking hall, offices, teller area, treasury, store rooms, kitchen, ablutions area, pause area and ATM room needs to be refreshed with the new Absa lux colours. This will enhance the look and feel of the branch. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of Works Remove existing floor tiles to banking hall , kitchen and ablution facilities (110sqm) Supply and install new floor tiles to previously tiled areas (110sqm) Repaint all wooden painted doors (x17) Paint all internal walls to banking hall, offices, cash areas, back of house and ablution facilities (635sqm). Cleaning touch points to be arranged with branch cleaner. Project to be carried out over a weekend and a dedicated project guard will be arranged. |  |  | Region 3 | Mpumalanga | 77938X | 1000-70644-01 | Komati Spar Centre-Rissik St-Komatipoort |  | 2022-06-01 | 2022-09-30 |  | ASP-MP0105 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-01 |  | 1550.55 |  | 100 | 2022-06-30 | 2022-06-30 | 0 |  |  |  |  | C000060370 | IGNORE | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Thea Spamers | 0 |  |  |  |  | 2023-01-10 | 15505.55 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000490 | Minor Works - Absa Bethal (CIP 2022)Absa | Minor Works Absa Bethal (CIP 2022)Absa Bethal was last refreshed in 2017, however the ablution facilities were not part of the scope of work. The floor and wall finishes of the ablution facilities has faded and deteriorated over a period of time and need to be refreshed. The Current CIT deliveries to the branch is through the banking hall located BCTU booth and this does not align with current Absa standards. A request was made to install a new CIT lobby using metal walling adjacent to the teller section, with direct access from the street. The existing BCTU to be relocated to the new CIT lobby and a suitable ramp will be created to provide easy trolley access as recommended by design office.Note: RIF & Design Layout approval received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Support obtained from AFS.Scope of works: Remove existing wall tiles to ablution facilities (100sqm) Supply and install new wall tiles to previously tiled areas (80sqm) Paint to previously painted walls and doors (76sqm) Remove existing floor tiles and cart away (40sqm) Supply and install new floor tiles (40sqm) Creation of new CIT lobby with metal walling (13lm) Supply and install new CIT room door (x1) Relocate BCTU to new CIT lobby (x1) Paint newly constructed CIT lobby walling to match existing (79sqm) Supply and install security cameras and alarms Construct a suitable ramp connecting the outer CIT room. Enhanced Covid clean to be carried out at the end of the project. Project to be carried out over a weekend and provision made for security services for the duration of project. |  |  | Region 3 | Mpumalanga | 77421X | 1000-70625-01 | Bethal-Vuyusile Mini St-Bethal |  | 2022-05-05 | 2022-06-30 |  | ASP-MP0106 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-04 |  | 5680.82 | Approved | 100 | 2022-05-12 | 2023-10-07 | 333132.98 |  |  |  |  | C000061824 | PHASE11 | 2022-05-05 | 2022-06-30 | SIYANDA DLAMINI | Thea Spamers | 0 |  |  |  |  | 2023-01-17 | 65329.5 | 232872.59 |  |  | C000061824 | 56808.26 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000491 | Minor Works- Absa Kanyamazane (CIP 2022) | Minor Works Absa Kanyamazane (CIP 2022)Absa Kanyamazane branch was last refreshed in 2015 and converted into a tellerless outlet in 2021 which resulted in the bulk of the banking hall no longer being utilized by customers. This has therefore resulted in the need to separate the excess space with a dry wall partition and install an access controlled door. In addition, the walls to the banking hall, offices, ATM room, ATM lobby, tellers, treasury, store rooms, pause area, utility room, kitchen and ablution facilities need to be repainted to enhance the look and feel of the branch as they have deteriorated over time. Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Floor plan updated. Supported by AFS & OHS.Scope of Works Painting of walls to banking hall, offices, ATM room, ATM lobby, tellers, treasury, store rooms, pause area, utility room, kitchen and ablution facilities (547sqm) Construction of new dry wall partitioning to divide banking hall into two areas (7m) Painting of the new dry wall partitioning (21sqm) Repainting of all wooden doors in branch (x14) Installation of access control keypad to new door leading to cordoned off area. Covid wipe down on touch points . Project to be carried out over a weekend and a dedicated project guard will be arranged. |  |  | Region 3 | Mpumalanga | 77100X | 1000-70609-01 | Kanyamazane Shopping Centre-Chris Hani Umgwaco St-Kanyamazane |  | 2022-06-09 | 2022-07-29 |  | ASP-MP0107 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-04 |  | 3397.22 |  | 100 | 2022-06-30 | 2022-06-30 | 0 |  |  |  |  | C000060633 | IGNORE | 2022-06-09 | 2022-07-29 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-11 | 33972.28 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000492 | Relocation of treasury safe The Absa Erm | Relocation of treasury safe The Absa Ermelo branch does not have sufficient cash storage devices in their treasury. During the revamp project at Absa Midcentral, it was recommended that the treasury safe that was previously used at Absa Midcentral be relocated to Absa Ermelo branch. This will be an existing safe and therefore only the cost for transport and labour will be incured by the branch. The installation will take place during normal working hours.Note: Approved by RIF and LL. Supported by AFS. This project was prioritised by the region and spend will be allocated from the regional minor works budgetScope of Works Collect and deliver Treasury safe from stores to Absa Ermelo. Rigging and Positioning of safe on site Special A frame to be constructed to aid on site rigging due to stepped floor levels |  |  | Region 3 | Mpumalanga | 77584X | 1000-70638-01 | Absa ErmeloUnited BuildingCnr De Clercq and Kerk StreetErmelo |  | 2022-08-25 |  |  | ASP-MP0110 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-11 |  | 10011.1 |  | Approved | 2022-08-19 | 2022-08-19 | 0 |  |  |  |  | C000061002 | CLOSED |  |  | Siyanda Dlamini | Thea Spamers | 0 |  |  |  |  | 2023-01-12 | 9100.99 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000493 | Paint to internal wallsAbsa Elukwatini w | Paint to internal wallsAbsa Elukwatini was last refreshed in 2017 and the paint has deteriorated and needs to be rejuvenated. It is recommended that the all internal walls to the branch be repainted in new Absa lux colours and the following areas are to be included in the project scope: Front of office, banking hall, manager office, business tellers, treasury, ATM room and ATM lobby, entrance arch, teller area, controller area, customer services area, sales area, back of house, utility room ablution facilities, kitchen, pause area and back office. Store room to also be repainted. Absa lux colours to be applied to identified walls (focus walls) in, waiting area, offices, tellers including business tellers, sales area and pause area.Note: Approved at RIF. The project has been approved at round Robin Forum. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Prepare and paint internal walls grey plascon neight jewel paint (469m2) Prepare and paint focus walls in Absa Lux colours (81m2) Prepare and paint all wooden doors in architectural grey enamel paint (x11) Final clean upon completion of project Provision made for project security guard The project will take three days to complete and will be carried out over a weekend. |  |  | Region 3 | Mpumalanga | 21892X | 1000-70563-01 | Absa ElukwatiniShop- 6-7 Elukwatini SqaureMain RoadElukwatini |  | 2022-10-20 | 2022-10-20 |  | ASP-MP0111 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 11587.49 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000061785 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-17 | 19406.4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000494 | Replacement of tiles in the Sales, Entra | Replacement of tiles in the Sales, Entrance and ATM Lobby areasAbsa Middelburg Mall received a partial visual identity upgrade in April 2022 however, the floor tiles to the sales area, entrance hall and ATM lobby were not replaced to match the banking hall s new look as it was not included in the scope of works. It has been recommended that the existing porcelain tiles to sales, entrance hall and ATM lobby be replaced with matching porcelain tiles to maintain uniformity of finishes through out the branch. In addition, there are ceiling tiles in the back office and pause area which are not matching as a result of resulting from occasional replacement of ceiling boards by swopping out ceiling boards from these areas to replace damaged ceiling boards in the customer facing areas leading to an assortment of ceiling board brands in the back office and pause area.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Hack off exiting porcelain tiles in sales area and ATM lobby and cart away(90m2) Supply and installation 600x600 porcelain tiles to match banking hall tiles (110m2) Supply and installation of 1200x600 ceiling tiles to match existing ceiling tiles in back office and pause area (40m2) Final Clean upon project completion Provision made for project security guard |  |  | Region 3 | Mpumalanga | 22407X | 1000-70565-01 | Absa Middelburg Mall,Shop 52 Middelburg MallCnr Dolerite Cresent and Sondagsriver Street,Middelburg |  | 2022-10-20 | 2022-10-20 |  | ASP-MP0112 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 12987.24 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039894 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000495 | Installation of weather strip to emergen | Installation of weather strip to emergency exit door & internal directional signage x2Absa Ilanga Mall emergency exit door has a gab below the door. This is resulting in insects crawling into the branch. The recommendation was made to install a weather strip to close the gap to prevent insects from entering into the branch. In addition, a ceiling suspended internal directional signage is required to the teller area for improved customer flow management.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Artwork approval received.Scope of Works Supply and installation of an aluminium weather strip with a rubber seal to the emergency back door Install suspended internal directional signage 800mm x300mm (x2) No additional security required |  |  | Region 3 | Mpumalanga | 22227X | 1000-70564-01 | Absa Ilanga MallShop LG 14,Ilkanga MallCnr Samora Machel Drive andPenny Gum StreetNelspruit |  | 2022-10-20 | 2022-10-20 |  | ASP-MP0113 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 1315.77 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039895 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000496 | Installation of weather strip to emergen | Installation of weather strip to emergency exit door Absa Bushbuckridge emergency exit door has a gab below the door. This is resulting in insects crawling into the branch. The recommendation was made to install a weather strip to close the gap to prevent insects from entering into the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply and installation of an aluminium weather strip with a rubber seal to the emergency back door No additional security required |  |  | Region 3 | Mpumalanga | 35026X | 1000-70577-01 | Absa BushbuckrigeShop 34Twin CityCnr R40 and R533 |  | 2022-10-20 | 2022-10-20 |  | ASP-MP0114 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 351.43 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039893 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000497 | Installation of weather strip to emergen | Installation of weather strip to emergency exit door Absa Kanyamazane emergency exit door has a gab below the door. This is resulting in insects crawling into the branch. The recommendation was made to install a weather strip to close the gap to prevent insects from entering into the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply and installation of an aluminium weather strip with a rubber seal to the emergency back door No additional security required |  |  | Region 3 | Mpumalanga | 77100X | 1000-70609-01 | Absa KanyamazaneShop 16Ground Floor,Kanyamazane Shopping CentreChris Hani Street |  | 2022-10-20 | 2022-10-20 |  | ASP-MP0115 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 237.46 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039899 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000498 | Installation of weather strip to emergen | Installation of weather strip to emergency exit door Absa Emalahleni emergency exit door has a gab below the door. This is resulting in insects crawling into the branch. The recommendation was made to install a weather strip to close the gap to prevent insects from entering into the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply and installation of an aluminium weather strip with a rubber seal to the emergency back door No additional security required |  |  | Region 3 | Mpumalanga | 78577X | 1000-70656-01 | Absa EmalahleniSaveways Crescent CentreCnr OR Tambo & Mandela Drive |  | 2022-10-20 |  |  | ASP-MP0116 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 300.38 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039898 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000499 | Installation of weather strip to emergen | Installation of weather strip to emergency exit door Absa Komatipoort emergency exit door has a gab below the door. This is resulting in insects crawling into the branch. The recommendation was made to install a weather strip to close the gap to prevent insects from entering into the branch.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply and installation of an aluminium weather strip with a rubber seal to the emergency back door No additional security required |  |  | Region 3 | Mpumalanga | 77938X | 1000-70644-01 | Absa KomatipoortShop 13Komati Spar CentreRissik Street |  | 2022-10-20 |  |  | ASP-MP0117 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 399.8 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000040015 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000500 | Dilaps | Dilaps |  |  | Region 3 | Mpumalanga | 77446X | 1000-70628-01 | Absa Hazyview |  | 2022-10-20 | 2022-10-20 |  | ASP-MP0118 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-09-16 |  | 9078.61 |  | Approved | 2022-09-18 | 2022-09-18 | 0 |  |  |  |  | C000040016 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000501 | Enclosure to Manager s Office (CIP 2022) | Enclosure to Manager s Office (CIP 2022)The branch was built in 2018 as per the new coporate identity look and feel with open plan offices. As a result, concerns were raised regarding privacy involving the branch manager addressing staff matters. The recommendation was that the office be enclosed with prefabricated wall panels. The existing services to the current work station will suffice and no additional modifications will be required.Note: Approved at RIF,Approved floor plan received and supported by BFM Eng. This project was prioritised by the region and spend will be allocated from the regional minor works budget. LL support obtained. Scope of Works Supply and installation of prefabricated wall panels to branch manager s office. (5,6m) Supply and installation of a door to branch manager s office. (x1) Make good affected finishes. |  |  | Region 3 | Mpumalanga | 37064X | 1000-71685-01 | Willowbrooke Square Delmas-Van Der Walt 29232 St-Delmas |  | 2022-06-01 | 2022-09-30 |  | ASP-MP0121 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | CEASARS | 2022-04-08 |  | 6918.09 | Approved | 100 | 2022-08-19 | 2023-10-07 | 79558.09 |  | {"MANDT":"111","REFERENCE":70000501,"ONEVIEW":"37064X","DATE01":"2022-03-23","DATE02":"2022-04-20","DATE03":"2022-04-27","DATE04":"2022-04-27","DATE05":"2022-06-01","DATE06":"2022-09-30","DATE07":"2022-10-21","DATE08":"2022-12-05","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-30","FORECAST_END":"2022-10-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wW2xldGVkIGFuZCBQT0Mgc3VibWl0dGVk","RATING":""} |  |  | C000061086 | PHASE11 | 2022-09-30 | 2022-10-21 | NANDE MAQUBELA | Thea Spamers | 23000560 |  |  |  |  | 2023-01-12 | 69180.95 | 0 |  |  | C000061086 | 69180.96 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000502 | Enclosure to Manager s office (CIP 2022) | Enclosure to Manager s office (CIP 2022)The branch was built in 2019 as per the new coporate identity look and feel with open plan offices. As a result, concerns were raised regarding privacy involving the branch manager addressing staff matters. The recommendation was that the office be enclosed with prefabricated wall panels. The existing services to the current work station will suffice and no additional modifications will be required.Note: Approved at RIF. Supported by Absa design office, BFM Eng and Land Lord. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Works Supply and installation of prefabricated wall panels to branch manager s office. (5,6m) Supply and installation of a door to branch manager s office (x1) Make good affected finishes |  |  | Region 3 | Mpumalanga | 78577X | 1000-70656-01 | Saveways Crescent Centre-Cnr OR Tambo Rd & Mandela St-Emalahleni |  | 2022-06-01 | 2022-09-30 |  | ASP-MP0122 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | CEASARS | 2022-04-08 |  | 8566.65 | Approved | 100 | 2022-08-25 | 2023-10-07 | 98516.48 |  | {"MANDT":"111","REFERENCE":70000502,"ONEVIEW":"78577X","DATE01":"2022-03-23","DATE02":"2022-04-20","DATE03":"2022-04-27","DATE04":"2022-04-27","DATE05":"2022-06-01","DATE06":"2022-09-30","DATE07":"2022-10-21","DATE08":"2022-12-05","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-30","FORECAST_END":"2022-10-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIFBPQyBzdWJtaXR0ZWQ=","RATING":""} |  |  | C000061144 | PHASE11 | 2022-09-30 | 2022-10-21 | NANDE MAQUBELA | Thea Spamers | 23000543 |  |  |  |  | 2022-08-26 | 85666.5 | 0 |  |  | C000061144 | 85666.5 | CIP2023XP | 8433.32 |  | 0 | 0 |  | 0 |  | 0
70000503 | Removal of Equipment: Deinstallation and | Removal of Equipment: Deinstallation and remove all internal and External signage, Deinstallation and removal of TVs, Deinstallation and removal of security equipment, Deinstallation and removal of safes,Deinstallation and removal of furniture including scrapping thereof. |  |  | Region 3 | Mpumalanga | 76953X | 1000-70604-01 | Absa Witbank |  | 2022-08-01 |  |  | ASP-MP0126 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-09 |  | 5837.92 |  | Approved | 2022-05-22 | 2022-05-22 | 0 |  |  |  |  | C000062851# | CLOSED | 2022-08-01 | 2022-09-30 | SIYANDA DLAMINI | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 16823.38 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000504 | New Water tank with booster pump and fil | New Water tank with booster pump and filtration system (CIP 2022)Absa Mkhuhlu has no backup water supply system in place and during prolonged water disruptions, the yellow bin does not provide adequate water supply back up to meet the water demands for the branch. It has been recommended that a 1500 litre water tank with a suitable booster pump and a filtration system be installed as a backup supply to the branch. Six Monthly services for the pump, tank disinfection, filter change, legionella and portability test to be catered for.Note: Supported by BFM Engineering. Landlord approval has been received.Scope of Work Construction of reinforced conrete base with bund walling for the water tank Supply and install 1500 litre black lined water tank Supply and install a booster pump complete with power requirements Provide all the necessary plumbing for the installation Commisioning of the system and issue of as built drawings Install a cage to secure the pump Supply and install palisade fencing complete with lockable gate Issue a COC for the new electrical installation. Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test has been catered for No additional security required |  |  | Region 3 | Mpumalanga | 77974X | 1000-70646-01 | Mkhuhlu Mall-Kruger Gate Rd-Mkhuhlu |  | 2022-06-01 |  |  | ASP-MP0127 | REL BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | CEASARS | 2022-05-13 |  | 5974.21 | Approved | 100 | 2022-10-27 | 2023-10-07 | 68703.45 |  |  |  |  | C000062740 | PHASE09 | 2022-07-01 | 2022-07-22 | SIYANDA DLAMINI | Thea Spamers | 23000571 |  |  |  |  | 2023-01-20 | 79008.97 | 0 |  |  | C000149104 | 59742.13 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000505 | Removal of Generator - Absa Witbank has | Removal of Generator Absa Witbank has undergone a space reduction and a revamp, with the existing 330kVA generator and old Aros tower type UPS now being redundant. The generator unit has been replaced with a smaller generator that aligns with the reduced branch size. The UPS was replaced with an intelcab size UPS. The old generator set and UPS therefore need to be removed from site and sent to stores. There was a delay in reaching a decision regarding the future of the generator and UPS, hence the late submission for removal of items from site. We have approval from Absa CRES (Engineering) to have the unit removed from site.The work will be carried out during normal working hours as it has no impact on business operations. i will take a day to complete the removals. |  |  | Region 3 | Mpumalanga | 0 | 1000-70604-01 | Absa Witbank |  | 2022-09-08 | 2022-10-06 |  | ASP-MP0128 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-08-30 |  | 12316.35 |  | Approved | 2022-08-30 | 2022-08-30 | 0 |  |  |  |  | C000034407 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000506 | Replacement of damaged shopfront and ban | Replacement of damaged shopfront and banking hour decals (19991231ctive)This request seeks 19991231ctive approval. Absa Malelane shopfront were damaged when a vehicle crushed and dislodged a concrete dustbin into the shopfront resulting in extensive damage. The aluminium framework and glazing had to be replaced. The various signage decals applied on the shopfront were also replaced accordingly. The work was completed via the INSOG process as emergency work.Note: Approved by Cres VP. Work Completed on 6 Sep 2022 via INSOG Insurance process. Scope of Works Remove damaged section of shopfront and cart away 2.4m Supply and install new shopfronts 2.4m Supply and install western union decal (x1) Supply and install safety pattern decal(x1) Supply and install foreign exchange decal (x1) |  |  | Region 3 | Mpumalanga | 37008X | 1000-70592-01 | Ingwe Mall-Impala St-Malelane |  | 2022-10-06 | 2022-10-13 |  | ASP-MP0129 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-05 |  | 4366.79 |  | 100 | 2022-10-13 | 2022-10-13 | 0 |  |  |  |  | C000062340 | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-18 | 43667.96 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000507 | Replacement of vandalized air conditioni | Replacement of vandalized air conditioning units and electrical copper wireThe Absa Mandela Drive is owned building and is occupied by both Absa retail branch and external tenants. The branch alerted Bidvest FM of possible theft onsite. Upon investigation, it was found that the HVAC with electrical cables on the ground and 1st floors were vandalized. The ground floor was completely stripped, all piping and cables were stolen from the units and the return air grills and controllers on five Mitsubishi units were missing. On the first floor it was discovered that the piping between the condenser and indoor units was missing (no visible damage to units was found). For the IntelCab Unit, all refrigerant piping was stripped and stolen. It was recommended that the five vandalized units be replaced with new fix speed units as they were beyond repair.Note: Supported by BFM Engineering. Approved by CRES Engineering. INSOG Insurance process followed.Scope of Work Deinstallation of vandalized units and removal from site Supply and installation of (x5) Fixed Speed Units Replace piping, return air grills and controllers Replace refrigerant piping to Intelcab Recommission all the newly installed units including the intelcab unit |  |  | Region 3 | Mpumalanga | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank |  | 2022-11-04 | 2022-11-15 |  | ASP-MP0130 | CLSD BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-20 |  | 40210.25 | Approved | 100 | 2022-10-27 | 2023-10-07 | 462417.88 |  | {"MANDT":"111","REFERENCE":70000507,"ONEVIEW":"76953X","DATE01":"2022-08-26","DATE02":"2022-09-02","DATE03":"2022-09-23","DATE04":"2022-09-30","DATE05":"2022-10-21","DATE06":"2022-11-04","DATE07":"2022-11-15","DATE08":"2023-08-31","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-04","FORECAST_END":"2022-11-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmVxdWVzdGVkIGNvbW1pc3Npb25pbmcgZGF0YSBmcm9tIHN1cHBsaWVyIEVUQSAyMiBTZXB0","RATING":""} |  |  | C000062853 | PHASE11 | 2022-11-04 | 2022-11-15 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 402102.5 | 0 |  |  | C000062853 | 402102.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000508 | Absa Komatipoort Spar Centre - New Queue | Absa Komatipoort Spar Centre New Queue Railing SystemAbsa Komatipoort Spar Centre was last refreshed in August 2022. The existing queue railing system is the old post and stay system with plastic links. It is currently a challenge when attempts are made to put it back onto the retiled floor surfaces due to age and the poor availability of spare links. A new post and belt link system is therefore recommended to replace the old system, that it is easy to assemble and manoeuvre to align with the branch operational requirements. The existing system was not put back after the project because it was not in good condition to reuse.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Supply and installation of new post and belt queue railing system Removal of old queue railing from site. No additional guard required |  |  | Region 3 | Mpumalanga | 77938X | 1000-70644-01 | Komati Spar Centre-Rissik St-Komatipoort |  | 2022-11-04 |  |  | ASP-MP0131 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-20 |  | 6130.41 | Approved | 100 | 2022-10-27 | 2023-10-07 | 70499.75 |  | {"MANDT":"111","REFERENCE":70000508,"ONEVIEW":"77938X","DATE01":"2022-08-26","DATE02":"2022-09-23","DATE03":"2022-09-30","DATE04":"2022-09-30","DATE05":"2022-11-04","DATE06":"2022-12-04","DATE07":"2022-12-25","DATE08":"2023-02-08","DATE09":"2023-02-28","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-04","FORECAST_END":"2022-12-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgUE9DIHN1Ym1pdHRlZCB0byBmaW5hbmNl","RATING":""} |  |  | C000062731 | PHASE11 | 2022-12-04 | 2022-12-25 | NANDE MAQUBELA | Thea Spamers | 23000568 |  |  |  |  | 2023-01-20 | 61304.13 | 0 |  |  | C000062731 | 61304.13 | CIP2023XP | 6227.25 |  | 0 | 0 |  | 0 |  | 0
70000509 | Relocation of external signageAbsa KG Ma | Relocation of external signageAbsa KG Mall was built in 2018 and did not have adequate space for the installation of external signage to be mounted directly above the entrance of the branch as per the standard requirements. After discussions held with the landlord, it was agreed to relocate the PNL signage to the back of the building to create space for the Absa external signage which is currently 50m away from the branch s entrance. Absa will carry the cost for both relocations. Note: Approved at RIF. Approved by LL. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Deinstallation the PNL wall mount signage above Absa Entrance Deinstallation of the Absa wall mount signage located 50m from the branch entrance Reinstallation of Absa wall mount signage where PNL signage was removed and connect to existing power Reinstallation of PNL wall mount signage at a position pointed out by the land lord at the back of the building. No additional guard required |  |  | Region 3 | Mpumalanga | 37068X | 1000-70595-01 | KG Mall-Cnr N4 East & Mathew Phosa Dr-Witbank |  | 2022-10-28 |  |  | ASP-MP0132 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-20 |  | 988.2 | Approved | 100 | 2022-10-27 | 2023-10-07 | 11364.3 |  |  |  |  | C000046274 | PHASE11 | 2022-11-27 | 2022-12-18 | NANDE MAQUBELA | Thea Spamers | 23000622 |  |  |  |  | 2022-10-12 | 11364.3 | 0 |  |  | C000046274 | 9882 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000510 | Installation of Burglar Bars to the Entr | Installation of Burglar Bars to the Entrance GateAbsa Carolina was fitted with an automated staff entrance gate and metal spikes to the opening between the building and the concrete column supporting the slab above. The spikes have proven to be inadequate deterrents for street kids to temper with trying to gain access to the backyard. It is recommended that burglar bars be installed to replace the metal spikes.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. AFS were consulted. Scope of Work Remove existing metal spikes and cart away Supply and install new burglar bars to close the sedewall opening (2700mm High x 250mm Wide) Prepare and paint burglar bars to match existing gate No additional security guard required as this is external work. |  |  | Region 3 | Mpumalanga | 78145X | 1000-70684-01 | Absa Carolina-Voortrekker St-Carolina |  | 2022-11-03 | 2022-11-30 |  | ASP-MP0133 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 529.37 | Approved | 100 | 2022-10-27 | 2023-10-07 | 6087.76 |  |  |  |  | C000062727 | PHASE11 | 2022-11-03 | 2022-11-30 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 6087.76 | 0 |  |  | C000062727 | 5293.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000511 | Installation of New Time DecalAbsa Kabok | Installation of New Time DecalAbsa Kabokweni is a cashless branch and the trading hours time decals need to be updated due to recent changes in trading hours following the lifting of the Covid19 protocols. The region decided to align trading hours with that of other branches in the region.Note: Approved by RIF. This project was prioritized by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing time decal and cart away Prepare and paste new time decal to shopfront |  |  | Region 3 | Mpumalanga | 78671X | 1000-70657-01 | Kabokweni Plaza-Cnr Kabokweni & Palaston Rd-White River |  | 2022-11-03 | 2022-11-30 |  | ASP-MP0134 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 862.03 |  | 100 | 2022-10-27 | 2022-10-27 | 0 |  |  |  |  | C000062730# | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 8620.36 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000512 | Installation of New Time DecalAbsa Highv | Installation of New Time DecalAbsa Highveld Mall branch used to close at 13h00 on Saturdays and the trading hours have been revised by the region to 12h00. It is therefore recommended that the time decal be updated due to this recent changes in trading hours.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing time decal and cart away Prepare and paste new time decal to shopfront |  |  | Region 3 | Mpumalanga | 78558X | 1000-70655-01 | Absa HighveldShop 107Highveld MallCnr Mandela Street& N4Emalahleni |  | 2022-11-03 | 2022-11-30 |  | ASP-MP0135 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-10-25 |  | 413.03 | Approved | 100 | 2022-10-27 | 2023-10-07 | 4749.91 |  | {"MANDT":"111","REFERENCE":70000512,"ONEVIEW":"78558X","DATE01":"2022-08-25","DATE02":"2022-09-01","DATE03":"2022-09-22","DATE04":"2022-09-29","DATE05":"2022-10-20","DATE06":"2022-11-03","DATE07":"2022-11-30","DATE08":"2022-12-21","DATE09":"2022-12-18","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-03","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgUE9DIHN1Ym1pdHRlZCB0byBmYW5hbmNl","RATING":""} |  |  | C000062732 | PHASE11 | 2022-11-03 | 2022-11-30 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 4130.36 | 0 |  |  | C000046456 | 4130.36 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000513 | Installation of New Time DecalAbsa Secun | Installation of New Time DecalAbsa Secunda Mall branch used to close at 13h00 on Saturdays and the trading hours have been revised by the region to 12h00. It is therefore recommended that the time decal be updated due to this recent changes in trading hours.Note: Approved by RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of Work Remove existing time decal and cart away Prepare and paste new time decal to shopfront |  |  | Region 3 | Mpumalanga | 35034X | 1000-70578-01 | Absa Secunda MallShop LG 32Cnr PDP Kruger Street andOliver Tambo DriveSecunda |  | 2022-11-03 | 2022-11-30 |  | ASP-MP0136 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-10-25 |  | 410.43 | Approved | 100 | 2022-10-27 | 2023-10-07 | 4720.01 |  |  |  |  | C000062729 | PHASE11 | 2022-11-03 | 2022-11-30 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 4720.01 | 0 |  |  | C000046453 | 4104.36 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000514 | COC | COC |  |  | Region 3 | Mpumalanga | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank |  | 2022-12-05 |  |  | ASP-MP0141 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-22 |  | 1223.5 |  | 100 | 2022-12-12 | 2022-12-12 | 0 |  |  |  |  | C000064142 | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-26 | 12235 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000515 | New Water tank with booster pump and fil | New Water tank with booster pump and filtration system (CIP 2022)Absa Piet Retief has no backup water supply system in place and during prolonged water disruptions, the yellow bin does not provide adequate water supply backup to meet the water demand for the branch. It has been recommended that a 2500 liter water tank with a suitable booster pump and a filtration system be installed as a backup supply to the branch. Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test to be catered for.Note: Supported by BFM EngineeringScope of Work Construction of reinforced conrete base with bund walling for the water tank Supply and install 2500 litre black lined water tank Supply and install a booster pump complete with power requirements Provide all the necessary plumbing for the installation Commisioning of the system and issue of as built drawings Install a cage to secure the pump Supply and install palisade fencing complete with lockable gate Issue a COC for the new electrical installation. Six Monthly service for the pump, tank disinfection, filter change, legionella and portability test has been catered for No additional security required |  |  | Region 3 | Mpumalanga | 77121X | 1000-70610-01 | Absa Piet Retief-Church St-Piet Retief |  | 2022-12-09 |  |  | ASP-MP0143 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  | L |  | NOMNGANGAL | 2022-12-07 |  | 6715.36 | Approved | 100 | 2022-10-27 | 2023-10-07 | 77226.7 |  | {"MANDT":"111","REFERENCE":70000515,"ONEVIEW":"77121X","DATE01":"2022-09-30","DATE02":"2022-10-07","DATE03":"2022-10-28","DATE04":"2022-11-04","DATE05":"2022-11-25","DATE06":"2022-12-09","DATE07":"2023-01-08","DATE08":"2023-08-31","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":85,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-09","FORECAST_END":"2023-01-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UFJPSkVDVCBDT01QTEVURUQgUE9DIFRPIEJFIEZJTkFMSVpFRA==","RATING":""} |  |  | C000062742 | PHASE08 | 2022-12-09 | 2023-01-08 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-20 | 67153.65 | 0 |  |  | C000062742 | 67153.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000516 | Replacement of Intelcab UPS Batteries (2 | Replacement of Intelcab UPS Batteries (2021 Accrual 19991231ctive) |  |  | Region 2 | Western Cape | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2021-07-29 | 2021-12-15 |  | ASP-N00026 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | Leaseh |  | LOUISR | 2021-07-09 |  | 23886.65 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2856834 | IGNORE |  |  | JOSEPH BWOWE | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000517 | Replacement of Standby Systems UPS Batte | Replacement of Standby Systems UPS Batteries at Various WC Branches (CIP 2022) |  |  | Region 2 | Western Cape | Various | 1000-70842-01 | Various WC Branches |  | 2022-04-01 | 2022-05-31 |  | ASP-N00032 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2022 |  | Variou |  | CEASARS | 2022-02-24 |  | 534500 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2910098 | CLOSED | 2022-04-01 | 2022-05-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000518 | Replacement of Intelcab UPS Batteries at | Replacement of Intelcab UPS Batteries at Various WC Branches (CIP 2022)The UPS Batteries at listed sites below were identified and included in the CIP for 2022 to be replaced as they have reached End of Life (EOL).The contracted maintenance vendor was consulted and recommended the replacement of these batteries. The expected lifespan on these batteries are 3 to 5 years. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Included in the EOL CIP 2022 budget for replacement. Disposal certificates to be provided. CIP 2022 budget allocated was R50k.Scope of works:Supply and Install Intelcab UPS Batteries at the following branches as per EOL CIP 2022 LIST: 76964X Cape Town International Airport: APC SRT 10 kVA UPS Current Load Output 27% 2 x Batteries (R23 886.65 including VAT) 77654X Absa N1 City: APC SRT 10 kVA UPS Current Load Output 30% 2x Batteries (R23 886.65 including VAT) Disposal certificates will be provided on completion. Covid wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | Various | 1000-70841-01 | Various WC Branches |  | 2022-04-29 | 2022-06-30 |  | ASP-N00033 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2022 |  | Variou |  | CEASARS | 2022-03-14 |  | 50000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912268 | CLOSED | 2022-04-29 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000519 | Replacement of Generator Starter Batteri | Replacement of Generator Starter Batteries at Various EC Branches (CIP 2022)The generator batteries at the below sites have reached their End of Life and was included in the CIP for replacement in 2022. These starter batteries were installed more than 5 years ago. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Supported by Engineering. CIP 2022 budget allocated was R64k. Disposal certificate will be provided.Scope of works:Supply and Install Intelcab UPS Batteries at the following branches as per EOL CIP 2022 LIST x8 Sites: 36206X Absa Uitenhage SDMO 80KVA 1x 12v maintenance free battery Deltec: Battery 105A/h R4 034.95 incl VAT 36221X Absa Mthatha Mall SDMO J110 1x 12v maintenance free battery Deltec: Battery 105A/h R5 430.47 incl VAT 70570X Absa Cathedral Square Mthatha SDMO J220 1x 12v maintenance free battery Deltec: Battery 105A/h R5 430.47 incl VAT 76934X Absa Cradock SDMO 110kVA 1x 12v maintenance free battery Deltec: Battery 105A/h R5 692.10 incl VAT 77401X Absa Beaufort West JOHN DEERE 88KVA 1x 12v maintenance free battery Deltec: Battery 105A/h R5 979.60 incl VAT 78937X Absa Mquanduli SDMO 66KVA 1x 12v maintenance free battery Deltec: Battery 105A/h R5 430.47 incl VAT 79176X Absa Mdantsane DEUTZ 100KVA 1x 12v maintenance free battery Deltec: Battery 105A/h R5 430.47 incl VAT 79244X Absa East London JOHN DEERE 88KVA 1x 12v maintenance free battery Deltec: Battery 105A/h R5 979.60 incl VAT Disposal certificat will be provided on completion. COVID wipe down to be done by contractor on all touch points. |  |  | Region 2 | Eastern Cape | Various |  | Various EC Branches |  | 2022-04-14 | 2022-05-31 |  | ASP-N00034 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Laxine Maliffe |  |  | 2022 |  | Variou |  | CEASARS | 2022-03-17 |  | 44000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912265 | CLOSED | 2022-04-14 | 2022-05-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000520 | Replacement of Generator Starter Batteri | Replacement of Generator Starter Batteries at Various WC Branches (CIP 2022)The generator batteries at the below sites have reached their End of Life. These starter batteries were installed more than 5 years ago. The expected lifespan on these batteries are 3 to 5 years. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Supported by Engineering. CIP 2022 budget allocated was R16k. Disposal certificate will be provided. Scope of works:Supply and install Generator Starter Batteries at the following branches as per EOL CIP 2022 LIST x2 Sites: 77261X Absa 21 McIntyre Parow: Volvo 200kVA 1x Deltec Battery 105A/h (12 Months Warranty) (R5 704.86 including VAT) 78131X Absa Citrusdal: John Deere 88kVA 1x Deltec Battery 105A/h (12 Months Warranty) (R5 704.86 including VAT) Disposal certificate will be provided on completion. COVID wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | Various |  | Various WC Branches |  | 2022-04-14 | 2022-05-31 |  | ASP-N00035 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2022 |  | Variou |  | CEASARS | 2022-03-17 |  | 16000 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2912894 | CLOSED | 2022-04-14 | 2022-05-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000521 | Replacement of UPS Batteries at Various | Replacement of UPS Batteries at Various EC Branches (CIP 2022)The UPS batteries at the listed sites below were identified and included in the CIP for 2022 to be replaced as they have reached End of Life (EOL). The contracted maintenance vendor was consulted and recommended the replacement of these batteries. The expected lifespan on these batteries are 3 to 5 years. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Included in the EOL CIP 2022 budget for replacement. Disposal certificate will be provided. CIP 2022 budget allocated was R550k.Scope of works:Supply and install UPS Batteries at the following branches as per EOL CIP 2022 LIST x17 Sites: 20948X Absa Port St Johns 10Kva Current Load Output 16% QTY 32 @ R8 903.23 incl VAT 35033X Absa Dutywa 10kVA SMS Current Load Output 14% QTY 32 @ R11 940.99 incl VAT 36106X Absa Baywest Mall 15kVA MST Current Load Output 10% QTY 80 @ R24 578.21 incl VAT 36206X Absa Uitenhage 20kVA MST Current Load Output 10% QTY 80 @ R24 182.20 incl VAT 36221X Absa Mthatha Mall 20Kva Current Load Output 6% QTY 120 @ R35 765.65 incl VAT 70570X Absa Cathedral Square Mthatha 20kVA MST Current Load Output 24% QTY 80 @ R20 808.51 incl VAT 70631X Absa Lusikisiki 10kVA MST Current Load Output 12% QTY 80 @ R21 344.40 incl VAT 70633X Absa Bizana 10kVA MST Current Load Output 15% QTY 32 @ R22 114.43 incl VAT 76387X Absa Newton Park 20kVA MST Current Load Output 28% QTY 80 @ R24 578.21 incl VAT 76665X Absa Motherwell 10kVA MST Current Load Output 27% QTY 32 @R10 288.37 incl VAT 76934X Absa Cradock 10 kVA SMS ST Current Load Output 23% QTY 32 @ R16 924.48 incl VAT 77262X Absa Knysna 10kVA MST Current Load Output 13% QTY 40 @ R38 971.86 incl VAT 78381X Absa Cathcart Road Queenstown 10kVA SMS Current Load Output 20% QTY 32 @ R10 157.88 incl VAT 78540X Absa Cofimvaba 10kVA SMS Current Load Output 21% QTY 40 @ R15 505.65 incl VAT 78801X Absa Hexagon Circle Queenstown 10kVA SMS Current Load Output 37% QTY 32 @ R8 635.28 incl VAT 78937X Absa Mquanduli 10kVA MST Current Load Output 34% QTY 40 @ R16 145.53 incl VAT 79394X Absa 106 York Street George 40kVA MST Current Load Output 10% QTY 40 @ R69 358.12 incl VAT Disposal certificate will be provided on completion. Covid wipe down to be done by contractor on all touch points. |  |  | Region 2 | Eastern Cape |  |  | Building not in our database |  | 2022-04-14 | 2022-05-31 |  | ASP-N00036 | REL BUDG AVAC RESA SETC: |  | false | true |  | Laxine Maliffe |  |  | 2022 |  | Variou |  | CEASARS | 2022-03-17 |  | 380203.06 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | C000093832 | IGNORE | 2022-04-14 | 2022-05-31 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-25 | 26900.94 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000522 | Evacuation Floor Plans - Absa Retail Sit | Evacuation Floor Plans Absa Retail SitesThis request seeks the approval to obtain evacuation floor plans for various retail sites. Evacuation floor plans give employees and clients an indication of exactly where the nearest exit point of a building is situated. The plans also indicate key fire, first aid equipment locations in the event of an emergency as well as a trained individual and contact details in the event of an emergency. It was requested by Absa CRES Group OHS that all sites have evacuation plans. Currently site verifications and As Builts for the Documentation Compliance Programme are being completed. The existing Professional Consultant conducting the compliance programme has been to the sites previously which would reduce costs, as opposed to appointing a new consultant to conduct site verifications and audits.Note: Supported by Absa CRES OHS.Scope of works: Supply Evacuation Floor Layouts 132 sites (Document Compliance Retail Professional Services). |  |  | National | National | Various | 1000-70027-01 | National - Absa Retail Sites |  | 2022-07-07 | 2022-12-15 |  | ASP-N00037 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Lucia Amunga |  |  | 2022 |  | Variou |  | LOUISR | 2022-06-22 |  | 21014 |  | Approved | 2022-06-23 | 2022-06-23 | 0 |  |  |  |  | C000022946 | CLOSED |  |  | LUCIA AMUNGA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000523 | Supply medical supplies to various Retai | Supply medical supplies to various Retail branches and Corporate buildingsThis request seeks approval for the supply of medical equipment and masks to various Absa Corporate and Retail branches nationally. Note: Supported by CRES OHS. Scope of works:Retail supplies: (R 405 314.28 incl.VAT) BVM PVC Adult incl Mask Size #5 (x 687) BVM PVC Paediatric incl Mask Size #3 (x 687) Anesthetic Mask # 01 Face (x 687) Clear PVC Bag with Zip and handle (x 687) Oversized Box Size 200 x 60 x 40cm (Weight 40kg) x 1 Corporate supplies: (R 21 022.92 incl.VAT) VWBV Ventria Adult PVC BVM Resuscitator (x 60) (incl PVC Adult Mask Size 5) VPVCM3 PVC Resuscitation (size 3) Mask Adult (x 60) VB Ventria PVC Bag Only (x 60) |  |  | National | National |  | 1000-70027-01 | Building not in our database |  | 2022-08-31 | 2022-12-15 |  | ASP-N00038 | REL BUDG AVAC RESA SETC: |  | false | true |  | Lucia Amunga |  |  | 2022 |  | Variou |  | LOUISR | 2022-06-22 |  | 37072.8 |  | Approved | 2022-06-23 | 2022-06-23 | 0 |  |  |  |  | C000023410 | IGNORE |  |  | LUCIA AMUNGA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000524 | Removal of Check In Desk signage at Va | Removal of Check In Desk signage at Various WC Absa branches (x8)The Check in Desk function is no longer being utilised at various Absa Retail branches (x8) in the Western Cape. The request was received from the region that signage indicating the Check In Desk be removed.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB and ENG support received. Scope of works:Removal of Check In Desk signage at: 77654X N1 City R1 942.81 Incl. VAT 77657X Roggebaai R1 821.72 Incl. VAT 77702X Somerset West R2 557.60 Incl. VAT 77913X Tableview R1 961.44 Incl. VAT 77946X Stellenbosch R2 650.75 Incl. VAT 36245X Table Bay Mall R2 054.59 Incl. VAT 77369X Durbanville R2 185.00 Incl. VAT 77083X Parow Centre R2 035.96 Incl. VAT |  |  | Region 2 | Western Cape | Various | 1000-70841-01 | Various |  | 2022-09-30 | 2022-10-31 |  | ASP-N00040 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-07-28 |  | 19070.37 |  | Approved | 2022-08-19 | 2022-08-19 | 0 |  |  |  |  | C000032514 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000525 | Noise annoyance survey s - Absa Pretoria | Noise annoyance survey s Absa Pretoria Campus & Auckland Park Call CentreCRES OHS requested that noise annoyance survey s be conducted at Absa Auckland Park and Pretoria Campus. The noise survey will be performed in office areas in accordance with the requirements of SANS 10103: The measurement and rating of environmental noise with respect to annoyance and to speech communication. The noisedosimetry survey will be performed to determine ambient noise levels in respect to annoyance and to speech communication at the call centres. Note: Supported by CRES OHS.Scope of works: Noise annoyance survey measurement and rating of environmental noise with respect to annoyance and to speech communication in accordance to SANS Code of Practice 10103 Personal Noise Exposure noisedosimetry survey will be performed to determine ambient noise levels in respect to annoyance and to speech communication at the call centres. Project duration: 1 2 days |  |  | National | National | Various | 1000-70027-01 | Various |  | 2022-08-18 | 2022-12-15 |  | ASP-N00041 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Lucia Amunga |  |  | 2022 |  | Variou |  | LOUISR | 2022-08-04 |  | 1260 | Approved |  | 2022-08-19 | 2023-10-07 | 14489.99 |  |  |  |  | C000060889 | PHASE11 | 2022-08-18 | 2022-12-15 | LUCIA AMUNGA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-12 | 12599.99 | 0 |  |  | C000032515 | 12600 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000526 | OHS Emergency Induction VideosOHS emerge | OHS Emergency Induction VideosOHS emergency induction videos where created by Global Access during Q2 2022 to educate our staff on our emergency procedures for our corporate sites. COVID 19 restrictions that were lifted on the 23rd June 2022 and some of the restrictions are no longer required, it was therefore requested that the video s be edited to align with the new changes made. Note: CRES OHS Approval obtained. Scope of works: Additional video shoot to edit some of the existing footage. Update the script to remove the reference to COVID 19 protocols and add a disclaimer that the use of face masks is voluntary. |  |  | National | National |  | 1000-70027-01 | Building not in our database |  | 2022-08-18 | 2022-12-15 |  | ASP-N00042 | CRTD AVAC: |  | false | true |  | Lucia Amunga |  |  | 2022 |  | Variou |  | LOUISR | 2022-08-11 |  | 0 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | 0 | IGNORE |  |  | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000527 | Operating Equipment (OE) Smalls - Procur | Operating Equipment (OE) Smalls Procurement of Hospitality, Front of house equipment and stirrer stick holders (CIP 2022)This request seeks approval to procure front of house equipment and stirrer stick holders for various Absa Corporate Sites. Based on the operational requirements at the Absa Regional Offices, additional stirrer stick holders are required in the employee break away areas/pause areas where we have hot beverage vending machines located to provide free hot beverages to Absa employees. We have found that there is no standard across the landscape and would like to create uniformity in providing a standard container to place the stirrer sticks in. Based on the equipment counts from inception stirrer stick holders were not accounted for.In addition to the above, there is a requirement to procure front of house smalls for Absa Alice Lane North, Absa Alice Lane South, Absa Towers North, Absa Towers West, Absa 270 Republic road, Absa Auckland Park, Absa Pretoria Campus due to an increase in business and in order to start implementing a specific look and feel in the Catering Landscape. We have only proposed equipment smalls at this stage where the demand is high and have included Alice Lane South due to the Alice Lane Campus numbers increasing. Note: Pending CRES VP. As per the agreement, there is a responsibility of 50% to be paid by Absa through the CIP Line R/PR/8/04 - CORP - BAU Catering and 50% to be for the cost of Bidvest. The total amount quoted for the Stirrer stick holders, Hospitality Smalls & Front of house smalls comes to R 655 159.60 including VAT.Scope of works: Supply of Hospitality equipment, Front of House equipment and stirrer stick holders for various Absa Corporate Sites.Cost Breakdown: Absa to contribute R 327 579.80 including VATAbsa Ridgeside @ R 1 351,25 Incl.VATAbsa Auckland Park @ R 25 432,25 Incl.VATAbsa 270 Republic @ R 24 645,65 Incl.VATAbsa Pretoria Campus @ R 25 646,15 Incl.VATAbsa Bridge Park @ R 2 300,00 Incl.VATAbsa Clearwater @ R 333,50 Incl.VATAbsa Towers North @ R 168 646,35 Incl.VATAbsa Towers West @ R 75 543,50 Incl.VATAbsa Alice Lane South @ R 164 310,85 Incl.VATAnsa Alice Lane North @ R 163 977,35 Incl.VATAbsa Meadowdale @ R 500,25 Incl.VATAbsa Lowerlong @ R 833,75 Incl.VATAbsa Nelspruit @ R 902,75 Incl.VATAbsa Polokwane @ R 736,00 Incl.VAT |  |  | National | National | Unknown | 1000-70027-01 | Unknown Building - not in our database | U | 2022-11-10 | 2022-12-15 |  | ASP-N00045 | CLSD BUDG AVAC SETC: |  | false | true |  | Lorri-Anne Louis |  |  | 2022 |  | U |  | LOUISR | 2022-10-24 |  | 327579.8 |  | 100 | 2022-10-27 | 2022-10-27 | 327579.8 |  | {"MANDT":"111","REFERENCE":70000527,"ONEVIEW":"Unknown","DATE01":"2022-09-01","DATE02":"2022-09-08","DATE03":"2022-09-29","DATE04":"2022-10-06","DATE05":"2022-10-27","DATE06":"2022-11-10","DATE07":"2022-12-15","DATE08":"2023-01-05","DATE09":"2022-12-25","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-10","FORECAST_END":"2022-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000063017 | PHASE11 | 2022-11-10 | 2022-12-15 | LUCIA AMUNGA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-20 | 284852 | 0 |  |  | C000063017 | 284852 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000528 | Automation of data transfer to the Envir | Automation of data transfer to the Environmental / Greenstone portal (CIP 2022)Energy and water consumption data reporting is currently handled manually and reported onto the reporting portal. As recommended by the external data assurance auditor (PWC), data reporting onto the repoting portal/platform is to be automated as far as possible in order to reduce risk of human error resulting from manual readings.Scope of Work The process is to aggregate and summate the data for the months for each site with smart electricity and water meters managed by EMS and export the full month data according to the Greenstone template formats for all the site onto the Greenstone SFTP platform for processing. Only sites with full month data should be exported into the SFTP for reporting purposes. A view to be built on the metering dashboard portal to captured data from the other utility service provider platform in other to consolidate the data into one single file for export onto the Greenstone SFTP.The data captured here include full month data from the various platform as well as the factors to calculate the consumptions for some of the following sites: 21335X Absa 270 Republic Road Main Incomer 21335X Absa 270 Republic Road Data Centre Summation 36225X Bridge Park Bridgeway Century City 70656X - Alice Lane North office 70656X - Alice Lane North Data Centre 36110X Samrand Data Centre | Ym5Wc2JDQT0g | l | Energy | National | Not site specific | 1000-70027-01 | Various Sites | U | 2022-11-10 | 2023-12-15 |  | ASP-N00046 | CLSD BUDG AVAC RESA SETC: | LOUISR | false | true | null | Wesigye Mukuru | na | This project is not site specific and is systems driven to automate data transfer from the metering portal to Greenstone reporting portal | 0 |  | U |  | LOUISR | 2022-10-26 |  | 222456 | Project approved as per requirements by external auditor (PWC) in order to mitigate against human error when capturing environmental data. | 100 | 2022-10-27 | 2022-10-27 | 222456 | R222456 approved at CB on 25th October 2022. 50% of the project value (R111 228) rolled over into 2023 FY. | {"MANDT":"111","REFERENCE":70000528,"ONEVIEW":"Unknown","DATE01":"2022-09-01","DATE02":"2022-09-08","DATE03":"2022-09-29","DATE04":"2022-10-06","DATE05":"2022-10-27","DATE06":"2022-11-25","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-25","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtMTgvMDcvMjAyMy0gUHJvamVjdCBhbmQgaW52b2ljaW5nIGNvbXBsZXRlZA==","RATING":""} |  |  | C000062473 | PHASE11 | 2022-11-25 | 2023-04-30 | LUCIA AMUNGA | Floyd Mofokeng | 23000538 |  |  |  |  | 2023-01-19 | 193440 | 0 |  |  | C000045995 | 193440 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000529 | Replacement of Operating Hour decals at | Replacement of Operating Hour decals at Various Limpopo Absa branches (X8)The operating hour decals is no longer in alignment with current branches trading hours at various Absa Retail branches (x8) in Limpopo. The request was received from the region to replace the existing decals to reflect the new operating hours. Note: Approved by RBB. This project was prioritised by the region as it possesses reputational damage and spend will be allocated from the regional minor works budget. Project to be funded from Opex budget as agreed with the region and Absa Finance.Scope of WorkReplacement of Trading Hour signage at: 76709X Ba Phalaborwa (Eden Square) Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 37073X Makhado Crossing Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 76808X Absa Tzaneen Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 78873X Mutsindo Mall Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 36254X Thavhani Mall Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 35151X Tubatse Crossing Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 36240X Burgersfort Strip existing and install new banking hour decal R5 440.48 VAT Inclusive 78979X Pick & Pay (Limpopo Mall) Strip existing and install new banking hour decal R5 440.48 VAT Inclusive |  |  | Region 3 | Limpopo |  |  | Building not in our database |  | 2022-11-30 |  |  | ASP-N00047 | REL BUDG AVAC SETC: |  | false | true |  | Justice Mogadime |  |  | 2022 |  | Leaseh |  | NOMNGANGAL | 2022-11-07 |  | 3784.67 |  | 100 | 2022-11-10 | 2022-11-10 | 0 |  |  |  |  | C000052160 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000530 | Signage replacements : Decals and Vinyl | Signage replacements : Decals and Vinyl (19991231ctive)The Absa PMO/Design Team received an instruction from the regional RBB team to urgently replace the trading hour decals at Absa Garden Route Mall, Langeberg Mall and the Lifestyle Graphics on the shopfronts at Absa George. The Absa PMO/Design Team issued an instruction to the signage vendor to proceed with the replacement which was completed in October 2022. The request was received from Absa PMO/Design Team for Bidvest to issue a Purchase Order to the signage vendor as the work was completed.Note: Regional RBB cost approval received and Artwork was approved . Work completed in October 2022.Scope of works:(1) Absa George: 79394X R 107 635.40 incl.VAT Remove existing, print and apply new Lifestyle graphics to the shopfront. Windows 1 and 2: 1180x 2735mm Windows 3 9: 1418x 2735mm(2) Absa Langeberg Mall: 78529X R 5 054.25 incl.VAT Remove the existing decal and replace with new. Sizes: 700x1300mm(3) Absa Garden Route Mall: 78863X R 5 054.25 incl.VAT Remove the existing decal and replace with new. Sizes: 700x1300mm |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street-York St-George | N | 2022-11-30 | 2022-12-31 |  | ASP-N00048 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Laxine Maliffe |  |  | 2022 |  | U |  | CEASARS | 2022-11-16 |  | 117743.9 |  | 100 | 2022-12-01 | 2022-12-06 | 117743.9 |  | {"MANDT":"111","REFERENCE":70000530,"ONEVIEW":"79394X","DATE01":"2022-11-01","DATE02":"2022-11-09","DATE03":"2022-11-09","DATE04":"2022-11-30","DATE05":"2022-12-06","DATE06":"2022-12-06","DATE07":"2022-12-06","DATE08":"2023-02-06","DATE09":"2023-03-16","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:8:0:21:6:0:0:62:38:22","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-06","FORECAST_END":"2022-12-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmV0cm9zcGVjdGl2ZSBCaWxsaW5nIG9mIHdvcmsgcmVxdWVzdGVkIGJ5IEFic2EuCjYgRmViIC1GaW5hbCBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000065397 | PHASE11 | 2022-12-06 | 2022-12-06 | RODERICK NEVAY | Nokuthula Manzini | 23000536 |  |  |  |  | 2023-02-01 | 102386 | 0 |  |  |  | 102386 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000531 | Minor Works - Absa Oude Bloemhof (CIP 20 | Minor Works Absa Oude Bloemhof (CIP 2022)Absa Oude Bloemhof is a freehold building divided into the branch (GF and 1st floor) and offices that are occupied by external tenants ( 2nd to 4th floor). A revamp was done in 2019 to the branch and common areas of the building. The changing/store room located in the basement parking L1 is utilised by the cleaning and security staff. This was excluded from the scope during the previous revamp. The wall and floor finishes of this area have deteriorated over the years and require a revamp. Furthermore, the unisex ablution facility which is utilised by these staff members, located between L1 and GF, has cracked wall and floor tiles posing a risk and requires an upgrade. In addition, it is recommended that a dedicated change room be created for the cleaning and security staff alongside the existing room utilising 1 x parking bay adjacent to the existing room.Note: Supported by FM, Africa Security , Engineering and Absa Design.Scope of works:Storeroom Prepare and paint ceiling ,internal and external walls - 56 sqm Prepare and Tile Flooring 15sqm Paint door - 1 of each Supply and Install Blinds - 1 of each (800x800mm) Supply and Install Metal Lockers - 3 of each( 2 Door Steel locker 1800 ht X 300 w X 450 d) Supply bumper rail as per the Absa specChange Room Construct drywall and paint 13lm Supply male and female signage to the newly fitted doors Install lights (x2) on both female and male section and provide COC. Supply benches 2 of eachAblution Facility Uplift walls tiles, skim and paint - 29sqm Uplift floor tiles and replace with new 6sqm Paint ceiling area white 4sqm Install 1 x toilet suite including basin with splashback and tap Install 600x600mm Mirror Repaint door 1 of each Manned guard service for the project |  |  | Region 2 | Western Cape | 22491X | 1000-70866-01 | Absa Oude Bloemhof Building, Cnr Van Ryneveld & Plein Streets, Stellenbosch |  | 2022-09-01 | 2022-09-30 |  | ASP-WC0061 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2021-01-26 |  | 205256.48 |  | Approved | 2022-08-11 | 2022-08-11 | 0 |  |  |  |  | C000061033# | CLOSED | 2022-09-01 | 2022-09-30 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-12 | 10855.47 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000532 | Waterproofing Due Diligence - Item for N | Waterproofing Due Diligence Item for NotingAbsa Vredenburg is a freehold building. The building has experienced various roof leaks during the rain seasons. Reactive maintenance and patchwork has been done over the years. When an initial site visit was conducted with waterproofing vendors the roof was found to be in a very poor condition and the overall integrity of the roof was questioned (Parapets and IBR Sheeting). It was recommended that engineering consultants be appointed in order to do a full assessment and provide recommendations to address the findings. Consultants were approached and it was recommended that both a structural engineer and waterproofing consultant do the inspection to advise in terms of the integrity of the roof and waterproofing solutions.Note: Project is part of the prioritised Waterproofing projects for 2022 with a budget of R850k. Approved Out of Cycle on 20 May 2022.Scope of works:Due Diligence Report Structural Engineer and Waterproofing Consultant to conduct DD Provide a report detailing recommendations and specifications for the repair work requiredConstruction Inspections Allow for 2 additional site visits for the team to inspect Work in Progress and to conduct Final Inspection upon completion. |  |  | Region 2 | Western Cape | 77722X | 1000-70852-01 | Absa Vredenburg-Main St-Vredenburg |  | 2022-05-30 |  |  | ASP-WC0119 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | F |  | CEASARS | 2021-06-29 |  | 40101.99 |  | 100 | 2022-05-25 | 2022-05-20 | 40101.99 |  | {"MANDT":"111","REFERENCE":70000532,"ONEVIEW":"77722X","DATE01":"2022-03-21","DATE02":"2022-03-28","DATE03":"2022-04-18","DATE04":"2022-04-25","DATE05":"2022-05-16","DATE06":"2022-08-08","DATE07":"2023-05-08","DATE08":"2023-07-28","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"316:7:21:7:21:84:273:81:34:11","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-08-08","FORECAST_END":"2023-05-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWF5IGZpbmFsIHJlcG9ydCByZXF1ZXN0ZWQgZnJvbSBEU1AKMjAgSnVseSBSZXBvcnQgU3RpbGwgb3V0c3RhbmRpbmcKMjAgSnVseSBGb2xsb3dlZCB3aXRoIERTUC4gSW52b2ljZSByZWNlaXZlZCwgaG93ZXZlciwgcmVwb3J0IHBlbmRpbmcKMjcgSnVseSBQT0Mgc2VudCB0byBBYnNhIGZvciBmaW5hbCBzaWdub2ZmCjI4IEp1bHkgUE9DIFN1Ym1pdHRlZCB0byBmaW5hbmNl","RATING":"Low"} |  |  | C000015818 | PHASE11 | 2022-08-08 | 2023-05-08 | RODERICK NEVAY | Michael Maluleka | 23000590 |  |  |  |  | 2022-05-30 | 34871.3 | 0 |  |  | C000015818 | 34871.3 |  | 1754.85 |  | 0 | 0 |  | 0 |  | 0
70000533 | Minor Works - Absa Langebaan (CIP 2022)T | Minor Works Absa Langebaan (CIP 2022)The client facing area received a refresher in 2016/7, however the back office areas were not addressed as part of the project. The back area facilities have deteriorated over a period of time and require a revamp. The back office/pause area have filing cupboards that have shelves that are missing and they require restructuring so as to effectively utilise the current storage space. For the back office ceiling tiles; some are stained and mismatched due to previous leaks and repairs. The existing carpets are soiled, worn, loose, mismatched and can no longer be effectively cleaned. In the kitchen area the cupboard edges are chipped and some of the vinyl tiles are cracked. In the ablution some of the vinyl tiles are cracked and require replacement. The request is to upgrade the kitchen, ablution and back office so as to meet the required corporate identity.Note: RBB approval received; Engineering support received. This project was prioritised by the region and spend will be allocated from the regional minor works budgets. Scope of works:BACK OFFICE Strip and remove 2 x cupboards Replace ceiling tiles (Georgian) - 12sqm Replace carpet tiles (Belgotex Accelerate Boost) - 12sqm Prepare and paint walls - 36sqm Supply and fit 2 x cupboards as follow: [1775w x 900h x 500d; 1870w x 2100h x 600d]KITCHEN Strip and fit new kitchen cupboard including single sink and mixer tap (hot & cold water) Supply and fit 200 x 200 white splash back tiles above sink - 2sqm Strip the existing vinyl, prepare and lay 2mm Moor Grey - 1.89sqm Prepare and paint walls and ceiling including 1 x door (800 x 2100)- 16sqmABLUTION Strip the existing vinyl, prepare and lay 2mm Moor Grey - 2.06sqm Strip and fit new sanitary ware - toilet basin and mixer (hot & cold water) Supply and fit 200 x 200 white splash back tiles above basin Supply and fit 1 x mirror - 600 x 600 Prepare and paint walls and ceiling including 1 x door (800 x 2100). Covid wipe down will be done by the contractor daily on all touch points. |  |  | Region 2 | Western Cape | 77019X | 1000-70796-01 | Absa Langebaan, Marra Square, 2B Bree Street, Langebaan |  | 2022-02-15 | 2022-03-31 |  | ASP-WC0178 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2021-11-16 |  | 185134.54 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2910274 | CLOSED | 2021-02-15 | 2022-03-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000534 | Installation of roller shutter battery b | Installation of roller shutter battery back up & trap door (2022 CIP)During the minor project in 2021 a new roller shutter door was installed to replace the stacking door at the main entrance to the branch. No provision was made to manually override the door during the power outages. This was highlighted/detected during load shedding when the landlord s generator which supplies the branch during these periods did not kick in. The branch could not manually override the existing roller shutter in order to close the door. It was also noted that no trap door was created in the bulk head in order to access the existing motor/control mechanism. The request is for the installation of a battery back up motor to manual override during power outages and to create a trap door in order to access and service the motor.Note: Supported by Engineering, AFS and RBB.Scope of Works: Remove existing AC motor and controls. Supply & install 1 x DC motor including battery back up and 4 x hand remotes. Create new trap door in existing bulk head (600 x 600 opening) situated inside the branch adjacent to the existing shopfront, utilising T frame and a return air grille. Prepare and repaint the bulkhead to match the existing colour. Contractor to do a Covid wipe down on completion. |  |  | Region 2 | Western Cape | 77398X | 1000-70829-01 | Absa Kenilworth Centre, 76 Chichester road, Claremont |  | 2022-03-01 | 2022-03-02 |  | ASP-WC0179 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2021-12-07 |  | 27751.97 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2901605 | CLOSED | 2022-03-01 | 2022-03-02 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000535 | Replacement of UPS Batteries | Replacement of UPS Batteries |  |  | Region 2 | Western Cape | 78111X | 1000-70885-01 | Absa De Doorns, |  | 2022-01-31 | 2022-02-28 |  | ASP-WC0182 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2021-12-09 |  | 25000 |  | Approved | 2022-01-19 | 2022-01-19 | 0 |  |  |  |  | 2896121 | CLOSED | 2022-01-31 | 2022-02-28 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000536 | Replacement of new LED lights in the bra | Replacement of new LED lights in the branch |  |  | Region 2 | Western Cape | 36245X | 1000-70762-01 | Absa Table Bay Mall, |  | 2021-12-15 | 2022-01-31 |  | ASP-WC0184 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2021-12-09 |  | 140033.93 |  | Approved | 2022-01-19 | 2022-01-19 | 0 |  |  |  |  | 2896102 | CLOSED | 2021-12-15 | 2022-01-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000537 | Installation of new roller shutter door | Installation of new roller shutter door at the ATM area (2022 CIP) |  |  | Region 2 | Western Cape | 77781X | 1000-70858-01 | Absa Lansdowne |  | 2022-02-14 | 2022-04-08 |  | ASP-WC0185 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-19 |  | 49383.67 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2901604 | CLOSED | 2022-02-14 | 2022-04-08 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000538 | UPS Battery Replacement (Item for noting | UPS Battery Replacement (Item for noting) (2021 Accrual List) |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Absa Bridge Park, Bridgeway |  | 2021-10-21 | 2021-10-21 |  | ASP-WC0186 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-21 |  | 7787.57 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900400 | CLOSED | 2021-10-21 | 2021-10-21 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000539 | Replacement of damaged UPS (19991231ctiv | Replacement of damaged UPS (19991231ctive) |  |  | Region 2 | Western Cape | 76946X | 1000-70791-01 | Absa Cape Town International Airport |  | 2022-01-25 | 2022-02-28 |  | ASP-WC0187 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-24 |  | 17500 |  | Approved | 2022-01-25 | 2022-01-25 | 0 |  |  |  |  | 2898225 | CLOSED | 2022-01-25 | 2022-02-28 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000540 | Replacement of an HVAC condenser unit an | Replacement of an HVAC condenser unit and installation of new security cages (2022 CIP Item for Noting) |  |  | Region 2 | Western Cape | 78113X | 1000-70887-01 | Absa Malmesbury, |  | 2022-02-22 | 2022-03-31 |  | ASP-WC0188 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-01 |  | 139565.51 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2900063 | CLOSED | 2022-02-22 | 2022-03-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000541 | Installation of ClearVu Fence (CIP 2022) | Installation of ClearVu Fence (CIP 2022) |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester |  | 2022-03-07 | 2022-03-31 |  | ASP-WC0189 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-02-01 |  | 147051.31 |  | Approved | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2902833 | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000542 | Replacement of UPS Batteries (2022 CIP) | Replacement of UPS Batteries (2022 CIP) |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Absa Bridge Park, Bridgeway, Century City |  | 2022-02-14 | 2022-02-19 |  | ASP-WC0190 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-02-09 |  | 350000 |  | Approved | 2022-02-10 | 2022-02-10 | 0 |  |  |  |  | 2901614 | CLOSED | 2022-02-14 | 2022-02-19 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000543 | TI - Replacement of Carpets | TI Replacement of Carpets |  |  | Region 2 | Western Cape | 77946X | 1000-70866-01 | Absa Oude Bloemhof Stellenbosch |  | 2022-03-14 | 2022-04-29 |  | ASP-WC0192 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-02-21 |  | 66503.95 |  | Approved | 2022-02-22 | 2022-02-22 | 0 |  |  |  |  | 2904058 | CLOSED | 2022-03-14 | 2022-04-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000544 | Replacement of HVAC Units | Replacement of HVAC Units |  |  | Region 2 | Western Cape | 77019X | 1000-70796-01 | Absa Langebaan |  | 2022-04-18 | 2022-04-30 |  | ASP-WC0194 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-02 |  | 220250 |  | Approved | 2022-03-17 | 2022-03-17 | 0 |  |  |  |  | 2910103 | CLOSED | 2022-04-18 | 2022-04-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000545 | Operating Equipment (OE) Smalls Function | Operating Equipment (OE) Smalls Function Equipment (19991231ctive)Due to the Covid 19 Pandemic, Absa requested that Bidvest Catering Services serve meals for functions in individually sealed Bio degradable take away like containers, as it was deduced that this protocol would circumvent the possible spread of the Covid 19 infection. A function took place in October 2021 for Absa Exco at Absa Alice Lane and the request came through that an alternative serving style was required. The solution used was that the meals be served with a cloche covering the plate. In November the Absa Bridge Park Catering team received a request for a similar function from the Executive office. As the Absa Bridge Park Catering Services did not have cloches in stock, it was requested that cloches be procured to support this hospitality offering function. These stainless steel cloches are a requirement implemented in order to execute for the executive functions due to Covid requirements as well as future use. This 19991231ctive request is to recover the cost for the new operating equipment. Once off charge for Absa to be billed 100% = R6 842.50 inclusive of VAT. Note: Supported by CRES VP. Delivery date: 22.11.2021 and approval obtained from Absa finance to allocate against catering budgetScope of works: Supply stainless steel dome cloches ( x20) |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Absa Bridge Park, 5 & 6 Bridgeway Road,Century City |  | 2022-03-15 | 2022-03-15 |  | ASP-WC0195 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-02 |  | 6842.5 |  | Approved | 2022-04-07 | 2022-04-07 | 0 |  |  |  |  | C000019964 | CLOSED | 2022-03-15 | 2022-03-15 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000546 | Replacement of damaged condenser unit (I | Replacement of damaged condenser unit (Item for noting) (2021 Accrual) |  |  | Region 2 | Western Cape | 22225X | 1000-70707-01 | Absa Tokai Junction |  | 2021-12-08 | 2021-12-31 |  | ASP-WC0196 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-01-21 |  | 37256.09 |  | Approved | 2022-02-03 | 2022-02-03 | 0 |  |  |  |  | 2900487 | CLOSED | 2021-12-08 | 2021-12-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000547 | Supply and fit new bumper rails in offic | Supply and fit new bumper rails in officesAbsa Kenilworth branch had a minor refresh project in 2020, however the bumper rails were not included as part of the project. Due to the limited space in the offices between the chairs and walls, the walls are getting damaged by the chairs. The request is to fit new bumper rails in order to minimize the maintenance and associated cost.Note: RBB approval received. Bumper rails are as per RBB specifications. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Supply and fit new PVC bumper rails in x 5 Offices as per Absa specification. Work will take place after hours. Covid wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | 77398X | 1000-70829-01 | Absa Kenilworth Centre,76 Chichester Road,Claremont |  | 2022-03-31 | 2022-04-30 |  | ASP-WC0197 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-04 |  | 9937.75 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913205 | CLOSED | 2022-03-31 | 2022-04-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000548 | Minor Works - Absa Barrydale (CIP 2022)T | Minor Works Absa Barrydale (CIP 2022)The client facing areas received a refresher in 2016/7 , however the back office areas were not addressed as part of the project. The ablution and kitchen facilities have deteriorated over a period of time and require a revamp. In the kitchen area the cupboards are old, damaged and the branch is currently using a kettle for hot water which is not in line with the current OHS standards. In the ablution, the sanitary fittings have worn out and are currently discoloured/rusting internally. The vinyl tiles in both the kitchen and ablution area are cracked, stained and require replacement. The request is to upgrade the kitchen and ablution area along with the installation of a Hydroboil with inline filters.Note: RBB Regional Approval Received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Strip and fit new kitchen cupboard including single sink and tap Supply and fit splash back tiles above sink [1800x600mm] Supply and Install a 2.5Liter Hydroboil with inline filter Issue electrical and Plumbing COC Strip the existing vinyl floor tiles, prepare and lay signature grey tiles in ablution and kitchen - 67 m2 Strip the existing wall tiles, skim and paint wall in ablutions - 40m2 Strip and fit new sanitary ware - 2 x ( toilet, basin and tap) Supply and fit splash back tiles above basins Supply and fit mirror - 2 No (600 x 600mm) Remove and reinstall existing hygiene equipment Prepare and paint walls (Absa Grey) and ceilings (White) in Passage and Kitchen 75m2 Varnish Doors and Repaint Frames 5 No Manned Guarding Services to be provided. Contractor to do Covid wipe down daily on all touch points and deep clean on completion. |  |  | Region 2 | Western Cape | 78087X | 1000-70877-01 | Absa Barrydale,37 Van Riebeeck Street,Barrydale |  | 2022-05-01 | 2022-06-30 |  | ASP-WC0198 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-07 |  | 289967.6 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2913211 | CLOSED | 2022-05-01 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000549 | Additional Cupboard in Backoffice/Pause | Additional Cupboard in Backoffice/Pause Area (CIP 2022)Absa Clanwilliam had a minor revamp project to downsize the branch in 2016/2017. There is currently insufficient storage space in the backoffice/pause area which has resulted in house keeping issues due to lack of storage. This request is for the installation of a new cupboard for the storage of stationery and cleaning material.Note: RBB Design was consulted, RBB Regional Approval and Security Clearance Received. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works: Supply and install 1 x Melamine white 2 door cupboard (2500h x 900w) Covid wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | 77526X | 1000-70836-01 | Absa Clanwilliam, Die Kunshuis21 Main Road, Clanwilliam |  | 2022-03-30 | 2022-04-30 |  | ASP-WC0199 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-07 |  | 14274.5 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912262 | CLOSED | 2022-03-30 | 2022-04-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000550 | Request for Vari Electric Desk (White) ( | Request for Vari Electric Desk (White) (CIP 2022) |  |  | Region 2 | Western Cape |  | 1000-70877-01 | Building not in our database |  | 2022-03-31 | 2022-04-29 |  | ASP-WC0202 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-10 |  | 12903 |  | Approved | 2022-03-10 | 2022-03-10 | 0 |  |  |  |  | 2908662 | IGNORE | 2022-03-31 | 2022-04-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000551 | Replacement of HVAC UnitsThe existing HV | Replacement of HVAC UnitsThe existing HVAC units in this branch are 18 years old and have reached the end of their economic life. Numerous repairs were carried out on the units and the service reports highlighted that the failures were due to the units reaching end of life. The compressors for both units are faulty and it was recommended to replace the units instead of repairing them for cost saving purposes. Note: Supported by Engineering. The design has been optimised for environmental considerations and the equipment is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. RBB and Africa Security support obtained. Scope of works: Supply and Install 1 x Samsung AC250 KNH Ducted Inverter at the Banking Hall (25kW) Supply and Install 1x Samsung AC140 KNH Ducted Inverter at the Insurance Broker Area (14kW) Replace existing isolator switches and issue an Electrical COC. Gas & Equipment Disposal certificates will be supplied. New duct transformations to be installed. Ceiling and Patchwork Repairs Manned Guarding Service for the duration of the project Covid wipe down to be done by contractor daily on all touch points. |  |  | Region 2 | Western Cape | 77877X | 1000-70863-01 | Absa Robertson,22 Paul Kruger Street,Robertson |  | 2022-05-02 | 2022-06-30 |  | ASP-WC0203 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-14 |  | 274000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912264 | CLOSED | 2022-05-02 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000552 | Replacement of Eaton UPS Batteries (CIP | Replacement of Eaton UPS Batteries (CIP 2022)The UPS Batteries at Absa Lower Long were identified and included in the CIP for 2022 to be replaced as they have reached End of Life (EOL). The contracted maintenance vendor was consulted and recommended the replacement of these batteries. The expected lifespan on these batteries are 3 to 5 years. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Included in the EOL CIP 2022 budget for replacement. Disposal certificate will be provided. CIP 2022 budget allocated was R131k.Scope of works:Supply and Install Eaton UPS Batteries as per EOL CIP 2022 LIST 93PM 40KVA x 2 Output/Bypass 3/N/PE 380/400/415V 384 x 12V 34W 9AH Batteries Disposal certificate will be provided on completion. COVID wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long,31 Lower Long Street, Cape Town |  | 2022-04-29 | 2022-06-30 |  | ASP-WC0204 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-14 |  | 182000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912258 | CLOSED | 2022-04-29 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000553 | Replacement of ABB UPS Batteries (CIP 20 | Replacement of ABB UPS Batteries (CIP 2022)The UPS Batteries at Absa Santyger were identified and included in the CIP 2022 to be replaced as they have reached End of Life (EOL). The contracted maintenance vendor was consulted and recommended the replacement of these batteries. The expected lifespan on these batteries are 3 to 5 years. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Engineering supported. Included in the EOL CIP 2022 budget for replacement for R25 000. Disposal certificate will be provided.Scope of works:Supply and Install ABB UPS Batteries at the following branches as per EOL CIP 2022 LIST: 78188X Absa Santyger: 15kVA ABB Power scale Current Load Output 35% 80 x Batteries (R21 253.28 including VAT) Disposal certificates will be provided on completion. Covid wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | 78188X | 1000-71447-01 | Absa Santyger, Suntyger Building,313 Durban Road, Cape Town |  | 2022-04-29 | 2022-06-30 |  | ASP-WC0205 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-14 |  | 25000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912266 | CLOSED | 2022-04-29 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000554 | Replacement of Generator Starter Batteri | Replacement of Generator Starter Batteries (CIP 2022)The generator batteries at Absa Bridge Park East & West, have reached their End of Life. These starter batteries were installed more than 5 years ago. Replacing the batteries will ensure greater reliability, increased uptime of critical load and reduced potential failures on critical equipment. Note: Included in the EOL CIP 2022 budget for replacement. Considerations for the Absa Bridge Park dilaps were discussed and it was agreed that this work would proceed. CIP 2022 budget allocated was R32k.Scope of works: Supply and install Generator Starter Batteries as per EOL CIP 2022 LIST: Deltec Battery 105A/h (12 Months Warranty) Genset 1 400KVA 2 x batteries Genset 2 400KVA 2 x batteries Genset 3 880KVA 4 x batteries Genset 4 880KVA 4 x batteries Covid wipe down to be done by contractor on all touch points. |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Absa Bridge Park, 5&7 Bridgeway Road,Century City |  | 2022-04-14 | 2022-05-31 |  | ASP-WC0206 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-16 |  | 37000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912270 | CLOSED | 2022-04-14 | 2022-05-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000555 | Minor Works - Absa Riebeek West (CIP 202 | Minor Works Absa Riebeek West (CIP 2022)Absa Riebeek West had minor works done in 2016/7 , however the teller, kitchen and ablution areas were not addressed as part of the project. These areas (wall and floor finishes) have deteriorated over a period of time and require a revamp. The ceiling tiles in the branch are mismatched due to the previous replacements and the unavailability of old specification tiles. The branch is currently using a kettle for hot water which is not in line with the current standards. The request is to upgrade the teller, kitchen and ablution area so as to meet the required corporate identity.Note: RBB Regional Approval Received. This project was prioritised by the region and spend will be allocated from the regional minor works budget.Scope of works:KITCHEN AND ABLUTION Supply and install a 2.5liter hydroboil with inline filter (3 permanent staff, excluding security) Issue Electrical and Plumbing COC Replace ceiling tiles (1200x600mm) - 9m2 Strip existing vinyl flooring and replace with tiles (Signature Grey 600x600) - 9m2 Paint walls - 43m2 Remove and reinstall existing hygiene equipment TELLER AREA Remove and reinstate ceiling cage - 20m2 Replace ceiling tiles (1200 x 600mm) - 25m2 Paint walls 40m2 Replace carpet tiles as per Absa spec - 25m2 Remove and reinstall cameras and downlightsBANKING HALL Replace ceiling tiles (1200 x 600mm) - 15m2 Paint skirtings - 10 lm Remove and reinstall cameras and downlights Covid wipe down daily on all touch points and deep cleaning of the site will be done by contractor+E45 |  |  | Region 2 | Western Cape | 78135X | 1000-70892-01 | Absa Riebeek West, 13 Voortrekker Street,Cape Town |  | 2022-06-01 | 2022-09-30 |  | ASP-WC0207 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-16 |  | 211369.38 |  | Approved | 2022-05-04 | 2022-05-04 | 0 |  |  |  |  | C000060127# | CLOSED | 2022-06-01 | 2022-09-30 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-09 | 610.99 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000556 | Lift Controller UpgradeAbsa Paarl is a f | Lift Controller UpgradeAbsa Paarl is a freehold building. The existing lift is approximately 20years old and reaching its End of Life. The lift recently failed and the Original Equipment Manufacturer (OEM) rebuilt one of the existing control boards as these spares are obsolete and can no longer be sourced. The options considered were to upgrade the existing control mechanism which would extend the lifespan of the lift by +/ 5 years. The second option considered was for a full lift replacement.Recommendation from Engineering is to upgrade the controller as the preferred option at this stage and the lift upgrade will be deferred.Note: This was supported by the region and prioritised by Engineering. Scope of works: Replace the logic prints with PLC in the existing lift controller Testing and Commissioning Covid wipe down will be done by the contractor daily on all touch points. |  |  | Region 2 | Western Cape | 77053X | 1000-70798-01 | Absa Paarl,Cnr Main & Nantes Street, Paarl |  | 2022-08-01 | 2022-12-30 |  | ASP-WC0208 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-03-17 |  | 300000 |  | Approved | 2022-03-24 | 2022-03-24 | 0 |  |  |  |  | 2912269 | CLOSED | 2022-08-01 | 2022-12-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000557 | Galvanised barrier below HVAC CondenserA | Galvanised barrier below HVAC CondenserAbsa Tokai has HVAC condensing units installed on the wall in the service alley behind the branch which is utilised by the delivery trucks. These units are installed at the highest possible level on the wall. There have been repeated incidents where trucks have driven into these units due to limited visibility resulting in full replacements of the condensers. This request is for a galvanised barrier to be installed on ground level below the HVAC Condenser which will be painted yellow/black to ensure visibility.Note: Supported by Engineering. To be funded from CIP 2022 cancelled project budget allocated to Atlantis Generator was R629k.Scope of works: Manufacture and install a galvanised, yellow/black barrier under the HVAC Condenser [1m wide by 1.5m long by 1m protruding from the wall] Contractor to do Covid wipe down daily on all touch points. |  |  | Region 2 | Western Cape | 77877X | 1000-70707-01 | Absa Tokai Junction, Shops G22, G23, G24 & G25A,238 Main Road, Tokai |  | 2022-05-01 | 2022-06-30 |  | ASP-WC0209 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-03-24 |  | 16057 |  | Approved | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 2912888 | CLOSED | 2022-05-01 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000558 | Minor Works - Absa Porterville (CIP 2022 | Minor Works Absa Porterville (CIP 2022)Absa Porterville had a refresh approximately 5 years ago, however the back area was not addressed as part of the project. The existing kitchen cupboards have deteriorated over time and do not make provision for the microwave and a fridge. The existing 90litre fridge is undersized for the branch which has a complement of 7 people, and it is showing signs of rust and leaks due to wear and tear over the years. The vinyl flooring in both the kitchen and ablution area is cracked, stained and require replacement. The request is to upgrade kitchen cupboards along with the procurement of a new fridge and to replace vinyl flooring in the kitchen and ablution areas.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. Engineering clearance received. RBB approval received on cost breakdown. Scope of works:KITCHEN AND ABLUTION Supply and fit new kitchen cupboard with microwave cabinet [Floor Unit 1800mm in Length with Post Form Top; Wall Unit 2000mm in Length] Supply and fit new double sink and tap as per Absa spec including splash back Supply and deliver KIC 170L Top freezer fridge. Dispose of old unit and issue of disposal letter. Varnish doors and door frames no 7 Replace vinyl flooring in kitchen and ablution with tiles (signature grey ceramic tiles ) 30sqm Covid wipe down daily on all touch points by contractor Manned Guard Services for the project |  |  | Region 2 | Western Cape | 78133X | 1000-70891-01 | Absa Porterville,29 Voortrekker Street,Porterville |  | 2022-06-01 | 2022-09-30 |  | ASP-WC0211 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-13 |  | 119460.97 |  | Approved | 2022-05-18 | 2022-05-18 | 0 |  |  |  |  | C000062057 | CLOSED | 2022-06-01 | 2022-09-30 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-18 | 17130.1 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000559 | Minor Works - Absa Lansdowne (CIP 2022)A | Minor Works Absa Lansdowne (CIP 2022)Absa Lansdowne had a refresh +/ 5 years ago, however the back area was not addressed as part of the project. The wall and floor finishes (paint and carpets) have deteriorated over the years and require a revamp. The existing carpets are soiled, worn, mismatched and can no longer be effectively cleaned. The request is to replace the carpets and paint the walls in order to meet the corporate standards.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works: Replace carpets with new spec - 30sqm Paint Skirtings 40m Paint Walls - 140sqm Paint Doors and Frames 4 of each Contractor to do a daily Covid wipe down on all touch points Manned guard service for the project. |  |  | Region 2 | Western Cape | 77781X | 1000-70858-01 | Absa Lansdowne,AR Rasheed Centre,Kanarie Road,Lansdowne |  | 2022-09-01 | 2022-09-30 |  | ASP-WC0213 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-04-20 |  | 59385.4 |  | Approved | 2022-06-09 | 2022-06-09 | 0 |  |  |  |  | C000019958 | CLOSED | 2022-09-01 | 2022-09-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000560 | WaterproofingAbsa Caledon has experience | WaterproofingAbsa Caledon has experienced various roof leaks during the rainy seasons in the back office area. Reactive maintenance and patchwork has been done over the years, however due to the wear and tear of the original waterproofing, the request has been made that the waterproofing is redone where affected and a warranty be provided.It is recommended that the existing bitumen torch on be removed and replaced with new to the affected area.Note: Project is part of the prioritised Waterproofing projects for 2022 with a budget of R50k. Workmanship warranty for 7 years and product warranty for 10 years.Scope of works: Remove existing waterproofing on the affected area (30sqm). Create a slope towards the outlets and full bores for proper water drainage. Clean, prepare and prime affected areas with ABE Bituminous Primer (30sqm). Apply ABE 4mm torch on with 100mm overlaps (30sqm). Overcoat the area with ABE silver coat aluminium paint (83sqm) Fix and secure the gutter Manned Guard Services for the project |  |  | Region 2 | Western Cape | 77399X | 1000-70830-01 | Absa Caledon,6 Donkin Square,Caledon |  | 2022-09-01 | 2022-09-30 |  | ASP-WC0215 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-04-28 |  | 57971.91 |  | Approved | 2022-05-18 | 2022-05-18 | 0 |  |  |  |  | C000015822 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000561 | Disposal of generator | Disposal of generator |  |  | Region 2 | Western Cape | 77151X | 1000-71429-01 | Absa Liberty Promenade |  | 2022-07-01 |  |  | ASP-WC0216 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-04 |  | 69382.71 |  | Approved | 2022-08-16 | 2022-08-16 | 0 |  |  |  |  | C000061024# | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-12 | 11243.58 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000562 | Replacement of HVAC Units- Absa Houtbay | Replacement of HVAC Units Absa Houtbay (CIP EOL List 2022)The existing HVAC unit servicing the banking hall and offices in the branch is 20 years old and has reached the end of its economic life. Spares for this unit are not readily available resulting in extended down time. In addition due to the heat build up in the ATM room it was requested that new unit to be installed in the ATM room. The request is for the Banking Hall HVAC to be replaced and for a new HVAC to be installed in the ATM room.Note: Supported by Engineering, RBB and Africa Security. The design has been optimised for environmental considerations and the equipment is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. Scope of works: Supply and Install 1 x Samsung hideaway AC250KNH (25kW) in Banking Hall Supply and Install 1 x Samsung AR18TSHC (5.2kW) in the ATM room Replace existing isolator switches, provide new power supply for the new ATM unit and issue an Electrical COC. Install new copper gas piping and control cables. External pipework to be enclosed in galvanised trunking Gas & Equipment Disposal certificates will be supplied. Replace flexi ducting pipes Clean and disinfect fixed ducting Ceiling and Patchwork Repairs Bluchem treatment on all outdoor units Manned Guarding Service for the duration of the project |  |  | Region 2 | Western Cape | 77254X | 1000-70814-01 | Absa Mainstream Centre, Cnr Main Road & Princess Street, Hout Bay |  | 2022-07-31 | 2022-09-30 |  | ASP-WC0217 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-05-23 |  | 265750 |  | Approved | 2022-07-21 | 2022-07-21 | 0 |  |  |  |  | C000027092 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000563 | Replacement of HVAC Unit in the teller a | Replacement of HVAC Unit in the teller area (CIP 2022)Absa Robertson is a Leasehold Building and the existing HVAC units in the teller area are 18 years old and has reached its economic end of life. The ducted unit in the teller area is currently not operational due to the spares that are no longer readily available and have been discontinued. To mitigate the lack of cooling, there are currently 2 portable air conditioning units to provide temporary cooling in the consultants and banking hall areas. The installation of the air conditioning units in this branch will ensure adequate air circulation and cooling temperature in Robertson as it exceeds 35 degrees Celsius in summer. This request seeks approval for these units to be replaced.Note: The design is similar to the existing, but the equipment is new technology inverters utilising R410 gas. Gas & Equipment Disposal certificates will be supplied. Like for like replacement, no GMP Cost Impact. Scope of Works Supply and Install 1 x Mitsubishi PEA RP250 Ducted Split unit in the Teller Area Replace existing isolator switches and issue an Electrical COC. Gas & Equipment Disposal certificates will be supplied. New duct transformations to be installed Ceiling and Patchwork Repairs Manned Guarding Service for the duration of the project |  |  | Region 2 | Western Cape | 77877X | 1000-70863-01 | Robertson-Paul Kruger St-Robertson | Y | 2022-08-01 |  |  | ASP-WC0220 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-06-03 |  | 190070.74 |  | 100 | 2022-10-13 | 2022-10-13 | 190070.74 |  | {"MANDT":"111","REFERENCE":70000563,"ONEVIEW":"77877X","DATE01":"2022-10-03","DATE02":"2022-10-03","DATE03":"2022-10-12","DATE04":"2022-10-13","DATE05":"2022-10-13","DATE06":"2022-11-21","DATE07":"2022-11-25","DATE08":"2023-02-02","DATE09":"2023-03-19","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:9:1:0:39:4:69:45:12","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-21","FORECAST_END":"2022-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MiBGZWIgRmluYWwgUG9jayBTdWJtaXR0ZWQgdG8gRmluYW5jZSA=","RATING":"Low"} |  |  | C000062138 | PHASE11 | 2022-11-21 | 2022-11-25 | RODERICK NEVAY | Michael Maluleka | 23000521 |  |  |  |  | 2023-01-18 | 165278.9 | 0 |  |  | C000043759 | 165278.9 | CIP2023XP | 16915.52 |  | 0 | 0 |  | 0 |  | 0
70000564 | Generator Exhaust Extension The current | Generator Exhaust Extension The current generator exhaust at Absa Bredasdorp is located next to a HVAC condenser and window area. Currently during power outages when the generator is in use fumes and noise enters the adjacent window and through the HVAC system. The request is to extend the existing exhaust away from the area to above the roof to prevent noise and fumes from entering the branch.Note: Supported by Engineering, RBB and Africa Security. Scope of works: Supply and install 4m 304 stainless steel pipe 101mm diameter, Supply and install 2x90 degree bends reduced to 90mm on inlet Supply and Install Rain Flap. |  |  | Region 2 | Western Cape | 77641X | 1000-70839-01 | Absa Bredasdorp,17 Long Street,Bredasdorp |  | 2022-07-07 |  |  | ASP-WC0221 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-06-09 |  | 17500 |  | Approved | 2022-08-04 | 2022-08-04 | 0 |  |  |  |  | C000029903 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000565 | Linking of the UPS DB to the Main DB (CI | Linking of the UPS DB to the Main DB (CIP 2022)Absa Tokai has an existing 10KVA Aros UPS installed, however, some of the circuit breakers in the UPS DB are not linked to the Main DB and this causes disruption of power on the critical equipment during power outage. The ATM s (x2 at a size of 1kVA each) are currently not connected to the existing UPS due to the plug tops that are connected into the incorrect sockets. The current output on the UPS load is divided into red phase (2%), yellow phase (7%) and blue phase (30%). Both ATMs will be connected on the red phase and the rest of the equipment will be distributed between the yellow and blue phase in order to balance the load on all 3 phases. This request is for all circuit breakers in the existing UPS DB to be linked to the Main DB in order to avoid disruption of power during power outage. The estimated load after the ATM and the rest of the equipment has been installed is estimated to be within 75% 80%.Note: Africa Security, RBB and Engineering support received. The existing DB has surge protection.Scope of works:Connect all ATM s to the correct dedicated socket outlet: UPS Distribution Board in Server Room Supply and install TP indicator light complete with fuses to indicate if there is power on the DB. Supply and install 1x changeover switch to bypass the UPS in the event of a failure. Supply and install 1x Schneider 20A 6KA circuit breaker in DB for rest of branch essential sockets. Rewire DB to install the additional switchgear. Trace circuits fed from DB to ensure that plugs and isolators to match the circuit breakers. Re label if needed.Main Distribution Board Supply and install 4mm 4core Surfix Cable from Main Switch to 20A TP circuit breaker in UPS DB. Supply and install 1x 63A Schneider 6KA Isolator in UPS section of DB as new Main Switch for Section Rewire existing circuit breakers through Main Switch. Rewire DB to install the additional switchgear. Trace circuits fed from DB to ensure that plugs and isolators to match circuit breakers. Re label if needed. Update Legend Cards. Issue Electrical COC Manned Guarding Service for the duration of the project. |  |  | Region 2 | Western Cape | 22225x | 1000-70707-01 | Tokai Junction, Shops G22,G23,G24 & G25A-Main Rd-Tokai | N | 2022-10-01 |  |  | ASP-WC0222 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-06-20 |  | 33362.59 |  | 100 | 2022-08-25 | 2022-08-25 | 33362.59 |  | {"MANDT":"111","REFERENCE":70000565,"ONEVIEW":"22225x","DATE01":"2022-07-23","DATE02":"2022-07-30","DATE03":"2022-08-20","DATE04":"2022-08-27","DATE05":"2022-09-17","DATE06":"2022-09-01","DATE07":"2022-12-10","DATE08":"2023-04-19","DATE09":"2023-06-03","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"220:7:21:7:21:-16:100:130:45:14","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-01","FORECAST_END":"2022-12-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000033649 | PHASE11 | 2022-09-01 | 2022-12-10 | RODERICK NEVAY | Michael Maluleka | 23000597 | [5 empty] | 29010.95 | 0 |  |  | C000033649 | 29010.95 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000566 | 21 Mc Intyre Road, Parow - Dilaps | 21 Mc Intyre Road, Parow - Dilaps |  |  | Region 2 | Western Cape | 77261X | 1000-70815-01 | Absa Parow McIntyre | N | 2022-08-15 |  |  | ASP-WC0225 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-07-18 |  | 473272.27 |  | 100 | 2022-10-07 | 2022-10-07 | 473272.27 | Contingency remaining R 40 492.88 Incl Vat | {"MANDT":"111","REFERENCE":70000566,"ONEVIEW":"77261X","DATE01":"2022-07-18","DATE02":"2022-07-25","DATE03":"2022-10-06","DATE04":"2022-10-07","DATE05":"2022-10-07","DATE06":"2022-11-01","DATE07":"2022-11-30","DATE08":"2022-12-05","DATE09":"2022-12-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:73:1:0:25:29:5:26:9","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-01","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBERUMgRmluYWwgUE9DIFN1Ym1pdHRlZCBmb3IgRkFEVCBhbmQgR3VhcmRpbmcgUjU3IDc0OC4wMiAtIFRvdGFsIFI0MTAgMjY1LjkwCjMwIE5vdiBIYW5kb3ZlciAzMCBOb3YKMTcgTm92IFBhcnQgMiBTdWJtaXR0ZWQgdG8gRmluYW5jZSBSMjk0IDQ2NC45MwoxNiBOb3YuIFBhcnQgMiB0byBiZSBzdWJtaXR0ZWQgZm9yIC0gUiAyODYgNjkwLjkzICwgVG90YWwgUiAzNDQgNzQzLjg4IAoxNCBOb3YgUE9DIEV4cGVjdGVkIDI1IE5vdgoxMCBOb3YgUGFydCAxIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZSBSNTggMDUyLjk1Cg==","RATING":""} |  |  | C000062735 | PHASE11 | 2022-11-01 | 2022-11-30 | RODERICK NEVAY | Michael Maluleka | 23000534 |  |  |  |  | 2023-01-20 | 103926.75 | 0 |  |  | C000042251 | 411541.09 |  | 77166.38 |  | 0 | 0 |  | 0 |  | 0
70000567 | Minor Works - Absa Lutzville (CIP 2022)A | Minor Works Absa Lutzville (CIP 2022)Absa Lutzville was converted to tellerless in 2021 and had a minor refresh in the front of house area in 2015. The back of house area was not addressed as part of the previous projects. Currently the banking hall tiles are chipped and cracked, and the current specification is no longer available. In the back of house area the floor and wall finishes, kitchen cupboards and sanitary ware have deteriorated over the years. The request is for the replacement of the tiles in the banking hall and the upgrade of the back of house area in order to comply with the corporate standards. In addition, the request is to replace mismatched ceiling tiles in the banking hall to create uniformity.Note : This project was prioritised by the region and spend will be allocated from the regional minor works budget. Engineering, Africa Security and RBB support received. Absa design supported the specifications.Scope of WorkBanking Hall Area Replace ceramic tiles with the new 600x600 signature grey specification (49sqm) Remove old queue rails, supply movable black queue rails (x4) Allow for 7 boxes for ceiling tiles (to replace mismatched and stained tiles)Pause Area Repaint walls (50sqm), skirting (6m) and door + frame (x 1) Remove old carpets , replace with new hard grafted specification (18sqm)Kitchen Area Passage area, remove old carpets, replace with 600x600mm signature ceramic tiles (4sqm) Replace vinyl tiles with 600x600mm signature grey ceramic tiles (7sqm) Repaint walls (17sqm) and wooden skirting (3m) Replace kitchen cupboards with new spec (1.7m long , ceiling height 2.7m). Male Toilet Replace toilet suite, 1 basin and tap, install splashback Replace vinyl tiles with 600x600mm signature grey ceramic tiles 3sqm Repaint walls (9sqm) and door + frame (x 1)Female Toilet Replace toilet suite, 1 basin and tap, install splashback Replace vinyl tiles with 600x600mm signature grey ceramic tiles (4sqm) Repaint walls (12sqm) and door + frame (x 1) Guarding service for the project |  |  | Region 2 | Western Cape | 77802X | 1000-70860-01 | Absa Lutzville, 108 Namakwa Street,Lutzville |  | 2022-09-19 | 2022-11-10 |  | ASP-WC0227 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-07-28 |  | 335047.29 |  | Approved | 2022-08-25 | 2022-08-25 | 0 |  |  |  |  | C000061149# | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-13 | 33286.64 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000568 | Minor Works - Absa Mountain Mill (CIP 2 | Minor Works Absa Mountain Mill (CIP 2022)The Absa Mountain Mill Branch was converted to a tellerless branch in 2022 by RBB PMO and as part of the scope a minor refresh was conducted. The back of house area was not addressed as part of the project and the area reflects the old corporate image. In the back of house area the floor and wall finishes, kitchen cupboards and sanitary ware have deteriorated over the years and require an upgrade. Request is for the back of house areas to be refreshed in order to meet the corporate standards.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB and Engineering support received.Scope of works:Server room Replace old vinyl tile with new abs specification vinyl tile (9sqm) Repaint wooden skirting (9sqm), walls (24sqm) and doors (x2)Back office Repaint walls (60sqm), wooden skirting (22sqm) Remove old and install new hard grafted carpets (23sqm)Check Book Library Remove old and install new hard grafted carpets (7sqm) Repaint wooden skirting (8sqm)Male Toilet Remove old floor tiles replace with 600x600 signature grey tiles (4sqm) Reuse existing sanitary fittings and install new mirror Strip all wall tiles, rhinolite and repaint (10sqm) Repaint door and frame (x1) Pause area Repaint door (x1) Remove old and install new hard grafted carpets(38sqm)Female Toilet Replace sanitary ware and install mirror Repaint door and frame x 1 Remove wall tiles, rhinolite and paint (7sqm) Remove old floor tiles and replace with 600x600 signature grey tiles (3sqm)Kitchen Remove old and replace with new kitchen cupboard (1787m long) along with the sink and tap Remove and+L14 reinstall hydroboil Remove old floor tiles and replace with 600x600 signature grey tiles (6sqm)Branch Admin office Remove old flooring and replace with hard grafted carpets (19sqm) Repaint wooden skirting (17m) Mannes guarding services for the project |  |  | Region 2 | Western Cape | 77271X | 1000-71431-01 | Absa Mountain Mill Shopping Centre, 13 Mountain Mill Drive, Worcester |  | 2022-09-30 |  |  | ASP-WC0228 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-07-28 |  | 229826.99 |  | Approved | 2022-09-01 | 2022-09-01 | 0 |  |  |  |  | C000035254 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000569 | Removal of Check-in deskAbsa Table Bay M | Removal of Check in deskAbsa Table Bay Mall has an existing Check in Desk that is no longer being utilised. Request was received from the region that entire desk and raised flooring be removed and relocate equipment (mimic panel) to a new position.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB, Engineering and Africa Security support received. Design approval received. Scope of works: Dismantle and remove the check in desk Relocate existing equipment (mimic panel) to a new location Remove raised flooring and carpets Patch floor tiles and match existing tile specification (8sqm) Remove electric power pole and make safe Repair damaged ceiling Repaint wall (10sqm) Issue COC on completion. Security guard services for the project. |  |  | Region 2 | Western Cape | 36245X | 1000-70762-01 | Absa Table Bay Mall,Cnr R27 & Berkshire Blvd,Cape Town |  | 2022-11-01 |  |  | ASP-WC0230 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-15 |  | 42870.18 |  | Approved | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C000038750 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000570 | Removal of Check-in deskAbsa Oude Bloemh | Removal of Check in deskAbsa Oude Bloemhof has an existing Check in Desk that is no longer being utilised. Request was received from the region that entire desk and raised flooring be removed and relocate equipment (mimic panel) to a new position.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB, Engineering and Africa Security support received. Design approval received. Scope of works: Dismantle and remove the check in desk. Relocate existing equipment (mimic panel) to a new position. Remove raised flooring and carpets. Patch floor tiles and match existing tile specification (6sqm) Remove electrical reticulation and make safe; Issue COC on completion. Security guard services for the project. |  |  | Region 2 | Western Cape | 77946X | 1000-70866-01 | Absa Oude BloemhofBuilding, Cnr Van Ryneveld& Plein Street,Stellenbosch |  | 2022-11-01 |  |  | ASP-WC0231 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-08-15 |  | 42185.26 |  | Approved | 2022-09-15 | 2022-09-15 | 0 |  |  |  |  | C00003840 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000571 | External Signage Removal | External Signage Removal |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Absa Bridge Park |  | 2022-09-19 |  |  | ASP-WC0232 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Freeho |  | CEASARS | 2022-08-26 |  | 53613.8 |  | Approved | 2022-08-30 | 2022-08-30 | 0 |  |  |  |  | C000034406 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000572 | Upgrade to Generator (19991231ctive)The | Upgrade to Generator (19991231ctive)The generator at Absa Cavendish Square was taken over in a state of disrepair by Absa from the landlord. The generator failed repeatedly, i.e. failing to stop and caused loss of power to the branch. A reactive request was logged and found that the original design is unsuitable. Recommendation was made for the upgrade to the generator, (i) Wiring upgrade and (2) Changeover with upgrade.Note: 19991231ctive request done via INSOG Process, Ref WO no. 409501663, Notification no. 303684782 and Supplier PO 4500748997 issued. Works was completed on 27/07/2022. Scope of works:Changeover switch upgrade 100A Motorised changeover, with manual Common Bridge Bar & additional tails Additional Relay for zero position change Link wiring and additional bridge pieces Panel wiring, installation and sundries Software configuration, testing and handover.Wiring upgrade High power 3pole contactor Additional Relay for secondary coil, additional fuses Repair to cable harness Rewire harness, installation of contactor, Dinrail Panel Wiring and installation, sundries Software configuration, testing and handover. |  |  | Region 2 | Western Cape | 37177X | 1000-70812-01 | Absa Cavendish Square Shopping Centre, Dreyer Street, Claremont |  | 2022-09-15 | 2022-09-30 |  | ASP-WC0233 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-08-31 |  | 50370.5 |  | Approved | 2022-09-08 | 2022-09-08 | 0 |  |  |  |  | C000037140 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000573 | Supply of x2 new modified Cat LaddersAbs | Supply of x2 new modified Cat LaddersAbsa Worcester is a Freehold building and there has been various reported incidents of vandalism and theft of the equipment that s located at the back of the building and on the roof/canopy area. A high boundary wall, electric fence and clearvu fence were installed in the past years to increase the security of the site. However, continuous vandalism reports are still being reported at this branch. Africa Security were consulted in order to put additional measures in place to secure the equipment. The recommendation is to extend the electric fence, post a permanent night shift guard and to supply new modified cat ladders. This request is for the supply and installation of 2 x new modified cat ladders to prevent illegal access onto the canopy and roof area.Note: Engineering, FM and Africa Security Support received.Scope of Works Remove two steel cat ladders and cart off site. Supply two new Galvanised Cat Ladders with bottom trap doors and diamond mesh around the vertical section and install on site. |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester-Stockenstrom St-Worcester | N | 2022-11-01 |  |  | ASP-WC0235 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-09-06 |  | 95917.9 |  | 100 | 2022-10-13 | 2022-10-13 | 95917.9 |  | {"MANDT":"111","REFERENCE":70000573,"ONEVIEW":"78016X","DATE01":"2022-09-05","DATE02":"2022-09-12","DATE03":"2022-09-19","DATE04":"2022-10-13","DATE05":"2022-10-13","DATE06":"2022-11-16","DATE07":"2022-12-02","DATE08":"2022-12-12","DATE09":"2023-01-21","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:7:24:0:34:16:10:40:10","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-16","FORECAST_END":"2022-12-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgLSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000062126 | PHASE11 | 2022-11-16 | 2022-12-02 | RODERICK NEVAY | Michael Maluleka | 23000545 |  |  |  |  | 2023-01-18 | 83406.87 | 0 |  |  | C000044052 | 83406.87 | CIP2023XP | 8378.9 |  | 0 | 0 |  | 0 |  | 0
70000574 | Minor Works - Absa Citrusdal (CIP 2022)A | Minor Works Absa Citrusdal (CIP 2022)Absa Citrusdal received a minor refresher +/ 5years ago. The back of house area was not addressed as part of the project and the area reflects the old corporate image. At the back of house area the kitchen, ablution, back office, floor and wall finishes have deteriorated over time and need to be upgraded to enhance staff experience. The carpets are stained and can no longer be effectively cleaned. Some of the tiles are cracked and faded, and the walls need to be repainted with the new Absa colours. The kitchen cupboards have also deteriorated over a period of time and need to be replaced, and a new hydroboil with inline filters will be installed. This refresh will enhance the look and feel of the branch. In addition, the request is for steps to be built at the fire escape route as the door is opening in the wrong direction of the current steps. Request is for the back of house area to be upgraded in order to meet the corporate standards.Note: Approved at RIF. This project was prioritised by the region and spend will be allocated from the regional minor works budget. RBB and Engineering support received. Confirmation obtained from BFM Engineering that there is sufficient fresh air in ablution facilities. Scope of WorkLadies Ablution Remove old flooring and replace with new signature grey ceramic tiles (13sqm) Remove old and replace with new sanitary ware (2 x basins, 2 x taps and 2 mirrors) Paint walls (30sqm) and ceilings (9sqm) Varnish doors (x 3), frames (x 2) and paint door (x 1) Male Ablution Remove old flooring and replace with new signature grey ceramic tiles (12sqm) Paint walls (28sqm) and ceilings (9sqm) Remove old and replace with new sanitary ware (1 x tap, 1 x basin, 1 x urinal and 1 x mirror) Remove old curtains and make good (x 4) Varnish doors (x 2), frames (x 1) and paint door (x 1) Strip wall tiles by urinal area, skim and paint area (3sqm) Demolition bottom wall by old urinal, allow for new plumbing and make good Kitchen Remove old flooring and replace with new signature grey ceramic tiles (6sqm) Paint walls (8sqm) and ceilings (4sqm) Remove and install new kitchen cupboard as per the Absa spec with sink and tap Supply and install new 2.5L hydroboil with inline filters. Allow for plumbing and electrical point for new hydroboil Issue Electrical COC Pause Area/ Boardroom , Passage way and Store room Deep clean vinyl tile in storeroom and reseal the area (12sqm) Remove old flooring in boardroom and replace with hard grafted carpet tiles (14sqm) Supply and install Aluminium skirting in the boardroom (12m) Remove old flooring in passage way and replace with signature grey ceramic tiles (35sqm) Paint walls (89sqm) and ceilings (9sqm) Varnish doors (x 2), frames (x 1) and paint door (x 1) Vendor to conduct deep cleaning on project completion before hand over Extend fire escape steps Manned guarding for the project. |  |  | Region 2 | Western Cape | 78131X | 1000-71446-01 | Absa Citrusdal,44 Voortrekker Street, Citrusdal | N | 2022-11-01 |  |  | ASP-WC0237 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-09-09 |  | 360741.09 |  | 100 | 2022-10-05 | 2022-10-05 | 360741.09 |  | {"MANDT":"111","REFERENCE":70000574,"ONEVIEW":"78131X","DATE01":"2022-09-07","DATE02":"2022-09-14","DATE03":"2022-09-19","DATE04":"2022-09-26","DATE05":"2022-10-06","DATE06":"2022-11-03","DATE07":"2022-11-16","DATE08":"2022-11-17","DATE09":"2022-11-30","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:5:7:10:28:13:1:13:15","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-03","FORECAST_END":"2022-11-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTcgTm92IEZpbmFsIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000061969 | PHASE11 | 2022-11-03 | 2022-11-16 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-17 | 20717.2 | 0 |  |  | C000042169 | 313687.9 |  | 9761.78 |  | 0 | 0 |  | 0 |  | 0
70000575 | Minor Work - Absa Bredasdorp (CIP 2022)A | Minor Work Absa Bredasdorp (CIP 2022)Absa Bredasdorp received a minor refresh approximately 5 years ago. The back of house area was not addressed as part of the project and the area reflects the old corporate image. At the back of house area the kitchen, ablution, back office, floor and wall finishes have deteriorated over time and need to be upgraded to enhance staff experience. Request is for the back of house area to be upgraded in order to meet the corporate standards.Note: Approved by RIF. BFM Engineering support received. This project was prioritised by the region and spend will be allocated from the regional minor works budget. Scope of works:Female Ablution Replace floor tiles with new signature grey ceramic tiles (74sqm) Install new sanitary ware (3 x toilets, 2 x basins and mirrors) Install window blinds ( 590 x 955mm and 590 x 580mm) Paint walls (56sqm) and varnish doors (x 4) Male Ablution Replace floor tiles with new signature grey ceramic tiles (76sqm) Paint walls (60sqm) and varnish doors (x2) Install new sanitary ware (1 x toilet, 1 x basin, 2 x urinals and mirror) Install window blinds (590 x 955mm and 590 x 580mm) Kitchen, Staircase and Passage Remove old floor finishes and replace with new signature grey ceramic tiles (50sqm) Paint doors (x2), skirtings (34m), walls and ceilings (90sqm) Install new kitchen cupboard as per the Absa spec with basin and tap Install new blinds (900 x 970mm and 1200 x 1466mm) Back Office and Boardroom Replace carpet tiles with new hard grafted carpet tiles (72sqm) Paint skirting (62sqm), door and frame (x 1), walls and bulkhead(90sqm) Install blinds (980 x 1220 mm) Manned guarding for the project |  |  | Region 2 | Western Cape | 77641X | 1000-70839-01 | Absa Bredasdorp,17 Long Street, Bredasdorp |  | 2022-11-01 |  |  | ASP-WC0238 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-09-09 |  | 498622.43 |  | Approved | 2022-09-22 | 2022-09-22 | 0 |  |  |  |  | C000039619 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000577 | Dilaps | Dilaps |  |  | Region 2 | Western Cape | 76975X | 1000-71443-01 | Absa Eighty Beach Road |  | 2022-10-11 |  |  | ASP-WC0245 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | GAMIETR | 2022-10-12 |  | 544.42 |  | Approved | 2022-10-13 | 2022-10-13 | 0 |  |  |  |  | C000044055 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000578 | Replacement of Generator (CIP 2022)The e | Replacement of Generator (CIP 2022)The existing Cummins generator at Absa Tokai is faulty and there have been numerous repairs which have been conducted on the unit without any success. It has further been determined that the generator still requires further repairs on the engine and alternator in order to be fully operational. To mitigate the risk a mobile generator was hired that has been on site for + four months during attempted repairs in order to provide the backup required by the branch. This request is to replace the existing Cummins Generator with an ex stock 60kVA SDMO generator which is currently stored in Johannesburg.Note: Supported by Engineering. Like for like replacement, No GMP Cost Impact. Scope of Work Service the 60kVA SDMO generator Relocation of generator from Johannesburg to Cape Town Existing change over panel to be re used New battery to be installed Decommissioning the Cummins generator and relocate it back to Johannesburg |  |  | Region 2 | Western Cape | 22225X | 1000-70707-01 | Absa Tokai Junction,Shop G22-24, Tokai Junction, cnr Tokai and Main Roads | N | 2022-10-11 |  |  | ASP-WC0246 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | GAMIETR | 2022-10-12 |  | 127101.67 |  | 100 | 2022-10-20 | 2022-10-20 | 127101.67 |  | {"MANDT":"111","REFERENCE":70000578,"ONEVIEW":"22225X","DATE01":"2022-10-12","DATE02":"2022-10-14","DATE03":"2022-10-14","DATE04":"2022-10-17","DATE05":"2022-10-20","DATE06":"2022-11-12","DATE07":"2022-11-12","DATE08":"2022-12-01","DATE09":"2022-12-15","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:2:0:3:3:23:0:19:14:5","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-12","FORECAST_END":"2022-11-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MSBEZWMgRmluYWwgUE9DIFN1Ym1pdHRlZAo=","RATING":"Low"} |  |  | C000081725 | PHASE11 | 2022-11-12 | 2022-11-12 | Michael Maluleka | RODERICK NEVAY | 23000533 |  |  |  |  | 2023-04-25 | 110523.2 | 0 |  |  | C000045397 | 110523.2 | CIP2023XP | 11466.06 |  | 0 | 0 |  | 0 |  | 0
70000579 | Alterations to emergency exit door (Retr | Alterations to emergency exit door (19991231ctive INSOG)Absa Delphi Arch branch in Tableview uses the emergency exit door to grant access to paraplegic clients with walking aids and wheelchairs as the Mantrap door is too small to accommodate them and a helper simultaneously. There was however a challenge with the emergency exit door in that the frame has a strip/crossbar at the bottom that impedes access and creates a tripping risk. On numerous occasions clients tripped over this strip/crossbar. This request was to alter the frame to grant easy access and remove the OHS risk.Note: A Reactive Call was logged and work was completed on Friday 14 October 2022. Reference WO no. 409738535, Notification no. 303758335 and PO no. 4500766656. Scope of works: Remove existing emergency exit door and set aside for reuse. Remove bottom door sill and make good. Add weather guard onto front of door to cover gap underneath the door. |  |  | Region 2 | Western Cape | 77913X | 1000-70865-01 | Absa Delphi Arch,65 Raats Drive, Table View | N | 2022-08-27 | 2022-08-27 |  | ASP-WC0247 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-10-26 |  | 5791.4 |  | 100 | 2022-11-02 | 2022-11-02 | 5791.4 | Was Insog Item for Noting | {"MANDT":"111","REFERENCE":70000579,"ONEVIEW":"77913X","DATE01":"2022-10-25","DATE02":"2022-10-25","DATE03":"2022-10-25","DATE04":"2022-11-01","DATE05":"2022-11-02","DATE06":"2022-11-02","DATE07":"2022-11-02","DATE08":"2022-11-10","DATE09":"2022-12-04","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:7:1:0:0:8:24:20","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-02","FORECAST_END":"2022-11-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"V2FzIEluc29nIEl0ZW0gZm9yIE5vdGluZwoxMCBOb3YgUE9DIHN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Low"} |  |  | C000061815 | PHASE11 | 2022-11-02 | 2022-11-02 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-17 | 5036 | 0 |  |  | C000047870 | 5036 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000580 | Review of HVAC Design and provide report | Review of HVAC Design and provide report Absa Cape Gate (Item for noting)Absa Cape Gate is a leasehold building and the branch had a revamp in 2019 were Dunham Bush Ducted HVAC units were installed. The Branch HVAC system comprises of x3 condensing units which makes up one system. The HVAC system is currently providing the branch with ventilation with no cooling effect as the compressors were found to be faulty due to the design issues. The branch is currently using portable air conditioning units for air circulation and cooling. This request is for the consultant to be appointed in order to review the existing design and provide a report on the remedial work that can be done to resolve the design/system issues.Note: Supported by Engineering. Approved Out of Cycle on 16/11/2022. Scope Work Mechanical engineering consulting services for design review, report and comment on the drawings. |  |  | Region 2 | Western Cape | 77288x | 1000-71432-01 | CapeGate Shopping Centre-Cnr Okavango & De Bron Rd-Brackenfell | N | 2022-12-01 |  |  | ASP-WC0248 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-10-28 |  | 56746.65 |  | 100 | 2022-11-17 | 2022-11-17 | 56746.65 |  | {"MANDT":"111","REFERENCE":70000580,"ONEVIEW":"77288x","DATE01":"2022-09-22","DATE02":"2022-09-29","DATE03":"2022-10-20","DATE04":"2022-10-27","DATE05":"2022-11-17","DATE06":"2022-11-28","DATE07":"2022-12-30","DATE08":"2023-02-15","DATE09":"2023-03-25","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"159:7:21:7:21:11:32:47:38:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-28","FORECAST_END":"2022-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000062982 | PHASE11 | 2022-11-28 | 2022-12-30 | RODERICK NEVAY | Michael Maluleka | 23000575 |  |  |  |  | 2023-01-20 | 49344.9 | 0 |  |  | C000062982 | 49344.9 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000581 | External signage replacement (19991231ct | External signage replacement (19991231ctive Insurance)It was reported by the branch that the Absa external sign was damaged when the Fidelity truck drove into the hanging sign in the parking area. This happened on the 26th of August 2022. A P2 call was logged on 27 August 2022 and the contractor went to site to remove the sign and make the area safe. This request seeks approval for the removal of the external Absa sign and making good to the area and for the installation of the newly manufactured sign.Note: Reference of call logged: Notification no. 303750461, WO no. 409709211 and PO no. 4500765065 for the removal of the sign.Scope of works: Removal of external Absa sign and make good of area. Manufacture and install new Led illuminated Ci 2018 fabricated logo onto backing panel to existing power. Size: W 2750 x H 370 mm; Logo height: 490mm. |  |  | Region 2 | Western Cape | 77877X | 1000-70863-01 | Absa Robertson |  | 2022-08-27 | 2022-08-27 |  | ASP-WC0249 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | Leaseh |  | CEASARS | 2022-10-28 |  | 2238.89 |  | Approved | 2022-11-02 | 2022-11-02 | 0 |  |  |  |  | C000047853 | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000582 | Replacement of shopfront window vinylAbs | Replacement of shopfront window vinylAbsa Donald Court is a leasehold Building. The existing shopfront window tinting has deteriorated over time and currently peeling off on the edges. Request is for new shopfront window vinyl to be applied in order to maintain corporate standard.Note: This project was prioritised by the region and spend will be allocated from the regional minor works budget. Work can commence during the 1st week of December subject to the PO issued by latest 14 November 2022. Supported and approved by RBB and Absa Design.Scope of works: Remove old tinting and replace with new lifestyle graphic vinyl to shopfront windows.1 x W 570 x H 2700; 4 x W 835 x H 1515; 1 x W 1695 x H 27002 x W 1605 x H 2700; 3 x W 1880 x H 2700; 1 x W 1710 x H 27003 x W 1470 x H 2700; and 1 x W 1930 x H 2700. |  |  | Region 2 | Western Cape | 22465X | 1000-70711-01 | Absa Donald Court,Cnr Arthur & Main Road, Sea Point | N | 2022-12-01 |  |  | ASP-WC0250 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-11-08 |  | 136916.6 |  | 100 | 2022-11-10 | 2022-11-10 | 136916.6 |  | {"MANDT":"111","REFERENCE":70000582,"ONEVIEW":"22465X","DATE01":"2022-11-03","DATE02":"2022-11-03","DATE03":"2022-11-08","DATE04":"2022-11-08","DATE05":"2022-11-10","DATE06":"2022-11-29","DATE07":"2022-11-30","DATE08":"2022-12-06","DATE09":"2022-12-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:5:0:2:19:1:6:25:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-29","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBEZWMgUE9DIHBhY2sgc3VibWl0dGVk","RATING":"Low"} |  |  | C000063015 | PHASE11 | 2022-11-29 | 2022-11-30 | RODERICK NEVAY | Michael Maluleka | 23000530 |  |  |  |  | 2023-01-20 | 119057.91 | 0 |  |  | C000049288 | 119057.91 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000583 | Absa Parow McIntyre - Dilaps VO | Absa Parow McIntyre - Dilaps VO - Dilaps - Removal of Generator |  |  | Region 2 | Western Cape | 77261X | 1000-70815-01 | Absa Parow McIntyre | N | 2022-11-01 | 2022-11-30 |  | ASP-WC0252 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-11-10 |  | 109611.85 |  | 100 | 2022-11-18 | 2022-11-18 | 109611.85 |  | {"MANDT":"111","REFERENCE":70000583,"ONEVIEW":"77261X","DATE01":"2022-11-01","DATE02":"2022-11-08","DATE03":"2022-11-10","DATE04":"2022-11-18","DATE05":"2022-11-18","DATE06":"2022-11-18","DATE07":"2022-11-30","DATE08":"2022-12-02","DATE09":"2022-12-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:2:8:0:0:12:2:29:15","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-18","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHN1Ym1pdHRlZCAyIERlYw==","RATING":"Low"} |  |  | C000051949 | PHASE11 | 2022-11-18 | 2022-11-30 | RODERICK NEVAY | Michael Maluleka | 23000540 |  |  |  |  | 2023-02-18 | 95314.65 | 0 |  |  | C000051949 | 95314.65 |  | 9896.53 |  | 0 | 0 |  | 0 |  | 0
70000584 | Replacement of Courtyard Door (Item for | Replacement of Courtyard Door (Item for noting)Absa Simphiwe is a leasehold building. The external courtyard door which needs to serve as both an access door to the courtyard and as an emergency exit is not compliant and posing a security risk. The courtyard area is currently not accessible from the outside to gain access into the yard due to a push bar and lock thats been installed on the inside of the door i.e. within the courtyard. The branch is thus required to open their emergency exit door to unlock and open the courtyard door to allow access for the service providers to attend to the assets (HVAC and Generator), this process poses a security risk to the branch. In addition, the door being physically locked on the inside poses a compliance risk as it needs to serve as a fire escape exit in case of an emergency. The request is for the installation of a new courtyard door that is to be compliant in terms of serving as an emergency exit door and can be unlocked from outside the courtyard to allow vendors access to service the assets.Note: Approval received for proposed door from Africa Security, Landlord, Absa OHS, Bidvest Compliance, RBB and Municipality. The landlord shall be responsible for the maintenance of the door thus no GMP impact. Lead Time on the manufacturing of the door is 10 15 working days. Planned Completion date scheduled for 14/12/2022.Scope of works: Remove & Reinstall new Passage Safety Door Slam lock / Striker Lock CISA Elettrika Booster 12 24VDC / VAC Input 12VAC Output Securi Prod Power Supply 13.6VDC 3Amp Power Securi Prod 12V 7.2Ah SLA Battery Receiver Channel Rolling Code (434) Blue Transmitter/Remotes Blu Mix Rolling Code x 12 4x2 Calvinize steel box 12 Month Warranty on Equipment and Door |  |  | Region 2 | Western Cape | 77766X | 1000-70856-01 | Absa Simphiwe Building, 64 Saldanha Road, Saldanha | N | 2022-12-14 |  |  | ASP-WC0253 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-11-15 |  | 45506.66 |  | 100 | 2022-11-18 | 2022-11-18 | 45506.66 |  | {"MANDT":"111","REFERENCE":70000584,"ONEVIEW":"77766X","DATE01":"2022-11-10","DATE02":"2022-11-10","DATE03":"2022-11-14","DATE04":"2022-11-18","DATE05":"2022-11-18","DATE06":"2022-12-02","DATE07":"2022-12-15","DATE08":"2023-01-05","DATE09":"2023-01-31","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:4:4:0:14:13:21:26:27","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-02","FORECAST_END":"2022-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBKYW4gLSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":""} |  |  | C000063103 | PHASE11 | 2022-12-02 | 2022-12-15 | RODERICK NEVAY | Michael Maluleka | 23000585 |  |  |  |  | 2023-01-23 | 39571.01 | 0 |  |  | C000063103 | 39571.01 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000585 | Absa Odendaalsrus - Supply and install S | Absa Odendaalsrus - Supply and install S |  |  | Region 3 |  | 79056X | 1000-71599-01 | Absa Odendaalsrus-Odendaal St-Odendaalsrus |  | 2022-12-19 |  |  | ASP-CR0369 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-13 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000586 | Absa Victoria West-Install 40KVA Diesel | Absa Victoria West-Install 40KVA Diesel |  |  | Region 3 |  | 21821X | 1000-71320-01 | 31 Church Street Victoria West-Church St-Victoria West |  | 2022-12-19 |  |  | ASP-CR0370 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-13 | D | 21443.83 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 246604.11 | Approved | {"MANDT":"111","REFERENCE":70000586,"ONEVIEW":"21821X","DATE01":"2022-10-10","DATE02":"2022-10-17","DATE03":"2022-11-07","DATE04":"2022-11-14","DATE05":"2022-12-05","DATE06":"2022-12-19","DATE07":"2023-01-18","DATE08":"2023-02-08","DATE09":"2023-02-02","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-19","FORECAST_END":"2023-01-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBkb25lLiBBd2FpdGluZyBQQyBzaWduIG9mZi4=","RATING":""} |  |  | C000064767 | PHASE11 | 2022-12-19 | 2023-01-18 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-30 | 214438.36 | 0 |  |  | C000064767 | 214438.36 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000587 | Absa Phuthaditjhaba- Generator Major Ser | Absa Phuthaditjhaba- Generator Major Ser |  |  | Region 3 |  | 78615X | 1000-71593-01 | Phuthaditjhaba Shopping Centre-Cnr Setai & Motloung St-Phuthaditjhaba |  | 2022-12-21 |  |  | ASP-CR0371 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000588 | Absa Villiers - Minor Works | Absa Villiers - Minor Works |  |  | Region 3 | Free State | 78810X | 1000-71554-01 | Absa Villiers-Hoof St-Villiers |  | 2023-02-24 | 2023-03-10 |  | ASP-CR0409 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | MOKOENAM2 | 2023-03-14 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":70000588,"ONEVIEW":"78810X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-10","DATE07":"2023-03-31","DATE08":"2023-05-15","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-10","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE10 | 2023-03-10 | 2023-03-31 | NANDE MAQUBELA | Floyd Mofokeng | 23000340 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000589 | Absa Vincent Office Park - Cassette HVAC | Absa Vincent Office Park - Cassette HVAC for reception area |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Vincent Office Park-Western Ave-East London | N | 2022-12-13 | 2023-01-31 |  | ASP-EC0266 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | L |  | CEASARS | 2022-12-02 | D | 99624.85 | 2023.03.02: Approved by Kobus J vR 2023.02.28: Supported by Rob L | 100 | 2023-03-02 | 2023-03-02 | 99624.85 | Approved | {"MANDT":"111","REFERENCE":70000589,"ONEVIEW":"79369X","DATE01":"2022-11-30","DATE02":"2022-12-07","DATE03":"2023-01-31","DATE04":"2023-03-02","DATE05":"2023-03-02","DATE06":"2023-04-10","DATE07":"2023-04-12","DATE08":"2023-05-19","DATE09":"2023-05-25","DATE10":"2023-06-26","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"212:7:55:30:0:39:2:37:6:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-10","FORECAST_END":"2023-04-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgTWF5IC0gUE9DIHN1Ym1pdHRlZCB0byBmaW5hbmNl","RATING":"Low"} |  |  | C000071409 | PHASE11 | 2023-04-10 | 2023-04-12 | RODERICK NEVAY | Nokuthula Manzini | 23000318 |  |  |  |  | 2023-03-02 | 86630.3 | 0 |  |  | C000071409 | 86630.3 | CIP2023XP | 9056.8 |  | 0 | 0 |  | 0 |  | 0
70000590 | Absa Prins Albert - Power Reticulation I | Absa Prins Albert - Power Reticulation I |  |  | Region 2 |  |  | 1000-71024-01 | Building not in our database |  | 2023-01-31 | 2023-03-31 |  | ASP-EC0268 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2022-12-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000591 | Absa Barkly East - New Fence/Gate in backyard | Absa Barkly East - New Fence/Gate in backyard |  |  | Region 2 | Eastern Cape | 78658X | 1000-71050-01 | Absa Barkly East-Cole St-Barkly East | N | 2023-01-31 | 2023-03-31 |  | ASP-EC0269 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2022-12-02 | D | 0 |  | 1 |  |  | 0 | 11 Sept - Building still not been erected 14 Aug - No change 13 July Confirmation Received the Spar Building works on Hold, had issues with Municipal approvals. Thus gate cannot be installed accordingly. | {"MANDT":"111","REFERENCE":70000591,"ONEVIEW":"78658X","DATE01":"2023-01-19","DATE02":"2023-07-24","DATE03":"2023-08-04","DATE04":"2023-08-14","DATE05":"2023-08-14","DATE06":"2023-09-08","DATE07":"2023-09-09","DATE08":"2023-09-30","DATE09":"2023-10-31","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:186:11:10:0:25:1:21:31:14","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-08","FORECAST_END":"2023-09-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgSnVseSBDb25maXJtYXRpb24gUmVjZWl2ZWQgdGhlIFNwYXIgQnVpbGRpbmcgd29ya3Mgb24gSG9sZCwgaGFkIGlzc3VlcyB3aXRoIE11bmljaXBhbCBhcHByb3ZhbHMuIFRodXMgZ2F0ZSBjYW5ub3QgYmUgaW5zdGFsbGVkIGFjY29yZGluZ2x5LiBTY29wZS9CaWxsIGNhbm5vdCBiZSBkZXRlcm1pbmVk","RATING":""} |  |  |  | PHASE12 | 2023-09-08 | 2023-09-09 |  |  | 23000349 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000592 | Absa Uniondale - Trading Hours Decal | Absa Uniondale - Trading Hours Decal |  |  | Region 2 |  | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale |  | 2023-01-15 | 2023-01-31 |  | ASP-EC0270 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2022-12-13 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000593 | Absa King Williams Town - HVAC in bankin | Absa King Williams Town - HVAC in banking Hall |  |  | Region 2 | Eastern Cape | 78329X | 1000-71043-01 | Absa King William s Town-Cnr Cathcart & Maclean St-King William s Town | N | 2023-01-15 | 2023-03-31 |  | ASP-EC0271 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2022-12-13 | D | 211867.61 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 211867.61 | Approved | {"MANDT":"111","REFERENCE":70000593,"ONEVIEW":"78329X","DATE01":"2022-11-06","DATE02":"2022-12-16","DATE03":"2023-01-06","DATE04":"2023-01-06","DATE05":"2023-01-20","DATE06":"2023-04-04","DATE07":"2023-04-06","DATE08":"2023-05-31","DATE09":"2023-06-26","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"267:40:21:0:14:74:2:55:26:16","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-04","FORECAST_END":"2023-04-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgTWF5IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000073707 | PHASE11 | 2023-04-04 | 2023-04-06 | RODERICK NEVAY | Nokuthula Manzini | 23000320 |  |  |  |  | 2023-03-14 | 184232.71 | 0 |  |  | C000073707 | 184232.71 | CIP2023XP | 19260.69 |  | 0 | 0 |  | 0 |  | 0
70000594 | Moffett Office Park: 10 Portable AC + 10 | Moffett Office Park: 10 Portable AC + 10 |  |  | Region 2 | Eastern Cape | Various | 1000-70957-01 | Various Sites EC | U | 2023-01-31 | 2023-03-31 |  | ASP-EC0272 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Laxine Maliffe |  |  | 2023 |  | U |  | CEASARS | 2022-12-13 | D | 126922.28 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 126922.28 | Approved | {"MANDT":"111","REFERENCE":70000594,"ONEVIEW":"Various","DATE01":"2022-12-12","DATE02":"2022-12-13","DATE03":"2022-12-15","DATE04":"2023-01-11","DATE05":"2023-01-19","DATE06":"2023-03-02","DATE07":"2023-03-02","DATE08":"2023-03-24","DATE09":"2023-04-30","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:1:2:27:8:42:0:22:37:23","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-02","FORECAST_END":"2023-03-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjQgTWFyY2ggUE9DIFN1Ym1pdHRlZCB0byBmaW5hbmNl","RATING":"Low"} |  |  | C000068187 | PHASE11 | 2023-03-02 | 2023-03-02 | RODERICK NEVAY | Juanita van Coller | 23000279 |  |  |  |  | 2023-02-15 | 110367.2 | 0 |  |  | C000068187 | 110367.2 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000595 | The Boulders Replace check in desk with | The Boulders Replace check in desk with |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-09-26 |  |  | ASP-GN0175 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-12-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000596 | Pretoria Campus Request for Net One High | Pretoria Campus Request for Net One High |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2022-12-12 | 2022-12-31 |  | ASP-GN0176 | REL BUDG SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-12-12 | D | 0 |  |  |  |  | 0 |  |  |  |  | 2022 NO PO | IGNORE |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000597 | Towers West Butterfly Blinds | Towers West Butterfly Blinds |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-30 |  |  | ASP-GS0593 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-12-07 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000090806# | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-06-09 | 93413.79 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000598 | Primrose Mall Frosting on ATM door | Primrose Mall Frosting on ATM door |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-08-30 |  |  | ASP-GS0594 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-12-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000599 | Alice Lane North - Removal Vinyl Rebrand | â¢ Strip existing vinyl, clean and prepare substrate for new Installation. â¢ Install new vinyl. â¢ Installation will be done after normal working hours (Friday & one weekend). â¢ On site security guard to assist for the duration of the Installation. â¢ Material Leadtime: +-2 day. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | N | 2022-12-08 | 2022-12-31 |  | ASP-GS0595 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2022 |  | L |  | GAMIETR | 2022-12-08 | D | 31293.23 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 31293.23 | Approved | {"MANDT":"111","REFERENCE":70000599,"ONEVIEW":"70656X","DATE01":"2022-09-29","DATE02":"2022-10-06","DATE03":"2022-10-27","DATE04":"2022-11-03","DATE05":"2022-11-24","DATE06":"2022-12-14","DATE07":"2022-12-14","DATE08":"2023-01-04","DATE09":"2023-02-18","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"244:7:21:7:21:20:0:21:45:5","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-14","FORECAST_END":"2022-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000060165 | PHASE11 | 2022-12-14 | 2022-12-14 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000570 |  |  |  |  | 2023-01-09 | 31293.23 | 0 |  |  | C000060165 | 27211.5 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000600 | Alice Lane North Request for Net One Hig | Alice Lane North Request for Net One Hig |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-12-12 | 2022-12-31 |  | ASP-GS0596 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-12-12 | D | 658 |  |  |  |  | 0 |  |  |  |  | C000066902# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-02-08 | 6580 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000601 | The Glen Dilaps / Reinstatement | 1.Removal of all TV Screens and projectors. 2.Removal of all Safes 3.Removal of Mantrap Door 4.Removal of Money delivery tubes systems. 5.Removal of all cameras. 6.Removal of the security system and access control. 7.Disconnecting the UPS system and delivering to stores. 8.Collection and delivery of furniture from Absa stores to Swing space 9,Disposal of Confidential documentation. |  |  | Region 1 |  | 77239X | 1000-70359-01 | The Glen Shopping Centre-Cnr Orpen & Letaba St-Oakdene | Y | 2023-03-09 | 2023-12-15 |  | ASP-GS0621 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-03-14 | D | 173196.87 | Approved at CB/BTB | 100 | 2023-03-22 | 2023-03-22 | 173196.87 | Approved | {"MANDT":"111","REFERENCE":70000601,"ONEVIEW":"77239X","DATE01":"2022-12-29","DATE02":"2023-01-05","DATE03":"2023-01-26","DATE04":"2023-02-02","DATE05":"2023-02-23","DATE06":"2023-03-09","DATE07":"2023-04-08","DATE08":"2023-04-29","DATE09":"2023-06-13","DATE10":"2023-07-31","DATE11":"2023-06-13","DATE12":"2023-06-13","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":89,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-09","FORECAST_END":"2023-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000075730 | PHASE10 | 2023-03-09 | 2023-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 173196.85 | 0 |  |  | C000075730 | 150605.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000602 | Absa Jetmart - Replacement of BMS Screen | Absa Jetmart - Replacement of BMS Screen |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-19 | 2022-12-23 |  | ASP-KZ0215 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-13 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000603 | Absa Shelly Beach -Install Temp Rental G | Absa Shelly Beach -Install Temp Rental G |  |  | Region 3 |  | 77417X | 1000-71171-01 | Shelly Beach-East St-Shelly Beach |  | 2022-12-22 | 2022-12-30 |  | ASP-KZ0216 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000604 | Absa Dundee -Minor Works | Absa Dundee -Minor Works |  |  | Region 3 |  | 78106X | 1000-71212-01 | Dundee-Victoria St-Dundee |  | 2023-03-01 |  |  | ASP-KZ0217 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000605 | Absa Ballito Junction - Replace Carpet T | Absa Ballito Junction - Replace Carpet T |  |  | Region 3 |  | 78271X | 1000-71219-01 | Ballito Junction Regional Mall-Leonora Dr-Ballito |  | 2023-03-03 |  |  | ASP-KZ0218 | REL AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000606 | Absa Ixopo - Replace Ceiling Tile & Hydr | Absa Ixopo - Replace Ceiling Tile & Hydr |  |  | Region 3 |  | 77258X | 1000-71160-01 | Ixopo Memorial Hall-Margaret St-Ixopo |  | 2023-03-03 |  |  | ASP-KZ0219 | REL AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-19 | D | 0 | 2023.07.13: Approved by Conrad M |  | 2023-07-13 | 2023-07-13 | 495081.38 | Approved |  |  |  | C000098572 | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-07-18 | 430505.55 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000607 | Absa Verulam - Minor Works | Absa Verulam - Minor Works |  |  | Region 3 |  | 77269X | 1000-71162-01 | Verulam Kohinoor Centre-Cnr Moss & Wick St-Verulam |  | 2023-03-01 | 2023-03-30 |  | ASP-KZ0220 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000608 | Absa Davenport -Replacement of ceiling t | Absa Davenport -Replacement of ceiling t |  |  | Region 3 |  | 77015X | 1000-71153-01 | Glenwood-Brand Rd-Berea |  | 2023-03-01 | 2023-03-30 |  | ASP-KZ0221 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000609 | Absa Nkandla (Ithala)- Replace floor til | Absa Nkandla (Ithala)- Replace floor til |  |  | Region 3 |  | 77968X | 1000-71204-01 | Ithala Centre Nkandla-Nkandla Township-Durban |  | 2023-03-03 | 2023-03-30 |  | ASP-KZ0222 | REL AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-22 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000114112 | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-10-03 | 320172.41 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000610 | Absa Nquthu - Minor Plaza | Absa Nquthu - Minor Plaza |  |  | Region 3 |  | 79051X | 1000-71231-01 | Nquthu Plaza-Manzolwandle Dr-Nquthu |  | 2023-03-01 | 2023-03-30 |  | ASP-KZ0223 | REL AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000611 | Absa Stanger - Minor Works | Absa Stanger - Minor Works |  |  | Region 3 |  | 77928X | 1000-71201-01 | Whitehouse Centre-Chief Albert Luthuli St-Stanger |  | 2023-03-01 | 2023-03-30 |  | ASP-KZ0224 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2022-12-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000612 | Absa Siyabuswa - Rental Energy Diesel Ta | Absa Siyabuswa - Rental Energy Diesel Ta |  |  | Region 3 |  | 36259X | 1000-70681-01 | Siyabuswa Mall-Bongimfundo Rd-Siyabuswa |  | 2022-12-21 | 2022-12-30 |  | ASP-LP0149 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-15 | D | 2590.01 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 29785.18 | Approved |  |  |  | C000064766 | PHASE11 | 2022-12-21 | 2022-12-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-01-30 | 29785.18 | 0 |  |  | C000064766 | 25900.15 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000613 | Absa Hoedspruit - Replacement of LED Pan | Absa Hoedspruit - Replacement of LED Pan |  |  | Region 3 |  | 76718X | 1000-70519-01 | Spar Centre Hoedspruit-Koedoe St-Hoedspruit |  | 2022-12-21 | 2022-12-30 |  | ASP-LP0150 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000614 | Absa Highland Mews - Replacement of LED | Absa Highland Mews - Replacement of LED |  |  | Region 3 |  | 77121X | 1000-70610-01 | Absa Piet Retief-Church St-Piet Retief |  | 2022-12-13 |  |  | ASP-MP0144 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000615 | Absa Witbank - Energy Lighting to Baseme | Absa Witbank - Energy Lighting to Baseme |  |  | Region 3 | Mpumalanga | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank |  | 2022-12-21 |  |  | ASP-MP0145 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-12-15 | D | 42130.25 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 42130.25 | Approved | {"MANDT":"111","REFERENCE":70000615,"ONEVIEW":"76953X","DATE01":"2022-10-12","DATE02":"2022-11-09","DATE03":"2022-11-16","DATE04":"2022-11-16","DATE05":"2022-12-21","DATE06":"2023-01-20","DATE07":"2023-02-10","DATE08":"2023-07-31","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-20","FORECAST_END":"2023-02-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHNoYXJlZCB3aXRoIGNsaWVudCB0byBzaWduIG9uIG5ldyB0ZW1wbGF0ZQ==","RATING":""} |  |  | C000064758 | PHASE11 | 2023-01-20 | 2023-02-10 | NANDE MAQUBELA | Thea Spamers | 23000391 |  |  |  |  | 2023-01-30 | 42130.25 | 0 |  |  | C000064758 | 36635 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000616 | Absa Ceres - Extract fan on uPS cabinet | Absa Ceres - Extract fan on uPS cabinet |  |  | Region 2 | Western Cape | 70568X | 1000-70782-01 | Ceres-Voortrekker St-Ceres | N | 2023-01-15 |  |  | ASP-WC0256 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2022-12-13 | D | 0 |  | 1 | 2023-08-04 | 2023-08-04 | 0 | Testing Upload of Approvals | {"MANDT":"111","REFERENCE":70000616,"ONEVIEW":"70568X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-05-14","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:-6:30","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBBdWcgLSBFbmdpbmVlcmluZyBjb25maXJtZWQgRG9vcnMgY2FuIGJlIHJlbW92ZWQsIHRvIGFkdmlzZSBpZiB0byBiZSBkb25lIGFnYWluc3QgcHJvamVjdAoxNyBKdWx5IC0gUE0gdG8gZm9sbG93IHVwIHdpdGggRW5naW5lZXJpbmcgcmUgU29sdXRpb24gYW5kIFNwZWNpZmljYXRpb24=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 | RODERICK NEVAY | Michael Maluleka | 23000431 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000617 | Frankfort Minor Works | Frankfort Minor Works |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-02-03 |  |  | ASP-CR0234 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-02-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000618 | Trompsburg - Replacement of an air condi | Trompsburg - Replacement of an air condi |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-02-15 |  |  | ASP-CR0236 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-02-15 | D | 0 |  |  |  |  | 0 |  |  | {"APRO_TYPE":"AB","NAME":"Trompsburg - Replacement of an air condi","REASON":"80","ENVIR_INVEST":"70000","PRIORITY":"3","APPROVA_YEAR":0,"PLANNED_APPR":"--","IMPLEMENT_ST":"--","COUNTRY_INVS":"ZA","APPLICANT":"","AUTHORIZER":"","INVESTPROG":"","YEAR":0,"POSITION_ID":"","R_CO_CODE":"1000","REQ_COST_C":"19509200","REQ_PROFIT_C":"19509200","DIVISION":"07","R_CO_CODE2":"1000","REQ_COST_C2":"19509200","REQ_PROFIT_C2":"19509200","PLANT":"AB10","CURRENCY":"ZAR","V_NAME":"Q3","VARIANT":"10","COSTS":"","COSTS1":"0","COSTS2":"0","COSTS3":"0","COSTS4":"0","COSTS5":"0","COSTS6":"0","COSTS7":"0","COSTS8":"0","COSTS9":"0","STATUS":"FAPR","VERSION":"B3","FUNCT_LOCATION":"","DETAILS":"","ABSAREQNO":70000618} |  |  | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000619 | Kimberley Region HO - External Structura | Kimberley Region HO - External Structura |  |  | Region 3 |  | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley |  | 2022-04-14 | 2022-05-31 |  | ASP-CR0249 | CLSD AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  |  |  | CEASARS | 2022-04-04 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-04-14 | 2022-05-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000620 | Absa Zastron: Dilaps: Generator Removal | Absa Zastron: Dilaps: Generator Removal |  |  | Region 3 |  | 78989X | 1000-71565-01 | Absa Zastron-Cnr Ralph & Mathee St-Zastron |  | 2022-04-14 | 2022-05-31 |  | ASP-CR0250 | REL BUDG AVAC SETC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  |  |  | CEASARS | 2022-04-04 | D | 12795.1 |  |  |  |  | 0 |  |  |  |  | 2915142 | IGNORE | 2022-04-14 | 2022-05-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000621 | Absa Burger Street Rustenburg - Minor Wo | Absa Burger Street Rustenburg - Minor Wo |  |  | Region 3 |  | 77057X | 1000-71282-01 | Absa Burger Street-Cnr Nelson Mandela & Beyers Naude St-Rustenburg |  | 2022-06-01 | 2022-07-29 |  | ASP-CR0251 | CRTD AVAC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  |  |  | CEASARS | 2022-04-05 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-06-01 | 2022-07-29 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000622 | Kimberley RHO - Clearvu fencing | Kimberley RHO - Clearvu fencing |  |  | Region 3 |  | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley |  | 2022-06-01 | 2022-09-30 |  | ASP-CR0256 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-04-11 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000623 | Absa Frankfort - Minor works | Absa Frankfort - Minor works |  |  | Region 3 |  | 78306X | 1000-71536-01 | Frankfort-Brand St-Frankfort |  | 2022-07-01 | 2022-08-31 |  | ASP-CR0258 | CRTD DLFL AVAC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  |  |  | CEASARS | 2022-04-22 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-07-01 | 2022-08-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000624 | Hoopstad - Minor Works | Hoopstad - Minor Works |  |  | Region 3 |  | 79299X | 1000-71579-01 | Hoopstad-Van Zyl St-Hoopstad |  | 2022-06-15 | 2022-08-31 |  | ASP-CR0259 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-04-22 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-06-15 | 2022-08-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000625 | Absa Ottosdal - Wter tank, booster pump | Absa Ottosdal - Wter tank, booster pump |  |  | Region 3 |  | 78143X | 1000-71606-01 | Absa Ottosdal-Voortrekker St-Ottosdal |  | 2022-03-17 |  |  | ASP-CR0266 | CRTD AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-05-03 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000121833 | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-08 | 82585.65 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000626 | Absa Odendaalsrus - Replacement of chair | Absa Odendaalsrus - Replacement of chair |  |  | Region 3 |  | 79056X | 1000-71599-01 | Absa Odendaalsrus-Odendaal St-Odendaalsrus |  | 2022-05-26 |  |  | ASP-CR0272 | CRTD AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-05-10 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000627 | Absa Brits - Minor Works | Absa Brits - Minor Works |  |  | Region 3 |  | 22229X | 1000-71244-01 | Brits Mall-Cnr Hendrik Verwoerd & Maple Ridge Ave-Brits |  | 2022-07-07 | 2022-08-11 |  | ASP-CR0275 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-05-19 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000628 | Absa Hennenman - Plug Point ATM room | Absa Hennenman - Plug Point ATM room |  |  | Region 3 |  | 78855X | 1000-71558-01 | Absa Hennenman-Kerk St-Hennenman |  | 2022-06-13 |  |  | ASP-CR0276 | CRTD AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-05-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000629 | Absa Koppies - Wheelchair Ramp | Absa Koppies - Wheelchair Ramp |  |  | Region 3 |  | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies |  | 2022-07-07 | 2022-08-11 |  | ASP-CR0277 | REL AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-05-19 | D | 211.95 | 2023.05.17: Approved by Conrad M as per email 2023.05.16: Supported by Leko N |  | 2023-05-18 | 2023-05-18 | 105399.73 | Approved |  |  |  | C000086507# | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-22 | 91651.94 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000630 | Land for Demountable - External Minor Wo | Land for Demountable - External Minor Wo |  |  | Region 3 |  | 78633X | 1000-71547-01 | Hinterland-Van Der Walt St-Marquard |  | 2022-07-07 | 2022-08-11 |  | ASP-CR0278 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-05-19 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000631 | Absa Bloemhof Minor Works | Absa Bloemhof Minor Works |  |  | Region 3 |  | 79119X | 1000-71314-01 | Absa Bloemhof-Prins St-Bloemhof |  | 2022-07-14 | 2022-08-11 |  | ASP-CR0279 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-05-20 | D | 9296.49 | Approved | 100 | 2023-10-07 | 2023-10-07 | 13793.03 |  | {"MANDT":"111","REFERENCE":70000631,"ONEVIEW":"79119X","DATE01":"2022-05-05","DATE02":"2022-05-12","DATE03":"2022-06-02","DATE04":"2022-06-09","DATE05":"2022-06-30","DATE06":"2022-07-14","DATE07":"2022-08-11","DATE08":"2022-09-01","DATE09":"2022-08-28","DATE10":"2022-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-14","FORECAST_END":"2022-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060839 | PHASE10 | 2022-07-14 | 2022-08-11 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-01-12 | 11993.94 | 0 |  |  | C000031016 | 92964.94 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000632 | Absa Nampo Park Variation Order 2 | Absa Nampo Park Variation Order 2 |  |  | Region 3 |  | 79033X | 1000-71568-01 | Nampo Park-R30-Bothaville |  |  | 2022-05-23 |  | ASP-CR0280 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2022-05-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000633 | Absa Klerskdorp -Install Tv sets from Wa | Absa Klerskdorp -Install Tv sets from Wa |  |  | Region 3 |  | 77852X | 1000-71301-01 | Absa Church Street-Oliver Tambo St-Klerksdorp |  | 2022-07-29 |  |  | ASP-CR0282 | CRTD AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-05-25 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000634 | Phuthaditjhaba - Water Filtration System | Phuthaditjhaba - Water Filtration System |  |  | Region 3 |  | 78615X | 1000-71593-01 | Phuthaditjhaba Shopping Centre-Cnr Setai & Motloung St-Phuthaditjhaba |  | 2022-07-07 |  |  | ASP-CR0283 | CRTD AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-06-06 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000635 | Absa Koppies Bloemfontein - Green Star S | Absa Koppies Bloemfontein - Green Star S |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-26 |  |  | ASP-CR0284 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000060105 | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-01-09 | 13594.17 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000636 | Absa Lichtenburg - Green Star SA Rating | Absa Lichtenburg - Green Star SA Rating |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-26 |  |  | ASP-CR0285 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000637 | Absa Lichtenburg - Install grid-tied roo | Absa Lichtenburg - Install grid-tied roo |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-07-07 |  |  | ASP-CR0286 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000638 | Senekal - Installation of filtration sys | Senekal - Installation of filtration sys |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-30 |  |  | ASP-CR0287 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000639 | Harrismith - Installation of filtration | Harrismith - Installation of filtration |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-30 |  |  | ASP-CR0288 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000640 | Bethlehem Church Street - Smart water me | Bethlehem Church Street - Smart water me |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-06-09 |  |  | ASP-CR0289 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000641 | Absa Reitz - Installation of a UPS | Absa Reitz - Installation of a UPS |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-09-16 |  |  | ASP-CR0290 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000642 | Absa Parys - Smart water meter installat | Absa Parys - Smart water meter installat |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-06-09 |  |  | ASP-CR0291 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000643 | Ficksburg - Smart water meter installati | Ficksburg - Smart water meter installati |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-06-09 |  |  | ASP-CR0292 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000644 | Absa Koppies Bloemfontein - Smart electr | Absa Koppies Bloemfontein - Smart electr |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-06-09 |  |  | ASP-CR0293 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000645 | Theunissen - Installation of new water t | Theunissen - Installation of new water t |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-10-26 |  |  | ASP-CR0294 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000646 | Absa Bank Frankfort - Lighting Replaceme | Absa Bank Frankfort - Lighting Replaceme |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-02-17 |  |  | ASP-CR0295 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000647 | Absa Reitz - Lighting Replacement with L | Absa Reitz - Lighting Replacement with L |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-02-17 |  |  | ASP-CR0296 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000648 | De Aar - Extend ATM Room | De Aar - Extend ATM Room |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-30 |  |  | ASP-CR0297 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000649 | Kimberley RHO- Dilaps | Kimberley RHO- Dilaps |  |  | Region 3 |  | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley |  | 2022-11-01 |  |  | ASP-CR0300 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-06-27 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-10-31 | 2022-11-01 | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000650 | Absa Koster- Replacement of Waterproofin | Absa Koster- Replacement of Waterproofin |  |  | Region 3 |  | 77546X | 1000-71294-01 | Absa Koster-Jameson Rd-Koster |  | 2022-09-01 |  |  | ASP-CR0303 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000651 | Absa Ladybrand -External Minor Works (VO | Absa Ladybrand -External Minor Works (VO |  |  | Region 3 |  | 78841X | 1000-71556-01 | Absa 17A Joubert Street-Joubert St-Ladybrand |  | 2022-07-21 | 2022-09-02 |  | ASP-CR0306 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000652 | Absa Vryburg-Installation of electrical | Absa Vryburg-Installation of electrical |  |  | Region 3 |  | 77745X | 1000-71604-01 | Vryburg-Market St-Vryburg |  | 2022-09-08 | 2022-09-29 |  | ASP-CR0308 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-11 | D | 0 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR |  | 2023-04-06 | 2023-04-06 | 10979.45 | Approved |  |  |  | C000079205# | IGNORE |  |  |  |  | 0 |  |  |  |  | 2023-04-12 | 9547.35 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000653 | Absa Ventersdorp - Replace Waterproofing | Absa Ventersdorp - Replace Waterproofing |  |  | Region 3 | North West | 77096X | 1000-71284-01 | Absa Ventersdorp-Charmichael St-Ventersdorp |  | 2022-09-29 | 2022-11-10 |  | ASP-CR0311 | CRTD AVAC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-18 | D | 227.34 | Approved | 100 | 2023-10-07 | 2023-10-07 | 2614.44 |  | {"MANDT":"111","REFERENCE":70000653,"ONEVIEW":"77096X","DATE01":"2022-07-21","DATE02":"2022-08-18","DATE03":"2022-08-25","DATE04":"2022-08-25","DATE05":"2022-09-29","DATE06":"2022-11-10","DATE07":"2022-12-01","DATE08":"2023-01-15","DATE09":"2023-01-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-10","FORECAST_END":"2022-12-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000060799 | PHASE10 | 2022-11-10 | 2022-12-01 | NANDE MAQUBELA | Floyd Mofokeng | 23000562 |  |  |  |  | 2023-01-11 | 2273.43 | 0 |  |  | C000030795 | 2273.44 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000654 | Absa Wilkoppies Klerksdorp-Alterate Bank | Absa Wilkoppies Klerksdorp-Alterate Bank |  |  | Region 3 |  | 77150X | 1000-71287-01 | Austin Crossing Centre-Cnr Austin & Ametis St-Klerksdorp |  | 2022-09-22 | 2022-09-22 |  | ASP-CR0316 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-27 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000655 | Absa Cnr Church & Johanna-Revise Electri | Absa Cnr Church & Johanna-Revise Electri |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-09-08 |  |  | ASP-CR0321 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-08-05 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000656 | Absa Wilkoppies Klerksdorp- Supply Chair | Absa Wilkoppies Klerksdorp- Supply Chair |  |  | Region 3 |  | 77150X | 1000-71287-01 | Austin Crossing Centre-Cnr Austin & Ametis St-Klerksdorp |  | 2022-09-22 | 2022-12-01 |  | ASP-CR0327 | CRTD DLFL: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-08-24 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000062725 | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-01-20 | 60038.81 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000657 | Absa Taung Forum -Minor Works | Absa Taung Forum -Minor Works |  |  | Region 3 | North West | 79227X | 1000-71608-01 | Taung Forum-Station Rd-Taung |  | 2022-10-06 |  |  | ASP-CR0331 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-12 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":70000657,"ONEVIEW":"79227X","DATE01":"2022-07-28","DATE02":"2022-08-25","DATE03":"2022-09-01","DATE04":"2022-09-01","DATE05":"2022-10-06","DATE06":"2022-11-05","DATE07":"2022-11-26","DATE08":"2023-01-10","DATE09":"2023-01-31","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-05","FORECAST_END":"2022-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE10 | 2022-11-05 | 2022-11-26 | NANDE MAQUBELA | floyd mofokeng | 23000489 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000658 | Absa Wolmaransstad- Minor Works Internal | Absa Wolmaransstad- Minor Works Internal |  |  | Region 3 |  | 77605X | 1000-71295-01 | Wolmaransstad-Kruger St-Wolmaransstad |  | 2022-10-06 |  |  | ASP-CR0332 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-12 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000659 | Absa Brandfort - Replace &Remove damaged | Absa Brandfort - Replace &Remove damaged |  |  | Region 3 |  | 79333X | 1000-71584-01 | Absa Brandfort-Voortrekker St-Brandfort |  | 2022-10-10 |  |  | ASP-CR0335 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-28 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000660 | Absa Reitz -UPS Battery Replace and New | Absa Reitz -UPS Battery Replace and New |  |  | Region 3 |  | 78402X | 1000-71538-01 | Absa Reitz-Church St-Reitz |  | 2022-10-24 |  |  | ASP-CR0341 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-19 | D | 0 | 2023.04.26: Approved by Kobus JvR as per email 2023.04.25: Supported by Rob L |  | 2023-04-26 | 2023-04-26 | 113594.25 | Approved |  |  |  | C000082131 | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-04-26 | 98777.61 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000661 | Absa Virginia -Generator Dummy Load Test | Absa Virginia -Generator Dummy Load Test |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-11-03 |  |  | ASP-CR0345 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-26 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000662 | Absa Bultfontein-Repairs of Burnt ATM Ro | Absa Bultfontein-Repairs of Burnt ATM Ro |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-11-03 | 2022-11-03 |  | ASP-CR0346 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-31 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000663 | Absa Bloemfontein Forum - Replace Earthi | Absa Bloemfontein Forum - Replace Earthi |  |  | Region 3 |  | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein |  | 2022-11-03 |  |  | ASP-CR0347 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-31 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000664 | Taung Forum - Replace carpets, paint wal | Taung Forum - Replace carpets, paint wal |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-26 |  |  | ASP-CR0349 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000665 | Hartbeesfontein - Close out back office | Hartbeesfontein - Close out back office |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-26 |  |  | ASP-CR0350 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000666 | Absa Koster - Waterproofing service | Absa Koster - Waterproofing service |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-09-30 |  |  | ASP-CR0351 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000667 | Taung Forum - Installation of water tank | Taung Forum - Installation of water tank |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-12 |  |  | ASP-CR0352 |  |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000668 | Taung Forum - Installation of water tank | Taung Forum - Installation of water tank |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-12 |  |  | ASP-CR0353 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000669 | Absa Kuruman- Replace Stained Vinyl Tile | Absa Kuruman- Replace Stained Vinyl Tile |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-11-18 |  |  | ASP-CR0358 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-16 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000670 | Absa Mahikeng | Absa Mahikeng |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-21 | 2023-01-13 |  | ASP-CR0360 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | MOKOENAM2 | 2022-11-17 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000671 | Absa Bloemhof | Absa Bloemhof |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-21 | 2023-01-13 |  | ASP-CR0361 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | MOKOENAM2 | 2022-11-17 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000672 | Absa Klerksdorp | Absa Klerksdorp |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-21 | 2023-01-13 |  | ASP-CR0362 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | MOKOENAM2 | 2022-11-17 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000673 | Absa Hennenman | Absa Hennenman |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-30 | 2023-01-19 |  | ASP-CR0363 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000674 | Absa Vryburg | Absa Vryburg |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-28 | 2023-01-18 |  | ASP-CR0364 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000675 | Absa Wolmaransstad - Flood lights | Absa Wolmaransstad - Flood lights |  |  | Region 3 |  | 77605X | 1000-71295-01 | Wolmaransstad-Kruger St-Wolmaransstad |  | 2022-12-28 | 2022-12-30 |  | ASP-CR0365 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | MOKOENAM2 | 2022-11-23 | D | 1662.5 | 2023.04.14: Approved by Kous JvR Supported by BFM Engineering |  | 2023-04-14 | 2023-04-14 | 34595.45 | Approved |  |  |  | C000080527 | IGNORE |  |  | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-19 | 30083 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000676 | Absa Sannieshof | Absa Sannieshof |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-21 | 2022-12-30 |  | ASP-CR0366 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | MOKOENAM2 | 2022-11-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000677 | Absa Hoopstad | Absa Hoopstad |  |  | Region 3 |  | 79299X | 1000-71579-01 | Hoopstad-Van Zyl St-Hoopstad |  | 2022-12-28 |  |  | ASP-CR0368 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | MOKOENAM2 | 2022-11-30 | D | 0 | Approved at CB/BTB | 100 | 2023-04-13 | 2023-04-13 | 56129.2 | Approved | {"MANDT":"111","REFERENCE":70000677,"ONEVIEW":"79299X","DATE01":"2022-10-19","DATE02":"2022-10-26","DATE03":"2022-11-16","DATE04":"2022-11-23","DATE05":"2022-12-14","DATE06":"2022-12-28","DATE07":"2023-01-27","DATE08":"2023-02-17","DATE09":"2023-02-11","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-28","FORECAST_END":"2023-01-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  | C000079642 | PHASE11 | 2022-12-28 | 2023-01-27 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-14 | 48808 | 0 |  |  | C000079642 | 48808 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000678 | Absa Cradock - Kickplates in bulk telle | Absa Cradock - Kickplates in bulk telle |  |  | Region 2 | Eastern Cape |  | 1000-71022-01 | Building not in our database |  | 2022-02-22 | 2022-03-31 |  | ASP-EC0188 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-01-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-02-22 | 2022-03-31 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000679 | Absa Motherwell - Minor Works | Absa Motherwell - Minor Works |  |  | Region 2 | Eastern Cape | 76665X | 1000-71018-01 | Motherwell Shopping Centre-Cnr Nyara, Tyiniara & WM Maku St-Port Elizabeth |  | 2022-03-07 | 2022-03-31 |  | ASP-EC0191 | CLSD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-01-19 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000680 | Plettenberg Bay Sun Centre - New Chairs | Plettenberg Bay Sun Centre - New Chairs |  |  | Region 2 | Eastern Cape |  | 1000-71034-01 | Building not in our database |  | 2022-05-01 | 2022-06-30 |  | ASP-EC0192 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-03-24 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-05-01 | 2022-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000681 | Absa East London 85 Oxford - Repaint bra | Absa East London 85 Oxford - Repaint bra |  |  | Region 2 | Eastern Cape | 79244X | 1000-71469-01 | 85 Oxford Street-Oxford St-East London |  | 2022-03-07 | 2022-03-31 |  | ASP-EC0193 | CLSD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-01-19 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000682 | Mount Frere - Mini refresh ( Carpets, Pa | Mount Frere - Mini refresh ( Carpets, Pa |  |  | Region 2 | Eastern Cape | 78953X | 1000-71060-01 | Mount Frere-Main St-Mount Frere |  | 2022-06-01 | 2022-08-31 |  | ASP-EC0200 | CLSD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-02-07 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-06-01 | 2022-08-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000683 | Sterkspruit Shopping Centre - Limited sc | Sterkspruit Shopping Centre - Limited sc |  |  | Region 2 | Eastern Cape | 78939X | 1000-71059-01 | Sterkspruit Shopping Centre-Main St-Sterkspruit |  | 2022-06-01 | 2022-08-31 |  | ASP-EC0201 | CLSD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-02-07 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000684 | Burgersdorp - Revamp (ceiling tiles, car | Burgersdorp - Revamp (ceiling tiles, car |  |  | Region 2 | Eastern Cape |  | 1000-71063-01 | Building not in our database |  | 2022-09-01 | 2022-12-31 |  | ASP-EC0202 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-02-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000685 | Absa 6th Avenue Walmer - Dilaps [Closure | Absa 6th Avenue Walmer - Dilaps [Closure |  |  | Region 2 | Eastern Cape |  | 1000-71019-01 | Building not in our database |  | 2022-03-22 | 2022-05-31 |  | ASP-EC0205 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-03-22 | 2022-05-31 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000686 | Knysna Garden Route Centre - New Chairs | Knysna Garden Route Centre - New Chairs |  |  | Region 2 | Eastern Cape |  | 1000-70816-01 | Building not in our database |  | 2022-05-01 | 2022-06-30 |  | ASP-EC0209 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-03-24 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-05-01 | 2022-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000687 | Dutywa Central Square - HVAC EOL | Dutywa Central Square - HVAC EOL |  |  | Region 2 | Eastern Cape |  |  | Building not in our database |  | 2022-05-01 |  |  | ASP-EC0211 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-03-24 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000688 | Vincent Park - Furniture covering with P | Vincent Park - Furniture covering with P |  |  | Region 2 | Eastern Cape |  | 1000-71051-01 | Building not in our database |  | 2022-07-01 | 2022-09-30 |  | ASP-EC0214 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-04-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-07-01 | 2022-09-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000689 | Matatiele Morcross Centre - Minor Works | Matatiele Morcross Centre - Minor Works |  |  | Region 2 | Eastern Cape |  | 1000-71025-01 | Building not in our database |  | 2022-08-01 | 2022-09-30 |  | ASP-EC0220 | REL AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-05-12 | D | 945130 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000690 | Kirkwood - Upgrade ATM lobby and wheelch | Kirkwood - Upgrade ATM lobby and wheelch |  |  | Region 2 | Eastern Cape | 76548X | 1000-71013-01 | Absa Kirkwood-Hoof St-Kirkwood |  | 2022-09-01 | 2022-09-30 |  | ASP-EC0225 | CLSD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000691 | Absa Patensie - Extend Fence | Absa Patensie - Extend Fence |  |  | Region 2 | Eastern Cape |  | 1000-71036-01 | Building not in our database |  | 2022-09-30 | 2022-10-31 |  | ASP-EC0233 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-07-28 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000692 | Absa Patensie - External tap at Jojo tan | Absa Patensie - External tap at Jojo tan |  |  | Region 2 | Eastern Cape |  | 1000-71036-01 | Building not in our database |  | 2022-11-01 |  |  | ASP-EC0237 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000693 | Absa Plettenberg Bay - Additional seatin | Absa Plettenberg Bay - Additional seatin |  |  | Region 2 | Eastern Cape |  | 1000-71034-01 | Building not in our database |  | 2022-11-01 |  |  | ASP-EC0238 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000694 | Absa Fynbos Centre Stilbaai - Minor Work | Absa Fynbos Centre Stilbaai - Minor Work |  |  | Region 2 | Eastern Cape |  | 1000-70895-01 | Building not in our database |  | 2022-11-01 |  |  | ASP-EC0239 | REL AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-15 | D | 350000 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000695 | Absa Unionddale - SFP Mantrap, plugs, li | Absa Unionddale - SFP Mantrap, plugs, li |  |  | Region 2 | Eastern Cape |  | 1000-71039-01 | Building not in our database |  | 2022-11-01 |  |  | ASP-EC0240 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-15 | D | 250000 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000696 | Absa Prins Albert - BCTU and SFP Mantrap | Absa Prins Albert - BCTU and SFP Mantrap |  |  | Region 2 | Eastern Cape |  | 1000-71024-01 | Building not in our database |  | 2022-11-01 |  |  | ASP-EC0241 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-15 | D | 250000 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000697 | Absa Albertinia - SFP Mantrap and Lights | Absa Albertinia - SFP Mantrap and Lights |  |  | Region 2 | Eastern Cape |  | 1000-71033-01 | Building not in our database |  | 2022-12-30 |  |  | ASP-EC0242 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-17 | D | 245993.5 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000698 | Absa Kareedouw - Emergency Lights | Absa Kareedouw - Emergency Lights |  |  | Region 2 | Eastern Cape |  | 1000-71462-01 | Building not in our database |  | 2022-12-30 |  |  | ASP-EC0243 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-17 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000699 | Absa Beacon Bay - TTW Drop Safe | Absa Beacon Bay - TTW Drop Safe + Back Office Training Desk |  |  | Region 2 | Eastern Cape | 78299X | 1000-71041-01 | Beacon Bay Retail Park-Bonza Bay Rd-Beacon Bay | N | 2022-10-17 | 2022-10-31 |  | ASP-EC0245 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | CEASARS | 2022-08-26 | D | 167900.03 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Judith B | 100 | 2023-06-26 | 2023-08-03 | 167900.03 | Approved | {"MANDT":"111","REFERENCE":70000699,"ONEVIEW":"78299X","DATE01":"2023-06-02","DATE02":"2023-06-02","DATE03":"2023-06-14","DATE04":"2023-06-26","DATE05":"2023-08-03","DATE06":"2023-09-18","DATE07":"2023-09-22","DATE08":"2023-10-13","DATE09":"2023-10-23","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"151:0:12:12:38:46:4:21:10:17","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-18","FORECAST_END":"2023-09-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MiBBdWcgQXBwcm92ZWQgQ0IyOSAzIEF1Z3VzdCAtIFNpZ25lZCBEZWNrIFBlbmRpbmcgc2lnbmVkIGRlY2sgdG8gcmVxdWVzdCBQTydzCjE3IEp1bHkgUGVuZGluZyBmZWVkYmFjayBmcm9tIHJlZ2lvbiBhcyBwbGFjZWQgb24gaG9sZCBkdWUgdG8gZGVsaXZlcnkgY29zdApSZWdpb24gcXVlcmllZCBEZWxpdmVyeSBjb3N0IGZvciBVa2h1bmksIEFic2EgcHJvY3VyZW1lbnQgY29uc3VsdGVkLCBwZW5kaW5nIHJlZ2lvbmFsIHN1cHBvcnQgdG8gcmVzdWJtaXQg","RATING":""} |  |  | C000102808 | PHASE11 | 2023-09-06 | 2023-09-18 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-08 | 146000.03 | 0 |  |  | C000102808 | 146000.03 |  | 13634.09 |  | 0 | 0 |  | 0 |  | 0
70000700 | Absa Kareedouw - Entrance Decal | Absa Kareedouw - Entrance Decal |  |  | Region 2 | Eastern Cape | 78089X | 1000-71462-01 | Kareedouw Shopping Centre-Van Riebeeck St-Kareedouw |  | 2022-10-17 | 2022-10-31 |  | ASP-EC0246 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-08-26 | D | 10000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000701 | Absa Stone Waters - rusted generator can | Absa Stone Waters - rusted generator can |  |  | Region 2 |  |  |  | Building not in our database |  | 2022-11-01 |  |  | ASP-EC0250 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-09-06 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000702 | Absa Aliwal North - Indemnity Sig & Inte | Absa Aliwal North - Indemnity Sig & Inte |  |  | Region 2 | Eastern Cape | 79209X | 1000-71069-01 | Absa Aliwal North-Somerset St-Aliwal North |  | 2022-12-01 | 2022-12-31 |  | ASP-EC0255 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-09-30 | D | 15000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000703 | Prince Albert UPS Power Power connection | Prince Albert UPS Power Power connection |  |  | Region 2 | Eastern Cape | 77111X | 1000-71024-01 | Absa Prins Albert-Church St-Prins Albert | N | 2022-10-11 | 2023-04-30 |  | ASP-EC0256 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | GAMIETR | 2022-10-12 | D | 28429.44 | Approved at CB/BTB | 100 | 2023-03-16 | 2023-03-16 | 28429.44 | Approved | {"MANDT":"111","REFERENCE":70000703,"ONEVIEW":"77111X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-03-09","DATE04":"2023-03-16","DATE05":"2023-03-16","DATE06":"2023-04-06","DATE07":"2023-04-06","DATE08":"2023-05-16","DATE09":"2023-05-31","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:42:7:0:21:0:40:15:5","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-06","FORECAST_END":"2023-04-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTYgTWF5IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000074703 | PHASE11 | 2023-04-06 | 2023-04-06 | RODERICK NEVAY | Nokuthula Manzini | 23000414 |  |  |  |  | 2023-03-17 | 24721.25 | 0 |  |  | C000074703 | 24721.25 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000704 | Queenstown UPS Power connection | Queenstown UPS Power connection |  |  | Region 2 | Eastern Cape | 78801X | 1000-71054-01 | Hexagon Circle-Hexagon Circle-Queenstown | N | 2023-03-20 | 2023-04-30 |  | ASP-EC0257 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | GAMIETR | 2022-10-21 | D | 73031.59 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 73031.59 | Approved | {"MANDT":"111","REFERENCE":70000704,"ONEVIEW":"78801X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-20","DATE04":"2023-03-09","DATE05":"2023-03-09","DATE06":"2023-03-18","DATE07":"2023-03-20","DATE08":"2023-05-18","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:25:17:0:9:2:59:43:27","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-18","FORECAST_END":"2023-03-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWF5IFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZQ==","RATING":""} |  |  | C000073401 | PHASE11 | 2023-03-18 | 2023-03-20 | RODERICK NEVAY | Nokuthula Manzini | 23000334 |  |  |  |  | 2023-03-13 | 63505.73 | 0 |  |  | C000073401 | 63505.73 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000705 | Langeberg Mall Operating Hrs Decal | Langeberg Mall Operating Hrs Decal |  |  | Region 2 |  |  |  | Building not in our database |  | 2022-10-20 |  |  | ASP-EC0258 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-10-21 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000706 | 106 York Street George Frosting - Lifest | 106 York Street George Frosting - Lifest |  |  | Region 2 |  |  |  | Building not in our database |  | 2022-10-20 |  |  | ASP-EC0259 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-10-21 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000707 | Absa Patensie - New HVAC installation | Absa Patensie - New HVAC installation |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2022-12-01 | 2022-12-31 |  | ASP-EC0260 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  | F |  | CEASARS | 2022-10-25 | D | 0 |  | 1 |  |  | 0 | Approved against National Headwinds 31 May for R144 335.57 due to scope change to include Fire and Fresh Air - ALP-N00043 | {"MANDT":"111","REFERENCE":70000707,"ONEVIEW":"Unknown","DATE01":"2022-09-22","DATE02":"2022-09-29","DATE03":"2022-10-20","DATE04":"2022-10-27","DATE05":"2022-11-17","DATE06":"2022-12-01","DATE07":"2022-12-31","DATE08":"2023-01-21","DATE09":"2023-01-15","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-12-01","FORECAST_END":"2022-12-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-24 | 2023-04-23 | RODERICK NEVAY | nokuthula manzini | 23000388 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000708 | Absa Moffett Office Park - Alpha Plug Sets | Absa Moffett Office Park - Alpha Plug Sets |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-03-01 | 2023-04-28 |  | ASP-EC0262 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2022-10-26 | D | 87846.2 | Approved at CB/BTB | 100 | 2023-02-02 | 2023-02-02 | 87846.2 | Approved | {"MANDT":"111","REFERENCE":70000708,"ONEVIEW":"22937X","DATE01":"2022-10-22","DATE02":"2022-11-30","DATE03":"2023-01-27","DATE04":"2023-02-02","DATE05":"2023-02-02","DATE06":"2023-03-22","DATE07":"2023-03-22","DATE08":"2023-04-25","DATE09":"2023-05-31","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:39:58:6:0:48:0:34:36:15","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-22","FORECAST_END":"2023-03-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjUgQXByaWwgUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Low"} |  |  | C000066424 | PHASE11 | 2023-03-22 | 2023-03-22 | RODERICK NEVAY | Nokuthula Manzini | 23000322 |  |  |  |  | 2023-02-07 | 76388 | 0 |  |  | C000066424 | 76388 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000709 | Absa 85 Oxford East London - Close off A | Absa 85 Oxford East London - Close off A |  |  | Region 2 |  |  | 1000-71469-01 | Building not in our database |  | 2023-01-31 | 2023-01-31 |  | ASP-EC0264 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2022-11-16 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000710 | Pretoria Campus - DD Professional Fees | Pretoria Campus - DD Professional Fees |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-01-19 |  |  | ASP-GN0123 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-01-25 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000711 | Centurion Signage | Centurion Signage |  |  | Region 1 | Gauteng North | 77509X | 1000-70372-01 | United Bank Centurion-Cnr Hendrik Verwoerd Dr & Heuwel Ave-Centurion |  | 2021-01-29 | 2022-12-31 |  | ASP-GN0126 | REL BUDG AVAC SETC: |  | false | false |  | Yashir Somaru |  |  | 2021 |  |  |  | GAMIETR | 2022-02-09 | D | 5332.67 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":70000711,"ONEVIEW":"77509X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2021-01-29","DATE07":"2022-12-31","DATE08":"2023-01-21","DATE09":"2021-03-15","DATE10":"2021-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-01-29","FORECAST_END":"2022-12-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000053052 | PHASE08 | 2021-01-29 | 2022-12-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000053052 | 53326.71 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000712 | Mall@Reds ATM room floor tiles and paint | Mall@Reds ATM room floor tiles and paint |  |  | Region 1 | Gauteng North | 76471X | 1000-71382-01 | Mall@Reds-Cnr Hendrik Verwoerd Dr & Rooihuiskraal Rd-Pretoria |  | 2021-01-29 | 2022-03-31 |  | ASP-GN0127 | CLSD RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2021 |  |  |  | GAMIETR | 2022-02-15 | D | 7000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000713 | Absa Pretoria Campus Replace deck at the | Absa Pretoria Campus Replace deck at the |  |  | Region 1 | Gauteng North | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2021-01-29 | 2022-06-30 |  | ASP-GN0144 | CLSD ISBD AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2021 |  |  |  | GAMIETR | 2022-05-18 | D | 1497960 | Approved | 100 | 2023-10-07 | 2023-10-07 | 11344.34 |  |  |  |  | C000059731 | PHASE11 | 2021-01-29 | 2022-06-30 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-01-06 | 11344.34 | 0 |  |  | C000014888 | 9864.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000714 | Absa Pretoria Campus Waterproofing Reinforcement | Absa Pretoria Campus Waterproofing (Total Roof Area sqm) 13 789sqm IBR and 8200sqm concrete slabs -Waterproofing will be re-done in order to enhance the corporate image and to address the water ingress issues; -High pressure clean overall roof; -Repair rusted holes to end of click lock roof sheets; -Apply one full coat Duraflex Rust stop to clip lock sheets and two coats Duraflex liquid rubber grey to clip lock roof sheets; -Apply one full coat Duraflex Bond-it to concrete flat roof in various buildings; -Apply one full coat Duraflex Rubber seal to the roofs and two coats Duraflex liquid rubber to flat roof; Security Guarding Services to be provided for duration of project. " |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | Y | 2022-01-29 | 2022-10-31 |  | ASP-GN0145 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  | F |  | GAMIETR | 2022-05-30 | D | 7508005.42 | Upgrade and re-surfacing to existing waterproofing | 100 | 2023-07-21 | 2023-07-27 | 70508005 | Project approved and BFM PO issued. | {"MANDT":"111","REFERENCE":70000714,"ONEVIEW":"22491X","DATE01":"2021-11-20","DATE02":"2021-11-27","DATE03":"2021-12-18","DATE04":"2021-12-25","DATE05":"2022-01-15","DATE06":"2022-01-29","DATE07":"2023-12-22","DATE08":"2024-01-31","DATE09":"2023-12-25","DATE10":"2023-12-31","DATE11":"2023-12-06","DATE12":"2023-12-06","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":60,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"771:7:21:7:21:14:692:40:-37:25","PROGRESS":42,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-29","FORECAST_END":"2023-12-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQTyB0byBiZSBpc3N1ZWQgaW4gdGhlIGludGVyaW0KUGxhbm5lZCBzdGFydCBkYXRlLTEwLzEwLzIwMjMKUGxhbm5lZCBjb21wbGV0aW9uLTIzLzEyLzIwMjMKRmluYW5jaWFsIFJvbGwtb3ZlciAyMDI0ClBsYW5uZWQgY29tcGxldGlvbiBlbmQgIDMxIEphbiAyMDI0","RATING":"Medium"} |  |  | C0000144094 | PHASE11 | 2022-01-29 | 2023-12-22 | PRESHANE MUNTHREE | Obakeng Phuti | 0 | 2023-10-02 | 2023-11-18 | 2023-10-02 |  | 2023-03-11 | 61311308.7 | 0 |  |  | C000061197 | 94490.17 |  | 567060.91 |  | 0 | 0 |  | 0 |  | 0
70000715 | Pretoria Campus Electric Fence Replaceme | Pretoria Campus Electric Fence Replaceme |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2022-09-15 | 2022-10-31 |  | ASP-GN0161 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2022 |  |  |  | GAMIETR | 2022-09-19 | D | 12274.95 |  |  |  |  | 0 |  |  |  |  | 00021147-2 | CLOSED |  |  | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000716 | Waverley Branch Front Shop windows | Waverley Branch Front Shop windows |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-09-26 |  |  | ASP-GN0165 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-10-24 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000717 | Glen Marais (BOM-Woodbridge) BOM General | Glen Marais (BOM-Woodbridge) BOM General |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-11-20 |  |  | ASP-GN0170 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-11-21 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000718 | Absa Huis Herfsblaar Dil | Absa Huis Herfsblaar Dilaps and removal of signage |  | l | Region 1 | Gauteng North | 76685X | 1000-70312-01 | Huisherfsblaar-Webb St-Pretoria | N | 2022-10-31 | 2022-10-31 |  | ASP-GN0171 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2022 |  | L | 2023-01-30 | GAMIETR | 2022-11-21 | D | 4332.4 | Approved at CB/BTB | 100 | 2022-11-09 | 2023-01-25 | 4332.4 | Approved | {"MANDT":"111","REFERENCE":70000718,"ONEVIEW":"76685X","DATE01":"2022-09-06","DATE02":"2022-09-13","DATE03":"2022-10-04","DATE04":"2022-10-11","DATE05":"2022-11-01","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-01-21","DATE09":"2023-02-15","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:7:21:7:21:-304:383:2:25:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000063834 | PHASE11 | 2023-01-04 | 2023-01-05 | PRESHANE MUNTHREE | Obakeng Phuti | 23000631 | 2023-02-15 | 2023-03-22 |  |  | 2023-01-23 | 4332.4 | 0 |  |  | C000063834 | 3767.3 |  | 315.45 |  | 0 | 0 |  | 0 |  | 0
70000719 | Absa Towers West & North Remedial Work | Absa Towers West & North Remedial Work |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-01-03 | 2022-01-31 |  | ASP-GS0407 | CRTD: |  | false | false |  | Yashir Somaru |  |  | 2022 |  |  |  | GAMIETR | 2022-01-04 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000720 | Trade Route Mall Minor Works | Trade Route Mall Minor Works |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-01-28 |  |  | ASP-GS0413 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-01-31 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000721 | Eastgate International Repaint entire br | Eastgate International Repaint entire br |  |  | Region 1 |  | 76420X | 1000-70247-01 | Eastgate Shopping Centre-Bradford Rd-Bedfordview |  | 2022-01-28 | 2022-03-31 |  | ASP-GS0414 | CLSD BUDG AVAC SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | GAMIETR | 2022-01-31 | D | 4336.06 |  |  |  |  | 0 |  |  |  |  | 2902117 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000722 | Eastgate Repaint entire branch | Eastgate Repaint entire branch |  |  | Region 1 |  | 76420X | 1000-70247-01 | Eastgate Shopping Centre-Bradford Rd-Bedfordview |  | 2022-01-28 | 2022-03-31 |  | ASP-GS0415 | CLSD BUDG AVAC SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | GAMIETR | 2022-01-31 | D | 16514.29 |  |  |  |  | 0 |  |  |  |  | 2902116 | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000723 | Norwood Mall Minor Works | Uplift existing old carpets and install vinyl flex floor is (362 sqm) Allow for 75mm anodised aluminium skirting 286m Supply 6 X benches in the Banking hall Cut wall in the Teller area to install space saver safe Allow for builders work around the Space Saver Safe and make good Finish wall to match existing and paint Clean area on completion Work will be conducted over 6 nights (after Hours), which includes 6 weekdays & 1 weekend and will not interfere with business operations. |  |  | Region 1 | Gauteng South | 78421X | 1000-70403-01 | Norwood Mall-Cnr 6th Ave & Hamlin St-Norwood | N | 2023-01-29 | 2023-04-30 |  | ASP-GS0421 | REL BUDG AVAC RESA SETC: |  | R | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2022-02-09 | D | 430367.67 | Approved at CB/BTB | 100 | 2023-01-26 | 2023-01-26 | 430367.67 | Approved | {"MANDT":"111","REFERENCE":70000723,"ONEVIEW":"78421X","DATE01":"2022-11-20","DATE02":"2022-11-27","DATE03":"2022-12-18","DATE04":"2022-12-25","DATE05":"2023-01-15","DATE06":"2023-02-01","DATE07":"2023-02-28","DATE08":"2023-03-30","DATE09":"2023-05-09","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-01","FORECAST_END":"2023-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000066536 | PHASE11 | 2023-02-01 | 2023-02-28 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000498 |  |  |  |  | 2023-02-07 | 430367.66 | 0 |  |  | C000066536 | 374232.75 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000724 | Mall @ Carnival - Minor Works | Mall @ Carnival - Minor Works |  |  | Region 1 |  |  |  | Building not in our database |  | 2020-06-30 |  |  | ASP-GS0422 | CRTD: |  | false | false |  |  |  |  | 2020 |  |  |  | GAMIETR | 2022-02-11 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000725 | Mall @ Carnival Evacuation door require | Mall @ Carnival Evacuation door require |  |  | Region 1 | Gauteng South | 21869X | 1000-70043-01 | Mall@Carnival-Cnr Airport & Heidelberg Rd-Brakpan |  | 2021-01-29 | 2022-03-31 |  | ASP-GS0425 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2021 |  |  |  | GAMIETR | 2022-02-15 | D | 50000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000726 | Absa Annan Road, Carletonville Ceiling t | Absa Annan Road, Carletonville Ceiling t |  |  | Region 1 | Gauteng South | 76403X | 1000-70241-01 | Absa Annan Road-Annan Rd-Carletonville |  | 2021-01-29 | 2022-03-31 |  | ASP-GS0426 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2021 |  |  |  | GAMIETR | 2022-02-15 | D | 50000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000727 | OR Tambo International Airport Repaintin | OR Tambo International Airport Repaintin |  |  | Region 1 | Gauteng South | 76576X | 1000-70291-01 | OR Tambo International Airport-R24 Highway-Kempton Park |  | 2021-01-29 | 2022-03-31 |  | ASP-GS0427 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2021 |  |  |  | GAMIETR | 2022-02-15 | D | 30000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000728 | The Village Square Repaint entire branch | The Village Square Repaint entire branch |  |  | Region 1 | Gauteng North | 77666X | 1000-71401-01 | The Village Square-Main Reef Rd-Randfontein |  | 2021-01-29 | 2022-03-31 |  | ASP-GS0428 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2021 |  |  |  | GAMIETR | 2022-02-15 | D | 40000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000729 | Daveyton Sales Consultant Desk | Daveyton Sales Consultant Desk |  |  | Region 1 | Gauteng South | SGS_10941 | 1000-67723-01 | Daveyton-- |  | 2022-02-15 | 2022-03-31 |  | ASP-GS0429 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | GAMIETR | 2022-02-21 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000730 | Quo Vadis Centre, Westonaria Back office | Quo Vadis Centre, Westonaria Back office |  |  | Region 1 | Gauteng South | 76563X | 1000-70289-01 | Quo Vadis Centre-Pakeman St-Westonaria |  | 2021-01-29 | 2022-04-30 |  | ASP-GS0433 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2021 |  |  |  | GAMIETR | 2022-03-07 | D | 27400 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000731 | 270 Republic Road - Red plugs & circuit | 270 Republic Road - Red plugs & circuit |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-03-14 |  |  | ASP-GS0435 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-03-14 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000732 | Oakfields Enclose Counters | Oakfields Enclose Counters |  |  | Region 1 |  | 79055X | 1000-71417-01 | Oakfields Shopping Centre-Cnr Oak & Hanekom St-Benoni |  | 2022-03-18 | 2022-04-30 |  | ASP-GS0437 | CLSD AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | GAMIETR | 2022-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000733 | Absa Towers West Replace the Absa Logo o | Absa Towers West Replace the Absa Logo o |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2021-01-29 |  |  | ASP-GS0448 | CRTD: |  | false | false |  |  |  |  | 2021 |  |  |  | GAMIETR | 2022-04-19 | D | 170000 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000734 | Towers West Art Hot Spot Gallery Opening | Towers West Art Hot Spot Gallery Opening |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-05-27 | 2022-08-31 |  | ASP-GS0464 | CRTD: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-05-30 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000735 | Tsakane mall- Relocate wall mounted airc | Tsakane mall- Relocate wall mounted airc |  |  | Region 1 |  | 21857X | 1000-70041-01 | Tsakane Mall-Cnr Modjadji & Malandela St-Tsakane |  | 2022-06-23 | 2022-12-15 |  | ASP-GS0478 | CRTD AVAC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | LOUISR | 2022-06-14 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | PRESHANE MUNTHREE |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000736 | Ackland park- Temperature Difference Ass | Ackland park- Temperature Difference Ass |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-06-23 | 2022-12-15 |  | ASP-GS0481 | CRTD AVAC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | LOUISR | 2022-06-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | PRESHANE MUNTHREE |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000737 | Meadowdale- Replace floor tiles on fron | Meadowdale- Replace floor tiles on fron |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-07 | 2022-12-15 |  | ASP-GS0483 | CRTD AVAC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  |  |  | LOUISR | 2022-06-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000738 | 270 Republic Road - Replace PA system | 270 Republic Road - Replace PA system |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-07 |  |  | ASP-GS0485 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-06-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000739 | Alice Lane North 2nd Floor Wallpaper Ins | Alice Lane North 2nd Floor Wallpaper Ins |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-29 |  |  | ASP-GS0500 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-07-18 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000740 | Alice Lane Towers Kitchen Plumbing Repai | Alice Lane Towers Kitchen Plumbing Repai |  |  | Region 1 | Gauteng South | 70656X | 1000-71371-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-07-29 | 2022-09-30 |  | ASP-GS0511 | REL BUDG AVAC SETC: |  | R | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | GAMIETR | 2022-07-28 | D | 3970.33 | Approved | 100 | 2023-10-07 | 2023-10-07 | 45658.78 |  |  |  |  | C000062105 | PHASE11 | 2022-01-01 | 2023-01-19 | CHRISTOPHER MPOFU | Michael Maluleka | 23000584 |  |  |  |  | 2023-01-18 | 45658.78 | 0 |  |  | C000062105 | 39703.29 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000741 | Highlands Warehouse Boundary Wall Repai | Highlands Warehouse Boundary Wall Repai |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2022-07-29 | 2022-09-30 |  | ASP-GS0512 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-07-29 | D | 475 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000742 | Aucklandpark- Safety net installation | Aucklandpark- Safety net installation |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-08-18 | 2022-12-15 |  | ASP-GS0513 | REL BUDG AVAC SETC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | LOUISR | 2022-08-05 | D | 41176 |  |  |  |  | 0 |  |  |  |  | C000060729 | IGNORE |  |  | LUCIA AMUNGA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-11 | 90669.99 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000743 | Alberton Procurement of Frames | Alberton Procurement of Frames |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-29 |  |  | ASP-GS0514 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000744 | Auckland Park 6 Industrial Microwaves Me | Auckland Park 6 Industrial Microwaves Me |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-07-29 | 2022-12-31 |  | ASP-GS0523 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-08-11 | D | 9067 |  |  |  |  | 0 |  |  |  |  | C000030642 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000745 | Northmead Replace Aircon Condesner Unit | Northmead Replace Aircon Condesner Unit |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-29 | 2022-10-31 |  | ASP-GS0536 | CRTD: |  | false | false |  | Yashir Somaru |  |  | 2022 |  |  |  | GAMIETR | 2022-09-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000746 | Towers East Goods lift water damaged-App | Towers East Goods lift water damaged-App |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-29 |  |  | ASP-GS0538 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-09-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000747 | Auckland Park Waterproofing-Ford Credit- | Auckland Park Waterproofing-Ford Credit- |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-07-29 |  |  | ASP-GS0543 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-09-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000748 | Highlands Warehouse Consulting fees for | Highlands Warehouse Consulting fees for |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-09-26 |  |  | ASP-GS0546 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-09-26 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000749 | Alice Lane North Supply of new 20 x DATO | Alice Lane North Supply of new 20 x DATO |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-11-01 | 2022-12-30 |  | ASP-GS0567 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | GAMIETR | 2022-11-02 | D | 10392 | Approved | 100 | 2023-10-07 | 2023-10-07 | 119508 |  |  |  |  | C000062848 | PHASE11 | 2022-11-01 | 2022-12-30 | PRESHANE MUNTHREE | Buhle Qwabe | 23000531 |  |  |  |  | 2023-01-20 | 119508 | 0 |  |  | C000047869 | 103920 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000750 | Towers West Supply and install new opera | Towers West Supply and install new opera |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-11-01 | 2022-12-15 |  | ASP-GS0568 | CRTD: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-11-02 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000062829# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-01-20 | 1443.48 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000751 | Auckland Park Gym revamp | Auckland Park Gym revamp |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-11-01 |  |  | ASP-GS0576 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-11-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000752 | Sunward Park Replacement of damaged floo | Sunward Park Replacement of damaged floo |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-11-07 |  |  | ASP-GS0577 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-11-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000753 | Auckland Park CC Supply and delivery of | Auckland Park CC Supply and delivery of |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-11-07 |  |  | ASP-GS0578 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-11-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000754 | Various Sites 4 x Microwaves Stock | Various Sites 4 x Microwaves Stock |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-11-07 | 2022-12-15 |  | ASP-GS0579 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2022 |  |  |  | GAMIETR | 2022-11-09 | D | 6058 |  |  |  |  | 0 |  |  |  |  | C000039617 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000755 | Absa Towers North LG Storeroom-Cable Man | Absa Towers North LG Storeroom-Cable Man |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-10-14 |  |  | ASP-GS0584 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-11-13 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000756 | Alice Lane South Furniture re-upholster | Alice Lane South Furniture re-upholster |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-10-14 |  |  | ASP-GS0586 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-11-21 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000757 | Alice Lane North - Coffee bar door repla | Alice Lane North - Coffee bar door repla |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2023-02-28 | 2023-03-31 |  | ASP-GS0587 | REL BUDG AVAC SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2022-11-21 | D | 2102.13 | Approved at CB/BTB |  | 2023-02-16 | 2023-02-16 | 24174.55 | Approved |  |  |  | C000069658 | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-02-22 | 21021.34 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000758 | Absa Musgrave - New 15KVa UPS with Batte | Absa Musgrave - New 15KVa UPS with Batte |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-02-09 |  |  | ASP-KZ0149 | CRTD AVAC: |  | false | false |  | Nthabiseng Sathekge |  |  | 2022 |  |  |  | CEASARS | 2022-02-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000759 | Pavillion ShopCentre - TTW Drop Safe | Pavillion ShopCentre - TTW Drop Safe |  |  | Region 3 |  | 77543X | 1000-71182-01 | The Pavillion Shopping Centre-Jack Martens Dr-Westville |  | 2022-07-01 |  |  | ASP-KZ0169 | CRTD AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | CEASARS | 2022-05-16 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000760 | Absa Bell Street - Minor Works | Absa Bell Street - Minor Works |  |  | Region 3 |  | 76978X | 1000-71151-01 | Absa Bell Street-Cnr Bell & Pine St-Greytown |  | 2022-07-29 |  |  | ASP-KZ0170 | REL AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | CEASARS | 2022-05-18 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000761 | AVAF Trade Centre- Geyser Retrosp. | AVAF Trade Centre- Geyser Retrosp. |  |  | Region 3 |  | 22338X | 1000-71093-01 | AVAF Trade Centre-Hunter St-Durban |  | 2022-07-14 |  |  | ASP-KZ0172 | CRTD AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-05-25 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000762 | Davenport - Painting, counter tops and l | Davenport - Painting, counter tops and l |  |  | Region 3 |  |  |  | Building not in our database |  | 2021-09-17 |  |  | ASP-KZ0173 | CRTD: |  | false | false |  |  |  |  | 2021 |  |  |  | CEASARS | 2022-06-06 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000763 | Absa Davenport -Minor Works Variation Or | Absa Davenport -Minor Works Variation Or |  |  | Region 3 | KwaZulu-Natal | 77015X | 1000-71153-01 | Glenwood-Brand Rd-Berea |  | 2022-07-28 | 2022-09-08 |  | ASP-KZ0180 | CRTD: |  | R | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-28 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":70000763,"ONEVIEW":"77015X","DATE01":"2022-05-19","DATE02":"2022-06-16","DATE03":"2022-06-23","DATE04":"2022-06-23","DATE05":"2022-07-28","DATE06":"2022-09-08","DATE07":"2022-09-29","DATE08":"2022-11-13","DATE09":"2022-11-30","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-08","FORECAST_END":"2022-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZQ==","RATING":""} |  |  |  | PHASE10 | 2022-09-08 | 2022-09-29 |  |  | 23000569 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000764 | Chatterton Road Private Bank - Dilaps | Chatterton Road Private Bank - Dilaps |  |  | Region 3 |  | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg |  | 2022-10-21 |  |  | ASP-KZ0184 | CRTD AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-08-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000765 | Absa Arbour Crossing Retail - Minor Refr | Absa Arbour Crossing Retail - Minor Refr |  |  | Region 3 |  | 70634X | 1000-71145-01 | Arbour Crossing Retail Centre-Arbour Rd-Amanzimtoti |  | 2022-10-21 |  |  | ASP-KZ0185 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-08-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000766 | Absa Hillcrest-Worktop in ATM Room | Absa Hillcrest-Worktop in ATM Room |  |  | Region 3 |  | 77291X | 1000-71164-01 | Pick & Pay Christians Village-Cnr Old Main & Inanda Rd-Hillcrest |  | 2022-10-12 | 2022-10-17 |  | ASP-KZ0188 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-12 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000767 | Absa Pavillion - Worktop in ATM Room | Absa Pavillion - Worktop in ATM Room |  |  | Region 3 |  | 77543X | 1000-71182-01 | The Pavillion Shopping Centre-Jack Martens Dr-Westville |  | 2022-10-17 | 2022-10-17 |  | ASP-KZ0189 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-12 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000768 | Absa Ridgeside- Backwall Remedial Work& | Absa Ridgeside- Backwall Remedial Work& |  |  | Region 3 |  | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2022-11-07 |  |  | ASP-KZ0195 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-10 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000769 | Absa Chatterton Private Bank-Minor Refur | Absa Chatterton Private Bank-Minor Refur |  |  | Region 3 |  | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg |  | 2022-11-04 | 2022-11-26 |  | ASP-KZ0204 | CRTD DLFL AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-21 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000770 | Absa Arbour Crossing- Minor Refurbishmen | Absa Arbour Crossing- Minor Refurbishmen |  |  | Region 3 |  | 70634X | 1000-71145-01 | Arbour Crossing Retail Centre-Arbour Rd-Amanzimtoti |  |  | 2022-10-21 |  | ASP-KZ0205 | CRTD DLFL AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2022-10-21 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000771 | Die Restant Newcastle - Split generator | Die Restant Newcastle - Split generator |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-05-05 | 2022-11-30 |  | ASP-KZ0210 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000772 | Absa Hillcrest- Replacement of Damaged G | Absa Hillcrest- Replacement of Damaged G |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-11-11 |  |  | ASP-KZ0212 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-13 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000773 | Absa Jozini (Ithala Centre)- Dilaps | Absa Jozini (Ithala Centre)- Dilaps |  |  | Region 3 |  | 77681X | 1000-71617-01 | Ithala Centre Makhathini-Main Rd-Jozini |  | 2022-11-30 | 2022-12-30 |  | ASP-KZ0213 | REL AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000774 | Absa Thaba Mall - UPS batteries (IntelC | Absa Thaba Mall - UPS batteries (IntelC |  |  | Region 3 |  | 37045X | 1000-70507-01 | Thaba Mall-Cnr Warmbad Weg Rd & R510-Thabazimbi |  | 2022-02-07 | 2022-02-28 |  | ASP-LP0109 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | CEASARS | 2022-02-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000775 | Absa Landros Mare Pioneer Centre - UPS & | Absa Landros Mare Pioneer Centre - UPS & |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-03-25 |  |  | ASP-LP0118 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-03-11 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000776 | Absa Maake Plaza - TCR Project | Absa Maake Plaza - TCR Project |  |  | Region 3 |  | 22530X | 1000-70472-01 | Maake Plaza-Cnr R36 & Main Rd-Tzaneen |  | 2022-08-01 | 2022-09-30 |  | ASP-LP0123 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | CEASARS | 2022-05-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-08-01 | 2022-09-30 | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000777 | Absa Tzaneen Hotel - Minor Works | Absa Tzaneen Hotel - Minor Works |  |  | Region 3 |  | 76808X | 1000-70526-01 | Danie Joubert Street Tzaneen-Danie Joubert St Tzaneen Hotel-Tzaneen |  | 2022-07-07 |  |  | ASP-LP0126 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | CEASARS | 2022-05-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000778 | Absa Matsamo- Install New Generator & UP | Absa Matsamo- Install New Generator & UP |  |  | Region 3 |  | 77316X | 1000-70622-01 | Matsamo Plaza-Cnr R570 & R323 Rd-Matsamo |  | 2022-09-01 |  |  | ASP-LP0128 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-28 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | Siyanda Dlamini | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000779 | Absa Senwabarwana - Minor Wors | Absa Senwabarwana - Minor Wors |  |  | Region 3 |  | 22539X | 1000-70473-01 | Blouberg Mall-Blouberg Rd-Bochum |  | 2022-09-01 | 2022-09-01 |  | ASP-LP0129 | CLSD AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-28 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | Siyanda Dlamini | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000780 | Absa Makhado Crossing- Canopy to CIT Del | Absa Makhado Crossing- Canopy to CIT Del |  |  | Region 3 |  | 37073X | 1000-70508-01 | Makhado Crossing Shopping Centre-Cnr Sibasa & N1 Main Rd-Makhado |  | 2022-11-01 |  |  | ASP-LP0138 | CLSD AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-16 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000781 | Absa Savanah Mall-Refurbishment Internal | Absa Savanah Mall-Refurbishment Internal |  |  | Region 3 |  | 21331X | 1000-70452-01 | Savannah Mall-Cnr Grimm & Thabo Mbeki St-Polokwane |  | 2022-10-20 |  |  | ASP-LP0139 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-16 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000782 | Absa Mokopane -Bumper Rail consultant Of | Absa Mokopane -Bumper Rail consultant Of |  |  | Region 3 |  | 76721X | 1000-70668-01 | Mokopane-Thabo Mbeki St-Mokopane |  | 2022-10-20 |  |  | ASP-LP0140 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-16 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000783 | Absa 76E Schoeman- Dilaps VO | Absa 76E Schoeman- Dilaps VO |  |  | Region 3 |  | 76717X | 1000-70518-01 | 76E Schoeman Street-Schoeman St-Polokwane |  | 2022-10-14 | 2022-10-21 |  | ASP-LP0142 | REL BUDG AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-10-13 | D | 1156.06 |  |  |  |  | 0 |  |  |  |  | C000062139# | IGNORE |  |  | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-01-18 | 11560.64 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000784 | 20 Paul kruger- Installation of new Hydr | 20 Paul kruger- Installation of new Hydr |  |  | Region 1 |  | 77878X | 1000-70683-01 | Absa, Square-Paul Kruger St-Nelspruit |  | 2022-03-17 | 2022-12-15 |  | ASP-MP0099 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | LOUISR | 2022-03-10 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000785 | Absa Nelspruit-Minor Works Dilaps | Absa Nelspruit-Minor Works Dilaps |  |  | Region 3 |  | 37007X | 1000-70591-01 | Nelspruit Plaza-Cnr Henshall & Bester St-Nelspruit |  | 2022-07-14 |  |  | ASP-MP0108 | CLSD AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-06-14 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | Siyanda Dlamini | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000786 | Absa Phalaborwa- Replacement of HVAC | Absa Phalaborwa- Replacement of HVAC |  |  | Region 3 |  | 79265X | 1000-70559-01 | Thulamahashe Plaza-Main Rd-Phalaborwa |  | 2022-09-08 | 2022-11-17 |  | ASP-MP0109 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-12 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000787 | Absa Standerton Centre- Dilaps | Absa Standerton Centre- Dilaps |  |  | Region 3 |  | 77093X | 1000-70608-01 | Standerton-Charl Cilliers St-Standerton |  | 2022-10-20 |  |  | ASP-MP0119 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-16 | D | 11052.71 |  |  |  |  | 0 |  |  |  |  | C000041576 | CLOSED |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000788 | Absa White River - Enclosed manager offi | Absa White River - Enclosed manager offi |  |  | Region 3 |  | 77602X | 1000-70682-01 | White River Square-Cnr Chief Mgiyeni Khumalo Dr & Hennie Van Till St-White River |  | 2022-06-01 | 2022-09-30 |  | ASP-MP0123 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | CEASARS | 2022-04-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000789 | Absa Jock of Bushveld - Minor Works [Bli | Absa Jock of Bushveld - Minor Works [Bli |  |  | Region 3 |  | 77136X | 1000-70611-01 | Jock of the Bushveld Centre-General St-Barberton |  | 2022-06-01 | 2022-07-29 |  | ASP-MP0124 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | CEASARS | 2022-04-26 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-06-01 | 2022-07-29 | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000790 | PROJECT CANCELLED | PROJECT CANCELLED |  |  | Region 3 |  | 77028X | 1000-70606-01 | Kriel Mall-Bronwyn St-Kriel |  | 2022-05-19 |  |  | ASP-MP0125 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | CEASARS | 2022-05-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-05-19 | 2022-06-30 | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000791 | "Absa Piet Retief - Refresh building fac | "Absa Piet Retief - Refresh building fac |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-08-05 |  |  | ASP-MP0137 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000792 | Absa Standerton - Branch project swing S | Absa Standerton - Branch project swing S |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-11-30 |  |  | ASP-MP0138 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000793 | Absa KG Mall - Cleaner Storage Cabinet | Absa KG Mall - Cleaner Storage Cabinet |  |  | Region 3 |  | 37068X | 1000-70595-01 | KG Mall-Cnr N4 East & Mathew Phosa Dr-Witbank |  | 2022-11-30 | 2022-11-30 |  | ASP-MP0139 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-02 | D | 530.8 | Approved at CB/BTB |  | 2023-02-02 | 2023-02-02 | 6104.2 | Approved |  |  |  | C000066425 | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-02-07 | 5308 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000794 | Absa Witbank- Replacement of stolen Copp | Absa Witbank- Replacement of stolen Copp |  |  | Region 3 |  | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank |  | 2022-11-30 | 2022-11-30 |  | ASP-MP0140 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000795 | Absa Square Mbombela - Replace Server Ro | Absa Square Mbombela - Replace Server Ro |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-12-26 |  |  | ASP-MP0142 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000796 | National- Corporate smart meter roll out | National- Corporate smart meter roll out |  |  | National |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-07-15 | 2022-12-15 |  | ASP-N00039 | CRTD AVAC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | LOUISR | 2022-07-01 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000797 | Various Corporate Sites- Vivreau brandin | Various Corporate Sites- Vivreau brandin |  |  | National |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-09-12 | 2022-12-15 |  | ASP-N00043 | CRTD AVAC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | LOUISR | 2022-09-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000798 | Various-Replacement of INTELCAB batterie | Various-Replacement of INTELCAB batterie |  |  | National |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-10-20 | 2022-12-15 |  | ASP-N00044 | CRTD AVAC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | LOUISR | 2022-10-11 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000799 | Absa Atlantis City Mall - Generator & Ca | Absa Atlantis City Mall - Generator & Ca |  |  | Region 2 | Western Cape | 77927X | 1000-71441-01 | Atlantis City Mall-Wesfleur Circle-Atlantis |  | 2022-04-04 | 2022-04-30 |  | ASP-WC0191 | CLSD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-02-15 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000800 | Bonnievale - Minor Works | Bonnievale - Minor Works |  |  | Region 2 | Western Cape |  | 1000-70842-01 | Building not in our database |  | 2022-04-04 | 2022-04-29 |  | ASP-WC0193 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-02-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-04-04 | 2022-04-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000801 | Brackenfell Shopping Centre - Minor Work | Brackenfell Shopping Centre - Minor Work |  |  | Region 2 | Western Cape |  | 1000-70862-01 | Building not in our database |  | 2022-06-01 | 2022-06-30 |  | ASP-WC0200 | REL AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-03-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-06-01 | 2022-06-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000802 | Absa Lower Long - Waterproofing | Absa Lower Long - Waterproofing |  |  | Region 2 | Western Cape |  | 1000-71437-01 | Building not in our database |  | 2022-04-18 | 2022-05-31 |  | ASP-WC0201 | REL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-03-07 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-04-18 | 2022-05-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000803 | Malmesbury - Revamp Teller Counter and r | Malmesbury - Revamp Teller Counter and r |  |  | Region 2 | Western Cape | 78113X | 1000-70887-01 | Absa Malmesbury-Voortrekker Rd-Malmesbury |  | 2022-09-01 | 2022-09-30 |  | ASP-WC0210 | CLSD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-04-13 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-09-01 | 2022-09-30 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000804 | 30 on Main Grabouw - Repaint grey walls | 30 on Main Grabouw - Repaint grey walls |  |  | Region 2 | Western Cape | 36241X | 1000-70760-01 | 30 on Main Grabouw-Cnr Oudeberg Rd & Voortrekker St-Grabouw |  | 2022-09-01 | 2022-09-30 |  | ASP-WC0212 | CLSD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-04-19 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000805 | PROJECT CANCELLED | PROJECT CANCELLED |  |  | Region 2 | Western Cape |  | 1000-70854-01 | Building not in our database |  | 2022-06-01 | 2022-07-29 |  | ASP-WC0214 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-04-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-06-01 | 2022-07-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000806 | Absa Montagu Cogmans Centre - HVAC | Absa Montagu Cogmans Centre - HVAC |  |  | Region 2 |  |  | 1000-70854-01 | Building not in our database |  | 2022-07-07 | 2022-09-30 |  | ASP-WC0218 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-05-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000807 | Absa Worcester Stockenstrom St - Securit | Absa Worcester Stockenstrom St - Securit |  |  | Region 2 | Western Cape |  | 1000-70870-01 | Building not in our database |  | 2022-07-07 | 2022-09-30 |  | ASP-WC0219 | REL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-05-24 | D | 60000 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000808 | Eskom Building - Swellendam - Minor Work | Eskom Building - Swellendam - Minor Work |  |  | Region 2 | Western Cape | 78147X | 1000-70893-01 | Eskom Building-Voortrek St-Swellendam |  | 2022-09-01 |  |  | ASP-WC0223 | PREL DLFL AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-07-18 | D | 475000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000809 | Airport ShopCentre - Belhar- Minor Works | Airport ShopCentre - Belhar- Minor Works |  |  | Region 2 | Western Cape | 78324X | 1000-70896-01 | Airport Shopping Centre-Cnr Belhar & Stellenbosch Arterial Dr-Belhar |  | 2022-09-19 |  |  | ASP-WC0224 | CLSD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-07-18 | D | 451000 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000810 | Absa Saldanha Simphiwe - Ceiling Tiles | Absa Saldanha Simphiwe - Ceiling Tiles |  |  | Region 2 | Western Cape | 77766X | 1000-70856-01 | Simphiwe Building-Saldanha Rd-Saldanha |  | 2022-06-01 |  |  | ASP-WC0226 | CLSD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-07-20 | D | 383999 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000811 | Absa Clanwilliam Kunshuis - Fire extingu | Absa Clanwilliam Kunshuis - Fire extingu |  |  | Region 2 | Western Cape |  | 1000-71431-01 | Building not in our database |  | 2022-09-30 |  |  | ASP-WC0229 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-08-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000812 | Absa Bonnievale- midwall split unit | Absa Bonnievale- midwall split unit |  |  | Region 2 | Western Cape |  |  | Building not in our database |  | 2022-11-01 |  |  | ASP-WC0234 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-09-06 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000813 | Absa Worcester - Install electric fence | Absa Worcester - Install electric fence |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester-Stockenstrom St-Worcester |  | 2022-11-01 | 2022-11-30 |  | ASP-WC0236 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-09-06 | D | 1401.72 |  |  |  |  | 0 |  |  |  |  | C000061215# | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-01-13 | 667.49 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000814 | Absa Bridge Park West 3rd Floor - Dilaps | Absa Bridge Park West 3rd Floor - Dilaps |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town |  | 2022-12-01 |  |  | ASP-WC0239 | CRTD DLFL AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-09-13 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000815 | Absa Alexandria - Dilaps COC Ph2 Remedia | Absa Alexandria - Dilaps COC Ph2 Remedia |  |  | Region 2 |  |  |  | Building not in our database |  | 2022-12-01 |  |  | ASP-WC0240 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-09-14 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000816 | Absa Heidelberg Dilaps | Absa Heidelberg Dilaps |  |  | Region 2 | Western Cape |  | 1000-70879-01 | Building not in our database |  | 2022-12-01 |  |  | ASP-WC0241 | REL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-09-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000817 | Zevenwacht Mall Kuilsriver - LED Lights | Zevenwacht Mall Kuilsriver - LED Lights |  |  | Region 2 | Western Cape |  | 1000-70897-01 | Building not in our database |  | 2022-11-01 |  |  | ASP-WC0242 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-09-22 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000818 | Absa Moorreesburg - Minor Works | Absa Moorreesburg - Minor Works |  |  | Region 2 | Western Cape | 77249X | 1000-70811-01 | Absa Moorreesburg-Cnr Main & Long St-Moorreesburg |  | 2022-12-01 |  |  | ASP-WC0243 | CLSD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-10-05 | D | 324246.56 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000819 | Absa Ceres - Minor Works | Absa Ceres - Minor Works |  |  | Region 2 | Western Cape | 70568X | 1000-70782-01 | Ceres-Voortrekker St-Ceres | N | 2022-12-01 |  |  | ASP-WC0244 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-10-05 | D | 382945.02 |  | 100 | 2022-10-27 | 2022-10-27 | 382945.02 |  | {"MANDT":"111","REFERENCE":70000819,"ONEVIEW":"70568X","DATE01":"2022-10-03","DATE02":"2022-10-05","DATE03":"2022-10-19","DATE04":"2022-10-27","DATE05":"2022-10-27","DATE06":"2022-11-14","DATE07":"2022-12-05","DATE08":"2022-12-06","DATE09":"2023-01-13","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:2:14:8:0:18:21:1:38:18","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-14","FORECAST_END":"2022-12-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBEZWMgRmluYWwgUE9DIFBhY2sgU3VibWl0dGVk","RATING":"Low"} |  |  | C000062737 | PHASE11 | 2022-11-14 | 2022-12-05 | RODERICK NEVAY | Michael Maluleka | 23000504 |  |  |  |  | 2023-01-20 | 332995.67 | 0 |  |  | C000046438 | 332995.67 | CIP2023XP | 10700.83 |  | 0 | 0 |  | 0 |  | 0
70000820 | Absa Airport Mall Belhar - Emergency Lig | Absa Airport Mall Belhar - Emergency Lig |  |  | Region 2 |  |  | 1000-70896-01 | Building not in our database |  | 2022-12-01 |  |  | ASP-WC0251 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-11-08 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000821 | Absa 32 Voortrekker - Relocation of Chec | Absa 32 Voortrekker - Relocation of Chec |  |  | Region 2 |  |  | 1000-70888-01 | Building not in our database |  | 2022-11-30 |  |  | ASP-WC0254 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-11-15 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000822 | Absa Riebeeck West - AC Cassette Units | Absa Riebeeck West - AC Cassette Units |  |  | Region 2 | Western Cape | 78135X | 1000-70892-01 | 13 Voortrekker Street Riebeek West-Voortrekker St-Cape Town | N | 2022-12-01 |  |  | ASP-WC0255 | CLSD BUDG AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  | L |  | CEASARS | 2022-11-18 | D | 139580.38 | Approved at CB/BTB | 1 | 2023-01-27 | 2023-02-02 | 139580.37 | 7 July Signed Deck received to Cancel PO's 6 July Signed deck Pending 4 July Signed CB Deck Pending for all PO's to be cancelled 29 June Change Note Approved at CB Signed Deck to Follow in order to Cancel all PO's, Budget to be reallocated 20 June Confirmation received Branch is closing BC to be tabled to reverse approval. | {"MANDT":"111","REFERENCE":70000822,"ONEVIEW":"78135X","DATE01":"2022-11-18","DATE02":"2022-11-25","DATE03":"2022-12-16","DATE04":"2023-01-27","DATE05":"2023-02-02","DATE06":"2023-04-03","DATE07":"2023-05-03","DATE08":"2023-05-24","DATE09":"2023-05-18","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:42:6:60:30:21:-6:16","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-03","FORECAST_END":"2023-05-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBNYXJjaCAtIFdhcyBQbGFjZWQgb24gSG9sZCBQb3N0IGFwcHJvdmFsIHBlbmRpbmcgc2l0ZSBjbG9zdXJlCjIwIEp1bmUgQ29uZmlybWF0aW9uIHJlY2VpdmVkIEJyYW5jaCBpcyBjbG9zaW5nCjI5IEp1bmUgQ2hhbmdlIE5vdGUgQXBwcm92ZWQgYXQgQ0IgU2lnbmVkIERlY2sgdG8gRm9sbG93IGluIG9yZGVyIHRvIENhbmNlbCBhbGwgUE8ncywgQnVkZ2V0IHRvIGJlIHJlYWxsb2NhdGVk","RATING":""} |  |  | C000066427 | PHASE11 | 2023-04-03 | 2023-05-03 |  |  | 23000275 |  |  |  |  | 2023-02-07 | 121374.24 | 0 |  |  | C000066427 | 121374.24 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000823 | Kimberley RHO- Dilaps | Kimberley RHO- Dilaps |  |  | Region 3 |  |  |  | Building not in our database |  | 2022-11-01 |  |  | ALP-CR001 |  |  | false | false |  |  |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-07-06 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000824 | Frankfort Minor Works | Frankfort Minor Works |  |  | Region 3 |  | 78306X | 1000-71536-01 | Frankfort-Brand St-Frankfort |  | 2022-02-03 | 2022-12-30 |  | ALP-CR0013 | CLSD AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | GAMIETR | 2022-02-09 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-02-03 | 2022-12-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000825 | Nampo Park Minor upgrade | Nampo Park Minor upgrade |  |  | Region 3 |  | 79033X | 1000-71568-01 | Nampo Park-R30-Bothaville |  | 2022-02-03 | 2022-03-31 |  | ALP-CR0014 | CRTD: |  | false | false |  | Nande Maqubela |  |  | 2022 |  |  |  | GAMIETR | 2022-02-09 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | SIYANDA DLAMINI |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000826 | Burger Street Rustenburg - Minor Works | Burger Street Rustenburg - Minor Works |  |  | Region 3 |  | 77057X | 1000-71282-01 | Absa Burger Street-Cnr Nelson Mandela & Beyers Naude St-Rustenburg |  | 2022-06-01 | 2022-08-31 |  | ALP-CR0016 | CLSD AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2022 |  |  |  | CEASARS | 2022-04-22 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-06-01 | 2022-08-31 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000827 | Project Cancelled Refer ALP-CR0013 | Project Cancelled Refer ALP-CR0013 |  |  | Region 3 |  | 78306X | 1000-71536-01 | Frankfort-Brand St-Frankfort |  | 2022-06-13 | 2022-09-30 |  | ALP-CR0017 | CRTD AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | CEASARS | 2022-04-25 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE | 2022-06-13 | 2022-09-30 | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000828 | Absa Wolmaransstad - Minor Works | Absa Wolmaransstad - Minor Works |  |  | Region 3 |  | 77605X | 1000-71295-01 | Wolmaransstad-Kruger St-Wolmaransstad |  | 2022-11-30 | 2022-11-30 |  | ALP-CR0020 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-02 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000829 | Absa Jan Kempdorp - ATM Extension | Absa Jan Kempdorp - ATM Extension |  |  | Region 3 | Northern Cape | 78326X | 1000-71347-01 | Jan Kempdorp-De La Rey St-Jan Kempdorp |  | 2022-11-30 | 2022-11-30 |  | ALP-CR0022 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-02 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 1158119.12 |  | {"MANDT":"111","REFERENCE":70000829,"ONEVIEW":"78326X","DATE01":"2022-09-21","DATE02":"2022-10-19","DATE03":"2022-10-26","DATE04":"2022-10-26","DATE05":"2022-11-30","DATE06":"2022-11-30","DATE07":"2022-12-21","DATE08":"2023-08-01","DATE09":"2023-08-25","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"160:28:7:0:35:0:21:223:24:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-30","FORECAST_END":"2022-12-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000096861 | PHASE10 | 2022-11-30 | 2022-12-21 | NANDE MAQUBELA | Juanita Van Coller | 23000464 |  |  |  |  | 2023-07-10 | 1007060.1 | 0 |  |  | C000096861 | 1007060.1 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000830 | Moffett Office Park External Signage Ref | Moffett Office Park External Signage Ref |  |  | Region 2 |  |  |  | Building not in our database |  | 2022-10-20 |  |  | ALP-EC0010 | CRTD DLFL: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | GAMIETR | 2022-10-21 | D | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000831 | Absa Lusikisiki - Minor Works | Absa Lusikisiki - Minor Works |  |  | Region 2 | Eastern Cape | 70631X | 1000-71001-01 | Rhino Centre Lusikisiki-Main Rd-Lusikisiki |  | 2022-03-07 | 2022-03-31 |  | ALP-EC0192 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2022 |  |  |  | CEASARS | 2022-01-19 | D | 676000 |  |  |  |  | 0 | [5 empty] | CLOSED | 2022-03-07 | 2022-03-31 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000832 | PTA Campus- Block E Canteen upgrade | PTA Campus- Block E Canteen upgrade |  |  | Region 1 |  |  |  | Building not in our database |  | 2022-06-30 |  |  | ALP-GN0008 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | LOUISR | 2022-06-14 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000833 | Centurion Decoupling Dilaps | Centurion Decoupling Dilaps |  |  | Region 1 |  | 77509X | 1000-70372-01 | United Bank Centurion-Cnr Hendrik Verwoerd Dr & Heuwel Ave-Centurion |  | 2022-11-01 | 2022-11-30 |  | ALP-GN0012 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  |  |  | GAMIETR | 2022-11-04 | D | 199710.43 | Approved | 100 | 2023-10-07 | 2023-10-07 | 2296670.04 |  | {"MANDT":"111","REFERENCE":70000833,"ONEVIEW":"77509X","DATE01":"2022-08-23","DATE02":"2022-08-30","DATE03":"2022-09-20","DATE04":"2022-09-27","DATE05":"2022-10-18","DATE06":"2022-11-01","DATE07":"2022-11-30","DATE08":"2022-12-21","DATE09":"2022-12-16","DATE10":"2022-12-31","DATE11":"2022-12-16","DATE12":"2022-12-16","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-11-01","FORECAST_END":"2022-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000070158 | PHASE08 | 2022-11-01 | 2022-11-30 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-02-24 | 1997104.38 | 0 |  |  | C000070158 | 1997104.38 |  | 181905.08 |  | 0 | 0 |  | 0 |  | 0
70000834 | Absa Towers North Waterproofing Professi | Absa Towers North Waterproofing Professi |  |  | Region 1 | Gauteng South |  |  | Building not in our database |  | 2022-01-19 |  |  | ALP-GS0027 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | GAMIETR | 2022-01-20 | D | 5775000 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000835 | Quadrum Office Park Phase 2 | Quadrum Office Park Phase 2 |  |  | Region 1 | Gauteng South | 21332X | 1000-70025-01 | Quadrum Office Park-Constantia Blvd-Roodepoort |  | 2022-06-17 | 2022-12-15 |  | ALP-GS0037 | CRTD AVAC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | LOUISR | 2022-06-13 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | PRESHANE MUNTHREE |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000836 | Aucklandpark- Safety net installation | Aucklandpark- Safety net installation |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2022-09-05 | 2022-12-15 |  | ALP-GS0041 | CRTD AVAC: |  | false | false |  | Lucia Amunga |  |  | 2022 |  |  |  | LOUISR | 2022-08-23 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000837 | Absa Towers North Replacement of 21 Cond | Absa Towers North Replacement of 21 Cond |  |  | Region 1 |  | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2022-09-26 | 2023-03-31 |  | ALP-GS0047 | REL BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2022 |  |  |  | GAMIETR | 2022-10-31 | D | 0 | Approved at CB/BTB | 100 | 2022-12-01 | 2022-12-01 | 1213651.58 | Approved | {"MANDT":"111","REFERENCE":70000837,"ONEVIEW":"77381X","DATE01":"2022-07-18","DATE02":"2022-07-25","DATE03":"2022-08-15","DATE04":"2022-08-22","DATE05":"2022-09-12","DATE06":"2022-09-26","DATE07":"2023-03-31","DATE08":"2023-04-21","DATE09":"2022-11-10","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-09-26","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000073593 | PHASE08 | 2022-09-26 | 2023-03-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-03-13 | 1055349.57 | 0 |  |  | C000073593 | 1055349.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000838 | Alice Lane South - First Floor Room Soun | Alice Lane South - First Floor Room Soun |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2022-11-07 | 2022-12-30 |  | ALP-GS0048 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | GAMIETR | 2022-11-08 | D | 59072.73 |  |  |  |  | 0 |  |  |  |  | C000074605# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-03-17 | 590727.36 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000839 | Alice Lane N&S PODS | Alice Lane N&S PODS |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2022-11-15 | 2022-12-31 |  | ALP-GS0049 | REL BUDG AVAC SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  |  |  | GAMIETR | 2022-11-17 | D | 80821.68 |  |  |  |  | 0 |  |  |  |  | C000074408# | IGNORE |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-03-16 | 748676.78 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000840 | Ridgeside ABSA Regional Office - Interna | Ridgeside ABSA Regional Office - Interna |  |  | Region 3 |  |  |  | Building not in our database |  | 2021-03-20 |  |  | ALP-KZ0006 | CRTD: |  | false | false |  |  |  |  | 2021 |  |  |  | GAMIETR | 2022-01-25 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000841 | Absa Hazyview- Branch Reinstatement | Absa Hazyview- Branch Reinstatement |  |  | Region 3 |  | 77446X | 1000-70628-01 | Blue Haze Shopping Centre-Main Rd-Hazyview |  | 2022-10-20 |  |  | ALP-MP0200 | REL AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-09-19 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000842 | Absa Square Mbombela - Consolidation Pro | Absa Square Mbombela - Consolidation Pro |  |  | Region 3 |  | 77878X | 1000-70683-01 | Absa, Square-Paul Kruger St-Nelspruit |  | 2022-12-30 |  |  | ALP-MP0203 | REL AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2022 |  |  |  | NOMNGANGAL | 2022-11-29 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000843 | DASH Environmental and monitoring servic | DASH Environmental and monitoring servic |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2022-03-10 | 2022-12-15 |  | ALP-N00028 | REL BUDG AVAC RESA SETC: |  | false | false |  | Joseph Bwowe |  |  | 2022 |  |  |  | LOUISR | 2022-03-01 | D | 151400 |  |  |  |  | 0 |  |  |  |  | 2906216 | IGNORE |  |  | JOSEPH BWOWE | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000844 | Retail Solar PV Program (Beaufort West, Meyerton, Kirkwood, Dutywa & Vredenburg) | Retail Solar PV - Beaufort West, Meyerton, Kirkwood, Dutywa & Vredenburg |  |  | Energy | National | Various | 1000-70027-01 | Various Sites |  | 2022-11-18 | 2022-12-15 |  | ALP-N00034 | REL BUDG AVAC RESA SETC: |  | false | true |  | Wesigye Mukuru |  | Sites include: Beaufort West, Meyerton, Kirkwood, Dutywa & Vredenburg | 2022 |  |  |  | LOUISR | 2022-10-28 | D | 11494976.96 | Projects approved in order for Absa to increase its renewable energy production in relation to its overall energy consumption and utilize the renewable energy sustainability linked loan requirements while reducing municipality reliance for the branches | 100 | 2022-09-29 | 2022-10-13 | 11494976.96 |  | {"MANDT":"111","REFERENCE":70000844,"ONEVIEW":"Various","DATE01":"2022-09-09","DATE02":"2022-09-16","DATE03":"2022-10-07","DATE04":"2022-10-14","DATE05":"2022-11-04","DATE06":"2023-05-19","DATE07":"2023-07-31","DATE08":"2023-08-31","DATE09":"2023-10-31","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"144:7:21:7:21:196:73:31:61:29","PROGRESS":87,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TVc6IDE5LzA5LzIwMjM6IE1leWVydG9uIGNvbXBsZXRlZC4gQmVhdWZvcnQgV2VzdCBpbiBleGVjdXRpb24uIFZyZWRlbmJ1cmcgT0hTIGN1cnJlbnRseSB1bmRlciByZXZpZXcuClNjb3BlIGNoYW5nZS4gRHV0eXdhIHJlcGxhY2VkIHdpdGggTWFsbCBvZiB0aGUgU291dGggZHVlIHRvIHBvcnRmb2xpbyBtb3ZlbWVudC4gTWFsbCBvZiB0aGUgU291dGggT0hTIHN1Ym1pc3Npb24gb24gMTMvOQo=","RATING":""} |  |  | C000063973 | PHASE08 | 2023-05-19 | 2023-07-31 | LUCIA AMUNGA | Thea Spamers | 0 | 2022-11-09 | 2022-12-23 | 2022-11-08 | 2022-11-09 | 2023-01-24 | 9995632.14 | 9252475.93 |  |  | c000140420 | 743156.24 |  | 704511.68 |  | 0 | 0 |  | 0 |  | 0
70000845 | National- VAMM Asset Management | Tagged and Uploading Assets at the following Sites: CRES Offices National Branches Storerooms Warehouses numismatics |  |  | National | National | Various | 1000-70027-01 | Various Sites | N | 2022-11-10 | 2022-12-15 |  | ALP-N00036 | REL BUDG AVAC RESA SETC: |  | N | true |  | Tshegofatso Segooa (Non PM) |  |  | 2022 |  | U |  | LOUISR | 2022-11-04 | D | 194153.46 |  | 100 | 2022-09-22 | 2022-09-22 | 2232764 |  | {"MANDT":"111","REFERENCE":70000845,"ONEVIEW":"Various","DATE01":"2022-09-01","DATE02":"2022-09-29","DATE03":"2022-10-06","DATE04":"2022-10-27","DATE05":"2022-11-10","DATE06":"2023-10-31","DATE07":"2023-11-21","DATE08":"2024-01-05","DATE09":"2024-01-14","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":40,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"180:28:7:21:14:355:21:45:9:0","PROGRESS":49,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-11-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3Mu","RATING":"Medium"} |  |  | C000061979 | PHASE06 | 2023-10-31 | 2023-11-21 | LUCIA AMUNGA | Michael Maluleka | 23000458 | 2022-12-15 | 2023-01-13 |  |  | 2023-01-17 | 1941534.68 | 0 |  |  | C000061979 | 1941534.68 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000846 | Absa Montagu Cogmans Centre - HVAC | Absa Montagu Cogmans Centre - HVAC |  |  | Region 2 | Western Cape |  | 1000-70854-01 | Building not in our database |  | 2022-08-01 |  |  | ALP-WC0009 | REL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-05-24 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000847 | Absa Worcester - Security Cages [AC+Gene | Absa Worcester - Security Cages [AC+Gene |  |  | Region 2 | Western Cape |  | 1000-70870-01 | Building not in our database |  | 2022-08-01 |  |  | ALP-WC0010 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-07-05 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000848 | Absa Robertson - Hvac upgrade | Absa Robertson - Hvac upgrade |  |  | Region 2 | Western Cape |  | 1000-70863-01 | Building not in our database |  | 2022-09-19 |  |  | ALP-WC0011 | PREL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2022 |  |  |  | CEASARS | 2022-07-18 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000849 | Airport Shopping Centre - Belhar - Minor | Airport Shopping Centre - Belhar - Minor |  |  | Region 2 | Western Cape |  |  | Building not in our database |  | 2022-09-19 |  |  | ALP-WC0012 | CRTD: |  | false | false |  |  |  |  | 2022 |  |  |  | CEASARS | 2022-07-28 | D | 0 |  |  |  |  | 0 | [5 empty] | IGNORE |  |  |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000850 | Piet Retief - Water tank, booster pump + | Piet Retief - Water tank, booster pump + |  |  | Region 3 | Mpumalanga | 77121X | 1000-70610-01 | Absa Piet Retief-Church St-Piet Retief |  | 2022-06-01 | 2022-09-30 |  | ASP-MP0066 | CRTD AVAC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NGIDIN | 2021-04-01 |  | 110000 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":70000850,"ONEVIEW":"77121X","DATE01":"2022-03-23","DATE02":"2022-03-30","DATE03":"2022-04-20","DATE04":"2022-04-27","DATE05":"2022-05-18","DATE06":"2022-06-01","DATE07":"2022-09-30","DATE08":"2023-07-07","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-01","FORECAST_END":"2022-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RHVwbGljYXRpb24gb2YgQVNQLU1QMDE0MyAtIFByb2plY3QgdG8gYmUgY2FuY2VsbGVk","RATING":""} |  |  |  | PHASE09 | 2022-06-01 | 2022-09-30 | SIYANDA DLAMINI | Thea Spamers | 23000564 | [5 empty] | 67153.04 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000851 | Chris Hani Installation of new generator | Chris Hani Installation of new generator |  |  | Region 1 | Gauteng South | 22226X | 1000-71367-01 | Chris Hani Crossing-Bierman Rd-Vosloorus | N | 2021-05-04 | 2021-06-30 |  | ALP-GS0016 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 0 |  |  |  | GAMIETR | 2021-04-30 |  | 11875.71 | Approved | 100 | 2023-10-07 | 2023-10-07 | 136570.68 |  | {"MANDT":"111","REFERENCE":70000851,"ONEVIEW":"Unknown","DATE01":"2021-02-23","DATE02":"2021-03-02","DATE03":"2021-03-23","DATE04":"2021-03-30","DATE05":"2021-04-20","DATE06":"2021-05-04","DATE07":"2021-06-30","DATE08":"2021-07-21","DATE09":"2021-06-18","DATE10":"2021-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-05-04","FORECAST_END":"2021-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | 2844729 | PHASE11 | 2021-07-13 | 2022-04-28 | Buhle Qwabe | PRESHANE MUNTHREE | 23000491 | [5 empty] | 136570.68 | 0 |  |  | 2844729 | 118757.11 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000852 | Absa 15 Alice Lane Professional Fees for | Absa 15 Alice Lane Professional Fees for |  |  | Region 1 | Gauteng South | 70656X | 1000-71371-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2021-05-07 | 2021-11-30 |  | ALP-GS0019 | REL BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 0 |  |  |  | GAMIETR | 2021-06-04 |  | 106445.43 | Approved | 100 | 2023-10-07 | 2023-10-07 | 1468576.17 |  | {"MANDT":"111","REFERENCE":70000852,"ONEVIEW":"70656X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | 2851483 | PHASE09 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Michael Maluleka | 23000500 | [5 empty] | 1224122.55 | 212568.37 |  |  | 2851483 | 1064454.39 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000853 | Corporate Solar PV Program (Auckland Park, Ridgeside, Bridge Park East, and 270 RR) | National - Solar PV program for the following sites: 1. 270 Republic Rd 2. Bridge Park 3. Ridgeside 4. Auckland Park. | bnVsbCA%253D |  | Energy | National | Various | 1000-70027-01 | Various Sites | U | 2021-08-31 | 2021-12-15 |  | ALP-N00015 | REL BUDG AVAC RESA SETC: | LOUISR | N | true | null | Sanelisiwe Celu | na |  | 0 |  | U |  | LOUISR | 2021-06-14 |  | 44328458.63 | Absa Environmental Action Plan (EAP) targets - renewable energy growth targets | 100 | 2023-01-26 | 2022-10-27 | 5557991.06 | VO WA dates has been used for ABSA legal. Old PO details has been used once clarity with new PO details has been resolved I will update full PO value. | {"MANDT":"111","REFERENCE":70000853,"ONEVIEW":"Various","DATE01":"2021-06-22","DATE02":"2021-06-29","DATE03":"2021-07-20","DATE04":"2021-07-27","DATE05":"2021-08-17","DATE06":"2023-01-28","DATE07":"2023-10-31","DATE08":"2023-11-15","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"829:7:21:7:21:529:276:15:106:29","PROGRESS":75,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-28","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBwcm9ncmVzcy4gMTAvMDcvMjAyMy0gUHJvamVjdHMgc3RpbGwgaW4gcHJvZ3Jlc3MgcGFydGlhbCBpbnZvaWNlcyBzdWJtaXR0ZWQgdG8gZmluYW5jZQpCUEUgJiAyNzBSUiBzY2hlZHVsZWQgZm9yIFBDIE9jdCAnMjMuIFN5c3RlbSB0byBiZSBtb25pdG9yZWQgZm9yIDMgbW9udGhzIHRoZXJlYWZ0ZXIsIHJldGVudGlvbiBhbW91bnQgdG8gYmUgcGFpZCB0byBzdXBwbGllcnMuIApUaGlzIHdpbGwgYmUgYSBmaW5hbmNpYWwgcm9sbCBvdmVyLiA=","RATING":""} |  |  | C000081590 | PHASE07 | 2023-01-28 | 2023-10-31 | LUCIA AMUNGA | Thea Spamers | 0 | 2023-03-29 | 2023-04-17 |  |  | 2023-04-25 | 4833035.7 | 34702704.68 |  |  | C000142158 | 826116.61 | CIP2023XP | 58656.92 |  | 0 | 0 |  | 0 |  | 0
70000854 | Auckland Park Call Centre Lift Replaceme | Auckland Park Call Centre Lift Replaceme |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2021-07-31 | 2022-11-30 |  | ALP-GS0022 | REL CNF BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 0 |  |  |  | GAMIETR | 2021-08-05 |  | 95580.33 | Approved | 100 | 2023-10-07 | 2023-10-07 | 290641.35 |  | {"MANDT":"111","REFERENCE":70000854,"ONEVIEW":"76849X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000059706 | PHASE08 | 2022-01-01 | 2023-01-19 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000563 |  |  |  |  | 2023-01-06 | 290641.35 | 775127 |  |  | 2880074 | 180676.52 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000855 | Alice Lane North Critical UPS to Statics | Alice Lane North Critical UPS to Statics |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2021-09-29 | 2021-11-30 |  | ALP-GS0024 | REL BUDG AVAC RESA SETC: |  | R | false |  | Roshen Aniruth |  |  | 0 |  |  |  | GAMIETR | 2021-09-28 |  | 957685.72 | Approved | 100 | 2023-10-07 | 2023-10-07 | 2868303.62 |  | {"MANDT":"111","REFERENCE":70000855,"ONEVIEW":"70656X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"2022-01-01","DATE07":"2023-01-19","DATE08":"2023-02-09","DATE09":"2023-03-26","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-01-01","FORECAST_END":"2023-01-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000059724 | PHASE08 | 2022-01-01 | 2023-01-19 | PRESHANE MUNTHREE | Michael Maluleka | 23000449 |  |  |  |  | 2023-01-06 | 2868303.62 | 0 |  |  | 2880543 | 9576857.2 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
70000857 | 268 Republic Road Install Gate Motors | 1) Supply and Install Hansa Elite - Industrial Sub-terrain swing motors. 2)-Supply and install Battery back up with Loop indicator facility and duty cycle 3) Supply and install anti-theft braces and Anti theft swing mounts covers 4) Reinforce wall for the gates. 5), Supply and install free standing control box. 6) remove paving and make good all areas. Note: 1. Work will take place during normal working hours on weekends |  |  | Region 1 |  | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg | N | 2022-07-29 |  |  | ASP-GS0636 | CRTD: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | GAMIETR | 2023-04-06 | D | 0 |  | 1 | 2023-04-10 |  | 0 |  | {"MANDT":"111","REFERENCE":70000857,"ONEVIEW":"21334X","DATE01":"2022-05-20","DATE02":"2022-05-27","DATE03":"2022-06-17","DATE04":"2022-06-24","DATE05":"2022-07-15","DATE06":"2022-07-29","DATE07":"2022-08-28","DATE08":"2023-07-31","DATE09":"2023-09-14","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":50,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"194:7:21:7:21:14:30:337:45:28","PROGRESS":75,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-29","FORECAST_END":"2022-08-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBTY29wZWQgYW5kIEJDIHN1Ym1pdHRlZCwgaG93ZXZlciBwcm9qZWN0IHdhcyBjYW5jZWxsZWQgYnkgVlA=","RATING":""} |  |  |  | PHASE08 | 2022-07-29 | 2022-08-28 |  |  | 23000278 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000858 | Freehold- Document complia | Freehold- Document compliance phase 1 |  |  | National | National | 21526X | 1000-70027-01 | Various Sites | U | 2021-06-18 | 2021-12-08 |  | ALP-N00009 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa |  |  | 2021 |  | U |  | LOUISR | 2021-05-13 | D | 11268730 |  | 100 | 2021-04-22 | 2021-05-06 | 11268730 | Approved. Do not close PO until compliance programme is done. | {"MANDT":"111","REFERENCE":70000858,"ONEVIEW":"21526X","DATE01":"2021-04-09","DATE02":"2021-04-16","DATE03":"2021-05-07","DATE04":"2021-05-14","DATE05":"2021-06-04","DATE06":"2021-05-17","DATE07":"2021-09-03","DATE08":"2021-09-24","DATE09":"2023-11-30","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"235:7:21:7:21:-18:109:21:797:22","PROGRESS":71,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-05-17","FORECAST_END":"2021-09-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIENvbXBsaWFuY2UgcHJvamVjdCBpcyBjb21wbGV0ZWQgTEwtIDE4LzA3LzIwMjMtIFByb2plY3Qgc2F2aW5ncyBhcmUgYmVpbmcgdXNlZCBvbiBvdGhlciBDb21wbGlhbmNlIHJlcXVlc3RzLiBMTC0gMDQvMDkvMjAyMy0gUHJvamVjdCBzdGlsbCBpbiBwcm9ncmVzcyBwYXJ0aWFsIGludm9pY2VzIGFyZSBiZWluZyBzdWJtaXR0ZWQu","RATING":"Medium"} |  |  | C000091624 | PHASE10 | 2021-05-17 | 2021-09-03 | LUCIA AMUNGA | Michael Maluleka | 0 | 2021-06-09 | 2021-06-24 |  |  | 2023-06-13 | 94082.84 | 0 |  |  | C000091624 | 9793093.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000859 | National- Corporate docume | National- Corporate document compliance |  |  | National | National |  |  | Various sites | U | 2021-07-23 | 2021-12-15 |  | ALP-N00013 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa | rollover |  | 2021 |  | U |  | LOUISR | 2021-06-14 | D | 2768402 |  | 100 | 2021-04-15 | 2021-04-21 | 2768402 |  | {"MANDT":"111","REFERENCE":70000859,"ONEVIEW":"","DATE01":"2021-05-14","DATE02":"2021-05-21","DATE03":"2021-06-11","DATE04":"2021-06-18","DATE05":"2021-07-09","DATE06":"2021-07-23","DATE07":"2021-12-15","DATE08":"2022-01-05","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"290:7:21:7:21:14:145:21:709:9","PROGRESS":79,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-07-23","FORECAST_END":"2021-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIENvbXBsaWFuY2UgcHJvamVjdCBpcyBjb21wbGV0ZWQu","RATING":""} |  |  | 2853835 | PHASE07 | 2021-07-23 | 2021-12-15 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | 2021-06-17 | 2021-06-24 |  |  | 2021-06-25 | 2407306.91 | 0 |  |  | 2853835 | 2407306.91 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000860 | National - Retail Compliance 73 Sites | National- Retail document compliance 73 |  |  | National | National |  |  | Various Sites | U | 2021-07-30 | 2021-12-15 |  | ALP-N00014 | REL BUDG AVAC RESA SETC: |  | false | true |  | Sibulele Gwangqa | rollover |  | 2021 |  | U |  | LOUISR | 2021-06-14 | D | 1381614.34 |  | 60 | 2021-05-06 | 2021-06-24 | 1381614 | AS: 08.08.23 Note PO 2853744 is superseded by C00009613 | {"MANDT":"111","REFERENCE":70000860,"ONEVIEW":"","DATE01":"2021-05-21","DATE02":"2021-05-28","DATE03":"2021-06-18","DATE04":"2021-06-25","DATE05":"2021-07-16","DATE06":"2021-07-30","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"283:7:21:7:21:14:700:21:45:9","PROGRESS":79,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-07-30","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIENvbXBsaWFuY2UgcHJvamVjdCBpcyBjb21wbGV0ZWQuCkxMLSAxOC8wNy8yMDIzLSBQcm9qZWN0IHNhdmluZ3MgYXJlIGJlaW5nIHVzZWQgb24gb3RoZXIgQ29tcGxpYW5jZSByZXF1ZXN0cy4=","RATING":"Low"} |  |  | 2853744 | PHASE07 | 2021-07-30 | 2023-06-30 | CHRISTOPHER MPOFU | Michael Maluleka | 23000524 | [5 empty] | 1201403.77 | 0 |  |  | 2853744 | 1201403.77 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000861 | National- Reistallation of | National- Reistallation of the BOCC syst |  |  | National | National |  |  | Various sites | U | 2021-08-31 | 2021-12-15 |  | ALP-N00019 | REL BUDG AVAC RESA SETC: |  | false | true |  | Lorri-Anne Louis |  |  | 2021 |  | U |  | LOUISR | 2021-08-11 | D | 2243482 |  | 100 | 2021-02-04 | 2021-02-19 | 2243482 |  | {"MANDT":"111","REFERENCE":70000861,"ONEVIEW":"","DATE01":"2021-06-22","DATE02":"2021-06-29","DATE03":"2021-07-20","DATE04":"2021-07-27","DATE05":"2021-08-17","DATE06":"2021-08-31","DATE07":"2021-12-15","DATE08":"2022-01-05","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"251:7:21:7:21:14:106:21:709:9","PROGRESS":79,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-08-31","FORECAST_END":"2021-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCB1bmRlciBpbnZlc3RpZ2F0aW9uIGN1cnJlbnRseSBpbiBXZXJuZXIgVGVpY2hsZXIncyBoYW5kcy4KMjQvMDUvMjAyMy0gTEwtIFJlZmVyIHRvIGVtYWlsIHNlbnQgYnkgV2VybmVyIDI0LzA1LzIwMjMu","RATING":""} |  |  | 2861009 | PHASE09 | 2021-08-31 | 2021-12-15 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | 2021-06-15 | 2021-08-02 |  |  |  | 1950836.52 | 0 |  |  | 2861009 | 1950836.52 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000862 | National- Document compliance | National- Document compliance phase 2-56 Sites |  |  | National | National | 21526X | 1000-70027-01 | Various Sites | U | 2021-09-17 | 2021-12-15 |  | ALP-N00021 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa | rollover |  | 2021 |  | U |  | LOUISR | 2021-08-23 | D | 4437397.59 |  | 100 | 2021-08-05 | 2021-08-17 | 4437398 | Dates have been amended according to1st dates instead of roll over dates. | {"MANDT":"111","REFERENCE":70000862,"ONEVIEW":"21526X","DATE01":"2021-07-09","DATE02":"2021-07-16","DATE03":"2021-08-06","DATE04":"2021-08-13","DATE05":"2021-09-03","DATE06":"2021-11-09","DATE07":"2022-02-28","DATE08":"2022-03-21","DATE09":"2024-06-28","DATE10":"2024-06-30","DATE11":"2024-06-28","DATE12":"2024-06-28","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":40,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"905:7:21:7:21:67:111:21:830:16","PROGRESS":47,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-11-09","FORECAST_END":"2022-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE8gbm90IHRvIGJlIGNsb3NlZCB1bnRpbCBDb21wbGlhbmNlIHByb2plY3QgaXMgY29tcGxldGVkIExMLSAxOC8wNy8yMDIzLSBQcm9qZWN0IHNhdmluZ3MgYXJlIGJlaW5nIHVzZWQgb24gb3RoZXIgQ29tcGxpYW5jZSByZXF1ZXN0cy4gTEwtIDA0LzA5LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3MgcGFydGlhbCBpbnZvaWNlcyBhcmUgYmVpbmcgc3VibWl0dGVkLgoxNi8xMS8yMDIzIExMLSBQcm9qZWN0IHN0aWxsIGluIHByb2dyZXNzIHBhcnRpYWwgaW52b2ljZXMgc3VibWl0dGVkIFByb2plY3Qgbm90IHRvIGJlIGNsb3NlZCB3aWxsIGJlIGEgcm9sbCBvdmVyLgoyNy8xMS8yMDIzIC0gUHJvamVjdCBzdGlsbCBpbiBwcm9ncmVzcyBwYXJ0aWFsIGludm9pY2VzIHN1Ym1pdHRlZCBQcm9qZWN0IG5vdCB0byBiZSBjbG9zZWQgd2lsbCBiZSBhIHJvbGwgb3Zlci4=","RATING":"Low"} |  |  | 2875712 | PHASE06 | 2021-11-09 | 2022-02-28 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | 2021-10-06 | 2021-10-08 |  |  | 2021-10-11 | 3858606.6 | 0 |  |  | 2875712 | 3858606.6 |  | 142858.2 |  | 0 | 0 | C000012357 | 1928333.6 | C000147693 | 690218.99 |  |  | 2022-05-27 | 2024-03-07
70000863 | National- Document complia | National- Document compliance phase 2b-7 |  |  | National | National | 21526X | 1000-70027-01 | Various Sites | U | 2021-10-29 | 2021-12-15 |  | ALP-N00022 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa |  |  | 2021 |  | U |  | LOUISR | 2021-10-08 | D | 3833078 |  | 100 | 2021-09-23 | 2021-09-30 | 3833078 |  | {"MANDT":"111","REFERENCE":70000863,"ONEVIEW":"21526X","DATE01":"2021-08-20","DATE02":"2021-08-27","DATE03":"2021-09-17","DATE04":"2021-09-24","DATE05":"2021-10-15","DATE06":"2021-10-29","DATE07":"2021-12-15","DATE08":"2022-01-05","DATE09":"2022-02-19","DATE10":"2023-12-15","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-10-29","FORECAST_END":"2021-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHVudGlsIENvbXBsaWFuY2UgcHJvamVjdCBpcyBjb21wbGV0ZWQuCg==","RATING":""} |  |  | C000012358 | PHASE10 | 2021-10-29 | 2021-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 | 2021-10-15 | 2021-10-18 |  |  | 2022-05-31 | 3333111.3 | 0 |  |  | 2877473 | 3333111.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000864 | Hillcrest Office Park- Compliance Fire A | Hillcrest Office Park- Compliance Fire A |  |  | National | National | 78531X | 1000-70416-01 | Hillcrest Office Park-Lunnon Rd-Pretoria | U | 2021-11-19 | 2021-12-15 |  | ASP-GN0112 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa | rollover |  | 2021 |  | U |  | LOUISR | 2021-10-29 | D | 69342.76 |  | 60 | 2021-10-29 | 2021-10-29 | 69342.76 | WA not applicable | {"MANDT":"111","REFERENCE":70000864,"ONEVIEW":"78531X","DATE01":"2021-09-10","DATE02":"2021-09-17","DATE03":"2021-10-08","DATE04":"2021-10-15","DATE05":"2021-11-05","DATE06":"2021-11-19","DATE07":"2021-12-15","DATE08":"2022-01-05","DATE09":"2022-02-19","DATE10":"2022-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":0,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":72,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-11-19","FORECAST_END":"2021-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBub3QgdG8gYmUgY2xvc2VkIHNhdmluZ3MgdG8gYmUgbW92ZWQgaW50byBDb21wbGlhbmNlIHByb2plY3QuIExMLSAxOC8wNy8yMDIzLSBQcm9qZWN0IHNhdmluZ3MgYXJlIGJlaW5nIHVzZWQgb24gb3RoZXIgQ29tcGxpYW5jZSByZXF1ZXN0cy4=","RATING":"Low"} |  |  | 2880662 | PHASE11 | 2021-11-19 | 2021-12-15 | JOSEPH BWOWE | Obakeng Phuti | 0 |  |  |  |  | 2021-11-03 | 60298.06 | 0 |  |  | 2880662 | 60298.06 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000865 | Absa Vincent Park - Dedicated plugs | Absa Vincent Park - Connection of Equipment to UPS supply. |  |  | Region 2 | Eastern Cape | 78697X | 1000-71051-01 | Vincent Park-Devereux Ave-East London | N |  | 2023-08-30 |  | ASP-EC0311 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-04-25 | D | 7772.56 | 2023.06.29: Approved by Kobus JvR 2023.06.27: Supported by Rob L | 100 | 2023-06-29 | 2023-06-29 | 7772.56 | Approved | {"MANDT":"111","REFERENCE":70000865,"ONEVIEW":"78697X","DATE01":"2023-06-14","DATE02":"2023-06-16","DATE03":"2023-06-22","DATE04":"2023-06-29","DATE05":"2023-06-29","DATE06":"2023-07-15","DATE07":"2023-07-28","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"139:2:6:7:0:16:13:24:45:29","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-15","FORECAST_END":"2023-07-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgQXVnIFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZQ==","RATING":"Low"} |  |  | C000096884 | PHASE11 | 2023-07-15 | 2023-07-28 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-10 | 6758.75 | 0 |  |  | C000096884 | 6758.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000866 | Maponya Mall Installation of aircon in | Maponya Mall Installation of aircon in the ATM Room |  |  | Region 1 | Gauteng South | 79059X | 1000-70442-01 | Maponya Mall-Old Potchefstroom Rd-Soweto | N | 2022-10-14 |  |  | ASP-GS0644 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2022 |  | L | 2022-09-29 | GAMIETR | 2023-04-28 | D | 46354.49 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-02 | 2023-05-03 | 46354.49 | Approved | {"MANDT":"111","REFERENCE":70000866,"ONEVIEW":"79059X","DATE01":"2022-08-05","DATE02":"2022-08-12","DATE03":"2022-09-02","DATE04":"2022-09-09","DATE05":"2022-09-30","DATE06":"2022-10-14","DATE07":"2023-06-02","DATE08":"2023-07-07","DATE09":"2023-08-21","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"391:7:21:7:21:14:231:35:45:24","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-14","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083198 | PHASE11 | 2022-10-14 | 2023-06-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-05 | 40308.25 | 0 |  |  | C000083198 | 40308.25 |  | 2300 |  | 0 | 0 |  | 0 |  | 0
70000867 | Auckland Park Call Centre Temperature d | Provide Assessment Report with the following; Ã¢ÂÂ¢ Details of the methods used to investigate the temperature differences. between the ground floor and ceiling throughout the office. Ã¢ÂÂ¢ Document all findings of investigation and to provide a permanent solution. Ã¢ÂÂ¢ Conclusions drawn from investigation. Ã¢ÂÂ¢ Recommendations Ã¢ÂÂ Provide BOQ/BOM for RFQ. |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2022-10-26 |  |  | ASP-GS0651 | CRTD: |  | false | false |  | Tsholofelo Sello |  |  | 2022 |  | F |  | GAMIETR | 2023-05-04 | D | 0 |  | 100 |  |  | 81939.39 |  | {"MANDT":"111","REFERENCE":70000867,"ONEVIEW":"76849X","DATE01":"2022-08-17","DATE02":"2022-08-24","DATE03":"2022-09-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-10-26","DATE07":"2022-11-25","DATE08":"2022-12-16","DATE09":"2023-01-30","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-26","FORECAST_END":"2022-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Medium"} |  |  | C000021189 | PHASE10 | 2022-10-26 | 2022-11-25 |  |  | 0 |  |  |  |  | 2022-06-29 | 71251.64 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000868 | Absa Highlands Meadowdale | Absa Highlands Meadowdale - Provide steel gates for vehicle holding bay |  |  | Region 1 |  | 22896X | 1000-70079-01 | 230 Lilian Ngoyi Street-Lilian Ngoyi St-Pretoria |  |  | 2023-06-06 |  | ASP-GN0202 | CRTD SETC: |  | false | false |  | Mponeng Mokoena |  |  | 0 |  |  |  | MOKOENAM2 | 2023-06-06 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 3473.46 |  | {"MANDT":"111","REFERENCE":70000868,"ONEVIEW":"22896X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"0000-00-00","DATE07":"2023-06-06","DATE08":"2023-06-27","DATE09":"2023-08-11","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"0000-00-00","FORECAST_END":"0000-00-00","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000091053 | PHASE08 |  | 2023-06-06 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-12 | 3020.4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000869 | Absa Lakeside New Tube System | Supply and install new tube system including 2 x 160mm diameter flag Supply 2 X Undercounter Safes Security guards required for the duration of the works. Work will be carried out after normal working hours. Material Leadtime: +-3 working days. Onsite timeline: 10 working days |  |  | Region 1 | Gauteng South | 36202X | 1000-71373-01 | Lakeside Mall-Tom Jones St-Benoni | N |  | 2023-06-25 |  | ASP-GS0699 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | L |  | GAMIETR | 2023-06-25 | D | 318345.25 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Winston P & Ilana vdW | 100 | 2023-06-26 | 2023-07-27 | 318345.25 | Approved | {"MANDT":"111","REFERENCE":70000869,"ONEVIEW":"36202X","DATE01":"2023-07-17","DATE02":"2023-07-18","DATE03":"2023-07-20","DATE04":"2023-07-23","DATE05":"2023-07-26","DATE06":"2023-07-27","DATE07":"2023-08-11","DATE08":"2023-10-02","DATE09":"2023-11-16","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:1:2:3:3:1:15:52:45:1","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-27","FORECAST_END":"2023-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYXdhaXRpbmcgQ2xpZW50IHNpZ24tb2ZmLg==","RATING":"Low"} |  |  | C000101332 | PHASE11 | 2023-07-27 | 2023-08-11 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-01 | 276821.95 | 0 |  |  | C000101332 | 276821.95 |  | 5700 |  | 0 | 0 |  | 0 |  | 0
70000870 | Absa Northmead New Tube system | Supply and install new tube system including 2 x 160mm diameter flag Security guards required for the duration of the works. Work will be carried out after normal working hours. Material Leadtime: +-3 working days. Onsite timeline: 10 working days. |  |  | Region 1 | Gauteng South | 36244X | 1000-70196-01 | Northmead Square-14th Ave-Benoni | N |  | 2023-06-25 |  | ASP-GS0700 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | L |  | GAMIETR | 2023-06-25 | D | 328933.17 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Winston P & Ilana vdW | 100 | 2023-06-29 | 2023-07-27 | 328933.17 |  | {"MANDT":"111","REFERENCE":70000870,"ONEVIEW":"36244X","DATE01":"0000-00-00","DATE02":"2023-05-07","DATE03":"2023-05-31","DATE04":"2023-06-01","DATE05":"2023-07-13","DATE06":"2023-07-20","DATE07":"2023-08-06","DATE08":"2023-09-27","DATE09":"2023-10-11","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-20","FORECAST_END":"2023-08-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHRvIGJlIHNpZ25lZCAtb2ZmIGJ5IEFic2EgUGxhbm5lci4=","RATING":"Low"} |  |  | C000101334 | PHASE11 | NaN--Na-N- | NaN--Na-N- | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-01 | 286028.84 | 0 |  |  | C000101334 | 286028.84 |  | 5000 |  | 0 | 0 |  | 0 |  | 0
70000871 | Absa Vaal New Tube system | Supply and install new tube system including 3 x 160mm diameter flag Security guards required for the duration of the works. Work will be carried out after normal working hours. Material Leadtime: +-3 working days. Onsite timeline: 10 working days |  |  | Region 1 |  | 77152X | 1000-70350-01 | Vaal Mall-Cnr Barrage Rd & Rossini Blvd-Vanderbijlpark | N |  | 2023-06-25 |  | ASP-GS0704 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | L |  | GAMIETR | 2023-06-25 | D | 374083.17 |  | 1 | 2023-06-26 |  | 0 |  | {"MANDT":"111","REFERENCE":70000871,"ONEVIEW":"77152X","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"0000-00-00","DATE07":"2023-06-25","DATE08":"2023-07-16","DATE09":"2023-08-30","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":1,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"0000-00-00","FORECAST_END":"2023-06-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 |  | 2023-06-25 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000872 | Absa 15 Alice Lane - Earth Cable 1 | Absa 15 Alice Lane - Earth Cable 1 |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2022-04-07 | 2022-04-07 |  | ALP-GS0085 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2022 |  |  |  | CEASARS | 2023-11-17 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE08 | 2022-04-07 | 2022-04-07 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000141957 | 714056.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000873 | Absa Protea Gardens - INS Fire Extinguis | Absa Protea Gardens - INS Fire Extinguis |  |  | Region 1 |  | 77139X | 1000-71394-01 | Protea Gardens Shopping Centre-Chris Hani Rd-Soweto |  | 2023-05-09 | 2023-05-24 |  | ASP-GS0790 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2024-02-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-05-09 | 2023-05-24 | OTHER | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000145598 | 1380 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000874 | Absa Witbank - INS Basement Lights | Absa Witbank - INS Basement Lights |  |  | Region 3 |  | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank |  | 2023-07-12 | 2023-07-28 |  | ASP-MP0180 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | CEASARS | 2024-02-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-07-12 | 2023-07-28 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000875 | Absa Bizana - Generator Rental Extended | Absa Bizana - Generator Rental Extended |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2023-10-01 | 2024-03-31 |  | ASP-EC0408 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2024-02-14 | D | 0 |  | 1 |  |  | 0 | 22 Feb Extended rental to be processed Via GMP | {"MANDT":"111","REFERENCE":70000875,"ONEVIEW":"70633X","DATE01":"2023-07-23","DATE02":"2023-07-30","DATE03":"2023-08-20","DATE04":"2023-08-27","DATE05":"2023-09-17","DATE06":"2023-10-01","DATE07":"2024-03-31","DATE08":"2024-04-21","DATE09":"2024-06-05","DATE10":"2024-06-30","DATE11":"2024-06-05","DATE12":"2024-06-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-01","FORECAST_END":"2024-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgRmViIFBSRiBQZW5kaW5nIGZvciBFeHRlbmRlZCBSZW50YWw=","RATING":""} |  |  |  | PHASE12 | 2023-10-01 | 2024-03-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000876 | Absa Vanderbijlpark - INS Sign | Absa Vanderbijlpark - INS Sign |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2023-01-01 | 2023-12-31 |  | ASP-GS0794 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2024-02-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-01-01 | 2023-12-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000145605 | 17610.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000877 | Absa 13 Top Road - INS 8 Car shade nets | Absa 13 Top Road - INS 8 Car shade nets |  |  | Region 1 |  | 79271X | 1000-71418-01 | 13 Top Road-Top Rd-Boksburg |  | 2023-11-01 | 2023-12-31 |  | ASP-GS0795 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2024-02-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-01 | 2023-12-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000145607 | 54870 |  | 0 |  | 0 | 0 |  | 0 |  | 0
70000878 | Absa 8 Top Road - INS 8 Car shade nets | Absa 8 Top Road - INS 8 Car shade nets |  |  | Region 1 |  | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg |  | 2023-06-01 | 2023-12-31 |  | ASP-GS0796 | CRTD AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2024-02-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-06-01 | 2023-12-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  | 2902842 | 18757.93 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000000 | Absa Wolmaransstad - HVAC Repair | Absa Wolmaransstad - HVAC Repair |  |  | Region 3 | North West | 77605X | 1000-71295-01 | Wolmaransstad-Kruger St-Wolmaransstad |  | 2023-03-01 | 2023-03-01 |  | ASP-CR0372 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L |  | NOMNGANGAL | 2023-01-13 |  | 42380.4 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 42380.4 | Approved | {"MANDT":"111","REFERENCE":90000000,"ONEVIEW":"77605X","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-25","DATE05":"2023-03-01","DATE06":"2023-01-20","DATE07":"2023-02-20","DATE08":"2023-04-06","DATE09":"2023-05-01","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-20","FORECAST_END":"2023-02-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000064826 | PHASE11 | 2023-01-20 | 2023-02-20 | NANDE MAQUBELA | Floyd Mofokeng | 23000390 | [5 empty] | 36852.52 | 0 |  |  | C000064826 | 36852.52 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000001 | Absa Bloemfontein Forum Extractor Fan | Absa Bloemfontein Forum Extractor Fan |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein |  | 2023-01-31 | 2023-01-31 |  | ASP-CR0373 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-17 |  | 0 |  | 1 |  |  | 0 | The project was rejected at Cost Board | {"MANDT":"111","REFERENCE":90000001,"ONEVIEW":"22161X","DATE01":"2022-11-22","DATE02":"2022-12-20","DATE03":"2022-12-27","DATE04":"2022-12-27","DATE05":"2023-01-31","DATE06":"2023-01-31","DATE07":"2023-02-21","DATE08":"2023-04-07","DATE09":"2023-04-30","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-31","FORECAST_END":"2023-02-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-01-31 | 2023-02-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000085 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000002 | Absa Vrede Minor Works | Absa Vrede Minor Works |  |  | Region 3 | Free State | 77122X | 1000-71531-01 | Absa Vrede-Church St-Vrede |  | 2023-02-03 | 2023-02-24 |  | ASP-CR0374 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-23 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000002,"ONEVIEW":"77122X","DATE01":"2022-11-25","DATE02":"2022-12-23","DATE03":"2022-12-30","DATE04":"2022-12-30","DATE05":"2023-02-03","DATE06":"2023-02-24","DATE07":"2023-03-17","DATE08":"2023-05-01","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-24","FORECAST_END":"2023-03-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE10 | 2023-02-24 | 2023-03-17 | NANDE MAQUBELA | Juanita Van Coller | 23000164 | [5 empty] | 0 | 0 |  |  | C000144332 | 168248.5 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000003 | Absa Viljoenskroon Minor Works | Absa Viljoenskroon Minor Works |  |  | Region 3 | Free State | 78481X | 1000-71540-01 | Viljoenskroon-Cnr Engelbrecht & Church St-Viljoenskroon |  | 2023-02-13 | 2023-02-13 |  | ASP-CR0375 | REL AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | F |  | MOKOENAM2 | 2023-01-23 |  | 6355.76 | CB04 | 100 | 2023-02-09 | 2023-02-09 | 0 | [5 empty] | PHASE05 | 2023-02-13 | 2023-03-06 | NANDE MAQUBELA | Juanita Van Coller | 23000035 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000004 | Absa Wesselsbron Minor Works | Absa Wesselsbron Minor Works |  |  | Region 3 | Free State | 78738X | 1000-71552-01 | Absa Wesselsbron-Erwees St-Wesselsbron |  | 2023-02-06 | 2023-02-27 |  | ASP-CR0376 | REL AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-23 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000004,"ONEVIEW":"78738X","DATE01":"2022-11-28","DATE02":"2022-12-26","DATE03":"2023-01-02","DATE04":"2023-01-02","DATE05":"2023-02-06","DATE06":"2023-02-27","DATE07":"2023-11-09","DATE08":"2023-12-24","DATE09":"2024-01-20","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"346:28:7:0:35:21:255:45:27:162","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-11-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBpbXBsZW1lbnRhdGlvbiBkYXRlLiBGaW5hbmNpYWwgcm9sbG92ZXIu","RATING":""} |  |  |  | PHASE02 | 2023-02-27 | 2023-11-09 | NANDE MAQUBELA | Juanita Van Coller | 23000129 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000005 | Absa Bloemfontein RHO Mobile AC Units | Absa Bloemfontein RHO Mobile AC Units |  |  | Region 3 | Free State | 78754X | 1000-71544-01 | Bloemfontein CBD-Charlotte Maxeke St-Bloemfontein |  | 2023-02-22 | 2023-03-15 |  | ASP-CR0377 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-26 |  | 0 |  | 15 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000005,"ONEVIEW":"78754X","DATE01":"2022-12-14","DATE02":"2023-01-11","DATE03":"2023-01-18","DATE04":"2023-01-18","DATE05":"2023-02-22","DATE06":"2023-03-15","DATE07":"2023-04-05","DATE08":"2023-05-20","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-15","FORECAST_END":"2023-04-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE02 | 2023-03-15 | 2023-04-05 | NANDE MAQUBELA | Floyd Mofokeng | 23000402 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000006 | Absa Fleurdal | Absa Fleurdal |  |  | Region 3 | Free State | 79303X | 1000-71580-01 | Fleurdal Mall-Vereeniging Dr-Bloemfontein |  | 2023-02-23 | 2023-03-16 |  | ASP-CR0378 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-27 |  | 0 |  | 0 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000006,"ONEVIEW":"79303X","DATE01":"2022-12-15","DATE02":"2023-01-12","DATE03":"2023-01-19","DATE04":"2023-01-19","DATE05":"2023-02-23","DATE06":"2023-03-16","DATE07":"2023-04-06","DATE08":"2023-05-21","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-16","FORECAST_END":"2023-04-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE02 | 2023-03-16 | 2023-04-06 | NANDE MAQUBELA | Floyd Mofokeng | 23000182 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000007 | Absa Fleurdal Minor Works | Absa Fleurdal Minor Works |  |  | Region 3 | Free State | 79303X | 1000-71517-01 | Fleurdal Mall-Vereeniging Dr-Bloemfontein |  | 2023-02-24 | 2023-03-16 |  | ASP-CR0379 | CRTD RESA: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-30 |  | 0 |  | 0 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000007,"ONEVIEW":"79303X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-16","DATE07":"2023-04-06","DATE08":"2023-05-21","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-16","FORECAST_END":"2023-04-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE02 | 2023-03-16 | 2023-04-06 | NANDE MAQUBELA | Juanita Van Coller | 23000182 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000008 | Absa Phuthaditjhaba Setsin | Absa Phuthaditjhaba - installation of water tank and filtration system |  | h | Region 3 | Free State | 70622X | 1000-71516-01 | Phuthaditjhaba Setsing Crescent-Cnr Setai & Motloung St-Phuthaditjhaba | N | 2023-01-16 | 2023-01-22 |  | ASP-CR0380 | CLSD BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 0 |  | L | 2024-05-30 | MOKOENAM2 | 2023-01-30 |  | 11846.94 | Approved at CB/BTB | 100 | 2022-11-09 | 2023-02-09 | 11846.94 | Approved | {"MANDT":"111","REFERENCE":90000008,"ONEVIEW":"70622X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-17","DATE07":"2023-04-07","DATE08":"2023-05-23","DATE09":"2023-06-01","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"166:28:7:0:35:21:21:46:9:0","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-17","FORECAST_END":"2023-04-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDb21wbGV0ZWQsIEludm9pY2luZyBpbiBwcm9ncmVzcw==","RATING":""} |  |  | C000067587 | PHASE11 | 2023-03-17 | 2023-04-07 | NANDE MAQUBELA | Floyd Mofokeng | 23000558 |  |  |  |  | 2023-02-13 | 10301.69 | 0 |  |  | C000067587 | 10301.69 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000009 | Absa Reitz | Absa Reitz |  |  | Region 3 | Free State | 78402X | 1000-71538-01 | Absa Reitz-Church St-Reitz | U | 2023-02-24 | 2023-03-28 |  | ASP-CR0381 | REL AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  | not on budget list | 0 |  | F |  | MOKOENAM2 | 2023-01-30 |  | 0 |  | 70 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000009,"ONEVIEW":"78402X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-28","DATE07":"2023-04-18","DATE08":"2023-06-02","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-28","FORECAST_END":"2023-04-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE02 | 2023-03-28 | 2023-04-18 |  | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000010 | Absa Loch Logan | Absa Loch Logan |  |  | Region 3 | Free State | 78795X | 1000-71597-01 | Loch Logan Waterfront-Henry St-Bloemfontein |  | 2023-02-24 | 2023-03-17 |  | ASP-CR0382 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-30 |  | 67092.97 | 2023.03.30: Approved by Conrad M | 100 | 2023-03-30 | 2023-03-30 | 67092.97 | Approved | {"MANDT":"111","REFERENCE":90000010,"ONEVIEW":"78795X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-17","DATE07":"2023-04-07","DATE08":"2023-05-22","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"2023-05-31","DATE12":"2023-05-31","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-17","FORECAST_END":"2023-04-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IEludm9pY2VkLg==","RATING":""} |  |  | C000077506 | PHASE06 | 2023-03-17 | 2023-04-07 | NANDE MAQUBELA | Juanita Van Coller | 23000296 |  |  |  |  | 2023-03-31 | 58341.71 | 0 |  |  | C000077506 | 58341.71 | CIP2023XP | 6099.36 |  | 0 | 6099.36 | C000145803 | 24686.71 |  | 0 | 2024-12-02 | 2024-02-20 | 2024-02-29
90000011 | Absa Koppies | Absa Koppies |  |  | Region 3 | Free State | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies |  | 2023-02-24 | 2023-03-06 |  | ASP-CR0383 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-30 |  | 0 |  | 1 |  |  | 0 | Duplication | {"MANDT":"111","REFERENCE":90000011,"ONEVIEW":"78856X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-06","DATE07":"2023-03-27","DATE08":"2023-05-11","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-06","FORECAST_END":"2023-03-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RnVsbHkgaW52b2ljZWQuRHVwbGljYXRpb24u","RATING":""} |  |  |  | PHASE12 | 2023-03-06 | 2023-03-27 | NANDE MAQUBELA | Floyd Mofokeng | 23000261 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000012 | Absa Warden | Absa Warden |  |  | Region 3 | Free State | 79096X | 1000-71571-01 | Absa Warden-Piet Retief St-Warden |  | 2023-02-24 | 2023-03-13 |  | ASP-CR0384 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-30 |  | 0 |  | 1 |  |  | 0 | Duplication | {"MANDT":"111","REFERENCE":90000012,"ONEVIEW":"79096X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-13","DATE07":"2023-04-03","DATE08":"2023-05-18","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-13","FORECAST_END":"2023-04-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RnVsbHkgaW52b2ljZWQuIER1cGxpY2F0aW9u","RATING":""} |  |  |  | PHASE12 | 2023-03-13 | 2023-04-03 | NANDE MAQUBELA | Floyd Mofokeng | 23000387 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000013 | Absa Bultfontein - UPS & Generator insta | Absa Bultfontein - UPS & Generator insta |  |  | Region 3 | Free State | 79115X | 1000-71574-01 | Absa Bultfontein-President Swart St-Bultfontein |  | 2023-03-03 | 2023-03-30 |  | ASP-CR0385 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | F |  | NOMNGANGAL | 2023-01-31 |  | 208287.99 | Approved at CB/BTB | 100 | 2023-02-02 | 2023-02-02 | 208287.99 | Approved | {"MANDT":"111","REFERENCE":90000013,"ONEVIEW":"79115X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-02-27","DATE10":"2023-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"189:28:7:0:35:27:21:45:-97:0","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGZ1bGx5IGludm9pY2Vk","RATING":""} |  |  | C000065092 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-01-31 | 181119.99 | 0 |  |  | C000065092 | 181119.99 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000014 | Absa Senekal | Absa Senekal |  |  | Region 3 | Free State | 78639X | 1000-71548-01 | Senekal-Cnr Voortrekker & Goosen St-Senekal | Y | 2023-02-24 | 2023-03-14 |  | ASP-CR0386 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2024-04-29 | MOKOENAM2 | 2023-01-31 |  | 0 |  | 1 |  |  | 0 | Cancelled | {"MANDT":"111","REFERENCE":90000014,"ONEVIEW":"78639X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-14","DATE07":"2023-04-04","DATE08":"2023-05-19","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-14","FORECAST_END":"2023-04-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE12 | 2023-03-14 | 2023-04-04 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000015 | Absa Heilbron | Absa Heilbron |  |  | Region 3 | Free State | 78854X | 1000-71557-01 | Absa Heilbron-Kerk St-Heilbron | N | 2023-02-24 | 2023-03-14 |  | ASP-CR0387 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | F |  | MOKOENAM2 | 2023-01-31 |  | 0 | No approvals are requested. | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000015,"ONEVIEW":"78854X","DATE01":"2022-12-16","DATE02":"2023-01-13","DATE03":"2023-01-20","DATE04":"2023-01-20","DATE05":"2023-02-24","DATE06":"2023-03-14","DATE07":"2023-04-04","DATE08":"2023-05-19","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-14","FORECAST_END":"2023-04-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE02 | 2023-03-14 | 2023-04-04 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000016 | Absa Bloemfontein RHO | Absa Bloemfontein RHO |  |  | Region 3 | Free State | 78754X | 1000-71476-01 | Bloemfontein CBD-Charlotte Maxeke St-Bloemfontein | N | 2023-03-01 | 2023-03-29 |  | ASP-CR0388 | CLSD BUDG AVAC SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2022-02-27 | MOKOENAM2 | 2023-02-01 |  | 552.68 | Approved at CB/BTB | 100 | 2023-02-09 | 2023-02-09 | 6355.76 | Approved | {"MANDT":"111","REFERENCE":90000016,"ONEVIEW":"78754X","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-25","DATE05":"2023-03-01","DATE06":"2023-03-29","DATE07":"2023-04-19","DATE08":"2023-06-03","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-29","FORECAST_END":"2023-04-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RHVwbGljYXRpb24uIA==","RATING":""} |  |  | C000067781 | PHASE11 | 2023-03-29 | 2023-04-19 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-02-13 | 5526.75 | 0 |  |  | C000067781 | 5526.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000017 | Absa Postmasburg - Cosmetic Upgrade/ ban | Absa Postmasburg - Cosmetic Upgrade/ ban |  |  | Region 3 | Northern Cape | 21312X |  | Postmasburg-Springbok St-Postmasburg |  | 2023-03-03 | 2023-03-30 |  | ASP-CR0389 | REL AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-01 |  | 0 |  | 100 |  |  | 769321.67 |  | {"MANDT":"111","REFERENCE":90000017,"ONEVIEW":"21312X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE10 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 23000204 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000018 | Absa Warrenton - Replace banking hall fl | Absa Warrenton - Replace banking hall fl |  |  | Region 3 | Northern Cape | 21822X |  | Warrenton-Uys St-Warrenton |  | 2023-03-03 | 2023-03-30 |  | ASP-CR0390 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-01 |  | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000018,"ONEVIEW":"21822X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | floyd mofokeng | 23000280 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000019 | Absa Wibsa Upington - Paint Walls CIT Ar | Absa Wibsa Upington - Paint Walls CIT Ar |  |  | Region 3 | Northern Cape | 36271X |  | Wibsa Upington-Schroder St-Upington |  | 2023-03-03 |  |  | ASP-CR0391 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-01 |  | 0 | 2023.06.29: Approved by Conrad M 2023.06.27: Supported by Leko N & Ilana vdW | 100 | 2023-06-29 | 2023-06-29 | 122779.76 | Approved | {"MANDT":"111","REFERENCE":90000019,"ONEVIEW":"36271X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-04-02","DATE07":"2023-04-23","DATE08":"2023-06-07","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-02","FORECAST_END":"2023-04-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000095235 | PHASE10 | 2023-04-02 | 2023-04-23 | NANDE MAQUBELA | Juanita Van Coller | 23000355 |  |  |  |  | 2023-06-30 | 106765.01 | 0 |  |  | C000095235 | 106765.01 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000020 | Absa Kuruman - Replace Vinyl Frosting on | Absa Kuruman - Replace Vinyl Frosting on |  |  | Region 3 | Northern Cape | 78504X |  | Kuruman-Cnr Hoof & Livingstone Rd-Kuruman |  | 2023-03-03 |  |  | ASP-CR0392 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-01 |  | 39868.77 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 39868.77 | Approved | {"MANDT":"111","REFERENCE":90000020,"ONEVIEW":"78504X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-04-02","DATE07":"2023-04-23","DATE08":"2023-06-07","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-02","FORECAST_END":"2023-04-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000073561 | PHASE10 | 2023-04-02 | 2023-04-23 | NANDE MAQUBELA | Juanita Van Coller | 23000408 |  |  |  |  | 2023-03-13 | 34668.5 | 0 |  |  | C000073561 | 34668.5 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000021 | Absa Colesburg- Replace Kitchen&bathroom | Absa Colesburg- Replace Kitchen&bathroom |  |  | Region 3 | Free State | 78406X |  | Colesberg-Church St-Colesberg |  | 2023-03-03 |  |  | ASP-CR0393 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-01 |  | 0 | 2023.06.15: Approved by Conrad M as per email 2023.06.13: Supported by Leko N & Ilana vdW | 100 | 2023-06-15 | 2023-06-15 | 229361.62 | Approved | {"MANDT":"111","REFERENCE":90000021,"ONEVIEW":"78406X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-04-02","DATE07":"2023-04-23","DATE08":"2023-06-07","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-02","FORECAST_END":"2023-04-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEF3YWl0aW5nIEludm9pY2luZy4=","RATING":""} |  |  | C000092904 | PHASE10 | 2023-04-02 | 2023-04-23 | NANDE MAQUBELA | Juanita Van Coller | 23000319 |  |  |  |  | 2023-06-20 | 199444.89 | 0 |  |  | C000092904 | 199444.89 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000022 | Absa Odendaalsrus | Absa Odendaalsrus |  |  | Region 3 | Free State | 79056X | 1000-71599-01 | Absa Odendaalsrus-Odendaal St-Odendaalsrus |  | 2023-03-02 | 2023-04-06 |  | ASP-CR0394 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-02 |  | 0 |  | 100 |  |  | 1854522.72 |  | {"MANDT":"111","REFERENCE":90000022,"ONEVIEW":"79056X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-04-06","DATE07":"2023-04-27","DATE08":"2023-06-11","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-06","FORECAST_END":"2023-04-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE02 | 2023-04-06 | 2023-04-27 | NANDE MAQUBELA | Floyd Mofokeng | 23000027 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000023 | Absa Douglas | Absa Douglas |  |  | Region 3 | Northern Cape | 78432X |  | Douglas Spar Shopping Centre-Cnr Arnot & Loch St-Kimberley |  | 2023-03-02 | 2023-03-02 |  | ASP-CR0395 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-02 |  | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000023,"ONEVIEW":"78432X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-03-02","DATE07":"2023-03-23","DATE08":"2023-05-07","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-02","FORECAST_END":"2023-03-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE12 | 2023-03-02 | 2023-03-23 | NANDE MAQUBELA | Floyd Mofokeng | 23000183 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000024 | Absa Rustenburg (Phoken | Absa Rustenburg (Phokeng Plaza) |  |  | Region 3 | North West | 36215X | 1000-71282-01 | Rustenburg Phokeng Plaza-Cnr R565 & Direpotsane St-Rustenburg | N | 2023-03-02 | 2023-03-30 |  | ASP-CR0396 | REL AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2021-04-29 | MOKOENAM2 | 2023-02-02 |  | 0 | No approvals were requested, only travelling claims under the project. | 1 |  |  | 0 | No approvals were requested, only travelling claims under the project. | {"MANDT":"111","REFERENCE":90000024,"ONEVIEW":"36215X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000025 | Absa Bank Mahikeng CBD | Absa Bank Mahikeng CBD |  |  | Region 3 | North West | 77725X | 1000-71297-01 | Mafikeng CBD-Main St-Mafikeng | Y | 2023-03-02 | 2023-03-30 |  | ASP-CR0397 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2024-09-29 | MOKOENAM2 | 2023-02-02 |  | 0 | 2023.07.13: Approved by Conrad M | 100 | 2023-07-13 | 2023-07-13 | 178956.92 | Approved | {"MANDT":"111","REFERENCE":90000025,"ONEVIEW":"77725X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEF3YWl0aW5nIEludm9pY2luZy4=","RATING":""} |  |  | C000098575 | PHASE06 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-07-18 | 155614.72 | 0 |  |  | C000098575 | 155614.72 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000026 | Absa Boitekong Mall | Absa Boitekong Mall |  |  | Region 3 | North West | 22485X | 1000-62950-01 | Boitekong Mall-Cnr Thlou St & R510-Rustenburg |  | 2023-03-02 | 2023-03-30 |  | ASP-CR0398 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-02 |  | 240850.16 | 2023.03.16: Approved by Conrad M 2023.03.14: Supported by Leko N & Ilana vdW | 100 | 2023-03-16 | 2023-03-16 | 240850.16 | Approved | {"MANDT":"111","REFERENCE":90000026,"ONEVIEW":"22485X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEludm9pY2luZyBpbiBwcm9ncmVzcy4=","RATING":""} |  |  | C000074873 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 23000154 |  |  |  |  | 2023-03-17 | 209434.91 | 0 |  |  | C000074873 | 209434.91 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000027 | Absa Mogwase | Absa Mogwase |  |  | Region 3 | North West | 77787X | 1000-71300-01 | Mogwase Shopping Centre-Railway Rd-Mogwase |  | 2023-03-02 | 2023-03-30 |  | ASP-CR0399 | REL AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-02 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000027,"ONEVIEW":"77787X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE10 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 23000180 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000028 | Absa Hartbeesfontein | Absa Hartbeesfontein |  |  | Region 3 | North West | 77915X |  | Hartbeesfontein-Voortrekker St-Hartbeesfontein |  | 2023-03-02 | 2023-03-30 |  | ASP-CR0400 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-02 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000028,"ONEVIEW":"77915X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEludm9pY2luZyBpbiBwcm9ncmVzcy4=","RATING":""} |  |  |  | PHASE02 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Floyd Mofokeng | 23000254 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000029 | Absa Heidedal LED light fittings | Absa Heidedal LED light fittings |  |  | Region 3 | Free State | 36261X | 1000-71587-01 | Twin City Mall Heidedal-Heatherdale Rd-Bloemfontein |  | 2023-03-01 | 2023-03-30 |  | ASP-CR0401 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-09 |  | 174619.46 | 2023.07.20: Approved by Conrad M Supported by Cres Engineering | 100 | 2023-03-09 | 2023-07-20 | 140007.53 | Approved | {"MANDT":"111","REFERENCE":90000029,"ONEVIEW":"36261X","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-25","DATE05":"2023-03-01","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHBhY2sgc3VibWl0dGVkIHRvIENyZXMgRW5naW5lZXJpbmcgZm9yIEFwcHJvdmFs","RATING":""} |  |  | C000100098 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Floyd Mofokeng | 23000202 |  |  |  |  | 2023-07-26 | 121745.67 | 0 |  |  | C000100098 | 121745.67 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000030 | Absa Burger Street- New COC for the buil | Absa Burger Street- New COC for the buil |  |  | Region 3 | North West | 77057X | 1000-71282-01 | Absa Burger Street Cnr Nelson Mandela & Beyers Naude St - Rustenburg | N | 2023-03-30 |  |  | ASP-CR0402 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | F |  | NOMNGANGAL | 2023-02-10 |  | 0 | Approved at CB/BTB | 100 | 2023-03-28 | 2023-03-28 | 178658.25 | Approved | {"MANDT":"111","REFERENCE":90000030,"ONEVIEW":"77057X","DATE01":"2023-01-19","DATE02":"2023-02-16","DATE03":"2023-02-23","DATE04":"2023-02-23","DATE05":"2023-03-30","DATE06":"2023-04-29","DATE07":"2023-05-20","DATE08":"2023-07-04","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-29","FORECAST_END":"2023-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000076927 | PHASE11 | 2023-04-29 | 2023-05-20 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-03-29 | 155355 | 0 |  |  | C000076927 | 155355 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000031 | Absa Corner Church & Johan - Floor Conso | Absa Corner Church & Johan - Floor Conso |  |  | Region 3 | North West | 37181X | 1000-77497-01 | Corner of Church Street and Johanna Van Der Merwe Streets |  | 2023-02-28 | 2023-03-31 |  | ASP-CR0403 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Floyd Mofokeng |  |  | 0 |  | L |  | NOMNGANGAL | 2023-02-15 |  | 434105.24 | Approved by Lebusa M |  | 2023-02-15 | 2023-05-06 | 78522.77 | Approved | {"MANDT":"111","REFERENCE":90000031,"ONEVIEW":"37181X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-01-24","DATE04":"2023-01-24","DATE05":"2023-02-28","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083573 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000440 |  |  |  |  | 2023-08-31 | 68280.67 | 0 |  |  | C000083573 | 68280.67 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000032 | Absa Fleurdal Mall | Absa Fleurdal Mall |  |  | Region 3 | Free State | 79303X | 1000-71587-01 | Fleurdal Mall-Vereeniging Dr-Bloemfontein | Y | 2023-03-15 | 2023-04-05 |  | ASP-CR0404 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2023-09-29 | MOKOENAM2 | 2023-02-15 |  | 0 | No approvals were requested for the project | 1 |  |  | 0 | Duplicate | {"MANDT":"111","REFERENCE":90000032,"ONEVIEW":"79303X","DATE01":"2023-01-04","DATE02":"2023-02-01","DATE03":"2023-02-08","DATE04":"2023-02-08","DATE05":"2023-03-15","DATE06":"2023-04-05","DATE07":"2023-04-26","DATE08":"2023-06-10","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-04-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RHVwbGljYXRlLg==","RATING":""} |  |  |  | PHASE11 | 2023-04-05 | 2023-04-26 | NANDE MAQUBELA | Juanita Van Coller | 23000182 | [5 empty] | 0 | 0 |  |  | C000073705 | 151843 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000033 | Absa Britz - Certificate | Absa Britz - Certificate of Compliance |  |  | Region 3 | North West | 22229X | 1000-71277-01 | Brits Mall-Cnr Hendrik Verwoerd & Maple Ridge Ave-Brits | Y | 2023-03-03 | 2023-03-31 |  | ASP-CR0405 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2025-10-30 | NOMNGANGAL | 2023-02-23 |  | 28366.98 | Approved at CB/BTB | 100 | 2023-02-28 | 2023-02-28 | 28366.98 | Approved | {"MANDT":"111","REFERENCE":90000033,"ONEVIEW":"22229X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000071299 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-03-02 | 24666.94 | 0 |  |  | C000071299 | 24666.94 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000034 | Absa Brits - Branch Di | Absa Brits - Branch Dilapitation prior t |  |  | Region 3 | North West | 22229X | 1000-71277-01 | Brits Mall-Cnr Hendrik Verwoerd & Maple Ridge Ave-Brits | Y | 2023-03-31 | 2023-03-31 |  | ASP-CR0406 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2025-10-30 | NOMNGANGAL | 2023-02-27 |  | 116320.27 | Approved at CB/BTB | 100 | 2023-03-15 | 2023-03-15 | 116320.27 | Approved | {"MANDT":"111","REFERENCE":90000034,"ONEVIEW":"22229X","DATE01":"2023-01-20","DATE02":"2023-02-17","DATE03":"2023-02-24","DATE04":"2023-02-24","DATE05":"2023-03-31","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-04-21","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"161:28:7:0:35:0:21:45:-45:0","PROGRESS":23,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIFBPQyBzdWJtaXR0ZWQgdG8gRmluYW5jZSAyMSBBcHJpbCAyMDIz","RATING":""} |  |  | C000075276 | PHASE09 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-03-22 | 101148.06 | 0 |  |  | C000075276 | 101148.06 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000035 | Absa Kroonstad | Absa Kroonstad |  |  | Region 3 | Free State | 37158X |  | Corner President, Cross and Hill Streets, Kroonstad | Y | 2023-04-05 | 2023-04-26 |  | ASP-CR0407 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2024-04-29 | MOKOENAM2 | 2023-03-01 |  | 64655.47 |  | 100 | 2023-03-13 | 2023-03-13 | 64655.47 | Supplier PO's were requested on the 13 March 2023 | {"MANDT":"111","REFERENCE":90000035,"ONEVIEW":"37158X","DATE01":"2023-01-25","DATE02":"2023-02-22","DATE03":"2023-03-01","DATE04":"2023-03-01","DATE05":"2023-04-05","DATE06":"2023-04-26","DATE07":"2023-05-17","DATE08":"2023-07-01","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-26","FORECAST_END":"2023-05-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  | C000115084 | PHASE11 | 2023-04-26 | 2023-05-17 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-06 | 67894.01 | 0 |  |  | C000073402 | 67894.01 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000036 | Moffett Office Park Underceiling HVAC re | Moffett Office Park Underceiling HVAC re |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N |  | 2023-03-31 |  | ASP-EC0273 | CLSD BUDG AVAC RESA SETC: | SAPMT | false | false | null | Laxine Maliffe | na |  | 0 |  | L |  | GAMIETR | 2023-01-17 |  | 47975.36 | Approved at CB/BTB | 100 | 2023-01-27 | 2023-02-16 | 47975.36 | Approved | {"MANDT":"111","REFERENCE":90000036,"ONEVIEW":"22937X","DATE01":"2023-01-18","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-27","DATE05":"2023-02-16","DATE06":"2023-03-10","DATE07":"2023-03-17","DATE08":"2023-05-19","DATE09":"2023-06-28","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:7:2:20:22:7:63:40:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-10","FORECAST_END":"2023-03-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgTWF5IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000069878 | PHASE11 | 2023-03-10 | 2023-03-17 | RODERICK NEVAY | Nokuthula Manzini | 23000366 |  |  |  |  | 2023-02-22 | 41717.7 | 0 |  |  | C000069878 | 41717.7 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000037 | Absa Murraysburg - Closure - Dilaps | Absa Murraysburg - Closure - Dilaps |  |  | Region 2 | Eastern Cape | 76566X | 1000-70788-01 | Murraysburg-Pastorie St-Murraysburg | N | 2023-02-21 | 2023-04-30 |  | ASP-EC0274 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-01-20 |  | 95666.99 | Approved at CB/BTB | 100 | 2023-02-06 | 2023-02-06 | 95666.99 | Approved | {"MANDT":"111","REFERENCE":90000037,"ONEVIEW":"76566X","DATE01":"2022-12-13","DATE02":"2023-01-15","DATE03":"2023-01-31","DATE04":"2023-02-06","DATE05":"2023-02-06","DATE06":"2023-02-17","DATE07":"2023-03-17","DATE08":"2023-04-24","DATE09":"2023-05-31","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"169:33:16:6:0:11:28:38:37:9","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-17","FORECAST_END":"2023-03-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjQgQXByaWwgLSBGaW5hbCBQT0Mgc3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000067183 | PHASE11 | 2023-02-17 | 2023-03-17 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-02-10 | 83188.69 | 0 |  |  | C000067183 | 83188.69 |  | 7637.91 |  | 0 | 0 |  | 0 |  | 0
90000038 | Absa Stone Towers KWT - Generator rental | Absa Stone Towers KWT - Generator rental (OPEX Retrospective) |  |  | Region 2 | Eastern Cape | 78247X | 1000-71463-01 | Stone Towers Shopping Centre-Alexandra Rd-King William s Town | N | 2023-01-15 | 2023-06-30 |  | ASP-EC0275 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-01-20 |  | 77913.65 | CB04 | 100 | 2023-02-09 | 2023-02-09 | 77913.65 |  | {"MANDT":"111","REFERENCE":90000038,"ONEVIEW":"78247X","DATE01":"2023-01-19","DATE02":"2023-01-19","DATE03":"2023-01-19","DATE04":"2023-01-26","DATE05":"2023-02-09","DATE06":"2023-02-09","DATE07":"2023-02-09","DATE08":"2023-03-10","DATE09":"2023-03-30","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:7:14:0:0:29:20:12","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-09","FORECAST_END":"2023-02-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTAgTWFyIEZpbmFsIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000067805 | PHASE11 | 2023-02-09 | 2023-02-09 | RODERICK NEVAY | Juanita van Coller | 0 | [5 empty] | 67751 | 0 |  |  | C000067805 | 67751 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000039 | Absa Linton Arcade - UPS Replacement | Absa Linton Arcade - UPS Replacement | Ym5Wc2JDQT0g |  | Region 2 | Eastern Cape | 76436X | 1000-71457-01 | Linton Arcade-Cape Rd-Port Elizabeth |  | 2023-02-01 | 2023-03-13 |  | ASP-EC0276 | CRTD AVAC: | SAP_018 | false | false | null | Laxine Maliffe | na |  | 0 |  |  |  | CEASARS | 2023-01-20 |  | 0 | null | 1 |  |  | 0 | null | {"MANDT":"111","REFERENCE":90000039,"ONEVIEW":"76436X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-06","DATE05":"2023-02-27","DATE06":"2023-03-13","DATE07":"2023-03-31","DATE08":"2023-04-21","DATE09":"2023-06-05","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-13","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDYW5jZWxsZWQ=","RATING":""} |  |  |  | PHASE12 | 2023-03-13 | 2023-03-31 | RODERICK NEVAY | nokuthula manzini | 23000474 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000040 | Moffett Office Park External Signage Ref | Moffett Office Park External Signage Replacement |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-03-13 | 2023-04-30 |  | ASP-EC0277 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-01-20 |  | 310381.67 | Approved at CB/BTB | 100 | 2023-02-16 | 2023-02-16 | 310381.67 | Approved | {"MANDT":"111","REFERENCE":90000040,"ONEVIEW":"22937X","DATE01":"2023-01-02","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-13","DATE05":"2023-02-16","DATE06":"2023-03-24","DATE07":"2023-03-26","DATE08":"2023-03-30","DATE09":"2023-04-30","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"149:21:21:0:3:36:2:4:31:20","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-24","FORECAST_END":"2023-03-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzAgTWFyY2ggRmluYWwgUE9DIFN1Ym1pdHRlZA==","RATING":""} |  |  | C000069654 | PHASE11 | 2023-03-24 | 2023-03-26 | RODERICK NEVAY | Juanita van Coller | 23000167 |  |  |  |  | 2023-02-22 | 269897.1 | 0 |  |  | C000069654 | 269897.1 | CIP2023XP | 28216.52 |  | 0 | 0 |  | 0 |  | 0
90000041 | Absa Ntabankulu - HVAC Cages | Absa Ntabankulu - Relocation of outdoor Units + HVAC Cages |  |  | Region 2 | Eastern Cape | 20949X | 1000-70921-01 | Ntabankulu-Main St-Ntabankulu | N | 2023-03-13 | 2023-04-30 |  | ASP-EC0278 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-01-31 |  | 124797.88 | 2023.04.14: Approved by Kous JvR 2023.04.11: Supported by Rob L | 100 | 2023-04-14 | 2023-04-14 | 124797.88 | Absa Ref : 240129_215 | {"MANDT":"111","REFERENCE":90000041,"ONEVIEW":"20949X","DATE01":"2023-01-19","DATE02":"2023-02-14","DATE03":"2023-03-31","DATE04":"2023-04-14","DATE05":"2023-04-14","DATE06":"2023-06-19","DATE07":"2023-12-19","DATE08":"2023-12-19","DATE09":"2024-02-02","DATE10":"2024-02-29","DATE11":"2024-01-29","DATE12":"2024-01-29","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"377:26:45:14:0:66:183:0:45:2","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-19","FORECAST_END":"2023-12-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgRmViIFBNIHRvIGVtYWlsIHByb2N1cmVtZW50IGFuZCBmb2xsb3cgdXAgd2l0aCB0aGUgdmVuZG9yIHRvIGFkZHJlc3Mgc25hZ3MKMDggRmViIFBNIHRvIGVtYWlsIHByb2N1cmVtZW50IGFuZCBmb2xsb3cgdXAgd2l0aCB0aGUgdmVuZG9yIHRvIGFkZHJlc3Mgc25hZ3MKIEZlYiAtIFBNIHRvIGVtYWlsIHByb2N1cmVtZW50IGZvciBhc3Npc3RhbmNlIHRvIGVuZ2FnZSBWZW5kb3IKMSBGZWIgUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yIGlmIENvbXBsZXRlZAoyOSBKYW4gVmVuZG9yIHJldHVybmluZyB0byBhZGRyZXNzIHNuYWdzIDMxIEphbgoyNSBKYW4gUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yCjIyIEphbiBQTSB0byBmb2xsb3cgdXAgcmUgc25hZ3MKMTUgSmFuIHRvIHJldHVybiBhcyBzbmFncwoxNCBEZWMgQ2FnZXMgdG8gYmUgaW5zdGFsbGVkIDE4LzE5IERlYwoxMSBEZWMgUE0gdG8gY29uZmlybSBpbnN0YWxsYXRpb24gZGF0ZQo3IERlYyAtIFBNIHRvIGNvbmZpcm0gaW5zdGFsbGF0aW9uIGRhdGUgQVNBUC4KNCBEZWMgUE0gdG8gZm9sbG93IHVwIHJlIGNhZ2VzIGFzIHdhcyBkdWUgMSBEZWMKMzAgTm92IFBtIHRvIGZvbGxvdyB1cCB3aXRoIHRoZSBWZW5kb3IgcmUgdGhlIGluc3RhbGxhdGlvbiB0byBiZSBkb25lIGJ5IDEgRGVjCjI3IE5vdiAtIENhZ2VzIHRvIGJlIHJlaW5zdGFsbGVkIC0gVmVtZG9yIHRvIGNvbmZpcm0gZGF0ZQoyMyBOb3YgQ2FnZXMgbmVlZCB0byBiZSBpbnN0YWxsZWQsIFBNIHRvIGNvbmZpcm0gZGF0ZXMgLiBWZW5kb3IgdG8gcmVtYW51ZmFjdHVyZSB0aGUgY2FnZXMgYXMgdGhlIGN1cnJlbnQgb25lcyBhcmUgdG9vIGJpZy9oZWF2eQoxNyBOb3YgQ2FnZXMgdG8gYmUgaW5zdGFsbGVkIFBNIGluZm9ybWVkIFZlbmRvciB0byBQcm9jZWVkCjE2IE5vdiBXYWl0aW5nIHBpY3R1cmVzIHRvIHNlbmQgdG8gQWZyaWNhIFNlY3VyaXR5IHRvIGRlY2xpbmUgdGhlIHJlcXVlc3QgZm9yIGNhZ2VzCjkgTm92IENvbmZpcm1hdGlvbiBmcm9tIEFTIHJlcXVpcmVkIHRvIGNsb3NlIHByb2plY3QgcmUgdGhlIENhZ2VzCjI2IE9jdCBQYXJ0IDEgUE9DIFN1Ym1pdHRlZC4gUiA4OSA5OTIuOTEKMjMgT2N0IFBPQyBzZW50IHRvIEFic2EgRW5naW5lZXJpbmcgZm9yIFNpZ25vZmYKMTAgT2N0IC0gUE9DIHRvIGJlIHN1Ym1pdHRlZCB0byBBYnNhIGZvciBTaWdub2ZmCjEwIE9jdCAtIFBPQyB0byBiZSBzdWJtaXR0ZWQgdG8gQWJzYSBmb3IgU2lnbm9mZgoyOCBTZXB0IC0gV2FycmVudHkgSW5mb3JtYXRpb24gb3V0c3RhbmRpbmcgZm9yIHRoZSBIVkFDIHVuaXRzCjIxIFNlcHQgLSBQT0MgdG8gYmUgc3VibWl0dGVkIGZvciByZWxvY2F0aW9uIGFuZCBjYWdlcyB0byBiZSBjb25maXJtZWQKIDEyIFNlcHQgLSBIVkFDIFBPQyByZWplY3RlZCBieSBNaG9saSBvbiAyNC8wNSBBc3NldCB1cGxvYWQgc2hhcmVkIHdpdGggU2lwaGVsZWxlIG9uIDEyLzA5IGFmdGVyIGZpbmFsbHkgcmVjZWl2aW5nIGZyb20gU3VwcGxpZXIgSW52b2ljZSBmb3IgQ2FnZXMgb3V0c3RhbmRpbmcsIEkgaGF2ZSByZXF1ZXN0ZWQgaXQgZnJvbSB0aGUgdmVuZG9yIG9uIDEzLzA5Cgo=","RATING":"Low"} |  |  | C000080524 | PHASE08 | 2023-06-19 | 2023-12-19 | RODERICK NEVAY | Floyd Mofokeng | 23000083 |  |  |  |  | 2023-04-19 | 108519.9 | 0 |  |  | C000080524 | 108519.9 | CIP2023XP | 11345.26 |  | 0 | 0 |  | 0 |  | 0
90000042 | Absa Walmer Park - Signage | Absa Walmer Park - Signage - Vinyl Contra Vision | bnVsbCA%3D |  | Region 2 | Eastern Cape | 77686X | 1000-71032-01 | Walmer Park Shopping Centre-Main Rd-Port Elizabeth | N | 2023-03-31 | 2023-04-30 |  | ASP-EC0279 | CLSD BUDG AVAC RESA SETC: | SAP_018 | false | false | null | Laxine Maliffe | na | null | 0 |  | L |  | CEASARS | 2023-02-14 |  | 52472.96 | 2023.03.30: Approved by Conrad M 2023.03.28: Supported by Judith B & Ilana vdW | 100 | 2023-03-30 | 2023-03-30 | 52472.96 | Approved | {"MANDT":"111","REFERENCE":90000042,"ONEVIEW":"77686X","DATE01":"2023-02-09","DATE02":"2023-02-09","DATE03":"2023-03-16","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-05-02","DATE07":"2023-05-15","DATE08":"2023-06-26","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:35:14:0:33:13:42:35:1","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-02","FORECAST_END":"2023-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgSnVuZSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000077507 | PHASE11 | 2023-05-02 | 2023-05-15 | RODERICK NEVAY | Nokuthula Manzini | 23000120 |  |  |  |  | 2023-03-31 | 45628.66 | 0 |  |  | C000077507 | 45628.66 | CIP2023XP | 4770.27 |  | 0 | 0 |  | 0 |  | 0
90000043 | Absa Plettenberg Bay - Signage Welcome c | Absa Plettenberg Bay - Signage Welcome c |  |  | Region 2 |  | 77723X | 1000-71034-01 | Sun Centre Development-Main St-Plettenberg Bay |  | 2023-04-10 | 2023-04-30 |  | ASP-EC0280 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  |  |  | CEASARS | 2023-02-16 |  | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000044 | Absa High Road Butterworth ATM Room ATM Room Worktop | Absa High Road Butterworth ATM Room Worktop |  |  | Region 2 | Eastern Cape | 78501X | 1000-71048-01 | High Road Butterworth-Cnr High Rd & Bell St-Butterworth | N | 2023-03-31 | 2023-04-30 |  | ASP-EC0281 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-02-23 |  | 26996.19 | 2023.05.04: Approved by Conrad M 2023.05.02: Supported by Judith B & Ilana vdW | 100 | 2023-05-04 | 2023-05-04 | 26996.19 | Approved | {"MANDT":"111","REFERENCE":90000044,"ONEVIEW":"78501X","DATE01":"2023-02-23","DATE02":"2023-02-24","DATE03":"2023-04-20","DATE04":"2023-05-04","DATE05":"2023-05-04","DATE06":"2023-06-18","DATE07":"2023-07-02","DATE08":"2023-07-23","DATE09":"2023-09-06","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:1:55:14:0:45:14:21:45:11","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-18","FORECAST_END":"2023-07-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVseSAtIEFic2EgdG8gY29uZmlybSBpdCBjb250aW51ZSBhcyBkb3VidCBoYXMgYXJpc2VuIG92ZXIgdGhlIHNpemUgdGhhdCBjYW4gYmUgaW5zdGFsbGVkIC0gUE0gdG8gY29uZmlybSB3aXRoIEFic2EgUGxhbm5lci4=","RATING":"Low"} |  |  | C000083706 | PHASE11 | 2023-10-31 | 2023-10-31 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-08 | 23474.95 | 0 |  |  | C000083706 | 23474.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000045 | Mamelodi Plaza Dilaps | Mamelodi Plaza Dilaps |  |  | Region 1 |  | 78512X | 1000-71408-01 | Mamelodi Plaza-Cnr Tsamaya Rd & K54-Mamelodi | Y | 2023-02-16 | 2023-02-16 |  | ASP-GN0177 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 0 |  | L |  | GAMIETR | 2023-01-20 |  | 60332.55 | Approved at CB/BTB | 100 | 2023-01-25 | 2023-01-25 | 69382.43 | Approved | {"MANDT":"111","REFERENCE":90000045,"ONEVIEW":"78512X","DATE01":"2022-11-08","DATE02":"2022-11-15","DATE03":"2022-12-06","DATE04":"2022-12-13","DATE05":"2023-01-03","DATE06":"2023-02-17","DATE07":"2023-02-17","DATE08":"2023-03-10","DATE09":"2023-04-24","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"234:7:21:7:21:45:0:21:45:25","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-17","FORECAST_END":"2023-02-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | c000063835 | PHASE11 | 2023-02-17 | 2023-03-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 | [5 empty] | 69382.43 | 0 |  |  | c000063835 | 60332.55 |  | 6143.86 |  | 0 | 0 |  | 0 |  | 0
90000046 | Pretoria Campus Cooling Fans | Decommission old UPS fans. Supply and install new X6 fan kits for 160kVA MPT and X4 fan kits for 60kVA MST UPSs. Test and commission. Installation will be conducted during normal working hours for 2 days. Material lead-time: 2-3 days. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-01-16 | 2023-03-31 |  | ASP-GN0178 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 0 |  | F |  | GAMIETR | 2023-02-07 |  | 244475.12 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 244475.12 | Approved | {"MANDT":"111","REFERENCE":90000046,"ONEVIEW":"22491X","DATE01":"2022-11-07","DATE02":"2022-11-14","DATE03":"2022-12-05","DATE04":"2022-12-12","DATE05":"2023-01-02","DATE06":"2023-02-01","DATE07":"2023-02-28","DATE08":"2023-03-21","DATE09":"2023-03-31","DATE10":"2023-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-01","FORECAST_END":"2023-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000066678 | PHASE11 | 2023-02-01 | 2023-02-28 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000361 |  |  |  |  | 2023-02-08 | 244475.12 | 0 |  |  | C000066678 | 212587.06 | CIP2023XP | 22090.47 |  | 0 | 0 |  | 0 |  | 0
90000047 | Hillcrest Office Dilaps Building Signage | Removal of signage on the left side of the building using a cherry picker. Signage will be removed during normal working hours for one day. On site security guard to assist during the removal of the signage. |  |  | Region 1 |  | 78531X | 1000-70416-01 | Hillcrest Office Park-Lunnon Rd-Pretoria | N | 2023-02-06 | 2023-03-31 |  | ASP-GN0179 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 0 |  | L |  | GAMIETR | 2023-02-07 |  | 37275.94 | Approved at CB/BTB | 100 | 2023-02-09 | 2023-02-09 | 37275.94 | Approved | {"MANDT":"111","REFERENCE":90000047,"ONEVIEW":"78531X","DATE01":"2022-11-28","DATE02":"2022-12-05","DATE03":"2022-12-26","DATE04":"2023-01-02","DATE05":"2023-01-23","DATE06":"2023-02-06","DATE07":"2023-03-31","DATE08":"2023-04-21","DATE09":"2023-06-05","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-06","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000067570 | PHASE11 | 2023-07-14 | 2023-07-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000484 |  |  |  |  | 2023-02-13 | 37275.94 | 0 |  |  | c00067570 | 32413.86 |  | 3257.81 |  | 0 | 0 |  | 0 |  | 0
90000048 | Alice Lane South Replace | Alice Lane South Replace cushions or reu |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | Y | 2022-12-29 | 2023-04-29 |  | ASP-GS0597 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 0 |  | L |  | GAMIETR | 2023-01-16 |  | 174251.47 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 174251.47 | Approved | {"MANDT":"111","REFERENCE":90000048,"ONEVIEW":"35041X","DATE01":"2022-06-21","DATE02":"2023-01-29","DATE03":"2023-02-19","DATE04":"2023-02-26","DATE05":"2023-03-05","DATE06":"2022-08-30","DATE07":"2023-06-21","DATE08":"2023-07-12","DATE09":"2023-08-26","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-08-30","FORECAST_END":"2023-06-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000111024 | PHASE11 | 2023-01-23 | 2023-02-20 | PRESHANE MUNTHREE | Michael Maluleka | 0 |  |  |  |  | 2023-09-15 | 190939.33 | 0 |  |  | C000064760 | 151523.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000049 | 270 Republic Road Canteen Kitchen Swing door | Ã¢ÂÂ¢Breaking tiles and making a good opening (1,5 sqm). Ã¢ÂÂ¢Installation of a new canteen swing door. Ã¢ÂÂ¢Security guard for the duration of the works. Ã¢ÂÂ¢Work will be carried out after normal working hours for 3 days. Ã¢ÂÂ¢Material Leadtime: +-5 days. |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg | N | 2022-10-26 |  |  | ASP-GS0598 | CRTD: |  | false | false |  |  |  |  | 0 |  | F |  | GAMIETR | 2023-01-23 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000049,"ONEVIEW":"21335X","DATE01":"2022-08-17","DATE02":"2022-08-24","DATE03":"2022-09-14","DATE04":"2022-09-21","DATE05":"2022-10-12","DATE06":"2022-10-26","DATE07":"2022-11-25","DATE08":"2022-12-16","DATE09":"2023-01-30","DATE10":"2023-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-26","FORECAST_END":"2022-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE08 | 2022-10-26 | 2022-11-25 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000050 | Absa Sandton Atrium - Dilaps 5th Floor | Absa Sandton Atrium - Dilaps 5th Floor |  |  | Region 1 | Gauteng South | 78604X | 1000-71411-01 | Sandton Atrium on 5th-Cnr Rivonia Rd & 5th St-Sandton |  | 2023-03-03 | 2023-03-30 |  | ASP-GS0599 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 0 |  | F |  | NOMNGANGAL | 2023-01-27 |  | 14594.44 | Approved at CB/BTB | 100 | 2023-01-27 | 2023-01-27 | 167836.11 | Approved | {"MANDT":"111","REFERENCE":90000050,"ONEVIEW":"78604X","DATE01":"2022-12-23","DATE02":"2022-12-30","DATE03":"2023-01-20","DATE04":"2023-01-27","DATE05":"2023-02-17","DATE06":"2023-03-03","DATE07":"2023-03-30","DATE08":"2023-04-20","DATE09":"2023-06-04","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-03","FORECAST_END":"2023-03-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000064518 | PHASE10 | 2023-03-03 | 2023-03-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 0 |  |  |  |  | 2023-01-28 | 167836.12 | 0 |  |  | C000064518 | 145944.45 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000051 | 268 Republic Road water reticulation Investigation | 1.Radar Diagnostic scanning of water reticulation system along Republic road and guard house area. 2.Excavate from the meter that come from the tanks to each of the X3 blocks 3.Supply 50mm HDE pipes and fittings to feed water from the tanks to the X3 blocks 4.The pipes will run in the garden as far as possible 5.Lift and replace paving where necessary 6.Works to be carried over one day and during normal working hours. |  |  | Energy | Gauteng | 21334X | 1000-70026-01 | Absa 268 Republic Road | N | 2023-02-06 | 2023-03-31 |  | ASP-GS0600 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 0 |  | F |  | GAMIETR | 2023-02-06 |  | 254960.75 | Approved at CB/BTB | 100 | 2023-02-09 | 2023-02-09 | 254960.75 | Approved | {"MANDT":"111","REFERENCE":90000051,"ONEVIEW":"21334X","DATE01":"2022-11-28","DATE02":"2022-12-05","DATE03":"2022-12-26","DATE04":"2023-01-02","DATE05":"2023-01-23","DATE06":"2023-02-06","DATE07":"2023-05-08","DATE08":"2023-05-29","DATE09":"2023-07-13","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"214:7:21:7:21:14:91:21:45:25","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-06","FORECAST_END":"2023-05-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000067715 | PHASE11 | 2023-02-06 | 2023-05-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-02-13 | 221705 | 0 |  |  | C000067715 | 221705 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000052 | Absa Towers Main Repairing cracking epoxy | Repair cracking epoxy flooring with crack sealers Apply under coats Apply epoxy flooring paint |  |  | Region 1 |  | 78944X | 1000-71415-01 | ABSA TOWERS MAIN-Main St-Johannesburg | N | 2023-02-06 | 2023-03-31 |  | ASP-GS0601 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 0 |  | L |  | GAMIETR | 2023-02-07 |  | 38640 |  | 60 | 2023-02-06 | 2023-02-06 | 38640 |  | {"MANDT":"111","REFERENCE":90000052,"ONEVIEW":"78944X","DATE01":"2022-11-28","DATE02":"2022-12-05","DATE03":"2022-12-26","DATE04":"2023-01-02","DATE05":"2023-01-23","DATE06":"2023-02-06","DATE07":"2023-03-31","DATE08":"2023-04-21","DATE09":"2023-06-05","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-06","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000067337 | PHASE11 | 2023-02-06 | 2023-03-31 | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2023-02-10 | 33600 | 0 |  |  | C000067337 | 33600 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000053 | Alice Lane North Replace glass panel at | Alice Lane North Replace glass panel at |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | N | 2023-01-31 |  |  | ASP-GS0602 | CRTD: |  | false | false |  | Tsholofelo Sello |  |  | 0 |  | L |  | GAMIETR | 2023-02-07 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000053,"ONEVIEW":"70656X","DATE01":"2022-11-22","DATE02":"2022-11-29","DATE03":"2022-12-20","DATE04":"2022-12-27","DATE05":"2023-01-17","DATE06":"2023-01-31","DATE07":"2023-03-02","DATE08":"2023-03-23","DATE09":"2023-05-07","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-31","FORECAST_END":"2023-03-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE08 | 2023-01-31 | 2023-03-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000054 | Absa Towers West Supply Cooling Fans | Absa Towers West Supply and Install 36 UPS Cooling Fans |  | l | Region 1 | Gauteng North | 21526X | 1000-70027-01 | Absa Towers West Supply Cooling Fans | Y | 2023-01-16 | 2023-03-31 |  | ASP-GS0603 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Athi Magqashela | na |  | 0 |  | F |  | GAMIETR | 2023-02-07 |  | 275461.34 | Approved at CB/BTB | 100 | 2023-01-19 | 2023-01-19 | 275461.34 | Approved | {"MANDT":"111","REFERENCE":90000054,"ONEVIEW":"21526X","DATE01":"2022-11-07","DATE02":"2022-11-14","DATE03":"2022-12-05","DATE04":"2022-12-12","DATE05":"2023-01-02","DATE06":"2023-01-16","DATE07":"2023-03-03","DATE08":"2023-03-24","DATE09":"2023-05-08","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"235:7:21:7:21:14:46:-25:0:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-16","FORECAST_END":"2023-03-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000066532 | PHASE11 | 2023-01-16 | 2023-03-03 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000195 |  |  |  |  | 2023-02-07 | 275461.34 | 0 |  |  | C000066532 | 239531.6 | CIP2023XP | 25041.94 |  | 0 | 0 |  | 0 |  | 0
90000055 | Absa Towers North ATM lobby floor tiles | Absa Towers North ATM lobby floor tiles |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2022-07-29 | 2023-03-31 |  | ASP-GS0604 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Athi Magqashela |  |  | 0 |  | F |  | GAMIETR | 2023-02-21 |  | 28239.94 | Approved at CB/BTB | 100 | 2023-02-23 | 2023-02-23 | 22877.53 | Approved | {"MANDT":"111","REFERENCE":90000055,"ONEVIEW":"77381X","DATE01":"2022-05-20","DATE02":"2023-01-29","DATE03":"2023-02-19","DATE04":"2023-02-26","DATE05":"2023-03-05","DATE06":"2022-07-29","DATE07":"2023-04-15","DATE08":"2023-07-10","DATE09":"2023-08-19","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"376:254:21:7:7:-219:260:86:40:0","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-07-29","FORECAST_END":"2023-04-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000070119 | PHASE11 | 2022-07-29 | 2023-04-15 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-02-23 | 22877.53 | 0 |  |  | C000070119 | 19893.5 |  | 2567.27 |  | 0 | 0 |  | 0 |  | 0
90000056 | Voortrekker Street - COC | Assess electrical infrastructure and give recommendations. remedy electricals work as per the recommendations. Issue COC. Work will be done after normal working hours for 3 days. Security guard during the execution of the works. Material lead time: +- 1 week. |  |  | Region 1 | Gauteng South | 79331X | 1000-70447-01 | Absa Voortrekker Street Alberton-Voortrekker St-Alberton | N | 2023-02-21 | 2023-03-31 |  | ASP-GS0605 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 0 |  | L |  | GAMIETR | 2023-02-21 |  | 60763.56 | Approved at CB/BTB | 100 | 2023-02-21 | 2023-02-21 | 60763.56 | Approved | {"MANDT":"111","REFERENCE":90000056,"ONEVIEW":"79331X","DATE01":"2022-12-13","DATE02":"2022-12-20","DATE03":"2023-01-10","DATE04":"2023-01-17","DATE05":"2023-02-07","DATE06":"2023-02-21","DATE07":"2023-03-31","DATE08":"2023-07-31","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-21","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000123271 | PHASE11 | 2023-07-14 | 2023-07-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-14 | 52837.89 | 0 |  |  | C000069973 | 52837.89 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000057 | Meyerton COC Investigation and remedial | Assess electrical infrastructure and give recommendations. remedy electricals work as per the recommendations. Issue COC. Work will be done after normal working hours for 3 days. Security guard during the execution of the works. Material lead time: +- 1 week. |  |  | Region 1 | Gauteng South | 77636X | 1000-70376-01 | Absa Meyerton-Loch St-Meyerton | N | 2023-02-21 | 2023-03-31 |  | ASP-GS0606 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 0 |  | L |  | GAMIETR | 2023-02-21 |  | 31418.91 | Approved at CB/BTB | 100 | 2023-02-21 | 2023-02-21 | 31418.91 | Approved | {"MANDT":"111","REFERENCE":90000057,"ONEVIEW":"77636X","DATE01":"2022-12-13","DATE02":"2022-12-20","DATE03":"2023-01-10","DATE04":"2023-01-17","DATE05":"2023-06-30","DATE06":"2023-07-14","DATE07":"2023-07-31","DATE08":"2023-09-30","DATE09":"2023-10-10","DATE10":"2023-10-31","DATE11":"2023-10-10","DATE12":"2023-10-10","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"230:7:21:7:164:14:17:61:10:0","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-14","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMi8yMCBOTjogRm9sbG93IHVwIHdpdGggQnJpZGdldCBvbiBNdWhvbGkncyBzaWduYXR1cmU=","RATING":""} |  |  | C000069971 | PHASE08 | 2023-07-14 | 2023-07-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-02-22 | 36131.75 | 0 |  |  | C000069971 | 27320.79 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000058 | Quo Vadis Centre, Westonaria Ceiling til | Quo Vadis Centre, Westonaria Ceiling tile | bnVsbCA%3D |  | Region 1 | Gauteng South | 76563X | 1000-70289-01 | Quo Vadis Centre-Pakeman St-Westonaria |  | 2023-01-29 | 2023-05-31 |  | ASP-GS0607 | REL BUDG AVAC RESA SETC: | SAPMT | false | false | null | Roshen Aniruth | na | null | 0 |  | L |  | GAMIETR | 2023-02-26 |  | 495321.15 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 495321.15 | Approved | {"MANDT":"111","REFERENCE":90000058,"ONEVIEW":"76563X","DATE01":"2020-11-20","DATE02":"2020-11-27","DATE03":"2020-12-18","DATE04":"2020-12-25","DATE05":"2021-01-15","DATE06":"2021-01-29","DATE07":"2021-02-28","DATE08":"2021-03-21","DATE09":"2021-05-05","DATE10":"2021-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2021-01-29","FORECAST_END":"2021-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000072612 | PHASE08 | 2023-07-31 | 2023-08-28 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000497 |  |  |  |  | 2023-03-08 | 495321.16 | 0 |  |  | C000072612 | 430714.05 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000059 | Absa Vanderbijlpark Alter Steel Cage | Absa Vanderbijlpark Alter Steel Cage |  |  | Region 1 | Gauteng South | 77470X | 1000-70369-01 | Vanderbijlpark-FW Beyers St-Vanderbijlpark | N | 2023-02-27 |  |  | ASP-GS0608 | CRTD: |  | false | false |  | Tsholofelo Sello |  |  | 0 |  | L |  | GAMIETR | 2023-02-27 |  | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000059,"ONEVIEW":"","DATE01":"2022-12-19","DATE02":"2022-12-26","DATE03":"2023-01-16","DATE04":"2023-01-23","DATE05":"2023-02-13","DATE06":"2023-02-27","DATE07":"2023-03-29","DATE08":"2023-04-19","DATE09":"2023-06-03","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-03-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE11 | 2023-02-27 | 2023-03-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000060 | Absa Vanderbijlpark Removal of Portable | Absa Vanderbijlpark Removal of Portable |  |  | Region 1 | Gauteng South | 77470X | 1000-70369-01 | Vanderbijlpark-FW Beyers St-Vanderbijlpark | N | 2023-02-27 |  |  | ASP-GS0609 | CRTD: |  | false | false |  |  |  |  | 0 |  | L |  | GAMIETR | 2023-02-27 |  | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000060,"ONEVIEW":"77470X","DATE01":"2022-12-19","DATE02":"2022-12-26","DATE03":"2023-01-16","DATE04":"2023-01-23","DATE05":"2023-02-13","DATE06":"2023-02-27","DATE07":"2023-03-29","DATE08":"2023-04-19","DATE09":"2023-06-03","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-03-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-02-27 | 2023-03-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000061 | Absa Vanderbijlpark Supply 4 tube capsul | Absa Vanderbijlpark Supply 4 tube capsul |  |  | Region 1 | Gauteng South | 77470X | 1000-70369-01 | Vanderbijlpark-FW Beyers St-Vanderbijlpark | N | 2023-02-27 |  |  | ASP-GS0610 | CRTD: |  | false | false |  |  |  |  | 0 |  | L |  | GAMIETR | 2023-02-27 |  | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000061,"ONEVIEW":"77470X","DATE01":"2022-12-19","DATE02":"2022-12-26","DATE03":"2023-01-16","DATE04":"2023-01-23","DATE05":"2023-02-13","DATE06":"2023-02-27","DATE07":"2023-03-29","DATE08":"2023-04-19","DATE09":"2023-06-03","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-03-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-02-27 | 2023-03-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000062 | Oakfields Shopping Dilaps Closure | Dilapidations (Removal of Absa equipment) |  |  | Region 1 | Gauteng North | 79055X | 1000-71417-01 | Oakfields Shopping Centre-Cnr Oak & Hanekom St-Benoni | N | 2023-01-31 | 2023-05-31 |  | ASP-GS0611 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 0 |  | L | 2024-11-29 | GAMIETR | 2023-03-02 |  | 113362.29 | Approved at CB/BTB | 100 | 2023-02-28 | 2023-02-28 | 113362.29 | Approved | {"MANDT":"111","REFERENCE":90000062,"ONEVIEW":"79055X","DATE01":"2022-11-22","DATE02":"2022-11-29","DATE03":"2022-12-20","DATE04":"2022-12-27","DATE05":"2023-01-17","DATE06":"2023-01-31","DATE07":"2023-03-01","DATE08":"2023-03-21","DATE09":"2023-04-30","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-01-31","FORECAST_END":"2023-03-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071301 | PHASE11 | 2023-01-31 | 2023-03-01 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-03-02 | 113362.29 | 0 |  |  | C000071301 | 98575.9 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000063 | Absa Durban North (18 Swapo)- External R | Absa 18 Swapo Street (Durban North) has not received an external refurbishment since its inception. The exterior paintwork of the structure has discoloured over time and defects such as peeling and blistering are visible in places. The band of brickwork which spans the bottom section of the building has been subject to unsightly efflorescence, and the louvres on the windows have rusted. The paraplegic parking bay markings need to be repainted, and a paraplegic sign installed for visibility. Waterproofing reinforcement at certain portions of the roof is also necessary as some of the membranes are loose, thus compromising the integrity of the waterproofing |  |  | Region 3 | KwaZulu-Natal | 77409X | 1000-71170-01 | Absa 18 Swapo Street-Swapo St-Durban |  | 2023-03-01 | 2023-03-30 |  | ASP-KZ0225 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-16 |  | 306796.05 | 2023.03.16: Approved by Conrad M 2023.03.14: Supported by Leko N |  | 2023-03-16 | 2023-03-16 | 306796.05 | Approved | {"MANDT":"111","REFERENCE":90000063,"ONEVIEW":"77409X","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-25","DATE05":"2023-03-01","DATE06":"2023-04-05","DATE07":"2023-04-18","DATE08":"2023-06-02","DATE09":"2023-06-28","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"191:28:7:0:35:35:13:45:26:0","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-04-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000075379 | PHASE11 | 2023-04-07 | 2023-04-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000173 |  |  |  |  | 2023-03-22 | 266779.18 | 0 |  |  | C000075379 | 266779.18 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000064 | Absa Paulpietersburg (17 High Str)-Exter | Absa Paulpietersburg (17 High Str)-Exter |  |  | Region 3 | KwaZulu-Natal | 77511X | 1000-71177-01 | Absa 17 High Street-High St-Paulpietersburg |  | 2023-03-03 | 2023-03-30 |  | ASP-KZ0226 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-16 |  | 0 | 2023.05.04: Approved by Conrad M |  | 2023-05-04 | 2023-05-04 | 279805.9 | Approved |  |  |  | C000083509 | PHASE08 | 2023-05-19 | 2023-05-28 | NANDE MAQUBELA | Juanita van Coller | 23000174 |  |  |  |  | 2023-05-08 | 243309.48 | 0 |  |  | C000083509 | 243309.48 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000065 | Absa Greytown (Bell Str)- External Refur | Absa Greytown (Bell Str)- External Refur |  |  | Region 3 | KwaZulu-Natal | 76978X | 1000-71151-01 | Absa Bell Street-Cnr Bell & Pine St-Greytown |  | 2023-03-03 | 2023-03-30 |  | ASP-KZ0227 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-16 |  | 0 |  | 100 |  |  | 151902.81 |  | {"MANDT":"111","REFERENCE":90000065,"ONEVIEW":"76978X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-07-18","DATE04":"2023-07-20","DATE05":"2023-08-01","DATE06":"2023-08-04","DATE07":"2023-09-27","DATE08":"2023-10-18","DATE09":"2023-10-25","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":60,"PROG06":100,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":29,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-04","FORECAST_END":"2023-09-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBwcm9ncmVzcywgUE9DIHRvIGJlIHN1Ym1pdHRlZCBPY3RvYmVyIDIwMjM=","RATING":""} |  |  |  | PHASE07 | 2023-08-04 | 2023-09-27 | NANDE MAQUBELA | Juanita van Coller | 23000191 | [5 empty] | 0 | 0 |  |  | C000109802 | 424724.75 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000066 | Absa Ladysmith (Murchison)- Replace Ceil | Absa Ladysmith (Murchison)- Replace Ceil |  |  | Region 3 | KwaZulu-Natal | 21052X | 1000-71074-01 | 150 Murchison Street-Murchison St-Ladysmith |  | 2023-03-30 | 2023-03-30 |  | ASP-KZ0228 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L |  | NOMNGANGAL | 2023-01-18 |  | 232046.43 | Approved at CB/BTB |  | 2023-03-02 | 2023-03-02 | 232046.43 | Approved |  |  |  | C000071698 | PHASE11 | 2023-03-20 | 2023-03-31 | NANDE MAQUBELA | Juanita Van Coller | 23000139 |  |  |  |  | 2023-03-03 | 201779.5 | 0 |  |  | C000071698 | 201779.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000067 | Absa Ridgeside - Purchase of Portable Ai | Absa Ridgeside - Purchase of Portable Ai |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2023-03-03 | 2023-03-31 |  | ASP-KZ0229 | CRTD: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-25 |  | 0 |  |  |  |  | 0 | [5 empty] | PHASE02 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | floyd mofokeng | 23000263 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000068 | Absa Eshowe - Minor Works | Absa Eshowe - Minor Works |  |  | Region 3 | KwaZulu-Natal | 77861X | 1000-71196-01 | Eshowe-Osborn Rd-Eshowe |  | 2023-03-30 | 2023-03-30 |  | ASP-KZ0230 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-30 |  | 0 | 2023.06.15: Approved by Conrad M as per email 2023.06.13: Supported by Leko N & Ilana vdW |  | 2023-06-15 | 2023-06-15 | 416300.17 | Approved |  |  |  | C000092903 | PHASE08 | 2023-06-12 | 2023-07-13 | NANDE MAQUBELA | Juanita Van Coller | 23000218 |  |  |  |  | 2023-06-20 | 362000.13 | 0 |  |  | C000092903 | 362000.13 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000069 | Absa Boardwalk Shopping- Installation of | Absa Boardwalk Shopping- Installation of blinds and signage |  |  | Region 3 | KwaZulu-Natal | 36265X | 1000-71131-01 | Building not in Real Estate Database | Y | 2023-03-03 | 2023-03-30 |  | ASP-KZ0231 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L | 2022-05-30 | NOMNGANGAL | 2023-01-31 |  | 52353.55 | Approved at CB/BTB |  | 2023-04-09 | 2023-03-09 | 730141.8 | project is completed there is no contingency left on the project.. | {"MANDT":"111","REFERENCE":90000069,"ONEVIEW":"36265X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-10","DATE06":"2023-03-29","DATE07":"2023-04-26","DATE08":"2023-06-10","DATE09":"2023-07-06","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-29","FORECAST_END":"2023-04-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071332 | PHASE11 | 2023-03-29 | 2023-04-26 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-03-13 | 634905.91 | 0 |  |  | C000073632 | 45524.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000070 | Absa Bergville - Deliver | Absa Bergville - Delivery of Visitors Ch |  |  | Region 3 | KwaZulu-Natal | 78037X | 1000-71209-01 | Bergville-Tatham Rd-Bergville | Y | 2023-03-30 |  |  | ASP-KZ0232 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L | 2022-10-30 | NOMNGANGAL | 2023-02-02 |  | 7238.79 | Approved at CB/BTB |  | 2023-02-16 | 2023-02-16 | 7238.79 | Approved | {"MANDT":"111","REFERENCE":90000070,"ONEVIEW":"78037X","DATE01":"2023-01-19","DATE02":"2023-02-16","DATE03":"2023-02-23","DATE04":"2023-02-23","DATE05":"2023-03-30","DATE06":"2023-04-29","DATE07":"2023-05-20","DATE08":"2023-07-04","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-29","FORECAST_END":"2023-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000069229 | PHASE11 | 2023-03-20 | 2023-03-31 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-02-20 | 6294.6 | 0 |  |  | C000069229 | 6294.6 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000071 | Absa House Pinetown- Ins | Absa House Pinetown- Installation of Blinds |  |  | Region 3 | KwaZulu-Natal | 77102X | 1000-71156-01 | House Pinetown-Church Ln-Pinetown | Y | 2023-03-03 | 2023-03-31 |  | ASP-KZ0233 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L | 2023-01-30 | NOMNGANGAL | 2023-02-02 |  | 38052.06 | 2023.04.19: Approved by Conrad M as per email 2023.04.18: Supported by Leko N & Ilana vdW |  | 2023-04-20 | 2023-04-20 | 38052.06 | Approved | {"MANDT":"111","REFERENCE":90000071,"ONEVIEW":"77102X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-03-06","DATE04":"2023-01-27","DATE05":"2023-04-19","DATE06":"2023-05-11","DATE07":"2023-06-13","DATE08":"2023-07-20","DATE09":"2023-07-21","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-11","FORECAST_END":"2023-06-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000081303 | PHASE11 | 2023-05-11 | 2023-06-13 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-21 | 33088.75 | 0 |  |  | C000081303 | 33088.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000072 | Absa 78 Field Street- Installation of Bl | Absa 78 Field Street- Installation of Blinds |  |  | Region 3 | KwaZulu-Natal | 77449X | 1000-71174-01 | 78 Field Street-Joe Slovo St-Durban |  | 2023-03-03 | 2023-03-31 |  | ASP-KZ0234 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-02 |  | 10330.45 | Approved at CB/BTB |  | 2023-03-09 | 2023-03-09 | 10330.45 | Approved | {"MANDT":"111","REFERENCE":90000072,"ONEVIEW":"77449X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-27","DATE07":"2023-04-26","DATE08":"2023-06-10","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-27","FORECAST_END":"2023-04-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000073706 | PHASE10 | 2023-03-27 | 2023-04-26 | NANDE MAQUBELA | Juanita Van Coller | 23000315 |  |  |  |  | 2023-03-14 | 8983 | 0 |  |  | C000073706 | 8983 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000073 | Absa Umlazi Mega City- Replace Carpets i | Absa Umlazi Mega City- Replace Carpets i |  |  | Region 3 | KwaZulu-Natal | 77729X | 1000-71191-01 | Umlazi Mega City-Griffiths Mxenge Highway-Umlazi |  | 2023-03-03 | 2023-03-31 |  | ASP-KZ0235 | REL BUDG AVAC SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L |  | NOMNGANGAL | 2023-02-02 |  | 46334 | Approved at CB/BTB |  | 2023-02-16 | 2023-02-16 | 46334 | Approved |  |  |  | C000069228 | PHASE06 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Juanita van Coller | 23000399 |  |  |  |  | 2023-02-20 | 40290.43 | 0 |  |  | C000069228 | 40290.43 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000074 | Absa Vryheid - Modificat | Absa Vryheid - Modification of Generator Exhaust |  |  | Region 3 | KwaZulu-Natal | 77113X | 1000-71614-01 | Absa Vryheid-Church St-Vryheid | N | 2023-03-03 | 2023-03-31 |  | ASP-KZ0236 | REL BUDG AVAC SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | F |  | NOMNGANGAL | 2023-02-03 |  | 17112.72 | Approved at CB/BTB |  | 2023-02-16 | 2023-02-16 | 17112.72 | Approved | {"MANDT":"111","REFERENCE":90000074,"ONEVIEW":"77113X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-02-13","DATE06":"2023-03-10","DATE07":"2023-03-15","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-10","FORECAST_END":"2023-03-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000067598 | PHASE10 | 2023-03-10 | 2023-03-15 | NANDE MAQUBELA | Juanita van Coller | 0 |  |  |  |  | 2023-02-13 | 14880.63 | 0 |  |  | C000067598 | 14880.63 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000075 | Absa House Pinetown - | Absa House Pinetown - Replacement of Parking boom |  |  | Region 3 | KwaZulu-Natal | 77102X | 1000-71156-01 | House Pinetown-Church Ln-Pinetown | Y | 2023-03-03 |  |  | ASP-KZ0237 | CRTD: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L | 2023-01-29 | NOMNGANGAL | 2023-02-16 |  | 17112.72 |  |  | 2023-02-13 | 2023-02-13 | 17112.72 | Supplier PO's were requested on the 13 February 2023 | {"MANDT":"111","REFERENCE":90000075,"ONEVIEW":"77102X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-04-02","DATE07":"2023-04-23","DATE08":"2023-06-07","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-02","FORECAST_END":"2023-04-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE02 | 2023-04-02 | 2023-04-23 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000076 | Absa Ridgeside - Replacement of HVAC Fil | Absa Ridgeside - Replacement of HVAC Filters |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2023-03-03 | 2023-03-31 |  | ASP-KZ0238 | REL BUDG AVAC SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-22 |  | 90278.22 | 2023.03.02: Approved by Kobus J vR 2023.02.28: Supported by Rob L |  | 2023-03-02 | 2023-03-02 | 90278.22 | Approved | {"MANDT":"111","REFERENCE":90000076,"ONEVIEW":"22460X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-20","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-29","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"189:28:7:0:35:17:31:45:25:0","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-20","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071699 | PHASE10 | 2023-03-20 | 2023-04-20 | NANDE MAQUBELA | Juanita Van Coller | 23000342 |  |  |  |  | 2023-03-03 | 78502.8 | 0 |  |  | C000071699 | 78502.8 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000077 | Absa Vryheid (Variation Order) - DILAPS | Absa Vryheid (Variation Order) - DILAPS |  |  | Region 3 | KwaZulu-Natal | 77113X | 1000-71614-01 | Absa Vryheid-Church St-Vryheid |  | 2023-03-30 |  |  | ASP-KZ0239 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | F |  | NOMNGANGAL | 2023-02-22 |  | 177370.77 | Approved at CB/BTB |  | 2023-02-23 | 2023-02-23 | 198370.77 | Approved |  |  |  | C000070300 | PHASE11 | 2023-03-01 | 2023-03-06 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-02-24 | 154235.45 | 0 |  |  | C000070300 | 154235.45 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000078 | Absa Tubatse Crossing - UPS Replacement | Absa Tubatse Crossing - UPS Replacement |  |  | Region 3 | Limpopo | 35151X | 1000-70488-01 | Tubatse Crossing-Cnr R37 R555-Burgers Fort | Y | 2023-03-01 | 2023-03-01 |  | ASP-LP0151 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L | 2023-01-30 | NOMNGANGAL | 2023-01-11 |  | 43763.25 |  | 60 | 2023-02-10 | 2023-02-10 | 43763.25 | Supplier PO's were requested on the 10 February 2023 | {"MANDT":"111","REFERENCE":90000078,"ONEVIEW":"35151X","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-25","DATE05":"2023-03-01","DATE06":"2023-03-01","DATE07":"2023-03-22","DATE08":"2023-05-06","DATE09":"2023-04-21","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-01","FORECAST_END":"2023-03-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"V29yayBjb21wbGV0ZWQgYW5kIGludm9pY2Ugc3VibWl0dGVkIG9uIHRoZSAyMSBBcHJpbCAyMDIz","RATING":""} |  |  | C000065693 | PHASE11 | 2023-03-01 | 2023-03-22 | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-02-02 | 38055 | 0 |  |  | C000065693 | 38055 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000079 | Absa 76E Schoeman Street | Absa 76E Schoeman Street- Purchase Porta |  |  | Region 3 | Limpopo | 76717X | 1000-70518-01 | 76E Schoeman Street-Schoeman St-Polokwane | Y | 2023-03-03 | 2023-03-31 |  | ASP-LP0152 | CRTD: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L | 2022-09-29 | NOMNGANGAL | 2023-01-25 |  | 0 | cancelled | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000079,"ONEVIEW":"76717X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE04 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000080 | Absa Makhado Crossing- H | Absa Makhado Crossing- HVAC compressor r |  |  | Region 3 | Limpopo | 37073X | 1000-70508-01 | Makhado Crossing Shopping Centre-Cnr Sibasa & N1 Main Rd-Makhado | Y | 2023-03-03 | 2023-03-30 |  | ASP-LP0153 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L | 2024-05-30 | NOMNGANGAL | 2023-01-29 |  | 65479.28 | Approved at CB/BTB | 100 | 2023-02-02 | 2023-02-02 | 65479.28 | Approved | {"MANDT":"111","REFERENCE":90000080,"ONEVIEW":"37033X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000066428 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-02-07 | 65479.28 | 0 |  |  | C000066428 | 56938.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000081 | Absa Bopedi Shopping Centre - Minor Work | Absa Bopedi Shopping Centre - Minor Work |  |  | Region 3 | Limpopo | 79106X | 1000-70553-01 | Bopedi Shopping Centre-Apel Rd-Apel |  | 2023-02-28 | 2023-03-31 |  | ASP-LP0154 | REL BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L |  | NOMNGANGAL | 2023-02-14 |  | 348128.52 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 348128.52 | Approved |  |  |  | C000071702 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000136 |  |  |  |  | 2023-03-03 | 348128.52 | 0 |  |  | C000071702 | 302720.45 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000082 | Absa Twin City Burgersfort - Minor Works | Absa Twin City Burgersfort - Minor Works |  |  | Region 3 | Limpopo | 36240X | 1000-70501-01 | Twin City Burgers Fort-Cnr Dirk Winterbach & Kruis St-Burgers Fort |  | 2023-02-28 | 2023-03-31 |  | ASP-LP0155 | REL BUDG AVAC SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L |  | NOMNGANGAL | 2023-02-14 |  | 451397.15 | Approved at CB/BTB | 1 | 2023-03-02 | 2023-03-02 | 451397.15 | Approved |  |  |  | C000071700 | PHASE12 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Juanita van Coller | 23000165 |  |  |  |  | 2023-03-03 | 451397.15 | 0 |  |  | C000071700 | 392519.26 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000083 | Absa Mall of the North - Minor Works | Absa Mall of the North - Minor Works |  |  | Region 3 | Limpopo | 21853X | 1000-70461-01 | Mall Of The North-Cnr R81 & N1-Polokwane |  | 2023-02-28 | 2023-03-31 |  | ASP-LP0156 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L |  | NOMNGANGAL | 2023-02-14 |  | 233111.05 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 233111.05 | Approved |  |  |  | C000124779 | PHASE11 | 2023-08-14 | 2023-08-14 | NANDE MAQUBELA | Floyd Mofokeng | 23000199 |  |  |  |  | 2023-11-20 | 23165.72 | 0 |  |  | C000071697 | 202705.26 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000084 | Absa Lephalale Mall - | Absa Lephalale Mall - Minor Works |  |  | Region 3 | Limpopo | 36103X | 1000-70666-01 | Lephalale Mall-Cnr Nelson Mandela Dr & Chris Hani Ave-Lephalale | Y | 2023-02-28 |  |  | ASP-LP0157 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L | 2023-09-29 | NOMNGANGAL | 2023-02-14 |  | 185519.63 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 185519.63 | Approved | {"MANDT":"111","REFERENCE":90000084,"ONEVIEW":"36103X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-01-24","DATE04":"2023-01-24","DATE05":"2023-02-28","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071696 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Buhle Qwabe | 0 |  |  |  |  | 2023-03-03 | 185519.62 | 0 |  |  | C000071696 | 161321.41 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000085 | Absa Limpopo Mall - Minor Works | Absa Limpopo Mall - Minor Works |  |  | Region 3 | Limpopo | 78979X | 1000-70547-01 | Limpopo Mall-Cnr Rissik, Market, Devenish & Kerk St-Polokwane |  | 2023-02-28 | 2023-03-31 |  | ASP-LP0158 | TECO BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L |  | NOMNGANGAL | 2023-02-14 |  | 207758.96 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 207758.96 | Approved |  |  |  | C000124778 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000207 |  |  |  |  | 2023-11-20 | 24108.9 | 0 |  |  | C000071701 | 180659.96 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000086 | Absa Lephalale - Minor Works | Absa Lephalale - Minor Works |  |  | Region 3 | Limpopo | 76789X | 1000-70525-01 | Absa Lephalale-Cnr Strydom & Fox Odendaal St-Lephalale | Y | 2023-02-28 | 2023-03-31 |  | ASP-LP0159 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L | 2023-09-29 | NOMNGANGAL | 2023-02-14 |  | 0 | 2023.06.15: Approved by Conrad M as per email 2023.06.13: Supported by Judith B & Ilana vdW | 100 | 2023-06-15 | 2023-06-15 | 356505.79 | Approved | {"MANDT":"111","REFERENCE":90000086,"ONEVIEW":"36103X","DATE01":"2022-12-20","DATE02":"2023-03-20","DATE03":"2023-04-10","DATE04":"2023-06-09","DATE05":"2023-06-15","DATE06":"2023-07-14","DATE07":"2023-07-14","DATE08":"2023-07-31","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-14","FORECAST_END":"2023-07-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"VTI1aFoyZHBibWNsTWpCcGJpVXlNSEJ5YjJkeVpYTno=","RATING":""} |  |  | C000092902 | PHASE11 | 2023-07-14 | 2023-07-14 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-20 | 356505.78 | 0 |  |  | C000092902 | 310005.03 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000087 | Absa Thaba Mall - Minor Works | Absa Thaba Mall - Minor Works |  |  | Region 3 | Limpopo | 37045X | 1000-70507-01 | Thaba Mall-Cnr Warmbad Weg Rd & R510-Thabazimbi |  | 2023-02-28 |  |  | ASP-LP0160 | CLSD ISBD AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 302151.25 | Reinstated by region | 100 | 2023-09-26 | 2023-09-28 | 302151.25 |  | {"MANDT":"111","REFERENCE":90000087,"ONEVIEW":"37045X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-09-04","DATE04":"2023-01-24","DATE05":"2023-09-11","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q29zdGluZyBzaGFyZWQgd2l0aCByZWdpb24gZm9yIGFwcHJvdmFsIC1wcm9qZWN0IHJlb3BlbmVkIGZvciAyMDIz","RATING":""} |  |  | C000114113 | PHASE11 | 2023-10-13 | 2023-10-16 | NANDE MAQUBELA | Floyd Mofokeng | 23000231 |  |  |  |  | 2023-10-03 | 262740.22 | 0 |  |  | C000114113 | 262740.22 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000088 | Absa Mokopane - Minor Works | Absa Mokopane - Minor Works |  |  | Region 3 | Limpopo | 76721X | 1000-70668-01 | Mokopane-Thabo Mbeki St-Mokopane |  | 2023-02-28 | 2023-03-31 |  | ASP-LP0161 | REL BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 177971.43 | 2023.04.05: Approved by Conrad M 2023.04.04: Supported by Winston P & Ilana vdW | 100 | 2023-04-06 | 2023-04-06 | 177971.43 | Approved |  |  |  | C000089457 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Floyd Mofokeng | 23000247 |  |  |  |  | 2023-06-05 | 370768.77 | 0 |  |  | C000078698 | 154757.76 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000089 | Absa Pioneer Centre - Minor Works | Absa Pioneer Centre - Minor Works |  |  | Region 3 | Limpopo | 76790X | 1000-70669-01 | Pioneer Centre-Schoeman St-Polokwane |  | 2023-02-28 | 2023-03-31 |  | ALP-LP0201 | REL BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 887569.73 | Legal documents to be submitted for approval | 70 | 2023-09-14 | 2023-07-28 | 887569.73 |  | {"MANDT":"111","REFERENCE":90000089,"ONEVIEW":"76790X","DATE01":"2022-12-20","DATE02":"2023-03-16","DATE03":"2023-03-24","DATE04":"2023-07-07","DATE05":"2023-07-14","DATE06":"2023-07-31","DATE07":"2023-08-11","DATE08":"2023-08-25","DATE09":"2023-09-29","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-31","FORECAST_END":"2023-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TGVnYWwgZG9jdW1lbnRzIHRvIGJlIHNoYXJlZCBmb3IgYXBwcm92YWwuClBsYW5uaW5nIHBoYXNl","RATING":""} |  |  | C000119032 | PHASE07 | 2023-07-31 | 2024-01-05 | NANDE MAQUBELA | Floyd Mofokeng | 23000266 | 2023-10-02 |  |  |  | 2023-10-25 | 771799.77 | 0 |  |  | C000140803 | 771799.77 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000090 | Absa Secunda Mall- UPS Replacement | Absa Secunda Mall- UPS Replacement |  |  | Region 3 | Mpumalanga | 35155X | 1000-70582-01 | Checkers Mall Secunda-Rautenbach St-Secunda |  | 2023-03-01 | 2023-03-01 |  | ASP-MP0146 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-11 |  | 3736.78 | Approved | 100 | 2023-10-07 | 2023-10-07 | 42972.97 |  |  |  |  | C000065696 | PHASE11 | 2023-03-01 | 2023-03-22 | NANDE MAQUBELA | Thea Spamers | 23000237 |  |  |  |  | 2023-02-02 | 42972.97 | 0 |  |  | C000065696 | 37367.8 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000091 | Absa Nelspruit (Absa Squ | Absa Nelspruit (Absa Square) - Dilapidat |  |  | Region 3 | Mpumalanga | 77878X | 1000-70683-01 | Absa, Square-Paul Kruger St-Nelspruit | Y | 2023-02-28 |  |  | ASP-MP0147 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  | L | 2024-12-30 | NOMNGANGAL | 2023-01-12 |  | 119294.68 | Approved at CB/BTB | 100 | 2023-01-16 | 2023-01-16 | 119294.68 | Approved | {"MANDT":"111","REFERENCE":90000091,"ONEVIEW":"77878X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-01-24","DATE04":"2023-01-24","DATE05":"2023-02-28","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIDEgb2YgMiBzdWJtaXR0ZWQgb24gMjEgQXByaWwgMjAyMw==","RATING":""} |  |  | C000061642 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-01-16 | 119294.69 | 0 |  |  | C000149575 | 103734.51 |  | 3657.47 |  | 0 | 0 |  | 0 |  | 0
90000092 | Absa Acornhoek Mall- Minor Works | Absa Acornhoek Mall- Minor Works |  |  | Region 3 | Mpumalanga | 37053X | 1000-70593-01 | Acornhoek Mall-Greenvalley Extension 1-Acornhoek |  | 2023-02-28 |  |  | ASP-MP0148 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 93848.41 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 93848.41 | Approved | {"MANDT":"111","REFERENCE":90000092,"ONEVIEW":"37053X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-01-24","DATE04":"2023-01-24","DATE05":"2023-02-28","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000073595 | PHASE11 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | Thea Spamers | 23000403 |  |  |  |  | 2023-03-13 | 93848.42 | 0 |  |  | C000073595 | 81607.32 | CIP2023XP | 7931.67 |  | 0 | 0 |  | 0 |  | 0
90000093 | Absa Mkhuhlu-Minor Works | Absa Mkhuhlu-Minor Works |  |  | Region 3 | Mpumalanga | 77974X | 1000-70646-01 | Mkhuhlu Mall-Kruger Gate Rd-Mkhuhlu |  | 2023-02-28 | 2023-03-31 |  | ASP-MP0149 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 125919.65 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 125919.65 | Approved |  |  |  | C000073606 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Thea Spamers | 23000291 |  |  |  |  | 2023-03-13 | 125919.65 | 0 |  |  | C000073606 | 109495.35 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000094 | Absa Matsamo Plaza- Minor Works | Absa Matsamo Plaza- Minor Works |  |  | Region 3 | Mpumalanga | 77316X | 1000-70622-01 | Matsamo Plaza-Cnr R570 & R323 Rd-Matsamo |  | 2023-02-28 | 2023-03-31 |  | ASP-MP0150 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 47435.62 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 47435.62 | Approved | {"MANDT":"111","REFERENCE":90000094,"ONEVIEW":"77316X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-01-24","DATE04":"2023-01-24","DATE05":"2023-02-28","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000073594 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Thea Spamers | 23000293 |  |  |  |  | 2023-03-13 | 47435.63 | 0 |  |  | C000073594 | 41248.37 |  | 3939.6 |  | 0 | 0 |  | 0 |  | 0
90000095 | Absa Ingwe Mall - Minor Works | Absa Ingwe Mall - Minor Works |  |  | Region 3 | Mpumalanga | 37008X | 1000-70592-01 | Ingwe Mall-Impala St-Malelane |  | 2023-03-30 | 2023-03-31 |  | ASP-MP0151 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 116812.18 | Approved at CB/BTB | 100 | 2023-03-09 | 2023-03-09 | 116812.18 | Approved | {"MANDT":"111","REFERENCE":90000095,"ONEVIEW":"37008X","DATE01":"2023-01-19","DATE02":"2023-02-16","DATE03":"2023-02-23","DATE04":"2023-02-23","DATE05":"2023-03-30","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":89,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjE6MDcuMjMgQVMgOiBDaGFuZ2VkIHRoZSBzdGF0dXMgb24gQmlsbGluZyBhbmQgQ2FzaGZsb3cgdG8gcGFydGlhbGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000123787 | PHASE11 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Thea Spamers | 23000313 |  |  |  |  | 2023-11-15 | 14254.81 | 0 |  |  | C000073562 | 101575.81 | CIP2023XP | 10328.38 |  | 0 | 0 |  | 0 |  | 0
90000096 | Absa Kabokweni Plaza- Minor Works | Absa Kabokweni Plaza- Minor Works |  |  | Region 3 | Mpumalanga | 78671X | 1000-70657-01 | Kabokweni Plaza-Cnr Kabokweni & Palaston Rd-White River |  | 2023-02-28 | 2023-03-31 |  | ASP-MP0152 | CRTD: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 0 | Cancelled by the Region | 1 |  |  | 0 | [5 empty] | PHASE04 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Thea Spamers | 23000260 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000097 | Absa Thulamahashe - Minor Works | Absa Thulamahashe - Minor Works |  |  | Region 3 | Mpumalanga | 79265X | 1000-70559-01 | Thulamahashe Plaza-Main Rd-Phalaborwa |  | 2023-02-28 | 2023-03-31 |  | ASP-MP0153 | REL AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 0 | Cancelled by the Region | 1 |  |  | 0 | Branch to be re-allocated | {"MANDT":"111","REFERENCE":90000097,"ONEVIEW":"79265X","DATE01":"2022-12-20","DATE02":"2023-01-17","DATE03":"2023-01-24","DATE04":"2023-01-24","DATE05":"2023-02-28","DATE06":"2023-03-31","DATE07":"2023-04-21","DATE08":"2023-06-05","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxsZWQgYnkgdGhlIHJlZ2lvbg==","RATING":""} |  |  |  | PHASE12 | 2023-03-31 | 2023-04-21 | NANDE MAQUBELA | Thea Spamers | 23000362 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000098 | Absa Spar Centre Lydenburg - Minor Works | Absa Spar Centre Lydenburg - Minor Works |  |  | Region 3 | Mpumalanga | 77360X | 1000-70623-01 | Spar Centre Lydenburg-Cnr Voortrekker & Viljoen St-Lydenburg |  | 2023-02-28 |  |  | ASP-MP0154 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 302119.11 | 2023.07.13: Approved by Conrad M | 100 | 2023-07-13 | 2023-07-13 | 302119.11 | Approved |  |  |  | C000098569 | PHASE11 | 2023-08-11 | 2023-08-11 | NANDE MAQUBELA | Thea Spamers | 23000206 |  |  |  |  | 2023-07-18 | 302119.11 | 0 |  |  | C000098569 | 262712.27 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000099 | Absa Kriel Mall - Minor Works | Absa Kriel Mall - Minor Works |  |  | Region 3 | Mpumalanga | 77028X | 1000-70606-01 | Kriel Mall-Bronwyn St-Kriel |  | 2023-05-02 |  |  | ASP-MP0155 | REL AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 0 | Cancelled by the Region | 1 |  |  | 0 | [5 empty] | PHASE04 | 2023-06-01 | 2023-06-22 | NANDE MAQUBELA | Thea Spamers | 23000235 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000100 | Absa Volksrust - Minor Works | Absa Volksrust - Minor Works |  |  | Region 3 | Mpumalanga | 77566X | 1000-70636-01 | Absa Volksrust-Joubert St-Volksrust |  | 2023-05-02 |  |  | ALP-MP0207 | CRTD: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-14 |  | 569351.03 | Minor Works - Enhancement | 90 | 2023-08-24 | 2023-08-31 | 569351.03 |  | {"MANDT":"111","REFERENCE":90000100,"ONEVIEW":"77566X","DATE01":"2023-02-21","DATE02":"2023-05-05","DATE03":"2023-06-15","DATE04":"2023-06-23","DATE05":"2023-07-07","DATE06":"2023-08-18","DATE07":"2023-08-18","DATE08":"2023-08-31","DATE09":"2023-09-29","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-18","FORECAST_END":"2023-08-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TGVnYWwgZG9jdW1lbnRzIGluIHByb2dyZXNz","RATING":""} |  |  |  | PHASE10 | 2023-10-02 | 2023-10-16 |  |  | 23000210 | 2023-10-02 | 2023-10-05 | 2023-10-06 |  |  | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000101 | Absa WC Various Branches - Decals Replac | Absa WC Various Branches - Decals Replac |  |  | Region 2 | Western Cape | Various |  | Various Sites WC |  | 2023-03-31 | 2023-04-30 |  | ASP-N00049 | CRTD AVAC: |  | false | true |  | Nyasha Wena |  |  | 0 |  | U |  | CEASARS | 2023-02-07 |  | 140301.2 |  | 100 | 2023-02-22 | 2023-03-03 | 140301.2 |  | {"MANDT":"111","REFERENCE":90000101,"ONEVIEW":"Various","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-03","DATE06":"2023-03-31","DATE07":"2023-06-02","DATE08":"2023-06-15","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071694 | PHASE10 | 2023-03-31 | 2023-06-02 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-03-03 | 122001.04 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000102 | Various- Power Quality Meter fleet management | Various- Power Quality Meter fleet management |  |  | Energy | National | Various | Various | Various Sites | U | 2023-03-01 | 2023-12-15 |  | ASP-N00050 | CLSD BUDG AVAC RESA SETC: |  | N | true |  | Wesigye Mukuru |  | 13 x Power Quality Meters spread across 6 sites | 0 |  | U |  | LOUISR | 2023-02-21 |  | 452088 | Approval granted due to the fact that the 13 x meters were not available online. Meters have subsequently brought back onto a portal accessible by Abs CRES and BFM Engineering and BFM Utilities | 100 | 2023-02-16 | 2023-02-28 | 452088 | WA not applicable. Approval granted due to the fact that the 13 x meters were not available online. Meters have subsequently brought back onto a portal accessible by Abs CRES and BFM Engineering and BFM Utilities | {"MANDT":"111","REFERENCE":90000102,"ONEVIEW":"Various","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-02-15","DATE05":"2023-03-01","DATE06":"2023-12-15","DATE07":"2022-03-22","DATE08":"2022-05-06","DATE09":"2022-05-16","DATE10":"2022-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"435:28:7:21:14:289:-633:45:10:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-15","FORECAST_END":"2022-03-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"VGhlIFNPVyBpcyB0byByZWluc3RhdGUgdGhlIGN1cnJlbnQgbWV0ZXJzIGFjY2VzcyBwb3J0YWwgYW5kIG5vIHBoeXNpY2FsIHdvcmsgaXMgdG8gYmUgZG9uZSBvbiBzaXRl","RATING":"Low"} |  |  | C000071663 | PHASE11 | 2023-12-15 | 2022-03-22 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-03-03 | 452088 | 0 |  |  | C000071663 | 393120 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000103 | Absa Moorreesburg - UPS Installation | Absa Moorreesburg - Installation of 15KVA stand alone UPS | bnVsbCA%3D |  | Region 2 | Western Cape | 77249X | 1000-70811-01 | Absa Moorreesburg-Cnr Main & Long St-Moorreesburg | N | 2023-03-31 | NaNN------ |  | ASP-WC0257 | CLSD BUDG AVAC RESA SETC: | SAP_018 | false | false | null | Nyasha Wena | na | null | 0 |  | U |  | CEASARS | 2023-01-24 |  | 107822.86 | 2023.04.26: Approved by Kobus JvR as per email 2023.04.25: Supported by Rob L | 100 | 2023-04-26 | 2023-04-26 | 107822.86 | Approved | {"MANDT":"111","REFERENCE":90000103,"ONEVIEW":"77249X","DATE01":"2023-01-19","DATE02":"2023-02-06","DATE03":"2023-04-19","DATE04":"2023-04-26","DATE05":"2023-04-26","DATE06":"2023-06-05","DATE07":"2023-06-27","DATE08":"2023-07-17","DATE09":"2023-07-26","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:18:72:7:0:40:22:20:9:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-05","FORECAST_END":"2023-06-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTcgSnVseSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000082138 | PHASE11 | 2023-06-05 | 2023-06-27 | RODERICK NEVAY | Michael Maluleka | 23000252 |  |  |  |  | 2023-04-26 | 93759.01 | 0 |  |  | C000082138 | 93759.01 | CIP2023XP | 9592.99 |  | 0 | 0 |  | 0 |  | 0
90000104 | Absa Die Kunshuis Clanwilliam - HVAC Upg | Absa Die Kunshuis Clanwilliam - HVAC Upgrade | bnVsbCA%3D |  | Region 2 | Western Cape | 77526X | 1000-70836-01 | Die Kunshuis-Main Rd-Clanwilliam | Y | 2023-03-31 | NaNN------ |  | ASP-WC0258 | CLSD BUDG AVAC RESA SETC: | SAP_018 | false | false | null | Nyasha Wena | na | null | 0 |  | L |  | CEASARS | 2023-01-24 |  | 379363.09 | Approved at CB/BTB | 100 | 2023-02-16 | 2023-02-16 | 379363.09 | Approved | {"MANDT":"111","REFERENCE":90000104,"ONEVIEW":"77526X","DATE01":"2023-01-20","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-16","DATE05":"2023-02-16","DATE06":"2023-03-13","DATE07":"2023-03-24","DATE08":"2023-04-19","DATE09":"2023-06-03","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"131:3:21:3:0:25:11:26:45:2","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-13","FORECAST_END":"2023-03-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgQXByaWwgLSBGaW5hbCBQT0MgU3VibWl0dGVk","RATING":"Low"} |  |  | C000069876 | PHASE11 | 2023-03-13 | 2023-03-24 | RODERICK NEVAY | Michael Maluleka | 23000141 |  |  |  |  | 2023-02-22 | 329880.95 | 0 |  |  | C000069876 | 329880.95 | CIP2023XP | 17722.05 |  | 0 | 0 |  | 0 |  | 0
90000105 | Absa Piketberg - Minor Works | Absa Piketberg - Minor Works |  |  | Region 2 |  | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg |  | 2023-03-31 |  |  | ASP-WC0259 | REL DLFL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  |  |  | CEASARS | 2023-01-24 |  | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000106 | Absa Brackenfell - LED Replacement | Absa Brackenfell - LED Replacement |  |  | Region 2 | Western Cape | 77848X | 1000-70862-01 | Brackenfell Shopping Centre-Old Paarl Rd-Brackenfell | Y | 2023-02-01 |  |  | ASP-WC0260 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-01-27 |  | 226566.54 | Approved at CB/BTB | 100 | 2023-01-30 | 2023-02-02 | 226566.54 | Approved | {"MANDT":"111","REFERENCE":90000106,"ONEVIEW":"77848X","DATE01":"2023-01-09","DATE02":"2023-01-09","DATE03":"2023-01-27","DATE04":"2023-01-30","DATE05":"2023-01-30","DATE06":"2023-02-02","DATE07":"2023-02-06","DATE08":"2023-03-13","DATE09":"2023-04-27","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:18:3:0:3:4:35:45:20","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-02","FORECAST_END":"2023-02-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgTWFyIFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZQ==","RATING":"Low"} |  |  | C000066426 | PHASE11 | 2023-02-02 | 2023-02-06 | RODERICK NEVAY | Michael Maluleka | 23000492 |  |  |  |  | 2023-02-07 | 197014.39 | 0 |  |  | C000066426 | 197014.39 | CIP2023XP | 20542.41 |  | 0 | 0 |  | 0 |  | 0
90000107 | Absa Lower Long - Generator Batteries | Absa Lower Long - Generator Batteries |  |  | National | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | Y | 2023-03-13 |  |  | ASP-WC0261 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 0 |  | F |  | CEASARS | 2023-02-01 |  | 20517.84 | 2023.05.31: Approved by Kobus JvR as per email 2023.05.30: Supported by Rob L |  | 2023-06-01 | 2023-06-01 | 20517.84 | Approved | {"MANDT":"111","REFERENCE":90000107,"ONEVIEW":"77657X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-06","DATE05":"2023-02-27","DATE06":"2023-03-13","DATE07":"2023-05-31","DATE08":"2023-06-21","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:7:21:7:21:14:79:21:45:13","PROGRESS":56,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-13","FORECAST_END":"2023-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTAvMDcvMjAyMy0gUHJvamVjdCBpbiBwcm9ncmVzcw==","RATING":"Medium"} |  |  | C000089062 | PHASE11 | 2023-03-13 | 2023-05-31 | LUCIA AMUNGA | Thea Spamers | 23000424 |  |  |  |  | 2023-06-01 | 17841.6 | 0 |  |  | C000089062 | 17841.6 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000108 | Absa Lower Long - Creation of storerooms | Absa Lower Long - Creation of storerooms and Restroom in Basement |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | N | 2023-03-31 |  |  | ASP-WC0262 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | F |  | CEASARS | 2023-02-01 |  | 215701.9 | 2023.04.25: Approved by Conrad M as per email 2023.04.25: Supported by Judith B | 100 | 2023-04-27 | 2023-04-26 | 215701.9 | Approved | {"MANDT":"111","REFERENCE":90000108,"ONEVIEW":"77657X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-04-17","DATE04":"2023-04-26","DATE05":"2023-04-27","DATE06":"2023-05-25","DATE07":"2023-07-06","DATE08":"2023-07-31","DATE09":"2023-09-14","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"253:7:80:9:1:28:42:25:45:20","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-25","FORECAST_END":"2023-07-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgSnVseSBTaWduZWQgUE9DIHJlY2VpdmVkIGFuZCBTdWJtaXR0ZWQgdG8gRmluYW5jZQoxOSBKdWx5IFBPQyBTaWdub2ZmIGluIFByb2dyZXNz","RATING":"Low"} |  |  | C000082135 | PHASE11 | 2023-05-25 | 2023-07-06 | RODERICK NEVAY | Michael Maluleka | 23000214 |  |  |  |  | 2023-05-03 | 187566.87 | 0 |  |  | C000082135 | 187566.87 | CIP2023XP | 19565.63 |  | 0 | 0 |  | 0 |  | 0
90000109 | Absa WC Various Branches - Decals Replac | Absa WC Various Branches - Decals Replac |  |  | Region 2 | Western Cape | Various |  | Various Sites WC |  | 2023-03-13 |  |  | ASP-WC0263 | CRTD BUDG: |  | false | true |  | Nyasha Wena |  |  | 0 |  |  |  | CEASARS | 2023-02-07 |  | 140301.2 |  | 1 | 2023-02-22 |  | 0 | Was approved and processed against ALP-N00039 - FM Smalls - Final POC against above submitted 15 June | {"MANDT":"111","REFERENCE":90000109,"ONEVIEW":"Various","DATE01":"2023-02-01","DATE02":"2023-02-08","DATE03":"2023-01-29","DATE04":"2023-02-05","DATE05":"2023-03-03","DATE06":"2023-05-01","DATE07":"2023-06-02","DATE08":"2023-06-15","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:-10:7:26:59:32:13:15:13","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-01","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  |  | PHASE10 | 2023-05-01 | 2023-06-02 |  |  | 0 |  |  |  |  | 2023-03-07 | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000110 | Absa Saldanha - Shopfront Privacy | Absa Saldanha - Shopfront Privacy |  |  | Region 2 | Western Cape | 77766X | 1000-70856-01 | Simphiwe Building-Saldanha Rd-Saldanha | N | 2023-03-13 |  |  | ASP-WC0264 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-02-07 |  | 57657.38 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 57657.38 | Approved | {"MANDT":"111","REFERENCE":90000110,"ONEVIEW":"77766X","DATE01":"2023-02-02","DATE02":"2023-02-09","DATE03":"2023-02-22","DATE04":"2023-03-02","DATE05":"2023-03-02","DATE06":"2023-04-24","DATE07":"2023-04-24","DATE08":"2023-05-04","DATE09":"2023-06-18","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:13:8:0:53:0:10:45:4","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-24","FORECAST_END":"2023-04-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXkgUE9DIHN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Low"} |  |  | C000072021 | PHASE11 | 2023-04-24 | 2023-04-24 | RODERICK NEVAY | Michael Maluleka | 23000585 |  |  |  |  | 2023-03-06 | 50136.85 | 0 |  |  | C000071669 | 50136.85 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000111 | Absa Cape Gate - Replace 3 Condensers | Absa Cape Gate - Replace 3 Condensers |  |  | Region 2 | Western Cape | 77288X | 1000-71432-01 | CapeGate Shopping Centre-Cnr Okavango & De Bron Rd-Brackenfell | N | 2023-03-31 |  |  | ASP-WC0265 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-02-07 |  | 446435.5 | Approved at CB/BTB | 100 | 2023-02-10 | 2023-02-16 | 446435.5 | Contingency Remaining R 22 105.66 Incl Vat | {"MANDT":"111","REFERENCE":90000111,"ONEVIEW":"77288X","DATE01":"2023-01-20","DATE02":"2023-01-20","DATE03":"2023-02-09","DATE04":"2023-02-10","DATE05":"2023-02-10","DATE06":"2023-02-27","DATE07":"2023-04-14","DATE08":"2023-04-19","DATE09":"2023-05-29","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"161:0:20:1:0:17:46:5:40:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-04-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgQXByaWwgLSBGaW5hbCBQT0MgU3VibWl0dGVk","RATING":"Low"} |  |  | C000067571 | PHASE11 | 2023-02-27 | 2023-04-14 | RODERICK NEVAY | Michael Maluleka | 23000125 |  |  |  |  | 2023-02-13 | 388204.78 | 0 |  |  | C000067571 | 388204.78 | CIP2023XP | 40511.41 |  | 0 | 0 |  | 0 |  | 0
90000112 | Absa 132 Adderley Street - Signage Removal | Absa 132 Adderley Street - Building Signage Removal |  |  | Region 2 | Western Cape | 76935X | 1000-70789-01 | Absa Adderley Street-Adderley St-Cape Town | N | 2023-03-31 |  |  | ASP-WC0266 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-02-15 |  | 3547.91 | Approved at CB/BTB | 100 | 2023-02-20 | 2023-02-15 | 3547.91 | Approved | {"MANDT":"111","REFERENCE":90000112,"ONEVIEW":"76935X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-20","DATE05":"2023-02-20","DATE06":"2023-03-02","DATE07":"2023-03-03","DATE08":"2023-03-09","DATE09":"2023-04-23","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:7:21:3:0:10:1:6:45:26","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-02","FORECAST_END":"2023-03-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OSBNYXIgLSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000069656 | PHASE11 | 2023-03-02 | 2023-03-03 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-02-22 | 3085.14 | 0 |  |  | C000069656 | 3085.14 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000113 | Absa Paarl Main - Dilaps | Absa Paarl Main - Dilaps - For PMO Project |  |  | Region 2 | Western Cape | 77053X | 1000-70798-01 | Absa Paarl-Cnr Main & Nantes St-Paarl | N | 2023-03-13 |  |  | ASP-WC0267 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | F |  | CEASARS | 2023-02-20 |  | 25601.67 | Approved at CB/BTB | 100 | 2023-02-22 | 2023-02-21 | 25601.67 | Approved | {"MANDT":"111","REFERENCE":90000113,"ONEVIEW":"77053X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-22","DATE05":"2023-02-22","DATE06":"2023-03-06","DATE07":"2023-03-06","DATE08":"2023-03-13","DATE09":"2023-04-27","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"149:7:21:23:0:12:0:7:45:20","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-06","FORECAST_END":"2023-03-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgTWFyIFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZSA=","RATING":"Low"} |  |  | C000069974 | PHASE11 | 2023-03-06 | 2023-03-06 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-02-22 | 22262.32 | 0 |  |  | C000069974 | 22262.32 |  | 1486.26 |  | 0 | 0 |  | 0 |  | 0
90000114 | Absa Corner Church Stree | Absa Corner Church Street & Johanna-2nd |  |  | Region 3 | North West | 37181X | 1000-77497-01 | Corner of Church Street and Johanna Van Der Merwe Streets | Y | 2023-03-03 | 2023-03-30 |  | ALP-CR0025 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2026-09-29 | NOMNGANGAL | 2023-01-25 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000114,"ONEVIEW":"37181X","DATE01":"2022-12-23","DATE02":"2023-01-20","DATE03":"2023-01-27","DATE04":"2023-01-27","DATE05":"2023-03-03","DATE06":"2023-03-30","DATE07":"2023-04-20","DATE08":"2023-06-04","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE02 | 2023-03-30 | 2023-04-20 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000115 | Absa Odendaalsrus Minor Refresh | Absa Odendaalsrus Minor Refresh |  |  | Region 3 | Free State | 79056X | 1000-71599-01 | Absa Odendaalsrus-Odendaal St-Odendaalsrus |  | 2023-02-23 | 2023-03-23 |  | ALP-CR0026 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-26 |  | 1854522.73 | Absa Direct Supplier Simanyene: Contract Value: R1 101 426,05 incl.VAT | 100 | 2023-03-16 | 2023-03-16 | 1854522.73 | Approved | {"MANDT":"111","REFERENCE":90000115,"ONEVIEW":"79056X","DATE01":"2022-12-15","DATE02":"2023-01-12","DATE03":"2023-01-19","DATE04":"2023-01-19","DATE05":"2023-03-16","DATE06":"2023-04-13","DATE07":"2023-05-04","DATE08":"2023-06-18","DATE09":"2023-06-21","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":32,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-13","FORECAST_END":"2023-05-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIER1cGxpY2F0ZS4=","RATING":""} |  |  | C000095867 | PHASE11 | 2023-04-13 | 2023-05-04 | NANDE MAQUBELA | Juanita Van Coller | 23000027 | 2023-03-20 | 2023-06-21 | 2023-03-17 | 2023-03-20 | 2023-07-04 | 1612628.45 | 0 |  |  | C000095867 | 1612628.45 | CIP2023XP | 138375.66 |  | 0 | 0 |  | 0 |  | 0
90000116 | Absa Viljoenskroon | Absa Viljoenskroon |  |  | Region 3 | Free State | 78481X | 1000-71540-01 | Viljoenskroon-Cnr Engelbrecht & Church St-Viljoenskroon |  | 2023-03-01 | 2023-03-28 |  | ALP-CR0027 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-01 |  | 0 |  | 1 |  |  | 0 | Duplicate | {"MANDT":"111","REFERENCE":90000116,"ONEVIEW":"78481X","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-01-25","DATE05":"2023-03-01","DATE06":"2023-03-28","DATE07":"2023-04-18","DATE08":"2023-06-02","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-28","FORECAST_END":"2023-04-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLiBEdXBsaWNhdGUu","RATING":""} |  |  |  | PHASE12 | 2023-03-28 | 2023-04-18 | NANDE MAQUBELA | Floyd Mofokeng | 23000035 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000117 | Absa Douglas | Absa Douglas |  |  | Region 3 | Northern Cape | 78432X |  | Douglas Spar Shopping Centre-Cnr Arnot & Loch St-Kimberley |  | 2023-03-02 | 2023-04-04 |  | ALP-CR0028 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-09 |  | 0 |  | 1 |  |  | 0 | Duplicate | {"MANDT":"111","REFERENCE":90000117,"ONEVIEW":"78432X","DATE01":"2022-12-22","DATE02":"2023-01-19","DATE03":"2023-01-26","DATE04":"2023-01-26","DATE05":"2023-03-02","DATE06":"2023-04-04","DATE07":"2023-04-25","DATE08":"2023-06-09","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-04","FORECAST_END":"2023-04-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLiBEdXBsaWNhdGUu","RATING":""} |  |  |  | PHASE12 | 2023-04-04 | 2023-04-25 | NANDE MAQUBELA | Floyd Mofokeng | 23000183 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000118 | Absa Reitz | Absa Reitz |  |  | Region 3 | Free State | 78402X | 1000-71587-01 | Absa Reitz-Church St-Reitz | Y | 2023-04-03 | 2023-04-24 |  | ALP-CR0029 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | L | 2023-11-29 | MOKOENAM2 | 2023-02-28 |  | 1140559.15 | Approved at CB/BTB | 100 | 2023-04-20 | 2023-04-20 | 1140559.15 | Approved | {"MANDT":"111","REFERENCE":90000118,"ONEVIEW":"78402X","DATE01":"2023-01-23","DATE02":"2023-02-20","DATE03":"2023-02-27","DATE04":"2023-02-27","DATE05":"2023-04-03","DATE06":"2023-04-24","DATE07":"2023-05-15","DATE08":"2023-06-13","DATE09":"2023-06-14","DATE10":"2023-06-30","DATE11":"2023-06-14","DATE12":"2023-06-14","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":80,"PROG06":50,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"158:28:7:0:35:21:21:29:1:0","PROGRESS":39,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-24","FORECAST_END":"2023-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"V0ErU0ZBLiBGaW5hbmNpYWwgcm9sbG92ZXIu","RATING":""} |  |  | C000120732 | PHASE10 | 2023-04-24 | 2023-05-15 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-02 | 964191.79 | 0 |  |  | C000140958 | 964191.79 |  | 6719.21 |  | 0 | 0 |  | 0 |  | 0
90000119 | Absa Vrede | Absa Vrede |  |  | Region 3 | Free State | 77122X | 1000-71531-01 | Absa Vrede-Church St-Vrede |  | 2023-04-03 | 2023-04-24 |  | ALP-CR0030 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-28 |  | 1177792.65 | Absa Direct Supplier Basathi Construction and Projects: Contract Value: R1 101 426,05 incl.VAT | 100 | 2023-03-16 | 2023-03-16 | 1177792.65 | Approved | {"MANDT":"111","REFERENCE":90000119,"ONEVIEW":"77122X","DATE01":"2023-01-23","DATE02":"2023-02-20","DATE03":"2023-02-27","DATE04":"2023-02-27","DATE05":"2023-04-03","DATE06":"2023-04-24","DATE07":"2023-11-13","DATE08":"2023-12-28","DATE09":"2023-12-29","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"158:28:7:0:35:21:203:45:1:0","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-24","FORECAST_END":"2023-11-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U0ZBK1dBLiBGaW5hbmNpYWwgcm9sbG92ZXIu","RATING":""} |  |  | C000098084 | PHASE06 | 2023-04-24 | 2023-11-13 | NANDE MAQUBELA | Juanita Van Coller | 23000164 |  |  |  |  | 2023-07-14 | 1024167.52 | 0 |  |  | C000098084 | 1024167.52 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000120 | Absa Wesselsbron | Absa Wesselsbron |  |  | Region 3 | Free State | 78738X | 1000-71552-01 | Absa Wesselsbron-Erwees St-Wesselsbron |  | 2023-04-03 | 2023-04-24 |  | ALP-CR0031 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-02-28 |  | 0 | Approved at CB/BTB | 100 | 2023-06-08 | 2023-06-08 | 1073942.67 | Approved | {"MANDT":"111","REFERENCE":90000120,"ONEVIEW":"78738X","DATE01":"2023-01-23","DATE02":"2023-02-20","DATE03":"2023-02-27","DATE04":"2023-02-27","DATE05":"2023-04-03","DATE06":"2023-04-24","DATE07":"2023-05-15","DATE08":"2023-06-29","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-24","FORECAST_END":"2023-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgaW1wbGVtZW50YXRpb24gZGF0ZS4gRHVwbGljYXRlLg==","RATING":""} |  |  | C000118465 | PHASE02 | 2023-04-24 | 2023-05-15 | NANDE MAQUBELA | Juanita Van Coller | 23000129 |  |  |  |  | 2023-10-23 | 919358.84 | 0 |  |  | C000118465 | 919358.84 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000121 | Absa Postmasburg - Cosmetic Upgrade | Absa Postmasburg - Cosmetic Upgrade |  |  | Region 3 | Northern Cape | 21312X | 1000-74493-01 | Postmasburg-Springbok St-Postmasburg |  | 2023-03-30 |  |  | ALP-CR0032 | REL BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2023-02-28 |  | 769321.67 | Absa Direct Supplier Bhathokwa Consolidated Projects: Contract Value: R 462 204,47 incl.VAT | 100 | 2023-03-16 | 2023-03-16 | 769321.67 | Approved | {"MANDT":"111","REFERENCE":90000121,"ONEVIEW":"21312X","DATE01":"2023-01-19","DATE02":"2023-02-16","DATE03":"2023-02-23","DATE04":"2023-02-23","DATE05":"2023-03-30","DATE06":"2023-04-29","DATE07":"2023-05-20","DATE08":"2023-07-04","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-29","FORECAST_END":"2023-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLiBEdXBsaWNhdGUu","RATING":""} |  |  | C000090811 | PHASE10 | 2023-04-29 | 2023-05-20 | NANDE MAQUBELA | Juanita Van Coller | 23000204 |  |  |  |  | 2023-06-09 | 668975.37 | 0 |  |  | C000090811 | 668975.37 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000122 | Letsoho Shopping Centre Generator instal | 1. Build 200mm thick concrete plinth. 2.Supply, deliver, install and commission 60KVA Generator: - Connect generator to BMS - Perform Factory Acceptance TestÂ (FAT) - Supply Fire extinguisher - Issue COC - Updated electrical layout - Install Palisade Fence 3m x 2m with lockable gate and roof - First Fuel Fill - 6th and 12th Month Service level agreement 3. Security guarding services to be included for duration of project |  |  | Region 1 | Gauteng South | 76627X | 1000-70299-01 | Letsoho Shopping Centre-Cnr Hospital & Letsoho St-Katlehong | N | 2023-02-27 | 2023-03-31 |  | ALP-GS0051 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | L |  | NOMNGANGAL | 2023-01-26 |  | 61376.92 | Approved | 100 | 2022-12-01 | 2023-10-07 | 705834.55 |  | {"MANDT":"111","REFERENCE":90000122,"ONEVIEW":"Unknown","DATE01":"2022-12-19","DATE02":"2022-12-26","DATE03":"2023-01-16","DATE04":"2023-01-23","DATE05":"2023-02-13","DATE06":"2023-02-27","DATE07":"2023-03-31","DATE08":"2023-04-21","DATE09":"2023-06-05","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000080632 | PHASE11 | 2023-02-27 | 2023-03-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | 2023-04-04 | 2023-04-06 | 2023-04-06 | 2023-04-06 | 2023-04-19 | 705834.55 | 0 |  |  | C000080632 | 613769.17 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000123 | Westgate Dilaps | Westgate Dilaps |  |  | Region 1 | Gauteng South | 35110X | 1000-70089-01 | Westgate Shopping Centre-Ontdekkers Rd-Roodepoort | N | 2023-02-02 | 2023-04-30 |  | ALP-GS0052 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 0 |  | L | 2023-01-30 | GAMIETR | 2023-02-06 |  | 1760306.16 | Approved at CB/BTB | 100 | 2023-02-20 | 2023-02-20 | 1824759.51 | Approved | {"MANDT":"111","REFERENCE":90000123,"ONEVIEW":"35110X","DATE01":"2022-11-24","DATE02":"2022-12-01","DATE03":"2022-12-22","DATE04":"2022-12-29","DATE05":"2023-01-19","DATE06":"2023-02-02","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-02","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000070019 | PHASE11 | 2022-12-07 | 2022-12-12 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-02-22 | 1760306.16 | 0 |  |  | C000070019 | 1530701.01 |  | 152261.1 |  | 0 | 0 |  | 0 |  | 0
90000124 | Auckland Park - Renovations to Fish Bow | The fish bowl section will have to be cordened off using a partition to prevent dust to the rest of the floor. Soundproof the fish bowl space at lower ground (Ground to Soffit - including doors and internal walls). Supply and install 4 x Red Flashing Emergency Lights including a siren. Install and supply writable walls on x9 desk pilliars, x3 ducting pillars (broad sides of pillars, total 6), x1 surface wall near project stand, Frosting 2/3 of all glass walls (bottom to 3/4 glass height). Supply 5 of 2m X 0.9m portable/mobile bulletin boards. Provision to install PA system with 18 x ceiling speakers (supplied by Direct Delivery client). Create opening to new game room. Close up space where existing doorway is and remove door. Build new partition wall as per floor plan to incorporate additional desks. All works to walls, ceilings, floors etc. must be painted, cleaned and made good for daily office operation to commence. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-03-01 | 2023-12-15 |  | ALP-GS0053 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 0 |  | F |  | LOUISR | 2023-02-10 |  | 845803.89 | Approved at CB/BTB | 100 | 2023-02-09 | 2023-02-09 | 845803.89 | Approved | {"MANDT":"111","REFERENCE":90000124,"ONEVIEW":"76849X","DATE01":"2022-12-21","DATE02":"2022-12-28","DATE03":"2023-01-18","DATE04":"2023-01-25","DATE05":"2023-02-15","DATE06":"2023-03-01","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-01","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000093974 | PHASE11 | 2023-03-01 | 2023-07-03 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-05-22 | 2023-05-29 | 2023-06-01 | 2023-06-05 | 2023-06-26 | 735481.74 | 0 |  |  | C000093974 | 735481.74 |  | 31416.21 |  | 0 | 0 |  | 0 |  | 0
90000125 | Quadrum - Dilaps/ Decoupling | Removal of all security equipment, the alarm, CCTV cameras and access control; Removal of all the furniture Removal of a TVs Removal of all signage Decommission of all UPSs and issue COC Removal of all gas suppressors Decommission all the double PFC cabinets Electrical work Replace all non-working light fittings and issue a COC No security guard required for the duration of the works. Work will be carried out after normal working hours. Material Leadtime: +-5 working days. Onsite timeline: 15 working days |  |  | Region 1 | Gauteng South | 21332X | 1000-70025-01 | Quadrum Office Park-Constantia Blvd-Roodepoort | N | 2023-02-15 | 2023-05-31 |  | ALP-GS0054 | CRTD AVAC RESA: |  | false | false |  | Athi Magqashela |  |  | 0 |  | L | 2023-05-30 | GAMIETR | 2023-02-16 |  | 476892.96 |  | 100 | 2023-05-24 | 2023-05-24 | 476892.96 |  | {"MANDT":"111","REFERENCE":90000125,"ONEVIEW":"21332X","DATE01":"2022-12-07","DATE02":"2023-05-22","DATE03":"2023-05-24","DATE04":"2023-05-24","DATE05":"2023-05-24","DATE06":"2023-05-25","DATE07":"2023-05-25","DATE08":"2023-06-15","DATE09":"2023-07-30","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-25","FORECAST_END":"2023-05-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000087543 | PHASE11 | 2023-05-25 | 2023-05-25 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-25 | 414689.53 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000126 | Absa Ithala Centre (Makh | Absa Ithala Centre (Makhathini) - Dilaps |  |  | Region 3 | KwaZulu-Natal | 77968X | 1000-71617-01 | Ithala Centre Nkandla-Nkandla Township-Durban | Y | 2023-03-10 |  |  | ALP-KZ2003 | REL BUDG AVAC RESA SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L | 2019-02-27 | NOMNGANGAL | 2023-02-22 |  | 839663.07 | Approved at CB/BTB |  | 2023-02-23 | 2023-03-02 | 839663.07 | Approved | {"MANDT":"111","REFERENCE":90000126,"ONEVIEW":"77968X","DATE01":"2022-12-30","DATE02":"2023-01-27","DATE03":"2023-02-03","DATE04":"2023-02-03","DATE05":"2023-03-10","DATE06":"2023-04-09","DATE07":"2023-04-30","DATE08":"2023-06-14","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-09","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071332 | PHASE10 | 2023-04-09 | 2023-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-03-02 | 730141.8 | 0 |  |  | C000071332 | 730141.8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000127 | Absa Square (Nelspruit) - Floor Space Co | Absa Square (Nelspruit) - Floor Space Co |  |  | Region 3 | Mpumalanga | 77878X | 1000-70683-01 | Absa, Square-Paul Kruger St-Nelspruit |  | 2023-03-30 |  |  | ALP-MP0204 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Justice Mogadime |  |  | 0 |  |  |  | NOMNGANGAL | 2023-01-30 |  | 177560.9 | Approved at CB/BTB | 100 | 2023-02-09 | 2023-02-09 | 2041950 | Approved | {"MANDT":"111","REFERENCE":90000127,"ONEVIEW":"77878X","DATE01":"2023-01-19","DATE02":"2023-02-16","DATE03":"2023-02-23","DATE04":"2023-02-23","DATE05":"2023-03-30","DATE06":"2023-04-29","DATE07":"2023-05-20","DATE08":"2023-07-04","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-29","FORECAST_END":"2023-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE8gdG8gYmUgY2FuY2VsbGVkIGFuZCBwcm9qZWN0IGNsb3NlZApQYXJ0IGludm9pY2luZyBzdWJtaXR0ZWQ=","RATING":""} |  |  | C000083428 | PHASE11 | 2023-04-29 | 2023-05-20 | NANDE MAQUBELA | Thea Spamers | 23000023 |  |  |  |  | 2023-05-05 | 2041950.41 | 0 |  |  | C000083428 | 1775609.05 |  | 91767.69 |  | 0 | 0 |  | 0 |  | 0
90000128 | National-White Goods Microwaves,Fridges | National-White Goods Microwaves,Fridges |  |  | National | National | Various | 1000-70027-01 | Various Sites | Y | 2023-03-01 | 2023-12-15 |  | ALP-N00037 | REL BUDG AVAC RESA SETC: |  | N | true |  | Lorri-Anne Louis |  |  | 0 |  | U |  | LOUISR | 2023-02-07 |  | 1150000 | Approved at CB/BTB |  | 2023-01-12 | 2023-01-12 | 1150000 | Approved | {"MANDT":"111","REFERENCE":90000128,"ONEVIEW":"Various","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-02-15","DATE05":"2023-03-01","DATE06":"2023-12-15","DATE07":"2024-01-05","DATE08":"2024-02-19","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":0,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":72,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-15","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3QgUE9DIHBhY2tzIGFuZCBkZWxpdmVyeSBvZiB3aGl0ZSBnb29kcyBhcmUgYmVpbmcgZG9uZSB2aWEgUmVnaW9ucy4K","RATING":"Medium"} |  |  | C000071093 | PHASE06 | 2023-03-28 | 2023-07-20 | LUCIA AMUNGA | Michael Maluleka | 23000041 | 2023-02-07 | 2023-02-07 |  |  | 2023-03-01 | 1000000 | 0 |  |  | C000071093 | 1000000 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000129 | National- UPS Batteries for Various Abs | National- UPS Batteries for Various Abs | bnVsbCA%3D |  | National | National | Various | 1000-70027-01 | Various Sites | Y | 2023-03-01 | 2023-12-15 |  | ALP-N00038 | REL BUDG AVAC RESA SETC: | SAP_018 | N | true | null | Lorri-Anne Louis | na | null | 0 |  | U |  | LOUISR | 2023-02-09 |  | 1200000 | Approved at CB/BTB |  | 2023-02-16 | 2023-02-16 | 1200000 | Approved | {"MANDT":"111","REFERENCE":90000129,"ONEVIEW":"Various","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-02-15","DATE05":"2023-03-01","DATE06":"2023-12-15","DATE07":"2024-01-05","DATE08":"2024-02-19","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":80,"PROG08":0,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":72,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-15","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3QgUE9DIHBhY2tzIGFuZCBkZWxpdmVyeSBvZiB3aGl0ZSBnb29kcyBhcmUgYmVpbmcgZG9uZSB2aWEgUmVnaW9ucy4=","RATING":""} |  |  | C000071627 | PHASE06 | 2023-11-15 | 2023-11-15 | LUCIA AMUNGA | Michael Maluleka | 2300034 | 2023-05-03 | 2023-05-03 |  |  | 2023-03-03 | 1043478.26 | 0 |  |  | C000071627 | 1043478.26 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000130 | National-Small FM items Like for Like-De | National-Small FM items Like for Like-De |  |  | National | National | Various | 1000-70027-01 | Various Sites | N | 2023-03-01 | 2023-12-15 |  | ALP-N00039 | REL BUDG AVAC RESA SETC: |  | N | true |  | Lorri-Anne Louis |  |  | 0 |  | U |  | LOUISR | 2023-02-10 |  | 1150000 | Approved at CB/BTB |  | 2023-01-12 | 2023-01-12 | 1150000 | Approved | {"MANDT":"111","REFERENCE":90000130,"ONEVIEW":"Various","DATE01":"2022-12-21","DATE02":"2023-01-18","DATE03":"2023-01-25","DATE04":"2023-02-15","DATE05":"2023-03-01","DATE06":"2023-12-15","DATE07":"2024-01-05","DATE08":"2024-02-19","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-15","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000071694 | PHASE06 | 2023-11-15 | 2023-11-15 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-02-22 | 2023-03-07 |  |  | 2023-03-03 | 1000000 | 0 |  |  | C000071694 | 1000000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000131 | 2023 Retail LED lighting rollout | 2023 Retail LED lighting rollout (32 branches) |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | N | 2023-03-31 | 2023-12-15 |  | ALP-N00040 | CLSD BUDG AVAC RESA SETC: |  | N | true |  | Sanelisiwe Celu | rollover | 32 retail branches located nationally | 0 |  | U |  | LOUISR | 2023-02-21 |  | 17637227 | Cost efficiencies and Absa Environmental Action Plan (EAP) targets | 100 | 2022-11-25 | 2022-12-01 | 19457506.69 | Approved | {"MANDT":"111","REFERENCE":90000131,"ONEVIEW":"Various Sites","DATE01":"2023-01-20","DATE02":"2022-11-11","DATE03":"2022-11-18","DATE04":"2022-11-25","DATE05":"2022-12-01","DATE06":"2023-04-03","DATE07":"2023-04-10","DATE08":"2023-08-31","DATE09":"2023-09-10","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"273:-70:7:7:6:123:7:143:10:11","PROGRESS":89,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-03","FORECAST_END":"2023-04-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"T00gLSAyMS8wNy8yMDIzIC0gUHJvamVjdCBzdGlsbCBpbiBwcm9ncmVzcy4g","RATING":""} |  |  | C000070083 | PHASE11 | 2023-04-03 | 2023-04-10 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-01-16 | 2023-02-21 | 2023-01-11 | 2023-01-13 | 2023-02-23 | 15336718.81 | 0 |  |  | C000070083 | 15336719.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000132 | 2023 Corporate LED lighting rollout | 2023 Corporate LED lighting rollout (3 Corporate Sites) |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | N | 2023-03-31 | 2023-12-15 |  | ALP-N00041 | CLSD BUDG AVAC RESA SETC: |  | N | true |  | Sanelisiwe Celu | possible | 3 Corporate Sites located nationally | 0 |  | U |  | LOUISR | 2023-02-22 |  | 4706839.19 | Cost efficiencies and Absa Environmental Action Plan (EAP) targets | 100 | 2022-11-25 | 2022-12-01 | 5606752.25 | Approved | {"MANDT":"111","REFERENCE":90000132,"ONEVIEW":"Various Sites","DATE01":"2023-01-20","DATE02":"2022-11-11","DATE03":"2022-11-18","DATE04":"2022-11-25","DATE05":"2022-12-01","DATE06":"2023-04-03","DATE07":"2023-04-10","DATE08":"2023-08-31","DATE09":"2023-09-15","DATE10":"2023-09-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"273:-70:7:7:6:123:7:143:15:11","PROGRESS":89,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-03","FORECAST_END":"2023-04-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"T00gLSAyMS8wNy8yMDIzIC0gUHJvamVjdCBzdGlsbCBpbiBwcm9ncmVzcy4=","RATING":"Medium"} |  |  | C000070110 | PHASE11 | 2023-04-03 | 2023-04-10 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-01-16 | 2023-02-21 | 2023-01-11 | 2023-01-13 | 2023-02-23 | 4092903.64 | 0 |  |  | C000070110 | 4092903.48 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000133 | Absa Cape Gate - HVAC Repairs | Absa Cape Gate - HVAC Repairs |  |  | Region 2 |  | 77288X | 1000-71432-01 | CapeGate Shopping Centre-Cnr Okavango & De Bron Rd-Brackenfell |  | 2023-03-31 |  |  | ALP-WC0016 | CRTD DLFL AVAC: |  | false | false |  | Nyasha Wena |  |  | 0 |  |  |  | CEASARS | 2023-01-24 |  | 0 |  |  |  |  | 0 | [5 empty] | CLOSED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000134 | Absa Moorreesburg - Minor Works | Absa Moorreesburg - Minor Works |  |  | Region 2 | Western Cape | 77249X | 1000-70811-01 | Absa Moorreesburg-Cnr Main & Long St-Moorreesburg | N | 2023-03-31 |  |  | ALP-WC0017 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-01-24 |  | 730279.99 | Absa Direct Supplier Associated Alterations: Contract Value: R529992,45 incl.VAT | 100 | 2023-03-16 | 2023-03-16 | 730279.99 | Contingency Remaining R 55 294.98 Incl Vat | {"MANDT":"111","REFERENCE":90000134,"ONEVIEW":"77249X","DATE01":"2023-01-20","DATE02":"2023-01-31","DATE03":"2023-03-10","DATE04":"2023-03-16","DATE05":"2023-03-16","DATE06":"2023-05-15","DATE07":"2023-06-15","DATE08":"2023-08-08","DATE09":"2023-09-22","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"223:11:38:6:0:60:31:54:45:11","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-06-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBdWcgLSBGaW5hbCBQT0MgU3VibWl0dGVkIGZvciBGQURUCjE5IEp1bHkgRm9sbG93IHVwIG1haWwgc2VudCB0byBGQURUIHJlIG91dHN0YW5kaW5nIEludm9pY2UKMTkgSnVuZSAtIFBPQyBQYXJ0IDEgUGFydCAxIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZSBSIDU2MSA0ODMuNDgtICBGQURUIEludm9pY2Ugb3V0c3RhbmRpbmc=","RATING":"Medium"} |  |  | C000082912 | PHASE11 | 2023-05-15 | 2023-06-15 | RODERICK NEVAY | Michael Maluleka | 23000058 |  |  |  |  | 2023-05-03 | 635026.08 | 0 |  |  | C000082912 | 635026.08 | CIP2023XP | 62654.98 |  | 0 | 0 |  | 0 |  | 0
90000135 | Absa Piketberg - Minor Works | Absa Piketberg - Minor Works |  |  | Region 2 | Western Cape | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg | N | 2023-04-10 |  |  | ALP-WC0018 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  |  |  | CEASARS | 2023-02-14 |  | 952395.8 | Absa Direct Supplier AOC Johanneburg: Contract Value: R1 101 426,05 incl.VAT | 100 | 2023-03-16 | 2023-03-16 | 952395.81 | Approved The balance of contingency is R 15 120.51 Inc. VAT | {"MANDT":"111","REFERENCE":90000135,"ONEVIEW":"78132X","DATE01":"2023-01-19","DATE02":"2023-01-20","DATE03":"2023-02-27","DATE04":"2023-03-16","DATE05":"2023-03-16","DATE06":"2023-05-15","DATE07":"2023-06-14","DATE08":"2023-07-05","DATE09":"2023-06-19","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:1:38:17:0:60:30:21:-16:12","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-06-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBKdWx5IEZpbmFsIFBPQyBzdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000082702 | PHASE11 | 2023-05-15 | 2023-06-14 | RODERICK NEVAY | Michael Maluleka | 23000087 |  |  |  |  | 2023-05-03 | 828170.27 | 0 |  |  | C000082702 | 828170.27 | CIP2023XP | 81599.42 |  | 0 | 0 |  | 0 |  | 0
90000136 | Absa Bridge Park West - Dilaps - Storage PO s for Capital Projects | Absa Bridge Park West - Dilaps - Storage POs for Capital Projects |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2023-03-13 |  |  | ALP-WC0019 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | F |  | CEASARS | 2023-02-17 |  | 1094478 |  | 100 | 2023-02-17 | 2023-02-17 | 1094478 | Absa Ref : Opex Was Approved as per Out of Cycle request from Head of CRES, PO from Absa Capital Projects received post BV PO.s, approval was obtained from COO, Vendor Invoices Monthly for the duration of the Project. Runs to June 2024 | {"MANDT":"111","REFERENCE":90000136,"ONEVIEW":"36225X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-06","DATE05":"2023-02-27","DATE06":"2023-03-01","DATE07":"2024-06-01","DATE08":"2024-06-22","DATE09":"2024-08-06","DATE10":"2024-08-31","DATE11":"2024-08-06","DATE12":"2024-08-06","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:7:21:7:21:2:458:21:45:24","PROGRESS":71,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-01","FORECAST_END":"2024-06-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgRmViIFBhcnQgMTAgUE9DIFN1Ym1pdHRlZCAxMyBGZWIgZm9yIFIgMTMwIDI5NS4wMCAsIFRvdGFsIHRvIGRhdGUgLSBSIDg0NCAzNDEuNTAKMTIgRmViIFBPQyAxMCBzdWJtaXR0ZWQgdG8gQ2FwaXRhbCBQcm9qZWN0cyBmb3IgU2lnbm9mZgozMSBKYW4gUGFydCA5IFBPQyBTdWJtaXR0ZWQgMzEgSmFuIGZvciBSNjUgMTQ3LjUwICwgVG90YWwgSW52b2ljZSB2YWx1ZSB0byBkYXRlIC0gUiA3MTQgMDQ2LjUwCjUgRGVjIFBhcnQgOCBQT0MgU3VibWl0dGVkIDUgRGVjIGZvciBSNjUgMTQ3LjUwICwgVG90YWwgdG8gZGF0ZSAtIFIgNjQ4IDg5OS4wMAoyOSBOb3YgRGVjIEludm9pY2VzIHJlY2VpdmVkIHRvIGJlIHN1Ym1pdHRlZCBmb3IgcGF5bWVudAoyMCBOb3YgRm9sbG93IHVwIGluIGFueSBJbnZvaWNlcyB0aGF0IGNhbiBiZSBzdWJtaXR0ZWQKMTAgTm92IFBPQyBQYXJ0IDcgU3VibWl0dGVkIFIgNjUgMTQ3LjUwIC0gVG90YWwgdG8gRGF0ZSBSIDU4MyA3NTEuNTAKNiBOb3YgLSBOb3YgaW52b2ljZXMgdG8gYmUgc3VibWl0dGVkCjMgT2N0IC0gUGFydCA2IFN1Ym1pdHRlZCAzIE9jdCBmb3IgUiA2NSAxNDcuNTAgLSBJbnZvaWNlZCB0byBkYXRlIC0gUiA1MjEgMTgwLjAwCjIyIFNlcHQgLSBSdW5zIHRvIEp1bmUgMjAyNCAtIFdpbGwgaGF2ZSBSb2xsb3ZlciAtIE9wZXgKUGFydCA1IFN1Ym1pdHRlZCB0byBGaW5hbmNlIDEyIFNlcHQgLSBSIDY1IDE0Ny41MApQYXJ0IDQgU3VibWl0dGVkIHRvIEZpbmFuY2UgOCBBdWcgLSBSIDY1IDE0Ny41MApQYXJ0IDMgU3VibWl0dGVkIDUgSnVsIC0gIFIgNjUxNDcuNTAKUGFydCAyIFN1Ym1pdHRlZCAxMyBKdW5lIC0gUjEzMCAyOTUuMApQYXJ0IDEgU3VibWl0dGVkIDUgTWF5IC0gUjEzMCAyOTUuMDA=","RATING":"Low"} |  |  | C000082121 | PHASE08 | 2023-03-01 | 2024-06-01 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-26 | 951720 | 0 |  |  | C000082121 | 951720 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000137 | Pretoria Campus Replacement of 1 hydro t | Pretoria Campus Replacement of 1 hydro t |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-03-03 |  |  | ASP-GN0180 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 0 |  |  |  | GAMIETR | 2023-03-13 |  | 95449.2 | 2023.03.16: Approved by Conrad M 2023.03.14: Supported by Winston P | 100 | 2023-03-16 | 2023-03-16 | 95449.2 | Approved | {"MANDT":"111","REFERENCE":90000137,"ONEVIEW":"22491X","DATE01":"2022-12-23","DATE02":"2022-12-30","DATE03":"2023-01-20","DATE04":"2023-01-27","DATE05":"2023-02-17","DATE06":"2023-03-03","DATE07":"2023-04-02","DATE08":"2023-04-23","DATE09":"2023-06-07","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-03","FORECAST_END":"2023-04-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000074870 | PHASE11 | 2023-03-03 | 2023-04-02 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-03-17 | 109766.58 | 0 |  |  | C000074870 | 82999.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000138 | Daveyton Sales Consultant Desk | Daveyton Sales Consultant Desk |  |  | Region 1 |  | SGS_10941 | 1000-67723-01 | Daveyton-- |  | 2022-03-14 | 2023-03-31 |  | ASP-GN0181 | CRTD AVAC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  |  |  | GAMIETR | 2023-03-13 |  | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000138,"ONEVIEW":"SGS_10941","DATE01":"2022-01-03","DATE02":"2023-01-18","DATE03":"2023-03-21","DATE04":"2023-03-27","DATE05":"2023-04-10","DATE06":"2023-04-14","DATE07":"2023-04-18","DATE08":"2023-05-18","DATE09":"2023-05-22","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-14","FORECAST_END":"2023-04-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-04-14 | 2023-04-18 | PRESHANE MUNTHREE | Buhle Qwabe | 23000373 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000139 | Absa Brooklyn Main 110 KVA SDMO generator exhaust system extension | This request is to extend the exhaust system at Absa Brooklyn Malls 110 KVA SDMO generator and bend away from the basement parking area where the unit is positioned. The generator was installed in 2018, and its short exhaust is causing smoke and fumes in the basement. Furthermore, the fumes pose an OHS risk to customers in the parking area when the generator starts during power failures or load shedding. The landlord has allocated a route for the exhaust extension and provided and approved a route for the required exhaust system extension. |  |  | Region 1 | Gauteng North | 76422X | 1000-70249-01 | Brooklyn Mall & Design Square-Bronkhorst St-Pretoria | N | 2023-03-13 |  |  | ASP-GN0182 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | L |  | GAMIETR | 2023-03-13 |  | 106121.32 | 2023.03.16: Approved by Kobus JvR 2023.03.14: Supported by Sambulo K | 100 | 2023-03-13 | 2023-03-16 | 106121.32 | Approved | {"MANDT":"111","REFERENCE":90000139,"ONEVIEW":"76422X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-06","DATE05":"2023-02-27","DATE06":"2023-03-13","DATE07":"2023-04-12","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:7:21:7:21:14:30:202:45:13","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-13","FORECAST_END":"2023-04-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8xMTogUHJvamVjdCBjb21wbGV0ZS4gQXdhaXRpbmcgcHJvamVjdCBwYXBlcndvcmsgZnJvbSBFU00gJiBQQyBmb3IgUE9DIHByb2R1Y3Rpb24u","RATING":""} |  |  | C000077263 | PHASE11 | 2023-03-13 | 2023-04-12 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-03-30 | 106121.32 | 0 |  |  | C000077263 | 92279.41 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000140 | Absa Towers North Multi faith room | Absa Towers North Multi Faithroom Upgrade |  |  | Region 1 | Gauteng South | 77831X |  | Absa Towers North | N | 2023-03-13 |  |  | ASP-GS0617 | CRTD: |  | false | false |  | Athi Magqashela |  |  | 0 |  | F |  | GAMIETR | 2023-03-13 |  | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000140,"ONEVIEW":"77831X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-06","DATE05":"2023-02-27","DATE06":"2023-05-22","DATE07":"2023-06-02","DATE08":"2023-06-23","DATE09":"2023-08-07","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:7:21:7:21:84:11:21:45:13","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-22","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxsZWQ=","RATING":""} |  |  |  | PHASE12 | 2023-05-22 | 2023-06-02 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000141 | Alice Lane North 16 Swivel Chairs and plug sets | Supply and deliver 16 x WITHME SWIVEL CHAIR P PRF BLACK Chairs Mechanism: ME-WM: synchronous, automatic weight adjustment, automatic backrest tilt force adjustment ,Backrest: Perforated, made of polyamide, Seat: Upholstered with plastic cover. (full spec on quote). Supply, deliver and install 8 x Power set - 3Pin, 2Pin, USB A & 3m AC power cable. ( Power supply for plus allowed for in Pods RTB). Security not allowed for as itÃÂÃÂ¢ÃÂÃÂÃÂÃÂs a drop off. - 50% deposit required on order. - The standard manufacturing lead time for the chairs is 12-14 working weeks. - Chairs and plug sets are guaranteed against faulty workmanship and defective materials for a period of 5 years. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | N | 2023-03-13 |  |  | ASP-GS0618 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 0 |  | L |  | GAMIETR | 2023-03-13 |  | 144752.8 | 2023.03.16: Approved by Conrad M 2023.03.14: Supported by Rhulani N | 100 | 2023-03-16 | 2023-03-16 | 144752.8 | Approved | {"MANDT":"111","REFERENCE":90000141,"ONEVIEW":"70656X","DATE01":"2023-01-02","DATE02":"2023-01-09","DATE03":"2023-01-30","DATE04":"2023-02-06","DATE05":"2023-04-06","DATE06":"2023-04-20","DATE07":"2023-05-20","DATE08":"2023-06-10","DATE09":"2023-07-25","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:7:21:7:59:14:30:21:45:13","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-20","FORECAST_END":"2023-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079892 | PHASE11 | 2023-04-20 | 2023-05-20 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 144752.8 | 0 |  |  | C000079892 | 125872 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000142 | Daveyton Sales Consultant Desk | Daveyton Sales Consultant Desk |  |  | Region 1 | Gauteng South | 78727X | 1000-70433-01 | Daveyton Shopping Centre-Eiselen St-Daveyton |  | 2022-03-14 |  |  | ASP-GS0619 | REL BUDG AVAC RESA SETC: |  | R | false |  | Christopher Mpofu |  |  | 0 |  | L |  | GAMIETR | 2023-03-13 |  | 89249.51 | 2023.03.16: Approved by Conrad M 2023.03.14: Supported by Winston P & Ilana vdW | 100 | 2023-03-16 | 2023-03-16 | 89249.51 | Approved | {"MANDT":"111","REFERENCE":90000142,"ONEVIEW":"78727X","DATE01":"2022-01-03","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-20","DATE05":"2023-02-27","DATE06":"2022-03-14","DATE07":"2023-05-06","DATE08":"2023-05-27","DATE09":"2023-07-11","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-03-14","FORECAST_END":"2023-05-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000076752 | PHASE11 | 2022-03-14 | 2023-05-06 | PRESHANE MUNTHREE | Nokuthula Manzini | 0 |  |  |  |  | 2023-03-29 | 89249.51 | 0 |  |  | C000076752 | 77608.27 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000143 | Auckland Park CC Upgrade the Honeywell N | Upgrade SW-OW-CON - ONYXWorks Software, View and Control. Upgrade OnyxWorks and Implementing Firmware Updates on the Fire System Work will take place during normal working hours on weekdays. |  |  | Region 1 | Gauteng North | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-03-13 |  |  | ASP-GS0620 | REL BUDG AVAC SETC: |  | R | false |  | Tsholofelo Sello |  |  | 0 |  | F |  | GAMIETR | 2023-03-13 |  | 118663.69 | Approved at CB/BTB | 100 | 2023-03-16 | 2023-03-16 | 118663.69 | Approved | {"MANDT":"111","REFERENCE":90000143,"ONEVIEW":"76849X","DATE01":"2023-01-02","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-20","DATE05":"2023-02-27","DATE06":"2023-03-13","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"210:21:21:7:7:14:140:21:45:20","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-13","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Medium"} |  |  | C000075337 | PHASE07 | 2023-03-13 | 2023-07-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000380 |  |  |  |  | 2023-03-22 | 103185.82 | 0 |  |  | C000075337 | 103185.82 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000144 | Absa Viljoenskroon Minor Works | Absa Viljoenskroon Minor Works |  |  | Region 3 |  | 78481X | 1000-71540-01 | Absa Viljoenskroon |  | 2023-02-13 | 2023-02-13 |  | ASP-CR0375 | REL AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | MOKOENAM2 | 2023-01-23 |  | 0 |  | 1 |  |  | 0 | Duplicate | {"MANDT":"111","REFERENCE":90000144,"ONEVIEW":"78481X","DATE01":"2022-12-05","DATE02":"2022-12-12","DATE03":"2023-01-02","DATE04":"2023-01-09","DATE05":"2023-01-30","DATE06":"2023-02-13","DATE07":"2023-02-13","DATE08":"2023-03-06","DATE09":"2023-04-20","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-13","FORECAST_END":"2023-02-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RHVwbGljYXRlLiBDYW5jZWxsZWQu","RATING":""} |  |  |  | PHASE12 | 2023-02-13 | 2023-02-13 | NANDE MAQUBELA | Juanita Van Coller | 23000035 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000145 | Absa Lichtenburg | Absa Lichtenburg |  |  | Region 3 | North West | 77806X | 1000-71605-01 | Absa Lichtenburg-Nelson Mandela Dr-Lichtenburg | N | 2023-03-28 | 2023-04-11 |  | ASP-CR0408 | CRTD: |  | R | false |  | Kagiso Seothaeng |  |  | 0 |  | F |  | MOKOENAM2 | 2023-03-08 |  | 0 |  | 40 |  |  | 0 | No approval received as yet as the work was done as an Insurance Claim and above R150k to be approved at CB. | {"MANDT":"111","REFERENCE":90000145,"ONEVIEW":"77806X","DATE01":"2023-01-17","DATE02":"2023-02-14","DATE03":"2023-02-21","DATE04":"2023-02-21","DATE05":"2023-03-28","DATE06":"2023-04-11","DATE07":"2023-05-02","DATE08":"2023-06-16","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-11","FORECAST_END":"2023-05-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIGludm9pY2luZyBpbiBwcm9ncmVzcy4=","RATING":""} |  |  |  | PHASE11 | 2023-04-11 | 2023-05-02 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000146 | Absa Walmer Park ShopCntre- Generator Rust Repairs / Replacement | Absa Walmer Park ShopCntre- Generator Rust Repairs / Replacement |  |  | Region 2 | Eastern Cape | 77686X | 1000-71032-01 | Walmer Park Shopping Centre-Main Rd-Port Elizabeth | N | 2023-04-24 | 2023-04-30 |  | ASP-EC0282 | TECO BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-03-08 |  | 376684.69 |  | 100 | 2023-08-31 | 2023-09-07 | 376684.69 | Absa Ref : 240129_072 | {"MANDT":"111","REFERENCE":90000146,"ONEVIEW":"77686X","DATE01":"2023-01-19","DATE02":"2023-07-31","DATE03":"2023-08-31","DATE04":"2023-10-05","DATE05":"2023-09-07","DATE06":"2023-10-22","DATE07":"2023-11-23","DATE08":"2024-02-12","DATE09":"2024-03-28","DATE10":"2024-03-31","DATE11":"2024-01-28","DATE12":"2024-01-28","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"437:193:31:35:-28:45:32:81:45:15","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-22","FORECAST_END":"2023-11-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRmViIEZpbmFsIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZSAtIENvbnRpbmdlbmN5IEZ1bGx5IHV0aWxpc2VkCjA5IEZlYiBTZW50IE1haWwgdG8gREogcmVxdWVzdGluZyBwcm9ncmVzcyB1cGRhdGUKMDggRmViIFBPQyB3aXRoIEFic2EgZm9yIHNpZ25vZmYuIFBNIHRvIGZvbGxvdyB1cAo1IEZlYiAtIFBNIHRvIGVzY2FsYXRlIGFzIHN1cHBsaWVyIGVzY2FsYXRlIHJlIEVuZ2luZWVyaW5nIGFzc2V0IGJ1aWxkMSBGZWIgVXJnZW50IFBPQyBzaWdub2ZmIHJlcXVpcmVkIFBNIHRvIGZvbGxvdyB1cAoyOSBKYW4gUE0gdG8gZm9sbG93IHJlIGFzc2V0cyBsb2FkCjI1IEphbiBQTSB0byBmb2xsb3cgdXAgcmUgYXNzZXQgdXBsb2FkcyBhcyB3YXJyYW50ZWUgaW5mbyByZWNlaXZlZCBmb3IgdGhlIHRhbmsKMjIgSmFuIC0gUE0gdG8gZm9sbG93IHVwIHdpdGggREkgcmUgd2FycmFudHkgZm9yIHRoZSB0YW5rCjE4IEphbiBXYXJyYW50eSBmb3IgVGFuayBvdXRzdGFuZGluZwoxNCBEZWMgLSBTZW50IHRvIEJpZHZlc3QgRW5naW5lZXJpbmcgZm9yIFNpZ25vZmYKNyBEZWMgLSBTZW5zb3IgYmVpbmcgaW5zdGFsbGVkIDcgRGVjLCBESSBpbnZvaWNlIHBlbmRpbmcKNCBEZWMgLSBQTSB0byBmb2xsb3cgdXAgd2l0aCBESSByZSBpbnZvaWNlLCBQTSB0byBmb2xsb3cgdXAgcmUgY29ubmVjdGlvbiBvZiBmdWVsIHNlbnNvciB0byBCTVMKMzAgTm92IERJIEludm9pY2Ugb3V0c3RhbmRpbmcgLSBDQ1MgSW52b2ljZSByZWNlaXZlZC4KMjcgTm92IC0gVW5pdCByZXR1cm5lZCB0byBzaXRlIDIzIE5vdiBQT0MgYW5kIEludm9pY2luZyB0byBGb2xsb3cKMjMgTm92IFZlbmRvciB3aWxsIGJlIG9uc2l0ZSB0b2RheSB0byBkZWluc3RhbGwgdGhlIEdlbmVyYXRvciBhdCA2cG0KMjAgTm92IFBsYW5uaW5nIHRvIHJldHVybiB1bml0IHRvIHNpdGUgYnkgMjZ0aCBOb3YgcGxhbm5pbmcgZm9yIDIzcmQgIAoxNCBOb3YgLSBWTyBhcHByb3ZlZCwgQlYgUE8gcmVxdWVzdGVkIC0gUiAxMyA4MDAuMDAgaW5jbHVkaW5nIFZhdCAtIDQ1MDA4NzQyMTkgSXNzdWVkIDIzIE5vdgo4IE5vdiBWTyBzdWJtaXR0ZWQgdG8gQWJzYSBFbmdpbmVlcmluZyBmb3IgYXBwcm92YWwKNiBOb3YgUXVvdGUgdG8gYmUgc3VibWl0dGVkIGZvciBWTyBmb3IgUnVzdGVkIEJhc2UgVGFuayArLSBSIDE2IDM4Ny41MAoyIE5vdiBPbmdvaW5nIFVuaXQgaW4gSkhCIGZvciByZW1lZGlhdGlvbgoyNiBPY3QgLSBJbiBQcm9ncmVzcyBHZW5lcmF0b3IgaW4gSkhCIGZvciBSZWZ1cmIKMjMgT2N0IC0gUmVtb3ZhbCBjb21wbGV0ZWQgdGVtcCB1bml0IGluc3RhbGxlZCBhbmQgdGVzdAoxOSBPY3QgQWxsIHNldCBmb3IgU3VuZGF5IDIyIE5EIE9jdAoxMiBPY3QgU2V0IGZvciAyMm5kLCBQTSB0byBzZXQgdXAgbWVldGluZyB3aXRoIGNsaWVudCB0byBpbmZvcm0gYWxsIHJlIHRoZSBzY2hlZHVsZSBhbmQga2VlcCBMTCBJbmZvcm1lZAoxMCBPY3QgLSBSaXNrIGNvbmZpcm1lZCBhcyBNZWQsIG9uIHRyYWNrIHRvIHJlbW92ZSAyMiBTZXB0LCBjaGFuZ2Ugbm90ZSB0byBiZSBjb21wbGV0ZWQKNSBPY3QgLSBCViBPSFMgdG8gY29uZmlybSByZSBPSFMgcmlzayBwb3N0IG1lZXRpbmcgd2l0aCBBYnNhLgoyOCBTZXB0IC0gT0hTIGNvbmZpcm1hdGlvbiBzdGlsbCBwZW5kaW5nCjIyIFNlcHQgLSBVbmRlciByZXZpZXcgYmV0d2VlbiBBYnNhIGFuZCBCaWR2ZXN0IE9IUyAtIFJpc2sgLSBXaWxsIGJlIFJvbGxvdmVyIC0gRmluYW5jaWFsIGZyb20gY2FzaGZsb3cgcGVyc3BlY3RpdmUKMTQgU2VwdCAtIE9uIHRyYWNrIC0gQ2hhbmdlcyBub3RlcyBhbmQgTEwgY29uc2VudC4KMTIgU2VwdCBBYnNhIFBPIHJlY2VpdmVkIEMwMDAxMDk5NTYgLCBCViBQTyByZXF1ZXN0ZWQKMTEgU2VwdCBBcHByb3ZlZCBDQjM0IC0gNyBTZXB0IC0gU2lnbmVkIGRlY2sgUmVjZWl2ZWQsIFBPJ3MgdG8gYmUgcmVxdWVzdGVkCjMxIEF1ZyByZSBTdWJtaXR0ZWQgZm9yIENCMzQKMzAgQXVnIC0gUHJvZ3JhbSB0byBiZSB2ZXJpZmllZCB3aXRoIERJIGFzIHRvIGJlIHN1Ym1pdHRlZCB3aXRoIHRoZSBwYWNrCjI5IEF1ZyBUbyBiZSByZXdvcmtlZCBhbmQgc3VibWl0dGVkIGZvciBDQjM0CjI0IEF1ZyB0byBiZSByZXN1Ym1pdHRlZCBDQjMzCg==","RATING":"Medium"} |  |  | C000109956 | PHASE09 | 2023-10-22 | 2023-11-23 | RODERICK NEVAY | Floyd Mofokeng | 23000120 |  |  |  |  | 2023-09-12 | 327551.9 | 0 |  |  | C000109956 | 327551.9 | CIP2023XP | 13800 |  | 13800 | 0 | C000146587 | 376684.69 |  | 0 |  |  | 2024-03-04
90000147 | Absa Mqanduli - Water Tank Connection DD | Absa Mqanduli - Water Tank Connection DD |  |  | Region 2 | Eastern Cape | 78937X | 1000-71058-01 | Main Street Mqanduli-Main St-Mqanduli | N | 2023-04-24 | 2023-04-30 |  | ASP-EC0283 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 0 |  | L |  | CEASARS | 2023-03-08 |  | 7238.96 | 2023.04.26: Approved by Kobus JvR as per email | 100 | 2023-04-26 | 2023-04-26 | 7238.96 | Approved | {"MANDT":"111","REFERENCE":90000147,"ONEVIEW":"78937X","DATE01":"2023-03-06","DATE02":"2023-03-13","DATE03":"2023-04-03","DATE04":"2023-04-26","DATE05":"2023-04-26","DATE06":"2023-05-02","DATE07":"2023-05-02","DATE08":"2023-05-19","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:23:0:6:0:17:42:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-02","FORECAST_END":"2023-05-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgTWF5IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000082108 | PHASE11 | 2023-05-02 | 2023-05-02 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-26 | 6294.75 | 0 |  |  | C000082108 | 6294.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000148 | Birch Acres Paint Ceilings and walls | Spray acoustic ceiling tiles. 450sqm Paint internal walls in the branch Grey Lux 550sqm. Security to be provided for duration of project. Work to be carried out after hours for duration of 6 days. |  |  | Region 1 | Gauteng South | 21330X | 1000-70024-01 | Birch Acres Mall-Cnr Andrew Mapheto Dr & Isimuku St-Tembisa | N | 2023-02-27 | 2023-05-31 |  | ASP-GS0612 | REL BUDG AVAC RESA SETC: |  | R | false |  | Tsholofelo Sello |  |  | 0 |  | L |  | GAMIETR | 2023-03-07 |  | 120702.23 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 120702.23 | Approved | {"MANDT":"111","REFERENCE":90000148,"ONEVIEW":"21330X","DATE01":"2022-12-19","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-20","DATE05":"2023-02-27","DATE06":"2023-02-27","DATE07":"2023-05-06","DATE08":"2023-06-21","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-02-27","FORECAST_END":"2023-05-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000072572 | PHASE08 | 2023-02-27 | 2023-05-06 | PRESHANE MUNTHREE | Nokuthula Manzini | 23000270 |  |  |  |  | 2023-03-08 | 104958.45 | 0 |  |  | C000072572 | 104958.45 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000149 | Tsakane Mall Install 24000 BTU | Supply, delivery and installation of 1 x 24 000 BTU/h Samsung Midwall Unit complete. Supply, delivery and Installation of pump out unit complete with drain. Installation of electrical supply circuit from main DB to AC Unit. Installation of surge protection type 3. Commissioning of System and issuing of COC. Security Guard to be provided for the duration of the project. Work to take place on a weekend after operational hours - duration (16 hrs- 2 days) Unit is in stock - Max 1 week leadtime. |  |  | Region 1 |  | 21857X | 1000-70041-01 | Tsakane Mall-Cnr Modjadji & Malandela St-Tsakane | N | 2023-03-01 | 2023-05-31 |  | ASP-GS0613 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | L |  | GAMIETR | 2023-03-07 |  | 63546.13 | Approved at CB/BTB | 100 | 2023-03-02 | 2023-03-02 | 63546.13 | Approved | {"MANDT":"111","REFERENCE":90000149,"ONEVIEW":"Unknown","DATE01":"2022-12-21","DATE02":"2022-12-28","DATE03":"2023-01-18","DATE04":"2023-01-25","DATE05":"2023-02-15","DATE06":"2023-03-01","DATE07":"2023-05-31","DATE08":"2023-06-21","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-01","FORECAST_END":"2023-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000072554 | PHASE11 | 2023-03-01 | 2023-05-31 | PRESHANE MUNTHREE | Nokuthula Manzini | 2300095 |  |  |  |  | 2023-03-08 | 63546.14 | 0 |  |  | C000072554 | 55257.51 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000150 | Auckland Park Basement AIC Store rooms | Supply and build new 220mm brickwalls to use existing concrete soffit to create new 6 x 3.01m enclosed area, including brick force plastered both sides, narrow widths, reveals, lintels, openings, etc. Expanded polystyrene built vertically on joints in columns Plastering internal and external Supply and install 1 x new 1618 x 2038mm high single door to match existing as close as possible, including rebated steel frame, doors, ironmongery, etc. Painting to walls including door-frames and doors Supply and install Fire seals to brickwork around existing services fixed to u/s concrete soffit. Supply and install Two (2) LED light and 1 lever switch colour white including wiring. Install access control and cameras in regulatory store (by others) Clean area on completion of works |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-03-07 | 2023-05-31 |  | ASP-GS0614 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 0 |  | F |  | GAMIETR | 2023-03-07 |  | 43476.26 | Approved and supported by VP FM and Real Estate VP, | 100 | 2023-03-09 | 2023-03-17 | 499976.99 |  | {"MANDT":"111","REFERENCE":90000150,"ONEVIEW":"76849X","DATE01":"2022-12-27","DATE02":"2023-01-03","DATE03":"2023-01-24","DATE04":"2023-01-31","DATE05":"2023-02-21","DATE06":"2023-03-07","DATE07":"2023-05-31","DATE08":"2023-06-21","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-07","FORECAST_END":"2023-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIHBhcnRpYWxseSBpbnZvaWNlZCwgYXdhaXRpbmcgb3RoZXIgd29ya3MgdG8gYmUgY29tcGxldGVkLA==","RATING":"Low"} |  |  | C000072555 | PHASE10 | 2023-03-07 | 2023-05-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-03-08 | 434762.6 | 0 |  |  | C000072555 | 434762.6 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000151 | Alice Lane North Install new coffee bar door | Removal of existing hollow door and frame to be safely disposed. Supply and installation of 1 X Natural veneered solid timber door installed in aluminium frame with hinge blocks fitted to both sides. All to SABS 545 Security Guarding Service to be provided for the installation of the door. Work to take place after operational hours. Project duration: 2 days |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | N | 2022-08-30 |  |  | ASP-GS0615 | CRTD: |  | false | false |  | Roshen Aniruth |  |  | 0 |  | L |  | GAMIETR | 2023-03-08 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000151,"ONEVIEW":"70656X","DATE01":"2022-06-21","DATE02":"2022-06-28","DATE03":"2022-04-27","DATE04":"2022-05-02","DATE05":"2022-05-06","DATE06":"2022-06-16","DATE07":"2022-07-16","DATE08":"2022-09-21","DATE09":"2022-11-05","DATE10":"2022-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"193:7:-62:5:4:41:30:67:45:27","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-06-16","FORECAST_END":"2022-07-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBjbG9zZSBvdXQgZG9jdW1lbnRhdGlvbiBmcm9tIHN1cHBsaWVycw==","RATING":"Medium"} |  |  | C000069658 | PHASE09 | 2022-06-16 | 2022-07-16 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-02-22 | 21517 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000152 | Eastgate Dilaps/Reinstatem | Eastgate Dilaps/Reinstatement |  |  | Region 1 | Gauteng South | 76420X | 1000-70247-01 | ABSA Eastgate | N | 2023-03-09 | 2023-03-31 |  | ASP-GS0616 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 0 |  | L |  | GAMIETR | 2023-03-10 |  | 114074.96 | Approved by Lebusa M | 100 | 2023-03-10 | 2023-05-25 | 114074.96 | Approved | {"MANDT":"111","REFERENCE":90000152,"ONEVIEW":"76420X","DATE01":"2022-12-29","DATE02":"2023-01-05","DATE03":"2023-01-26","DATE04":"2023-02-02","DATE05":"2023-02-23","DATE06":"2023-03-09","DATE07":"2023-02-01","DATE08":"2023-02-22","DATE09":"2023-04-08","DATE10":"2023-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-09","FORECAST_END":"2023-02-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000089456 | PHASE11 | 2023-02-01 | 2023-02-02 | PRESHANE MUNTHREE | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-05 | 114074.96 | 0 |  |  | C000089456 | 99195.61 |  | 10353.72 |  | 0 | 0 |  | 0 |  | 0
90000153 | Absa Ridgeside | Absa Ridgeside - Installation of Dehumidifiers |  |  | Region 3 | KwaZulu-Natal | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2023-03-30 | 2023-04-28 |  | ASP-KZ0240 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-03-08 |  | 365666.65 | Approved at CB/BTB |  | 2023-03-16 | 2023-03-16 | 365666.65 | Approved | {"MANDT":"111","REFERENCE":90000153,"ONEVIEW":"22460X","DATE01":"2023-01-19","DATE02":"2023-02-16","DATE03":"2023-02-23","DATE04":"2023-02-23","DATE05":"2023-03-30","DATE06":"2023-03-30","DATE07":"1-01--2-2","DATE08":"0001-01-22","DATE09":"0001-03-08","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"1-01--2-2","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000074874 | PHASE11 | 2023-03-17 | 2023-07-12 | NANDE MAQUBELA | Floyd Mofokeng | 23000263 |  |  |  |  | 2023-03-17 | 317971 | 0 |  |  | C000074874 | 317971 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000154 | Absa Durban Phoenix- Dil | Absa Durban Phoenix- Dilaps |  |  | Region 3 | KwaZulu-Natal | 77874X | 1000-71197-01 | Durban Phoenix Plaza-Parthenon St-Durban | Y | 2023-04-28 | 2023-04-28 |  | ASP-KZ0241 | CRTD: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  | L | 2022-03-30 | NOMNGANGAL | 2023-03-08 |  | 0 |  |  |  |  | 0 | The project was cancelled therefore the Project number needs to be cancelled too, | {"MANDT":"111","REFERENCE":90000154,"ONEVIEW":"77874X","DATE01":"2023-02-17","DATE02":"2023-03-17","DATE03":"2023-03-24","DATE04":"2023-03-24","DATE05":"2023-04-28","DATE06":"2023-04-28","DATE07":"2023-05-19","DATE08":"2023-07-03","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE02 | 2023-04-28 | 2023-05-19 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000155 | Absa Shelly Beach - Replace Existing Gen | Absa Shelly Beach - Replace Existing Generator |  |  | Region 3 | KwaZulu-Natal | 77417X | 1000-71189-01 | Shelly Beach-East St-Shelly Beach |  | 2023-04-28 |  |  | ASP-KZ0242 | CLSD BUDG AVAC SETC: |  | R | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-03-08 |  | 91268.4 | Approved at CB/BTB |  | 2023-03-16 | 2023-03-16 | 91268.4 | Approved | {"MANDT":"111","REFERENCE":90000155,"ONEVIEW":"77417X","DATE01":"2023-02-17","DATE02":"2023-02-17","DATE03":"2023-02-28","DATE04":"2023-03-13","DATE05":"2023-03-17","DATE06":"2023-04-28","DATE07":"2023-07-17","DATE08":"2023-08-31","DATE09":"2023-09-12","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-07-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000074895 | PHASE11 | 2023-04-28 | 2023-07-17 | NANDE MAQUBELA | Floyd Mofokeng | 23000535 |  |  |  |  | 2023-03-17 | 79363.83 | 0 |  |  | C000074895 | 79363.83 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000156 | Noise Survey at various corporate sites | Noise Survey at various corporate sites |  |  | National | National | Various | 1000-70027-01 | Various Sites | N | 2023-04-03 | 2023-12-15 |  | ASP-N00051 | CLSD BUDG AVAC RESA SETC: |  | N | true |  | Lorri-Anne Louis |  |  | 0 |  | U |  | LOUISR | 2023-03-06 |  | 27007.75 | Approved at CB/BTB |  | 2023-03-09 | 2023-03-09 | 27007.75 | Approved | {"MANDT":"111","REFERENCE":90000156,"ONEVIEW":"Various","DATE01":"2023-01-23","DATE02":"2023-02-20","DATE03":"2023-02-27","DATE04":"2023-03-20","DATE05":"2023-04-03","DATE06":"2023-12-15","DATE07":"2024-01-05","DATE08":"2024-02-19","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":40,"PROG08":0,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":48,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-15","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000073567 | PHASE11 | 2023-12-15 | 2024-01-05 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-03-13 | 23485 | 0 |  |  | C000073567 | 23485 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000157 | Absa Wellington - HVAC Replacement BM Office | Absa Wellington - HVAC Replacement BM Office only |  |  | Region 2 | Western Cape | 77126X | 1000-70801-01 | Wellington-Cnr Church & Prince St-Wellington | N | 2023-04-30 |  |  | ASP-WC0268 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  |  |  | CEASARS | 2023-03-09 |  | 45570.55 | 2023.03.30: Approved by Kobus 2023.03.28: Supported by Kobus JvR | 100 | 2023-03-30 | 2023-03-30 | 45570.55 | Approved | {"MANDT":"111","REFERENCE":90000157,"ONEVIEW":"77126X","DATE01":"2023-01-19","DATE02":"2023-03-13","DATE03":"2023-03-21","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-04-19","DATE07":"2023-04-20","DATE08":"2023-05-16","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:53:8:9:0:20:1:26:45:0","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-19","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTYgTWF5IFBPQyBTdWJtaXR0ZWQ=","RATING":"Low"} |  |  | C000078213 | PHASE11 | 2023-04-19 | 2023-04-20 | RODERICK NEVAY | Michael Maluleka | 23000080 |  |  |  |  | 2023-04-05 | 39626.57 | 0 |  |  | C000078213 | 39626.57 | CIP2023XP | 4142.78 |  | 0 | 0 |  | 0 |  | 0
90000158 | Absa Scottburgh Mall - Install New HVAC | Absa Scottburgh Mall - Install New HVAC |  |  | Region 3 | KwaZulu-Natal | 77691X | 1000-71189-01 | Scottburgh Mall-Cnr Old Main Rd Margaret Ave-Scottburgh |  | 2023-04-28 |  |  | ALP-KZ2004 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 0 |  |  |  | NOMNGANGAL | 2023-03-08 |  | 0 | Approved at CB/BTB |  | 2023-05-25 | 2023-05-25 | 968574 | Approved | {"MANDT":"111","REFERENCE":90000158,"ONEVIEW":"77691X","DATE01":"2023-02-17","DATE02":"2023-03-17","DATE03":"2023-03-24","DATE04":"2023-03-24","DATE05":"2023-04-28","DATE06":"2023-04-28","DATE07":"1-01--2-2","DATE08":"0001-01-22","DATE09":"0001-03-08","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"1-01--2-2","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000122348 | PHASE06 | 2023-09-13 | 2023-09-29 | NANDE MAQUBELA | Juanita Van Coller | 23000055 |  |  |  |  | 2023-11-09 | 842238.48 | 0 |  |  | C000140802 | 842238.48 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000159 | Occupational Hygiene Surveys at retail & | Occupational Hygiene Surveys at retail & |  |  | National | National | Various | 1000-70027-01 | Various Sites | N | 2023-04-03 | 2023-12-15 |  | ALP-N00042 | CLSD BUDG AVAC RESA SETC: |  | N | true |  | Lorri-Anne Louis |  |  | 0 |  | U |  | LOUISR | 2023-03-06 |  | 2096543 | Approved at CB/BTB |  | 2023-03-13 | 2023-03-09 | 2096543 | Approved | {"MANDT":"111","REFERENCE":90000159,"ONEVIEW":"Various","DATE01":"2023-01-23","DATE02":"2023-02-20","DATE03":"2023-02-27","DATE04":"2023-03-20","DATE05":"2023-04-03","DATE06":"2023-12-15","DATE07":"2024-01-05","DATE08":"2024-02-19","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":40,"PROG08":0,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":48,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-15","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBzdGlsbCBpbnByb2dyZXNz","RATING":""} |  |  | C000082393 | PHASE11 | 2023-12-15 | 2024-01-05 | LUCIA AMUNGA | Michael Maluleka | 23000019 | 2023-04-24 | 2023-04-25 | 2023-04-24 | 2023-04-25 | 2023-05-02 | 1823080.87 | 0 |  |  | C000082393 | 1823080.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000160 | Bulk- Various Sites - Adhoc Priority Req | Provision for unforeseen requests which are critical items in minimizing disruptions to operations for replacement and installation of urgent and new critical items. Bulk- Various Sites - Adhoc Priority Req. WC - Absa Grabouw - Standby Systems - CB17 WC - Absa Grabouw - Cape West Electrical - CB17 WC - Absa Grabouw - Fidelity Security - CB17 EC - Absa Beaufort West - South Shore - CB18 EC - Absa Oudtshoorn - Vhasa Engineering - CB18 EC - Absa Riversdale - Vhasa Engineering - CB18 GS - Auckland Park CC - CCS CB17 GS - Auckland Park CC - Rationale CB17 GS Alice Lane South - IT Master GS Alice Lane South - Ks and Miles Distribution GS Alice Lane South - Stan Smith Electrical FS Absa Petrusburg - Installation of Surge Protector GS-Alice Lane North - UV Induction Jet Installation - Catervent GS-Alice Lane North - UV Induction Jet Installation - Afrifuture GS-Alice Lane North - UV Induction Jet Installation - Brasco Electrical GS-Alice Lane North - UV Induction Jet Installation - Protea Coin EC - Absa Patensie - HVAC - SanAir - CB20 EC - Absa Patensie - HVAC - Fest Fire - CB20 EC - Absa Nautilus Jeffreys Bay - UPS Connection - GT Electrical - CB20 EC - Absa Mqanduli - Water tank connection - Spot on Plumbing - CB20 WC - Absa Riviersonderend - HVAC Cages - AC Envirocare - CB20 WC - Absa Bridge Park - Emergency Lanterns - Natal Aircon/Regal - CB21 EC - Fort Beaufort - Vhasa Engineering - CB26 |  |  | National | National | Various | 1000-70027-01 | Various Sites | N | 2023-04-03 | 2023-12-15 |  | ALP-N00043 | REL BUDG AVAC RESA SETC: |  | N | true |  | Lorri-Anne Louis |  |  | 0 |  | U |  | LOUISR | 2023-03-07 |  | 1000000 | Approved at CB/BTB | 100 | 2023-02-16 | 2023-02-16 | 1000000 | Approved | {"MANDT":"111","REFERENCE":90000160,"ONEVIEW":"Various","DATE01":"2023-01-23","DATE02":"2023-02-20","DATE03":"2023-02-27","DATE04":"2023-03-20","DATE05":"2023-04-03","DATE06":"2023-04-04","DATE07":"2023-07-20","DATE08":"2023-09-29","DATE09":"2023-11-13","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":60,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"250:28:7:21:14:1:107:71:45:21","PROGRESS":61,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-04","FORECAST_END":"2023-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3QgUE9DIHBhY2tzIGFuZCBBZGhvYyByZXF1ZXN0cyBhcmUgYmVpbmcgZG9uZSB2aWEgUmVnaW9ucy4KQVM6IDAyLzA4LzIwMjMtIENoYW5nZWQgdGhlIENhc2ggRmxvdyBlbmQgZGF0ZSB0byAzMC4xMS4yMw==","RATING":""} |  |  | C000083244 | PHASE06 | 2023-04-04 | 2023-07-20 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-04-25 | 2023-05-03 |  |  | 2023-05-05 | 869565.22 | 0 |  |  | C000083244 | 869565.22 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000161 | Absa Robertson - HVAC Replacement | Absa Robertson - HVAC Replacement |  |  | Region 2 | Western Cape | 77877X | 1000-70863-01 | Robertson-Paul Kruger St-Robertson | N | 2023-04-24 |  |  | ALP-WC0020 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-03-09 |  | 700523.93 | 25 May Approved at BTB | 100 | 2023-05-25 | 2023-05-25 | 700523.93 | Approved | {"MANDT":"111","REFERENCE":90000161,"ONEVIEW":"77877X","DATE01":"2023-01-19","DATE02":"2023-03-03","DATE03":"2023-05-12","DATE04":"2023-05-25","DATE05":"2023-05-25","DATE06":"2023-07-26","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"2023-12-04","DATE12":"2023-12-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"315:43:70:13:0:62:65:21:45:23","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-26","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgT2N0IEZpbmFsIFBPQyBTdWJtaXR0ZWQgLSBSIDU2NSA0OTguNDcgU2VjdXJpdHkgYW5kIGNvbnRpbmdlbmN5IG5vdCB1dGlsaXNlZAoyMCBPY3QgU2lnbmVkIFBPQyByZWNlaXZlZCBzZW50IHRvIFBDIHRvIHNlbmQgdG8gRmluYW5jZQo5IE9jdCAtIEVuZ2luZWVyaW5nIHNpZ25vZmYgc2NoZWR1bGVkIGZvciAxMSBPQ1QKMiBPY3QgLSBBdHRlbmRlZCBvbiBieSBWZW5kb3IgRnJpZGF5IFBNIHRvIHZlcmlmeSBpZiBmdWxseSBvcGVyYXRpb25hbCBpbiBvcmRlciB0byBzaWduIG9mZi4KMjggU2VwdCAtIFZlbmRvciByZXR1cm5pbmcgdG8gc2l0ZSAyOSBTZXB0IHRvIHJlc29sdmUgc25hZwoyMiBTZXB0IE5vIFJvbGxvdmVyIFJpc2sKMjEgU2VwdCBWZW5kb3IgdG8gdmlzaXQgRnJpZGF5IDIyIFNlcHQKMTQgU2VwdCAtIFZlbmRvciBlbmdhZ2VkIE1pdHN1YmlzaGkgVG8gY29tZSB0byBzaXRlIHRvIGFzc2lzdAoxMSBTZXB0IC0gU2Vuc29ycyByZXBsYWNlZCAtIG9uZSB1bml0IHN0aWxsIEZhdWx0eSwgUE0gdG8gZW5nYWdlIE5pZm1hYwo1IFNlcHQgLSAgU25hZ3MgQmVpbmcgYWRkcmVzc2VkIC0gQnVybnQgc2Vuc29ycyBmb3IgdGhlIGNvbnRyb2xsZXJzIG9yZGVyZWQuIFByZXZpb3VzbHkgcmVtb3ZlZCBjaXJjdWl0IGJyZWFrZXIgaW5zdGFsbGVkIGZvciBBQyAzLkNvbXBsZXRpb24gYnkgMTUgU2VwdGVtYmVyCg==","RATING":"Low"} |  |  | C000096143 | PHASE11 | 2023-07-26 | 2023-09-29 | RODERICK NEVAY | Michael Maluleka | 23000111 | 2023-05-31 | 2023-06-28 | 2023-05-30 | 2023-05-31 | 2023-07-05 | 595286.2 | 0 |  |  | C000096143 | 595286.2 | CIP2023XP | 57778.32 |  | 0 | 0 |  | 0 |  | 0
90000162 | Absa Cogman Cntre Montagu - HVAC Replace | Absa Cogman Cntre Montagu - HVAC Replace |  |  | Region 2 | Western Cape | 77744X | 1000-70854-01 | Cogmans Centre-Cnr Bath & Mark St-Montagu | N | 2023-04-30 |  |  | ALP-WC0021 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 0 |  | L |  | CEASARS | 2023-03-09 |  | 951618.35 | Approved at BTB on 13 Jul 2023 | 100 | 2023-07-13 | 2023-07-13 | 951618.35 | Absa Ref : 240129_071 | {"MANDT":"111","REFERENCE":90000162,"ONEVIEW":"77744X","DATE01":"2023-03-09","DATE02":"2023-05-08","DATE03":"2023-07-03","DATE04":"2023-07-13","DATE05":"2023-07-13","DATE06":"2024-03-05","DATE07":"2024-03-11","DATE08":"2024-04-12","DATE09":"2024-05-27","DATE10":"2024-05-31","DATE11":"2024-05-27","DATE12":"2024-05-27","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"449:60:56:10:0:236:6:32:45:45:45:22","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-03-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBcHJpbCBBc3NldCBidWlsZCBvdXRzdGFuZGluZyBmcm9tIEJWIEVuZ2luZWVyaW5nCjA0IEFwcmlsLiBBc3NldCBidWlsZCByZXF1ZXN0ZWQuIFBPQyBDb21waWxhdGlvbiBpbiBwcm9ncmVzcwoyNSBNYXJjaCAtIEludm9pY2UgYW5kIGhhbmRvdmVyIGRvY3VtZW50cyBwZW5kaW5nCjE4IE1hcmNoIEZ1bGwgY2xvc2Ugb3V0IHBhY2sgcmVxdWVzdGVkIGZyb20gdGhlIFZlbmRvcgoxMSBNYXJjaCAtIFdvcmtzIGNvbXBsZXRlZCBIYW5kb3ZlciBzY2hlZHVsZWQgMTEgTWFyY2gKNCBNYXJjaCBTdGFydCBvbiBzaXRlIDUgTWFyY2gKMjIgRmViIER1ZSB0byBzdGFydCBvbiBzaXRlIC0gIDUgTWFyY2ggdG8gMTEgTWFyY2gKMjIgRmViIE9uIHRyYWNrIHRvIHN0YXJ0IDUgTWFyY2gKMTUgRmViIFdvcmsgdG8gYmUgc2NoZWR1bGVkIGZvciAwNSB0byAxMSBNYXJjaCAyMDI0CjEyIEZlYiAtIEtpY2sgb2ZmIG1lZXRpbmcgdG8gY29uZmlybSBkYXRlcwowOSBGZWIgMjAyNCBSb2xsb3ZlciBQTyBJc3N1ZWQgQzAwMDE0MDk2NgowOCBGZWIgUE0gdG8gZm9sbG93IHVwIG9uIHRoZSBwcm9ncmFtIGFuZCBzY2hlZHVsZSBraWNrIG9mZiBtZWV0aW5nCjcgRmViIE9IUyBBcHByb3ZhbCByZWNlaXZlZCBmcm9tIEFic2EgT0hTIC0gU2NoZWR1bGUgdG8gYmUgZmluYWxpc2VkIEFTQVAKNSBGZWIgLSBPSFMgaW4gUSBmb3IgcmV2aWV3CjEgRmViIEJhY2sgaW4gdGhlIHJldmlldyBRIHdpdGggQWJzYSBPSFMKMzAgSmFuIGJhY2sgaW4gUSB3aXRoIEFic2EgT0hTIGZvciByZXZpZXcKMjkgSmFuIEFic2EgT0hTIG5vdCB5ZXQgQXBwcm92ZWQKMjIgSmFuIC0gUE0gdG8gZm9sbG93IHVwIHdpdGggRmlyc3QgQ29vbCByZSBPSFMgc3VibWlzc2lvbgoxOCBEZWMgLSBQTSB0byBmb2xsb3cgd2l0aCBGaXJzdCBjb29sIHJlIE9IUwoxMyBEZWMgMm5kIE9IUyBzdWJtaXNzaW9uIGZhaWxlZCwgdG8gYmUgcmVkb25lIGFuZCByZXN1Ym1pdHRlZAoxMSBEZWMgT0hTIERvY3VtZW50cyBwbGFjZWQgaW4gbGluZSBmb3IgcmV2aWV3CjcgRGVjIFZlbmRvciB0byByZS11cGxvYWQgZG9jdW1lbnRzIHJlIG5hbWluZyBjb252ZW50aW9ucwo0IERlYyAgUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yIHJlIE9IUwozMCBOb3YgT0hTIHN0aWxsIG91dHN0YW5kaW5nCjI2IE5vdiBBYnNhIE9IUyBhcHByb3ZhbCBpbiBzdGlsbCBwcm9ncmVzcwoyMyBOb3YgVmVuZG9yIHVwbG9hZGVkIGRvY3VtZW50cyBmb3IgcmV2aWV3LiBBYnNhIE9IUyByZXF1ZXN0ZWQgdGhhdCB0aGV5IG1ha2UgY2hhbmdlcyBiZWZvcmUgdGhleSBjYW4gcGxhY2UgdGhlbSBpbiBsaW5lIGZvciByZXZpZXcKMjAgTm92IC0gVmVuZG9yIGFwcG9pbnRlZCBjb25zdWx0YW50IHRvIGFzc2lzdCB3aXRoIE9IUywgcmV2aXNpb24gdG8gYmUgc3VibWl0dGVkCjE2IE5vdiBWZW5kb3Igc3RpbGwgYnVzeSB3aXRoIHRoZSBmaW5kaW5ncyAtIENvbnN1bHRhbnQgYXBwb2ludGVkIHRvIGFzc2lzdAo5IE5vdiAtIE9IUyByZXZpc2lvbiB1bmRlciB3YXkgVmVuZG9yIG9yIHJlc3VibWl0IG9uIGZpbmRpbmdzCjYgTm92IC0gQWJzYSBPSFMgZmVlZGJhY2sgcmVjZWl2ZWQgZmlsZSBmYWlsZWQgdmVuZG9yIGNvbnRhY3RlZCB0byBhZGRyZXNzCjEgTm92IEZvbGxvd2VkIHVwIHJlIE9IUyBpbmRpY2F0ZWQgb3V0Y29tZSB0byBiZSBzaGFyZWQgNiBOT1YKMzAgT2N0IFRvIGZvbGxvdyB1cCB3aXRoICBBYnNhIE9IUywgUE0gdG8gYWR2aXNlIHdoZW4gc3VibWl0dGVkCjIzIE9jdCAtIFBNIHRvIHJlcXVlc3QgVmVuZG9yIHRvIGZvbGxvdyBVUCBhcyBPSFMgd2lsbCBub3QgYWNjZXB0IGVtYWlsIGZyb20gUE0gaWYgRGlyZWN0IGFwcG9pbnRtZW50LgoxOSBPY3QgRm9sbG93IHVwIHdpdGggT0hTIAoxMiBPY3QgLSBCYWNrbG9nIGZyb20gT0hTIGZvbGxvd2luZyB1cCBhY2NvcmRpbmdseQo5IE9jdCBGZWVkYmFjayBwZW5kaW5nIGZyb20gT0hTIHJlIG5hbWluZyBjb252ZW50aW9uIG9mIGRvY3VtZW50cyB0byBiZSBhZGRyZXNzZWQKNSBTZXB0IC0gRm9sbG93IHVwIHdpdGggT0hTCjI4IFNlcHQgT0hTIGRvY3VtZW50cyB0byBiZSB1cGxvYWRlZCB0b2RheQoyMiBTZXB0IC0gT0hTIHBsYW5uZWQgdG8gYmUgc3VibWl0dGVkIGJ5IDI3IFNlcHQgYXMgZmlzdCB0aW1lIHN1Ym1pc3Npb24gdG8gQWJzYSBCViBPSFMgYXNzaXN0aW5nLiBGaW5hbmNpYWwgUm9sbG92ZXIgZXhwZWN0ZWQKMjEgU2VwdCAtIEZpcnN0IENvbGwgZG9jdW1lbnRzIHBlbmRpbmcgaW4gb3JkZXIgdG8gc3VibWl0IHRvIEFic2EKMTggU2VwdCAtIE9IUyB0byBiZSByZXZpc2l0ZWQgYXMgbm90IGluIHRlcm1zIG9mIHJlcXVpcmVtZW50cwoxNCBTZXB0IC0gV0EgYW5kIFNGIGFyZSBzaWduZWQsIE9IUyB0byBiZSBmaW5hbGlzZWQKMTEgU2VwdCAtIFBNIHRvIGZvbGxvdyB1cCB3aXRoIFZlbmRvciByZSBPSFMgZG9jdW1lbnRzCjcgU2VwdCBSZXBsYWNpbmcgU2Vuc29ycyA4IFNlcHQgYW5kIGZpbmFsIHRlc3RpbmcgY29tbWlzc2lvbmluZyBmb2xsb3cKNSBTZXB0IEFic2EgT0hTIGFwcHJvdmFsIHByb2Nlc3MgaXMgMiB3ZWVrcy4gTmV3IGNvbXBsZXRpb24gZGF0ZSBpcyAzMCBPY3RvYmVyIDIwMjMKMzEgQXVnIFZlbmRvciB0byB1cGxvYWQgdG8gYWJzIGZyb20gMSBTZXB0CjMwIE9IUyBTdWJtaXNzaW9ucyBpbiBwcm9ncmVzcyB3aXRoIEFic2EKMjYgQXVnIEJWIFBPJ3MgSXNzdWVkIC0gNDUwMDg1NDcxOSBDYXBlIFdlc3QsIDQ1MDA4NTQ3MjEgRWRlbiwgNDUwMDg1NDcxOCBGaXJzdCBDb29sCjI0IFZlbmRvciBQTydzIHJlcXVlc3RlZCwgT0hTIHRvIGJlIGZpbmFsaXNlZAoyMSBBdWcgQWJzYSBQTyBSZWNlaXZlZCBDMDAwMTA1MjI4CjIxIEF1ZyBTaWduZWQgV0EgYW5kIFNGIHJlY2VpdmVkIEFic2EgUE8gcmVxdWVzdGVkCjE0IEF1ZyAtIFNpZ25lZCBjb3B5J3MgcmVjZWl2ZWQsIHNlbnQgdG8gQWJzYSBmb3IgYXBwcm92YWwKMTEgQXVnIEFsbCBhcHByb3ZlZCAtIFdpdGggQlYgZm9yIGZpbmFsIFNpZ25vZmYKMyBBdWcgLSBEb2N1bWVudHMgZnJvbSBQcm9jdXJlbWVudCB0byBBYnNhIGxlZ2FsIGZvciBsYXN0IGNoZWNrcwoyMCBKdWx5IC0gV0EgYW5kIFNGIHRvIGJlIHN1Ym1pdHRlZCB0byBCViBMZWdhbCBGaXJzdC4gCjE3IEp1bHkgU2lnbmVkIERlY2tzIHJlY2VpdmVkIEFic2EgUE8ncyB0byBiZSByZXF1ZXN0ZWQKMTcgSnVsIFNpZ25lZCBQYWNrcyBwZW5kaW5nIFdBIGFuZCBTZiB0byBiZSBzdWJtaXR0ZWQgZm9yIGFwcHJvdmFsCgoxMyBKdWx5IEFwcHJvdmVkIGF0IENCMjYvQlRCMjYgMTMgSnVsCjMgSnVseSAtIFJQTSAtIHRvIGZvcndhcmRzIHRvIEFic2EgRW5naW5lZXJpbmcgZm9yIHN1cHBvcnQKMjggSnVuZSBGaW5hbCBQcm9jdXJlbWVudCBhcHByb3ZhbCByZXF1ZXN0ZWQKMTkgSnVuZSBVcGRhdGVkIEJDIHBhY2sgcmVjZWl2ZWQgLSBFbmdpbmVlcmluZyB0byBiZSBjb25zdWx0ZWQgcmUgQnVkZ2V0CjggSnVuZSB0byBiZSBzdWJtaXR0ZWQgZm9yIGFwcHJvdmFsIHdlZWsgb2YgdGhlIDEydGggSnVuZSBDQjIyCjUgSnVuZSAtIEJUQiBQYXBlciB0byBiZSBwcmVzZW50ZWQgIC0gQnVkZ2V0ID8gY2FuIGl0IGJlIGRvbmUgMjAyNAogMzEgTWF5IC0gVG8gYmUgcHJlc2VudGVkIG5leHQgd2VlayBUdWVzZGF5IDZ0aCBKdW5lCjI1IE1heSBDb3N0cyBkdWUgMjUgTWF5CjIyIE1heSAtIENvc3RzIGR1ZSAyNSBNYXkKMTggTWF5IFVwZGF0ZWQgcXVvdGVzIHRvIGJlIHJlcXVlc3RlZCByZSBzaXplcyBvZiB0aGUgdW5pdHMKMTEgTWF5IFN1Ym1pdHRlZCBDYWxjdWxhdGlvbnMgdG8gRU5HIGZvciByZXZpZXcKOCBNYXkgLSBDYWxjdWxhdGlvbnMgdG8gYmUgY29uZmlybWVkIGJ5IEVuZ2luZWVyaW5nIGFzIGNlcnRhaW4gdW5pdHMgdG8gYmUgZG93bnNpemVkCjQgTWF5IC0gSFZBQyBDYWxjdWxhdGlvbiByZWNlaXZlZCAtIFBNIHRvIGNvc3RpbmcKMjQgQXByaWwgU2l6ZXMgdG8gYmUgY29uZmlybWVkIHJlIHNpemVzIG9mIFVuaXRzCjE3IEFwcmlsIE5vIENhbGN1bGF0aW9ucyByZWNlaXZlZCBmcm9tIFRTTSBpbiBvcmRlciB0byB2ZXJpZnkgRXF1aXBtZW50IHNpemVzCjMgQXByIFBNIHRvIGZvbGxvdyB1cCByZSBjYWxjdWxhdGlvbnMgdG8gY29uZmlybSBTcGVjaWZpY2F0aW9ucwozMCBNYXIgLSBTaXRlIHZpc2l0IGNvbmR1Y3RlZCBmb3Igc2l6aW5nIEJUQiBwYWNrIHRvIGJlIGZpbmFsaXNlZCB0byBzaGFyZSB3aXRoIEFic2EgYnkgNiBBcHJpbAoyMyBNYXIgLSBUU00gdG8gdmlzaXQgd2VlayBvZiB0aGUgMjd0aCB0byBjb21wbGV0ZSBDYWxjdWxhdGlvbnMKMjAgTWFyIFF1b3RlcyByZWNlaXZlZCBCVEIgUGFjayBpbiBwcm9ncmVzcwoxNiBNYXIgSFZBQyBxdW90ZXMgcmVjZWl2ZWQKMTMgTWFyIFF1b3RlcyBkdWUgMTQgTWFyCjkgTWFyIFByaW9yaXRpc2VkIGJ5IEVuZ2luZWVyaW5nIGZvciBSZXBsYWNlbWVudA==","RATING":"Medium"} |  |  | C000105228 | PHASE08 | 2024-03-05 | 2024-03-11 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-21 | 827494.22 | 0 |  |  | C000105228 | 827494.22 |  | 81163.93 |  | 0 | 0 | C000140966 | 951618.35 |  | 0 |  |  | 2024-02-09
90000163 | Smart electrical and water meters rollout (2023) | 2023 National - Smart metering rollout |  |  | Energy | National | Various | Various | Various Sites | N | 2023-02-06 | 2023-03-31 |  | ABS-G00008 | REL BUDG AVAC RESA SETC: |  | false | false |  | Wesigye Mukuru |  | Supply, install, commission and manage smart meters at 136 sites in Absas retail portfolio | 0 |  |  |  | DUPREEZK | 2023-02-06 |  | 6426107.2 | Enhanced sustainability/ ESG reporting and utility bill validation | 100 | 2022-11-25 | 2022-12-01 | 6426107.2 | Approved | {"MANDT":"111","REFERENCE":90000163,"ONEVIEW":"Various","DATE01":"2022-11-28","DATE02":"2022-12-05","DATE03":"2022-12-26","DATE04":"2023-01-02","DATE05":"2023-01-23","DATE06":"2023-05-08","DATE07":"2023-07-03","DATE08":"2023-07-28","DATE09":"2023-09-15","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"319:7:21:7:21:105:56:25:49:0","PROGRESS":87,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-08","FORECAST_END":"2023-07-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"SW5zdGFsbGF0aW9ucyB1bmRlcndheQ==","RATING":""} |  |  | C000068007 | PHASE10 | 2023-05-08 | 2023-07-03 | ONISMS MANYEWE | Nokuthula Manzini | 0 | 2023-01-30 | 2023-02-02 | 2023-01-23 | 2023-01-30 | 2023-02-14 | 5587919.3 | 0 |  |  | C000068007 | 5587919.3 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000164 | ATN Relocation of smart meters | Absa Towers North - Relocation of smart meters from old to new MV chamber |  |  | Energy | Gauteng | 77381X | 1000-71397-01 | Absa Towers North | U | 2023-03-07 | 2023-03-31 |  | ABS-G00009 | CLSD RESA SETC: |  | false | false |  | Wesigye Mukuru |  | Funding for this work though SDE (main contractor) | 0 |  | F |  | DUPREEZK | 2023-03-07 |  | 33584.67 | BFM was the subcontractor to another Absa vendor (SDE) and as such there is no CIP approval for this project | 100 |  |  | 33584.67 | BFM was the subcontractor to another Absa vendor (SDE) and as such there is no CIP approval for this project. Approved by CRES Engineering | {"MANDT":"111","REFERENCE":90000164,"ONEVIEW":"77381X","DATE01":"2022-12-27","DATE02":"2023-01-03","DATE03":"2023-01-24","DATE04":"2023-01-31","DATE05":"2023-02-21","DATE06":"2023-04-05","DATE07":"2023-03-11","DATE08":"2023-03-16","DATE09":"2023-05-04","DATE10":"2023-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"185:7:21:7:21:43:-25:5:49:28","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-03-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U2l0ZSB3YXMgZGVlbmVyZ2l6ZWQgd2hpbGUgd29yayBpcyBiZWluZyBwZXJmb3JtZWQgc28gbG93IHJpc2sgZXhlcmNpc2UuClByb2plY3QgY29tcGxldGVkIGFuZCBpbnZvaWNlZCBhbmQgY2xvc2VkIG91dC4=","RATING":"Low"} |  |  | 1305 | PHASE11 | 2023-04-05 | 2023-03-11 | OTHER | Nokuthula Manzini | 0 | [5 empty] | 29204.06 | 0 |  |  | 1305 | 29204.06 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000165 | Absa Bloemfontein Forum - Minor Works | Absa Bloemfontein Forum - Minor Works |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein |  | 2023-04-24 |  |  | ASP-CR0410 | CLSD BUDG AVAC SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | MOKOENAM2 | 2023-03-20 | D | 6040.95 | 2023.03.30: Approved by Kobus 2023.03.28: Supported by Kobus JvR | 1 | 2023-03-30 | 2023-03-30 | 6040.95 | Approved | {"MANDT":"111","REFERENCE":90000165,"ONEVIEW":"22161X","DATE01":"2023-02-13","DATE02":"2023-03-13","DATE03":"2023-03-20","DATE04":"2023-03-20","DATE05":"2023-04-24","DATE06":"2023-05-24","DATE07":"2023-06-14","DATE08":"2023-07-29","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-24","FORECAST_END":"2023-06-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  | C000075590 | PHASE11 | 2023-05-24 | 2023-06-14 | NANDE MAQUBELA | floyd mofokeng | 23000085 |  |  |  |  | 2023-03-23 | 5253 | 0 |  |  | C000075590 | 5253 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000166 | Absa University of Free State - HVAC Ins | Absa University of Free State - HVAC Ins |  |  | Region 3 | Free State | 78702X | 1000-71595-01 | University of the Free State Bloemfontei-Nelson Mandela Dr-Bloemfontein | Y | 2023-04-26 | 2023-05-17 |  | ASP-CR0411 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2023-07-30 | MOKOENAM2 | 2023-03-22 | D | 20793.96 | 2023.03.30: Approved by Kobus Supported by BFM Engineering | 100 | 2023-04-04 | 2023-03-30 | 20793.96 | Approved | {"MANDT":"111","REFERENCE":90000166,"ONEVIEW":"78702X","DATE01":"2023-02-15","DATE02":"2023-03-15","DATE03":"2023-03-22","DATE04":"2023-03-22","DATE05":"2023-04-26","DATE06":"2023-05-17","DATE07":"2023-06-07","DATE08":"2023-07-22","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-17","FORECAST_END":"2023-06-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000078251 | PHASE11 | 2023-05-17 | 2023-06-07 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-05 | 18081.7 | 0 |  |  | C000078251 | 18081.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000167 | 51 Govan Mbeki - Modify Teller Counter | 51 Govan Mbeki - Modify Teller Counter |  |  | Region 2 | Eastern Cape | 22165X | 1000-70940-01 | 51 Govan Mbeki Avenue Building-Govan Mbeki Ave-Port Elizabeth | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0284 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-03-20 | D | 488823.33 | 2023.06.15: Approved by Conrad M as per email 2023.06.13: Supported by Judith B & Ilana vdW | 100 | 2023-06-15 | 2023-06-15 | 488823.33 | Approved | {"MANDT":"111","REFERENCE":90000167,"ONEVIEW":"22165X","DATE01":"2023-02-14","DATE02":"2023-04-03","DATE03":"2023-05-24","DATE04":"2023-06-15","DATE05":"2023-06-15","DATE06":"2023-07-17","DATE07":"2023-07-24","DATE08":"2023-08-11","DATE09":"2023-09-25","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"228:48:51:22:0:32:7:18:45:2","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-07-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgQXVnIEZpbmFsIFBPQyBTdWJtaXR0ZWQgUiAxMDkgNjc4Ljc0IC0gVG90YWwgUiA0MzMgNzM3LjY1CjIgQXVnIFBhcnQgMSBTdWJtaXR0ZWQgdG8gUEMgdG8gc3VibWl0IHRvIEZpbmFuY2UgUiAzMjQgMDU4LjkwCg==","RATING":"Low"} |  |  | C000092900 | PHASE11 | 2023-07-17 | 2023-07-24 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-06-20 | 425063.77 | 0 |  |  | C000092900 | 425063.77 |  | 23000 |  | 0 | 0 |  | 0 |  | 0
90000168 | 85 Oxford Street - East London - HVAC - UPS/DB Room | 85 Oxford Street - East London - HVAC - UPS/DB Room |  |  | Region 2 | Eastern Cape | 79244X | 1000-71469-01 | 85 Oxford Street-Oxford St-East London | Y | 2023-12-31 | 2023-12-31 |  | ASP-EC0285 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-03-20 | D | 42581.41 | 2023.04.14: Approved by Kous JvR 2023.04.11: Supported by Rob L | 100 | 2023-04-14 | 2023-04-14 | 42581.41 | Approved | {"MANDT":"111","REFERENCE":90000168,"ONEVIEW":"79244X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-04-14","DATE06":"2023-05-18","DATE07":"2023-06-14","DATE08":"2023-08-15","DATE09":"2023-09-15","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"174:7:21:7:0:34:27:62:31:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-18","FORECAST_END":"2023-06-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgQXVnIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000080525 | PHASE11 | 2023-05-18 | 2023-06-14 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-04-19 | 37027.31 | 0 |  |  | C000080525 | 37027.31 |  | 2341.03 |  | 0 | 0 |  | 0 |  | 0
90000169 | Absa Bizana - Straighten ATM wall | Absa Bizana - Straighten ATM wall |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0286 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-03-20 | D | 231226.14 | 2023.05.31: Approved by Conrad M as per email 2023.05.30: Supported by Judith B | 100 | 2023-06-01 | 2023-06-01 | 231226.14 | Contingency utilized remaining - R 5 089.41 Incl Vat | {"MANDT":"111","REFERENCE":90000169,"ONEVIEW":"70633X","DATE01":"2023-04-19","DATE02":"2023-04-26","DATE03":"2023-05-22","DATE04":"2023-06-01","DATE05":"2023-06-01","DATE06":"2023-07-10","DATE07":"2023-07-18","DATE08":"2023-08-08","DATE09":"2023-09-22","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:26:10:0:39:8:21:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-10","FORECAST_END":"2023-07-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFBhcnQgMiBTdWJtaXR0ZWQgMjUgQXVnIC0gMTMgOTI4LjgwIFNlY3V0ZWwgClBPQyBQYXJ0IDEgU3VibWl0dGVkIDMgQXVnIC0gUjE4MCAyNDkuMzE=","RATING":"Low"} |  |  | C000089061 | PHASE11 | 2023-07-10 | 2023-07-18 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-01 | 201066.21 | 0 |  |  | C000089061 | 201066.21 |  | 9424.9 |  | 0 | 0 |  | 0 |  | 0
90000170 | Absa Port Alfred - HVAC - Enterprise Office and Banking Hall | Absa Port Alfred - HVAC - Enterprise Office and Banking Hall |  |  | Region 2 | Eastern Cape | 76483X | 1000-71011-01 | Neave Stotter Chambers-Cnr Campbell & Main St-Port Alfred | Y | 2023-12-31 | 2023-12-31 |  | ASP-EC0287 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  | Know as Absa Port Alfred | 2023 |  | L |  | CEASARS | 2023-03-20 | D | 128316.57 | 2023.04.14: Approved by Kous JvR 2023.04.11: Supported by Rob L | 100 | 2023-04-14 | 2023-04-14 | 128316.57 | Approved | {"MANDT":"111","REFERENCE":90000170,"ONEVIEW":"76483X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-04-14","DATE06":"2023-05-17","DATE07":"2023-07-20","DATE08":"2023-08-17","DATE09":"2023-10-01","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"204:7:21:7:0:33:64:28:45:6","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-17","FORECAST_END":"2023-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTcgQXVnIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000080433 | PHASE11 | 2023-05-17 | 2023-07-20 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-04-18 | 111579.63 | 0 |  |  | C000080433 | 111579.63 |  | 6110.31 |  | 0 | 0 |  | 0 |  | 0
90000171 | Absa Stone Towers ShopCentr Add.Plugs | Absa Stone Towers Shop Centr - Add.Plugs |  |  | Region 2 | Eastern Cape | 78247X | 1000-71463-01 | Stone Towers Shopping Centre - King Williamstown | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0288 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-03-20 | D | 21304.24 | 2023.04.14: Approved by Kous JvR 2023.04.11: Supported by Rob L | 100 | 2023-04-13 | 2023-04-14 | 21304.24 | Approved | {"MANDT":"111","REFERENCE":90000171,"ONEVIEW":"78247X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-13","DATE05":"2023-04-13","DATE06":"2023-05-03","DATE07":"2023-05-03","DATE08":"2023-05-31","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:6:0:20:0:28:30:25","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-03","FORECAST_END":"2023-05-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgTWF5IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000080526 | PHASE11 | 2023-05-03 | 2023-05-03 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-19 | 18525.43 | 0 |  |  | C000080526 | 18525.43 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000172 | Absa 106 York Street - Replace AC units | Absa 106 York Street - Replace AC units |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street-York St-George | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0289 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 482496.41 | 2023.06.15: Approved by Kobus JvR as per email 2023.06.13: Supported by Rob L | 100 | 2023-06-15 | 2023-06-15 | 482496.41 | Approved | {"MANDT":"111","REFERENCE":90000172,"ONEVIEW":"79394X","DATE01":"2023-01-19","DATE02":"2023-04-24","DATE03":"2023-06-08","DATE04":"2023-06-15","DATE05":"2023-06-15","DATE06":"2023-07-21","DATE07":"2023-08-15","DATE08":"2023-09-05","DATE09":"2023-09-30","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:95:45:7:0:36:25:21:25:0","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-21","FORECAST_END":"2023-08-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVsIEVxdWlwbWVudCBvbiBPcmRlcg==","RATING":""} |  |  | C000092901 | PHASE11 | 2023-08-15 | 2023-08-18 | RODERICK NEVAY | Juanita van Coller | 23000115 |  |  |  |  | 2023-06-20 | 419562.1 | 0 |  |  | C000092901 | 419562.1 | CIP2023XP | 22976.02 |  | 0 | 0 |  | 0 |  | 0
90000173 | Absa Barkly East - Waterproofing: Warranty Maintenance | Absa Barkly East - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 78658X | 1000-71050-01 | Absa Barkly East-Cole St-Barkly East | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0290 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 91096.34 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 91096.34 | Approved | {"MANDT":"111","REFERENCE":90000173,"ONEVIEW":"78658X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-03-23","DATE04":"2023-03-23","DATE05":"2023-03-30","DATE06":"2023-05-23","DATE07":"2023-05-23","DATE08":"2023-06-21","DATE09":"2023-06-30","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"193:7:56:0:7:54:0:29:9:3","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-23","FORECAST_END":"2023-05-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgSnVuZSBQT0MgU3VibWl0dGVkIHRvIGZpbmFuY2U=","RATING":"Medium"} |  |  | C000078329 | PHASE11 | 2023-05-23 | 2023-05-23 | RODERICK NEVAY | Nokuthula Manzini | 23000381 |  |  |  |  | 2023-04-05 | 79214.21 | 0 |  |  | C000078329 | 79214.21 |  | 7676.94 |  | 0 | 0 |  | 0 |  | 0
90000174 | Absa Beaufort West - Waterproofing: Warranty Maintenance | Absa Beaufort West - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 77401X | 1000-71026-01 | Absa Beaufort West-Donkin St-Beaufort West | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0291 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 43070.97 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 43070.97 | Approved | {"MANDT":"111","REFERENCE":90000174,"ONEVIEW":"77401X","DATE01":"2023-01-19","DATE02":"2023-01-25","DATE03":"2023-03-03","DATE04":"2023-03-23","DATE05":"2023-03-30","DATE06":"2023-05-10","DATE07":"2023-05-11","DATE08":"2023-06-29","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:6:37:20:7:41:1:49:32:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-10","FORECAST_END":"2023-05-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkgSnVuZSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000078299 | PHASE11 | 2023-05-10 | 2023-05-11 | RODERICK NEVAY | Juanita van Coller | 23000350 |  |  |  |  | 2023-04-05 | 37453.02 | 0 |  |  | C000078299 | 37453.02 |  | 3438.27 |  | 0 | 0 |  | 0 |  | 0
90000175 | Absa Burgersdorp - Waterproofing: Warranty Maintenance | Absa Burgersdorp - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 79098X | 1000-71063-01 | Absa Burgersdorp-Pieter Retief St-Burgersdorp | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0292 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 113899.62 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 113899.62 | Approved | {"MANDT":"111","REFERENCE":90000175,"ONEVIEW":"79098X","DATE01":"2023-01-19","DATE02":"2023-01-24","DATE03":"2023-03-23","DATE04":"2023-03-23","DATE05":"2023-03-30","DATE06":"2023-05-24","DATE07":"2023-05-25","DATE08":"2023-07-06","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:5:58:0:7:55:1:42:25:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-24","FORECAST_END":"2023-05-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBKdWx5IFBPQyBwYWNrIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Low"} |  |  | C000078331 | PHASE11 | 2023-05-24 | 2023-05-25 | RODERICK NEVAY | Juanita van Coller | 23000354 |  |  |  |  | 2023-04-05 | 99043.15 | 0 |  |  | C000078331 | 99043.15 |  | 9854.51 |  | 0 | 0 |  | 0 |  | 0
90000176 | Absa Cradock - Waterproofing: Warranty Maintenance | Absa Cradock - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 76934X | 1000-71022-01 | Absa Cradock-Adderley St-Cradock | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0293 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 42127.92 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 42127.92 | Approved | {"MANDT":"111","REFERENCE":90000176,"ONEVIEW":"76934X","DATE01":"2023-01-19","DATE02":"2023-01-24","DATE03":"2023-02-25","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-05-11","DATE07":"2023-05-12","DATE08":"2023-06-29","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:5:32:33:0:42:1:48:32:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-11","FORECAST_END":"2023-05-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkgSnVuZSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000078330 | PHASE11 | 2023-05-11 | 2023-05-12 | RODERICK NEVAY | Juanita van Coller | 23000420 |  |  |  |  | 2023-04-05 | 36632.97 | 0 |  |  | C000078330 | 36632.97 |  | 3493.45 |  | 0 | 0 |  | 0 |  | 0
90000177 | Absa Grahamstown - Waterproofing: Warranty Maintenance | Absa Grahamstown - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 77512X | 1000-71029-01 | Absa Grahamstown-High St-Grahamstown | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0294 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 33058.36 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 33058.36 | Approved | {"MANDT":"111","REFERENCE":90000177,"ONEVIEW":"77512X","DATE01":"2023-01-19","DATE02":"2023-01-24","DATE03":"2023-02-25","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-05-15","DATE07":"2023-06-07","DATE08":"2023-08-03","DATE09":"2023-08-03","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"193:5:32:33:0:46:23:57:0:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-06-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBBdWcgUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNlCjE5IEp1bHkgLSBQT0Mgd2l0aCBFbmdpbmVlcmluZyBmb3IgU2lnbm9mZg==","RATING":"Low"} |  |  | C000078334 | PHASE11 | 2023-05-15 | 2023-06-07 | RODERICK NEVAY | Juanita van Coller | 23000337 |  |  |  |  | 2023-04-05 | 28746.4 | 0 |  |  | C000078334 | 28746.4 |  | 2900.76 |  | 0 | 0 |  | 0 |  | 0
90000178 | Absa King Williams Town - Waterproofing Warranty Maintenance | Absa King Williams Town - Waterproofing Warranty Maintenance |  |  | Region 2 | Eastern Cape | 78329X | 1000-71043-01 | Absa King William s Town-Cnr Cathcart & Maclean St-King William s Town | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0295 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 91155.78 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 91155.78 | Approved | {"MANDT":"111","REFERENCE":90000178,"ONEVIEW":"78329X","DATE01":"2023-01-19","DATE02":"2023-01-23","DATE03":"2023-02-28","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-05-15","DATE07":"2023-05-26","DATE08":"2023-07-28","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:4:36:30:0:46:11:63:34:0","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-05-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHdpdGggRW5naW5lZXJpbmcgZm9yIFNpZ25vZmY=","RATING":"Low"} |  |  | C000078339 | PHASE11 | 2023-05-15 | 2023-05-26 | RODERICK NEVAY | Juanita van Coller | 23000336 |  |  |  |  | 2023-04-05 | 79265.9 | 0 |  |  | C000078339 | 79265.89 |  | 7950.53 |  | 0 | 0 |  | 0 |  | 0
90000179 | Absa Willowmore - Waterproofing: Warranty Maintenance | Absa Willowmore - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 77596X | 1000-71031-01 | Absa Willowmore-Knysna St-Willowmore | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0296 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 21113.94 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 21113.94 | Approved | {"MANDT":"111","REFERENCE":90000179,"ONEVIEW":"77596X","DATE01":"2023-01-19","DATE02":"2023-01-24","DATE03":"2023-02-25","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-05-02","DATE07":"2023-05-09","DATE08":"2023-08-14","DATE09":"2023-08-14","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:5:32:33:0:33:7:97:0:15","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-02","FORECAST_END":"2023-05-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgQXVnIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000078335 | PHASE11 | 2023-05-02 | 2023-05-09 | RODERICK NEVAY | Juanita van Coller | 23000356 |  |  |  |  | 2023-04-05 | 18359.95 | 0 |  |  | C000078335 | 18359.95 |  | 1678.54 |  | 0 | 0 |  | 0 |  | 0
90000180 | Moffett Office Park - Create large meeti | Moffett Office Park - Create large meeti |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth |  | 2023-12-31 | 2023-12-31 |  | ASP-EC0297 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-03-20 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-06-12 | 2023-07-23 | RODERICK NEVAY | nokuthula manzini | 23000078 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000181 | Absa Aliwal North - Waterproofing: Warranty Maintenance | Absa Aliwal North - Waterproofing: Warranty Maintenance |  |  | Region 2 | Eastern Cape | 79209X | 1000-71069-01 | Absa Aliwal North-Somerset St-Aliwal North | N | 2023-06-01 | 2023-12-31 |  | ASP-EC0298 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 77873.44 | 2023.03.30: Approved by Kobus | 100 | 2023-03-30 | 2023-03-30 | 77873.44 | Approved | {"MANDT":"111","REFERENCE":90000181,"ONEVIEW":"79209X","DATE01":"2023-01-19","DATE02":"2023-01-24","DATE03":"2023-02-25","DATE04":"2023-03-30","DATE05":"2023-03-30","DATE06":"2023-05-24","DATE07":"2023-05-25","DATE08":"2023-07-27","DATE09":"2023-10-12","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:5:32:33:0:55:1:63:77:0","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-24","FORECAST_END":"2023-05-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjcgSnVseSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000078327 | PHASE11 | 2023-05-24 | 2023-05-25 | RODERICK NEVAY | Juanita van Coller | 23000359 |  |  |  |  | 2023-04-05 | 67716.03 | 0 |  |  | C000078327 | 67716.03 |  | 6543.04 |  | 0 | 0 |  | 0 |  | 0
90000182 | Absa Prins Albert - Waterproofing: Warr | Absa Prins Albert - Waterproofing: Warr |  |  | Region 2 | Eastern Cape | 77111X | 1000-71024-01 | Absa Prins Albert-Church St-Prins Albert | N | 2023-12-31 | 2023-12-31 |  | ASP-EC0299 | CRTD BUDG AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-03-20 | D | 0 |  | 1 |  |  | 0 | Reallocated | {"MANDT":"111","REFERENCE":90000182,"ONEVIEW":"77111X","DATE01":"2023-10-22","DATE02":"2023-02-06","DATE03":"2023-02-27","DATE04":"2023-02-27","DATE05":"2023-03-13","DATE06":"2023-04-03","DATE07":"2023-05-01","DATE08":"2024-01-21","DATE09":"2023-06-30","DATE10":"2023-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-03","FORECAST_END":"2023-05-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-04-03 | 2023-05-01 | RODERICK NEVAY | nokuthula manzini | 23000419 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000183 | GN Various Sites Supply and install oper | Ã¢ÂÂ¢ Remove existing operational hours decal for 15 branches and replace with new ABSA approved decal Ã¢ÂÂ¢Works to be carried over one day and during normal working hours. |  |  | Region 1 | Gauteng North | Unknown | 1000-70065-01 | Unknown Building - not in our database | N | 2023-02-27 |  |  | ASP-GN0183 | CLSD BUDG RESA SETC: |  | false | true |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | U |  | GAMIETR | 2023-03-20 | D | 4240.5 | Approved | 100 | 2023-02-27 | 2023-10-07 | 48765.75 |  | {"MANDT":"111","REFERENCE":90000183,"ONEVIEW":"Unknown","DATE01":"2022-12-19","DATE02":"2022-12-26","DATE03":"2023-01-16","DATE04":"2023-01-23","DATE05":"2023-02-13","DATE06":"2023-05-03","DATE07":"2023-05-10","DATE08":"2023-10-30","DATE09":"2023-12-14","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:7:21:7:21:79:7:173:45:16","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-03","FORECAST_END":"2023-05-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000076711 | PHASE11 | 2023-07-07 | 2023-07-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-03-28 | 48765.75 | 0 |  |  | C000076711 | 42405 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000184 | Alex plaza- Supply and install drip tray | Supply and install new drip tray to Server room Work will be carried out during normal working hours. Work wil be completed in 2 days including sourcing materials |  | m | Region 1 | Gauteng South | 78224X | 1000-70391-01 | Alex Plaza-3rd St-Wynberg | N | 2023-05-01 | 2023-05-02 |  | ASP-GN0184 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2024-08-30 | LOUISR | 2023-03-20 | D | 4119.16 | 2023.03.22: Approved by Kobus JvR as per email 2023.03.22: Supported by Rob L | 100 | 2023-03-13 | 2023-03-24 | 4119.16 | Approved | {"MANDT":"111","REFERENCE":90000184,"ONEVIEW":"78224X","DATE01":"2023-01-20","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-20","DATE05":"2023-04-25","DATE06":"2023-05-27","DATE07":"2023-07-02","DATE08":"2023-07-23","DATE09":"2023-09-06","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:3:21:7:64:32:36:21:45:20","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-27","FORECAST_END":"2023-07-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000076710 | PHASE11 | 2023-05-27 | 2023-07-02 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000423 |  |  |  |  | 2023-03-28 | 3581.88 | 0 |  |  | C000076710 | 3581.88 | CIP2023XP | 334.74 |  | 0 | 0 |  | 0 |  | 0
90000185 | Trade route mall- UPS Power dedicated pl | Trade route mall- UPS Power dedicated "Supply and install 4 x dedicated plugs in the Teller area and Treasury area (4)Supply and install 4 additional UPS power sockets at the Trade Route Mall's treasury and the teller area Issue ECOC on completion Issue as built drawings on completion" |  |  | Region 1 |  | 77216X | 1000-70356-01 | Trade Route Mall Centre-Cnr K43 & Nirvana Dr-Lenasia |  | 2023-03-31 | 2023-12-15 |  | ASP-GS0622 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | LOUISR | 2023-03-16 | D | 12076.3 | 2023.03.22: Approved by Kobus JvR as per email 2023.03.22: Supported by Rob L | 100 | 2023-03-24 | 2023-03-24 | 12076.3 | Approved | {"MANDT":"111","REFERENCE":90000185,"ONEVIEW":"77216X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"SW5zdGFsbGF0aW9uIGNvbXBsZXRlZCBQT0MgdG8gYmUgIGlzc3VlZCBmb3IgQ2xpZW50IHNpZ25hdHVyZS4=","RATING":"Low"} |  |  | C000075261 | PHASE08 | 2023-03-31 | 2023-12-15 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-03-22 | 10501.13 | 0 |  |  | C000075275 | 10501.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000186 | The Glen-Temporary UPS installation at S | The Glen-Temporary UPS installation at S |  |  | Region 1 |  | 77239X | 1000-70359-01 | The Glen Shopping Centre-Cnr Orpen & Letaba St-Oakdene |  | 2023-03-31 | 2023-12-15 |  | ASP-GS0623 | CRTD AVAC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | LOUISR | 2023-03-20 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000186,"ONEVIEW":"77239X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-04-30","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-30","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2Vk","RATING":""} |  |  |  | PHASE10 | 2023-04-30 | 2023-04-30 | CHRISTOPHER MPOFU |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000187 | Meyerton Dilaps- Waterproofing reinforce | Meyerton Dilaps- Waterproofing reinforce |  |  | Region 1 |  | 77636X | 1000-70376-01 | Absa Meyerton-Loch St-Meyerton |  | 2023-03-31 | 2023-12-15 |  | ASP-GS0624 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | LOUISR | 2023-03-20 | D | 96128.5 | 2023.04.26: Approved by Kobus JvR as per email Supported by Kobus JV Rensburg on 15 March 2023 | 60 | 2023-04-26 | 2023-04-26 | 96128.5 | Approved | {"MANDT":"111","REFERENCE":90000187,"ONEVIEW":"77636X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-05-25","DATE07":"2023-06-10","DATE08":"2023-08-03","DATE09":"2023-08-15","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-25","FORECAST_END":"2023-06-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2VkLg==","RATING":""} |  |  | C000082760 | PHASE11 | 2023-05-25 | 2023-06-10 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000213 |  |  |  |  | 2023-05-03 | 96128.5 | 0 |  |  | C000082367 | 83590 |  | 8613 |  | 0 | 0 |  | 0 |  | 0
90000188 | Various Sites WC x 7 - Install deep sea con | Various Sites WC x 7 - Install deep sea controllers on the generator - 2 Sites to be done - Oude Bloemhof and Parow only |  |  | Region 2 | Western Cape | Various |  | Various Sites | U | 2023-12-31 | 2023-12-31 |  | ASP-N00052 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2023 |  | U |  | CEASARS | 2023-03-20 | D | 211523.83 | 2023.04.26: Approved by Kobus JvR as per email 2023.04.25: Supported by Rob L | 100 | 2023-04-27 | 2023-04-26 | 211523.83 | Approved | {"MANDT":"111","REFERENCE":90000188,"ONEVIEW":"Various","DATE01":"2023-01-19","DATE02":"2023-03-17","DATE03":"2023-04-22","DATE04":"2023-04-27","DATE05":"2023-04-27","DATE06":"2023-07-20","DATE07":"2023-08-17","DATE08":"2023-09-20","DATE09":"2023-11-03","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"285:57:36:5:0:84:28:34:44:11","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-20","FORECAST_END":"2023-08-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgU2VwdCBQT0MgdG8gYmUgc2VudCB0byBFbmdpbmVlcmluZyBvbiAxMi8wOQoxNyBBdWcgV29ya3MgQ29tcGxldGVkCg==","RATING":"Low"} |  |  | C000082136 | PHASE11 | 2023-07-20 | 2023-08-17 | RODERICK NEVAY | Michael Maluleka | 23000098 |  |  |  |  | 2023-05-03 | 183933.77 | 0 |  |  | C000082136 | 183933.77 | CIP2023XP | 19138.53 |  | 0 | 0 |  | 0 |  | 0
90000189 | Absa 32 Voortrekker Bellville Dilaps | Absa 32 Voortrekker Bellville Dilaps for Revamp |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2023-05-01 |  |  | ASP-WC0269 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-03-16 | D | 114018.72 | Approved at CB/BTB | 100 | 2023-03-27 | 2023-03-27 | 114018.72 | Approved | {"MANDT":"111","REFERENCE":90000189,"ONEVIEW":"78126X","DATE01":"2023-03-13","DATE02":"2023-03-20","DATE03":"2023-03-24","DATE04":"2023-03-26","DATE05":"2023-03-27","DATE06":"2023-03-27","DATE07":"2023-04-05","DATE08":"2023-04-14","DATE09":"2023-04-25","DATE10":"2023-05-25","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"79:7:4:2:1:0:9:9:11:2","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-27","FORECAST_END":"2023-04-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgQXByaWwgRmluYWwgUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":"Low"} |  |  | C000076551 | PHASE11 | 2023-03-27 | 2023-04-05 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-03-28 | 99146.71 | 0 |  |  | C000076551 | 99146.71 |  | 23000 |  | 0 | 0 |  | 0 |  | 0
90000190 | Bridge Park - Automatic Swing Door Installation 1st Floor East Building | Bridge Park - Automatic Swing Door Installation 1st Floor East Building |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2023-12-31 |  |  | ASP-WC0270 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-03-20 | D | 88958.99 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-04 | 2023-05-03 | 88958.99 | Approved | {"MANDT":"111","REFERENCE":90000190,"ONEVIEW":"36225X","DATE01":"2023-01-19","DATE02":"2023-01-27","DATE03":"2023-04-26","DATE04":"2023-05-04","DATE05":"2023-05-04","DATE06":"2023-05-27","DATE07":"2023-06-05","DATE08":"2023-06-21","DATE09":"2023-06-26","DATE10":"2023-07-26","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"158:8:89:8:0:23:9:16:5:4","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-27","FORECAST_END":"2023-06-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgSnVuZSAtIEZpbmFsIFBPQyBzdWJtaXR0ZWQgdG8gZmluYW5jZQ==","RATING":""} |  |  | C000083197 | PHASE11 | 2023-05-27 | 2023-06-05 | RODERICK NEVAY | Michael Maluleka | 23000401 |  |  |  |  | 2023-05-05 | 77355.64 | 0 |  |  | C000083197 | 77355.64 | CIP2023XP | 8087.18 |  | 0 | 0 |  | 0 |  | 0
90000191 | Absa Bredasdorp - Ext ATM Profile + Sign | Absa Bredasdorp - Ext ATM Profile + Sign |  |  | Region 2 | Western Cape | 77641X | 1000-70839-01 | Absa Bredasdorp-Long St-Bredasdorp | N | 2023-06-01 |  |  | ASP-WC0271 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-03-22 | D | 140594.65 | 2023.05.25: Approved by Conrad M 2023.05.23: Supported by Judith B as per email & Ilana vdW | 100 | 2023-05-25 | 2023-05-25 | 140594.65 | Approved | {"MANDT":"111","REFERENCE":90000191,"ONEVIEW":"77641X","DATE01":"2023-03-23","DATE02":"2023-03-24","DATE03":"2023-05-17","DATE04":"2023-05-25","DATE05":"2023-05-25","DATE06":"2023-06-27","DATE07":"2023-06-30","DATE08":"2023-07-18","DATE09":"2023-07-26","DATE10":"2023-08-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"191:1:54:8:0:33:3:18:8:29","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-27","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggSnVseSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000104097 | PHASE11 | 2023-06-27 | 2023-06-30 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-05-26 | 122256.22 | 0 |  |  | C000087789 | 122256.23 |  | 6471.17 |  | 0 | 0 |  | 0 |  | 0
90000192 | Absa Worcester - Minor Works | Absa Worcester - Minor Works |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester-Stockenstrom St-Worcester | N | 2023-06-01 |  |  | ASP-WC0272 | CRTD AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-03-22 | D | 0 |  | 1 | 2023-07-20 | 2023-08-03 | 0 | Converted to Project ALP-WC0025 | {"MANDT":"111","REFERENCE":90000192,"ONEVIEW":"78016X","DATE01":"2023-06-19","DATE02":"2023-06-26","DATE03":"2023-07-17","DATE04":"2023-07-24","DATE05":"2023-08-03","DATE06":"2023-09-18","DATE07":"2023-10-18","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"164:7:21:7:10:46:30:13:45:0","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-18","FORECAST_END":"2023-10-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NyBBdWcgLSBXQSBhbmQgU0YgdG8gYmUgc3VibWl0dGVkIDggQXVnCjIgQXVnIEFwcHJvdmVkIENCMjkgMyBBdWd1c3QgLSBTaWduZWQgRGVjayBQZW5kaW5nIFdBIGFuZCBTRiB0byBiZSBzdWJtaXR0ZWQ=","RATING":"Low"} |  |  |  | PHASE12 | 2023-09-18 | 2023-10-18 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000193 | Mall of the south- Gen | Mall of the south- Generator |  |  | Region 1 |  | 36101X | 1000-70180-01 | Mall Of The South-Cnr Klipriver Dr & Swartkoppies Rd-Johannesburg | Y | 2023-03-31 | 2023-12-15 |  | ALP-GS0055 | CRTD AVAC: |  | false | false |  | Mukuru Wesigye (No Email) |  |  | 2023 |  | L | 2023-09-29 | LOUISR | 2023-03-16 | D | 0 | Project Cancelled and will be done under Energy budget | 1 |  |  | 0 | Project moved to Energy department | {"MANDT":"111","REFERENCE":90000193,"ONEVIEW":"36101X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-05-31","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-31","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxsZWQgYW5kIGhhbmRlZCBvdmVyIHRvIGVuZXJneSB0ZWFtLg==","RATING":""} |  |  |  | PHASE12 | 2023-05-31 | 2024-06-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000194 | Towers west- Obsolete Lift Ports | Phase Two Scope of Works: Schindler Replace each and every existing Z-Line Terminal with a PORT 1 BLE Terminal (Black). Replace all existing fixture shaft wiring. Install Power over Ethernet (POE) interphase boxes. Replace all exisiting Designation Plates. Install 1 x Handicap Designation riser per group. Supply and Install 2 x Programming Stations per Group, one in the Lift Motor Room and one for the Customers benificial use. Provision of My PORT Public functionality License Agreement for 2 years, thereafter an Annual fee will apply. Professional Lift Consultant Services Technical and quality checks of the detailed drawings; Checking and approval of lift operating philosophy; Approval of operating software philosophy; Installation quality control on electric components; Overseeing Installation and approval of quality; Update of current Annexure B (Safety Certificates); Installation sign-off at commissioning and Hand-Over |  |  | Region 1 | Gauteng | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | Y | 2023-03-31 | 2023-12-15 |  | ALP-GS0056 | CRTD AVAC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | LOUISR | 2023-03-20 | D | 10345176.11 | Supported by CRES | 60 | 2023-07-27 | 2023-07-27 | 1034176.11 | 2023.10.25 -WA review in progress BFM PO to be issued to the supplier in the interim to commence with procurement of lead-time spares. | {"MANDT":"111","REFERENCE":90000194,"ONEVIEW":"21526X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQT8OiwoDCmXMgdG8gYmUgaXNzdWVkIGluIHRoZSBpbnRlcmltClBsYW5uZWQgc3RhcnQgZGF0ZSA6MTUvMTAvMjAyMwpDb21wbGV0aW9uIGRhdGUtIDMxLzAzLzIwMjQKUHJvamVjdCByb2xsLW92ZXIgLTUwJSBSaXNrLSBkdWUgdG8gTGVhZHRpbWUgb24gaW1wb3J0IHNwYXJlcwpGaW5hbmNpYWwgUm9sbG92ZXItNTAlCkF3YWl0aW5nIFdBIGFwcHJvdmFsIGFuZCBQTw==","RATING":"Low"} |  |  |  | PHASE07 | 2023-03-31 | 2023-12-15 | CHRISTOPHER MPOFU |  | 23000517 | 2023-10-11 |  |  |  |  | 0 | 0 |  |  |  | 0 | CIP2023XP | 778855.44 |  | 0 | 0 |  | 0 |  | 0
90000195 | Retail Solar PV Program (Lichtenburg, Piet Retief and Witbank) | Solar PV- Lichtenburg, Piet Retief and Witbank |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | N | 2023-03-31 | 2023-12-15 |  | ALP-N00044 | REL BUDG AVAC RESA SETC: |  | N | true |  | Wesigye Mukuru |  |  | 2023 |  | U |  | LOUISR | 2023-03-23 | D | 7495288.8 | Approved at CB/BTB | 100 | 2023-02-16 | 2023-04-13 | 2198132.24 | Approved. 20.11.23 AS - This project has ABSA direct appointed suppliers. BFM will only invoice for management fees on this project. | {"MANDT":"111","REFERENCE":90000195,"ONEVIEW":"Various","DATE01":"2023-01-20","DATE02":"2023-02-17","DATE03":"2023-02-24","DATE04":"2023-03-17","DATE05":"2023-03-31","DATE06":"2023-08-31","DATE07":"2023-09-04","DATE08":"2023-11-30","DATE09":"2023-12-10","DATE10":"2023-12-15","DATE11":"2023-12-10","DATE12":"2023-12-10","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"405:28:7:21:14:153:4:87:10:0","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TVcgMTkvOS8yMzogRGVzaWduIG92ZXJsYXkgbWVldGluZyBvY2N1cnJlZCBhbmQgdXBkYXRlZCBkZXNpZ25zIHJlY2VpdmVkIGFuZCBzb2NpYWxpemVkIGZvciBhcHByb3ZhbCBvbiAxOS85LiBPSFMgc3VibWlzc2lvbnMgbm90IHlldCBkb25lIHRoZXJlZm9yZSBpbXBhY3QgdG8gcHJvamVjdCB0aW1lbGluZXMgc2lnbmlmaWNhbnQu","RATING":"High"} |  |  | C000101739 | PHASE06 | 2023-08-31 | 2023-09-04 | LUCIA AMUNGA | Thea Spamers | 0 | 2023-04-19 | 2023-06-29 | 2023-04-17 | 2023-04-19 |  | 6517642.43 | 209425.63 |  |  | C000153504 | 4186899.38 |  | 252246 |  | 0 | 0 |  | 0 |  | 0
90000196 | 2023 Absa Retail Green Star Certification | 2023 Absa Retail Green Star Certification (9 Retail branches) |  |  | Energy | National | Various | Various Sites | Various Sites | N | 2023-03-17 | 2024-03-31 |  | ABS-G00010 | REL BUDG AVAC RESA SETC: |  | false | true |  | Jaca Kgomotso |  | Various 9 retail branches | 2023 |  |  |  | DUPREEZK | 2023-03-17 | D | 2263399 | Approved at CB/BTB | 100 | 2022-12-02 | 2023-02-01 | 2263399 | Approved | {"MANDT":"111","REFERENCE":90000196,"ONEVIEW":"Various Sites","DATE01":"2023-01-06","DATE02":"2022-11-18","DATE03":"2022-11-25","DATE04":"2022-12-02","DATE05":"2022-12-08","DATE06":"2023-03-16","DATE07":"2023-05-15","DATE08":"2023-11-10","DATE09":"2023-11-24","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"541:-49:7:7:6:98:60:179:14:25","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-16","FORECAST_END":"2023-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RXhlY3V0aW9uIGluIHByb2dyZXNz","RATING":"Low"} |  |  | C000075632 | PHASE08 | 2023-03-16 | 2023-05-15 | ONISMS MANYEWE | Nokuthula Manzini | 23000140 | 2023-02-06 | 2023-03-10 | 2023-02-01 | 2023-02-02 | 2023-03-23 | 1968173.04 | 543045.04 |  |  | C000075635 | 1425128 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000197 | 2023 Absa Corporate Green Star Certification | 2023 Absa Corporate Green Star Certification (3 Corporate Buildings) |  |  | Energy | National | Various |  | Various Sites | N | 2023-03-17 | 2024-03-31 |  | ABS-G00011 | REL BUDG AVAC RESA SETC: |  | false | true |  | Jaca Kgomotso |  | 3 Corporate buildings | 2023 |  |  |  | DUPREEZK | 2023-03-17 | D | 2317153.24 | Approved at CB/BTB | 100 | 2022-12-02 | 2023-02-01 | 2317153.24 | Approved | {"MANDT":"111","REFERENCE":90000197,"ONEVIEW":"Various Sites","DATE01":"2023-01-06","DATE02":"2022-11-18","DATE03":"2022-11-25","DATE04":"2022-12-02","DATE05":"2022-12-08","DATE06":"2023-03-16","DATE07":"2023-05-15","DATE08":"2023-11-10","DATE09":"2023-11-24","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"572:-49:7:7:6:98:60:179:14:6","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-16","FORECAST_END":"2023-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RXhlY3V0aW9uIGluIHByb2dyZXNz","RATING":"Low"} |  |  | C000075635 | PHASE08 | 2023-03-16 | 2023-05-15 | ONISMS MANYEWE | Nokuthula Manzini | 23000033 | 2023-02-06 | 2023-03-10 | 2023-02-01 | 2023-02-03 | 2023-03-23 | 2014915.86 | 510527.07 |  |  | C000145456 | 1504388.78 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000198 | Carbon offsets procurement | Carbon offsets procurement and supply of carbon credits and Renewable Energy Certificates (RECs) required to offset part of Absas 2022 greenhouse gas (GHG) emissions. |  |  | Energy | National | Various |  | Various Sites | N | 2023-03-17 | 2024-03-31 |  | ABS-G00012 | REL BUDG AVAC RESA SETC: |  | false | true |  | Onisms Manyewe |  |  | 2023 |  |  |  | DUPREEZK | 2023-03-17 | D | 996757.5 | Purchasing carbon offsets to meet Absas 2023 Environmental Action Plan (EAP) targets | 100 | 2022-10-31 | 2022-11-10 | 996757.5 | BTB transactional paper approved, contracting completed, Absa PO issued, POs issued to suppliers, and transaction in progress. | {"MANDT":"111","REFERENCE":90000198,"ONEVIEW":"Various Sites","DATE01":"2023-01-06","DATE02":"2022-10-27","DATE03":"2022-10-28","DATE04":"2022-11-01","DATE05":"2022-11-10","DATE06":"2023-05-31","DATE07":"2023-06-05","DATE08":"2023-08-15","DATE09":"2023-08-25","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"541:-71:1:4:9:202:5:71:10:25","PROGRESS":87,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-31","FORECAST_END":"2023-06-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"T25pc21zOiBQT3MgaXNzdWVkIHRvIHN1cHBsaWVycy4gVHJhbnNhY3Rpb24gaXMgYXQgYWR2YW5jZWQgc3RhZ2UuIEV4cGVjdGVkIGRhdGUgZm9yIHByYWN0aWNhbCBjb21wbGV0aW9uOiAxNSBBdWcgMjAyMy4=","RATING":""} |  |  | C000088404 | PHASE08 | 2023-05-31 | 2023-06-05 | ONISMS MANYEWE | Nokuthula Manzini | 0 | 2023-03-09 | 2023-05-15 | 2023-03-06 | 2023-03-07 | 2023-05-30 | 866745.65 | 0 |  |  | C000088404 | 886745.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000199 | Absa Bridge Park - UPS B - Replacement(Retrospective) | Absa Bridge Park - UPS B - Replacement(Retrospective) |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2023-03-09 | 2023-03-30 |  | ASP-WC0273 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-03-27 | D | 323561.99 |  | 100 | 2023-04-13 | 2023-04-13 | 323561.99 | Retrospective Approval | {"MANDT":"111","REFERENCE":90000199,"ONEVIEW":"36225X","DATE01":"2023-03-22","DATE02":"2023-03-22","DATE03":"2023-04-13","DATE04":"2023-04-13","DATE05":"2023-04-13","DATE06":"2023-04-21","DATE07":"2023-04-21","DATE08":"2023-06-07","DATE09":"2023-06-08","DATE10":"2023-06-26","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"131:0:22:0:0:8:0:47:1:9","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-21","FORECAST_END":"2023-04-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NyBKdW5lIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000080518 | PHASE11 | 2023-04-21 | 2023-04-21 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-04-19 | 281358.25 | 0 |  |  | C000080518 | 281358.25 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000201 | Absa De Aar - Supply and Installation | "Supply and installation of steel palisade fence At Absa De Aar, the branch is experiencing street vagrants sleeping next to the building. As a preventative measure, it was proposed to close off the area next to the perimeter wall with palisade fencing between the pillars and to place a lockable gate on the far end to enable access for the cleaner to wash the windows. In addition, bended tooth wall spikes will be installed on the lower window sill to prevent people from sitting in that area. This request seeks approval to carry out the above-listed items. Note: Approved at RIF. Supported by Africa Security. Supported by BFM OHS. LL Approval obtained. Supported by BFM Engineering. Floorplan updated. This project was prioritized by the region and spending will be allocated from the regional minor works budget. Scope of Work Ã¢ÂÂ¢ Supply and install steel palisade fence (35m) Ã¢ÂÂ¢ Supply and install bended tooth wall spikes in window sill (14m) Ã¢ÂÂ¢ Supply and install (940 x 2100mm) swing lockable gate (x1) Ã¢ÂÂ¢ Supply and install (1260 x 2100mm) swing lockable gate (x1) Ã¢ÂÂ¢ Prepare and paint the palisade fence, 2 coats of gloss enamel to the palisade fence, gates, and posts (140mÃÂ²)" |  |  | Region 3 |  | 79329X | 1000-71361-01 | De Aar-Voortrekker St-De Aar |  | 2023-04-25 | 2023-05-16 |  | ASP-CR0412 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | MOKOENAM2 | 2023-03-28 | D | 95492.09 | 2023.04.25: Approved by Conrad M as per email 2023.04.25: Supported by Leko N | 95 | 2023-04-26 | 2023-04-26 | 95492.09 | Approved | {"MANDT":"111","REFERENCE":90000201,"ONEVIEW":"79329X","DATE01":"2023-02-14","DATE02":"2023-02-21","DATE03":"2023-03-14","DATE04":"2023-03-21","DATE05":"2023-04-11","DATE06":"2023-04-25","DATE07":"2023-05-16","DATE08":"2023-06-06","DATE09":"2023-07-21","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-25","FORECAST_END":"2023-05-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000082130 | PHASE11 | 2023-04-25 | 2023-05-16 | NANDE MAQUBELA | Floyd Mofokeng | 23000490 |  |  |  |  | 2023-04-26 | 83036.6 | 0 |  |  | C000082130 | 83036.6 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000202 | Pretoria Campus Block A Open Office Spac | Pretoria Campus Block A Open Office - Columns Labelling. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-03-31 |  |  | ASP-GN0185 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-04-03 | D | 184400.75 | 2023.04.05: Approved by Conrad M 2023.04.04: Supported by Winston P | 100 | 2023-04-06 | 2023-04-06 | 184400.75 | Approved | {"MANDT":"111","REFERENCE":90000202,"ONEVIEW":"22491X","DATE01":"2023-01-20","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-20","DATE05":"2023-02-27","DATE06":"2023-03-31","DATE07":"2023-06-30","DATE08":"2023-09-21","DATE09":"2023-11-05","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"253:3:21:7:7:32:91:83:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079204 | PHASE11 | 2023-03-31 | 2023-06-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-04-12 | 212060.86 | 0 |  |  | C000079204 | 160348.48 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000203 | PTA Campus X2 Water Tanks Repainting | Surface preparation and paint application (356m2). Work will be conducted during normal working hour for 3 - 4 days. Onsite security will be utilsed. Material lead-time: +-1 week. This is part of CIP 2023 funding, Q2. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-03-31 |  |  | ASP-GN0186 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-04-03 | D | 57772.5 | 2023.04.05: Approved by Conrad M 2023.04.04: Supported by Winston P | 100 | 2023-04-06 | 2023-04-06 | 57772.5 | Approved | {"MANDT":"111","REFERENCE":90000203,"ONEVIEW":"22491X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079104 | PHASE11 | 2023-03-31 | 2023-04-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000326 |  |  |  |  | 2023-04-12 | 50236.96 | 0 |  |  | C000079104 | 50236.96 | CIP2023XP | 5117.5 |  | 0 | 0 |  | 0 |  | 0
90000204 | Keywest Supply and Install a Compatible | Supply and install Deepsea controller Interface the generator into The BMS Test and commission Security guard not required for the duration of the works. Work will be carried out during normal working hours. Material Leadtime: +-2 working days. Onsite timeline: 2 working days. |  |  | Region 1 | Gauteng North | 22890X | 1000-70077-01 | Key West Shopping Centre-Cnr Paardekraal & Viljoen Rd-Krugersdorp | N | 2023-03-31 |  |  | ASP-GN0187 | REL BUDG AVAC SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-04-03 | D | 36895.15 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR | 100 | 2023-04-06 | 2023-04-06 | 36895.15 | Approved | {"MANDT":"111","REFERENCE":90000204,"ONEVIEW":"Unknown","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079210 | PHASE08 | 2023-03-31 | 2023-04-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-04-12 | 48793.83 | 0 |  |  | C000079210 | 32082.74 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000205 | Pretoria Campus Sewer Line Inspection 2 | Pretoria Campus Sewer Line Inspection 2 |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-03-31 |  |  | ASP-GN0188 | CRTD: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-04-03 | D | 11.9 |  | 100 | 2023-01-09 | 2023-01-13 | 11.9 |  | {"MANDT":"111","REFERENCE":90000205,"ONEVIEW":"22491X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-06-30","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"2023-12-15","DATE12":"2023-12-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"711:7:21:7:21:14:91:123:45:16","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8xMTogUHJvamVjdCBjb21wbGV0ZS4gQXdhaXRpbmcgYXBwcm92ZWQgQkMgcGFjayBmcm9tIFBDIHRvIGNvbXBpbGUgRmluYWwgUE9DLg==","RATING":""} |  |  | C000061198 | PHASE08 | 2023-03-31 | 2023-06-30 |  |  | 0 |  |  |  |  | 2023-01-13 | 10.35 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000206 | Alex Mall Dilaps | Alex Mall Dilaps |  |  | Region 1 | Gauteng South | 78224X | 1000-70391-01 | Alex Plaza-3rd St-Wynberg | N | 2023-03-31 |  |  | ASP-GS0625 | CRTD: |  | false | false |  |  |  |  | 2023 |  | L |  | GAMIETR | 2023-03-29 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000206,"ONEVIEW":"","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-03-31 | 2023-04-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000207 | Auckland Park CC Desk Dividers | Auckland Park CC Desk Dividers |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-03-30 | 2023-04-30 |  | ASP-GS0626 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-03-30 | D | 10624.5 |  | 100 |  |  | 122181.69 |  | {"MANDT":"111","REFERENCE":90000207,"ONEVIEW":"76849X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIFBPQyBzdWJtaXR0ZWQgdG8gZmluYW5jZQ==","RATING":""} |  |  | C000077505 | PHASE11 | 2023-03-30 | 2023-04-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-03-31 | 106244.95 | 0 |  |  | C000077505 | 106244.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000208 | Supply and install a grab rail | Supply and install a grab rail |  |  | Region 1 | Gauteng South | 78786X | 1000-70435-01 | 17 Harrison Street-Harrison St-Johannesburg | N | 2023-04-14 |  |  | ASP-GS0627 | CLSD BUDG AVAC RESA SETC: |  | R | false |  | Athi Magqashela |  |  | 2023 |  | L | 2024-03-30 | GAMIETR | 2023-03-31 | D | 21850 | 2023.04.25: Approved by Conrad M as per email 2023.04.25: Supported by Winston P & Ilana vdW | 100 | 2023-04-26 | 2023-04-26 | 3803.51 |  | {"MANDT":"111","REFERENCE":90000208,"ONEVIEW":"78786X","DATE01":"2023-02-03","DATE02":"2023-01-23","DATE03":"2023-02-13","DATE04":"2023-02-20","DATE05":"2023-08-21","DATE06":"2023-10-06","DATE07":"2023-10-28","DATE08":"2023-11-26","DATE09":"2023-12-22","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"147:-11:21:7:182:46:22:29:26:0","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-06","FORECAST_END":"2023-10-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RVNNIHRvIHByb3ZpZGUgYSBHTVAgY29zdCwgUE0gaGFzIGJlZW4gZm9sbG93aW5nLCB0aGUgcHJvamVjdCB3aWxsIGJlIGZpbmFuY2lhbCByb2xsIG92ZXIKQ29uc3VsdGluZyBmaXJtIHdhcyBhcHBvaW50ZWQgdG8gcHJlcGFyZSBkcmF3aW5ncywgc3BlY2lmaWNhdGlvbiBhbmQgcHJvY3VyZW1lbnQ=","RATING":""} |  |  | C000082368 | PHASE11 | 2023-06-11 | 2023-07-03 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-03 | 3307.4 | 0 |  |  | C000082368 | 3307.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000209 | Absa Eastgate - Dilaps | Absa Eastgate International - Dilaps |  |  | Region 1 |  | 76420X | 1000-70247-01 | Eastgate Shopping Centre-Bradford Rd-Bedfordview | N | 2023-04-14 |  |  | ASP-GS0628 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2022-11-29 | GAMIETR | 2023-03-31 | D | 338842.92 |  | 100 | 2023-06-21 | 2023-06-15 | 338842.92 |  | {"MANDT":"111","REFERENCE":90000209,"ONEVIEW":"76420X","DATE01":"2023-02-03","DATE02":"2023-02-10","DATE03":"2023-03-03","DATE04":"2023-03-10","DATE05":"2023-03-31","DATE06":"2023-04-14","DATE07":"2023-05-14","DATE08":"2023-06-04","DATE09":"2023-07-19","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-14","FORECAST_END":"2023-05-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000086749 | PHASE10 | 2023-04-14 | 2023-05-14 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-23 | 294646.02 | 0 |  |  | C000084172 | 294646.02 |  | 33315.15 |  | 0 | 0 |  | 0 |  | 0
90000210 | Absa Towers North - Up | Absa Towers North - Upgrade of Fire Pane |  |  | Region 1 |  | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2023-04-21 |  |  | ASP-GS0629 | REL BUDG AVAC SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | F |  | GAMIETR | 2023-03-31 | D | 146327.7 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR | 100 | 2023-04-06 | 2023-04-06 | 146327.7 | Approved | {"MANDT":"111","REFERENCE":90000210,"ONEVIEW":"77381X","DATE01":"2023-02-10","DATE02":"2023-02-17","DATE03":"2023-03-10","DATE04":"2023-03-17","DATE05":"2023-04-07","DATE06":"2023-04-21","DATE07":"2023-05-21","DATE08":"2023-06-11","DATE09":"2023-07-26","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-21","FORECAST_END":"2023-05-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079207 | PHASE08 | 2023-04-21 | 2023-05-21 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-12 | 127241.48 | 0 |  |  | C000079207 | 127241.48 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000211 | Greenstone Mall Supply a | Greenstone Mall Supply and install 3 additional UPS Red plugs. |  |  | Region 1 |  | 78551X | 1000-70418-01 | Greenstone Shopping Centre-Stoneridge Dr-Edenvale | Y | 2023-03-30 |  |  | ASP-GS0630 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-03-31 | D | 9144.28 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR | 100 | 2023-04-06 | 2023-04-06 | 9144.28 | Approved | {"MANDT":"111","REFERENCE":90000211,"ONEVIEW":"78551X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-07-04","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079209 | PHASE08 | 2023-03-30 | 2023-04-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-12 | 9144.28 | 0 |  |  | C000079209 | 7951.55 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000212 | 15 Alice Lane South Emergency power to A | 15 Alice Lane South Emergency power to A |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-03-30 | 2023-05-31 |  | ASP-GS0631 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-03-31 | D | 33254.47 | Approved | 100 | 2023-10-07 | 2023-10-07 | 382426.43 |  | {"MANDT":"111","REFERENCE":90000212,"ONEVIEW":"35041X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-05-31","DATE08":"2023-06-21","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000077784 | PHASE09 | 2023-03-31 | 2023-04-01 | CHRISTOPHER MPOFU | Michael Maluleka | 23000277 |  |  |  |  | 2023-04-05 | 382426.43 | 0 |  |  | C000077784 | 332544.72 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000213 | Alice Lane North Upgrade | Alice Lane North Upgrade Power Monitorin |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | Y | 2023-03-31 |  |  | ASP-GS0632 | REL BUDG AVAC SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L | 2023-04-29 | GAMIETR | 2023-04-03 | D | 39224.24 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR | 100 | 2023-04-06 | 2023-04-06 | 39224.24 | Approved | {"MANDT":"111","REFERENCE":90000213,"ONEVIEW":"Unknown","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079206 | PHASE08 | 2023-04-30 | 2023-04-30 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-04-12 | 45107.86 | 0 |  |  | C000079206 | 34108.03 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000214 | Absa Towers North Replacement of VSD Ass | Absa Towers North Replacement of VSD Ass |  |  | Region 1 | Gauteng South | 77831X |  | Absa Towers North | N | 2023-03-31 |  |  | ASP-GS0633 | CRTD: |  | false | false |  | (Non PM) |  |  | 2023 |  | F |  | GAMIETR | 2023-04-03 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000214,"ONEVIEW":"77831X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-03-31 | 2023-04-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000215 | Sasolburg relocation of generator | Sasolburg relocation of generator |  |  | Region 1 | Gauteng | 70647X | 1000-71518-01 | Sasol Pioneer Building-Cnr Fichardt & Bell St-Sasolburg | N | 2023-03-31 |  |  | ASP-GS0634 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-04-03 | D | 37664.6 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR | 100 | 2023-04-06 | 2023-04-06 | 37664.6 | Approved | {"MANDT":"111","REFERENCE":90000215,"ONEVIEW":"70647X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-05-30","DATE08":"2023-06-20","DATE09":"2023-08-04","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2VkLg==","RATING":""} |  |  | C000079103 | PHASE11 | 2023-03-31 | 2023-05-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-12 | 37644.61 | 0 |  |  | C000079103 | 32734.44 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000216 | Auckland Park Replacement of Compressor | Auckland Park Replacement of Compressor on Chiller 1 |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-03-31 |  |  | ASP-GS0635 | REL BUDG ACPT AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-04-03 | D | 150443.46 |  | 100 | 2023-09-07 | 2023-09-07 | 150443.46 |  | {"MANDT":"111","REFERENCE":90000216,"ONEVIEW":"76849X","DATE01":"2023-01-20","DATE02":"2023-01-27","DATE03":"2023-02-17","DATE04":"2023-02-24","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-04-30","DATE08":"2023-05-21","DATE09":"2023-07-05","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000110303 | PHASE10 | 2023-10-06 | 2023-10-16 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-09-13 | 130820.4 | 0 |  |  | C000110303 | 130820.4 |  | 13653.16 |  | 0 | 0 |  | 0 |  | 0
90000217 | Absa Anton Lembede Stree | Absa Anton Lembede Street - Install Tell |  |  | Region 3 |  | 77987X | 1000-71206-01 | Absa 291 Anton Lembede Street-Anton Lembede St-Durban | Y | 2023-05-31 |  |  | ASP-KZ0243 | CRTD: |  | false | false |  |  |  |  | 2023 |  | L | 2025-12-30 | NOMNGANGAL | 2023-03-31 | D | 0 |  |  |  |  | 0 | The project number needs to be deleted as the internal signs were done with Bulk PO ALP-N00039 | {"MANDT":"111","REFERENCE":90000217,"ONEVIEW":"","DATE01":"2023-03-22","DATE02":"2023-03-29","DATE03":"2023-04-19","DATE04":"2023-04-26","DATE05":"2023-05-17","DATE06":"2023-05-31","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-31","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-12 | 2023-05-12 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000218 | Absa Chatterton Road P- Install Kitchen | Absa Chatterton Road P- Install Kitchen |  |  | Region 3 |  | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg | Y | 2023-05-04 |  |  | ASP-KZ0244 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  | L | 2023-04-29 | NOMNGANGAL | 2023-03-31 | D | 9043.75 | 2023.04.19: Approved by Conrad M as per email 2023.04.18: Supported by Leko N & Ilana vdW |  | 2023-04-20 | 2023-04-20 | 9043.75 | Approved | {"MANDT":"111","REFERENCE":90000218,"ONEVIEW":"Unknown","DATE01":"2023-02-23","DATE02":"2023-03-02","DATE03":"2023-03-23","DATE04":"2023-03-30","DATE05":"2023-04-20","DATE06":"2023-05-04","DATE07":"2023-06-03","DATE08":"2023-06-24","DATE09":"2023-08-08","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-04","FORECAST_END":"2023-06-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000081300 | PHASE11 | 2023-05-05 | 2023-05-26 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-21 | 7864.13 | 0 |  |  | C000081300 | 7864.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000219 | Absa Die Restant Newcast | Absa Die Restant Newcastle-Seperate Gen |  |  | Region 3 | Kwazulu-Natal | 78136X | 1000-71215-01 | Die Restant Newcastle-Voortrekker St-Newcastle | Y | 2023-05-05 |  |  | ALP-KZ2005 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  | L | 2024-10-30 | NOMNGANGAL | 2023-03-31 | D | 0 | Approved at BTB 13 April 2023 |  | 2023-04-13 | 2023-04-13 | 748818.6 | Approved | {"MANDT":"111","REFERENCE":90000219,"ONEVIEW":"","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-04","DATE08":"2023-06-25","DATE09":"2023-08-09","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000090807 | PHASE10 | 2023-05-25 | 2023-06-24 | NANDE MAQUBELA | Juanita Van Coller | 23000084 |  |  |  |  | 2023-06-09 | 651146.61 | 0 |  |  | C000090807 | 651146.61 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000220 | Various- Retail Documentation Compliance | Various- Retail Documentation Compliance |  |  | National | National | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | U | 2023-05-02 | 2023-12-15 |  | ALP-N00045 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa |  |  | 2023 |  | U |  | LOUISR | 2023-03-31 | D | 9198388.83 |  | 100 | 2023-05-03 | 2023-05-11 | 9198388.83 |  | {"MANDT":"111","REFERENCE":90000220,"ONEVIEW":"21526X","DATE01":"2023-02-21","DATE02":"2023-02-28","DATE03":"2023-03-21","DATE04":"2023-03-28","DATE05":"2023-04-18","DATE06":"2023-05-02","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-02","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000092753 | PHASE10 | 2023-05-02 | 2023-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-06-14 | 2023-06-15 |  |  | 2023-06-20 | 7998598.98 | 0 |  |  | C000092753 | 7998598.98 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000221 | Absa Patensie - Generator Rental | Absa Patensie - Generator Rental |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2023-12-31 |  |  | ASP-EC0300 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-04-04 | D | 0 |  | 1 |  |  | 0 | 14 April Estimated Final cost R300k for the 90 Days shared with Absa Engineering - Outcome deemed not Viable | {"MANDT":"111","REFERENCE":90000221,"ONEVIEW":"77876X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgQXByaWwgRXN0aW1hdGVkIEZpbmFsIGNvc3QgUjMwMGsgZm9yIHRoZSA5MCBEYXlzIHNoYXJlZCB3aXRoIEFic2EgRW5naW5lZXJpbmcgLSBPdXRjb21lIGRlZW1lZCBub3QgVmlhYmxlIA==","RATING":""} |  |  |  | PHASE12 | 2023-06-13 | 2023-07-13 | RODERICK NEVAY | nokuthula manzini | 23000378 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000222 | Absa Mqanduli - UPS | Absa Mqanduli - UPS |  |  | Region 2 | Eastern Cape | 78937X | 1000-71058-01 | Main Street Mqanduli-Main St-Mqanduli |  | 2023-06-30 | 2023-06-30 |  | ASP-EC0301 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-04-04 | D | 0 |  | 1 |  |  | 0 | 20 April @ CB Review meeting held it was stated by Head Engineering to be funded from GMP, if an outside factor determined once RCF completed on the unit it will then to be taken back to CB for noting. Was R 60 961.62 | {"MANDT":"111","REFERENCE":90000222,"ONEVIEW":"78937X","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-05-26","DATE05":"2023-06-16","DATE06":"2023-06-30","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-30 | 2023-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000223 | Absa Butterworth - Yellow LED Replacemen | Absa Butterworth - Yellow LED Replacemen |  |  | Region 2 | Eastern Cape | 78501X | 1000-71048-01 | High Road Butterworth-Cnr High Rd & Bell St-Butterworth |  | 2023-06-30 | 2023-06-30 |  | ASP-EC0302 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-04-04 | D | 0 |  | 1 |  |  | 0 | 3 April - Approved PRF Pending - To be part of National Programme - Repairs - GMP | {"MANDT":"111","REFERENCE":90000223,"ONEVIEW":"78501X","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-05-26","DATE05":"2023-06-16","DATE06":"2023-06-30","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgU2VwdCBOb3QgcGFydCBvZiBHTVAgLSBQYXJ0IG9mIG5hdGlvbmFsIExFRCByZXBsYWNlbWVudHMsIExpZ2h0cyB1c2VkIGZyb20gR2FyZGVuIFJvdXRlIE1hbGwKMyBBcHJpbCAtIEFwcHJvdmVkIFBSRiBQZW5kaW5nIC0gVG8gYmUgcGFydCBvZiBOYXRpb25hbCBQcm9ncmFtbWU=","RATING":""} |  |  |  | PHASE12 | 2023-06-30 | 2023-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000224 | Absa Vincent Park - Yellow LED Replaceme | Absa Vincent Park - Yellow LED Replaceme |  |  | Region 2 | Eastern Cape | 78697X | 1000-71051-01 | Vincent Park-Devereux Ave-East London |  | 2023-06-30 | 2023-06-30 |  | ASP-EC0303 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-04-04 | D | 0 |  | 1 |  |  | 0 | 3 April - Approved PRF Pending - To be part of National Programme | {"MANDT":"111","REFERENCE":90000224,"ONEVIEW":"78697X","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-05-26","DATE05":"2023-06-16","DATE06":"2023-06-30","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-30 | 2023-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000225 | Absa Grahamstown - Yellow LED Replacemen | Absa Grahamstown - Yellow LED Replacemen |  |  | Region 2 | Eastern Cape | 77512X | 1000-71029-01 | Absa Grahamstown-High St-Grahamstown |  | 2023-06-30 | 2023-06-30 |  | ASP-EC0304 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-04-04 | D | 0 |  | 1 |  |  | 0 | 3 April - Approved PRF Pending - Part of National Programme | {"MANDT":"111","REFERENCE":90000225,"ONEVIEW":"77512X","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-05-26","DATE05":"2023-06-16","DATE06":"2023-06-30","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBBcHJpbCAtIEFwcHJvdmVkIFBSRiBQZW5kaW5nIC0gUGFydCBvZiBOYXRpb25hbCBQcm9ncmFtbWU=","RATING":""} |  |  |  | PHASE12 | 2023-06-30 | 2023-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000226 | Absa Bizana - Generator Repairs | Absa Bizana - Generator Repairs Including Rental |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2023-06-30 | 2023-06-30 |  | ASP-EC0305 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-04-04 | D | 174041 |  | 100 | 2023-08-15 | 2023-08-31 | 174041 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000226,"ONEVIEW":"70633X","DATE01":"2023-08-08","DATE02":"2023-08-11","DATE03":"2023-08-15","DATE04":"2023-08-22","DATE05":"2023-08-31","DATE06":"2023-08-31","DATE07":"2023-10-20","DATE08":"2024-01-31","DATE09":"2024-03-16","DATE10":"2024-03-31","DATE11":"2023-12-25","DATE12":"2023-12-25","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"145:3:4:7:9:0:50:103:45:6","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-10-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggLSBFbmdpbmVlcmluZyB0byBjb25maXJtIGlmIFdhcnJhbnRlZSBEb2N1bWVudHMgc3VibWl0dGVkIHRvIENSRVMgRW5naW5lZXJpbmcKNCBNYXJjaCBBYnNhIHJlcXVlc3RlZCByZXBvcnRzIHJlIHBhcnRzL1dhcnJhbnR5IGFuZCBjb25maXJtYXRpb24gZnJvbSBCaWR2ZXN0IEVuZ2luZWVyaW5nCjQgTWFyY2ggTWVldGluZyBzZXQgdG8gY29uZmlybSBBYnNhIHN0YW5kIDQgTWFyY2gKMjIgRmViIFByb2plY3QgRXhlYyB0byBhZGRyZXNzIHdpdGggQWJzYSBFbmcgZm9yIFNpZ25vZmYKMTUgRmViIFBPQyB3aXRoIEFic2EgRW5nIGZvciBzaWdub2ZmLiBDdXJyZW50bHkgYmVpbmcgcmVqZWN0ZWQKOSBGZWIgUmVzZW50IHRvIERKIGZvciB1cGxvYWQgZm9yIEFic2EgRW5nIFNpZ25vZmYKMDggRmViIFBPQyBlc2NhbGF0ZWQgZm9yIHNpZ25vZmYKNSBGZWIgLSBIYXZlIGVzY2FsYXRlZCBmb3Igc2lnbm9mZgoxIEZlYiAtIE1lZXRpbmcgc2NoZWR1bGVkIDEgRmViCjIyIEphbiBQTSB0byBmb2xsb3cgdXAgd2l0aCBTaGF1biAKMTggSmFuIEJpZHZlc3QgRW5naW5lZXJpbmcgdG8gU2luZyBPZmYKMTQgRGVjIC0gQlYgRW5naW5lZXJpbmcgdG8gZm9sbG93IHVwIHJlIHF1ZXN0aW9ucyBieSBDUkVTIEVuZ2luZWVyaW5nIGluIG9yZGVyIGZvciBBYnNhIHRvIFNpZ24gb2ZmCjExIERlYyBGZWVkYmFjayBwZW5kaW5nIGZyb20gQlYgRW5nIHRvIEFic2EgRW5nLiBQT0MgYXBwcm92YWwgcGVuZGluZyAKNyBEZWMgRmVlZGJhY2sgcGVuZGluZyB0byBBYnNhIEVuZ2luZWVyaW5nIGZyb20gQlYgRW5naW5lZXJpbmcgcmUgY3VycmVudCBzaXR1YXRpb24sIFBPQyBiZWluZyByZWplY3RlZCBieSBBYnNhIEVuZ2luZWVyaW5nIHBlbmRpbmcgZmVlZGJhY2sKNCBEZWMgUE9DIHN0aWxsIHdpdGggQWJzYSBFbmdpbmVlcmluZyBmb3IgU2lnbm9mZgozMCBOb3YgLSBXaXRoIEFic2EgRW5nIGZvciBTaWdub2ZmCjI3IE5vdiBQTSB0byBmb2xsb3cgdXAgcmUgc2lnbm9mZgoyMyBOb3YgUG0gdG8gZm9sbG93IHVwIHJlIHNpZ25vZmYKMjMgTm92IENyZXMgRW5nIHJlcXVlc3RlZCBpbmZvcm1hdGlvbiBmcm9tIEJpZHZlc3QuIEZpbmFsIG91dGNvbWUgdG8gYmUgZGVjaWRlZCBieSBDcmVzIEVuZy4KMTcgTm92IFBPQyBQYWNrIHN1Ym1pdHRlZCBmb3IgYXBwcm92YWwKMTYgTm92IE9uZ29pbmcgQmlkdmVzdCBFbmcgdG8gZW5nYWdlIENyZXMgRW5nIGZvciBhIHBlcm1hbmVudCBzb2x1dGlvbgo2IE5vdiAtIFBNIHRvIGNvbXBpbGUgZnVsbCByZXBvcnQgcmUgb3B0aW9ucyAtIFJlcGxhY2UgcmVwYWlyIGV0Yy4uLi4KMjYgT2N0IEVORyBhbmQgUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yCjIzIE9jdCBQTSB0byBmb2xsb3cgdXAgd2l0aCBWZW5kb3IgcmUgcHJvZ3Jlc3MKMTYgT2N0IC0gVmVuZG9yIHRvIHJlbWVkaWF0ZSBiZWZvcmUgcmV0dXJuaW5nIHRvIHNpdGUuCjEyIE9jdCBMb2FuIFVuaXQgb24gcm91dGUgYmFjayB0byBCaXphbmEgdG8gYmUgaW5zdGFsbGVkIDEyIE9jdAoxMCBPY3QgLSBHZW5lcmF0b3IgSW5zdGFsbGVkIGFuZCBGYWlsZWQgdG8gc3RhcnQgLSBWZW5kb3IgSW52ZXN0aWdhdGluZyBDYXVzZQo5IE9jdCBGYWN0b3J5IHRlc3QgY29tcGxldGVkIC0gUGFzc2VkCjYgT2N0IC0gUmVmdXJiZWQgZ2VuZXJhdG9yIHRvIGJlIHJldHVybmVkIHRvIHNpdGUgYnkgRnJpZGF5IDEzdGgsIG5vIGltcGFjdCBpbiB0ZXJtcyBvZiByZW50YWxzIGFzIGNvbmZpcm1lZCB3aXRoIHRoZSBWZW5kb3IKNSBPY3QgLSBWZW5kb3Igd2FpdGluZyBmb3IgT3V0c3RhbmRpbmcgRUNVLCB0ZXN0ZWQgZmluZSBvbiBsb2FuIHVuaXQKMjggU2VwdCBVbml0IEZhaWxlZCB0byBzdGFydCBWZW5kb3IgdG8gYWR2aXNlIG5ldyBEYXRlIGFzIHdhcyBwbGFubmluZyBmb3IgdGhlIDI5dGgKMjEgU2VwdCAtIFBsYW5uZWQgaW5zdGFsbCBkYXRlIDI5IFNlcHQxMSBTZXB0IC0gUE8ncyBzaGFyZWQgd2l0aCBWZW5kb3IgZm9yIHJlcGFpcnMgYW5kIGV4dGVuc2lvbiBvZiByZW50YWwKOCBTZXB0IEJWIFBPJ3MgcmVjZWl2ZWQgNDUwMDg1NzUxNCwgNDUwMDg1NzUxNSBVbml2ZXJzYWwgUG93ZXIKNiBTZXB0IEFic2EgUE8gcmVjZWl2ZWQgQzAwMDEwODY4Mwo1IFNlcHQgQXBwcm92ZWQgQ0IzMyAgbm8gUE9zIHJlY2VpdmVkCkFzIHBlciB0aGUgZW1haWwgZnJvbSB0aGUgc3VwcGxpZXIsIHRoZXkgY291bGQgaGF2ZSB0aGUgR2VuZXJhdG9yIG9uIHNpdGUgYnkgdGhlIDI2LzA5IGlmIHdlIGlzc3VlIHRoZW0gYSBQTyBiZWZvcmUgMDgvMDkKMzEgQXVnIEFwcHJvdmVkIENCMzMgLSBTaWduZWQgRGVjayBQZW5kaW5nIGluIG9yZGVyIHRvIHJlcXVlc3QgUE8ncyAtIFJlZnVyYmlzaGVkIENvc3QgLSBSMTE4IDg0MS4wMCBpbmNsLiBWQVQgRXh0ZW5kZWQgUmVudGFsICgwOS4wOC4yMDIzIHRvIDA5LjEwLjIwMjMpIC0gUjU1IDIwMC4wMCBpbmNsLiBWQVQKMTggQXVnIFN1Ym1pdHRlZCBpbiBDQjMyIERlY2sgCjE1IEF1ZyBTdWJtaXR0ZWQgdG8gQWJzYSBFbmdpbmVlcmluZyBmb3IgYXBwcm92YWwKMTQgQXVnIC0gT09DIEJDIHRvIGJlIHN1Ym1pdHRlZCB0byBBYnNhIEVuZ2luZWVyaW5nCjggQXVnIFBSRiBSZWNlaXZlZCIK","RATING":"Low"} |  |  | C000108683 | PHASE09 | 2023-08-31 | 2023-10-20 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-06 | 151340 | 0 |  |  | C000108683 | 151340 |  | 0 |  | 0 | 0 | C000146584 | 174041 |  | 0 | 2023-11-30 |  | 2024-03-04
90000227 | Absa York Street - Exhaust Extension | Absa York Street - Exhaust Extension |  |  | Region 2 | Eastern Cape | 79394X | 1000-70917-01 | Absa 106 York Street-York St-George | N | 2023-06-30 | 2023-06-30 |  | ASP-EC0306 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-04-04 | D | 95904.48 | 2023.05.31: Approved by Kobus JvR as per email 2023.05.30: Supported by Rob L | 100 | 2023-06-01 | 2023-06-01 | 95904.48 | Approved | {"MANDT":"111","REFERENCE":90000227,"ONEVIEW":"79394X","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-06-01","DATE05":"2023-06-01","DATE06":"2023-07-24","DATE07":"2023-08-06","DATE08":"2023-08-27","DATE09":"2023-10-11","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":50,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"162:7:21:13:0:53:13:21:45:9","PROGRESS":30,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-24","FORECAST_END":"2023-08-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVseSBQbGFubmVkIFN0YXJ0IG9uIFNpdGUgMjQgSnVseQ==","RATING":"Medium"} |  |  | C000089809 | PHASE11 | 2023-08-30 | 2023-09-11 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-06-07 | 83395.2 | 0 |  |  | C000089809 | 83395.2 |  | 4566.88 |  | 0 | 0 |  | 0 |  | 0
90000228 | Absa Queenstown - New plug point | Absa Queenstown - New plug point |  |  | Region 2 | Eastern Cape | 78801X | 1000-71054-01 | Hexagon Circle-Hexagon Circle-Queenstown | N | 2023-06-30 | 2023-06-30 |  | ASP-EC0307 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-04-04 | D | 8971.62 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-04 | 2023-05-03 | 8971.62 | Approved | {"MANDT":"111","REFERENCE":90000228,"ONEVIEW":"78801X","DATE01":"2023-04-03","DATE02":"2023-04-03","DATE03":"2023-04-14","DATE04":"2023-05-04","DATE05":"2023-05-04","DATE06":"2023-05-13","DATE07":"2023-05-13","DATE08":"2023-06-05","DATE09":"2023-07-20","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:11:20:0:9:0:23:45:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-13","FORECAST_END":"2023-05-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBKdW5lIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000083199 | PHASE11 | 2023-05-13 | 2023-05-13 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-05 | 7801.41 | 0 |  |  | C000083199 | 7801.41 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000229 | Towers West Phase Two Lift Ports | Towers West Phase Two Lift Ports Replace each and every existing Z-Line Terminal with a PORT 1 BLE Terminal (Black). Replace all existing fixture shaft wiring. Install Power over Ethernet (POE) interphase boxes. Replace all exisiting Designation Plates. Install 1 x Handicap Designation riser per group. Supply and Install 2 x Programming Stations per Group, one in the Lift Motor Room and one for the Customers benificial use. Provision of My PORT Public functionality License Agreement for 2 years, thereafter an Annual fee will apply. Professional Lift Consultant Services Technical and quality checks of the detailed drawings; Checking and approval of lift operating philosophy; Approval of operating software philosophy; Installation quality control on electric components; Overseeing Installation and approval of quality; Update of current Annexure B (Safety Certificates); Installation sign-off at commissioning and Hand-Over. | bnVsbCA%3D |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-03-28 | NaNN----a- |  | ALP-GS0057 | REL BUDG AVAC SETC: | SAP_018 | R | false | null | Christopher Mpofu | na | null | 0 |  | F |  | GAMIETR | 2023-04-04 | D | 10345176.11 | Approved at BTB on 20 July 2023 by Absa CRES | 100 | 2023-07-20 | 2023-07-20 | 10345176.11 | Approved at BTB on 20 July 2023 by Absa CRES | {"MANDT":"111","REFERENCE":90000229,"ONEVIEW":"21526X","DATE01":"2023-01-17","DATE02":"2023-02-16","DATE03":"2023-03-09","DATE04":"2023-03-16","DATE05":"2023-04-20","DATE06":"2023-09-04","DATE07":"2023-10-30","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":60,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-04","FORECAST_END":"2023-10-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQT+KAmXMgdG8gYmUgaXNzdWVkIGluIHRoZSBpbnRlcmlt","RATING":""} |  |  |  | PHASE04 | 2023-09-04 | 2023-10-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000004 | [5 empty] | 0 | 0 |  |  | NO FUNDING | 7484381.17 |  | 778855.44 |  | 0 | 0 |  | 0 |  | 0
90000230 | Absa Rustenburg Plaza - HVAC Design Chan | Absa Rustenburg Plaza - HVAC Repairs |  |  | Region 3 |  | 77309X | 1000-71603-01 | Rustenburg Plaza-Cnr Nelson Mandela St President Mbeki Dr-Rustenburg | Y | 2023-05-05 |  |  | ASP-CR0413 | CLSD ISBD AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2023-10-30 | NOMNGANGAL | 2023-04-05 | D | 376331.75 | 2023.04.05: Approved by Kobus JvR 2023.04.04: Supported by Kobus JvR | 100 | 2023-04-06 | 2023-04-06 | 376331.75 | Approved | {"MANDT":"111","REFERENCE":90000230,"ONEVIEW":"77309X","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-04","DATE08":"2023-06-25","DATE09":"2023-08-09","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VwcGxpZXIgcmVjZWl2ZWQgdGhlIFBPcyB0byBzdGFydCB3b3JraW5nLg==","RATING":""} |  |  | C000078699 | PHASE11 | 2023-05-05 | 2023-06-04 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-06 | 327245 | 0 |  |  | C000078699 | 327245 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000231 | Absa Central Square - HVAC Replacement | Absa Central Square - HVAC Replacement |  |  | Region 2 | Eastern Cape | 35033X | 1000-70958-01 | Central Square-Richardson Rd-Idutywa | N | 2023-05-12 | 2023-05-31 |  | ASP-EC0308 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-04-05 | D | 54187.29 | 2023.04.14: Approved by Kous JvR 2023.04.11: Supported by Rob L | 100 | 2023-04-14 | 2023-04-14 | 54187.29 | Contingency Remaining R1 739.42 Incl Vat | {"MANDT":"111","REFERENCE":90000231,"ONEVIEW":"35033X","DATE01":"2023-03-03","DATE02":"2023-03-10","DATE03":"2023-03-31","DATE04":"2023-04-14","DATE05":"2023-04-14","DATE06":"2023-05-23","DATE07":"2023-06-22","DATE08":"2023-06-30","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"181:7:21:14:0:39:30:8:31:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-23","FORECAST_END":"2023-06-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzAgSnVuZSBQT0MgUGFjayBTZW50IHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000080520 | PHASE11 | 2023-05-23 | 2023-06-22 | Rick Nevay | Juanita van Coller | 0 |  |  |  |  | 2023-04-19 | 47119.38 | 0 |  |  | C000080520 | 47119.38 |  | 4926.12 |  | 0 | 0 |  | 0 |  | 0
90000232 | Absa Central Square (Dutywa) - HVAC Repl | Absa Central Square (Dutywa) - HVAC Repl |  |  | Region 3 |  | 35033X | 1000-70958-01 | Central Square-Richardson Rd-Idutywa |  | 2023-05-12 |  |  | ASP-WC0274 | CRTD DLFL AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-04-05 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-05-12 | 2023-06-11 | Rick Nevay | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000233 | Absa Patensie - Due Diligence | Absa Patensie - Due Diligence and conduct signoff of recommended installation of HVAC and Fresh Air. |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2023-05-31 | 2023-05-31 |  | ASP-EC0309 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-04-06 | D | 30112.58 | 2023.04.14: Approved by Kous JvR 2023.04.11: Supported by Rob L | 100 | 2023-04-14 | 2023-04-14 | 30112.58 | Approved | {"MANDT":"111","REFERENCE":90000233,"ONEVIEW":"77876X","DATE01":"2023-03-29","DATE02":"2023-03-30","DATE03":"2023-04-03","DATE04":"2023-04-14","DATE05":"2023-04-14","DATE06":"2023-04-24","DATE07":"2023-09-15","DATE08":"2023-10-06","DATE09":"2023-11-20","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"216:1:4:11:0:10:144:21:45:26","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-24","FORECAST_END":"2023-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTAgT2N0IC0gV2FycmFudGVlIG91dHN0YW5kaW5nIGZvciBGaXJlIFBhbmVsIHRvIGNvbXBsZXRlIFN0cnVjdHVyZSBCdWlsZCAtIENBRCBkcmF3aW5ncyByZXF1ZXN0ZWQgYnkgQWJzYSBQTSB0byBmb2xsb3cgdXAuCjI4IFNlcHQgLSBGb3JtIDQgRG9jdW1lbnRzIHJlY2VpdmVkIC0gSW52b2ljZXMgb3V0c3RhbmRpbmcgCjIxIFNlcHQgLSBEb2N1bWVudHMgcGVuZGluZyBmcm9tIFZlbmRvciAtIFRvIGJlIHN1Ym1pdHRlZCB0byBUc2hhbWFubwoxOCBTZXB0IC0gQ29uc3VsdGFudCBhcHByb3ZlZCBJbnN0YWxsYXRpb24K","RATING":"Low"} |  |  | C000080000 | PHASE11 | 2023-04-24 | 2023-09-15 | Rick Nevay | Juanita van Coller | 0 |  |  |  |  | 2023-04-17 | 26184.85 | 0 |  |  | C000080000 | 26184.85 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000234 | Absa Pretoria Campus HVAC - Installation of Plenum New Boxes | Installation of Plenum boxes in block G and J System testing and commissioning Training of maintenance staff on new equipment day work period during business hours Utilize on-site security days lead time for materials |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0189 | REL BUDG SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-04-06 | D | 42527.54 | 2023.04.11: Supported by Rob L | 100 | 2023-04-14 | 2023-04-14 | 42527.54 | Approved | {"MANDT":"111","REFERENCE":90000234,"ONEVIEW":"22491X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-06-30","DATE08":"2023-09-27","DATE09":"2023-11-11","DATE10":"2023-11-30","DATE11":"2023-11-11","DATE12":"2023-11-11","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"248:7:21:7:21:14:86:89:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IDIwMjMvMTIvMjAgTk46IEZvbGxvdyB1cCB3aXRoIFNpeWEgZm9yIHNpZ25hdHVyZSA=","RATING":""} |  |  | C000080522 | PHASE08 | 2023-04-05 | 2023-06-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-04-19 | 42527.55 | 0 |  |  | C000080522 | 36980.48 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000235 | Absa Bultfontein - Waterproofing & Entir | Absa Bultfontein - Waterproofing & Entir |  |  | Region 3 |  | 79115X | 1000-71574-01 | Absa Bultfontein-President Swart St-Bultfontein |  | 2023-05-18 |  |  | ASP-CR0414 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-04-08 | D | 0 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-03 | 2023-05-03 | 114050.38 | Approved | {"MANDT":"111","REFERENCE":90000235,"ONEVIEW":"79115X","DATE01":"2023-03-09","DATE02":"2023-03-16","DATE03":"2023-04-06","DATE04":"2023-04-13","DATE05":"2023-05-04","DATE06":"2023-05-18","DATE07":"2023-06-17","DATE08":"2023-07-08","DATE09":"2023-08-22","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-18","FORECAST_END":"2023-06-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000083058 | PHASE11 | 2023-05-18 | 2023-06-17 | NANDE MAQUBELA | Juanita Van Coller | 23000113 |  |  |  |  | 2023-05-04 | 99174.24 | 0 |  |  | C000083058 | 99174.24 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000236 | Absa Kimberley RHO- Repl | Absa Kimberley RHO- Replacement of 10KVA |  |  | Region 3 |  | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley | Y | 2023-04-28 |  |  | ASP-CR0415 | CLSD BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2020-07-30 | NOMNGANGAL | 2023-04-12 | D | 69729.74 | 2023.04.19: Approved by Kobus JvR 2023.04.18: Supported by Rob L | 100 | 2023-04-20 | 2023-04-20 | 69729.74 | Approved- Reprioritised | {"MANDT":"111","REFERENCE":90000236,"ONEVIEW":"78316X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-03-17","DATE04":"2023-03-24","DATE05":"2023-04-14","DATE06":"2023-04-28","DATE07":"2023-05-28","DATE08":"2023-06-18","DATE09":"2023-08-02","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000079208 | PHASE11 | 2023-04-28 | 2023-05-28 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-04-12 | 60634.56 | 0 |  |  | C000079208 | 60634.56 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000237 | Absa Brandfort -Sewer Pipe Inspection an | Absa Brandfort -Sewer Pipe Inspection an |  |  | Region 3 |  | 79333x | 1000-71584-01 | Absa Brandfort |  | 2023-05-05 |  |  | ASP-CR0416 | CRTD AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-04-12 | D | 0 |  | 100 |  |  | 68022.52 |  | {"MANDT":"111","REFERENCE":90000237,"ONEVIEW":"79333x","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-04","DATE08":"2023-06-25","DATE09":"2023-08-09","DATE10":"2023-08-18","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":95,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2Ugc3VibWl0dGVkIA==","RATING":""} |  |  |  | PHASE11 | 2023-05-05 | 2023-06-04 | NANDE MAQUBELA | floyd mofokeng | 23000542 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000238 | Absa Towers West Replace flags with vinyl | Remove all existing Flags Supply and Install new Vinyl African Nations Flags to glass |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-04-11 | 2023-05-31 |  | ASP-GS0637 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-04-12 | D | 61563.76 |  | 100 | 2023-03-27 | 2023-03-30 | 61563.76 |  | {"MANDT":"111","REFERENCE":90000238,"ONEVIEW":"21526X","DATE01":"2023-01-31","DATE02":"2023-02-07","DATE03":"2023-02-28","DATE04":"2023-03-07","DATE05":"2023-03-28","DATE06":"2023-04-28","DATE07":"2023-05-29","DATE08":"2023-06-19","DATE09":"2023-08-03","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"212:7:21:7:21:31:31:21:45:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000079105 | PHASE11 | 2023-04-28 | 2023-05-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-12 | 53533.7 | 0 |  |  | C000079105 | 53533.7 |  | 5596.71 |  | 0 | 0 |  | 0 |  | 0
90000239 | Horison Dilaps | Horison Dilaps/Reinstatement |  |  | Region 1 |  | 76458X | 1000-71379-01 | Horison Park-Ontdekkers Rd-Roodepoort | N | 2023-04-11 |  |  | ASP-GS0638 | REL BUDG AVAC RESA SETC: |  | false | false |  | (Non PM) |  |  | 2023 |  |  | 2024-09-29 | GAMIETR | 2023-04-12 | D | 114074.95 | Approved at CB/BTB | 100 | 2023-04-21 | 2023-04-24 | 105862.87 | Approved | {"MANDT":"111","REFERENCE":90000239,"ONEVIEW":"76458X","DATE01":"2023-01-31","DATE02":"2023-02-07","DATE03":"2023-02-28","DATE04":"2023-03-07","DATE05":"2023-03-28","DATE06":"2023-04-11","DATE07":"2023-05-11","DATE08":"2023-06-01","DATE09":"2023-07-16","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-11","FORECAST_END":"2023-05-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IFByb2plY3QgY29tcGxldGVkIGFuZCBQT0Mgc3VibWl0dGVkIA==","RATING":""} |  |  | C000106276 | PHASE10 | 2023-04-11 | 2023-05-11 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-25 | 103251.49 | 0 |  |  | C000081492 | 92054.67 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000240 | Absa Bridge Park Bridge Way - Connection of VC Equipment to UPS Supply | Absa Bridge Park Bridge Way -Connection of VC Equipment to UPS Supply |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2023-05-04 | 2023-05-26 |  | ASP-WC0275 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-04-12 | D | 6118.15 | 2023.04.19: Approved by Kobus JvR 2023.04.18: Supported by Rob L | 100 | 2023-04-20 | 2023-04-20 | 6118.15 | Approved | {"MANDT":"111","REFERENCE":90000240,"ONEVIEW":"36225X","DATE01":"2023-04-12","DATE02":"2023-04-13","DATE03":"2023-04-13","DATE04":"2023-04-20","DATE05":"2023-04-20","DATE06":"2023-05-02","DATE07":"2023-05-02","DATE08":"2023-06-05","DATE09":"2023-06-26","DATE10":"2023-07-26","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"110:1:0:7:0:12:0:34:21:11","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-02","FORECAST_END":"2023-05-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBKdW5lIEZpbmFsIFBPQyBTdWJtaXR0ZWQ=","RATING":"Low"} |  |  | C000081302 | PHASE11 | 2023-05-02 | 2023-05-02 | Rick Nevay | Michael Maluleka | 0 |  |  |  |  | 2023-04-21 | 5320.13 | 0 |  |  | C000081302 | 5320.13 |  | 556.2 |  | 0 | 0 |  | 0 |  | 0
90000241 | Meyerton Dilaps | Meyerton Dilaps |  |  | Region 1 | Gauteng | 77636X | 1000-70376-01 | Absa Meyerton-Loch St-Meyerton | N | 2023-04-11 |  |  | ASP-GS0639 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-04-13 | D | 5963.03 | Approved at CB/BTB | 100 | 2023-05-01 | 2023-04-12 | 68574.8 | Approved | {"MANDT":"111","REFERENCE":90000241,"ONEVIEW":"77636X","DATE01":"2023-01-31","DATE02":"2023-02-07","DATE03":"2023-02-28","DATE04":"2023-03-07","DATE05":"2023-03-28","DATE06":"2023-04-11","DATE07":"2023-05-30","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"181:7:21:7:21:14:49:56:45:15","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-11","FORECAST_END":"2023-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgUE9DIGlzc3VlZCBhbmQgaW52b2ljZWQuCg==","RATING":""} |  |  | C000079646 | PHASE10 | 2023-04-11 | 2023-05-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-08 | 81596.17 | 0 |  |  | C000079646 | 59630.26 |  | 8613 |  | 0 | 0 |  | 0 |  | 0
90000242 | Absa 264 Victoria Road--Install Battery backup Roller Shutter Door | Absa 264 Victoria Road-Install Battery backup Roller Shutter Door |  |  | Region 2 | Western Cape | 78104X | 1000-70883-01 | 264 Victoria Road-Victoria Rd-Woodstock | N | 2023-05-25 |  |  | ASP-WC0276 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-04-14 | D | 45649.82 | 2023.04.19: Approved by Kobus JvR 2023.04.18: Supported by Rob L | 100 | 2023-04-20 | 2023-04-20 | 45649.82 | Approved | {"MANDT":"111","REFERENCE":90000242,"ONEVIEW":"78104X","DATE01":"2023-04-13","DATE02":"2023-04-14","DATE03":"2023-04-17","DATE04":"2023-04-20","DATE05":"2023-04-20","DATE06":"2023-05-08","DATE07":"2023-05-15","DATE08":"2023-06-14","DATE09":"2023-06-26","DATE10":"2023-07-26","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"109:1:3:3:0:18:7:30:12:2","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-08","FORECAST_END":"2023-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgSnVuZSBQT0Mgc3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000081304 | PHASE11 | 2023-05-08 | 2023-05-15 | Rick Nevay | Michael Maluleka | 0 |  |  |  |  | 2023-04-21 | 39695.5 | 0 |  |  | C000081304 | 39695.5 |  | 4138.62 |  | 0 | 0 |  | 0 |  | 0
90000243 | test title only added | We have to correct the text to see the correct text | VjFjd01WWXlUWGxUYTFKU1ZURldObFZyVGxabFZURkNTbFJPUlVwVVRrVktWRWwz | m | Region 3 | Mpumalanga | 20019X |  | Building not in Real Estate Database |  | 2023-05-26 | 2023-05-31 |  |  |  | SAPMT | false | false | null |  | na | There are no notes here | 0 |  |  |  |  | 2023-04-16 |  | 100 | WHat happended here? | 20 | 2023-04-25 | 2023-04-27 | 110 | This is a long note | {"MANDT":"111","REFERENCE":90000243,"ONEVIEW":"20019X","DATE01":"2023-03-01","DATE02":"2023-03-08","DATE03":"2023-03-29","DATE04":"2023-04-05","DATE05":"2023-04-30","DATE06":"2023-05-14","DATE07":"2023-05-28","DATE08":"2023-06-18","DATE09":"2023-08-02","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":60,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"152:7:21:7:25:14:14:21:45:2","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-14","FORECAST_END":"2023-05-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Tm90aGluZyUyMG1vcmUlMjB0byUyMHNheSUyMG9yJTIwd2hhdCUzRg==","RATING":"Low"} |  |  |  | PHASE05 | 2023-05-14 | 2023-05-28 |  |  | 0 |  |  |  |  | NaNN-aN-Na | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000244 | Pretoria Campus Entrance Tiling | Pretoria Campus Block B - External Entrance Tiling |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-04-17 |  |  | ASP-GN0190 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-04-17 | D | 159069.28 | 2023.04.12: Approved by Conrad M | 100 | 2023-04-14 | 2023-04-14 | 159069.28 | Approved | {"MANDT":"111","REFERENCE":90000244,"ONEVIEW":"Unknown","DATE01":"2023-03-15","DATE02":"2023-03-22","DATE03":"2023-04-12","DATE04":"2023-04-19","DATE05":"2023-05-10","DATE06":"2023-05-24","DATE07":"2023-05-31","DATE08":"2023-06-21","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-24","FORECAST_END":"2023-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IFByb2plY3QgaXMgY29tcGxldGUuIFBPQyBoYXMgYmVlbiBzdWJtaXR0ZWQgdG8gZmluYW5jZS4=","RATING":""} |  |  | C000080523 | PHASE11 | 2023-05-24 | 2023-05-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-04-19 | 159069.28 | 0 |  |  | C000080523 | 138321.11 |  | 14272.65 |  | 0 | 0 |  | 0 |  | 0
90000245 | Pretoria Campus 14 X Door Seal | Pretoria Campus 14 X Door Seal |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-04-17 |  |  | ASP-GN0191 | REL BUDG SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-04-17 | D | 16419.6 | 2023.04.12: Approved by Conrad M | 100 | 2023-04-14 | 2023-04-14 | 16419.6 | Approved | {"MANDT":"111","REFERENCE":90000245,"ONEVIEW":"22491X","DATE01":"2023-03-16","DATE02":"2023-03-23","DATE03":"2023-04-13","DATE04":"2023-04-20","DATE05":"2023-05-11","DATE06":"2023-05-25","DATE07":"2023-05-31","DATE08":"2023-06-21","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"2023-08-05","DATE12":"2023-08-05","PROG01":100,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-25","FORECAST_END":"2023-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEuMDI6IEJGTSBFbmdpbmVlcmluZyB0byBhZHZpc2Ugb24gdGhlIHdlYXRoZXIgc3RyaXAgc3BlY2lmaWNhdGlvbnMu","RATING":""} |  |  | C000080521 | PHASE06 | 2023-05-25 | 2023-05-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-04-19 | 16419.61 | 0 |  |  | C000080521 | 14277.92 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000246 | Absa Swartruggens - Conn | Absa Swartruggens - Connecting CS &Telle |  |  | Region 3 |  | 77433X | 1000-71291-01 | Swartruggens-Sarel Cilliers St-Swartruggens | Y | 2023-05-05 |  |  | ASP-CR0417 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2022-11-29 | NOMNGANGAL | 2023-04-19 | D | 6368.7 | 2023.04.26: Approved by Kobus JvR as per email 2023.04.25: Supported by Rob L | 100 | 2023-04-21 | 2023-04-26 | 6368.7 | Approved | {"MANDT":"111","REFERENCE":90000246,"ONEVIEW":"77433X","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-04","DATE08":"2023-06-25","DATE09":"2023-08-09","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000082132 | PHASE11 | 2023-05-05 | 2023-06-04 | NANDE MAQUBELA | Floyd Mofokeng | 23000411 |  |  |  |  | 2023-04-26 | 5538 | 0 |  |  | C000082132 | 5538 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000247 | Absa 31 Church Street | Absa 31 Church Street Victoria West-Rent |  |  | Region 3 |  | 21821X | 1000-71320-01 | 31 Church Street Victoria West-Church St-Victoria West | Y | 2023-05-11 |  |  | ASP-CR0418 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2025-03-30 | NOMNGANGAL | 2023-04-19 | D | 85119.03 | 2023.04.26: Approved by Kobus JvR as per email Supported by BFM Engineering | 100 | 2023-04-21 | 2023-04-26 | 85119.03 | Approved | {"MANDT":"111","REFERENCE":90000247,"ONEVIEW":"21821X","DATE01":"2023-03-02","DATE02":"2023-03-09","DATE03":"2023-03-30","DATE04":"2023-04-06","DATE05":"2023-04-27","DATE06":"2023-05-11","DATE07":"2023-06-10","DATE08":"2023-07-01","DATE09":"2023-08-15","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-11","FORECAST_END":"2023-06-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEF3YWl0aW5nIFBDIHNpZ24gb2ZmLg==","RATING":""} |  |  | C000082102 | PHASE11 | 2023-05-11 | 2023-06-10 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-04-26 | 74016.55 | 0 |  |  | C000082102 | 74016.55 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000248 | Moffett Office Park - Air Vents - Cold Well Cupboard | Moffett Office Park - Air Vents - Cold Well Cupboard |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-05-10 | 2023-06-30 |  | ASP-EC0310 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-04-19 | D | 2150.5 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Judith B | 100 | 2023-07-21 | 2023-07-27 | 2150.5 | 5 Sept Completed 05/09 | {"MANDT":"111","REFERENCE":90000248,"ONEVIEW":"22937X","DATE01":"2023-05-10","DATE02":"2023-05-31","DATE03":"2023-07-12","DATE04":"2023-07-21","DATE05":"2023-07-27","DATE06":"2023-09-05","DATE07":"2023-09-05","DATE08":"2023-09-26","DATE09":"2023-11-10","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"174:21:42:9:6:40:0:21:45:1","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-05","FORECAST_END":"2023-09-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBTZXB0IENvbXBsZXRlZCAwNS8wOQ==","RATING":"Low"} |  |  | C000100704 | PHASE11 | 2023-09-05 | 2023-09-05 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-28 | 1870 | 0 |  |  | C000100704 | 1870 |  | 195.5 |  | 0 | 0 |  | 0 |  | 0
90000249 | Absa Shelly Beach- Extension of Rental G | Absa Shelly Beach- Extension of Rental G |  |  | Region 3 |  | 77417X | 1000-71171-01 | Absa Shelly Beach |  | 2023-04-27 |  |  | ASP-KZ0245 | CLSD BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  | L | 2023-03-30 | NOMNGANGAL | 2023-04-20 | D | 98739 | 2023.04.26: Approved by Kobus JvR as per email Supported by BFM Engineering |  | 2023-04-26 | 2023-04-26 | 98739 | Approved | {"MANDT":"111","REFERENCE":90000249,"ONEVIEW":"Unknown","DATE01":"2023-02-16","DATE02":"2023-02-23","DATE03":"2023-03-16","DATE04":"2023-03-23","DATE05":"2023-04-13","DATE06":"2023-04-27","DATE07":"2023-05-27","DATE08":"2023-06-17","DATE09":"2023-08-01","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-27","FORECAST_END":"2023-05-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000082103 | PHASE11 | 2023-04-27 | 2023-05-27 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-04-26 | 85860 | 0 |  |  | C000082103 | 85860 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000250 | Absa Kamaqhekeza-Supply Portable tempora | Absa Kamaqhekeza-Supply Portable tempora |  |  | Region 3 | Mpumalanga | 77571X | 1000-70637-01 | Kamaqhekeza Plaza-Main Rd-Balfour | U | 2023-04-26 |  |  | ASP-MP0157 | CLSD BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-04-20 | D | 23313.26 | 2023.04.26: Approved by Kobus JvR as per email 2023.04.25: Supported by Rob L | 100 | 2023-04-26 | 2023-04-26 | 23313.26 | Approved | {"MANDT":"111","REFERENCE":90000250,"ONEVIEW":"Unknown","DATE01":"2023-02-15","DATE02":"2023-02-22","DATE03":"2023-03-15","DATE04":"2023-03-22","DATE05":"2023-04-12","DATE06":"2023-04-26","DATE07":"2023-05-26","DATE08":"2023-06-16","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-26","FORECAST_END":"2023-05-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000082104 | PHASE11 | 2023-04-26 | 2023-05-26 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-04-26 | 23313.26 | 0 |  |  | C000082104 | 20272.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000251 | Absa Koster - Waterproof | Absa Koster - Waterproofing Reinstatemen |  |  | Region 3 |  | 77546X | 1000-71294-01 | Absa Koster-Jameson Rd-Koster | N | 2023-05-04 | 2023-06-30 |  | ASP-CR0419 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-04-21 | D | 0 | 2023.05.04: Supported by Rob L | 100 | 2023-05-11 | 2023-05-11 | 25524.25 | Approved | {"MANDT":"111","REFERENCE":90000251,"ONEVIEW":"77546X","DATE01":"2023-02-23","DATE02":"2023-03-02","DATE03":"2023-03-23","DATE04":"2023-03-30","DATE05":"2023-04-20","DATE06":"2023-05-04","DATE07":"2023-06-30","DATE08":"2023-08-03","DATE09":"2023-09-17","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"219:7:21:7:21:14:57:34:45:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-04","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QVM6IDQvMDgvMjMgLiBGbG95ZCBjb25maXJtZWQgUE9DIHBhY2sgd2FzIHJlY2VpdmVkIDMgQXVndXN0IDIwMjMu","RATING":""} |  |  | C000084477 | PHASE11 | 2023-05-04 | 2023-06-30 | NANDE MAQUBELA | Floyd Mofokeng | 23000607 |  |  |  |  | 2023-05-11 | 22195 | 0 |  |  | C000084477 | 22195 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000252 | Absa Ottosdal - Waterproofing Reinstatem | Absa Ottosdal - Waterproofing Reinstatem |  |  | Region 3 |  | 78143X | 1000-71606-01 | Absa Ottosdal-Voortrekker St-Ottosdal |  | 2023-05-04 | 2023-06-30 |  | ASP-CR0420 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-04-21 | D | 0 | 2023.05.04: Supported by Rob L | 1 | 2023-05-11 | 2023-05-11 | 38101.8 | Approved | {"MANDT":"111","REFERENCE":90000252,"ONEVIEW":"78143X","DATE01":"2023-02-23","DATE02":"2023-03-02","DATE03":"2023-03-23","DATE04":"2023-03-30","DATE05":"2023-04-20","DATE06":"2023-05-04","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-04","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  | C000084473 | PHASE11 | 2023-05-04 | 2023-06-30 | NANDE MAQUBELA | floyd mofokeng | 23000246 |  |  |  |  | 2023-05-11 | 33132 | 0 |  |  | C000084473 | 33132 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000253 | Absa Ventersdorp - Water | Absa Ventersdorp - Waterproofing Reinsta |  |  | Region 3 |  | 77096X | 1000-71284-01 | Absa Ventersdorp-Charmichael St-Ventersdorp | Y | 2023-05-18 | 2023-06-30 |  | ASP-CR0421 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-04-21 | D | 0 | 2023.05.04: Supported by Rob L | 100 | 2023-04-21 | 2023-05-11 | 42113 | Approved | {"MANDT":"111","REFERENCE":90000253,"ONEVIEW":"77096X","DATE01":"2023-03-09","DATE02":"2023-03-16","DATE03":"2023-04-06","DATE04":"2023-04-13","DATE05":"2023-05-04","DATE06":"2023-05-18","DATE07":"2023-06-30","DATE08":"2023-08-03","DATE09":"2023-09-17","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"205:7:21:7:21:14:43:34:45:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-18","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QVM6NC8wOC8yMyBGbG95ZCBDb25maXJtZWQgUE9DIHBhY2sgd2FzIHJlY2VpdmVkIDMgQXVndXN0IDIwMjM=","RATING":""} |  |  | C000084470 | PHASE11 | 2023-05-18 | 2023-06-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-11 | 36620 | 0 |  |  | C000084470 | 36620 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000254 | Absa Schweizwer - Waterp | Absa Schweizwer - Waterprrofing Reinstat |  |  | Region 3 |  | 77953X | 1000-71303-01 | Absa Schweizer Reneke-Schweizer St-Schweizer Reneke | Y | 2023-05-11 | 2023-06-30 |  | ASP-CR0422 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2022-08-30 | NOMNGANGAL | 2023-04-21 | D | 0 | 2023.05.04: Supported by Rob L | 40 | 2023-05-11 | 2023-05-11 | 47214.4 | Approved | {"MANDT":"111","REFERENCE":90000254,"ONEVIEW":"77953X","DATE01":"2023-03-02","DATE02":"2023-03-09","DATE03":"2023-03-30","DATE04":"2023-04-06","DATE05":"2023-04-27","DATE06":"2023-05-11","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":90,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-11","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000084471 | PHASE11 | 2023-05-11 | 2023-06-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-11 | 41056 | 0 |  |  | C000084471 | 41056 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000255 | Pretoria Campus Upgrade/Refurb- Stormwat | Pretoria Campus Upgrade/Refurb- Stormwat |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0192 | REL BUDG AVAC SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | F |  | GAMIETR | 2023-04-21 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 284220.15 | Approved | {"MANDT":"111","REFERENCE":90000255,"ONEVIEW":"22491X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-07-21","DATE07":"2023-10-30","DATE08":"2023-11-20","DATE09":"2024-01-04","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:21:7:21:121:101:21:45:21","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-21","FORECAST_END":"2023-10-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000100032 | PHASE07 | 2023-07-21 | 2023-10-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-25 | 326853.17 | 0 |  |  | C000100032 | 247147.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000256 | Absa Northridge Shopping Mall - LED ligh | Absa Northridge Shopping Mall - LED ligh |  |  | Region 3 |  | 37037x | 1000-71588-01 | Absa Northridge Mall | N | 2023-06-22 |  |  | ASP-CR0423 | REL BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | L | 2024-04-29 | NOMNGANGAL | 2023-04-24 | D | 0 | 2023.07.20: Approved by Conrad M Supported by Cres Engineering | 40 | 2023-07-20 | 2023-07-20 | 25946.53 | Approved | {"MANDT":"111","REFERENCE":90000256,"ONEVIEW":"37037x","DATE01":"2023-04-13","DATE02":"2023-04-20","DATE03":"2023-05-03","DATE04":"2023-05-03","DATE05":"2023-06-29","DATE06":"2023-06-22","DATE07":"2023-07-22","DATE08":"2023-09-21","DATE09":"2023-11-05","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":60,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"170:7:13:0:57:-7:30:61:45:4","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-22","FORECAST_END":"2023-07-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDb21wbGV0ZWQgYnV0IG5vdCB5ZXQgaW52b2ljZWQsIEZpbmFuY2lhbCBSb2xsb3Zlcg==","RATING":""} |  |  | C000100100 | PHASE08 | 2023-06-22 | 2023-07-22 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-07-26 | 22562.2 | 0 |  |  | C000100100 | 22562.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000257 | Alice Lane North Smart Meter Installatio | Ã¢ÂÂ¢Arrive onsite, sign the register and unpack the tools inside the control room. Ã¢ÂÂ¢Perform Risk Assessment onsite and prepare proper tools Ã¢ÂÂ¢Switch off the Meter LV Breaker. Ã¢ÂÂ¢Test the voltage using line tester to check if thereÃ¢ÂÂs no voltage. Ã¢ÂÂ¢Open the meter terminal cover of the meter. Ã¢ÂÂ¢Short circuit the secondary connection of Current Transformer (CT) by removing the metering test block (PK2) cover of Feeder one and Feeder 2. Ã¢ÂÂ¢Remove the Voltage wires (VT) and CT wires from the terminal cover of the meter. Ã¢ÂÂ¢Remove the Ernemax Meter and Ester modem inside the Protection Panel. Ã¢ÂÂ¢Mount the new (L & G) meter inside the existing Protection Panel. Ã¢ÂÂ¢Connect the CT wires and VT wires to the new meter terminal block. Ã¢ÂÂ¢Energize the meter by switching on the Voltage circuit breaker. Ã¢ÂÂ¢Put back the PK 2 test block cover. Ã¢ÂÂ¢Check the polarity of the CTÃ¢ÂÂs using Map 110 Ã¢ÂÂ¢Configure the meter using Map 120 software. Ã¢ÂÂ¢Monitor the pulsing rate of the Kilowatt- Hour pulse LED while measuring the current drawn by the load and calculate the Watt-hours consumed within two minutes. Ã¢ÂÂ¢Record all the tests measurements. Ã¢ÂÂ¢Perform house cleaning and hand the system back to the customer. |  |  | Energy | Gauteng | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | N | 2023-04-21 |  |  | ASP-GS0640 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Wesigye Mukuru |  |  | 2023 |  | L | 2030-04-29 | MOKOENAM2 | 2023-04-24 | D | 6627.36 | 2023.04.26: Approved by Kobus JvR as per email 2023.04.25: Supported by Rob L | 100 | 2023-04-26 | 2023-04-26 | 6627.36 | Approved | {"MANDT":"111","REFERENCE":90000257,"ONEVIEW":"70656X","DATE01":"2023-02-10","DATE02":"2023-02-17","DATE03":"2023-03-10","DATE04":"2023-03-17","DATE05":"2023-04-07","DATE06":"2023-04-21","DATE07":"2023-05-21","DATE08":"2023-06-11","DATE09":"2023-07-26","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-21","FORECAST_END":"2023-05-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000082754 | PHASE11 | 2023-04-21 | 2023-05-21 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-03 | 6627.36 | 0 |  |  | C000082754 | 5762.92 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000258 | 17 Harrison Street - Extractor fans | 17 Harrison Street - Extractor fans |  |  | Region 1 | Gauteng South | 78786X | 1000-70435-01 | 17 Harrison Street-Harrison St-Johannesburg | N | 2023-04-21 |  |  | ASP-GS0641 | CRTD: |  | false | false |  |  |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-04-24 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000258,"ONEVIEW":"","DATE01":"2023-02-10","DATE02":"2023-02-17","DATE03":"2023-03-10","DATE04":"2023-03-17","DATE05":"2023-04-07","DATE06":"2023-04-21","DATE07":"2023-05-21","DATE08":"2023-06-11","DATE09":"2023-07-26","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-21","FORECAST_END":"2023-05-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-04-21 | 2023-05-21 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000259 | Clearwate 3 X Video Conferencing Units | Supply, deliver and install 3 x 55" Professional Display - UHD, 24/7 Usage, 500nit, Brightness, SoC Media Player: SSSP 9 Supply , deliver and install Flat panel tilt bracket 600x400 X 3 Supply P009 POLY Studio X 3 Supply ASSY, EX-MIC, POLYCOM Studio X 3 Work to take place after operation hours or weekends Allowance for security guard for duration of installation |  |  | Region 1 | Gauteng South | 77174X | 1000-70352-01 | Clearwater Office Park Building 4-Millenium Rd-Strubensvalley | N | 2023-04-25 | 2023-05-25 |  | ASP-GS0642 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  | L | 2025-07-30 | MOKOENAM2 | 2023-04-25 | D | 186629.57 | 2023.04.25: Approved by Conrad M as per email 2023.04.25: Supported by Winston P | 100 | 2023-04-26 | 2023-04-26 | 186629.57 | Approved | {"MANDT":"111","REFERENCE":90000259,"ONEVIEW":"77174X","DATE01":"2023-02-14","DATE02":"2023-02-21","DATE03":"2023-03-14","DATE04":"2023-03-21","DATE05":"2023-04-11","DATE06":"2023-04-25","DATE07":"2023-05-25","DATE08":"2023-08-31","DATE09":"2023-10-15","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"167:7:21:7:21:14:30:98:45:1","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-25","FORECAST_END":"2023-05-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Medium"} |  |  | C000082134 | PHASE08 | 2023-04-25 | 2023-05-25 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-26 | 162286.58 | 0 |  |  | C000082134 | 162286.58 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000260 | 49 Main Road Gansbaai - HVAC upgrade | 49 Main Road Gansbaai - HVAC upgrade |  |  | Region 2 | Western Cape | 77700X | 1000-70849-01 | 49 Main Road Gansbaai-Main Rd-Gansbaai | N | 2023-12-31 |  |  | ASP-WC0277 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | U |  | CEASARS | 2023-04-25 | D | 108117.9 | 2023.05.18: Approved by Kobus JvR as per email 2023.05.16: Supported by Rob L | 100 | 2023-05-18 | 2023-05-18 | 108117.9 | Contingency Remaining R 1 343.12 Incl Vat | {"MANDT":"111","REFERENCE":90000260,"ONEVIEW":"77700X","DATE01":"2023-01-19","DATE02":"2023-03-24","DATE03":"2023-05-09","DATE04":"2023-05-18","DATE05":"2023-05-18","DATE06":"2023-06-12","DATE07":"2023-07-13","DATE08":"2023-07-31","DATE09":"2023-09-14","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"254:64:46:9:0:25:31:18:45:13","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-12","FORECAST_END":"2023-07-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgSnVseSBGaW5hbCBQT0Mgc3VibWl0dGVkIHRvIGZpbmFuY2UKMTcgSnVseSBQYXJ0IDEgUE9DIFN1Ym1pdHRlZCAxNyBKdWwgLSBSIDEwMSA1MTQuODU=","RATING":"Low"} |  |  | C000086636 | PHASE11 | 2023-06-12 | 2023-07-13 | RODERICK NEVAY | Michael Maluleka | 23000227 |  |  |  |  | 2023-05-22 | 94015.57 | 0 |  |  | C000086636 | 94015.58 | CIP2023XP | 3098.09 |  | 0 | 0 |  | 0 |  | 0
90000261 | Absa Mangaung - Installation of amended | Absa Mangaung - Installation of amended |  |  | Region 3 |  | 36260X | 1000-71508-01 | Southern Centre Life Plaza-Charlotte Maxeke St-Bloemfontein |  | 2023-06-30 |  |  | ASP-CR0424 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-04-26 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000261,"ONEVIEW":"","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-05-26","DATE05":"2023-06-16","DATE06":"2023-06-30","DATE07":"2023-07-30","DATE08":"2023-08-20","DATE09":"2023-10-04","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-07-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-06-30 | 2023-07-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000262 | Absa Koster- External Refurbishment | Absa Koster- External Refurbishment |  |  | Region 3 |  | 77546X | 1000-71294-01 | Absa Koster-Jameson Rd-Koster |  | 2023-06-29 |  |  | ASP-CR0425 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-04-26 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.07.23: Supported by Leko N | 100 | 2023-08-03 | 2023-08-03 | 322232.2 | Approved | {"MANDT":"111","REFERENCE":90000262,"ONEVIEW":"77546X","DATE01":"2023-04-20","DATE02":"2023-04-27","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-09-19","DATE08":"2023-10-10","DATE09":"2023-11-24","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:7:21:7:21:14:82:21:45:4","PROGRESS":52,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-09-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCB3b3JrIGN1cnJlbnRseSBpbiBwcm9ncmVzcywgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  | C000102420 | PHASE11 | 2023-06-29 | 2023-09-19 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-08-04 | 280201.91 | 0 |  |  | C000102420 | 280201.91 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000263 | Absa Litchtenburg - External Refurbishme | Absa Litchtenburg - External Refurbishme |  |  | Region 3 |  | 77806X | 1000-71605-01 | Absa Lichtenburg-Nelson Mandela Dr-Lichtenburg |  | 2023-06-23 |  |  | ASP-CR0426 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-04-26 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Leko N | 100 | 2023-07-20 | 2023-07-20 | 497342.65 | Approved | {"MANDT":"111","REFERENCE":90000263,"ONEVIEW":"77806X","DATE01":"2023-04-14","DATE02":"2023-04-21","DATE03":"2023-05-12","DATE04":"2023-05-19","DATE05":"2023-06-09","DATE06":"2023-06-23","DATE07":"2023-07-23","DATE08":"2023-08-13","DATE09":"2023-09-27","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-23","FORECAST_END":"2023-07-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLiBEdXBsaWNhdGlvbi4=","RATING":""} |  |  | C000099533 | PHASE11 | 2023-06-23 | 2023-07-23 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-07-24 | 432471.87 | 0 |  |  | C000099533 | 432471.87 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000264 | Absa Nautilus Jeffreys Bay - UPS Connect | Absa Nautilus Jeffreys Bay - UPS Connect |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | The Nautilus Builiding-Da Gama Rd-Jeffreys Bay |  | 2023-05-15 | 2023-06-30 |  | ASP-EC0312 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-04-26 | D | 0 |  | 1 |  |  | 0 | Cancelled as approved as part of National Headwind ALP-N0043 | {"MANDT":"111","REFERENCE":90000264,"ONEVIEW":"22196X","DATE01":"2023-03-06","DATE02":"2023-03-13","DATE03":"2023-04-03","DATE04":"2023-04-10","DATE05":"2023-05-01","DATE06":"2023-05-15","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-05-15 | 2023-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000265 | Alex Plaza Dilaps | Alex Plaza Dilaps |  |  | Region 1 | Gauteng South | 36297X | 1000-70202-01 | Alex Mall-London Rd-Sandton | N | 2023-04-11 |  |  | ASP-GS0643 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2023-05-30 | GAMIETR | 2023-04-26 | D | 253219.7 | Approved at CB/BTB | 100 | 2023-04-17 | 2023-04-13 | 253219.7 | Approved | {"MANDT":"111","REFERENCE":90000265,"ONEVIEW":"Unknown","DATE01":"2023-01-31","DATE02":"2023-02-07","DATE03":"2023-02-28","DATE04":"2023-03-07","DATE05":"2023-03-28","DATE06":"2023-04-11","DATE07":"2023-05-11","DATE08":"2023-06-01","DATE09":"2023-07-16","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-11","FORECAST_END":"2023-05-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000082911 | PHASE11 | 2023-04-11 | 2023-05-11 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-03 | 253219.7 | 0 |  |  | C000082911 | 220191.04 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000266 | Absa Boardwalk Richards Bay - Seating | Absa Boardwalk Richards Bay - Seating |  |  | Region 2 |  | 36235X | 1000-71131-01 | Boardwalk Shopping Centre-Kruger Rand Rd-Richards Bay |  | 2023-05-15 | 2023-06-30 |  | ASP-WC0278 | CRTD DLFL AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  |  |  | CEASARS | 2023-04-26 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED |  |  | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000267 | Absa Zevenwacht Kuilsriver - TTW DropSafe | Absa Zevenwacht Kuilsriver - TTW DropSafe |  |  | Region 2 | Western Cape | 78340X | 1000-70897-01 | Zevenwacht Mall-Cnr Jan Van Riebeeck & Polkadraai Rd-Kuils River | N | 2023-05-15 | 2023-06-30 |  | ASP-WC0279 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-04-26 | D | 60885.42 | 2023.05.25: Approved by Conrad M 2023.05.23: Supported by Judith B as per email & Ilana vdW | 100 | 2023-05-25 | 2023-05-25 | 60885.42 | Approved | {"MANDT":"111","REFERENCE":90000267,"ONEVIEW":"78340X","DATE01":"2023-03-06","DATE02":"2023-03-13","DATE03":"2023-04-03","DATE04":"2023-04-10","DATE05":"2023-05-25","DATE06":"2023-06-17","DATE07":"2023-06-17","DATE08":"2023-07-26","DATE09":"2023-09-09","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"208:7:21:7:45:23:0:39:45:16","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-17","FORECAST_END":"2023-06-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgSnVseSBQYXJ0IDEgYW5kIDIgU3VibWl0dGVkIHRvIEZpbmFuY2UgMjYgSnVseSBQYXJ0IDEgUiAyNCA0NDQuMDAgLCBQYXJ0IDIgUiAyNzI2My4wMAoyMCBKdWx5IFBPQyBpbiBQcm9ncmVzcw==","RATING":"Low"} |  |  | C000087790 | PHASE11 | 2023-06-17 | 2023-06-17 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-05-26 | 52943.84 | 0 |  |  | C000087790 | 51541.05 |  | 2789.15 |  | 0 | 0 |  | 0 |  | 0
90000268 | Absa Bonnievale - Minor Works | Absa Bonnievale - Minor Works |  |  | Region 2 | Western Cape | 77671X | 1000-70842-01 | Absa Bonnievale-Main Rd-Bonnievale |  | 2023-06-01 | 2023-07-31 |  | ALP-WC0022 | CRTD AVAC: |  | false | false |  | Nyasha Wena | surrender |  | 2023 |  |  |  | CEASARS | 2023-04-26 | D | 0 |  | 1 |  |  | 0 | project cancelled | {"MANDT":"111","REFERENCE":90000268,"ONEVIEW":"77671X","DATE01":"2023-03-23","DATE02":"2023-03-30","DATE03":"2023-04-20","DATE04":"2023-04-27","DATE05":"2023-05-18","DATE06":"2023-06-01","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-01","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-01 | 2023-07-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000269 | Absa Eskom Bldg Swellendam - Minor Works | Absa Eskom Bldg Swellendam - Minor Works |  |  | Region 2 | Western Cape | 78147X | 1000-70893-01 | Eskom Building-Voortrek St-Swellendam | N | 2023-06-01 | 2023-07-31 |  | ALP-WC0023 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-04-26 | D | 0 |  | 1 |  |  | 0 | project cancelled | {"MANDT":"111","REFERENCE":90000269,"ONEVIEW":"78147X","DATE01":"2023-03-23","DATE02":"2023-03-30","DATE03":"2023-04-20","DATE04":"2023-04-27","DATE05":"2023-05-18","DATE06":"2023-06-01","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-01","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-01 | 2023-07-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000270 | Absa De Wagenweg Stellenbosch -MinorWork | Absa De Wagenweg Stellenbosch -MinorWork |  |  | Region 2 | Western Cape | 70650X | 1000-70785-01 | De Wagenweg Office Park Block B-Adam Tas Rd-Stellenbosch | N | 2023-06-01 | 2023-07-31 |  | ALP-WC0024 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-04-26 | D | 0 |  | 1 |  |  | 0 | project cancelled | {"MANDT":"111","REFERENCE":90000270,"ONEVIEW":"70650X","DATE01":"2023-03-23","DATE02":"2023-03-30","DATE03":"2023-04-20","DATE04":"2023-04-27","DATE05":"2023-05-18","DATE06":"2023-06-01","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-01","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-01 | 2023-07-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000271 | Sanridge SquareSupply and install a drip | Sanridge SquareSupply and install a drip |  |  | Region 1 |  | 21861X | 1000-70042-01 | Sanridge Square Shopping Centre-Cnr New & Lever Rd-Midrand | N | 2023-04-28 | 2023-05-12 |  | ASP-GN0193 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-04-28 | D | 0 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-03 | 2023-05-03 | 5364.2 | Approved | {"MANDT":"111","REFERENCE":90000271,"ONEVIEW":"35041X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-03-17","DATE04":"2023-03-24","DATE05":"2023-04-14","DATE06":"2023-04-28","DATE07":"2023-05-12","DATE08":"2023-06-02","DATE09":"2023-07-17","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCB0byBiZSByZXNjb3BlIHJlc2NvcGVkLiBUaGVyZSBpcyBpc3N1ZXMgd2l0aCB0aGUgc2NvcGUgYW5kIHRoZSBidWRnZXQgYWxsb3dlZCBmb3IuIA==","RATING":""} |  |  | C000083146 | PHASE06 | 2023-04-28 | 2023-05-12 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-05-04 | 5364.21 | 0 |  |  | C000083146 | 4664.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000272 | Park Station Supply and install a drip | Park Station Supply and install a drip Tray to a ATM Aircon |  |  | Region 1 | Gauteng South | 70638X | 1000-70235-01 | Johannesburg Park Station-Rissik St-Johannesburg | N | 2023-04-28 | 2023-05-26 |  | ASP-GS0645 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2021-02-27 | GAMIETR | 2023-04-28 | D | 3739.66 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-03 | 2023-05-03 | 4015.66 | Approved | {"MANDT":"111","REFERENCE":90000272,"ONEVIEW":"70638X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-03-17","DATE04":"2023-03-24","DATE05":"2023-04-14","DATE06":"2023-04-28","DATE07":"2023-05-26","DATE08":"2023-06-16","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083144 | PHASE11 | 2023-04-28 | 2023-06-19 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-04 | 4119.16 | 0 |  |  | C000083144 | 3491.88 |  | 334.74 |  | 0 | 0 |  | 0 |  | 0
90000273 | The Grove Drip Tray | The Grove Drip Tray |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-04-28 | 2023-05-12 |  | ASP-GS0646 | REL BUDG AVAC SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-04-28 | D | 0 | 2023.05.03: Approved by Kobus JvR as per email 2023.05.02: Supported by Rob L | 100 | 2023-05-03 | 2023-05-03 | 5755.2 | Approved | {"MANDT":"111","REFERENCE":90000273,"ONEVIEW":"35041X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-03-17","DATE04":"2023-03-24","DATE05":"2023-04-14","DATE06":"2023-04-28","DATE07":"2023-05-12","DATE08":"2023-06-02","DATE09":"2023-07-17","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083145 | PHASE08 | 2023-04-28 | 2023-05-12 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-04 | 5755.21 | 0 |  |  | C000083145 | 5004.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000274 | Olievenhout Plaza Minor Works | Ã¢ÂÂ¢ Removing outdated Q-rails and ceramic tiles (135m2). Ã¢ÂÂ¢ Repairing walls (1m2). Ã¢ÂÂ¢ Installing new floor tiles and expansion joints (135m2). Ã¢ÂÂ¢ Adding walk-off matt, wall protectors, and bumper rails. Ã¢ÂÂ¢ Repainting walls with Absa specification paint (373m2). Ã¢ÂÂ¢ Installing two new benches. Ã¢ÂÂ¢ Work will be conducted after normal working hour for 9 days. Ã¢ÂÂ¢ Security Guard for the duration of the project. Ã¢ÂÂ¢ Material lead-time: +-1 week. |  |  | Region 1 | Gauteng North | 36239X | 1000-70195-01 | Olievenhout Plaza-Cnr R55 & Jakalasi St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0194 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-05-01 | D | 287497.79 | 2023.05.04: Approved by Conrad M 2023.05.02: Supported by Ilana vdW & Winston P as per email | 100 | 2023-05-22 | 2023-05-04 | 287497.79 | Approved | {"MANDT":"111","REFERENCE":90000274,"ONEVIEW":"36239X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083795 | PHASE11 | 2023-06-14 | 2023-06-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-05-09 | 380200.78 | 0 |  |  | C000083795 | 249988.18 |  | 26000.58 |  | 0 | 0 |  | 0 |  | 0
90000275 | Towers West Replacement of signage (Retr | Towers West Replacement of signage (Retr |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-04-28 | 2023-05-01 |  | ASP-GS0647 | CRTD SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-05-01 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000275,"ONEVIEW":"21526X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-03-17","DATE04":"2023-03-24","DATE05":"2023-03-28","DATE06":"2023-04-28","DATE07":"2023-05-01","DATE08":"2023-05-22","DATE09":"2023-07-06","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE08 | 2023-04-28 | 2023-05-01 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000276 | Alice Lane North & South Loan privacy ch | Alice Lane North & South Loan privacy ch |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2023-04-28 | 2023-05-01 |  | ASP-GS0648 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-05-01 | D | 0 | 2023.05.10: Approved by Conrad M as per email | 100 | 2023-05-11 | 2023-05-11 | 53613 | Approved | {"MANDT":"111","REFERENCE":90000276,"ONEVIEW":"70656X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-03-17","DATE04":"2023-03-24","DATE05":"2023-04-14","DATE06":"2023-04-28","DATE07":"2023-05-01","DATE08":"2023-05-22","DATE09":"2023-07-06","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-28","FORECAST_END":"2023-05-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"VXBkYXRlIHRoZSBmdW5kaW5nIHRhYiwgUE8gZGF0ZSwgdmFsdWUgYW5kIGRhdGUgbWlzc2luZy4=","RATING":"Medium"} |  |  |  | PHASE08 | 2023-04-28 | 2023-05-01 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 46620 | 0 |  |  | C000084803 | 46620 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000277 | Mall@Carnival Minor Works | Mall@Carnival Minor Works |  |  | Region 1 |  | Unknown | 1000-70043-01 | Unknown Building - not in our database |  | 2023-04-05 |  |  | ASP-GS0649 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-05-01 | D | 0 | 2023.05.04: Approved by Conrad M 2023.05.02: Supported by Ilana vdW & Winston P as per email | 100 | 2023-05-04 | 2023-05-04 | 71700.44 | Approved |  |  |  | C000083879 | PHASE10 | 2023-04-05 | 2023-05-05 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-09 | 82455.49 | 0 |  |  | C000083879 | 62348.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000278 | 270 Republic Road Minor Works | 270 Republic Road Minor Works |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg | N | 2023-04-28 | 2023-05-01 |  | ASP-GS0650 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-05-01 | D | 0 | 2023.06.29: Approved by Conrad M 2023.06.28: Supported by Winston P | 100 | 2023-06-29 | 2023-06-29 | 209742.62 | Approved | {"MANDT":"111","REFERENCE":90000278,"ONEVIEW":"21335X","DATE01":"2023-02-17","DATE02":"2023-02-24","DATE03":"2023-04-24","DATE04":"2023-05-01","DATE05":"2023-05-22","DATE06":"2023-06-05","DATE07":"2023-06-08","DATE08":"2023-07-31","DATE09":"2023-09-14","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"164:7:59:7:21:14:3:53:45:25","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-05","FORECAST_END":"2023-06-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBjbG9zZSBvdXQgZG9jdW1lbnRz","RATING":"Medium"} |  |  | C000095217 | PHASE09 | 2023-06-05 | 2023-06-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 209742.62 | 0 |  |  | C000095217 | 182384.89 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000279 | Absa Warden - Install Water tank & Filtr | Absa Warden - Install Water tank & Filtr |  |  | Region 3 |  | 79096X | 1000-71571-01 | Absa Warden-Piet Retief St-Warden |  | 2023-06-15 |  |  | ASP-CR0427 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-02 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000279,"ONEVIEW":"","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-01","DATE06":"2023-06-15","DATE07":"2023-07-15","DATE08":"2023-08-05","DATE09":"2023-09-19","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-15","FORECAST_END":"2023-07-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-06-15 | 2023-07-15 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000280 | Absa Villiers - Install water Tank & Fil | Absa Villiers - Install water Tank & Fil |  |  | Region 3 |  | 78810X | 1000-71554-01 | Absa Villiers-Hoof St-Villiers |  | 2023-06-15 |  |  | ASP-CR0428 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-02 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000280,"ONEVIEW":"","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-01","DATE06":"2023-06-15","DATE07":"2023-07-15","DATE08":"2023-08-05","DATE09":"2023-09-19","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-15","FORECAST_END":"2023-07-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-06-15 | 2023-07-15 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000281 | Absa Boardwalk Port Elixabeth - Seating | Absa Boardwalk Port Elizabeth - Seating |  |  | Region 2 | Eastern Cape | 37203X | 1000-77537-01 | Boardwalk Mall | N | 2023-06-01 | 2023-07-31 |  | ASP-EC0313 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-05-02 | D | 0 |  | 1 |  |  | 0 | 29 May Cancelled as seating to be provided by PMO | {"MANDT":"111","REFERENCE":90000281,"ONEVIEW":"37203X","DATE01":"2023-03-23","DATE02":"2023-03-30","DATE03":"2023-04-20","DATE04":"2023-04-27","DATE05":"2023-05-18","DATE06":"2023-06-01","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-01","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDYW5jZWxsZWQgLSBTZWF0aW5nIGFkZHJlc3NlZCBieSBQTU8=","RATING":"Low"} |  |  |  | PHASE12 | 2023-06-01 | 2023-07-31 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000282 | Absa Paulpietersburg - Waterproofing | Absa Paulpietersburg - Waterproofing |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-06-28 |  |  | ASP-KZ0246 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-06-28 | 2023-07-28 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000283 | Absa Lephalale - Waterproofing | Absa Lephalale - Waterproofing |  |  | Region 3 | National | 76789X | 1000-70525-01 | Absa Lephalale-Cnr Strydom & Fox Odendaal St-Lephalale | Y | 2023-06-21 |  |  | ASP-LP0163 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-05-02 | D | 0 | 2023.05.04: Supported by Rob L | 100 | 2023-05-11 | 2023-05-11 | 144321.89 | Approved | {"MANDT":"111","REFERENCE":90000283,"ONEVIEW":"Unknown","DATE01":"2023-04-12","DATE02":"2023-04-19","DATE03":"2023-05-10","DATE04":"2023-05-17","DATE05":"2023-06-07","DATE06":"2023-06-21","DATE07":"2023-07-21","DATE08":"2023-08-11","DATE09":"2023-09-25","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-21","FORECAST_END":"2023-07-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000084469 | PHASE11 | 2023-06-21 | 2023-07-21 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-11 | 144321.9 | 0 |  |  | C000084469 | 125497.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000284 | Absa Carolina - Waterproofing | Absa Carolina - Waterproofing |  |  | Region 3 | Mpumalanga | 78145X | 1000-70684-01 | Absa Carolina-Voortrekker St-Carolina | U | 2023-06-22 |  |  | ASP-MP0158 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-05-02 | D | 0 | 2023.05.04: Supported by Rob L | 100 | 2023-05-11 | 2023-05-11 | 84719.1 | Approved | {"MANDT":"111","REFERENCE":90000284,"ONEVIEW":"78145X","DATE01":"2023-04-13","DATE02":"2023-04-20","DATE03":"2023-05-11","DATE04":"2023-05-18","DATE05":"2023-06-08","DATE06":"2023-06-22","DATE07":"2023-07-22","DATE08":"2023-08-12","DATE09":"2023-09-26","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-22","FORECAST_END":"2023-07-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000084468 | PHASE11 | 2023-06-22 | 2023-07-22 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-05-11 | 84719.1 | 0 |  |  | C000084468 | 73668.78 |  | 7238.1 |  | 0 | 0 |  | 0 |  | 0
90000285 | Absa Piet Retief- Building Facade & Back | Absa Piet Retief- Building Facade & Back |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-06-22 |  |  | ASP-MP0159 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-02 | D | 0 |  | 100 |  |  | 693940.14 |  | {"MANDT":"111","REFERENCE":90000285,"ONEVIEW":"","DATE01":"2023-04-13","DATE02":"2023-04-20","DATE03":"2023-05-11","DATE04":"2023-05-18","DATE05":"2023-06-08","DATE06":"2023-06-22","DATE07":"2023-07-22","DATE08":"2023-08-12","DATE09":"2023-09-26","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-22","FORECAST_END":"2023-07-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-06-22 | 2023-07-22 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000286 | Absa Carnarvon - Supply & Install Steel | Absa Carnarvon - Supply & Install Steel |  |  | Region 3 |  | Unknown | 1000-71360-01 | Unknown Building - not in our database |  | 2023-06-08 |  |  | ASP-CR0429 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-04 | D | 0 | 2023.05.17: Approved by Conrad M as per email | 100 | 2023-05-18 | 2023-05-18 | 83259.84 | Approved | {"MANDT":"111","REFERENCE":90000286,"ONEVIEW":"Unknown","DATE01":"2023-03-30","DATE02":"2023-04-06","DATE03":"2023-04-27","DATE04":"2023-05-04","DATE05":"2023-05-25","DATE06":"2023-06-08","DATE07":"2023-07-08","DATE08":"2023-07-29","DATE09":"2023-09-12","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":50,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"184:7:21:7:21:14:30:-4:45:18","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-08","FORECAST_END":"2023-07-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2luZw==","RATING":""} |  |  | C000086504 | PHASE11 | 2023-06-08 | 2023-07-08 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-22 | 72399.86 | 0 |  |  | C000086504 | 72399.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000287 | Towers West Procurement of x350 crates | Ã¢ÂÂ¢ Supply and delivery black crates (x350): - Exterior Top (600mm x 400mm x 315mm) - Interior Base (521mm x 339mm x 282mm) |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-05-08 | 2023-06-30 |  | ASP-GS0652 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tshegofatso Segooa |  |  | 2023 |  | F |  | MOKOENAM2 | 2023-05-04 | D | 150116.4 | 2023.04.25: Approved by Conrad M as per email 2023.04.25: Supported by Winston P | 100 | 2023-04-24 | 2023-04-26 | 150116.4 | Approved | {"MANDT":"111","REFERENCE":90000287,"ONEVIEW":"21526X","DATE01":"2023-02-27","DATE02":"2023-03-06","DATE03":"2023-03-27","DATE04":"2023-04-03","DATE05":"2023-04-24","DATE06":"2023-05-08","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-08","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083216 | PHASE11 | 2023-05-08 | 2023-06-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-05 | 130536 | 0 |  |  | C000083216 | 130536 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000288 | Auckland Park CC cat ladder and walkway | Auckland Park CC cat ladder and walkway |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-05-04 | 2023-06-01 |  | ASP-GS0653 | CRTD SETC: |  | false | false |  | (Non PM) |  |  | 2023 |  |  |  | GAMIETR | 2023-05-04 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000288,"ONEVIEW":"76849X","DATE01":"2023-02-23","DATE02":"2023-03-02","DATE03":"2023-03-23","DATE04":"2023-03-30","DATE05":"2023-04-20","DATE06":"2023-05-04","DATE07":"2023-06-01","DATE08":"2023-06-22","DATE09":"2023-08-06","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-04","FORECAST_END":"2023-06-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxsZWQ=","RATING":""} |  |  |  | PHASE12 | 2023-05-04 | 2023-06-01 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000289 | Auckland Park CC Solar PV interface to B | Auckland Park CC Solar PV interface to B |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-05-04 | 2023-06-01 |  | ASP-GS0654 | CRTD SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | GAMIETR | 2023-05-04 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000289,"ONEVIEW":"76849X","DATE01":"2023-02-23","DATE02":"2023-03-02","DATE03":"2023-03-23","DATE04":"2023-03-30","DATE05":"2023-04-20","DATE06":"2023-05-04","DATE07":"2023-06-01","DATE08":"2023-06-22","DATE09":"2023-08-06","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-04","FORECAST_END":"2023-06-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-04 | 2023-06-01 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000290 | Northmead Square MW-Carpet replacement, | Northmead Square MW-Carpet replacement, |  |  | Region 1 |  | Unknown | 1000-70196-01 | Unknown Building - not in our database |  | 2023-04-05 |  |  | ASP-GS0655 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-05-05 | D | 0 | 2023.05.10: Approved by Conrad M as per email 2023.05.10: Supported by Winston P as per email 2023.05.09: Supported by Ilana vdW | 100 | 2023-05-11 | 2023-05-11 | 177794.26 | Approved | {"MANDT":"111","REFERENCE":90000290,"ONEVIEW":"Unknown","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgYnJhbmNoIGNvbmZpcm1hdGlvbiBvbiBkYXRlcy4=","RATING":""} |  |  |  | PHASE09 | 2023-07-14 | 2023-08-13 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000084846 | 154603.71 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000291 | Absa Koppies - Construction of Carpots | Absa Koppies - Construction of Carpots |  |  | Region 3 |  | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies | N | 2023-06-22 | 2023-06-29 |  | ASP-CR0430 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan | rollover |  | 2023 |  | F |  | NOMNGANGAL | 2023-05-05 | D | 105399.73 |  | 60 | 2023-05-16 | 2023-05-18 | 105399.73 | 05 Feb - JVC - Contingency not utilised Supplier POs requested on 2023/05/22 | {"MANDT":"111","REFERENCE":90000291,"ONEVIEW":"78856X","DATE01":"2023-04-13","DATE02":"2023-07-12","DATE03":"2023-07-13","DATE04":"2023-07-18","DATE05":"2023-07-20","DATE06":"2023-08-10","DATE07":"2023-10-25","DATE08":"2024-02-08","DATE09":"2024-02-18","DATE10":"2024-02-29","DATE11":"2024-02-18","DATE12":"2024-02-18","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":50,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"260:90:1:5:2:21:76:106:10:11","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-10","FORECAST_END":"2023-10-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE0gYnVzeSB3aXRoIGNvdW5jaWwgc3VibWlzc2lvbnMsIEZpbmFuY2lhbCBSb2xsb3Zlcgo=","RATING":""} |  |  | C000119243 | PHASE03 | 2023-08-10 | 2023-10-25 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 213604.65 | 0 |  |  | C000119243 | 213604.65 |  | 20152.84 |  | 0 | 0 |  | 0 |  | 0
90000292 | Absa Springbok - Installation of Electri | Absa Springbok - Installation of Electri |  |  | Region 3 |  | 78083X | 1000-71344-01 | Springbok-Van Der Hof St-Springbok |  | 2023-06-22 | 2023-06-29 |  | ASP-CR0431 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-05 | D | 0 | 2023.05.18: Approved by Kobus JvR as per email 2023.05.16: Supported by Rob L | 100 | 2023-05-18 | 2023-05-18 | 29577.66 | Approved | {"MANDT":"111","REFERENCE":90000292,"ONEVIEW":"78083X","DATE01":"2023-04-13","DATE02":"2023-04-20","DATE03":"2023-05-11","DATE04":"2023-05-18","DATE05":"2023-06-08","DATE06":"2023-06-22","DATE07":"2023-06-29","DATE08":"2023-07-20","DATE09":"2023-09-03","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-22","FORECAST_END":"2023-06-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000086629 | PHASE11 | 2023-06-22 | 2023-06-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-22 | 25719.7 | 0 |  |  | C000086629 | 25719.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000293 | Tsakane Mall Close off 3 x teller count | Tsakane Mall Close off 3 x teller count |  |  | Region 1 |  | 21857X | 1000-70041-01 | Tsakane Mall-Cnr Modjadji & Malandela St-Tsakane |  | 2023-05-05 | 2023-06-02 |  | ASP-GS0656 | CRTD SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-05-05 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000293,"ONEVIEW":"21857X","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-02","DATE08":"2023-06-23","DATE09":"2023-08-07","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxlZCBieSBSZWdpb24uIA==","RATING":"Low"} |  |  |  | PHASE12 | 2023-05-05 | 2023-06-02 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000294 | Auckland Park CC DD Cat Ladder and Const | Auckland Park CC DD Cat Ladder and Const |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-05-05 | 2023-06-02 |  | ASP-GS0657 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-05-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000294,"ONEVIEW":"76849X","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-02","DATE08":"2023-06-23","DATE09":"2023-08-07","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE08 | 2023-05-05 | 2023-06-02 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000295 | Auckland Park CC solar PV to the BMS sys | Auckland Park CC solar PV to the BMS sys |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-05-05 | 2023-06-02 |  | ASP-GS0658 | CRTD SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | GAMIETR | 2023-05-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000295,"ONEVIEW":"76849X","DATE01":"2023-02-24","DATE02":"2023-03-03","DATE03":"2023-03-24","DATE04":"2023-03-31","DATE05":"2023-04-21","DATE06":"2023-05-05","DATE07":"2023-06-02","DATE08":"2023-06-23","DATE09":"2023-08-07","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-05","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-05 | 2023-06-02 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000296 | Absa Bloemfontein Forum - Installation o | Absa Bloemfontein Forum - Installation of additional plugs |  |  | Region 3 | Free State | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein | N | 2023-06-15 |  |  | ASP-CR0432 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-05-08 | D | 2809 | 2023.05.18: Approved by Kobus JvR as per email 2023.05.16: Supported by Rob L | 100 | 2022-08-11 | 2023-05-18 | 5663.29 | Approved | {"MANDT":"111","REFERENCE":90000296,"ONEVIEW":"22161X","DATE01":"2023-04-06","DATE02":"2023-05-08","DATE03":"2023-05-08","DATE04":"2023-05-09","DATE05":"2023-05-16","DATE06":"2023-05-23","DATE07":"2023-05-30","DATE08":"2023-06-05","DATE09":"2023-09-19","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-23","FORECAST_END":"2023-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGludm9pY2luZyBpbiBwcm9ncmVzcw==","RATING":""} |  |  | C000086623 | PHASE11 | 2023-05-23 | 2023-05-30 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-05-22 | 4924.6 | 0 |  |  | C000086623 | 4924.6 | CIP2023XP | 280.94 |  | 0 | 0 |  | 0 |  | 0
90000297 | Alice Lane North & South 2 X Loan PODS | Alice Lane North & South 2 X Loan PODS |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2023-05-08 | 2023-08-31 |  | ASP-GS0659 | CRTD SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-05-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE07 | 2023-05-08 | 2023-08-31 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000298 | Towers West Replacement of signage (Retr | Towers West Replacement of signage (Retr |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-05-08 | 2023-06-02 |  | ASP-GS0660 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-08 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 1575.5 |  |  |  |  | C000083769 | PHASE08 | 2023-05-08 | 2023-06-02 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-05-09 | 1575.5 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000299 | Retail Documentation Compliance Programm | Retail Documentation Compliance Programm.to execute fire remedial work and other services at 43 Absa Retail Leasehold Sites (Eastern Cape and Northern Cape) as part of Phase 3 part 1b, Bidvest FM will also provide project management services. Scope of Works: Ã¢ÂÂ¢ Removal of existing smoke detectors in wrong positions or too close to diffusers Ã¢ÂÂ¢ Removal of signage that is not mechanically fastened Ã¢ÂÂ¢ Supply and installation of fire safety and escape signage Ã¢ÂÂ¢ Supply and installation of fire hydrants, extinguishers and sprinklers Ã¢ÂÂ¢ Supply and installation of smoke detectors, sounder beacons, Manual Call Points (MCP) Ã¢ÂÂ¢ Override magnets; and various alterations, install fire rated doors, check fire detection system pressure, ironmongery, plumbing & drainage (if required). |  |  | National | National | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | U | 2023-05-31 | 2023-12-15 |  | ALP-N00046 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sibulele Gwangqa |  |  | 2023 |  | U |  | LOUISR | 2023-05-08 | D | 6875698.7 | Approved at BTB 11 May | 100 | 2023-05-11 | 2023-05-11 | 6875698.7 | Approved | {"MANDT":"111","REFERENCE":90000299,"ONEVIEW":"21526X","DATE01":"2023-03-22","DATE02":"2023-03-29","DATE03":"2023-04-19","DATE04":"2023-04-26","DATE05":"2023-05-17","DATE06":"2023-05-31","DATE07":"2023-12-15","DATE08":"2024-01-31","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"344:7:21:7:21:14:198:47:29:0","PROGRESS":63,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-31","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3MuCkFTLSAwMi8wOC8yMDIzIC0gVXBkYXRlZCB0aGUgY2FzaCBmbG93IGRhdGUgCkxMLSAwNC8wOS8yMDIzLSBQcm9qZWN0IHN0aWxsIGluIHByb2dyZXNzIHBhcnRpYWwgaW52b2ljZXMgYXJlIGJlaW5nIHN1Ym1pdHRlZC4KMjcvMDkvMjAyMywgTEEgLSBVcGRhdGVkIGNhc2ggZmxvdyBkYXRlLiBGaW5hbmNpYWwgcm9sbCBvdmVyLiA=","RATING":"Medium"} |  |  | C000091627 | PHASE10 | 2023-05-31 | 2023-12-15 | LUCIA AMUNGA | Michael Maluleka | 23000005 | 2023-06-01 | 2023-06-02 |  |  | 2023-06-13 | 5978868.43 | 0 |  |  | C000091627 | 5978868.43 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000300 | Eastgate Offices Towers Dilaps | Eastgate Offices Towers Dilaps/ Reinstatement |  |  | Region 1 | Gauteng South | 76420X | 1000-70247-01 | Eastgate Shopping Centre-Bradford Rd-Bedfordview | N | 2023-05-08 | 2023-06-02 |  | ASP-GS0661 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2023-05-30 | GAMIETR | 2023-05-09 | D | 260793.33 | Approved by Lebusa M | 100 | 2023-05-10 | 2023-05-24 | 260793.34 | Approved | {"MANDT":"111","REFERENCE":90000300,"ONEVIEW":"Unknown","DATE01":"2023-02-27","DATE02":"2023-03-06","DATE03":"2023-03-27","DATE04":"2023-04-03","DATE05":"2023-04-24","DATE06":"2023-05-08","DATE07":"2023-06-02","DATE08":"2023-06-23","DATE09":"2023-08-07","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-08","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000086748 | PHASE11 | 2023-05-08 | 2023-06-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-23 | 260793.33 | 0 |  |  | C000086748 | 274114.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000301 | Absa Grabouw - UPS & Surge Protector | Absa Grabouw - UPS & Surge Protector |  |  | Region 2 |  | 36241X | 1000-70760-01 | 30 on Main Grabouw-Cnr Oudeberg Rd & Voortrekker St-Grabouw | Y | 2023-06-12 | 2023-06-30 |  | ASP-WC0280 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-05-09 | D | 101970.46 |  | 100 | 2023-05-09 | 2023-05-12 | 101970.46 |  | {"MANDT":"111","REFERENCE":90000301,"ONEVIEW":"36241X","DATE01":"2023-04-25","DATE02":"2023-04-25","DATE03":"2023-04-18","DATE04":"2023-04-04","DATE05":"2023-03-17","DATE06":"2023-03-31","DATE07":"2023-03-23","DATE08":"2023-04-13","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-31","FORECAST_END":"2023-03-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000083244 | PHASE11 | 2023-07-05 | 2023-09-30 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-05-05 | 88669.97 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000302 | 2023 Retail Solar PV program (Bonnievale, De Doorns, Wesselsbron, and Oude Bloemhof) | Retail Solar - (Bonnievale, De Doorns, Wesselsbron, and Oude Bloemhof) |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | N | 2023-05-31 | 2023-12-15 |  | ALP-N00047 | REL BUDG AVAC RESA SETC: |  | false | true |  | Wesigye Mukuru |  |  | 2023 |  | U |  | LOUISR | 2023-05-09 | D | 11384897.11 | Projects approved in order for Absa to increase its renewable energy production in relation to its overall energy consumption and utilize the renewable energy sustainability linked loan requirements while reducing municipality reliance for the branches | 100 | 2023-04-24 | 2023-04-24 | 11384897.11 | Projects approved in order for Absa to increase its renewable energy production in relation to its overall energy consumption and utilize the renewable energy sustainability linked loan requirements while reducing municipality reliance for the branches | {"MANDT":"111","REFERENCE":90000302,"ONEVIEW":"Various Sites","DATE01":"2023-03-22","DATE02":"2023-03-29","DATE03":"2023-04-19","DATE04":"2023-04-21","DATE05":"2023-04-21","DATE06":"2023-08-20","DATE07":"2023-09-06","DATE08":"2023-11-04","DATE09":"2023-11-12","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"344:7:21:2:0:121:17:59:8:10","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-20","FORECAST_END":"2023-09-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtMTcvMDcvMjAyMy0gTXVrdXJ1IGluIHByb2Nlc3Mgd2l0aCBXQS4KTVc6IDIxLzA3MjAyMyAtIFdBIGFuZCBKQkNDIGRvY3VtZW50cyB3aXRoIEFic2EgbGVnYWwgc2luY2UgMTl0aCBKdWx5Ck1XIDIxLzA4LzIwMjMgLSBXQSBhbmQgSkJDQyBkb2N1bWVudHMgY29tcGxldGVkIGFuZCBzaWduZWQuIFBPIHJlcXVlc3QgdG8gQWJzYSBzZW50IHRvZGF5LiBEZXNpZ25zIGJlaW5nIGNvbXBsZXRlZCBieSBNYXRpbWJhIGJlZm9yZSBvdmVybGF5IG1lZXRpbmcgc2NoZHVsaW5n","RATING":"Medium"} |  |  |  | PHASE06 | 2023-08-20 | 2023-09-06 | LUCIA AMUNGA | Thea Spamers | 0 | 2023-07-19 |  | 2023-07-17 | 2023-07-18 |  | 9899910.53 | 0 |  |  | C000140419 | 9899910.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000303 | Absa Virginia - Installation of Temporar | Absa Virginia - Installation of Temporar |  |  | Region 3 |  | Unknown | 1000-71582-01 | Unknown Building - not in our database |  | 2023-06-28 |  |  | ASP-CR0433 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-10 | D | 0 | 2023.06.21: Approved by Conrad M as per email 2023.06.20: Supported by Leko N & Ilana VdW | 100 | 2023-06-22 | 2023-06-22 | 6026 | Approved | {"MANDT":"111","REFERENCE":90000303,"ONEVIEW":"Unknown","DATE01":"2023-04-19","DATE02":"2023-05-03","DATE03":"2023-05-03","DATE04":"2023-05-10","DATE05":"2023-05-18","DATE06":"2023-05-25","DATE07":"2023-05-12","DATE08":"2023-06-29","DATE09":"2023-10-02","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-25","FORECAST_END":"2023-05-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGZ1bGx5IGludm9pY2Vk","RATING":""} |  |  | C000093839 | PHASE11 | 2023-05-25 | 2023-05-12 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-25 | 5240 | 0 |  |  | C000086438 | 132291.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000304 | Absa Corner Church Street - Plug Install | Absa Corner Church Street - Plug Install |  |  | Region 3 | [5 empty] | 2023-06-29 |  |  | ASP-CR0434 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-10 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-06-29 | 2023-07-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000305 | Absa Oudtshoorn - UPS Connection | Absa Oudtshoorn - UPS Connection |  |  | Region 2 | Eastern Cape | 37146X | 1000-77433-01 | 48B High Street Oudtshoorn |  | 2023-06-12 | 2023-06-30 |  | ASP-EC0314 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-05-10 | D | 0 |  | 1 |  |  | 0 | Approved against Headwind ENG Bulk Project - ALP-N00043 | {"MANDT":"111","REFERENCE":90000305,"ONEVIEW":"37146X","DATE01":"2023-04-03","DATE02":"2023-04-10","DATE03":"2023-05-01","DATE04":"2023-05-08","DATE05":"2023-05-29","DATE06":"2023-06-12","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-12","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-12 | 2023-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000306 | Absa Othongathi - Dilaps | Absa Othongathi - Dilaps |  |  | Region 3 |  | 37067X | 1000-71140-01 | Othongathi Mall-Cnr Ganie St & Gopalall Hurbn-Tongaat |  | 2023-06-29 | 2023-06-29 |  | ASP-KZ0247 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-10 | D | 0 | Approved by Lebusa M |  | 2023-05-18 | 2023-05-18 | 82110.78 | Approved |  |  |  | C000086624 | PHASE10 | 2023-06-29 | 2023-06-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-05-22 | 71400.67 | 0 |  |  | C000086624 | 71400.67 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000307 | Absa Towers North Waterproofinf Phase 2 | Absa Towers North Waterproofinf Phase 2 |  |  | Region 1 |  | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2023-05-08 | 2023-07-31 |  | ALP-GS0058 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-05-10 | D | 0 |  | 15 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000307,"ONEVIEW":"77381X","DATE01":"2023-02-27","DATE02":"2023-03-06","DATE03":"2023-03-27","DATE04":"2023-04-03","DATE05":"2023-04-24","DATE06":"2023-05-08","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-08","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBvbiBIb2xkLgpDUkVTIEVuZyB0byBhZHZpc2UgaWYgdGhlIHByb2plY3Qgc2hvdWxkIHByb2NlZWQgIGJhc2VkIG9uIHJpc2sgcmVwb3J0Lg==","RATING":""} |  |  |  | PHASE00 | 2023-05-08 | 2023-07-31 | VANIE CATTIGAN | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | 2763199 | 1648014.33 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000308 | Auckland Park CC Waterproofing Phase 2 | Auckland Park CC Waterproofing Phase 2 "Waterproofing -Waterproofing will be redone in order to enhance the corporate image and to address the water ingress issues; -Remove existing floor slate tile, and screed floor for Torch-on waterproofing -Supply and install 1288 sqm of 200 x 200mm new African blue slate -Strip and grout 1288 sqm of 200x200mm -Supply and waterproof 1100 sqm of upper balconies with Torch-on waterproofing -Seal all full-bores around stormwater drainage pipes -Issue certificate of workmanship -Issue workmanship guarante as per SANS Code" |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-05-08 | 2023-06-02 |  | ALP-GS0059 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-05-10 | D | 0 | Approved at CB/BTB | 100 | 2023-06-29 | 2023-06-29 | 1304342.08 | Approved | {"MANDT":"111","REFERENCE":90000308,"ONEVIEW":"76849X","DATE01":"2023-02-27","DATE02":"2023-03-06","DATE03":"2023-03-27","DATE04":"2023-04-03","DATE05":"2023-04-24","DATE06":"2023-05-08","DATE07":"2023-06-02","DATE08":"2023-06-23","DATE09":"2023-08-07","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-08","FORECAST_END":"2023-06-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQT+KAmXMgdG8gYmUgaXNzdWVkIGluIHRoZSBpbnRlcmltClByb2plY3Qgc3RhcnQgZGF0ZSAtIDUvMTAvMjAyMwpDb21wbGV0aW9uIGRhdGUgLSAzMC8xMC8yMDIzClRvIGJlIGludm9pY2VkIHRoaXMgeWVhci4=","RATING":"Low"} |  |  | C000108900 | PHASE09 | 2023-05-08 | 2023-06-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  | 2023-08-13 | 2023-09-29 | 2023-09-07 | 1304342.08 | 0 |  |  | C000108900 | 1134210.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000309 | Pretoria Campus Waterproofing Phase 2 | Waterproofing (Total Roof Area 11800 sqm) -Waterproofing will be redone in order to enhance the corporate image and to address the water ingress issues; -High pressure clean overall roof; -Repair rusted holes to end of click lock roof sheets; -Apply one full coat Duraflex Rust stop to clip lock sheets and two coats Duraflex liquid rubber grey to clip lock roof sheets; -Apply one full coat Duraflex Bond-it to flat roof; -Apply one full coat Duraflex Rubber seal to the roofs and two coats Duraflex liquid rubber to flat roof; Security Guarding Services to be provided for duration of project. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-05-10 | 2023-08-31 |  | ALP-GS0060 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-05-10 | D | 7508.01 |  | 60 | 2023-07-03 | 2023-07-27 | 7508.01 |  | {"MANDT":"111","REFERENCE":90000309,"ONEVIEW":"22491X","DATE01":"2023-03-01","DATE02":"2023-03-08","DATE03":"2023-03-29","DATE04":"2023-04-05","DATE05":"2023-04-26","DATE06":"2023-05-10","DATE07":"2023-10-02","DATE08":"2023-10-23","DATE09":"2023-12-07","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":54,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-10","FORECAST_END":"2023-10-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQT8ODwqLDgsKAw4LCmXMgdG8gYmUgaXNzdWVkIGluIHRoZSBpbnRlcmltClBsYW5uZWQgc3RhcnQgZGF0ZSAxMC8xMC8yMDIzClBsYW5uZWQgY29tcGxldGlvbiAtMzEvMDMvMjAyMwpQbGFubmVkIGNhc2hmbG93MjAyMy03MCUKUm9sbC1vdmVyIDMwJQ==","RATING":""} |  |  | Await WA approval for Absa PO | PHASE07 | 2023-05-10 | 2023-10-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-08-08 |  |  |  |  | 0 | 0 |  |  | NO FUNDING | 6488591.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000310 | Absa Pioneer Centre (Landros Mare) -Mino | Absa Pioneer Centre (Landros Mare) -Mino |  |  | Region 3 |  | 76790X | 1000-70669-01 | Pioneer Centre-Schoeman St-Polokwane |  | 2023-06-29 |  |  | ALP-LP0201 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-10 | D | 0 | 2023.07.13: Approved by Conrad M |  | 2023-07-13 | 2023-07-13 | 887569.73 | Approved |  |  |  |  | PHASE05 | 2023-07-28 | 2023-07-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 | 2023-08-31 |  | 2023-08-31 |  |  | 0 | 0 |  |  | C000140803 | 771799.77 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000311 | Absa Villiers -Construction of Stormwate | Absa Villiers -Construction of Stormwate |  |  | Region 3 |  | Unknown | 1000-71554-01 | Unknown Building - not in our database |  | 2023-06-29 |  |  | ASP-CR0435 | CRTD AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-11 | D | 0 |  | 60 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000311,"ONEVIEW":"Unknown","DATE01":"2023-04-20","DATE02":"2023-05-23","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-07-29","DATE08":"2023-08-19","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE03 | 2023-06-29 | 2023-07-29 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000312 | Absa Newcastle Mall - Install External S | Absa Newcastle Mall - Install External S |  |  | Region 3 |  | Unknown | 1000-71095-01 | Unknown Building - not in our database |  | 2023-06-28 |  |  | ASP-KZ0248 | REL BUDG AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-11 | D | 0 | 2023.05.17: Approved by Conrad M as per email |  | 2023-05-18 | 2023-05-18 | 108645.68 | Approved |  |  |  | C000086505 | PHASE07 | 2023-06-28 | 2023-08-04 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-05-22 | 94474.5 | 0 |  |  | C000140528 | 94474.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000313 | Alice Lane South Electrical power boxes | Alice Lane South Electrical power boxes |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-05-12 | 2023-06-12 |  | ASP-GS0662 | CRTD SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-05-12 | D | 0 | 2023.05.18: Approved by Kobus JvR as per email 2023.05.16: Supported by Rob L | 100 | 2023-05-18 | 2023-05-18 | 127936.24 | Approved | {"MANDT":"111","REFERENCE":90000313,"ONEVIEW":"35041X","DATE01":"2023-03-03","DATE02":"2023-04-21","DATE03":"2023-04-30","DATE04":"2023-04-19","DATE05":"2023-04-28","DATE06":"2023-05-12","DATE07":"2023-05-29","DATE08":"2023-07-03","DATE09":"2023-08-17","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-12","FORECAST_END":"2023-05-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBzdWJtaXNzaW9uIG9mIGludm9pY2UgZnJvbSBzdXBwbGllciB0byBjbG9zZSBvdXQu","RATING":""} |  |  | C000083244 | PHASE09 | 2023-05-12 | 2023-05-29 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 111248.9 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000314 | Towers North Install 3 x 48000 BTU Units | Towers North Install 3 x 48000 BTU Units |  |  | Region 1 |  | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2023-05-12 | 2023-06-12 |  | ASP-GS0663 | CRTD SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-05-12 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000314,"ONEVIEW":"77381X","DATE01":"2023-03-03","DATE02":"2023-03-10","DATE03":"2023-03-31","DATE04":"2023-04-07","DATE05":"2023-04-28","DATE06":"2023-05-12","DATE07":"2023-06-12","DATE08":"2023-07-03","DATE09":"2023-08-17","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-12","FORECAST_END":"2023-06-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UFJPSkVDVCBDQU1DRUxFRCBCWSBFU00u","RATING":"Medium"} |  |  |  | PHASE12 | 2023-05-12 | 2023-06-12 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  | C000084172 | 226776.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000315 | Alice Lane South shredding machine for E | Alice Lane South shredding machine for E |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-05-12 | 2023-06-12 |  | ASP-GS0664 | REL BUDG AVAC SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-05-15 | D | 0 | 2023.05.17: Approved by Conrad M as per email 2023.05.16: Supported by Rhulani N | 100 | 2023-05-18 | 2023-05-18 | 35475.2 | Approved |  |  |  | C000086493 | PHASE08 | 2023-05-05 | 2023-06-12 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-05-22 | 35475.2 | 0 |  |  | C000086493 | 30848 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000316 | Auckland Park CC 2 x walk off mats | Auckland Park CC 2 x walk off mats |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-05-15 | 2023-06-16 |  | ASP-GS0665 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-05-15 | D | 0 | 2023.05.17: Approved by Conrad M as per email 2023.05.16: Supported by Winston P | 100 | 2023-05-18 | 2023-05-18 | 52640.34 | Approved |  |  |  | C000086503 | PHASE08 | 2023-07-12 | 2023-07-03 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-22 | 52640.34 | 0 |  |  | C000086503 | 45774.21 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000317 | Alice Lane North Fire doors replacement | â¢Remove 2x existing damaged fire doors and dispose; â¢Supply and install 2 x 1 Hour Fire Rated Door (Class A) to suit an opening of 1800x2680mm - Includes galvanised slam bar; â¢Re-use existing Fire door ironmongery; â¢Doors to be painted to match existing; â¢Supply and install 2 x clear awnings - above fire doors; â¢Work to be carried out during weekends and or afterhours |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane North | N | 2023-05-15 | 2023-06-16 |  | ASP-GS0666 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | F |  | GAMIETR | 2023-05-15 | D | 54700.93 | 2023.05.17: Approved by Conrad M as per email 2023.05.16: Supported by Rhulani N | 100 | 2023-05-15 | 2023-05-18 | 54700.93 | Approved | {"MANDT":"111","REFERENCE":90000317,"ONEVIEW":"76420X","DATE01":"2023-03-06","DATE02":"2023-03-13","DATE03":"2023-04-03","DATE04":"2023-04-10","DATE05":"2023-05-01","DATE06":"2023-05-15","DATE07":"2023-06-16","DATE08":"2023-07-07","DATE09":"2023-08-21","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-06-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000086750 | PHASE11 | 2023-06-20 | 2023-06-24 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-23 | 54700.92 | 0 |  |  | C000086750 | 47566.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000318 | Clearwater Re-upholster couches x 11 (Cl | Clearwater Re-upholster couches x 11 (Cl |  |  | Region 1 | Gauteng South | 77174X | 1000-70352-01 | Clearwater Office Park Building 4-Millenium Rd-Strubensvalley | N | 2023-04-05 |  |  | ASP-GS0667 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-05-15 | D | 0 | 2023.05.17: Approved by Conrad M as per email | 100 | 2023-05-18 | 2023-05-18 | 346347.61 | Approved | {"MANDT":"111","REFERENCE":90000318,"ONEVIEW":"36244X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-04-17","DATE04":"2023-04-24","DATE05":"2023-05-15","DATE06":"2023-08-31","DATE07":"2023-09-30","DATE08":"2023-10-21","DATE09":"2023-12-05","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:75:7:21:108:30:21:45:21","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIE1XIHByb2plY3QgaXMgY29tcGxldGUgYW5kIFBPQyB3YXMgc2VudCB0byBmaW5hbmNlLg==","RATING":""} |  |  | C000086506 | PHASE10 | 2023-08-31 | 2023-09-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-05-22 | 346347.62 | 0 |  |  | C000086506 | 301171.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000319 | Towers West Install 4 x cold room curta | Towers West Install 4 x cold room curta |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-05-15 | 2023-06-16 |  | ASP-GS0668 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-05-15 | D | 18874.94 | 2023.05.17: Approved by Conrad M as per email | 100 | 2023-05-18 | 2023-05-18 | 18874.94 | Approved | {"MANDT":"111","REFERENCE":90000319,"ONEVIEW":"21526X","DATE01":"2023-03-06","DATE02":"2023-03-13","DATE03":"2023-04-03","DATE04":"2023-04-10","DATE05":"2023-07-31","DATE06":"2023-08-14","DATE07":"2023-09-15","DATE08":"2023-10-06","DATE09":"2023-11-20","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"178:7:21:7:112:14:32:21:45:10","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-14","FORECAST_END":"2023-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8xMTogUHJvamVjdCBjb21wbGV0ZS4gQXdhaXRpbmcgZmluYWwgUE9DIHNpZ25hdHVyZSAoQWJzYSBWUCku","RATING":""} |  |  | C000097739 | PHASE11 | 2023-08-14 | 2023-09-15 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-13 | 16412.99 | 0 |  |  | C000097739 | 16412.99 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000320 | Springs Mall Close off 1 x teller counte | Springs Mall Close off 1 x teller counte |  |  | Region 1 |  | 36227X | 1000-70192-01 | Springs Mall-Cnr N17 & R51-Springs |  | 2023-05-15 | 2023-06-16 |  | ASP-GS0669 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-05-15 | D | 0 | 2023.05.25: Approved by Conrad M 2023.05.23: Supported by Winston P & Ilana vdW | 15 | 2023-05-25 | 2023-05-25 | 8481.71 | Approved | {"MANDT":"111","REFERENCE":90000320,"ONEVIEW":"36227X","DATE01":"2023-03-06","DATE02":"2023-03-13","DATE03":"2023-04-03","DATE04":"2023-04-10","DATE05":"2023-05-01","DATE06":"2023-05-15","DATE07":"2023-06-16","DATE08":"2023-07-07","DATE09":"2023-08-21","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-15","FORECAST_END":"2023-06-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UFJPSkVDVCBQTEFDRUQgT04gSE9MRC4gCjEwLzAyLSBDYW5jZWxsZWQgYXMgcGVyIFJlZ2lvbiAtIEVhcm1hcmtlZCBmb3IgUHJpbWFyeSBQcm9qZWN0IHRvIGJlIGRvbmUgdmlhIFBNTw==","RATING":""} |  |  |  | PHASE12 | 2023-05-15 | 2023-06-16 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000088246 | 7375.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000321 | Absa Cornubia Shopping Mall- Painting | Absa Cornubia Shopping Mall- Painting |  |  | Region 3 |  | Unknown | 1000-71135-01 | Unknown Building - not in our database |  | 2023-06-29 |  |  | ASP-KZ0249 | CLSD BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-15 | D | 0 | 2023.05.25: Approved by Conrad M 2023.05.23: Supported by Leko N & Ilana vdW |  | 2023-05-25 | 2023-05-25 | 9998.93 | Approved |  |  |  | C000124723 | PHASE11 | 2023-05-30 | 2023-06-23 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-11-20 | 8694.72 | 0 |  |  | C000087974 | 8694.72 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000322 | Absa Ingwe Mall - LED lights Replacement | Absa Ingwe Mall - LED lights Replacement |  |  | Region 3 |  | 37008X | 1000-70592-01 | Ingwe Mall-Impala St-Malelane |  | 2023-06-22 | 2023-06-29 |  | ASP-MP0160 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-15 | D | 296912.78 | 2023.06.15: Approved by Kobus JvR as per email 2023.06.13: Supported by Rob L | 100 | 2023-06-14 | 2023-06-15 | 296912.79 | Approved |  |  |  | C000092899 | PHASE11 | 2023-06-22 | 2023-06-29 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-06-20 | 296912.78 | 0 |  |  | C000092899 | 258185.03 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000323 | Absa Bultfontein - Extention of Rental G | Absa Bultfontein - Extention of Rental G |  |  | Region 3 |  | 79115X | 1000-71574-01 | Absa Bultfontein |  | 2023-06-02 |  |  | ASP-CR0436 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-16 | D | 0 | 2023.05.25: Approved by Kobus JvR 2023.05.23: Supported by Rob L | 100 | 2023-05-25 | 2023-05-25 | 65205 | Approved | {"MANDT":"111","REFERENCE":90000323,"ONEVIEW":"79115X","DATE01":"2023-03-24","DATE02":"2023-06-15","DATE03":"2023-06-17","DATE04":"2023-06-16","DATE05":"2023-05-17","DATE06":"2023-05-17","DATE07":"2023-05-17","DATE08":"2023-07-02","DATE09":"2023-09-06","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":92,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-17","FORECAST_END":"2023-05-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIHN1Ym1pdHRlZCB0byBGaW5hbmNlIGluIEp1bmU=","RATING":""} |  |  |  | PHASE11 | 2023-05-17 | 2023-05-17 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000088076 | 56700 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000324 | Absa Petrusburg - Installation of Surge | Absa Petrusburg - Installation of Surge |  |  | Region 3 |  | 79067X | 1000-71569-01 | Absa Petrusburg-Ossewa St-Petrusburg |  | 2023-05-31 |  |  | ASP-CR0437 | CRTD: |  | false | false |  |  |  | The project number will be deleted, this work was done from ALP-N00043 Absa various sites-Adhoc PO C000083244 | 2023 |  |  |  | NOMNGANGAL | 2023-05-16 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000324,"ONEVIEW":"","DATE01":"2023-03-22","DATE02":"2023-03-29","DATE03":"2023-04-19","DATE04":"2023-04-26","DATE05":"2023-05-17","DATE06":"2023-05-31","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-31","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-31 | 2023-06-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000325 | Absa Phuthaditjhaba - Installation of pl | Absa Phuthaditjhaba - Installation of pl |  |  | Region 3 |  | 70622X | 1000-71516-01 | Phuthaditjhaba Setsing Crescent-Cnr Setai & Motloung St-Phuthaditjhaba | N | 2023-05-25 |  |  | ASP-CR0438 | CRTD: |  | false | false |  |  |  |  | 2023 |  | L | 2023-06-29 | NOMNGANGAL | 2023-05-16 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000325,"ONEVIEW":"","DATE01":"2023-03-16","DATE02":"2023-03-23","DATE03":"2023-04-13","DATE04":"2023-04-20","DATE05":"2023-05-11","DATE06":"2023-05-25","DATE07":"2023-06-24","DATE08":"2023-07-15","DATE09":"2023-08-29","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-25","FORECAST_END":"2023-06-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-25 | 2023-06-24 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000326 | Pretoria Campus 2 X Generator hire | Delivery and collection of 2 X Mobile generator units plus fuel. Supply of cables for the connection of the generators Test run and connect the generators as per MW services method statement. |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-05-16 | 2023-06-30 |  | ASP-GN0195 | REL SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-05-16 | D | 113917 | 2023.05.18: Approved by Kobus JvR as per email 2023.05.16: Supported by Rob L | 100 | 2023-05-18 | 2023-05-18 | 113917 | Approved | {"MANDT":"111","REFERENCE":90000326,"ONEVIEW":"22491X","DATE01":"2023-03-07","DATE02":"2023-03-14","DATE03":"2023-04-04","DATE04":"2023-04-11","DATE05":"2023-05-02","DATE06":"2023-05-16","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-16","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFByb2plY3QgY29tcGxldGUuIFBhcnRpYWwgUE9DIGluIHByb2dyZXNzLCBwbGFubmVkIGZvciBlbmQgb2YgT2N0Lg==","RATING":""} |  |  | C000085951 | PHASE08 | 2023-05-16 | 2023-06-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-05-18 | 0 | 0 |  |  | C000085951 | 99058.26 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000327 | Absa Quadrum Office Park Dilaps | Absa Quadrum Office Park Dilaps |  |  | Region 1 |  | 21332X | 1000-70025-01 | Quadrum Office Park-Constantia Blvd-Roodepoort | N | 2023-05-16 | 2023-06-19 |  | ALP-GS0061 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-05-16 | D | 104768.99 | Approved by Lebusa M | 100 | 2023-05-22 | 2023-05-24 | 104768.99 | Approved | {"MANDT":"111","REFERENCE":90000327,"ONEVIEW":"21332X","DATE01":"2023-03-07","DATE02":"2023-03-14","DATE03":"2023-04-04","DATE04":"2023-04-11","DATE05":"2023-05-02","DATE06":"2023-05-16","DATE07":"2023-06-19","DATE08":"2023-07-10","DATE09":"2023-08-24","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-16","FORECAST_END":"2023-06-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000081492 | PHASE11 | 2023-05-16 | 2023-06-19 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-04-24 | 92054.67 | 0 |  |  | C000087543 | 414689.53 |  | 9590.4 |  | 0 | 0 |  | 0 |  | 0
90000328 | Various- Removal of Asbestos | Various- Removal of Asbestos RTB Notes Asbestos surveys were conducted on all Absa owned (Freehold) buildings during 2020 and 2021 to ensure compliance to the Asbestos Abatement regulations of 2020. There were 86 buildings identified with the presence of Asbestos Containing Materials (ACMs) nationally and the exposure risk was assessed from very low to high in the respective buildings. A project was completed in 2021/2022 to remove the asbestos from all the buildings with high and moderate exposure. To ensure compliance to the regulations, surveys needs to be done regularly and the Asbestos Containing Materials must be maintained regularly by registered service providers at a huge cost. The decision was made to remove the ACMs from the remaining 60 sites to elimate recurring costs of maintaining the ACMs in the buildings. This requests seeks the approval of R12 175 777.37 incl VAT to appoint Masheleni Trading and Projects (Absa direct appointment),Vombe Consulting (Absa direct appointment) and Bidvest FM for the removal of Asbestos Containing Materials at 60 freehold buildings. |  |  | National | National | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | U | 2023-05-31 | 2023-12-15 |  | ALP-N00048 | CRTD AVAC: |  | false | false |  | Lucia Amunga |  |  | 2023 |  | U |  | LOUISR | 2023-05-16 | D | 12175777.37 |  | 40 | 2023-05-11 | 2023-05-11 | 12175777.37 | 10.09.23 AS: Bidvest Portion is for 1. Fidelity Security R 647 000.00 2. Contingency R1054 179.86 3. Management Fees R579 798.92 PO value = R 2. 280 978.78 | {"MANDT":"111","REFERENCE":90000328,"ONEVIEW":"21526X","DATE01":"2023-03-22","DATE02":"2023-03-29","DATE03":"2023-04-19","DATE04":"2023-04-26","DATE05":"2023-05-17","DATE06":"2023-05-31","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":30,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-31","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtMTgvMDcvMjAyMy0gV0Egc3VibWl0dGVkIGZvciBhcHByb3ZhbC4gTEwtIDA0LzA5LzIwMjMtIFByb2plY3QgaW4gcHJvZ3Jlc3Mg","RATING":""} |  |  | C000099088 | PHASE06 | 2023-09-18 | 2024-04-03 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-07-12 | 2023-07-12 |  |  | 2023-07-20 | 1983459.82 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000329 | Absa Wilkoppies - Supply & Deliver Bench | Absa Wilkoppies - Supply & Deliver Bench |  |  | Region 3 |  | 77150X | 1000-71287-01 | Austin Crossing Centre-Cnr Austin & Ametis St-Klerksdorp |  | 2023-06-29 |  |  | ASP-CR0439 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2024-09-30 | NOMNGANGAL | 2023-05-19 | D | 0 | 2023.05.25: Approved by Conrad M 2023.05.23: Supported by Leko N & Ilana vdW | 100 | 2023-05-25 | 2023-05-25 | 28717.73 | Approved | {"MANDT":"111","REFERENCE":90000329,"ONEVIEW":"77150X","DATE01":"2023-04-20","DATE02":"2023-04-27","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-07-29","DATE08":"2023-08-19","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":24,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"T25jZSB0aGUgYmVuY2hlcyBhcmUgZGVsaXZlcmVkIHRvIHRoZSBicmFuY2guIFBPQyBwYWNrIHdpbGwgYmUgc3VibWl0dGVk","RATING":""} |  |  | 1 | PHASE11 | 2023-06-29 | 2023-07-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-05-29 | 0 | 0 |  |  | C000087976 | 24971.94 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000330 | 230 Lilian Ngoyi Street minor works Insu | 230 Lilian Ngoyi Street minor works Insu |  |  | Region 1 |  | 22896X | 1000-70079-01 | 230 Lilian Ngoyi Street-Lilian Ngoyi St-Pretoria |  | 2023-05-19 | 2023-05-19 |  | ASP-GN0196 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-19 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000331 | Auckland Park CC Apex to repair and repl | Auckland Park CC Apex to repair and repl |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-05-19 | 2023-05-19 |  | ASP-GS0670 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  | F |  | GAMIETR | 2023-05-19 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000331,"ONEVIEW":"76420X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-05-05","DATE06":"2023-05-19","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  | C000084172 | 226776.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000332 | Towers Main supply an iPad stand with po | Towers Main supply an iPad stand with po |  |  | Region 1 |  | 78944X | 1000-71415-01 | ABSA TOWERS MAIN-Main St-Johannesburg |  | 2023-05-19 | 2023-05-19 |  | ASP-GS0671 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-19 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 7797 |  |  |  |  | C000090799 | PHASE06 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-09 | 10311.53 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000333 | Protea Glen SC Supply 1 x yellow bin | Protea Glen SC Supply 1 x yellow bin |  |  | Region 1 |  | 35107X | 1000-70087-01 | Protea Glen Shopping Centre-Cnr R558 & Protea Blvd-Soweto | N | 2023-05-19 | 2023-05-19 |  | ASP-GS0672 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-19 | D | 1712.38 |  | 100 | 2023-05-25 | 2023-06-29 | 1969.24 |  | {"MANDT":"111","REFERENCE":90000333,"ONEVIEW":"35107X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2022-08-31","DATE05":"2022-09-21","DATE06":"2022-10-05","DATE07":"2022-10-05","DATE08":"2022-10-26","DATE09":"2022-12-10","DATE10":"2022-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":100,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"143:7:21:-219:21:14:0:21:45:7","PROGRESS":2,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2022-10-05","FORECAST_END":"2022-10-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000090798 C000090798 C000090798 | PHASE08 | 2022-10-05 | 2022-10-05 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-09 | 1712.38 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000334 | Towers West Supply 10 x wheelie bins | Towers West Supply 10 x wheelie bins |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-05-19 | 2023-05-19 |  | ASP-GS0673 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-19 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 6699.9 |  | {"MANDT":"111","REFERENCE":90000334,"ONEVIEW":"21526X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-05-05","DATE06":"2023-05-19","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000090800 | PHASE08 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-09 | 5826 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000335 | Annan Road Install fire extinguisher in | Annan Road Install fire extinguisher in |  |  | Region 1 |  | 76403X | 1000-70241-01 | Absa Annan Road-Annan Rd-Carletonville | N | 2023-05-19 | 2023-05-19 |  | ASP-GS0674 | CRTD SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  | L |  | GAMIETR | 2023-05-19 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 1609.14 |  | {"MANDT":"111","REFERENCE":90000335,"ONEVIEW":"76403X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-05-05","DATE06":"2023-05-19","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDYW5jZWxsZWQ=","RATING":""} |  |  | C000090797 | PHASE06 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-09 | 1609.14 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000336 | Highlands Install a security vehicle ho | Highlands Install a security vehicle ho |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale | N | 2023-05-19 | 2023-05-19 |  | ASP-GS0675 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-21 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000336,"ONEVIEW":"37006X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-05-05","DATE06":"2023-05-19","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  | C000084172 | 226776.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000337 | Absa Vrburg - Supply & Install external | Absa Vrburg - Supply & Install external |  |  | Region 3 | North West | 77745X | 1000-71604-01 | Vryburg-Market St-Vryburg |  | 2023-06-29 |  |  | ASP-CR0440 | CRTD RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  | L | 2022-03-30 | NOMNGANGAL | 2023-05-22 | D | 0 | No Approvals as yet. | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000337,"ONEVIEW":"77745X","DATE01":"2023-04-20","DATE02":"2023-04-27","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-10-19","DATE08":"2023-11-09","DATE09":"2023-12-24","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"184:7:21:7:21:14:112:21:45:18","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-10-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgQ291bmNpbCBhcHByb3ZhbC4=","RATING":""} |  |  |  | PHASE00 | 2023-06-29 | 2023-10-19 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000338 | Alice Lane North Induction Jet UV Light | Alice Lane North Induction Jet UV Light |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | N | 2023-05-19 | 2023-05-19 |  | ASP-GS0676 | CRTD SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-05-22 | D | 177519.72 | 2023.05.25: Approved by Kobus JvR 2023.05.23: Supported by Rob L | 100 | 2023-05-25 | 2023-05-25 | 177519.72 | Approved | {"MANDT":"111","REFERENCE":90000338,"ONEVIEW":"70656X","DATE01":"2023-03-10","DATE02":"2023-04-01","DATE03":"2023-04-04","DATE04":"2023-04-11","DATE05":"2023-04-27","DATE06":"2023-07-18","DATE07":"2023-07-26","DATE08":"2023-08-08","DATE09":"2023-09-22","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-18","FORECAST_END":"2023-07-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBTaWduIG9mZiBvZiBQT0MgMjcuMDkuMjAyMw==","RATING":""} |  |  | C000083244 | PHASE08 | 2023-07-18 | 2023-07-26 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 151364.97 | 0 |  |  | C000084172 | 226776.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000339 | Golden Walk SC Install ATM signage | Supply & install external suspended Sign 600mm x 1600mm external ATM signage |  |  | Region 1 |  | 70623X | 1000-70233-01 | Golden Walk Shopping Centre-Victoria St-Germiston | N | 2023-05-19 | 2023-05-19 |  | ASP-GS0677 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-05-22 | D | 49216.57 | 2023.05.25: Approved by Conrad M 2023.05.23: Supported by Winston P & Ilana vdW | 100 | 2023-05-22 | 2023-05-25 | 49216.57 | Approved | {"MANDT":"111","REFERENCE":90000339,"ONEVIEW":"70623X","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-05-05","DATE06":"2023-05-19","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgbmV3IHBvc2l0aW9uIG9mIHRoZSBuZXcgQVRNIHNpZ25hZ2UgZnJvbSBMTA==","RATING":""} |  |  | C000088373 | PHASE06 | 2023-05-19 | 2023-05-19 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 49216.57 | 0 |  |  | C000088373 | 42797.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000340 | Various Sites 2 x Icecream Machines | Various Sites 2 x Ice cream Machines |  |  | Region 1 |  |  |  | Building not in Real Estate Database |  | 2023-05-19 | 2023-05-19 |  | ASP-N00053 | REL CNF BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-05-22 | D | 98210 | Approved | 100 | 2023-07-24 | 2023-10-07 | 98210 |  | {"MANDT":"111","REFERENCE":90000340,"ONEVIEW":"","DATE01":"2023-03-10","DATE02":"2023-03-17","DATE03":"2023-04-07","DATE04":"2023-04-14","DATE05":"2023-05-05","DATE06":"2023-05-19","DATE07":"2023-05-19","DATE08":"2023-06-09","DATE09":"2023-07-24","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-19","FORECAST_END":"2023-05-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000103144 | PHASE08 | 2023-05-19 | 2023-05-19 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-08-10 | 85400 | 0 |  |  | C000103144 | 85400 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000341 | Absa Riviersonderend - HVAC Cages | Absa Riviersonderend - HVAC Cages |  |  | Region 2 | Western Cape | 77697X | 1000-70847-01 | Absa Riviersonderend-Main Rd-Riviersonderend | U | 2023-07-01 | 2023-08-31 |  | ASP-WC0281 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-05-22 | D | 49539.28 |  | 1 | 2023-05-25 | 2023-05-31 | 49539.28 | Note Was approved against Eng Headwind Bulk PO project ALP-N00043 | {"MANDT":"111","REFERENCE":90000341,"ONEVIEW":"77697X","DATE01":"2023-05-19","DATE02":"2023-05-19","DATE03":"2023-05-19","DATE04":"2023-05-23","DATE05":"2023-05-25","DATE06":"2023-06-14","DATE07":"2023-07-14","DATE08":"2023-07-27","DATE09":"2023-09-10","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:4:2:20:30:13:45:25","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-14","FORECAST_END":"2023-07-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Tm90ZSBXYXMgYXBwcm92ZWQgYWdhaW5zdCBFbmcgSGVhZHdpbmQgQnVsayBQTyBwcm9qZWN0IEFMUC1OMDAwNDM=","RATING":"Low"} |  |  |  | PHASE12 | 2023-06-14 | 2023-07-14 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-05-31 | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000342 | Absa Kuruman - Install New Generator 40K | Absa Kuruman - Install New Generator 40K |  |  | Region 3 |  | 78504X | 1000-71350-01 | Kuruman-Cnr Hoof & Livingstone Rd-Kuruman |  | 2023-06-29 |  |  | ALP-CR0033 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-22 | D | 0 | BTB paper to be approved | 40 |  |  | 0 | BTB paper to be approved | {"MANDT":"111","REFERENCE":90000342,"ONEVIEW":"78504X","DATE01":"2023-04-20","DATE02":"2023-04-27","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-07-29","DATE08":"2023-08-19","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE04 | 2023-06-29 | 2023-07-29 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000343 | Absa Ficksburg - Install New Generator 8 | Absa Ficksburg - Install New Generator 8 |  |  | Region 3 |  | 70645X | 1000-71517-01 | Absa Ficksburg |  | 2023-06-29 |  |  | ALP-CR0034 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-22 | D | 0 | 2023.06.15: Approved by Kobus JvR as per email | 100 | 2023-06-15 | 2023-06-15 | 1008119.42 | Approved | {"MANDT":"111","REFERENCE":90000343,"ONEVIEW":"70645X","DATE01":"2023-04-20","DATE02":"2023-05-26","DATE03":"2023-05-26","DATE04":"2023-06-07","DATE05":"2023-06-08","DATE06":"2023-07-11","DATE07":"2023-08-18","DATE08":"2023-08-31","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":87,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-11","FORECAST_END":"2023-08-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIFBDIHNpZ24gb2ZmIGNvbXBsZXRlZA==","RATING":""} |  |  |  | PHASE09 | 2023-07-11 | 2023-08-18 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000120450 | 876625.58 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000344 | Absa Virginia - Installlation of New Gen | Absa Virginia - Installlation of New Gen |  |  | Region 3 |  | Unknown | 1000-71582-01 | Unknown Building - not in our database |  | 2023-06-29 |  |  | ALP-CR0035 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-22 | D | 0 | 2023.06.15: Approved by Kobus JvR as per email | 100 | 2023-06-15 | 2023-06-15 | 1205505.86 | Approved | {"MANDT":"111","REFERENCE":90000344,"ONEVIEW":"Unknown","DATE01":"2023-04-20","DATE02":"2023-05-26","DATE03":"2023-05-26","DATE04":"2023-05-07","DATE05":"2023-06-08","DATE06":"2023-07-11","DATE07":"2023-08-18","DATE08":"2023-08-31","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-11","FORECAST_END":"2023-08-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDb21wbGV0ZWQgYW5kIFBDIHNpZ24gb2ZmIGNvbmR1Y3RlZA==","RATING":""} |  |  |  | PHASE09 | 2023-07-11 | 2023-08-18 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000120451 | 1048265.97 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000345 | Absa Bethlehem - Minor works | Absa Bethlehem - Minor works |  |  | Region 3 |  | Unknown | 1000-71480-01 | Unknown Building - not in our database |  | 2023-06-29 |  |  | ALP-CR0036 | REL RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-22 | D | 0 | BTB paper to be approved. | 0 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000345,"ONEVIEW":"Unknown","DATE01":"2023-04-20","DATE02":"2023-07-18","DATE03":"2023-07-18","DATE04":"2023-07-18","DATE05":"2023-07-25","DATE06":"2023-08-28","DATE07":"2023-09-04","DATE08":"2023-09-30","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":50,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-28","FORECAST_END":"2023-09-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2024-02-14 | 2024-02-21 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000346 | Absa Church Street (Victoria West) | Absa Church Street (Victoria West) |  |  | Region 3 |  | Unknown | 1000-71320-01 | Unknown Building - not in our database |  | 2023-06-28 |  |  | ALP-CR0037 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-22 | D | 0 | 2023.06.15: Approved by Kobus JvR as per email | 40 | 2023-06-15 | 2023-06-15 | 819216.45 | Approved | {"MANDT":"111","REFERENCE":90000346,"ONEVIEW":"Unknown","DATE01":"2023-04-19","DATE02":"2023-04-26","DATE03":"2023-05-17","DATE04":"2023-05-24","DATE05":"2023-06-14","DATE06":"2023-06-28","DATE07":"2023-07-28","DATE08":"2023-08-18","DATE09":"2023-10-02","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":50,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":1,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-28","FORECAST_END":"2023-07-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RHVwbGljYXRlLg==","RATING":""} |  |  |  | PHASE04 | 2023-06-28 | 2023-07-28 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000120447 | 695841.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000347 | Ntabankulu - Limited scope: Minor Works | Ntabankulu - Limited scope: Minor Works |  |  | Region 2 | Eastern Cape | 20949X | 1000-70921-01 | Ntabankulu-Main St-Ntabankulu | N | 2023-08-31 |  |  | ALP-EC0012 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-05-23 | D | 1308795.67 |  | 100 | 2023-07-13 | 2023-08-10 | 1308795.67 | PO received 16th Oct | {"MANDT":"111","REFERENCE":90000347,"ONEVIEW":"20949X","DATE01":"2023-03-06","DATE02":"2023-05-04","DATE03":"2023-07-07","DATE04":"2023-07-14","DATE05":"2023-08-10","DATE06":"2023-10-09","DATE07":"2023-10-19","DATE08":"2023-11-09","DATE09":"2023-12-24","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"300:59:64:7:27:60:10:21:45:7","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-09","FORECAST_END":"2023-10-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTYgT2N0IEFic2EgUE8gUmVjZWl2ZWQgQzAwMDExNjgzMyAtICBSIDEzMDg3OTUuNjcKMTIgT2N0IEZ1bGx5IFNpZ25lZCBXQSBhbmQgU0YgcmVjZWl2ZWQgQWJzYSBQTyB0byBiZSByZXF1ZXN0ZWQgLSBOb3RlIEJWIFBvJ3MgSXNzdWVk","RATING":"Medium"} |  |  | C000116833 | PHASE10 | 2023-10-09 | 2023-10-19 | RODERICK NEVAY | Floyd Mofokeng | 23000083 |  |  |  |  | 2023-10-13 | 1138083.19 | 0 |  |  | C000116833 | 1138083.19 | CIP2023XP | 107954.28 |  | 0 | 0 |  | 0 |  | 0
90000348 | Absa Kroonstad-Disconnecting plugs from | Absa Kroonstad-Disconnecting plugs from |  |  | Region 3 |  | 37158X | 1000-77439-01 | Corner President, Cross and Hill Streets, Kroonstad |  | 2023-06-29 |  |  | ASP-CR0441 | CLSD BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | L | 2024-04-29 | NOMNGANGAL | 2023-05-26 | D | 0 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Rob L | 100 | 2023-07-06 | 2023-07-06 | 37490.16 | Approved | {"MANDT":"111","REFERENCE":90000348,"ONEVIEW":"37158X","DATE01":"2023-04-20","DATE02":"2023-05-12","DATE03":"2023-07-12","DATE04":"2023-07-12","DATE05":"2023-07-15","DATE06":"2023-07-21","DATE07":"2023-09-28","DATE08":"2023-10-11","DATE09":"2023-10-12","DATE10":"2023-10-16","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"255:22:61:0:3:6:69:13:1:27","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-21","FORECAST_END":"2023-09-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2U=","RATING":""} |  |  | C000096922 | PHASE11 | 2023-07-21 | 2023-09-28 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-07-10 | 32600.14 | 0 |  |  | C000096922 | 32600.14 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000349 | Absa Kloof Village Mall - HVAC Replaceme | Absa Kloof Village Mall - HVAC Replaceme |  |  | Region 3 | Kwazulu-Natal | 78110X | 1000-71214-01 | Kloof Village Mall-Village Rd-Kloof |  | 2023-06-29 |  |  | ASP-KZ0250 | CLSD BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  | L | 2022-05-30 | NOMNGANGAL | 2023-05-26 | D | 0 | 2023.05.31: Approved by Kobus JvR as per email 2023.05.30: Supported by Rob L |  | 2023-06-01 | 2023-06-01 | 398934.74 | Approved | {"MANDT":"111","REFERENCE":90000349,"ONEVIEW":"","DATE01":"2023-04-20","DATE02":"2023-04-27","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-07-29","DATE08":"2023-08-19","DATE09":"2023-10-03","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000089059 | PHASE11 | 2023-10-06 | 2023-10-06 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-01 | 346899.77 | 0 |  |  | C000089059 | 346899.77 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000350 | Absa Ladysmith - Waterproofing | Absa Ladysmith - Waterproofing |  |  | Region 3 |  | Unknown | 1000-71074-01 | Unknown Building - not in our database |  | 2023-06-29 |  |  | ASP-KZ0251 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-26 | D | 0 | 2023.07.27: Approved by Kobus JvR as per email 2023.07.25: Supported by Rob L |  | 2023-07-27 | 2023-07-27 | 477701.75 | Approved |  |  |  | C000112433 | PHASE10 | 2023-08-31 | 2023-09-26 | NANDE MAQUBELA | Juanita van Coller | 0 |  |  |  |  | 2023-09-22 | 157608.41 | 0 |  |  | C000102222 | 415392.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000351 | Absa Twin City Burgersfort - New Manager | Absa Twin City Burgersfort - New Manager |  |  | Region 3 |  | 36240X | 1000-70501-01 | Twin City Burgers Fort-Cnr Dirk Winterbach & Kruis St-Burgers Fort |  | 2023-07-27 |  |  | ASP-LP0164 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L | 2026-08-30 | NOMNGANGAL | 2023-05-26 | D | 0 | Project has been cancelled | 1 |  |  | 0 | Project has been put on hold | {"MANDT":"111","REFERENCE":90000351,"ONEVIEW":"Unknown","DATE01":"2023-05-18","DATE02":"2023-05-25","DATE03":"2023-06-15","DATE04":"2023-06-22","DATE05":"2023-07-13","DATE06":"2023-07-27","DATE07":"2023-08-26","DATE08":"2023-09-16","DATE09":"2023-10-31","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-27","FORECAST_END":"2023-08-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-07-27 | 2023-08-26 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000352 | Absa EC Various Branches - Wheelie Bins | Absa EC Various Branches - Wheelie Bins (Burgersdorp, Ntabankulu, Alexandria) |  |  | Region 2 | Eastern Cape | Various | 1000-71063-01 | Various Sites EC | N | 2023-06-05 | 2023-06-30 |  | ASP-N00054 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Laxine Maliffe |  |  | 2023 |  | U |  | CEASARS | 2023-05-26 | D | 4288.43 | 2023.05.31: Approved by Conrad M as per email 2023.05.30: Supported by Judith B | 100 | 2023-05-31 | 2023-06-01 | 4288.41 | Approved | {"MANDT":"111","REFERENCE":90000352,"ONEVIEW":"Various","DATE01":"2023-05-11","DATE02":"2023-05-11","DATE03":"2023-05-22","DATE04":"2023-05-31","DATE05":"2023-05-31","DATE06":"2023-06-12","DATE07":"2023-06-12","DATE08":"2023-06-26","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:11:9:0:12:0:14:35:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-12","FORECAST_END":"2023-06-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgSnVuZSAtIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQ==","RATING":"Low"} |  |  | C000089060 | PHASE11 | 2023-06-12 | 2023-06-12 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-01 | 3729.05 | 0 |  |  | C000089060 | 3729.06 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000353 | Absa Oude Bloemhof - Minor Works | Absa Oude Bloemhof - Minor Works |  |  | Region 2 | Western Cape | 77946X | 1000-70866-01 | Oude Bloemhof Building-Cnr Van Ryneveld & Plein St-Stellenbosch | N | 2023-06-30 | 2023-08-31 |  | ASP-WC0282 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-05-26 | D | 338988.31 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Judith B as per email | 100 | 2023-07-13 | 2023-07-13 | 338988.31 | Absa Ref : 240129_127 | {"MANDT":"111","REFERENCE":90000353,"ONEVIEW":"77946X","DATE01":"2023-05-24","DATE02":"2023-06-10","DATE03":"2023-07-14","DATE04":"2023-07-13","DATE05":"2023-07-13","DATE06":"2023-08-14","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"2024-02-19","DATE12":"2024-02-19","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"252:17:34:-1:0:32:123:21:45:23","PROGRESS":71,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-14","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRmViIFBNIHRvIGZvbGxvdyB1cCB3aXRoIE11bmljaXBhbGl0eQo1IEZlYiBQTSB0byBjb25maXJtIGRhdGUgb2YgTWVldGluZwoyOSBKYW4gLSBNdW5pY2lwYWxpdHkgcmVxdWVzdGVkIHdlIGZvbGxvdyB1cCBpbiBGRUIgYWZ0ZXIgbWVldGluZwoxOCBKYW4gLSBQTSB0byBmb2xsb3cgdXAgd2l0aCBNdW5pY2lwYWxpdHkKMTEgRGVjIFBNIHRvIGNvbnRpbnVlIHdpdGggZm9sbG93IHVwJ3Mgd2l0aCBNdW5pY2lwYWxpdHkKNCBEZWMgLSBQTSBmb2xsb3dpbmcgdXAgd2l0aCBtdW5pY2lwYWxpdHksIG5vIHJlc3BvbnNlIGFzIG9uIDEgRGVjLgoyNyBOb3YgU3RpbGwgbm8gZmVlZGJhY2sgZnJvbSBNdW5pY2lwYWxpdHkgLSBQTSBXaWxsIGZvbGxvdyB1cCB3aXRoIG11bmljaXBhbGl0eQoyMCBOb3YgLSBObyBmZWVkYmFjayBmcm9tIE11bmljaXBhbGl0eSBQTSBjYWxsZWQgb24gRnJpZGF5IDE3dGgsIG1lZXRpbmcgeWV0IHRvIGJlIGhlbGQgdG8gY29uZmlybS4KNiBOb3YgLSBQTSB0byBmb2xsb3cgdXAgd2l0aCBNdW5pY2lwYWxpdHkgYXMgbm8gcmVzcG9uc2UuCjMwIE9jdCAtIFRvIGJlIHRhYmxlZCBvbiB0aGUgTXVuaWNpcGFsIE5vdmVtYmVyIEFnZW5kYSB0byBhcHByb3ZlLCBkYXRlIHRvIGJlIGNvbmZpcm1lZAoyNiBPY3QgVG8gZm9sbG93IHVwIGFnYWluIGFzIG5vIHJlc3BvbnNlIGZyb20gTXVuaWNpcGFsaXR5CjIzIE9jdCBQTSB0byBwaG9uZSBNdW5pY2lwYWxpdHkgcmUgZGVjaXNpb24KMTYgT2N0IFBNIEZvbGxvd2VkIHVwIHdpdGggTXVuaWNpcGFsaXR5IHJlIGFwcHJvdmFsIHRvIHByb2NlZWQgd2l0aCBGZW5jZQoxMyBPY3QgUE9DIFBhcnQgMSBTdWJtaXR0ZWQgLSBSIDI0NCAxMzQuNTIKMDkgT2N0IFBNIHRvIGZvbGxvdyB1cCB3aXRoIHRoZSBNdW5pY2lwYWxpdHkgcmUgYXBwcm92YWwgUE9DIHBhcnQgMSBTdWJtaXR0ZWQgZm9yIHNpZ25vZmYKMjIgU2VwdCAtIExhbmQgU3VydmV5b3IgdG8gbWVldCBvbiBzaXRlIDI2IFNlcHQgIC0gUG9zc2libGUgUm9sbG92ZXIgYmFzZWQgb24gdGhlIG91dGNvbWUgYW5kIGlmIGFwcGxpY2F0aW9ucyB0byBiZSBtYWRlIHRvIHRoZSBtdW5pY2lwYWxpdHkKMTggU2VwdCBMYW5kIFN1cnZleW9yIHRvIHZpc2l0IHRoaXMgd2VlayB0byBjb25maXJtIGFyZWEgYmVsb25ncyB0byBBYnNhIHRvIGNvbXBsZXRlIGJ5IDI5IFNlcHQKMTIgU2VwdCBBbWVuZGVkIFBPIHJlY2VpdmVkIDQ1MDA4NDQ1ODkKMTEgU2VwdCAtIExhbmQgU3VydmV5b3IgUXVvdGUgU3VibWl0dGVkIGFuZCBTdXBwb3J0ZWQgQnkgQ3JlcyAtIE1heCBQcm9qZWN0cyBMYW5kIFN1cnZleW9yIENvc3RzIGV4IHZhdCAgUiAxMiA3NDAuMDAgLSBGcm9tIENvbnRpbmdlbmN5CjUgU2VwdCAtIExhbmQgc3VydmV5b3IgY29zdHMgYmVpbmcgc291cmNlZC4gTXVuaWNpcGFsaXR5IHRvIGJlIGVuZ2FnZWQgaW4gdGVybXMgb2YgdGhlIGZlbmNlIGluc3RhbGxhdGlvbi4gUHJvcG9zZWQgY29tcGxldGlvbiBkYXRlIDMwIFNlcHRlbWJlciAoZGVwZW5kZW50IG9uIE11bmljaXBhbGl0eSBhcHByb3ZhbCkKMjggQXVnIC0gSXNzdWUgd2l0aCBmZW5jaW5nIHJlIG11bmljaXBhbGl0eSByZSBmZW5jZSBTaWduYWdlIHRvIGJlIGNvbmNsdWRlZCAyOC8yOSBBdWcgLSBXb3JrIGluIHByb2dyZXNzLiBMYW5kIFN1cnZleW9yIHRvIHBlZyB0aGUgYXJlYSBmb3IgdGhlIGZlbmNpbmcuIENvdW5jaWwgYXBwcm92YWwgdG8gYmUgb2J0YWluZWQgZm9yIHRoZSBmZW5jZQo=","RATING":"Low"} |  |  | C000098562 | PHASE08 | 2023-08-14 | 2023-12-15 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-07-18 | 294772.44 | 0 |  |  | C000098562 | 294772.43 |  | 16032.78 |  | 0 | 0 |  | 0 |  | 0
90000354 | Absa Lutzville - ATM Security Door | Absa Lutzville - ATM Room New Security Door |  |  | Region 2 | Western Cape | 77802X | 1000-70860-01 | Lutzville-Namakwa St-Lutzville | N | 2023-06-30 | 2023-08-31 |  | ASP-WC0283 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-05-26 | D | 141960.58 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Judith B & Ilana vdW | 100 | 2023-07-06 | 2023-07-06 | 141960.58 | Approved | {"MANDT":"111","REFERENCE":90000354,"ONEVIEW":"77802X","DATE01":"2023-05-26","DATE02":"2023-06-02","DATE03":"2023-06-30","DATE04":"2023-07-06","DATE05":"2023-07-06","DATE06":"2023-07-24","DATE07":"2023-07-28","DATE08":"2023-08-08","DATE09":"2023-09-22","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"158:7:28:6:0:18:4:11:45:29","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-24","FORECAST_END":"2023-07-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBdWcgRmluYWwgUE9DIFN1Ym1pdHRlZAoxOSBKdWx5IFBsYW5uZWQgc3RhcnQgb24gc2l0ZSAyNCBKdWx5CjI3IEp1bHkgV29yayBpbiBwcm9ncmVzcwoyOCBKdWx5IFdvcmtzIENvbXBsZXRlZA==","RATING":"Low"} |  |  | C000096891 | PHASE11 | 2023-07-24 | 2023-07-28 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-07-10 | 123443.98 | 0 |  |  | C000096891 | 123443.98 |  | 6295.74 |  | 0 | 0 |  | 0 |  | 0
90000355 | The Boulders Shopping Centre Minor Works | The Boulders Shopping Centre Minor Works |  |  | Region 1 |  | 36250X | 1000-70197-01 | The Boulders Shopping Centre-Old Pretoria Rd-Midrand | N | 2023-04-05 |  |  | ASP-GN0197 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2030-04-29 | MOKOENAM2 | 2023-05-29 | D | 285101.03 | 2023.05.31: Approved by Conrad M as per email 2023.05.30: Supported by Winston P | 100 | 2023-06-19 | 2023-06-01 | 285101.03 | Approved | {"MANDT":"111","REFERENCE":90000355,"ONEVIEW":"36250X","DATE01":"2023-01-25","DATE02":"2023-05-08","DATE03":"2023-05-29","DATE04":"2023-06-05","DATE05":"2023-07-04","DATE06":"2023-07-18","DATE07":"2023-08-04","DATE08":"2023-08-25","DATE09":"2023-10-09","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-18","FORECAST_END":"2023-08-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IFByb2plY3QgY29tcGxldGVkIGFuZCBQT0Mgc3VibWl0dGVkIA==","RATING":""} |  |  | C000089285 | PHASE11 | 2023-07-18 | 2023-08-04 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-07 | 247913.94 | 111265.59 |  |  | C000140955 | 18004.48 |  | 130380.78 |  | 0 | 0 |  | 0 |  | 0
90000356 | Sanridge Square Shopping Centre External | Remove electrical, fire and security equipment & set aside Remove electrical equipment & set aside Remove all ceiling panels (390m2) realignment of the ceiling hanger drop Install new ceilings as per Absa specifications (390m2) Reinstate electrical, fire and security equipment Supply and Install x3 new benches as per Absa specification Work will be conducted after normal working hours for 7 days Security Guard for the duration of the project Material lead-time: +-1 week |  |  | Region 1 | Gauteng North | 21861X | 1000-70042-01 | Sanridge Square Shopping Centre-Cnr New & Lever Rd-Midrand |  | 2023-04-05 |  |  | ASP-GN0198 | CRTD: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-05-29 | D | 278231.23 |  | 100 | 2023-08-10 | 2023-08-15 | 278231.23 |  | {"MANDT":"111","REFERENCE":90000356,"ONEVIEW":"21861X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-09-01","DATE06":"2023-09-15","DATE07":"2023-10-15","DATE08":"2023-11-05","DATE09":"2023-12-20","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:21:7:184:14:30:21:45:21","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-15","FORECAST_END":"2023-10-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RHVwbGljYXRlLiA=","RATING":""} |  |  | C000104094 | PHASE07 | 2023-09-15 | 2023-10-15 |  |  | 0 |  |  |  |  | 2023-08-15 | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000357 | Absa Meadowridge - Dilaps | Absa Meadowridge - Dilaps |  |  | Region 2 | Western Cape | 77452X | 1000-70833-01 | Park n Shop Meadowridge-Firgrove Way-Meadowridge | N | 2023-06-30 | 2023-08-31 |  | ASP-WC0284 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-05-29 | D | 254796.43 |  | 100 | 2023-08-21 | 2023-08-26 | 254796.43 | Approved | {"MANDT":"111","REFERENCE":90000357,"ONEVIEW":"77452X","DATE01":"2023-05-29","DATE02":"2023-06-16","DATE03":"2023-08-21","DATE04":"2023-08-28","DATE05":"2023-08-26","DATE06":"2023-09-04","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:18:66:7:-2:9:25:21:45:15","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-04","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkgQXVnIC0gQWJzYSBQTyByZWNlaXZlZCBDMDAwMTA2NjkxCjI2IEF1ZyBBcHByb3ZlZCBieSBSZWFsIEVzdGF0ZSBQTydzIFBlbmRpbmcKMjQgQXVnIFN1cHBvcnRlZCBieSBDUkVTIFZQIHNlbnQgdG8gUmVhbCBFc3RhdGUgZm9yIEFwcHJvdmFsCjIxIEF1ZyBCQyByZWNlaXZlZCByZXF1ZXN0ZWQgVlAgc3VwcG9ydCBmcm9tIExla28gYXMgSnVkaXRoIG9uIGxlYXZlCg==","RATING":"Low"} |  |  | C000106691 | PHASE11 | 2023-09-04 | 2023-09-15 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-08-28 | 221562.11 | 0 |  |  | C000106691 | 0 |  | 12024.83 |  | 0 | 0 |  | 0 |  | 0
90000358 | Absa Delta House Dilaps | Removal of Internal & external signage Removal of UPS Removal of Secutel, ITAS, Domestic lock & safe service and Fidelity ADT security equipment Removal of TVs and screens Removal of aircon units Dilapidations will be conducted during normal working hours and weekends for 10 days. |  |  | Region 1 |  | 76422X | 1000-71377-01 | Delta House |  | 2023-05-30 | 2023-05-30 |  | ASP-GN0199 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-05-30 | D | 326284.65 | Approved at CB/BTB | 100 | 2023-06-15 | 2023-06-21 | 326284.65 | Approved | {"MANDT":"111","REFERENCE":90000358,"ONEVIEW":"76422X","DATE01":"2023-03-21","DATE02":"2023-03-28","DATE03":"2023-04-18","DATE04":"2023-04-25","DATE05":"2023-06-21","DATE06":"2023-07-05","DATE07":"2023-07-05","DATE08":"2023-07-26","DATE09":"2023-09-09","DATE10":"2023-09-30","DATE11":"2023-09-09","DATE12":"2023-09-09","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-05","FORECAST_END":"2023-07-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUE9DIDEgJiAyIHNlbnQgdG8gZmluYW5jZS4gQXdhaXRpbmcgTGF1bWFyLCBJVFNBICYgU2VjdXRlbCBJbnZvaWNlIGZvciBGaW5hbCBQT0Mu","RATING":""} |  |  | C000093242 | PHASE08 | 2023-07-05 | 2023-07-05 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-21 | 283725.78 | 0 |  |  | C000093242 | 283725.78 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000359 | Absa Hillcrest Dilaps | Removal of Internal & external signage Removal of all Absa Artwork Removal of UPS Removal of security systems and equipment Removal of TVs and screens Removal of x 4 aircon units Dilapidations will be conducted during normal working hours and weekends for 10 days. |  |  | Region 1 |  | 78531X | 1000-70416-01 | Hillcrest Office Park-Lunnon Rd-Pretoria |  | 2023-05-30 | 2023-05-30 |  | ASP-GN0200 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-05-30 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 229554.06 |  | {"MANDT":"111","REFERENCE":90000359,"ONEVIEW":"78531X","DATE01":"2023-03-21","DATE02":"2023-03-28","DATE03":"2023-04-18","DATE04":"2023-04-25","DATE05":"2023-05-16","DATE06":"2023-05-30","DATE07":"2023-05-30","DATE08":"2023-06-20","DATE09":"2023-08-04","DATE10":"2023-08-31","DATE11":"2023-08-04","DATE12":"2023-08-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-30","FORECAST_END":"2023-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUE9DIDEsIDIgJiAzIHNlbnQgdG8gZmluYW5jZS4gQXdhaXRpbmcgRmlkZWxpdHkgSW52b2ljZSBmb3IgZmluYWwgUE9DLgo=","RATING":""} |  |  | C000089648 | PHASE08 | 2023-05-30 | 2023-05-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-05 | 263987.17 | 0 |  |  | C000089648 | 199612.23 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000360 | Absa East Rand Mall Dilaps | Absa East Rand Mall Dilaps |  |  | Region 1 |  | 78283X | 1000-70398-01 | East Rand Mall-Bentel Ave-Boksburg |  | 2023-05-29 | 2023-05-29 |  | ASP-GS0678 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-05-30 | D | 0 | 2023.05.31: Approved by Kobus JvR as per email 2023.05.30: Supported by Rob L | 100 | 2023-06-01 | 2023-06-01 | 364362.72 | Approved |  |  |  | C000089286 | PHASE08 | 2023-05-29 | 2023-05-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-02 | 418975.73 | 0 |  |  | C000089286 | 316805.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000361 | Absa Eden Square Shopping - Branch Dilap | Absa Eden Square Shopping - Branch Dilap |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-06-15 |  |  | ASP-MP0161 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-05-30 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-06-15 | 2023-07-15 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000362 | BUSHBUCKRIDGE COMPLETE HVAC REPLACEMENT |  |  |  | Region G |  | Unknown | 1000-70577-01 | Unknown Building - not in our database |  |  |  |  | ALP-MP0001 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 0 |  |  |  | NGIDIN | 2021-03-10 |  | 0 |  |  |  |  | 0 | [5 empty] | PHASE11 |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 808398 |  |  | 2858843 | 808398 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000363 | PIET RETIEF HVAC UPGRADE |  |  |  | Region G |  | Unknown | 1000-70610-01 | Unknown Building - not in our database |  |  |  |  | ALP-MP0003 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 0 |  |  |  | NGIDIN | 2021-07-01 |  | 0 |  |  |  |  | 0 | [5 empty] | PHASE11 |  |  | SIYANDA DLAMINI | Thea Spamers | 0 | [5 empty] | 0 | 717906.31 |  |  | 2855059 | 60087.92 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000364 | THE GROVE PROFESSIONAL REDESIGN ENTRANCE |  |  |  | Region 1 |  | Unknown | 1000-70006-01 | Unknown Building - not in our database |  |  |  |  | ALP-GS0023 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Tsholofelo Sello |  |  | 0 |  |  |  | GAMIETR | 2021-08-20 |  | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000364,"ONEVIEW":"Unknown","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"0000-00-00","DATE07":"0000-00-00","DATE08":"0001-01-22","DATE09":"0001-03-08","DATE10":"0000-00-00","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"0000-00-00","FORECAST_END":"0000-00-00","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"VGVzdCBub3Rl","RATING":""} |  |  |  | PHASE11 |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  | 2865537 | 570380.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000365 | DEMOUNTABLE TLHABANE - LIMITED SCOPE |  |  |  | Region G |  | Unknown | 1000-71311-01 | Unknown Building - not in our database |  |  |  |  | ASP-CR0212 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 0 |  |  |  | NGIDIN | 2021-08-20 |  | 0 |  |  |  |  | 0 | [5 empty] | PHASE11 |  |  | SIYANDA DLAMINI | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | 2867423 | 312513.34 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000366 | PHAROS HOUSE (WESTVILLE) MINOR WORKS VO |  |  |  | Region G |  | Unknown | 1000-71154-01 | Unknown Building - not in our database |  |  |  |  | ASP-KZ0137 | REL BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 0 |  |  |  | NGIDIN | 2021-09-28 |  | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | SIYANDA DLAMINI | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | 2876231 | 45062.35 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000367 | EYETHU MALL SHREDDING DOCUMENTS GP RIO |  |  |  | Region 1 | Gauteng South | 35152X | 1000-70093-01 | Eyethu Orange Farm Mall-Cnr Link Rd & 2nd St-Johannesburg | N |  |  |  | ASP-GS0389 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 0 |  | L |  | GAMIETR | 2021-11-22 |  | 1178.75 |  | 100 | 2021-08-19 |  | 1178.75 |  | {"MANDT":"111","REFERENCE":90000367,"ONEVIEW":"Unknown","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"0000-00-00","DATE07":"0000-00-00","DATE08":"0001-01-22","DATE09":"0001-03-08","DATE10":"0000-00-00","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"0000-00-00","FORECAST_END":"0000-00-00","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | 2889970 | PHASE11 |  |  | PRESHANE MUNTHREE | Buhle Qwabe | 0 |  |  |  |  | 2021-12-07 | 1025 | 0 |  |  | 2889970 | 1025 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000368 | ABSA BOTHAVILLE- -ADDITONAL PLUG FOR SEC |  |  |  | Region 3 |  | Unknown | 1000-71573-01 | Unknown Building - not in our database |  |  |  |  | ASP-CR0313 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 0 |  |  |  | NOMNGANGAL | 2022-07-21 |  | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000368,"ONEVIEW":"Unknown","DATE01":"0000-00-00","DATE02":"0000-00-00","DATE03":"0000-00-00","DATE04":"0000-00-00","DATE05":"0000-00-00","DATE06":"0000-00-00","DATE07":"0000-00-00","DATE08":"0001-01-22","DATE09":"0001-03-08","DATE10":"0000-00-00","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"0000-00-00","FORECAST_END":"0000-00-00","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2Vk","RATING":""} |  |  |  | PHASE11 |  |  | Siyanda Dlamini | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000030794 | 5731.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000369 | Moffett Office Park- Replacement of Gene | Moffett Office Park- Replacement of Gene |  |  | National | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth |  | 2023-06-23 | 2023-12-15 |  | ASP-EC0315 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-05-31 | D | 41344.8 | 2023.06.08: Approved by Kobus JvR as per email 2023.06.06: Supported by Rob L |  | 2023-06-05 | 2023-06-08 | 41344.8 | Approved | {"MANDT":"111","REFERENCE":90000369,"ONEVIEW":"22937X","DATE01":"2023-04-14","DATE02":"2023-04-21","DATE03":"2023-05-12","DATE04":"2023-05-19","DATE05":"2023-06-09","DATE06":"2023-06-23","DATE07":"2023-07-14","DATE08":"2023-07-18","DATE09":"2023-07-27","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-23","FORECAST_END":"2023-07-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"ODAlIGNvbXBsZXRl","RATING":""} |  |  | 4500835562 | PHASE11 | 2023-06-23 | 2023-07-14 | LUCIA AMUNGA | Thea Spamers | 0 | 2023-05-29 | 2023-07-05 | 2023-05-23 | 2023-07-10 | 2023-06-13 | 35952 | 0 |  |  | C000090808 | 35952 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000370 | Ridgeside-Replacement of UPS Batteries x | Ridgeside-Replacement of UPS Batteries x |  |  | Region 3 | National | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga | Y | 2023-06-23 | 2023-12-15 |  | ASP-KZ0252 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  | F |  | LOUISR | 2023-05-31 | D | 465932.94 | 2023.06.08: Approved by Kobus JvR as per email 2023.06.06: Supported by Rob L |  | 2023-05-25 | 2023-06-08 | 465932.94 | Approved | {"MANDT":"111","REFERENCE":90000370,"ONEVIEW":"22460X","DATE01":"2023-04-14","DATE02":"2023-04-21","DATE03":"2023-05-12","DATE04":"2023-05-19","DATE05":"2023-06-09","DATE06":"2023-06-23","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-23","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000090812 | PHASE11 | 2023-06-23 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 | 2023-06-08 | 2023-06-16 | 2023-06-15 | 2023-06-21 | 2023-06-21 | 405159.08 | 0 |  |  | C000090812 | 405159.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000371 | Absa Roggebaai Lower Long - Dilaps Closu | Absa Roggebaai Lower Long - Dilaps Closu |  |  | Region 2 |  | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town |  | 2023-06-30 | 2023-08-31 |  | ASP-WC0285 | CRTD DLFL AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  |  |  | CEASARS | 2023-05-31 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-06-30 | 2023-08-31 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000372 | Absa Rawsonville - Dilaps | Absa Rawsonville - Dilaps |  |  | Region 2 | Western Cape | 77016X | 1000-70795-01 | 2 Brand Street-Brand St-Rawsonville | N | 2023-06-30 | 2023-08-31 |  | ASP-WC0286 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-05-31 | D | 225268.41 | Approved at CB/BTB | 100 | 2023-06-29 | 2023-06-29 | 225268.41 | Approved | {"MANDT":"111","REFERENCE":90000372,"ONEVIEW":"77016X","DATE01":"2023-05-30","DATE02":"2023-06-05","DATE03":"2023-06-19","DATE04":"2023-06-29","DATE05":"2023-06-29","DATE06":"2023-07-14","DATE07":"2023-07-31","DATE08":"2023-08-08","DATE09":"2023-09-22","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"154:6:14:10:0:15:17:8:45:26","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-14","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBdWcgRmluYWwgUE9DIFN1Ym1pdHRlZCB0byBmaW5hbmNlCjMxIEp1bHkgV29ya3MgQ29tcGxldGVkCjE5IEp1bCBXb3JrIG9uIHNpdGUgaW4gUHJvZ3Jlc3M=","RATING":""} |  |  | C000095207 | PHASE11 | 2023-07-14 | 2023-07-31 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-06-30 | 195885.57 | 0 |  |  | C000095207 | 195885.57 |  | 19797.13 |  | 0 | 0 |  | 0 |  | 0
90000373 | Absa Vanderbijlpark Plumbing pipes repai | Absa Vanderbijlpark Plumbing pipes repai |  |  | Region 1 |  | 77470X | 1000-70369-01 | Vanderbijlpark-FW Beyers St-Vanderbijlpark |  | 2023-06-01 | 2023-06-01 |  | ASP-GS0679 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-06-01 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000373,"ONEVIEW":"77470X","DATE01":"2023-03-23","DATE02":"2023-03-30","DATE03":"2023-04-20","DATE04":"2023-04-27","DATE05":"2023-05-18","DATE06":"2023-06-01","DATE07":"2023-06-01","DATE08":"2023-06-22","DATE09":"2023-08-06","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":60,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-01","FORECAST_END":"2023-06-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBkb25lIHRocm91Z2ggUE1P","RATING":""} |  |  |  | PHASE12 | 2023-06-01 | 2023-06-01 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000374 | Absa Koppies - Erection Entrance Ramp fo | Absa Koppies - Erection Entrance Ramp fo |  |  | Region 3 |  | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies |  | 2023-06-08 | 2023-06-15 |  | ASP-CR0442 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-02 | D | 0 |  | 60 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000374,"ONEVIEW":"78856X","DATE01":"2023-03-30","DATE02":"2022-04-07","DATE03":"2023-05-11","DATE04":"2023-06-02","DATE05":"2023-06-22","DATE06":"2023-06-13","DATE07":"2023-09-14","DATE08":"2023-09-29","DATE09":"2023-10-22","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"154:-357:399:22:20:-9:93:15:23:11","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-09-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDb21wbGV0ZWQsIEludm9pY2luZyBpbiBwcm9ncmVzcw==","RATING":""} |  |  |  | PHASE08 | 2023-06-13 | 2023-09-14 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000086507 | 91651.94 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000375 | Absa De Wagenweg Generator Major Service | Absa De Wagenweg Generator Major Service |  |  | Region 2 | Western Cape | 70650X | 1000-70785-01 | De Wagenweg Office Park Block B-Adam Tas Rd-Stellenbosch | U | 2023-06-30 | 2023-07-31 |  | ASP-WC0287 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-06-02 | D | 18011.67 |  | 1 | 2023-06-05 |  | 0 | 3 Aug Done via ABQT | {"MANDT":"111","REFERENCE":90000375,"ONEVIEW":"70650X","DATE01":"2023-06-02","DATE02":"2023-07-14","DATE03":"2023-08-21","DATE04":"2023-08-28","DATE05":"2023-09-18","DATE06":"2023-10-02","DATE07":"2023-11-02","DATE08":"2023-11-23","DATE09":"2024-01-07","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:42:38:7:21:14:31:21:45:26","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-02","FORECAST_END":"2023-11-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgSlVMWSBCQyBQQUNLIFdBUyBTVUJNSVRURUQgRk9SIEFQUFJPVkFMUy4gTk8gRkVFREJBQ0sgWUVU","RATING":""} |  |  |  | PHASE12 | 2023-08-20 | 2023-09-20 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000376 | Lea Glen Stores Replacement of gutters | Erect scaffolding incl certification and to remove existing gutters and down pipes Supply, deliver and install new 150 x 150 antirust and weatherproof box gutters with 150mm diameter downpipes. Security guard to be provided for duration of works. |  |  | Region 1 | Gauteng South | 76949X | 1000-70344-01 | Lea Glen-Amanda Ave Lea Glen-Florida | N | 2023-04-05 |  |  | ASP-GS0680 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-06-04 | D | 285101.03 | 2023.06.29: Approved by Conrad M | 100 | 2023-06-29 | 2023-06-29 | 285101.03 | Approved | {"MANDT":"111","REFERENCE":90000376,"ONEVIEW":"76949X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-05-15","DATE05":"2023-06-05","DATE06":"2023-06-19","DATE07":"2023-07-28","DATE08":"2023-08-18","DATE09":"2023-10-02","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:21:82:21:14:39:21:45:21","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-19","FORECAST_END":"2023-07-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C00009524 | PHASE11 | 2023-06-19 | 2023-07-28 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 256385.53 | 0 |  |  | C000095240 | 256385.53 |  | 25866 |  | 0 | 0 |  | 0 |  | 0
90000377 | Absa Towers North 2 Hydrotaps | ÃÂ¢ÃÂÃÂ¢ Supply, deliver and install 2 x G5 Hydro tap BC60 Classic Plus Chrome ÃÂ¢ÃÂÃÂ¢ Work to take place over 2 weekends. ÃÂ¢ÃÂÃÂ¢ Security guard to be provided for duration of works. |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2023-06-04 | 2023-06-04 |  | ASP-GS0681 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-06-04 | D | 160688.37 | 2023.06.29: Approved by Conrad M | 100 | 2023-06-29 | 2023-06-29 | 160688.37 | Approved | {"MANDT":"111","REFERENCE":90000377,"ONEVIEW":"77381X","DATE01":"2023-03-26","DATE02":"2023-04-02","DATE03":"2023-04-24","DATE04":"2023-05-01","DATE05":"2023-06-20","DATE06":"2023-07-04","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"158:7:22:7:50:14:0:21:45:22","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-04","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000095236 | PHASE11 | 2023-07-04 | 2023-08-21 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 139729.02 | 0 |  |  | C000095236 | 153682.78 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000378 | Absa Towers West 3 Hydrotaps | Absa Towers West 3 Hydrotaps |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | Y | 2023-06-02 | 2023-06-30 |  | ASP-GS0682 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-06-04 | D | 338631.42 | 2023.06.29: Approved by Conrad M | 100 | 2023-06-26 | 2023-06-29 | 338631.42 | Approved | {"MANDT":"111","REFERENCE":90000378,"ONEVIEW":"21526X","DATE01":"2023-03-24","DATE02":"2023-05-22","DATE03":"2023-06-12","DATE04":"2023-06-19","DATE05":"2023-07-10","DATE06":"2023-07-14","DATE07":"2023-08-24","DATE08":"2023-09-19","DATE09":"2023-11-03","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"221:59:21:7:21:4:41:26:45:9","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-14","FORECAST_END":"2023-08-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000095237 | PHASE11 | 2023-07-14 | 2023-08-24 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 294462.1 | 0 |  |  | C000095237 | 219237.98 |  | 30763.77 |  | 0 | 0 |  | 0 |  | 0
90000379 | Absa Eden Square Shopping (Ba Phalaborwa | Absa Eden Square Shopping (Ba Phalaborwa |  |  | Region 3 |  | 76709X | 1000-70515-01 | Eden Square Shopping Centre-Cnr Palm Ave & Mandela Dr-Phalaborwa |  | 2023-06-20 | 2023-06-28 |  | ASP-LP0165 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-05 | D | 370768.77 | Dilapidations - Revamp | 100 | 2023-05-29 | 2023-05-29 | 370768.77 |  | {"MANDT":"111","REFERENCE":90000379,"ONEVIEW":"76709X","DATE01":"2023-04-11","DATE02":"2023-04-18","DATE03":"2023-05-09","DATE04":"2023-05-16","DATE05":"2023-06-06","DATE06":"2023-06-20","DATE07":"2023-06-28","DATE08":"2023-07-19","DATE09":"2023-08-25","DATE10":"2023-09-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"172:7:21:7:21:14:8:21:37:28","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-20","FORECAST_END":"2023-06-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"SW52b2ljZXMgcmVxdWVzdGVkIGZyb20gc3VwcGxpZXJz","RATING":""} |  |  | C000089457-2 | PHASE11 | 2023-06-20 | 2023-06-28 | NANDE MAQUBELA | Juanita van Coller | 0 |  |  |  |  | 2023-06-05 | 0 | 0 |  |  | C000089457 | 322407.63 |  | 32706.25 |  | 0 | 0 |  | 0 |  | 0
90000380 | Absa Highlands Meadowdale | Install a security vehicle holding bay and pedestrian gate. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale | N | 2023-06-13 | 2023-07-04 |  | ASP-GN0201 | CRTD SETC: |  | false | false |  | Mponeng Mokoena |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-06-06 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 46565.51 |  | {"MANDT":"111","REFERENCE":90000380,"ONEVIEW":"22896X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBudW1iZXIgd2FzIHJhaXNlZCBmb3IgSU5TT0cgcmVxdWVzdCAtIEluc3RhbGwgYSBzZWN1cml0eSB2ZWhpY2xlIGhvbGRpbmcgYmF5IGFuZCBwZWRlc3RyaWFuIGdhdGUgaW4gbGluZSB3aXRoIHRoZSBjdXJyZW50IGFjY2Vzcy4=","RATING":""} |  |  | C000091052 | PHASE08 | 2023-06-13 | 2023-07-04 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-12 | 40491.75 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000381 | Absa Highlands Meadowdale | Absa Highlands Meadowdale Install two security floodlights / perimeter security lighting as per security findings |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale | N | 2023-06-13 | 2023-07-04 |  | ASP-GN0203 | CRTD SETC: |  | false | false |  | Mponeng Mokoena |  |  | 2023 |  | F |  | MOKOENAM2 | 2023-06-06 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 14921.25 |  | {"MANDT":"111","REFERENCE":90000381,"ONEVIEW":"22896X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBOdW1iZXIgd2FzIGNyZWF0ZWQgZm9yIElOU09HIHJlcXVlc3QgLSAgSW5zdGFsbCB0d28gc2VjdXJpdHkgZmxvb2RsaWdodHMgLyBwZXJpbWV0ZXIgc2VjdXJpdHkgbGlnaHRpbmcgYXMgcGVyIHNlY3VyaXR5IGZpbmRpbmdz","RATING":""} |  |  | C000091051 | PHASE08 | 2023-06-13 | 2023-07-04 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-06-12 | 12975 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000382 | Absa 15 Alice Lane | Absa 15 Alice Lane |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-06-13 | 2023-07-04 |  | ASP-GS0683 | CRTD: |  | false | false |  | Mponeng Mokoena |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-06-06 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000382,"ONEVIEW":"","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-06-13 | 2023-07-04 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000383 | Absa 8 Top Road Galv Carports | Absa 8 Top Road 1.Supply and install new galvanized steel structure including support beams. 2.Supply and install new Knittex 100 shade netting including tension cables and tensioners for all 45 double carports. 3. Supply and install new Knittex 100 shade netting including tension cables and tensioners for 2 single carports. 4.Remove all old rusted uprights from site. 5.Excavate and plant new galvanized uprights in concrete. 6.Remove old netting and steel from site. 7.Clean to site before handover to the client. |  |  | Region 1 | Gauteng South | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg | N | 2023-06-13 | 2023-07-04 |  | ASP-GS0684 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  | Installation of new carports | 2023 |  | L |  | MOKOENAM2 | 2023-06-06 | D | 1773654.64 |  | 60 | 2023-10-02 | 2023-10-03 | 1773654.64 | Approved at BTB committee. BFM PO issued to supplier. | {"MANDT":"111","REFERENCE":90000383,"ONEVIEW":"78451X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhcHByb3ZlZCBPQ0MgMDMvMTAvMjAyMyAKV0EmIFNGQSB0byBiZSBjb21waWxlZCBhbmQgc3VibWl0dGVkIEFic2EgTGVnYWwgZm9yIGFwcHJvdmFsIGFuZCBpc3N1aW5nIG9mIEFic2EgUE8uCjIwMjMuMTEuMDcgLUJGTSBQTyByZWNlaXZlZCAgYXdhaXRpbmcgQWJzYSBQTy4=","RATING":"Low"} |  |  | 4500871511 | PHASE06 | 2023-06-13 | 2023-07-04 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | 2023-10-18 |  |  |  |  | 1315919.5 | 0 |  |  |  | 0 |  | 154059.84 |  | 0 | 0 |  | 0 |  | 0
90000384 | Absa Towers Vanderbijlpark | Absa Towers Vanderbijlpark |  |  | Region 1 |  | 77470X | 1000-70369-01 | Vanderbijlpark-FW Beyers St-Vanderbijlpark | N | 2023-06-13 | 2023-07-04 |  | ASP-GS0685 | CRTD SETC: |  | false | false |  | Mponeng Mokoena |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-06-06 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000384,"ONEVIEW":"77470X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-13 | 2023-07-04 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000385 | Absa Alex Plaza | Absa Alex Plaza |  |  | Region 1 |  | 78224X | 1000-70391-01 | Alex Plaza-3rd St-Wynberg | N | 2023-06-13 | 2023-07-04 |  | ASP-GS0686 | CRTD SETC: |  | false | false |  | Mponeng Mokoena |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-06-06 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000385,"ONEVIEW":"36279X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-06-13 | 2023-07-04 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000386 | Various- Replacement of UPS batteries GN | Various- Replacement of UPS batteries GN |  |  | National | Gauteng North | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | Y | 2023-06-29 | 2023-12-15 |  | ASP-N00055 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  | L |  | LOUISR | 2023-06-06 | D | 0 | 2023.06.15: Approved by Kobus JvR as per email 2023.06.13: Supported by Rob L |  | 2023-06-15 | 2023-06-15 | 286718.58 | Approved | {"MANDT":"111","REFERENCE":90000386,"ONEVIEW":"21526X","DATE01":"2023-04-20","DATE02":"2023-04-27","DATE03":"2023-05-18","DATE04":"2023-05-25","DATE05":"2023-06-15","DATE06":"2023-06-29","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":30,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-29","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000093144 | PHASE11 | 2023-06-29 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 |  |  |  |  | 2023-06-21 | 249320.5 | 0 |  |  | C000093144 | 249320.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000387 | Various Sites WC - Lanterns | Various Sites WC - Emergency Backup Lanterns - 269 x WACO LED Rechargeable Lanterns |  |  | Region 2 | Western Cape | Various WC | 1000-70759-01 | Various WC Sites | U | 2023-06-30 |  |  | ASP-N00056 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2023 |  | U |  | LOUISR | 2023-06-06 | D | 89377.39 | 2023.06.08: Approved by Kobus JvR as per email 2023.06.05: Approved Out of Cyle by Kobus JvR as per email | 100 | 2023-06-01 | 2023-06-08 | 89377.39 | Approved | {"MANDT":"111","REFERENCE":90000387,"ONEVIEW":"Various WC","DATE01":"2023-06-01","DATE02":"2023-06-01","DATE03":"2023-06-01","DATE04":"2023-06-01","DATE05":"2023-06-01","DATE06":"2023-06-09","DATE07":"2023-06-14","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:0:0:8:5:33:45:27","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-09","FORECAST_END":"2023-06-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTcgSnVseSBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000090163-2 | PHASE11 | 2023-06-09 | 2023-06-14 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-06-07 | 77719.47 | 0 |  |  | C000090163 | 77719.47 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000388 | Germinston Dilaps/Reinstatement | Germinston Dilaps/Reinstatement |  |  | Region 1 |  | 70654X | 1000-70237-01 | United House-Cnr Meyer & Library St-Germiston | N | 2023-06-06 | 2023-06-06 |  | ALP-GS0062 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2023-06-29 | GAMIETR | 2023-06-06 | D | 181074.14 |  | 100 | 2023-07-17 | 2023-07-25 | 181074.14 |  | {"MANDT":"111","REFERENCE":90000388,"ONEVIEW":"70654X","DATE01":"2023-03-28","DATE02":"2023-04-04","DATE03":"2023-04-25","DATE04":"2023-05-02","DATE05":"2023-05-23","DATE06":"2023-06-06","DATE07":"2023-06-06","DATE08":"2023-06-27","DATE09":"2023-08-11","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":0,"PROG06":0,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":57,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-06","FORECAST_END":"2023-06-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000099862 | PHASE11 | 2023-06-06 | 2023-06-06 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 157455.77 | 0 |  |  |  | 0 |  | 16314.65 |  | 0 | 0 |  | 0 |  | 0
90000389 | Various EC- Generator starter batteries | Various EC- Generator starter batteries |  |  | National |  | Unknown | 1000-70027-01 | Unknown Building - not in our database |  | 2023-06-30 |  |  | ASP-N00057 | REL BUDG AVAC RESA SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-06-08 | D | 0 | 2023.06.15: Approved by Kobus JvR as per email 2023.06.13: Supported by Rob L |  | 2023-06-15 | 2023-06-15 | 77650.27 | Approved |  |  |  | C000093146 | PHASE08 | 2023-06-30 | 2023-07-30 | RODERICK NEVAY | Thea Spamers | 0 |  |  |  |  | 2023-06-21 | 67521.97 | 48649.99 |  |  | C000140524 | 18871.98 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000390 | Bridge Park - Balcony - Balcony - Balustrade / Signage | Bridge Park - Balcony - Balustrade / Signage |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2023-12-31 |  |  | ASP-WC0288 | REL BUDG AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-06-08 | D | 17723.8 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B | 100 | 2023-07-20 | 2023-07-20 | 17723.8 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000390,"ONEVIEW":"36225X","DATE01":"2023-01-19","DATE02":"2023-04-28","DATE03":"2023-07-07","DATE04":"2023-07-13","DATE05":"2023-07-20","DATE06":"2023-09-02","DATE07":"2024-03-21","DATE08":"2024-06-06","DATE09":"2024-07-21","DATE10":"2024-07-31","DATE11":"2024-01-28","DATE12":"2024-01-28","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"377:99:70:6:7:44:201:77:45:3","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-02","FORECAST_END":"2024-03-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIC0gUXVvdGVzIHJlcXVlc3RlZCBmb3IgZml4ZWQgUSBSYWlscyAtIFNpZ25hZ2UgZGVzaWduIHByb3Bvc2FsIGluIHJldmlzaW9uIHdpdGggc3VwcGllcgoxMiBGZWIgLSBQTSB0byBvYnRhaW4gY29zdHMgZm9yIFFyYWlscyBhbmQgZm9sbG93IHVwIHJlIHNpZ25hZ2UgcmVxdWVzdGVkIGFzIHBlciBtYWlsIGZyb20gQWJzYSBFbmdpbmVlcmluZwoyMiBKYW4gLSBQTSB0byBvYnRhaW4gcXVvdGVzIHRvIHJhaXNlIGJhbHVzdHJhZGUKMTggSmFuIC0gUE0gdG8gZm9sbG93IHVwIHdpdGggU2lnbmFnZSBWZW5kb3IgYW5kIEJyb2xsIHJlIExMIEFwcHJvdmFsCjExIERlYyBQTSB0byBmb2xsb3cgdXAgd2l0aCBTJkcgYW5kIEJyb2xsCjQgRGVjIC0gUE0gdG8gZm9sbG93IHVwIHdpdGggUyZHIGFuZCBCcm9sbAoyNyBOb3YgV2lsbCBmb2xsb3cgdXAgb24gdGhlIHVwZGF0ZWQgYXJ0d29yay4gWWVsbG93IGxpbmUgYXBwcm92YWwgcGVuZGluZyBhcyB3ZWxsIGZyb20gTEwKMjAgTm92IGluZm9ybWF0aW9uIHRvIGJlIHNlbnQgdG8gQWJzYSBPSFMgZm9yIGFwcHJvdmFsCjEwIE5vdiAtIFBlbmRpbmcgcmV2aXNlZCBhcnR3b3JrIGFuIExMIGFwcHJvdmFsCjYgTm92IC0gUE0gdG8gZm9sbG93IHVwIHJlIHJldmlzZWQgYXJ0d29yayB1c2luZyBTdGljayBNZW4gYW5kIExMIGFwcHJvdmFsIGZvciB5ZWxsb3cgbGluZS4KMzEgT2N0IERlc2lnbnMgc2hhcmVkIHdpdGggQWJzYSBEZXNpZ24gZm9yIGFwcHJvdmFsLCBMTCBwZXJtaXNzaW9uIHJlcXVlc3RlZCB0byBwYWludCBjb250aW51ZXMgeWVsbG93IHN0cmlwZSAKMjcgT2N0IElsbHVzdHJhdGlvbnMgcmVxdWVzdGVkIGZyb20gU2lnbmFnZSBWZW5kb3IsIHRvIGJlIHN1Ym1pdHRlZCB0byBPSFMgZm9yIEFwcHJvdmFsCjIzIE9jdCAtIFNuYWcgUmVtZWRpYXRlZCByZSBsaW5lcyAxOXRoIE9jdCBWUCB0byBJbnNwZWN0IGluIG9yZGVyIHRvIFNpZ24gT2ZmCjAyIE9jdCBDb21wbGV0ZWQgMjggU2VwdCAtIEludm9pY2luZyAvIFBPQyB0byBmb2xsb3cKMjIgU2VwdCAtIFN0aWxsIHdldCBwcm9wb3NlZCBjb21wbGV0aW9uIGJ5IDMwIFNlcHQKMTggU2VwdCBSYWluZWQgMTV0aC8xNnRoIHRvIG1vbml0b3Igd2VhdGhlciB0byBzZWUgd2hlbiBpdCBjYW4gYmUgZG9uZSB0aGlzIHdlZWsgYXMgZXhwZWN0aW5nIGZhaXIgd2VhdGhlci4KMTEgU2VwdCBQbGFubmVkIGZvciB0aGUgMTZ0aCBTZXB0IFdlYXRoZXIgc3RpbGwgYSBjaGFsbGVuZ2UKNCBTZXB0IC0gRGVjYWxzIGluc3RhbGxlZC4gV2VhdGhlciBEZXBlbmRlbnQuIFllbGxvdyB0YXBlIHRvIGJlIGluc3RhbGxlZCBvbiAxNiBTZXB0ZW1iZXIuCjE4IEF1ZyBQcm9wb3NlZCBkYXRlIGlzIDIgU2VwdAoxNCBBdWcgUE0gdG8gZm9sbG93IHVwIHdpdGggQWJzYSBPSFMgcmUgbGVnYWwgaW5wdXRzCjcgQXVnIC0gQWJzYSBPSFMgcmVzcG9uc2UgcGVuZGluZwoyNyBKdWwgQlYgUE8ncyBpc3N1ZWQgNDUwMDg0NjAxNSBNaWxlIFN0b25lLCA0NTAwODQ1OTc2IFMmRwoyNCBKdWx5IEFic2EgUE8gQzAwMDA5OTY2MCByZWNlaXZlZCBCViBQTydzIHJlcXVlc3RlZAoyMCBKdWx5IEFwcHJvdmVkIENCMjcgU2lnbmVkIERlY2sgUGVuZGluZwoxMyBKdWx5IFN1Ym1pdHRlZCBmb3IgQ0IyNwozIEp1bHkgLSBDdXJyZW50bHkgd2l0aCBBYnNhIExhbmd1YWdlIGZvciBhcHByb3ZhbCBvZiBzaWduYWdlCjI4IEp1bmUgUE0gdG8gZm9sbG93IHVwIHdpdGggZGVzaWduIHRlYW0gcmUgcmV2aXNlZCBBcnR3b3JrIGFwcHJvdmFsCjE5IEp1bmUgLSBQTSB0byBmb2xsb3cgdXAgd2l0aCBTJkcgcmUgdXBkYXRlZCBBcnR3b3JrIHRvIGJlIGNoZWNrZWQgYnkgRGVzaWduIGFuZCBPSFMKMTVKdW5lIC0gUE0gdG8gZm9sbG93IHVwIHdpdGggTWF4IE51bWJlcnMgIGFuZCBXZWF0aGVyIE1lc3NhZ2UKCjUgSnVuZSAtIFJlcXVlc3QgcXVvdGF0aW9ucyBmb3IgTWFya2luZ3MsIGFuZCBPSFMgcmUgc2lnbmFnZQoyMiBNYXkgLSBSZXF1ZXN0IHF1b3RhdGlvbnMgZm9yIE1hcmtpbmdzLCBhbmQgT0hTIHJlIHNpZ25hZ2UKOCBNYXkgLSBFbWFpbCB0byBiZSBzZW50IHRvIENsZW9uYSByZSBPSFMgYXNwZWN0cwoyNCBBcHJpbCAtIFBNIHRvIGNoZWNrIHdpdGggT0hTIHJlIExpbWl0cyBhbmQgU2lnbmFnZQoxNyBBcHJpbCAtIE5vIG9mIHBlb3BsZSB0byBiZSBjYWxjdWxhdGVkCjMgQXByaWwgUE0gdG8gY2hlY2sgYW5kIGFkdmlzZSBpbiB0ZXJtcyBvZiBpbnZlc3RpZ2F0aW9uIGJ5IEZNCjI3IE1hciBQTSB0byBmb2xsb3cgdXAgcmUgbG9hZHMgYW5kIE9IUyBndWlkYW5jZQoxMyBNYXIgLSBQbSB0byBjaGVjayB3aXRoIEZNIGFuZCBFbmdpbmVlcmluZyByZSBubyBvZiBwZXJzb25zIGFuZCBhZGRpdGlvbmFsIHNpZ25zIG9uIHRoZSBiYWx1c3RyYWRlICsgbm8gZ28gem9uZQoyNyBGZWIgLSBQTSB0byBjaGVjayB3aXRoIEVuZ2luZWVyaW5nIHJlIGxpbWl0CjYgRmViIC0gRm9sbG93IHVwIG9uIGNvbXBsaWFuY2UgQnJvbGwgdG8gY29uZmlybSBmcm9tIExMIGFuZCB0aGUgTG9hZGluZyB0byBiZSBjb25maXJtZWQgaW4gb3JkZXIgdG8gY3JlYXRlIHNpZ25hZ2UKMjMgSmFuIC0gVG8gYmUgY29uZmlybWVkIHdpdGggTEwgaW4gdGVybXMgb2YgY29tcGxpYW5jZS4gSVNPMTA0MDAgaW5kaWNhdGVzIGl0IGlzIGNvbXBsaWFudC4gUE0gdG8gY2hlY2sgcmUgbG9hZGluZyBhcyBzaWduYWdlIHJlcXVpcmVkIGF0IGV4aXQgZG9vcnMu","RATING":"Low"} |  |  | C000099660 | PHASE07 | 2023-09-02 | 2024-03-21 | Rick Nevay | Floyd Mofokeng | 23000432 |  |  |  |  | 2023-07-24 | 15412 | 0 |  |  | C000099660 | 15412 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000391 | Absa Mimosa Mall - Supply of Reupholster | Absa Mimosa Mall - Supply of Reupholster |  |  | Region 3 |  | 78545x | 1000-71542-01 | Absa Mimosa Mall | N | 2023-06-29 |  |  | ASP-CR0443 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | L | 2024-06-29 | NOMNGANGAL | 2023-06-09 | D | 0 |  | 60 |  |  | 6026 |  | {"MANDT":"111","REFERENCE":90000391,"ONEVIEW":"78545x","DATE01":"2023-04-20","DATE02":"2023-05-24","DATE03":"2023-06-24","DATE04":"2023-06-08","DATE05":"2023-06-21","DATE06":"2023-07-06","DATE07":"2023-07-19","DATE08":"2023-09-21","DATE09":"2023-10-27","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"194:34:31:-16:13:15:13:64:36:28","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-06","FORECAST_END":"2023-07-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGludm9pY2luZyBpbiBwcm9ncmVzcw==","RATING":""} |  |  |  | PHASE11 | 2023-07-06 | 2023-07-19 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 5240 | 0 |  |  | C000093839 | 5240 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000392 | Absa Whitehouse Centre- Install of Diese | Absa Whitehouse Centre- Install of Diese |  |  | Region 3 | [5 empty] | 2023-07-20 |  |  | ASP-CR0444 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-07-20 | 2023-08-19 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000393 | Absa Bank Hopetown - Install Electrical | Absa Bank Hopetown - Install Electrical |  |  | Region 3 |  | Unknown | 1000-71353-01 | Unknown Building - not in our database |  | 2023-07-26 |  |  | ASP-CR0445 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-09 | D | 0 | 2023.06.22: Approved by Kobus JvR as per email 2023.06.20: Supported by Rob L | 100 | 2023-06-22 | 2023-06-22 | 10893.32 | Approved | {"MANDT":"111","REFERENCE":90000393,"ONEVIEW":"Unknown","DATE01":"2023-05-17","DATE02":"2023-05-24","DATE03":"2023-06-14","DATE04":"2023-06-21","DATE05":"2023-07-12","DATE06":"2023-07-26","DATE07":"2023-08-25","DATE08":"2023-09-15","DATE09":"2023-10-30","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":92,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-26","FORECAST_END":"2023-08-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000093838 | PHASE11 | 2023-07-26 | 2023-08-25 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-25 | 9472.45 | 0 |  |  | C000093838 | 9472.45 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000394 | Absa De Aar - Install Electrical Plug AT | Absa De Aar - Install Electrical Plug AT |  |  | Region 3 |  | Unknown | 1000-71361-01 | Unknown Building - not in our database |  | 2023-07-27 |  |  | ASP-CR0446 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-09 | D | 0 | 2023.06.22: Approved by Kobus JvR as per email 2023.06.20: Supported by Rob L | 100 | 2023-06-22 | 2023-06-22 | 17761.81 | Approved | {"MANDT":"111","REFERENCE":90000394,"ONEVIEW":"Unknown","DATE01":"2023-05-18","DATE02":"2023-05-25","DATE03":"2023-06-15","DATE04":"2023-06-22","DATE05":"2023-07-13","DATE06":"2023-07-27","DATE07":"2023-08-26","DATE08":"2023-09-16","DATE09":"2023-10-31","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-27","FORECAST_END":"2023-08-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IEludm9pY2VkLg==","RATING":""} |  |  | C000093836 | PHASE11 | 2023-07-27 | 2023-08-26 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-25 | 15445.05 | 0 |  |  | C000093836 | 15445.05 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000395 | Absa Bloemhof - Install dedicated power | Absa Bloemhof - Install dedicated power |  |  | Region 3 |  | Unknown | 1000-71314-01 | Unknown Building - not in our database |  | 2023-07-27 |  |  | ASP-CR0447 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-09 | D | 0 | 2023.06.22: Approved by Kobus JvR as per email 2023.06.20: Supported by Rob L | 100 | 2023-06-22 | 2023-06-22 | 24709.65 | Approved | {"MANDT":"111","REFERENCE":90000395,"ONEVIEW":"Unknown","DATE01":"2023-05-18","DATE02":"2023-05-25","DATE03":"2023-06-15","DATE04":"2023-06-22","DATE05":"2023-07-13","DATE06":"2023-07-27","DATE07":"2023-08-26","DATE08":"2023-09-16","DATE09":"2023-10-31","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-27","FORECAST_END":"2023-08-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  | C000093835 | PHASE11 | 2023-07-27 | 2023-08-26 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-25 | 21486.65 | 0 |  |  | C000093835 | 21486.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000396 | Absa Auckland Park CC Replacement of Compressor on Chiller 1 | Replacement of compressor on Chiller 1 Replacement of the cylinder refrigerant Test and commission. |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-06-15 | 2023-06-30 |  | ASP-GS0687 | CRTD: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | MOKOENAM2 | 2023-06-09 | D | 150443.46 |  | 100 | 2023-09-07 | 2023-09-07 | 150443.46 |  | {"MANDT":"111","REFERENCE":90000396,"ONEVIEW":"76849X","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-01","DATE06":"2023-06-15","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-15","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000110303 | PHASE09 | 2023-10-02 | 2023-10-17 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 |  |  |  |  | 2023-09-13 | 130820.4 | 0 |  |  |  | 0 |  | 13653.16 |  | 0 | 0 |  | 0 |  | 0
90000397 | Absa Raisethorpe - Installation of Blind | Absa Raisethorpe - Installation of Blind |  |  | Region 3 |  | Unknown | 1000-71195-01 | Unknown Building - not in our database |  | 2023-07-06 |  |  | ASP-KZ0253 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-09 | D | 0 | 2023.06.15: Approved by Conrad M as per email 2023.06.13: Supported by Leko N & Ilana vdW |  | 2023-06-15 | 2023-06-15 | 9691.05 | Approved |  |  |  | C000092846 | PHASE10 | 2023-07-06 | 2023-07-21 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-06-20 | 8427 | 0 |  |  | C000092846 | 8427 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000398 | Absa Vryheid - Water Ingress Repairs (In | Absa Vryheid - Water Ingress Repairs (In |  |  | Region 3 |  | 77113X | 1000-71614-01 | Absa Vryheid-Church St-Vryheid |  | 2023-07-27 | 2023-07-28 |  | ASP-KZ0254 | CRTD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-09 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-07-27 | 2023-07-28 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000399 | Cradock Heights (Rosebank Mall) | To fit a diameter of 450mm podded sound attenuator to the return air of the evaporator unit complete with offset Duct return air box offset and a new filter box Test and commission the system. |  |  | Region 1 | Gauteng South | 36280X | 1000-70200-01 | Cradock Heights-Cradock Ave-Johannesburg | N | 2023-06-15 | 2023-06-30 |  | ASP-GS0688 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-06-11 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 38216.5 | Approved | {"MANDT":"111","REFERENCE":90000399,"ONEVIEW":"36280X","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-07-31","DATE06":"2023-08-14","DATE07":"2023-08-29","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"2023-12-15","DATE12":"2023-12-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:7:21:7:81:14:15:63:45:26","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-14","FORECAST_END":"2023-08-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUHJvamVjdCBjb21wbGV0ZS4gQXdhaXRpbmcgaW52b2ljZSAmIFNGQyBmb3IgZmluYWwgUE9DLg==","RATING":""} |  |  | C000100121 | PHASE08 | 2023-08-14 | 2023-08-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-26 | 43948.98 | 0 |  |  | C000100121 | 33231.74 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000400 | Alice Lane South Refurbishment of 3rd floor client suite reception desk | â¢ Remove existing screen enclosures. â¢ Manufacture and fit new screen enclosures on the existing reception desk as per specification â¢ On-site security guard for the duration of the work. â¢ Paint white to match the existing finish and make good |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-06-15 | 2023-06-30 |  | ASP-GS0689 | REL BUDG RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L | 2030-04-29 | MOKOENAM2 | 2023-06-11 | D | 29095 | 2023.06.15: Approved by Conrad M as per email 2023.06.13: Supported by Rhulani N as per email | 100 | 2023-06-12 | 2023-06-15 | 29095 | Approved | {"MANDT":"111","REFERENCE":90000400,"ONEVIEW":"35041X","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-01","DATE06":"2023-06-15","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-15","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000092819 | PHASE08 | 2023-06-15 | 2023-06-30 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-06-20 | 29095 | 0 |  |  | C000092819 | 25300 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000401 | Absa Towers North - Integration of UPS | Absa Towers North - Integration of UPS |  |  | Region 1 |  | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2023-06-15 | 2023-06-30 |  | ASP-GS0690 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | MOKOENAM2 | 2023-06-11 | D | 200638.25 | 2023.06.22: Approved by Kobus JvR as per email 2023.06.20: Supported by Rob L | 100 | 2023-06-22 | 2023-06-22 | 200638.25 | Approved | {"MANDT":"111","REFERENCE":90000401,"ONEVIEW":"77381X","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-01","DATE06":"2023-06-15","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-15","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000093834 | PHASE07 | 2023-08-15 | 2023-09-15 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-25 | 174468.04 | 0 |  |  | C000140518 | 158607.31 |  | 18239.84 |  | 0 | 0 |  | 0 |  | 0
90000402 | Absa Vaal Mall - Installation of UPS | Absa Vaal Mall - Installation of UPS |  |  | Region 1 | Gauteng South | 77152X | 1000-70350-01 | Vaal Mall-Cnr Barrage Rd & Rossini Blvd-Vanderbijlpark | N | 2023-06-15 | 2023-06-30 |  | ASP-GS0691 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | MOKOENAM2 | 2023-06-11 | D | 0 | 2023.06.22: Approved by Kobus JvR as per email 2023.06.20: Supported by Rob L | 100 | 2023-06-22 | 2023-06-22 | 71918.13 | Approved | {"MANDT":"111","REFERENCE":90000402,"ONEVIEW":"77152X","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-01","DATE06":"2023-06-15","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-15","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000093550 | PHASE09 | 2023-06-15 | 2023-06-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-23 | 71918.13 | 0 |  |  | C000140520 | 62537.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000403 | Absa Warrenton - Installation of teller | Absa Warrenton - Installation of teller |  |  | Region 3 | [5 empty] | 2023-07-28 |  |  | ASP-CR0448 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-07-28 | 2023-08-27 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000404 | Absa Viljoenskroon - Install New Booster | Absa Viljoenskroon - Install New Booster |  |  | Region 3 |  | 78481X | 1000-71540-01 | Viljoenskroon-Cnr Engelbrecht & Church St-Viljoenskroon |  | 2023-07-28 |  |  | ASP-CR0449 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  | 2022-09-29 | NOMNGANGAL | 2023-06-12 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000404,"ONEVIEW":"78481X","DATE01":"2023-05-19","DATE02":"2023-05-26","DATE03":"2023-06-16","DATE04":"2023-06-23","DATE05":"2023-07-14","DATE06":"2023-07-28","DATE07":"2023-08-27","DATE08":"2023-09-17","DATE09":"2023-11-01","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":0,"PROG04":0,"PROG05":1,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":5,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-28","FORECAST_END":"2023-08-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxsZWQ=","RATING":""} |  |  |  | PHASE03 | 2023-07-28 | 2023-08-27 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000405 | 270 Republic Road - Fire Door | 270 Republic Road - Fire Door |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-06-12 | 2023-06-12 |  | ASP-GS0692 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-06-12 | D | 0 | 2023.06.29: Approved by Conrad M 2023.06.28: Supported by Winston P | 100 | 2023-06-29 | 2023-06-29 | 27774.72 | Approved | {"MANDT":"111","REFERENCE":90000405,"ONEVIEW":"21335X","DATE01":"2023-04-03","DATE02":"2023-04-10","DATE03":"2023-05-01","DATE04":"2023-05-08","DATE05":"2023-07-20","DATE06":"2023-08-03","DATE07":"2023-08-31","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"2023-12-15","DATE12":"2023-12-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"211:7:21:7:73:14:28:61:45:26","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-03","FORECAST_END":"2023-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUmVjZWl2ZWQgaW52b2ljZSBmcm9tIHN1cHBsaWVyLiBGaW5hbCBQT0MgaW4gcHJvZ3Jlc3Mu","RATING":""} |  |  | C000095208 | PHASE08 | 2023-08-03 | 2023-08-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 27774.72 | 0 |  |  | C000095208 | 24151.93 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000406 | Towers West - Re-Compact Paving | Supply paving bricks, paving sand and compacting equipment Compact and install paving |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-06-15 | 2023-06-30 |  | ASP-GS0693 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | MOKOENAM2 | 2023-06-12 | D | 14836.43 | 2023.06.21: Approved by Conrad M as per email 2023.06.20: Supported by Winston P | 100 | 2023-06-19 | 2023-06-22 | 14836.43 | Approved | {"MANDT":"111","REFERENCE":90000406,"ONEVIEW":"21526X","DATE01":"2023-04-06","DATE02":"2023-04-13","DATE03":"2023-05-04","DATE04":"2023-05-11","DATE05":"2023-06-22","DATE06":"2023-07-06","DATE07":"2023-07-29","DATE08":"2023-08-11","DATE09":"2023-09-25","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:7:21:7:42:14:23:13:45:26","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-06","FORECAST_END":"2023-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000096796 | PHASE11 | 2023-07-06 | 2023-08-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-10 | 148836.43 | 0 |  |  | C000096796 | 8728.4 |  | 1348.77 |  | 0 | 0 |  | 0 |  | 0
90000407 | Absa Towers North - Remedial Work SATT | Remediate the damages to the parking Replace sensors, Control card, PCB and rewire circuits. |  |  | Region 1 |  | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2023-06-15 | 2023-06-30 |  | ASP-GS0694 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | MOKOENAM2 | 2023-06-12 | D | 0 |  | 1 | 2023-06-12 |  | 0 |  | {"MANDT":"111","REFERENCE":90000407,"ONEVIEW":"77381X","DATE01":"2023-04-06","DATE02":"2023-09-29","DATE03":"2023-10-20","DATE04":"2023-10-27","DATE05":"2023-11-17","DATE06":"2023-12-01","DATE07":"2023-12-16","DATE08":"2024-01-06","DATE09":"2024-02-20","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:176:21:7:21:14:15:21:45:26","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-01","FORECAST_END":"2023-12-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RmluYWxpemluZyBzY29wZSB3aXRoIEVTTXM=","RATING":""} |  |  |  | PHASE12 | 2023-12-01 | 2023-12-16 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000408 | Absa Whitehouse (Stanger) - Diesel Tank | Absa Whitehouse (Stanger) - Diesel Tank |  |  | Region 3 |  | Unknown | 1000-71201-01 | Unknown Building - not in our database |  | 2023-06-29 |  |  | ASP-KZ0255 | CLSD BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-12 | D | 0 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Rob L |  | 2023-07-13 | 2023-07-13 | 94211.71 | Approved |  |  |  | C000124777 | PHASE11 | 2023-06-29 | 2023-07-11 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-20 | 81923.23 | 0 |  |  | C000095778 | 81923.23 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000409 | Forest Hill Dilaps | Dilapse. 1.Removal of all TV Screens and projectors. 2.Removal of all Safes 3.Removal of Mantrap Door 4.Removal of Money delivery tubes systems. 5.Removal of all cameras. 6.Removal of the security system and access control. 7.Disconnecting the UPS system and delivering to stores. 8.Collection and delivery of furniture from Absa stores to Swing space 9,Disposal of Confidential documentation. |  |  | Region 1 | Gauteng North | 35102X | 1000-70085-01 | Forest Hill City Mall-Forrest Beech St-Pretoria | N | 2023-06-13 | 2023-06-13 |  | ASP-GN0204 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-06-13 | D | 77553.61 | Approved at CB/BTB | 100 | 2023-06-14 | 2023-06-19 | 77553.62 | Approved | {"MANDT":"111","REFERENCE":90000409,"ONEVIEW":"35102X","DATE01":"2023-04-04","DATE02":"2023-04-30","DATE03":"2023-06-07","DATE04":"2023-06-12","DATE05":"2023-06-16","DATE06":"2023-06-13","DATE07":"2023-06-30","DATE08":"2023-07-21","DATE09":"2023-09-04","DATE10":"2023-09-30","DATE11":"2023-09-04","DATE12":"2023-09-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMzogUHJvamVjdCBjb21wbGV0ZS4gSXNzdWVzLiBzb21lIHdvcmsgd2FzIGRvbmUgd2l0aG91dCBQT3Mu","RATING":"Low"} |  |  | C000092847 | PHASE09 | 2023-06-13 | 2023-06-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-20 | 77553.62 | 0 |  |  | C000092847 | 80014.18 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000410 | 270 Republic Road Smart Water Meter Installation | 270 Republic Road Smart Water Meter Installation |  |  | Energy | Gauteng | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-06-13 | 2023-06-13 |  | ASP-GS0695 | CLSD CNF BUDG ISBD AVAC RESA SETC: |  | false | false |  | Wesigye Mukuru |  |  | 2023 |  |  |  | GAMIETR | 2023-06-13 | D | 33460.18 | 2023.06.08: Approved by Kobus JvR as per email 2023.06.06: Supported by Rob L | 100 | 2023-06-02 | 2023-06-08 | 33460.18 | Approved | {"MANDT":"111","REFERENCE":90000410,"ONEVIEW":"21335X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-07-06","DATE08":"2023-07-11","DATE09":"2023-07-31","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"149:7:21:7:21:14:23:5:20:13","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-07-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJhY3RpY2FsIGNvbXBsZXRpb24gcmVhbGl6ZWQgb24gNnRoIEp1bHkgIDIwMjMuIEZpbmFsIGludm9pY2luZyBhbmQgZmluYWwgYWNjb3VudCBzdWJtaXR0ZWQgdGhlcmVmb3JlIHByb2plY3QgY2xvc2VkLg==","RATING":"Low"} |  |  | C000091796 | PHASE11 | 2023-06-13 | 2023-07-06 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-14 | 29095.81 | 0 |  |  | C000091796 | 29095.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000411 | Absa East Rand Mall Dilaps | Absa East Rand Mall Dilaps |  |  | Region 1 | Gauteng South | 78283X | 1000-70398-01 | East Rand Mall-Bentel Ave-Boksburg | N | 2023-06-13 | 2023-06-13 |  | ASP-GS0696 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-06-13 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 42622.29 |  | {"MANDT":"111","REFERENCE":90000411,"ONEVIEW":"76420X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-06-13","DATE08":"2023-07-04","DATE09":"2023-08-18","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-06-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgUE9DIHNlbnQgZm9yIHNpZ24tb2ZmIGJ5IENsaWVudCAu","RATING":"Low"} |  |  | C000092244 | PHASE11 | 2023-06-13 | 2023-06-13 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-15 | 42622.29 | 0 |  |  | C000092244 | 37062.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000412 | Absa Koppies - UPS Replacement | Absa Koppies - UPS Replacement |  |  | Region 3 |  | Unknown | 1000-71559-01 | Unknown Building - not in our database |  | 2023-07-06 |  |  | ASP-CR0450 | CLSD BUDG AVAC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 0 | 2023.06.22: Approved by Kobus JvR as per email 2023.06.20: Supported by Rob L | 100 | 2023-06-22 | 2023-06-22 | 151383.44 | Approved | {"MANDT":"111","REFERENCE":90000412,"ONEVIEW":"Unknown","DATE01":"2023-04-27","DATE02":"2023-05-04","DATE03":"2023-05-25","DATE04":"2023-06-01","DATE05":"2023-06-22","DATE06":"2023-07-06","DATE07":"2023-08-05","DATE08":"2023-08-26","DATE09":"2023-10-10","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":92,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-06","FORECAST_END":"2023-08-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEludm9pY2luZyBpbiBwcm9qZWN0Lg==","RATING":""} |  |  | C000093837 | PHASE11 | 2023-07-06 | 2023-08-05 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-25 | 131637.77 | 0 |  |  | C000093837 | 131637.77 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000413 | Absa Southern Life (Mangaung) - UPS Repl | Absa Southern Life (Mangaung) - UPS Repl |  |  | Region 3 | [5 empty] | 2023-08-17 |  |  | ASP-CR0451 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-17 | 2023-09-16 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000414 | Absa Bultfontein -HVAC Replacement | Absa Bultfontein -HVAC Replacement |  |  | Region 3 | [5 empty] | 2023-08-23 |  |  | ASP-CR0452 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-23 | 2023-09-22 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000415 | Absa Victoria West - Extension Rental Ge | Absa Victoria West - Extension Rental Ge |  |  | Region 3 |  | Unknown | 1000-71320-01 | Unknown Building - not in our database |  | 2023-09-29 |  |  | ASP-CR0453 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 0 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Rob L | 100 | 2023-07-06 | 2023-07-06 | 85119.03 | Approved | {"MANDT":"111","REFERENCE":90000415,"ONEVIEW":"Unknown","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-10-29","DATE08":"2023-11-19","DATE09":"2024-01-03","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-10-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEF3YWl0aW5nIGludm9pY2luZy4=","RATING":""} |  |  | C000096795 | PHASE11 | 2023-09-29 | 2023-10-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-07-10 | 74016.55 | 0 |  |  | C000096795 | 74016.55 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000416 | Absa Carnarvon - Replacement of HVAC uni | Absa Carnarvon - Replacement of HVAC uni |  |  | Region 3 |  | Unknown | 1000-71360-01 | Unknown Building - not in our database |  | 2023-09-29 |  |  | ASP-CR0454 | CRTD AVAC RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 600656.9 |  | 70 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000416,"ONEVIEW":"Unknown","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-10-27","DATE08":"2023-11-17","DATE09":"2024-01-01","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":95,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"194:7:21:7:21:14:28:21:45:16","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-10-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgaW1wbGVtZW50YXRpb24uIEZpbmFuY2lhbCByb2xsb3Zlci4=","RATING":""} |  |  |  | PHASE04 | 2023-09-29 | 2023-10-27 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000417 | Absa Delta House Dilaps | Removal of Internal & external signage Removal of UPS Removal of Secutel, ITAS, Domestic lock & safe service and Fidelity ADT security equipment Removal of TVs and screens Removal of aircon units Dilapidations will be conducted during normal working hours and weekends for 10 days. |  |  | Region 1 | Gauteng North | 70652X | 1000-71377-01 | Delta House-Pretorius St-Pretoria | N | 2023-06-13 | 2023-06-13 |  | ASP-GN0205 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-14 | D | 326507.29 |  | 100 | 2023-05-31 | 2023-07-04 | 326507.29 |  | {"MANDT":"111","REFERENCE":90000417,"ONEVIEW":"70652X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-06-13","DATE08":"2023-07-04","DATE09":"2023-08-18","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-06-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000095779 | PHASE08 | 2023-06-13 | 2023-06-13 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-04 | 205157.14 | 0 |  |  | C000095779 | 205157.14 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000418 | Absa Tongaat - Additional Wheelie Bins | Absa Tongaat - Additional Wheelie Bins |  |  | Region 3 |  | Unknown | 1000-71140-01 | Unknown Building - not in our database |  | 2023-07-06 |  |  | ASP-KZ0256 | CLSD ISBD AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 0 | 2023.07.26: Approved by Conrad M as per email Supported by Cres VP |  | 2023-07-27 | 2023-07-27 | 2898 | Approved |  |  |  | C000093840 | PHASE11 | 2023-07-06 | 2023-08-05 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-06-25 | 1804 | 0 |  |  | C000093840 | 2520 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000419 | Absa Nongoma - Replacement of Door Locks | Absa Nongoma - Replacement of Door Locks |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-07-06 |  |  | ASP-KZ0257 | CLSD: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-14 | D | 0 | 2023.06.21: Approved by Conrad M as per email 2023.06.20: Supported by Leko N & Ilana VdW |  | 2023-06-22 | 2023-06-22 | 4441.3 | Approved |  |  |  | C000093847 | PHASE11 | 2023-07-06 | 2023-08-05 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-06-25 | 3862 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000420 | Absa Square Mbombela LED lighting installation | Absa Square Mbombela LED lighting installation |  |  | Energy | Mpumalanga | 77878X |  | Absa, Square-Paul Kruger St-Nelspruit | N | 2023-06-30 | 2023-12-15 |  | ALP-MP0007 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Onisms Manyewe |  |  | 2023 |  |  |  | LOUISR | 2023-06-14 | D | 899913.06 | To achieve energy and utility cost savings as well as contribute towards Absas carbon emission targets | 100 | 2023-02-26 | 2023-03-09 | 899913.06 | There was no need for a Works Authorisation (WA). Absa executed a Variation Agreement (VA) with the direct appointment supplier. | {"MANDT":"111","REFERENCE":90000420,"ONEVIEW":"77878X","DATE01":"2023-04-21","DATE02":"2023-02-17","DATE03":"2023-02-24","DATE04":"2023-02-25","DATE05":"2023-03-09","DATE06":"2023-03-23","DATE07":"2023-06-10","DATE08":"2023-07-28","DATE09":"2023-08-05","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"162:-63:7:1:12:14:79:48:8:22","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-23","FORECAST_END":"2023-06-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3MgcGFydGlhbCBpbnZvaWNlcyBzdWJtaXR0ZWQu","RATING":""} |  |  | C000092245 | PHASE11 | 2023-03-23 | 2023-06-10 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-03-14 | 2023-03-29 | 2023-03-09 | 2023-03-10 | 2023-06-15 | 782533.1 | 0 |  |  | C000092245 | 782533.1 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000421 | 2023 Retail LED lighting rollout (additional 3 branches) | LED lighting installation at 3 retail branches |  |  | Energy | National | Various | 1000-70027-01 | Various Sites | N | 2023-06-30 | 2023-12-15 |  | ALP-N00049 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Sanelisiwe Celu |  | 3 Retail branches located nationally | 2023 |  |  |  | LOUISR | 2023-06-14 | D | 1820279.69 |  | 100 | 2023-03-28 | 2023-03-28 | 1820279.69 | There was no need for a Works Authorisation (WA). Absa executed a Variation Agreement (VA) with the direct appointment supplier. | {"MANDT":"111","REFERENCE":90000421,"ONEVIEW":"Various Sites","DATE01":"2023-04-21","DATE02":"2023-04-28","DATE03":"2023-05-19","DATE04":"2023-05-26","DATE05":"2023-06-16","DATE06":"2023-06-30","DATE07":"2023-07-07","DATE08":"2023-07-28","DATE09":"2023-09-11","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"314:7:21:7:21:14:7:21:45:10","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-30","FORECAST_END":"2023-07-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3Mu","RATING":"Low"} |  |  | C000092246 | PHASE11 | 2023-06-30 | 2023-07-07 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-03-28 | 2023-03-28 |  |  | 2023-06-15 | 1582851.9 | 0 |  |  | C000092246 | 1582851.9 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000422 | Absa Pretoria Campus Refurbishment 18 fa | Install new DiBond Covers for enhanced durability. Apply new vinyl letters to new covers. 3-day work period during business hours Utilize on-site security. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0206 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-06-19 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000422,"ONEVIEW":"22491X","DATE01":"2023-01-25","DATE02":"2023-06-01","DATE03":"2023-06-30","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"2023-07-10","DATE12":"2023-07-10","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUE8gaXNzdWVkIHRvIHN1cHBsaWVyLiBJbnN0YWxsYXRpb24gcGxhbm5lZCBmb3IgMjAyMy8xMi8xOC0zMSBEZWMu","RATING":""} |  |  | C000121927 | PHASE06 | 2023-04-05 | 2023-05-05 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-11-08 | 77350 | 0 |  |  | C000141350 | 77350 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000423 | Auckland Park CC 3 Benches Upholstery | Collect, strip and reupholster 3 x bus stops. Work to take place offsite, no security guard required. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-06-19 | 2023-06-19 |  | ASP-GS0697 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-19 | D | 98768.86 | 2023.06.29: Approved by Conrad M 2023.06.28: Supported by Winston P | 100 | 2023-06-26 | 2023-06-29 | 98768.87 | Approved | {"MANDT":"111","REFERENCE":90000423,"ONEVIEW":"76849X","DATE01":"2023-04-10","DATE02":"2023-04-17","DATE03":"2023-05-08","DATE04":"2023-05-15","DATE05":"2023-06-05","DATE06":"2023-06-28","DATE07":"2023-06-28","DATE08":"2023-07-19","DATE09":"2023-09-02","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"143:7:21:7:21:23:0:21:45:7","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-28","FORECAST_END":"2023-06-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000095216 | PHASE11 | 2023-06-28 | 2023-06-28 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-06-30 | 98768.87 | 0 |  |  | C000084172 | 226776.81 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000424 | Absa Brandfort - Sewer Pipe Line Rerouti | Absa Brandfort - Sewer Pipe Line Rerouti |  |  | Region 3 |  | 79333x | 1000-71584-01 | Absa Brandfort |  | 2023-08-24 |  |  | ASP-CR0455 | CLSD BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-06-20 | D | 68022.52 | 2023.06.29: Approved by Kobus JvR 2023.06.27: Supported by Rob L | 100 | 2023-06-29 | 2023-06-29 | 68022.52 | Approved | {"MANDT":"111","REFERENCE":90000424,"ONEVIEW":"79333x","DATE01":"2023-06-15","DATE02":"2022-04-22","DATE03":"2023-06-20","DATE04":"2023-06-22","DATE05":"2023-06-29","DATE06":"2023-08-20","DATE07":"2023-08-24","DATE08":"2023-09-10","DATE09":"2023-11-28","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-20","FORECAST_END":"2023-08-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGZ1bGx5IGludm9pY2Vk","RATING":""} |  |  | C000124776 | PHASE11 | 2023-08-20 | 2023-08-24 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-20 | 59150.02 | 0 |  |  | C000096887 | 59150.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000425 | Absa Garden Route Mall - Soft Seating | Absa Garden Route Mall - Soft Seating |  |  | Region 2 | Eastern Cape | 78863X | 1000-70908-01 | Garden Route Mall George-Cnr N2 & Knysna Rd-George | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0316 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 100070.7 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Judith B | 100 | 2023-06-26 | 2023-08-03 | 100070.7 | Approved | {"MANDT":"111","REFERENCE":90000425,"ONEVIEW":"78863X","DATE01":"2023-05-25","DATE02":"2023-05-25","DATE03":"2023-06-14","DATE04":"2023-06-26","DATE05":"2023-08-03","DATE06":"2023-09-30","DATE07":"2023-10-04","DATE08":"2023-10-25","DATE09":"2023-12-09","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"189:0:20:12:38:58:4:21:45:28","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-30","FORECAST_END":"2023-10-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MiBBdWcgQXBwcm92ZWQgQ0IyOSAzIEF1Z3VzdCAtIFNpZ25lZCBEZWNrIFBlbmRpbmcgc2lnbmVkIGRlY2sgdG8gcmVxdWVzdCBQTydzCjIxIEp1bmUgUGVuZGluZyBmZWVkYmFjayBmcm9tIHJlZ2lvbiByZSBjb3N0IG9mIGRlbGl2ZXJ5","RATING":"Low"} |  |  | C000102810 | PHASE11 | 2023-09-14 | 2023-10-10 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-08-08 | 87018 | 0 |  |  | C000102810 | 87018 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000426 | Absa Garden Route Mall - LED Replacement | Absa Garden Route Mall - LED Replacement |  |  | Region 2 | Eastern Cape | 78863X | 1000-70908-01 | Garden Route Mall George-Cnr N2 & Knysna Rd-George | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0317 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 210984.7 | 2023.06.29: Approved by Kobus JvR 2023.06.27: Supported by Seiphathi P & Rob L | 100 | 2023-06-29 | 2023-06-29 | 210984.7 | Approved | {"MANDT":"111","REFERENCE":90000426,"ONEVIEW":"78863X","DATE01":"2023-06-14","DATE02":"2023-06-21","DATE03":"2023-06-16","DATE04":"2023-06-29","DATE05":"2023-06-29","DATE06":"2023-07-21","DATE07":"2023-07-22","DATE08":"2023-08-12","DATE09":"2023-09-26","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"139:7:-5:13:0:22:1:21:45:29","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-21","FORECAST_END":"2023-07-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjQgSnVseSBDb21wbGV0ZWQgMjIgSnVseSAtIFZlbmRvciBjb21wbGV0ZWQKUGxhbm5lZCBpbnN0YWxsYXRpb24gd2VlayBvZiB0aGUgMjR0aCBKdWx5","RATING":"Low"} |  |  | C000096892 | PHASE11 | 2023-07-21 | 2023-07-22 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-10 | 183464.96 | 0 |  |  | C000096892 | 183464.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000427 | Absa Riversdale - Contra vision | Absa Riversdale - Contra vision |  |  | Region 2 | Eastern Cape | 37159X | 1000-70797-01 | Absa Riversdale-Cnr Church & Dixon St-Riversdale | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0318 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 50321.47 | 2023.06.29: Approved by Conrad M 2023.06.27: Supported by Judith B & Ilana vdW | 100 | 2023-06-29 | 2023-06-29 | 50321.47 | Approved | {"MANDT":"111","REFERENCE":90000427,"ONEVIEW":"37159X","DATE01":"2023-06-14","DATE02":"2023-06-15","DATE03":"2023-06-21","DATE04":"2023-06-29","DATE05":"2023-06-29","DATE06":"2023-07-19","DATE07":"2023-07-19","DATE08":"2023-08-16","DATE09":"2023-09-30","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"108:1:6:8:0:20:0:28:45:7","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-19","FORECAST_END":"2023-07-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTYgQXVnIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQo=","RATING":"Low"} |  |  | C000095241 | PHASE11 | 2023-07-19 | 2023-07-19 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-06-30 | 43757.8 | 0 |  |  | C000095241 | 43757.8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000428 | Absa Cofimvaba - Chairs, Brochure Holder | Absa Cofimvaba - Chairs, Brochure Holder |  |  | Region 2 | Eastern Cape | 78540X | 1000-71049-01 | Cofimvaba-Cnr Market & Main St-Cofimvaba | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0319 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 0 |  | 1 |  |  | 0 | Reprioritised Project Cancelled | {"MANDT":"111","REFERENCE":90000428,"ONEVIEW":"78540X","DATE01":"2023-05-08","DATE02":"2023-05-15","DATE03":"2023-06-05","DATE04":"2023-06-12","DATE05":"2023-07-03","DATE06":"2023-07-17","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-07-06 | 2023-09-18 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000429 | Absa Jeffreys Bay - Exhaust Extension | Absa Jeffreys Bay - Exhaust Extension |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | The Nautilus Builiding-Da Gama Rd-Jeffreys Bay | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0320 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 360198.75 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Rob L | 100 | 2023-07-11 | 2023-07-13 | 360198.75 | Approved | {"MANDT":"111","REFERENCE":90000429,"ONEVIEW":"22196X","DATE01":"2023-07-01","DATE02":"2023-07-03","DATE03":"2023-07-07","DATE04":"2023-07-11","DATE05":"2023-07-11","DATE06":"2023-08-16","DATE07":"2023-08-24","DATE08":"2023-09-14","DATE09":"2023-10-29","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:2:4:4:0:36:8:21:45:27","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-16","FORECAST_END":"2023-08-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVseSBFeGhhdXN0IGluIE1hbnVmYWN0dXJl","RATING":"Medium"} |  |  | C000097181 | PHASE11 | 2023-09-11 | 2023-09-14 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-11 | 313216.3 | 0 |  |  | C000097181 | 313216.3 |  | 16456.5 |  | 0 | 0 |  | 0 |  | 0
90000430 | Absa Jeffreys Bay - Generator Service | Absa Jeffreys Bay - Generator Service |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | The Nautilus Builiding-Da Gama Rd-Jeffreys Bay |  | 2023-07-17 | 2023-09-29 |  | ASP-EC0321 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-06-20 | D | 0 |  | 1 |  |  | 0 | 3 Aug Done via ABQT | {"MANDT":"111","REFERENCE":90000430,"ONEVIEW":"22196X","DATE01":"2023-05-08","DATE02":"2023-05-15","DATE03":"2023-06-05","DATE04":"2023-06-12","DATE05":"2023-07-03","DATE06":"2023-07-17","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-07-17 | 2023-09-29 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000431 | Absa Mqanduli - Additional Plugs | Absa Mqanduli - Additional Plugs |  |  | Region 2 | Eastern Cape | 78937X | 1000-71058-01 | Main Street Mqanduli-Main St-Mqanduli | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0322 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 17079.26 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Rob L | 100 | 2023-07-06 | 2023-07-06 | 17079.26 | Approved | {"MANDT":"111","REFERENCE":90000431,"ONEVIEW":"78937X","DATE01":"2023-06-15","DATE02":"2023-06-15","DATE03":"2023-06-27","DATE04":"2023-07-06","DATE05":"2023-07-06","DATE06":"2023-07-21","DATE07":"2023-07-21","DATE08":"2023-08-11","DATE09":"2023-09-25","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"138:0:12:9:0:15:0:21:45:15","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-21","FORECAST_END":"2023-07-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjQgSnVseSBDb21wbGV0ZWQgMjEgSnVseQoxOSBKdWx5IFBsYW5uZWQgc3RhcnQgb24gc2l0ZSA3IEF1Zy4=","RATING":"Low"} |  |  | C000096886 | PHASE11 | 2023-08-16 | 2023-08-17 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-10 | 14851.53 | 0 |  |  | C000096886 | 14851.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000432 | Absa Kareedouw - Minor Works | Absa Kareedouw - Minor Works |  |  | Region 2 |  | 78089X | 1000-71462-01 | Kareedouw Shopping Centre-Van Riebeeck St-Kareedouw |  | 2023-07-17 | 2023-09-29 |  | ASP-EC0323 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-06-20 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-07-17 | 2023-09-29 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000433 | Absa Sterkspruit - Minor Works | Absa Sterkspruit - Minor Works |  |  | Region 2 |  | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale |  | 2023-07-17 | 2023-09-29 |  | ASP-EC0324 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-06-20 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-07-17 | 2023-09-29 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000434 | Absa Tzaneen - HVAC Modification | Absa Tzaneen - HVAC Modification |  |  | Region 3 | Limpopo | 76808X | 1000-70526-01 | Danie Joubert Street Tzaneen-Danie Joubert St Tzaneen Hotel-Tzaneen | U | 2023-08-30 |  |  | ASP-LP0166 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-06-20 | D | 447055.69 | Engineering Minor Works - Remedial Work | 100 | 2023-09-14 | 2023-09-29 | 447055.69 | Project approved and supplier POs issued. | {"MANDT":"111","REFERENCE":90000434,"ONEVIEW":"76808X","DATE01":"2023-06-21","DATE02":"2023-06-28","DATE03":"2023-07-19","DATE04":"2023-07-26","DATE05":"2023-08-16","DATE06":"2023-08-30","DATE07":"2023-10-16","DATE08":"2023-11-30","DATE09":"2023-11-30","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":20,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-30","FORECAST_END":"2023-10-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVk","RATING":""} |  |  | C000113506-2 | PHASE07 | 2023-08-30 | 2023-11-07 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-29 | 388744.08 | 0 |  |  | C000113506 | 388744.06 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000435 | Absa Savannah Mall - Dilaps | Absa Savannah Mall - Dilaps |  |  | Region 3 | Limpopo | 21331X | 1000-70452-01 | Savannah Mall-Cnr Grimm & Thabo Mbeki St-Polokwane | U | 2023-08-10 |  |  | ASP-LP0167 | TECO BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-06-20 | D | 103386.24 | Dilapidations - Revamp | 100 | 2023-08-07 | 2023-08-08 | 103386.24 |  | {"MANDT":"111","REFERENCE":90000435,"ONEVIEW":"21331X","DATE01":"2023-06-01","DATE02":"2023-06-08","DATE03":"2023-06-29","DATE04":"2023-07-06","DATE05":"2023-07-27","DATE06":"2023-08-10","DATE07":"2023-08-24","DATE08":"2023-09-30","DATE09":"2023-11-14","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-10","FORECAST_END":"2023-08-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"aW52b2ljZXMgcmVxdWVzdGVk","RATING":""} |  |  | C000113506 | PHASE10 | 2023-08-10 | 2023-08-24 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-29 | 388744.08 | 0 |  |  | C000104092 | 89901.09 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000436 | Absa Limpopo Mall - Minor Works | Absa Limpopo Mall - Minor Works |  |  | Region 3 | Limpopo | 78979X | 1000-70547-01 | Limpopo Mall-Cnr Rissik, Market, Devenish & Kerk St-Polokwane | U | 2023-08-23 |  |  | ASP-LP0168 | CRTD AVAC RESA: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-06-20 | D | 0 | Minor Works - Enhancements | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000436,"ONEVIEW":"78979X","DATE01":"2023-06-14","DATE02":"2023-06-21","DATE03":"2023-07-12","DATE04":"2023-07-19","DATE05":"2023-08-09","DATE06":"2023-08-23","DATE07":"2023-09-22","DATE08":"2023-10-13","DATE09":"2023-11-27","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":20,"PROG04":0,"PROG05":1,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":6,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-23","FORECAST_END":"2023-09-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVk","RATING":""} |  |  |  | PHASE12 | 2023-08-23 | 2023-09-22 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000437 | Absa Witbank - Ceiling Repairs (DILAPS) | Absa Witbank - Ceiling Repairs (DILAPS) |  |  | Region 3 | Mpumalanga | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank | U | 2023-08-24 |  |  | ASP-MP0162 | CRTD AVAC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-06-20 | D | 121212.38 | Insurance claim - Insog | 100 |  |  | 121212.38 |  | {"MANDT":"111","REFERENCE":90000437,"ONEVIEW":"76953XUnknown","DATE01":"2023-06-15","DATE02":"2023-06-22","DATE03":"2023-07-13","DATE04":"2023-07-20","DATE05":"2023-08-10","DATE06":"2023-08-24","DATE07":"2023-09-23","DATE08":"2023-10-14","DATE09":"2023-11-28","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-24","FORECAST_END":"2023-09-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE11 | 2023-07-17 | 2023-07-17 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000438 | Absa Siyabuswa Mall - Minor Works | Absa Siyabuswa Mall - Minor Works |  |  | Region 3 | Limpopo | 36259X | 1000-70681-01 | Siyabuswa Mall-Bongimfundo Rd-Siyabuswa | U | 2023-08-17 |  |  | ASP-MP0163 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-06-20 | D | 154830.88 | Approved | 100 | 2023-07-21 | 2023-10-07 | 154830.88 |  | {"MANDT":"111","REFERENCE":90000438,"ONEVIEW":"36259X","DATE01":"2023-06-08","DATE02":"2023-06-15","DATE03":"2023-07-06","DATE04":"2023-07-13","DATE05":"2023-08-03","DATE06":"2023-08-17","DATE07":"2023-09-16","DATE08":"2023-10-05","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"2023-10-05","DATE12":"2023-10-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-17","FORECAST_END":"2023-09-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgUE9DIHN1Ym1pdHRlZA==","RATING":""} |  |  | C000103924 | PHASE10 | 2023-08-17 | 2023-09-16 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-08-15 | 134635.55 | 123451.2 |  |  | C000149470 | 11184.35 |  | 17604.28 |  | 0 | 0 |  | 0 |  | 0
90000439 | Various- Open stickers for push bar | Various- Open stickers for push bar |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-07-05 | 2023-12-15 |  | ASP-N00058 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Lorri-Anne Louis |  |  | 2023 |  |  |  | LOUISR | 2023-06-20 | D | 0 | 2023.06.29: Approved by Conrad M |  | 2023-06-29 | 2023-06-29 | 25875 | Approved |  |  |  | C000096266 | PHASE11 | 2023-07-05 | 2023-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-07-06 | 22500 | 0 |  |  | C000096266 | 22500 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000440 | Absa 32 Voortrekker Belliville - Dilaps | Absa 32 Voortrekker Belliville - Dilaps For Building Sale |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | U | 2023-07-17 | 2023-09-29 |  | ASP-WC0289 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-06-20 | D | 247156.17 |  | 100 | 2023-08-02 | 2023-08-03 | 247156.17 | 8 Aug Absa PO Received C000102625 dd 7 Aug, BV PO's requested 2 Aug Submitted to Absa ENG who sent to Real Estate for Approval | {"MANDT":"111","REFERENCE":90000440,"ONEVIEW":"78126X","DATE01":"2023-06-26","DATE02":"2023-07-03","DATE03":"2023-07-24","DATE04":"2023-08-02","DATE05":"2023-08-03","DATE06":"2023-08-28","DATE07":"2023-10-20","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"2023-12-11","DATE12":"2023-12-11","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"188:7:21:9:1:25:53:7:45:6","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-28","FORECAST_END":"2023-10-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgRGVjIC0gRW5naW5lZXJpbmcgdG8gQWR2aXNlIHJlIG5leHQgc3RlcHMKMTEgRGVjIEJpZHZlc3QgRW5nIHRvIGFkdmlzZSBvbiB0aGUgcmVwYWlyIHdvcmsKNyBEZWMgRW5naW5lZXJpbmcgdG8gYWR2aXNlIGluIHRlcm1zIG9mIG5leHQgc3RlcHMgcmUgcmVtZWRpYWwgd29yawo0IERlYyAtIEJWIEVORyBpbmhvdXNlIHRlYW0gc3RpbGwgbm90IGNvbXBsZXRlZCB3aXRoIHRoZSByZW1lZGlhbCB3b3JrcwozMCBOb3YgRW5naW5lZXJpbmcgdG8gcmV0dXJuIHRvIGNvbXBsZXRlIHJlbWVkaWFsIHdvcmtzIGJ5IEZyaWRheSAxIERlYwoyNyBOb3YgVmVuZG9yIHNlbnQgYSBtZXNzYWdlIHRoYXQgd29yayB3YXNuJ3QgY29tcGxldGVkLiBXaWxsIGNhbGwgdG9tb3Jyb3cgZm9yIG1vcmUgZGV0YWlscyBhbmQgYWR2aXNlIGFjY29yZGluZ2x5CjIzIE5vdiBGaW5hbCBJbnNwZWN0aW9uIHNjaGVkdWxlZCBmb3IgMjcgTm92IGZvciB0aGUgQ09DCjIyIE5vdiBCRk0gdGVhbSBjb21wbGV0ZWQgd2l0aCByZW1lZGlhbCB3b3JrcywgQ09DIHRvIGJlIGlzc3VlZAoyMCBOb3YgLSBFbmcgdG8gYmUgb24gc2l0ZSAyMiBOb3YgcGxhbm5pbmcgdG8gY29tcGxldGUgYnkgMjR0aAoxNiBOb3YgQmlkdmVzdCBFbmcgc3RpbGwgYnVzeSB3aXRoIHJlcGFpciB3b3JrLiBTY2hlZHVsZWQgZm9yIHRoZSB3ZWVrZW5kIDE4IGFuZCAxOXRoIE5vdgoxNCBOb3YgUE9DIHN1Ym1pdHRlZCAyNyBPY3QgV2FzIEZpbmFsIFBPQyAtIE1haWwgZnJvbSBQTQo2IE5vdiAtIFBNIHRvIGZvbGxvdyB1cCB3aXRoIGluaG91c2UgdGVhbSByZSB3b3JrcyBvdXRzdGFuZGluZwowMiBOb3YgLSBFbmcgUE8gcGVuZGluZyBmb3IgbWF0ZXJpYWxzIHJlcXVpcmVkLCB0byBjb21wbGV0ZSBlYXJseSBuZXh0IHdlZWsKMjcgT0NUIEJWIGVuZ2luZWVyaW5nIHRvIGFkdmlzZSBvbiBjb21wbGV0aW9uIG9mIHJlbWVkaWFsIHdvcmtzCjI3IE9jdCBQT0MgMSBTdWJtaXR0ZWQgdG8gRmluYW5jZSBSIDIyMCAxMTcuNjkKMjYgT2N0IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIG9uIGNvbXBsZXRpb24gc3RpbGwgaW4gcHJvZ3Jlc3MKMjMgT2N0IC0gUE0gdG8gY2hlY2sgaWYgRW5naW5lZXJpbmcgcmUgY29tcGxldGlvbiBvZiB0aGUgcmVtZWRpYWwgd29yayBpbiBvcmRlciB0byBpc3N1ZSBDT0MKMTkgT2N0IFdvcmsgQmVpbmcgRG9uZSBieSBJbiBob3VzZSBCaWR2ZXN0IFRlYW0KMTIgT2N0IC0gUEUgdG8gZm9sbG93IHVwIHdpdGggRW5nIExlYWQgcmUgYXBwcm92YWwgb2Ygd29ya3MgcmVxdWlyZWQgYXMgR01QCjkgT2N0IC0gUE0gdG8gZm9sbG93IHVwIHdpdGggRU5HIHRvIGNvbXBsZXRlIHJlIHRoZSBNYWludGVuYW5jZSB3b3JrIGluIG9yZGVyIHRvIGlzc3VlIENPQwoyMiBTZXB0IC0gUE0gdG8gZm9sbG93IHVwIHdpdGggRW5naW5lZXJpbmcgcmUgTWFpbnRlbmFuY2UgV29yayBSZXF1aXJlZCAtIE9wZXgKMTEgU2VwdCBCcmVha2Rvd24gZm9yIEVsZWN0cmljYWwgcmVxdWlyZWQgdG8gc2hhcmUgd2l0aCBFbmdpbmVlcmluZyAtIFByb2plY3QgY2FuIG9ubHkgYmUgY29tcGxldGVkIHdoZW4gQ09DIGlzc3VlZCBhZnRlciBNYWludGVuYW5jZSBjb21wbGV0ZWQu","RATING":"Low"} |  |  | C000102625 | PHASE11 | 2023-08-28 | 2023-10-20 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-15 | 214918.41 | 0 |  |  | C000102625 | 214918.41 |  | 22414.2 |  | 0 | 22414.2 |  | 0 |  | 0
90000441 | Absa Gugulethu - Carpets Back Office | Absa Gugulethu - Carpets Back Office |  |  | Region 2 |  | 20992X | 1000-70691-01 | Gugulethu Square-Steve Biko St-Gugulethu |  | 2023-07-17 | 2023-09-29 |  | ASP-WC0290 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  |  |  | CEASARS | 2023-06-20 | D | 0 |  | 1 |  |  | 0 | project cancelled | {"MANDT":"111","REFERENCE":90000441,"ONEVIEW":"20992X","DATE01":"2023-05-08","DATE02":"2023-05-15","DATE03":"2023-06-05","DATE04":"2023-06-12","DATE05":"2023-07-03","DATE06":"2023-07-17","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-07-17 | 2023-09-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000442 | Absa 80 Beach Road Strand - ATM PrivScre | Absa 80 Beach Road Strand - ATM PrivScre |  |  | Region 2 | Western Cape | 76975X | 1000-70793-01 | Eighty Beach Road-Beach Rd-Strand | N | 2023-07-17 | 2023-09-29 |  | ASP-WC0291 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 63417.14 | 2023.07.13: Approved by Conrad M | 100 | 2023-07-13 | 2023-07-13 | 63417.14 | Approved | {"MANDT":"111","REFERENCE":90000442,"ONEVIEW":"76975X","DATE01":"2023-06-14","DATE02":"2023-06-21","DATE03":"2023-07-05","DATE04":"2023-07-13","DATE05":"2023-07-13","DATE06":"2023-08-07","DATE07":"2023-08-11","DATE08":"2023-09-01","DATE09":"2023-10-16","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:14:8:0:25:4:21:45:27","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-07","FORECAST_END":"2023-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVseSBQTydzIGluIFByb2dyZXNz","RATING":"Low"} |  |  | C000098564 | PHASE11 | 2023-08-02 | 2023-08-03 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-07-18 | 55145.34 | 0 |  |  | C000098564 | 55145.34 |  | 2967.48 |  | 0 | 0 |  | 0 |  | 0
90000443 | Absa Laingsburg - Carpets | Absa Laingsburg - Carpets and Tileing |  |  | Region 2 | Western Cape | 78112X | 1000-70886-01 | Absa Laingsburg-Voortrekker Rd-Laingsburg | N | 2023-07-17 | 2023-09-29 |  | ASP-WC0292 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 201691.5 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Judith B & Ilana vdW | 100 | 2023-07-20 | 2023-07-27 | 201691.5 | Approved | {"MANDT":"111","REFERENCE":90000443,"ONEVIEW":"78112X","DATE01":"2023-07-03","DATE02":"2023-07-10","DATE03":"2023-07-12","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-09-11","DATE07":"2023-09-15","DATE08":"2023-10-06","DATE09":"2023-11-20","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"212:7:2:8:7:46:4:21:45:20","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-11","FORECAST_END":"2023-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjcgSnVseSBBcHByb3ZlZCBDQjI4IFNpZ25lZCBEZWNrIFBlbmRpbmcgdG8gcmVxdWVzdCBQTwoyMCBKVUxZIEJDIFBBQ0sgU1VCTUlUVEVEIEZPUiBBUFBST1ZBTA==","RATING":"Low"} |  |  | C000100702 | PHASE11 | 2023-09-12 | 2023-10-18 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-07-28 | 175383.91 | 0 |  |  | C000100702 | 175383.91 |  | 9211.5 |  | 0 | 0 |  | 0 |  | 0
90000444 | Absa Bizana - Generator Replacement | Absa Bizana - Generator Replacement |  |  | Region 2 |  | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana |  | 2023-07-17 | 2023-09-29 |  | ALP-EC0013 | CRTD DLFL SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-06-20 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED |  |  | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000445 | Absa Bizana - Generator Replacement | Absa Bizana - Generator Replacement |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2023-08-01 | 2023-10-31 |  | ALP-EC0014 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 0 |  | 0 |  |  | 0 | 3 July - Budgeted for 2024 CIP - Engineering to advise | {"MANDT":"111","REFERENCE":90000445,"ONEVIEW":"70633X","DATE01":"2023-05-23","DATE02":"2023-05-30","DATE03":"2023-06-20","DATE04":"2023-06-27","DATE05":"2023-07-18","DATE06":"2023-08-01","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-01","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEganVuZSBGb3JtYWwgUFJGL3JlcXVlc3QgcGVuZGluZyByZSBvdXRjb21lIG9mIHJlcGFpcnMgaW4gcHJvZ3Jlc3M=","RATING":""} |  |  |  | DELETED | 2023-08-01 | 2023-10-31 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000446 | Absa Jeffreys Bay - Generator Replacemen | Absa Jeffreys Bay - Generator Replacemen |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | The Nautilus Builiding-Da Gama Rd-Jeffreys Bay |  | 2023-08-01 | 2023-10-31 |  | ALP-EC0015 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-06-20 | D | 0 |  | 1 |  |  | 0 | New 2024 Project ALPEC0032 | {"MANDT":"111","REFERENCE":90000446,"ONEVIEW":"22196X","DATE01":"2024-01-11","DATE02":"2024-01-18","DATE03":"2024-02-08","DATE04":"2024-02-15","DATE05":"2024-03-07","DATE06":"2024-03-21","DATE07":"2024-06-20","DATE08":"2024-07-11","DATE09":"2024-08-25","DATE10":"2024-08-31","DATE11":"2024-08-25","DATE12":"2024-08-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:91:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-21","FORECAST_END":"2024-06-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBKdWx5IC0gQnVkZ2V0ZWQgZm9yIDIwMjQgQ0lQIC0gRW5naW5lZXJpbmcgdG8gYWR2aXNl","RATING":""} |  |  |  | PHASE12 | 2024-03-21 | 2024-06-20 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000447 | Absa Sterkspruit - Minor Works | Absa Sterkspruit - Minor Works |  |  | Region 2 | Eastern Cape | 78939X | 1000-71059-01 | Sterkspruit Shopping Centre-Main St-Sterkspruit | N | 2023-08-01 | 2023-10-31 |  | ALP-EC0016 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 1519237.8 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B & Ilana vdW | 100 | 2023-07-20 | 2023-07-20 | 1519237.8 | Absa Ref : 240129_152 | {"MANDT":"111","REFERENCE":90000447,"ONEVIEW":"78939X","DATE01":"2023-05-30","DATE02":"2023-06-06","DATE03":"2023-07-07","DATE04":"2023-07-20","DATE05":"2023-07-20","DATE06":"2023-11-07","DATE07":"2023-11-22","DATE08":"2023-12-12","DATE09":"2024-01-26","DATE10":"2024-02-29","DATE11":"2024-01-27","DATE12":"2024-01-27","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"246:7:31:13:0:110:15:20:45:4","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-07","FORECAST_END":"2023-11-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OSBGZWIgMjAyNCBQTyBpc3N1ZWQgLSBDMDAwMTQwOTY1IC0gTm90ZSBGaW5hbCBQT0Mgd2FzIHN1Ym1pdHRlZCAxMiBEZWMgMjMgd2l0aCAyMDIzIFBPIEMwMDAxMTc3NjEKMDYgRmViIEpWQyAtIEZpbmFsIGludm9pY2Ugc3VibWl0dGVkIHRvIEFCU0EuIDA1IEZlYgoxMiBEZWMgUGFydCAyIGFuZCBGaW5hbCBQT0MgU3VibWl0dGVkICAtICBSIDE1OSA4OTUuNzIgLSBUb3RhbCAtIFIgMSAxOTggMzU4LjY0ICBmb3IgR0EsIEVkZW4sIEZBRFQsIFNlY3V0ZWwgYW5kIFVraHVuaQozMCBOb3YgUGFydCAxIFBPQyBTdWJtaXR0ZWQgLSBSIDEgMDM4IDQ2MS43NiAtIEJlYXRvbiwgU2VjdXRlbCwgUyZHLCBFcmdvLCBVa2h1bmkKMjcgTm92IC0gUE9DIGFuZCBJbnZvaWNpbmcgaW4gcHJvZ3Jlc3MKMjAgTm92IE9udHJhY2sgZm9yIGNvbXBsZXRpb24gYnkgMjIgTm92IGRlc3BpdGUgaW5pdGlhbCBkZWxheXMgd2l0aCBjbGVhcmluZyBjYXNoCjE3IE5vdiBCYWNrIG9uIFNjaGVkdWxlIGRlc3BpdGUgaW5pdGlhbCBEZWxheXMKNiBOb3YgU3RhcnQgb24gc2l0ZSA3IE5vdgozMCBPY3QgS2ljayBvZmYgTWVldGluZyAzMCBPY3QKMjMgT2N0IFByb2plY3Qgb24gdHJhY2sKMTkgT2N0IEFic2EgUE8gUmVjZWl2ZWQgLSBDMDAwMTE3NzYxCjE4IE9jdCBQQyBmb2xsb3dlZCB1cCBvbiB0aGUgQWJzYSBQTwoxMiBPY3QgRnVsbHkgU2lnbmVkIFdBIGFuZCBTRiByZWNlaXZlZCBBYnNhIFBPIHRvIGJlIHJlcXVlc3RlZCAtIEJWIFBPJ3MgSXNzdWVkCjExIE9jdCBBbGwgb24gdHJhY2sgV0EgYW5kIFNGIGluIGNpcmN1bGF0aW9uIGZvciBBYnNhIFBPCjUgT2N0IEFwcHJvdmVkIFdBIHNhbmQgU0YgUmVjZWl2ZWQgYW5kIHNlbnQgZm9yIHNpZ25vZmYKMjEgU2VwdCAtIFJpc2sgRmluYW5jaWFsIFJvbGxvdmVyIGFzIENsaWVudCByZXF1ZXN0ZWQgdGhlIHByb2plY3QgYmUgdW5kZXJ0YWtlbiBmcm9tIDcgTm92IHRvIDIyIE5vdgo=","RATING":"Medium"} |  |  | C000117761 | PHASE10 | 2023-11-07 | 2023-11-22 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-19 | 1321076.35 | 0 |  |  | C000140965 | 1321076.35 |  | 142723.47 |  | 0 | 142723.47 | C000140965 | 1519237.8 |  | 0 |  |  | 2024-02-08
90000448 | Absa Kareedouw - Minor Works | Absa Kareedouw - Minor Works |  |  | Region 2 | Eastern Cape | 78089X | 1000-71462-01 | Kareedouw Shopping Centre-Van Riebeeck St-Kareedouw | N | 2023-08-01 | 2023-10-31 |  | ALP-EC0017 | CRTD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-20 | D | 0 |  | 1 |  |  | 0 | Cancelled as to be done as PMO project | {"MANDT":"111","REFERENCE":90000448,"ONEVIEW":"78089X","DATE01":"2023-05-23","DATE02":"2023-05-30","DATE03":"2023-06-20","DATE04":"2023-06-27","DATE05":"2023-07-18","DATE06":"2023-08-01","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-01","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NyBBdWcgUE0gdG8gZm9sbG93IHVwIENhbGwgaGFkIHdpdGggSWxhbmE=","RATING":""} |  |  |  | PHASE12 | 2023-08-01 | 2023-08-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000449 | Absa Vincent Branch - Signage | Absa Vincent Branch - Signage |  |  | Region 2 | Eastern Cape | 78697X | 1000-71051-01 | Vincent Park-Devereux Ave-East London | N | 2023-07-17 | 2023-09-29 |  | ASP-EC0325 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-21 | D | 55002.02 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B & Ilana vdW | 100 | 2023-07-13 | 2023-07-20 | 55002.02 | Approved | {"MANDT":"111","REFERENCE":90000449,"ONEVIEW":"78697X","DATE01":"2023-06-16","DATE02":"2023-06-19","DATE03":"2023-07-13","DATE04":"2023-07-20","DATE05":"2023-07-20","DATE06":"2023-08-21","DATE07":"2023-08-25","DATE08":"2023-09-15","DATE09":"2023-10-30","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:3:24:7:0:32:4:21:45:27","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-21","FORECAST_END":"2023-08-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgSnVseSBBcHByb3ZlZCBDQiAyMCBQTydzIHRvIGZvbGxvdw==","RATING":"Low"} |  |  | C000099658 | PHASE11 | 2023-09-06 | 2023-09-29 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-24 | 47827.85 | 0 |  |  | C000099658 | 47825.85 |  | 5000.18 |  | 0 | 0 |  | 0 |  | 0
90000450 | Absa Bloemfontein Forum-Additional plugs | Absa Bloemfontein Forum-Additional plugs |  |  | Region 3 |  | Unknown | 1000-71476-01 | Unknown Building - not in our database |  | 2023-06-28 |  |  | ASP-CR0456 | CLSD BUDG ISBD AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-23 | D | 0 | 2023.06.29: Approved by Kobus JvR 2023.06.27: Supported by Rob L | 100 | 2023-06-29 | 2023-06-29 | 2809.4 | Approved | {"MANDT":"111","REFERENCE":90000450,"ONEVIEW":"Unknown","DATE01":"2023-04-19","DATE02":"2022-11-08","DATE03":"2022-11-08","DATE04":"2022-11-08","DATE05":"2023-11-17","DATE06":"2023-12-01","DATE07":"2022-11-23","DATE08":"2023-06-22","DATE09":"2024-01-26","DATE10":"2024-02-26","DATE11":"2023-10-02","DATE12":"2023-10-02","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"195:-162:0:0:374:14:-373:211:218:29","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-01","FORECAST_END":"2022-11-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZS4gCjA2LjAyLjIwMjQgRk06IEZpbmFsIFBPQyB3YXMgcmVjZWl2ZWQgb24gRGVjIDE1LCAyMDIzLCBhZnRlciBBQlNBIGN1dCBvZmYgYW5kIGJpbGxlZCBkb24gMjY6MDE6MjAyNC4=","RATING":""} |  |  | C000096890 | PHASE11 | 2023-12-01 | 2022-11-23 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-07-10 | 2442.95 | 0 |  |  | C000096890 | 2442.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000451 | Absa Ladysmith - Supply Office Furniture | Absa Ladysmith - Supply Office Furniture |  |  | Region 3 |  | Unknown | 1000-71074-01 | Unknown Building - not in our database |  | 2023-07-27 |  |  | ASP-KZ0258 | REL BUDG AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-23 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE06 | 2023-09-26 | 2023-10-20 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000140954 | 157608.41 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000452 | Absa Pretoria Campus replace damaged tar | Repair the pothole at the 270 Maggs Street entrance. Resurface 9m2 around the pothole at the 270 Maggs Street entrance. Restoration of road markings at the 270 Maggs Street entrance. Restoration of road markings on Petroleum Road. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0207 | REL BUDG AVAC SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | F |  | GAMIETR | 2023-06-25 | D | 0 | 2023.06.29: Approved by Conrad M 2023.06.28: Supported by Winston P | 100 | 2023-06-29 | 2023-06-29 | 38544.5 | Approved | {"MANDT":"111","REFERENCE":90000452,"ONEVIEW":"22491X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-08-07","DATE08":"2023-08-28","DATE09":"2023-10-12","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-08-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000095211 | PHASE07 | 2023-04-05 | 2023-08-07 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-30 | 38544.5 | 0 |  |  | C000140542 | 33516.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000453 | Hercules Minor Works | 1ST FLOOR: -Kitchen & pause area: (wall demolition 8.85 sqm, floor tile replacement 5.13sqm & painting 41.4 sqm) -Storeroom: (shelf removal 6X, replace vinyl flooring 16,5 sqm & painting 40sqm) -Toilets: (wall tiles 118 sqm & floor tile replacement 7.26 sqm, fixtures 10X, painting 9.5 sqm & lighting 1X) GROUND FLOOR: -Treasury: (shelves removal 1X , replace vinyl flooring 16.5 sqm & painting 58 sqm) -Passage: (replace vinyl flooring 36 sqm) -Toilet: (wall tiles 29 sqm & floor tile replacement 4.4 sqm, fixtures 8x & painting 6 sqm) -Work will be conducted after normal working hours for 15 days -Security Guard for the duration of the project -Material lead-time: +-1 week |  |  | Region 1 | Gauteng North | 21228X | 1000-70018-01 | Hercules-Van Der Hoff St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0208 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 56077.73 |  | 100 | 2023-09-07 | 2023-09-13 | 56077.73 |  | {"MANDT":"111","REFERENCE":90000453,"ONEVIEW":"21228X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"2023-07-10","DATE12":"2023-07-10","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000110192 | PHASE09 | 2023-04-05 | 2023-05-05 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-09-13 | 48763.24 | 0 |  |  | C000140949 | 48763.24 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000454 | Rayton Park Plaza Minor Works | Replace stained toilet x1 basin. Fix kitchen BIC x4 doors and replace x1 damaged side panel. Install 200 x 100mm tile skirting in the kitchen. Add 4m bumper rail to the online banking area. Remove x2 consultants dividers and make good carpets and ceilings. Reconfigure & reposition x2 plugs for consultants computers. Relocate x1 TV from back office to banking hall. Replace x1 ceiling panel (1200 x 600 x 12.5mm) in the storeroom. Replace storeroom carpet with vinyl 16m2. Repair branch walls 10m2. Repaint the entire branch 360m2. Work will be conducted after normal working hours for 15 days Security Guard for the duration of the project Material lead-time: +-1 week |  |  | Region 1 | Gauteng North | 78058X | 1000-70387-01 | Rayton Park Plaza-Cnr Theurnicht & Alley St-Rayton | N | 2023-04-05 |  |  | ASP-GN0209 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 128631.43 | 2023.06.29: Approved by Conrad M 2023.06.27: Supported by Winston P & Ilana vdW | 100 | 2023-06-26 | 2023-06-29 | 128631.42 | Approved | {"MANDT":"111","REFERENCE":90000454,"ONEVIEW":"78058X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-08-31","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:21:7:21:14:148:61:45:21","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFNuYWdzIGNvbXBsZXRlLiBGaW5hbCBQT0MgcGxhbm5lZCBmb3IgZW5kIG9mIE9jdC4=","RATING":""} |  |  | C000095238 | PHASE09 | 2023-04-05 | 2023-08-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-30 | 128631.42 | 86919.2 |  |  | C000140666 | 24934.21 |  | 11424.68 |  | 0 | 0 |  | 0 |  | 0
90000455 | Absa Monument Park Spray Paint Ceilings | Cover all equipment (Security, Lights, sprinklers & fire detection) with plastic. Clean & spray paint all ceiling boards throughout branch (483m2). Remove covers on all equipment and clean all areas once work is completed. Work will be conducted after normal working hours for 3 days Security Guard for the duration of the project Material lead-time: +-1 week |  |  | Region 1 |  | 77976X | 1000-70385-01 | Monument Park Shopping Centre-Skilpad Rd-Pretoria | N | 2023-06-26 | 2023-06-26 |  | ASP-GN0210 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 53701.13 | 2023.06.29: Approved by Conrad M 2023.06.27: Supported by Winston P & Ilana vdW | 100 | 2023-06-26 | 2023-06-29 | 53701.13 | Approved | {"MANDT":"111","REFERENCE":90000455,"ONEVIEW":"77976X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":19,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000096256 | PHASE09 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-06 | 53701.14 | 30149 |  |  | C000140664 | 16547.64 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000456 | Absa Queenswood Minor Works | Re-carpet the back office (20mÃÂÃÂÃÂÃÂ²) Update vinyl flooring in x2 storerooms (15mÃÂÃÂÃÂÃÂ²) Repair chipped walls (5mÃÂÃÂÃÂÃÂ²) Repaint entire branch as per Absa colour specifications (350mÃÂÃÂÃÂÃÂ²) Install x6 corner protectors (1.8m hi) in the teller and banking area Install x2 new bumper rails (2m and 1m) in the teller area ÃÂÃÂ¢ÃÂÃÂÃÂÃÂ¢ Apply vinyl wraps to x3 exterior columns at the entrance Work will be conducted after normal working hours for 7 days Security Guard for the duration of the project Material lead-time: +-1 week |  |  | Region 1 |  | 37014X | 1000-70207-01 | Queenswood Quarter-Cnr Whittle Ln & Shilling St Queenswood-Pretoria | N | 2023-06-26 | 2023-06-26 |  | ASP-GN0211 | CRTD SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 0 |  | 1 | 2023-06-26 |  | 0 |  | {"MANDT":"111","REFERENCE":90000456,"ONEVIEW":"37014X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFByb2plY3QgQ2FuY2VsbGVkLiAKQ2FuY2VsbGVkLg==","RATING":""} |  |  |  | PHASE05 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000457 | Absa Cosmo Mall Upgrade BIC and paint walls | FOH entrance and customer service area wallpaper removal and repainting sqm BOH kitchen Built-In Cupboard replacement Work will be conducted after normal working hours for 3 days Security guard for the duration of the works Material lead-time: +-1 week |  |  | Region 1 |  | 36216X | 1000-70188-01 | Cosmo Mall-Cnr Malibongwe & South Africa Dr-Johannesburg | N | 2023-06-26 | 2023-06-26 |  | ASP-GN0212 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 0 | 2023.06.29: Approved by Conrad M 2023.06.27: Supported by Winston P & Ilana vdW | 100 | 2023-06-26 | 2023-06-29 | 59741.75 | Approved | {"MANDT":"111","REFERENCE":90000457,"ONEVIEW":"36216X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000095239 | PHASE07 | 2023-06-26 | 2023-09-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-30 | 59741.75 | 0 |  |  | C000095239 | 51949.35 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000458 | Absa Southgate New Tube system | Supply and install new tube system including 2 x 160mm diameter flange Supply and install new drop safe (x2) Security guards required for the duration of the works. Work will be carried out after normal working hours. Material Leadtime: +-3 working days. Onsite timeline: 10 working days |  |  | Region 1 | Gauteng South | 77326X | 1000-70365-01 | Southgate Mall-Cnr Rifle Range Rd & Columbine Ave-Mondeor | N | 2023-06-25 | 2023-06-25 |  | ASP-GS0698 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L | 2023-10-30 | GAMIETR | 2023-06-25 | D | 0 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Winston P & Ilana vdW | 100 | 2023-07-27 | 2023-07-27 | 364629.97 | Approved | {"MANDT":"111","REFERENCE":90000458,"ONEVIEW":"77326X","DATE01":"2023-04-16","DATE02":"2023-04-23","DATE03":"2023-07-18","DATE04":"2023-07-21","DATE05":"2023-06-11","DATE06":"2023-06-25","DATE07":"2023-06-25","DATE08":"2023-07-16","DATE09":"2023-08-30","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-25","FORECAST_END":"2023-06-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBvbiBleGVjdXRpb24gdG8gYmUgY29tcGxldGVkIDA3LzEwLzIwMjM=","RATING":"Low"} |  |  | C000101333 | PHASE11 | 2023-06-25 | 2023-06-25 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-01 | 317069.53 | 0 |  |  | C000101333 | 317069.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000459 | Absa Heidelberg Mall New Tube system | Supply and install new tube system including 3 x 160mm diameter flag Security guards required for the duration of the works. Work will be carried out after normal working hours. Material Leadtime: +-3 working days. Onsite timeline: 10 working days |  |  | Region 1 | Gauteng South | 35105X | 1000-70086-01 | Heidelberg Mall-Marias St-Heidelberg | N | 2023-06-26 | 2023-06-26 |  | ASP-GS0701 | REL CNF BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  | Project completed, additional scope of work for the installation of Meta wall in the back office. | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 0 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Winston P & Ilana vdW | 100 | 2023-06-26 | 2023-07-27 | 405314.36 | Approved | {"MANDT":"111","REFERENCE":90000459,"ONEVIEW":"35105X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-10-19","DATE09":"2023-12-03","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"227:7:21:7:21:14:0:115:45:19","PROGRESS":86,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIHNpZ24tb2ZmIHdhaXRpbmcgc3VwcGxpZXIgaW52b2ljZXMgZm9yICBQT0MgdG8gYmUgaXNzdWVkLgoyMDIzLjEwLjE5LVBPQyBpc3N1ZWQgdG8gZmluYW5jZSBmb3IgcHJvY2Vzc2luZw==","RATING":""} |  |  | C000101348 | PHASE11 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-01 | 352447.26 | 0 |  |  | C000101348 | 352447.26 |  | 5000 |  | 0 | 0 |  | 0 |  | 0
90000460 | Multiflora Minor Works | Ã¢ÂÂ¢ Replace existing carpets and skirting in Back office and Teller area 20 sqm Ã¢ÂÂ¢ Paint walls in the back office, Server room and ATM room Ã¢ÂÂ¢ Install TV set on the wall in the Banking Hall Ã¢ÂÂ¢ Replace Outdated artwork with AO posters Ã¢ÂÂ¢ Supply and install new 5 litre Hydro boil in kitchen including plumbing and electrical Ã¢ÂÂ¢ Paint walls in the kitchen. |  |  | Region 1 |  | 76554X | 1000-70287-01 | Multiflora-Marjorie St-Johannesburg | N | 2023-04-05 |  |  | ASP-GS0702 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 96605.75 | 2023.06.29: Approved by Conrad M 2023.06.27: Supported by Winston P & Ilana vdW | 40 | 2023-06-29 | 2023-06-29 | 208974.55 |  | {"MANDT":"111","REFERENCE":90000460,"ONEVIEW":"76554X","DATE01":"2023-01-25","DATE02":"2023-04-17","DATE03":"2023-05-10","DATE04":"2023-05-23","DATE05":"2023-07-14","DATE06":"2023-07-23","DATE07":"2023-08-12","DATE08":"2023-09-02","DATE09":"2023-10-17","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":32,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-23","FORECAST_END":"2023-08-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE11 | 2023-07-23 | 2023-08-12 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000096260 | 181717 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000461 | Absa Village Square Randfontein Paint Br | Absa Village Square Randfontein Paint Br |  |  | Region 1 |  | 77666X | 1000-71401-01 | The Village Square-Main Reef Rd-Randfontein | N | 2023-06-26 | 2023-06-26 |  | ASP-GS0703 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 98282.45 |  | 1 | 2023-07-11 |  | 0 | Project was put on hold | {"MANDT":"111","REFERENCE":90000461,"ONEVIEW":"77666X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000462 | Absa Randburg Remove vinyl flooring and paint ATM Room | Remove existing floor covering and install new vinyl flooring as per Absa specification sqm Prepare and paint wall with LUX Grey paint Allow for weekend work |  |  | Region 1 | Gauteng South | 36015X | 1000-70173-01 | Ferndale on Republic-Republic Dr-Randburg | N | 2023-06-26 | 2023-06-26 |  | ASP-GS0705 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 0 |  | 1 | 2023-06-26 |  | 0 | Project put on hold | {"MANDT":"111","REFERENCE":90000462,"ONEVIEW":"36015X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000463 | Absa Hydepark Remove vinyl flooring and paint ATM Room | Remove existing floor covering and install new vinyl flooring as per Absa specification sqm Prepare and paint wall with LUX Grey paint Allow for weekend work |  |  | Region 1 |  | 78647X | 1000-70430-01 | Hyde Park Corner-Cnr William Nicol Dr & Jan Smuts Ave-Sandton | N | 2023-06-26 | 2023-06-26 |  | ASP-GS0706 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-06-25 | D | 0 |  | 1 | 2023-06-26 |  | 0 |  | {"MANDT":"111","REFERENCE":90000463,"ONEVIEW":"78647X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000464 | Absa Glenfair Dilaps | Absa Glenfair Dilaps |  |  | Region 1 | Gauteng South | 76510X | 1000-70276-01 | Absa Glen fair Boulevard Dilaps | N | 2023-06-26 | 2023-06-26 |  | ASP-GN0213 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-06-26 | D | 128092 | Approved at CB/BTB | 100 | 2023-06-28 | 2023-06-29 | 128092 | Approved | {"MANDT":"111","REFERENCE":90000464,"ONEVIEW":"76510X","DATE01":"2023-04-17","DATE02":"2023-04-24","DATE03":"2023-05-15","DATE04":"2023-05-22","DATE05":"2023-06-12","DATE06":"2023-06-26","DATE07":"2023-06-26","DATE08":"2023-07-17","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-26","FORECAST_END":"2023-06-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000095204 | PHASE09 | 2023-06-26 | 2023-06-26 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-06-30 | 128092.54 | 0 |  |  | C000095204 | 111384.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000465 | Various- Cholera awareness campaign | Various- Cholera awareness campaign |  |  | Region 1 | National | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | U | 2023-07-07 | 2023-12-15 |  | ASP-N00059 | REL BUDG AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2023 |  | U |  | LOUISR | 2023-06-27 | D | 9473.13 | 2023.06.29: Approved by Conrad M | 100 | 2023-06-29 | 2023-06-29 | 8695.15 | Approved | {"MANDT":"111","REFERENCE":90000465,"ONEVIEW":"21526X","DATE01":"2023-04-28","DATE02":"2023-05-05","DATE03":"2023-05-26","DATE04":"2023-06-02","DATE05":"2023-06-23","DATE06":"2023-07-07","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":54,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-07","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TEwtIDE4LzA3LzIwMjMtIFByb2plY3Qgc3RpbGwgaW4gcHJvZ3Jlc3Mu","RATING":""} |  |  | C000096267 | PHASE11 | 2023-07-07 | 2023-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-07-06 | 7561 | 0 |  |  | C000096267 | 7561 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000466 | Absa Warrenton - Replace Banking Hall fl | Absa Warrenton - Replace Banking Hall fl |  |  | Region 3 | [5 empty] | 2023-08-30 |  |  | ASP-CR0457 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-30 | 2023-09-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000467 | 270RR- Replacement of fire extinguishers | 270RR- Replacement of fire extinguishers |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-07-07 | 2023-12-15 |  | ASP-GS0707 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-06-28 | D | 0 | Project cancelled. | 1 |  |  | 0 | [5 empty] | PHASE00 | 2023-07-07 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000468 | Various-Replacement of UPS batteries at | Various-Replacement of UPS batteries at |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-07-07 | 2023-12-15 |  | ASP-N00060 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-06-28 | D | 0 | Approved at BTB | 100 |  |  | 0 | [5 empty] | PHASE06 | 2023-07-07 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000469 | Various-Replacement of UPS batteries at | Various-Replacement of UPS batteries at |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-07-07 | 2023-12-15 |  | ASP-N00061 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-06-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE05 | 2023-07-07 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000470 | Various-Replacement of UPS batteries at | Various-Replacement of UPS batteries at |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-07-07 | 2023-12-15 |  | ASP-N00062 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-06-28 | D | 0 | Approved at BTB |  |  |  | 0 | [5 empty] | PHASE05 | 2023-07-07 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000471 | Absa Worcester - Minor Works | Absa Worcester - Minor Works |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester-Stockenstrom St-Worcester | U | 2023-08-01 | 2023-09-30 |  | ALP-WC0025 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-06-28 | D | 1708223.4 |  | 100 | 2023-07-18 | 2023-08-03 | 1708223.4 | Absa Ref : 240129_148 Contingency Remaining R 37 593.50 | {"MANDT":"111","REFERENCE":90000471,"ONEVIEW":"78016X","DATE01":"2023-03-22","DATE02":"2023-06-14","DATE03":"2023-07-11","DATE04":"2023-07-18","DATE05":"2023-08-03","DATE06":"2023-10-23","DATE07":"2023-11-20","DATE08":"2023-12-04","DATE09":"2024-01-18","DATE10":"2024-01-31","DATE11":"2024-01-16","DATE12":"2024-01-16","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":85,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"315:84:27:7:16:81:28:14:45:15","PROGRESS":95,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-23","FORECAST_END":"2023-11-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OSBGZWIgMjAyNCBQTyBpc3N1ZWQgLSBDMDAwMTQwOTYyIC0gTm90ZSBGaW5hbCBQT0Mgd2FzIHN1Ym1pdHRlZCA0IERlYyAyMyB3aXRoIDIwMjMgUE8gQzAwMDExMTIzOAo0IERlYyBQYXJ0IDMgYW5kIEZpbmFsIFBPQyBTdWJtaXR0ZWQgZm9yIFIgNTMgNDkyLjI1IC0gVG90YWwgUiAxIDUzNSAwMDQuMzAgQ29udGluZ2VuY3kgUmVtYWluaW5nIFIgMzcgNTkzLjUwCjMwIE5vdiBQYXJ0IDIgUE9DIFN1Ym1pdHRlZCBSIDEgMzY1IDc5Ni43NSBUb3RhbCB0byBEYXRlIC0gUiAxIDQ4MSA1MTIuMDUKMjcgTm92IC0gUHJhY3RpY2FsIENvbXBsZXRpb24gQWNoaWV2ZWQsIFNuYWdzIG9uIHRoZSBjdXN0b21lciBjb3VudGVycyBjb21wbGV0ZWQgb24gMjYgTm92IC0gRmluYWwgU2lnbm9mZiBwZW5kaW5nCjIwIE5vdiAtIEluc3BlY3Rpb24gZm9yIHNpZ25vZmYgYmVpbmcgY29uZHVjdGVkIDIwIE5vdgoxNyBOb3YgUHJvamVjdCBPbmdvaW5nClZPIGFwcHJvdmVkIGZvciAyeCBGcmlkZ2VzIC0gNDUwMDg3MzIyNCAtIE1pbGUgU3RvbmUKOCBOb3YgUGFydCAxIFBPQyBTdWJtaXR0ZWQgZm9yIFMmRyBTaWducyBSIDExNTcxNS4zMCAtIFByb2plY3QgT25nb2luZwo2IE5vdiBXb3JrcyBvbmdvaW5nLCBjb21wbGV0ZWQgZ3JvdW5kIGZsb29yIGFibHV0aW9uIGFuZCBLaXRjaGVuICsgU2lnbmFnZSwgUGFydCBwYXltZW50IGZvciBzaWduYWdlCjIzIE9jdCBTdGFydGVkIG9uIFNpdGUgMjMgT2N0CjE4IE9jdC4gT0hTIEFwcHJvdmVkIC0gV29yayB0byBjb21tZW5jZSAyM3JkIE9DVAowOSBPY3QgLSBDYWxsIE9IUyByZSBwcm9wb3NlZCBzdGFydCAyMyBPY3QgYXMgcGVyIGJyYW5jaAoyMiBTZXB0IE9IUyBTdWJtaXR0ZWQgMTUgU2VwdCAtIEZlZWRiYWNrIHBlbmRpbmcgLSByaXNrIG9mIGZpbmFuY2lhbCBSb2xsb3ZlcgpGTSBQcm9qZWN0IGlzIGNvbXBsZXRlZCBjbG9zZWQgb24gMjcvMDIvMjAyNC4=","RATING":"Medium"} |  |  | C000111238 | PHASE11 | 2023-10-23 | 2023-11-20 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-18 | 1485411.65 | 109481.1 |  |  | C000140962 | 1375930.55 |  | 51750 |  | 14156.5 | 37593.5 | C000140962 | 1582320.13 |  | 0 |  |  | 2024-02-08
90000472 | Absa Wibsa Upington - Replacement of LED | Absa Wibsa Upington - Replacement of LED |  |  | Region 3 |  | 36271X | 1000-71336-01 | Wibsa Upington-Schroder St-Upington |  | 2023-08-30 |  |  | ASP-CR0458 | CRTD: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-29 | D | 0 |  | 15 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000472,"ONEVIEW":"Unknown","DATE01":"2023-06-21","DATE02":"2023-06-28","DATE03":"2023-07-19","DATE04":"2023-07-26","DATE05":"2023-08-16","DATE06":"2023-08-30","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-30","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Tm90IGltcGxlbWVudGVkLg==","RATING":""} |  |  |  | PHASE00 | 2023-08-30 | 2023-09-29 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000473 | Absa Ottosdal - Supply of Staff Chairs | Absa Ottosdal - Supply of Staff Chairs |  |  | Region 3 |  | 78143X | 1000-71606-01 | Absa Ottosdal-Voortrekker St-Ottosdal |  | 2023-07-31 |  |  | ASP-CR0459 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-29 | D | 0 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Leko N & Ilana vdW | 100 | 2023-07-06 | 2023-07-06 | 16180.5 | Approved | {"MANDT":"111","REFERENCE":90000473,"ONEVIEW":"Unknown","DATE01":"2023-05-22","DATE02":"2023-05-29","DATE03":"2023-06-19","DATE04":"2023-06-26","DATE05":"2023-07-17","DATE06":"2023-07-31","DATE07":"2023-10-11","DATE08":"2023-11-01","DATE09":"2023-12-16","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:7:21:7:21:14:72:21:45:26","PROGRESS":30,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-31","FORECAST_END":"2023-10-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBpbXBsZW1lbnRhdGlvbi4=","RATING":""} |  |  | C000096889 | PHASE07 | 2023-07-31 | 2023-10-11 | NANDE MAQUBELA | Juanita Van Coller | 23000043 |  |  |  |  | 2023-07-10 | 14070 | 0 |  |  | C000096889 | 14070 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000474 | Absa Vryburg - Supply & Apply Graphic Vi | Absa Vryburg - Supply & Apply Graphic Vi |  |  | Region 3 |  | 77745X | 1000-71604-01 | Vryburg-Market St-Vryburg |  | 2023-08-02 |  |  | ASP-CR0460 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-29 | D | 0 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Leko N & Ilana vdW | 100 | 2023-07-06 | 2023-07-06 | 89115.77 | Approved | {"MANDT":"111","REFERENCE":90000474,"ONEVIEW":"77745X","DATE01":"2023-05-24","DATE02":"2023-05-31","DATE03":"2023-06-21","DATE04":"2023-06-28","DATE05":"2023-07-19","DATE06":"2023-08-02","DATE07":"2023-09-01","DATE08":"2023-09-22","DATE09":"2023-11-06","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-02","FORECAST_END":"2023-09-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEludm9pY2luZyBpbiBwcm9ncmVzcy4=","RATING":""} |  |  | C000124775 | PHASE11 | 2023-08-02 | 2023-09-01 | NANDE MAQUBELA | Juanita Van Coller | 23000043 |  |  |  |  | 2023-11-20 | 9969.63 | 0 |  |  | C000096822 | 77491.98 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000475 | Absa Kroonstad (Corner President) -TCR R | Absa Kroonstad (Corner President) -TCR R |  |  | Region 3 |  | 78677X | 1000-71550-01 | Absa Building Kroonstad-Cnr President & Cross Hill St-Kroonstad |  | 2023-09-28 |  |  | ASP-CR0461 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-29 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 227536.22 |  | {"MANDT":"111","REFERENCE":90000475,"ONEVIEW":"78677X","DATE01":"2023-07-20","DATE02":"2023-06-28","DATE03":"2023-07-10","DATE04":"2023-08-24","DATE05":"2023-09-14","DATE06":"2023-09-28","DATE07":"2023-10-09","DATE08":"2023-10-30","DATE09":"2023-12-14","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":20,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"195:-22:12:45:21:14:11:21:45:29","PROGRESS":6,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-28","FORECAST_END":"2023-10-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  | C000112434 | PHASE07 | 2023-09-28 | 2023-10-09 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-09-22 | 197857.58 | 160230.76 |  |  | C000140951 | 37626.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000476 | Absa Vincent Office Park - Plugs | Absa Vincent Office Park - Plugs |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Vincent Office Park-Western Ave-East London | N | 2023-08-01 | 2023-10-31 |  | ASP-EC0326 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-29 | D | 42850 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Rob L | 100 | 2023-07-06 | 2023-07-06 | 42850 | Approved | {"MANDT":"111","REFERENCE":90000476,"ONEVIEW":"79369X","DATE01":"2023-06-28","DATE02":"2023-06-28","DATE03":"2023-06-29","DATE04":"2023-07-06","DATE05":"2023-07-06","DATE06":"2023-07-24","DATE07":"2023-07-28","DATE08":"2023-08-18","DATE09":"2023-10-02","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:1:7:0:18:4:21:45:26","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-24","FORECAST_END":"2023-07-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"T24gb3JkZXIgZXhwZWN0ZWQgZGVsaXZlcnkgd2VlayBvZiAyNHRoIEp1bHk=","RATING":""} |  |  | C000096893 | PHASE11 | 2023-08-24 | 2023-08-24 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-10 | 37260.87 | 0 |  |  | C000096893 | 37260.87 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000477 | Various EC Branches - 7 Deep sea control | Various EC Branches - Deep Se Controllers - Only Branch to receive - Burgersdorp - EC |  |  | Region 2 | Eastern Cape | Various EC | 1000-71063-01 | Various Sites EC | N | 2023-10-31 |  |  | ASP-EC0327 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Laxine Maliffe |  |  | 2023 |  | U |  | CEASARS | 2023-06-29 | D | 77501.54 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Rob L | 100 | 2023-07-13 | 2023-07-13 | 77501.54 | Approved | {"MANDT":"111","REFERENCE":90000477,"ONEVIEW":"Various EC","DATE01":"2023-01-19","DATE02":"2023-05-18","DATE03":"2023-06-26","DATE04":"2023-07-13","DATE05":"2023-07-13","DATE06":"2023-08-28","DATE07":"2023-09-01","DATE08":"2023-09-22","DATE09":"2023-11-06","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:119:39:17:0:46:4:21:45:25","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-28","FORECAST_END":"2023-09-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVseSBQTydzIGluIFByb2dyZXNzIA==","RATING":"Low"} |  |  | C000098565 | PHASE11 | 2023-09-19 | 2023-09-22 | RODERICK NEVAY | Juanita van Coller | 23000099 |  |  |  |  | 2023-07-18 | 67392.64 | 0 |  |  | C000098565 | 67392.64 | CIP2023XP | 7045.59 |  | 0 | 0 |  | 0 |  | 0
90000478 | Absa Bluff Hillside - LED lights Replace | Absa Bluff Hillside - LED lights Replace |  |  | Region 3 |  | Unknown | 1000-71167-01 | Unknown Building - not in our database |  | 2023-08-10 |  |  | ASP-KZ0259 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-06-29 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000117082 | PHASE00 | 2023-08-10 | 2023-09-09 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-16 | 384078.4 | 0 |  |  | C000141153 | 384078.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000479 | Absa Roggebaai Lower Long - Dilaps Close | Absa Roggebaai Lower Long - Dilaps Close |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | N | 2023-09-01 | 2023-12-31 |  | ALP-WC0026 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-06-29 | D | 530384.96 | Approved at CB/BTB | 100 | 2023-07-03 | 2023-06-30 | 530384.96 | Approved | {"MANDT":"111","REFERENCE":90000479,"ONEVIEW":"77657X","DATE01":"2023-06-05","DATE02":"2023-06-12","DATE03":"2023-06-30","DATE04":"2023-07-03","DATE05":"2023-07-03","DATE06":"2023-07-06","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:18:3:0:3:25:21:45:25","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-06","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgQXVnIC0gUGFydCAxIFBPQyBTdWJtaXR0ZWQgMjEgQXVnIFIgMTY4IDgzMi44NiAtIGZvciBTJkcgRGlsYXBzLCBTJkcgTGlmZXN0eWxlIGdyYXBoaWNzLCBTZWN1dGVsLCBHbG9iYWwgQWNjZXNzLCBDYXBlIFdlc3QsIFN0YW5kYnkgU3lzdGVtcw==","RATING":"Low"} |  |  | C000095468 | PHASE11 | 2023-07-06 | 2023-07-31 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-07-03 | 461204.31 | 0 |  |  | C000095468 | 461204.31 |  | 46313.02 |  | 0 | 0 |  | 0 |  | 0
90000480 | Absa King Williams Town - Plugs | Absa King Williams Town - Plugs |  |  | Region 2 | Eastern Cape | 78329X | 1000-71043-01 | Absa King Williams Town-Cnr Cathcart & Maclean St-King Williams Town | N | 2023-09-01 | 2023-10-31 |  | ASP-EC0328 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-06-30 | D | 27374.95 |  | 1 | 2023-07-20 | 2023-07-27 | 0 | 25 July Cancelled as Branch is undergoing revamp / rebuild late in 2023 Submitted for CB 27 July | {"MANDT":"111","REFERENCE":90000480,"ONEVIEW":"78329X","DATE01":"2023-06-30","DATE02":"2023-07-07","DATE03":"2023-07-21","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-08-07","DATE07":"2023-08-11","DATE08":"2023-09-01","DATE09":"2023-10-16","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:14:-1:7:11:4:21:45:26","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-07","FORECAST_END":"2023-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VibWl0dGVkIGZvciBDQiBhcHByb3ZhbCAyNyBKdWx5","RATING":""} |  |  |  | PHASE12 | 2023-08-07 | 2023-08-11 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000481 | Alice Lane Podium CPF Fish Bowel Due Diligence Report | Alice Lane Podium CPF Fish Bowel Due Diligence Report |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-07-03 | 2023-07-17 |  | ASP-GS0708 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | MOKOENAM2 | 2023-06-30 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 110829.18 |  | {"MANDT":"111","REFERENCE":90000481,"ONEVIEW":"35041X","DATE01":"2023-04-24","DATE02":"2023-05-01","DATE03":"2023-05-22","DATE04":"2023-05-29","DATE05":"2023-06-19","DATE06":"2023-07-03","DATE07":"2023-07-17","DATE08":"2023-08-07","DATE09":"2023-09-21","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-03","FORECAST_END":"2023-07-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000096193 | PHASE07 | 2023-07-03 | 2023-07-17 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-05 | 110829.18 | 0 |  |  | C000096193 | 96373.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000482 | Installation of Glass Panel Vinyl on the 3rd-floor Legal Area | Installation of Glass Panel Vinyl on the 3rd-floor Legal Area |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-07-10 | 2023-07-31 |  | ASP-GS0709 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | MOKOENAM2 | 2023-06-30 | D | 0 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Rhulani N | 100 | 2023-07-06 | 2023-07-06 | 13856.81 | Approved | {"MANDT":"111","REFERENCE":90000482,"ONEVIEW":"35041X","DATE01":"2023-05-01","DATE02":"2023-05-08","DATE03":"2023-06-30","DATE04":"2023-07-14","DATE05":"2023-07-20","DATE06":"2023-07-10","DATE07":"2023-07-31","DATE08":"2023-08-21","DATE09":"2023-10-05","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-10","FORECAST_END":"2023-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBDQiBhcHByb3ZhbC4=","RATING":""} |  |  | C000097246 | PHASE08 | 2023-07-10 | 2023-07-31 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-11 | 13856.81 | 0 |  |  | C000097246 | 12049.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000483 | Absa Moffett Office Park - Meeting Room | Absa Moffett Office Park - Convert Room 2.14 into MTR meeting room. |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-10-01 | 2023-12-31 |  | ALP-EC0018 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-06-30 | D | 768233.45 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B & Ilana vdW | 100 | 2023-07-20 | 2023-07-20 | 768233.45 | Absa Ref : 240129_166 | {"MANDT":"111","REFERENCE":90000483,"ONEVIEW":"22937X","DATE01":"2023-06-02","DATE02":"2023-06-09","DATE03":"2023-06-30","DATE04":"2023-07-14","DATE05":"2023-07-20","DATE06":"2024-02-19","DATE07":"2024-02-29","DATE08":"2024-03-15","DATE09":"2024-04-29","DATE10":"2024-04-30","DATE11":"2024-02-19","DATE12":"2024-02-19","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"333:7:21:14:6:214:10:15:45:24","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-19","FORECAST_END":"2024-02-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIC0gT21lZ2EgVGVhbSBvbnNpdGUsIHBsdWdzIGxlZnQgSkhCIDE2IEZlYgoxNSBGRUIgVk8gUE8ncyBpc3N1ZWQgLSA0NTAwODg5NzE5IENTIFNvbHV0aW9ucywgNDUwMDg4OTcyMCBNZWludGVpbgo5IEZlYiDDosKAwpMgT24gVHJhY2sgw6LCgMKTIEVxdWlwbWVudCBkZWxpdmVyZWQgdG8gUG9ydCBFbGl6YWJldGgKOSBGZWIgUE8gQzAwMDE0MDk2NCBpc3N1ZWQgZm9yIHJvbGxvdmVyCjUgRmViIC0gTWVldGluZyB3aXRoIElUIGFuZCBPbWVnYSB0byBkZXRlcm1pbmUgTmV0d29yayBuZWVkcywgTGVncyBhbmQgUGx1Z3MgdG8gYmUgc3VibWl0dGVkIGZvciBBcHByb3ZhbAoyOSBKYW4gLSBDb3N0cyBmb3IgcGx1Z3MgYW5kIExlZ3MgdG8gYmUgZmluYWxpc2VkIEFTQVAKMjIgSmFuIGRhdGVzIHNldCBmcm9tIDE5IEZlYiB0byAyNiBGZWIKMTggSmFuIC0gUXVvdGUgZm9yIFRWJ3MgZnJvbSBHQS4gCjE0IERlYyBJbnN0YWxsYXRpb24gcGVuZGluZyBFbmQgSmFudWFyeSAyMDI0IHRvIE1pZCBGZWIKNCBEZWMgLSBNZWV0aW5nIGhlbGQgd2l0aCBWZW5kb3Igb24gc2l0ZSAzMCBOb3YsIGRpc2N1c3Npb24gaGVsZCByZSBvcHRpb25zIG9mIHBsdWcgcG9pbnRzLCBwb3NzaWJpbGl0eSBvZiBmb3IgYWRkaXRpb25hbCBUVidzLiBQTSB0byBjaGVjayB3aXRoIE9tZWdhIHJlIFRWIE9wdGlvbnMgYW5kIGZvbGxvdyB1cCByZSBhZGRpdGlvbmFsIExlZ3MuIEZlZWRiYWNrIHBlbmRpbmcgcmUgZGVsaXZlcnkgb2YgZXF1aXBtZW50IGFuZCBwcm9qZWN0IHBsYW4uCjI3IE5vdiBQTSByZXF1ZXN0IFZlbmRvciBmb3IgZm9ybWFsIHJlc3BvbnNlIGZyb20gT21lZ2EgcmUgdGhlIGRlbGl2ZXIgb2YgdGhlIGVxdWlwbWVudCBhbmQgbG9naXN0aWNzIGFyb3VuZCB0aGUgSW1wb3J0cyB0aHJvdWdoIHBvcnRzCjIwIE5vdiBQTSB0byBmb2xsb3dlZCB1cCBpbiB0ZXJtcyBvZiBQcm9qZWN0IFByb2dyYW0gbGVhZCB0aW1lIGNvbmZpcm1hdGlvbiBmcm9tIE9tZWdhIGFzIFBPJ3MgSXNzdWVkCjE3IE5vdiBCViBQTyBJc3N1ZWQgLSA0NTAwODczMjE3IE9tZWdhIAoxNyBOb3YgU2Vjb25kIGFuZCBUaGlyZCBmb2xsb3cgdXAgc2VudAoxNiBOb3YgRm9sbG93IHVwIFNlbnQgcmUgUE8KMTUgTm92IEFic2EgUE8gQzAwMDEyMzUzOCByZWNlaXZlZCBCViBQTyByZXF1ZXN0ZWQKMTQgTm92IC0gQWJzYSBQTyBSZXF1ZXN0ZWQgZnJvbSBBYnNhIGZpbmFuY2UKMTMgTm92IFNpZ25lZCBXQSByZWNlaXZlZCBBYnNhIFBPIHRvIGJlIHJlcXVlc3RlZAoxMyBOb3YgRm9sbG93IHVwIGVtYWlsIHNlbnQKMTAgTm92IEZvbGxvdyB1cCBFbWFpbCBzZW50CjggTm92IFNpZ25lZCBvZmYgYnkgQmlkdmVzdCBzZW50IHRvIEFic2EgZm9yIGZpbmFsIFNpZ25hdHVyZQo3IE5vdiBBcHByb3ZlZCBXQSByZWNlaXZlZCBzdWJtaXR0ZWQgZm9yIEJWIFNpZ25vZmYKNiBOb3YgUE0gRm9sbG93ZWQgdXAgd2l0aCBQcm9jdXJlbWVudCByZSBXQSBBcHByb3ZhbAozIE5vdiBUZWNobmljYWwgU3VwcG9ydCByZWNlaXZlZCBmcm9tIENSRVMgaW4gb3JkZXIgdG8gaGF2ZSBmaW5hbCBhcHByb3ZhbCBmcm9tIEFic2EgTGVnYWwKMSBOb3YgUmVjZWl2ZWQgYmFjayBmcm9tIFByb2N1cmVtZW50IHdpdGggYWRkaXRpb25hbCBjb21tZW50cyBhZGRlZCBieSBMZWdhbCAtIFVwZGF0ZWQgYW5kIHJlc2VudCB0byBQcm9jdXJlbWVudAozMSBPY3QgV0Egc3VibWl0dGVkIGJ5IHByb2N1cmVtZW50IHRvIExlZ2FsIDMxIE9DVAozMCBPY3QgLSBGb2xsb3cgdXAgTWVldGluZyB3aXRoIFByb2N1cmVtZW50IDMwIE9jdCwgUE0gdG8gYWR2aXNlIHdoZW4gdG8gYmUgYXBwcm92ZWQuCjI3IE9jdCBQTSBmb2xsb3dpbmcgdXAgZGFpbHkgaW4gdGVybXMgb2YgV0EgYXBwcm92YWwKMjMgT2N0IFBNIHRvIGZvbGxvdyB1cCB3aXRoIFByb2N1cmVtZW50IHJlIFdBCjE2IE9jdCBQTSB0byBmb2xsb3cgdXAgd2l0aCBQcm9jdXJlbWVudCByZSBXQSB0byByZXNvbHZlIHRlY2huaWNhbGl0aWVzIG9mIHRoZSB3b3JrcyBpbnZvbHZlZC4KMTAgT2N0IFJQTSBmb2xsb3dlZCB1cCA1IE9jdCBGb2xsb3cgdXAgbWVldGluZyBoZWxkIHRvIHdpdGggQWJzYSBGaW5hbmNlIC8gTGVnYWwgZmluYWxpc2UgdGhlIFdBLCBQZXJtaXNzaW9uIGhhcyBiZWVuIHJlcXVlc3RlZCB0byBpc3N1ZSBCViBQTy4KMjIgU2VwdCBXQSBzZW50IHRvIEFic2EgU291cmNpbmcgZm9yIGFwcHJvdmFsIFBNIHRvIGZvbGxvdyB1cCwgIFdpbGwgYmUgYSBGaW5hbmNpYWwgUm9sbG92ZXIKMTggU2VwdCAtIFBNIHRvIGZvbGxvdyB1cCByZSBXQQoxMSBTZXB0IC0gUmVjZWl2ZWQgZnJvbSBQcm9jdXJlbWVudCA4IFNlcHQgLXJldmlzZWQgV0EgdG8gYmUgc3VibWl0dGVkIDExIFNlcHQKNSBTZXB0IC0gV0Egd2FzIHJldmlld2VkIGJ5IFBhbGVzYS4gUmVzdWJtaXNzaW9ucyB0byBiZSBmb3J3YXJkZWQgb24gMDcvMDkgYXMgYWRkaXRpb25hbCBpbmZvcm1hdGlvbiBoYXMgYmVlbiByZXF1ZXN0ZWQgCkJpZHZlc3QgT0hTIHJldmlldyBjb21wbGV0ZWQgYW5kIGFwcHJvdmVkIGFzIGEgTWVkaXVtIFJpc2sKMjggQXVnIC0gV0Egc3VibWl0dGVkIHRvIEJWIExlZ2FsIHRvIGFkdmlzZQoxNCBBdWcgV0EgdG8gYmUgc3VibWl0dGVkIDE0IEF1Zwo3IEF1ZyAtIFdBIHRvIGJlIHN1Ym1pdHRlZCA3IEF1ZwoyOCBKdWx5IE5vdGVkIGluIHRoZSBEZWNrIHJlY2VpdmVkIHJlcXVlc3RlZCBjb25maXJtYXRpb24gZnJvbSB0aGUgVlAgYXMgd2FzIGluZGljYXRlZCBpbiBNZWV0aW5nIGFzIG9uIEhvbGQKMjAgSnVseSBQbGFjZWQgb24gaG9sZCBhdCBCVEIgcGVuZGluZyBDYXBpdGFsIFByb2plY3RzIGFuZCBwcm9wb3NlZCBhZGRpdGlvbmFsIHJlY29uZmlndXJhdGlvbgoxNCBKdWx5IEluY2x1ZGVkIGluIEJUQiBwYWNrcyBmb3IgYXBwcm92YWwgMjAgSnVseQozIEp1bHkgLSBCRUUgQ2VydGlmaWNhdGUgcmVjZWl2ZWQgdG8gYmUgc2hhcmVkIHdpdGggQWJzYSBQcm9jdXJlbWVudAoyNiBKdW5lIC0gUE0gdG8gZW5nYWdlIEJWIHByb2N1cmVtZW50IHRvIGZpbmQgbmV4dCBzdGVwcwpXYXMgQVNQLUVDMDI5NwoxOSBKdW5lIC0gUE0gdG8gZW5nYWdlIHByb2N1cmVtZW50IGZvciBhcHByb3ZhbCB0byBjb21waWxlIEJDIGZvciBCVEIgc3VibWlzc2lvbgo1IEp1bmUgUm9vbSB0byBiZSBjb25maXJtZWQgd2l0aCBKdWxlcyBhbmQgY29zdGluZ3MgdG8gYmUgZmluYWxpc2VkIGZvciBDQiBzdWJtaXNzaW9uCjIgSnVuZSBSZXF1ZXN0ZWQgdG8gcHJvY2VlZCB3aXRoIE1UUiBSb29tCjEyIE1heSBQbGFjZWQgb24gaG9sZCBhcyBwZXIgbWFpbCBmcm9tIENSRVMgVlAKOCBNYXkgLSBQb3NzaWJsZSByZWxvY2F0aW9uIHRvIG5ldyBzaXRlLCBQTSBmb2xsb3dpbmcgdXAgcmUgTVRSIHJvb20gcXVvdGVzIAozIE1heSAtIFBNIGZvbGxvd2luZyB1cCByZSBxdW90ZXMgZm9yIE1UUiByb29tLCBUcmFpbmluZyBSb29tcyBwYXJ0aXRpb24gYW5kIGVsZWN0cmljYWwgcXVvdGVzIHJlY2VpdmVkCjI0IEFwcmlsIC0gT21lZ2EgaGFzIHZpc2l0ZWQsIHN0YWNrZXIgZG9vciBwb3NzaWJsZSBzdHJ1Y3R1cmFsIGlzc3VlZC4KMyBBcHIgLSBXb3JraW5nIGRyYXdpbmdzIHJlcXVlc3RlZCAtIEVuZ2luZWVyaW5nIGlucHV0cyB0byBiZSByZXF1ZXN0ZWQKMTMgTWFyIC0gUE0gdG8gZm9sbG93IHVwIG9uIGRldGFpbHMgZm9yIHF1b3RlcyAKNiBNYXIgdG8gY29udmVydCB0aGUgZXhpc3RpbmcgMi4xNCBpbnRvIGEgTVRSIG1lZXRpbmcgUm9vbSByZXF1ZXN0IFF1b3RlIGZyb20gIlgiCjYgRmViIC0gVlAgcHV0IG9uIGhvbGQgZm9yIG5vdwoxMyBNYXJjaCBNaWtlIEFkZGVk","RATING":"Low"} |  |  | C000123538 | PHASE09 | 2024-02-19 | 2024-03-07 | RODERICK NEVAY | Floyd Mofokeng | 23000078 |  |  |  |  | 2023-11-15 | 668029.09 | 0 |  |  | C000140964 | 668029.09 | CIP2023XP | 66513.72 |  | 36698.39 | 29815.33 | C000140964 | 768233.45 |  | 0 |  |  | 2024-02-08
90000484 | Absa Woodmead UPS Retrospective | Absa Woodmead UPS Retrospective |  |  | Region 1 |  | SGC_13891 | 1000-67320-01 | Woodmead |  | 2023-07-03 | 2023-07-03 |  | ASP-GN0214 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-07-03 | D | 91847.44 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000484,"ONEVIEW":"SGC_13891","DATE01":"2023-04-24","DATE02":"2023-05-01","DATE03":"2023-05-22","DATE04":"2023-05-29","DATE05":"2023-06-19","DATE06":"2023-07-03","DATE07":"2023-07-03","DATE08":"2023-07-24","DATE09":"2023-09-07","DATE10":"2023-09-30","DATE11":"2023-09-07","DATE12":"2023-09-07","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-03","FORECAST_END":"2023-07-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUHJvamVjdCBjb21wbGV0ZS4gQXdhaXRpbmcgQWJzYSBQTyB0byBkbyBmaW5hbCBQT0Mu","RATING":""} |  |  | C000125071 | PHASE08 | 2023-07-03 | 2023-07-03 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-11-21 | 79867.34 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000485 | Absa Southern Life (Mangaung) - UPS Repl | Absa Southern Life (Mangaung) - UPS Repl |  |  | Region 3 |  | Unknown | 1000-71535-01 | Unknown Building - not in our database |  | 2023-08-30 |  |  | ASP-CR0462 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-04 | D | 0 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Rob L | 100 | 2023-07-13 | 2023-07-13 | 63598.95 | Approved | {"MANDT":"111","REFERENCE":90000485,"ONEVIEW":"Unknown","DATE01":"2023-06-21","DATE02":"2023-06-07","DATE03":"2023-06-07","DATE04":"2023-06-15","DATE05":"2023-07-17","DATE06":"2023-07-20","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-20","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGludm9pY2luZyBpbiBwcm9ncmVzcw==","RATING":""} |  |  | C000098570 | PHASE11 | 2023-07-20 | 2023-09-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-07-18 | 55303.44 | 0 |  |  | C000098570 | 55303.44 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000486 | Absa Towers West Screens for 7th flr Bal | Absa Towers West Screens for 7th flr Bal |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-07-04 | 2023-07-04 |  | ASP-GS0710 | REL BUDG AVAC SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-07-04 | D | 0 | 2023.07.06: Approved by Conrad M 2023.07.04: Supported by Winston P | 100 | 2023-07-06 | 2023-07-06 | 222492 | Approved | {"MANDT":"111","REFERENCE":90000486,"ONEVIEW":"21526X","DATE01":"2023-04-25","DATE02":"2023-05-02","DATE03":"2023-05-23","DATE04":"2023-05-30","DATE05":"2023-06-20","DATE06":"2023-07-04","DATE07":"2023-07-04","DATE08":"2023-07-25","DATE09":"2023-09-08","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-04","FORECAST_END":"2023-07-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000097247 | PHASE07 | 2023-07-04 | 2023-07-04 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-11 | 222492 | 0 |  |  | C000097247 | 193471.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000487 | WC Various Branches - Furniture | WC Various Branches - Furniture |  |  | Region 2 | Western Cape | Unknown | 1000-70890-01 | Unknown Building - not in our database |  | 2023-09-01 | 2023-10-31 |  | ASP-WC0293 | CRTD DLFL AVAC SETC: |  | false | true |  | Nyasha Wena |  |  | 2023 |  |  |  | CEASARS | 2023-07-04 | D | 78650.11 |  | 40 | 2023-07-20 |  | 78650.11 |  | {"MANDT":"111","REFERENCE":90000487,"ONEVIEW":"78132X","DATE01":"2023-06-23","DATE02":"2023-06-30","DATE03":"2023-07-21","DATE04":"2023-07-28","DATE05":"2023-08-18","DATE06":"2023-09-01","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-01","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | DELETED | 2023-08-24 | 2023-10-23 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 68391.4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000488 | Absa Oude Bloemhof Stellenbosch - DHA Minor Works | Absa Oude Bloemhof Stellenbosch- DHA Minor Works |  |  | Region 2 | Western Cape | 77946X | 1000-70866-01 | Oude Bloemhof Building-Cnr Van Ryneveld & Plein St-Stellenbosch | N | 2023-09-01 | 2023-10-31 |  | ASP-WC0294 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-04 | D | 83093.46 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Judith B & Ilana vdW | 100 | 2023-07-20 | 2023-07-27 | 83093.46 | Approved | {"MANDT":"111","REFERENCE":90000488,"ONEVIEW":"77946X","DATE01":"2023-06-26","DATE02":"2023-06-26","DATE03":"2023-07-10","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-08-16","DATE07":"2023-09-04","DATE08":"2023-09-25","DATE09":"2023-11-09","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"157:0:14:10:7:20:19:21:45:3","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-16","FORECAST_END":"2023-09-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBTZXB0IC0gU2lnbmFnZSBDb21wbGV0ZWQgb24gMDQuMDkuMjMgLiBGaW5hbCBJbnNwZWN0aW9uIG9uIDA2LjA5LjIz","RATING":"Low"} |  |  | C000100701 | PHASE11 | 2023-08-16 | 2023-09-04 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-07-28 | 72255.18 | 0 |  |  | C000100701 | 72255.18 |  | 3878.26 |  | 0 | 0 |  | 0 |  | 0
90000489 | Absa Riverside Mall Rondebosch - Dilaps | Absa Riverside Mall Rondebosch - Dilaps |  |  | Region 2 | Western Cape | 77247X | 1000-70810-01 | Riverside Mall-Cnr Main & Belmont Rd-Rondebosch |  | 2023-09-01 | 2023-12-31 |  | ASP-WC0295 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  |  |  | CEASARS | 2023-07-04 | D | 232138.45 |  | 100 | 2023-08-24 | 2023-08-29 | 232138.45 | Approved | {"MANDT":"111","REFERENCE":90000489,"ONEVIEW":"77247X","DATE01":"2023-07-05","DATE02":"2023-07-05","DATE03":"2023-08-24","DATE04":"2023-08-31","DATE05":"2023-08-30","DATE06":"2023-09-04","DATE07":"2023-09-15","DATE08":"2023-10-06","DATE09":"2023-11-20","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:0:50:7:-1:5:11:21:45:26","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-04","FORECAST_END":"2023-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgU2VwdCBGQURUIEludm9pY2UgT3V0c3RhbmRpbmcKMjEgU2VwdCBQT0MgMSBTdWJtaXR0ZWQgUiAyMTQgOTcyLjkwIC0gRkFEVCBPdXRzdGFuZGluZwo=","RATING":"Low"} |  |  | C000107127 | PHASE11 | 2023-09-04 | 2023-09-15 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-08-30 | 201859.52 | 0 |  |  | C000095207 | 201859.51 |  | 14324.83 |  | 0 | 0 |  | 0 |  | 0
90000490 | Absa Carnarvon - Replacement of HVAC uni | Absa Carnarvon - Replacement of HVAC uni |  |  | Region 3 |  | 79297X | 1000-71360-01 | Absa Carnarvon-Cnr Victoria & Van Riebeeck St-Carnarvon |  | 2023-11-30 |  |  | ALP-CR0038 | REL BUDG AVAC RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-04 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B & Ilana vdW | 70 | 2023-07-20 | 2023-07-20 | 588280 | Approved | {"MANDT":"111","REFERENCE":90000490,"ONEVIEW":"79297X","DATE01":"2023-09-21","DATE02":"2023-09-28","DATE03":"2023-10-19","DATE04":"2023-10-26","DATE05":"2023-11-16","DATE06":"2023-11-30","DATE07":"2023-12-30","DATE08":"2024-01-20","DATE09":"2024-03-05","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-30","FORECAST_END":"2023-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgaW1wbGVtZW50YXRpb24u","RATING":""} |  |  |  | PHASE06 | 2023-11-30 | 2023-12-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000144111 | 522310.43 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000491 | Absa Grove Plaza Fort Beaufort - Connection of equipment to UPS | Absa Grove Plaza Fort Beaufort - Connection of equipment to UPS |  |  | Region 2 | Eastern Cape | 78377X | 1000-71464-01 | The Grove Plaza-Campbell St-Fort Beaufort | N | 2023-09-01 | 2023-10-31 |  | ASP-EC0329 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-07-06 | D | 17643.32 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Rob L | 100 | 2023-07-13 | 2023-07-13 | 17643.32 | Approved | {"MANDT":"111","REFERENCE":90000491,"ONEVIEW":"78377X","DATE01":"2023-07-05","DATE02":"2023-07-06","DATE03":"2023-07-07","DATE04":"2023-07-13","DATE05":"2023-07-13","DATE06":"2023-07-24","DATE07":"2023-07-28","DATE08":"2023-08-18","DATE09":"2023-10-02","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:1:1:6:0:11:4:21:45:26","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-24","FORECAST_END":"2023-07-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgSnVseSBQTydzIGluIFByb2dyZXNz","RATING":"Low"} |  |  | C000098563 | PHASE11 | 2023-08-01 | 2023-08-02 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-07-18 | 15342.02 | 0 |  |  | C000098563 | 15342.02 |  | 1603.94 |  | 0 | 0 |  | 0 |  | 0
90000492 | Absa Bizana - Genset Rental | Absa Bizana - Genset Rental - Emergency Request |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2023-07-08 | 2023-08-08 |  | ASP-EC0330 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-07-06 | D | 114809.1 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Rob L | 100 | 2023-07-05 | 2023-07-05 | 114809.1 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000492,"ONEVIEW":"70633X","DATE01":"2023-07-05","DATE02":"2023-07-05","DATE03":"2023-07-05","DATE04":"2023-07-06","DATE05":"2023-07-06","DATE06":"2023-07-07","DATE07":"2023-10-20","DATE08":"2023-11-24","DATE09":"2023-12-11","DATE10":"2024-01-30","DATE11":"2024-01-08","DATE12":"2024-01-08","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"210:0:0:1:0:1:105:35:17:23","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-07","FORECAST_END":"2023-10-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjQgTm92IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQoyMyBOb3YgQ3JlcyBFbmcgcmVxdWVzdGVkIGluZm9ybWF0aW9uIGZyb20gQmlkdmVzdC4gRmluYWwgb3V0Y29tZSB0byBiZSBkZWNpZGVkIGJ5IENyZXMgRW5nLiBQT0Mgd2l0aCBLb2J1cyBmb3Igc2lnbm9mZgoxNyBOb3YgUE9DIFBhY2sgc3VibWl0dGVkIGZvciBhcHByb3ZhbAoxNiBOb3YgT25nb2luZyBCaWR2ZXN0IEVuZyB0byBlbmdhZ2UgQ3JlcyBFbmcgZm9yIGEgcGVybWFuZW50IHNvbHV0aW9uCjI2IE9jdCBFTkcgYW5kIFBNIHRvIGZvbGxvdyB1cCB3aXRoIFZlbmRvcgoyMyBPY3QgUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yIHJlIHByb2dyZXNzCjE2IE9jdCAtIFZlbmRvciB0byByZW1lZGlhdGUgYmVmb3JlIHJldHVybmluZyB0byBzaXRlLgoxMiBPY3QgTG9hbiBVbml0IG9uIHJvdXRlIGJhY2sgdG8gQml6YW5hIHRvIGJlIGluc3RhbGxlZCAxMiBPY3QKMTAgT2N0IC0gR2VuZXJhdG9yIEluc3RhbGxlZCBhbmQgRmFpbGVkIHRvIHN0YXJ0IC0gVmVuZG9yIEludmVzdGlnYXRpbmcgQ2F1c2UKOSBPY3QgRmFjdG9yeSB0ZXN0IGNvbXBsZXRlZCAtIFBhc3NlZAoyMSBTZXB0IC0gUGxhbm5lZCBpbnN0YWxsIGRhdGUgMjkgU2VwdAoxNCBTZXB0IE9uIFRyYWNrCjUgU2VwdCAtIFJlcXVlc3RlZCBpbnZvaWNlIGZvciB0aGUgMXN0IG1vbnRocyByZW50YWwgZnJvbSB0aGUgdmVuZG9yIGNhbiBvbmx5IGNsb3NlIHdoZW4gcmVtb3ZlZCBpLmUuIGxpbmtlZCB0byByZXBhaXJzCg==","RATING":"Low"} |  |  | C000096447 | PHASE11 | 2023-07-07 | 2023-10-20 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-07-06 | 99834 | 0 |  |  | C000096447 | 99834 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000493 | Absa Towers Main Gallery Sliding door | Absa Towers Main Gallery Sliding door |  |  | Region 1 |  | 78944X | 1000-71415-01 | ABSA TOWERS MAIN-Main St-Johannesburg | N | 2023-07-06 | 2023-07-06 |  | ASP-GS0711 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  | L |  | GAMIETR | 2023-07-06 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000493,"ONEVIEW":"78944X","DATE01":"2023-04-27","DATE02":"2023-05-04","DATE03":"2023-05-25","DATE04":"2023-06-01","DATE05":"2023-06-22","DATE06":"2023-07-06","DATE07":"2023-07-06","DATE08":"2023-07-27","DATE09":"2023-09-10","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-06","FORECAST_END":"2023-07-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-07-06 | 2023-07-06 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000494 | Absa Church Street Klerksdorp - Disconne | Absa Church Street Klerksdorp - Disconne |  |  | Region 3 |  | 22229X | 1000-71244-01 | Brits Mall-Cnr Hendrik Verwoerd & Maple Ridge Ave-Brits |  | 2023-08-29 |  |  | ASP-CR0463 | REL BUDG ACPT AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-07 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000494,"ONEVIEW":"22229X","DATE01":"2023-06-20","DATE02":"2023-06-27","DATE03":"2023-07-18","DATE04":"2023-07-25","DATE05":"2023-08-15","DATE06":"2023-08-29","DATE07":"2023-09-28","DATE08":"2023-10-19","DATE09":"2023-12-03","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-29","FORECAST_END":"2023-09-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEludm9pY2luZyBpbiBwcm9ncmVzcy4=","RATING":""} |  |  |  | PHASE09 | 2023-08-29 | 2023-09-28 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000097927 | 70216.74 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000495 | Absa Baywest Mall - Minor Works | Absa Baywest Mall - Minor Works |  |  | Region 2 | Eastern Cape | 36106X | 1000-70985-01 | Baywest Mall-Baywest Blvd-Port Elizabeth | N | 2023-09-29 | 2023-12-29 |  | ASP-EC0331 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-07-07 | D | 0 |  | 20 |  |  | 0 | Budgeted for in CIP 2024 | {"MANDT":"111","REFERENCE":90000495,"ONEVIEW":"36106X","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QnVkZ2V0ZWQgZm9yIGluIENJUCAyMDI0","RATING":""} |  |  |  | PHASE00 | 2023-09-29 | 2023-12-29 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000496 | Absa Kempston Road - Dilaps | Absa Kempston Road - Dilaps |  |  | Region 2 | Eastern Cape | 76390X | 1000-71006-01 | Kempston Road-Kempston Rd-Port Elizabeth | N | 2023-10-01 | 2023-12-29 |  | ASP-EC0332 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-07-07 | D | 412900.89 |  | 100 | 2023-08-29 | 2023-09-01 | 412900.89 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000496,"ONEVIEW":"76390X","DATE01":"2023-07-03","DATE02":"2023-07-21","DATE03":"2023-08-28","DATE04":"2023-09-04","DATE05":"2023-09-01","DATE06":"2023-09-01","DATE07":"2024-02-29","DATE08":"2024-03-21","DATE09":"2024-05-05","DATE10":"2024-05-31","DATE11":"2024-05-05","DATE12":"2024-05-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:18:38:7:-3:0:181:21:45:27","PROGRESS":69,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-01","FORECAST_END":"2024-02-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBGZWIgQ29zdHMgdG8gc3VibWl0dGVkIGZvciByZW1vdmFsIG9mIGRvb3IgYW5kIGNvbnRyYSB2aXNpb24gLSBTZWUgQVNQLUVDMDQwNwoyMiBKYW4gQ2FtZXJhcyBhcmUgdG8gcmVtYWluIGZvciBub3cKMTggSmFuIC0gMjIgRGVjIGNhbWVyYXMgdG8gcmVtb3ZlZAoyMCBEZWMgUGFydCAzIFN1Ym1pdHRlZCB0byBGaW5hbmNlIC0gUiAxNiA1NDguNTAgKEtvZW4ncykgVG90YWwgdG8gZGF0ZSBSIDIyMiA0NzcuNzgKMTQgRGVjIC0gSXRhcyByZW1vdmluZyBNYW50cmFwIERvb3IgMTQgRGVjLCBTYWZlcyB0byBiZSBkb25lIE1vbmRheSAxOHRoLgoxMyBEZWMgUGFydCAyIFN1Ym1pdHRlZCB0byBGaW5hbmNlIC0gUiA4NSA3MjMuNDggLSBUb3RhbCBSIDIwNSA5MjkuMjggKEVkZW4gYW5kIEdBKQo0IERlYyAtIEdsb2JhbCBBY2Nlc3MgcmVtb3ZlZCBUVidzIDMwIE5vdiwgT25nb2luZwoxNyBOb3YgT25nb2luZyB0byBGZWIgMjQKNyBOb3YgUE9DIHBhcnQgMSBTdWJtaXR0ZWQgLSBSIDE2MCAxOTIuNDkgLSBFZGVuIFBhcnQgUGF5bWVudCArIFMmRyBTaWducyAtIE9uZ29pbmcgUHJvamVjdAo2IE5vdiAtIE9uZ29pbmcgaGFuZG92ZXIgMjkgRmViIDIwMjQgLSBQYXJ0aWFsIFBPQyB0byBiZSBzdWJtaXR0ZWQgZm9yIHdvcmtzIGNvbXBsZXRlZAoyMyBPY3QgLSBFeHRlcm5hbCBTaWduYWdlIGhhcyBiZWVuIFJlbW92ZWQgMjAgT2N0CjExIE9jdCAtIE9uZ29pbmcgLSBJbnRlcm5hbCBTaWduYWdlIFJlbW92ZWQKMjIgU2VwdCBXaWxsIGJlIGZpbmFuY2lhbCByb2xsb3ZlciBhcyBydW5zIHRvIDI5IEZlYiAyNCAtIE9QRVgKNSBTZXB0IFN1cHBsaWVyIFBPJ3MgaXNzdWVkIC0gNDUwMDg1Njc5OCBLb2VuJ3MgTG9ja3NtaXRoLCA0NTAwODU2Nzk5IEZpZGVsaXR5IEFEVCBhbmQgVGVjaG5pY2FsIChEZWluc3RhbGwpLCA0NTAwODU2ODAwIFNlY3V0ZWwgVGVjaG5vbG9naWVzIChEZWluc3RhbGwpLCA0NTAwODU2ODAxIEdsb2JhbCBBY2Nlc3MsIDQ1MDA4NTY4MDIgRWRlbiBTZWN1cml0eSBTZXJ2aWNlcywgNDUwMDg1NjgwMyBTdGFuZGJ5IFN5c3RlbXMsIDQ1MDA4NTY4MDQgSVRBUywgNDUwMDg1NjgwNiBDbGVhcmRhdGEsIDQ1MDA4NTY4MDcgUyZHIFNpZ25zIC0gYW5kIHNoYXJlZCAKNCBTZXB0IEFic2EgUE8gUmVjZWl2ZWQgLSBDMDAwMTA3OTc5CjEgU2VwdCBBcHByb3ZlZCBieSBSZWFsIEVzdGF0ZQpOb3RlOiBQcm9qZWN0IHJ1bnMgdG8gZW5kIEZlYiAyNCBhcyBMTCBkb2VzIG5vdCB3YW50IHRvIHRha2Ugc2l0ZSBlYXJseQ==","RATING":"Low"} |  |  | C000107979 | PHASE08 | 2023-09-01 | 2024-03-04 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-04 | 359044.26 | 0 |  |  | C000107979 | 359044.26 |  | 19609.57 |  | 0 | 0 |  | 0 |  | 0
90000497 | Absa Crescent Emalahleni- Vinly Frosting | Absa Crescent Emalahleni- Vinly Frosting |  |  | Region 3 |  | 78577X | 1000-70656-01 | Saveways Crescent Centre-Cnr OR Tambo Rd & Mandela St-Emalahleni |  | 2023-09-13 |  |  | ASP-MP0164 | CLSD BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-07 | D | 19065.27 | 2023.07.13: Approved by Conrad M | 100 | 2023-07-13 | 2023-07-13 | 19065.28 | Approved | {"MANDT":"111","REFERENCE":90000497,"ONEVIEW":"78577X","DATE01":"2023-07-05","DATE02":"2023-07-07","DATE03":"2023-07-10","DATE04":"2023-07-14","DATE05":"2023-07-14","DATE06":"2023-07-20","DATE07":"2023-08-04","DATE08":"2023-08-31","DATE09":"2023-08-31","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-20","FORECAST_END":"2023-08-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIGludm9pY2VzIHJlcXVlc3RlZA==","RATING":""} |  |  | C000098574 | PHASE11 | 2023-07-20 | 2023-08-04 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-07-18 | 19065.28 | 0 |  |  | C000098574 | 16578.5 |  | 1315.03 |  | 0 | 0 |  | 0 |  | 0
90000498 | Absa Willowbrooke(Delmas) - Vinly Frosti | Absa Willowbrooke(Delmas) - Vinly Frosti |  |  | Region 3 |  | 37064X | 1000-70594-01 | Willowbrooke Square Delmas-Van Der Walt 29232 St-Delmas |  | 2023-09-22 |  |  | ASP-MP0165 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-07 | D | 19347.01 | 2023.07.13: Approved by Conrad M | 100 | 2023-07-13 | 2023-07-13 | 19347.02 | Approved |  |  |  | C000098576 | PHASE11 | 2023-07-31 | 2023-08-04 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-07-18 | 19347.01 | 0 |  |  | C000098576 | 16823.49 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000499 | Absa Riebeek West - Dilaps | Absa Riebeek West - Dilaps |  |  | Region 2 | Western Cape | 78135X | 1000-70892-01 | 13 Voortrekker Street Riebeek West-Voortrekker St-Cape Town | N | 2023-09-29 | 2023-12-29 |  | ASP-WC0296 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-07 | D | 260909.68 |  | 100 | 2023-09-01 | 2023-09-05 | 260909.68 | Approved | {"MANDT":"111","REFERENCE":90000499,"ONEVIEW":"78135X","DATE01":"2023-07-17","DATE02":"2023-08-28","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-09-05","DATE06":"2023-09-07","DATE07":"2023-09-15","DATE08":"2023-10-06","DATE09":"2023-11-20","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"167:42:3:7:-2:2:8:21:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-07","FORECAST_END":"2023-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgU2VwdCBGQURUIEludm9pY2Ugb3V0c3RhbmRpbmcsIE5hdGlvbmFsIFNhZmVzIHJlY2VpdmVkCjIwIFNlcHQgLSBQYXJ0IDEgUE9DIFN1Ym1pdHRlZCAtIFIgMjA1IDY2MS43MiBmb3IgUyZHIFNpZ25zLCBSVCBTeXN0ZW1zLCBTZWN1dGVsLCBZYW50ZWsKMTggU2VwdCBIYW5kZWQgQmFjayAxNSBTZXB0Cg==","RATING":"Low"} |  |  | C000108320 | PHASE11 | 2023-09-07 | 2023-09-15 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-05 | 226877.98 | 0 |  |  | C000108320 | 226877.98 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000500 | Absa Cavendish Claremont - Generator Replacement | Absa Cavendish Claremont - Generator Replacement |  |  | Region 2 | Western Cape | 77252X | 1000-70812-01 | Grove Exchange-Cnr Main Rd & Grove Ave-Claremont |  | 2023-09-29 | 2023-12-29 |  | ALP-WC0027 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  |  |  | CEASARS | 2023-07-07 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000500,"ONEVIEW":"77252X","DATE01":"2023-07-21","DATE02":"2023-10-13","DATE03":"2023-11-03","DATE04":"2023-11-10","DATE05":"2023-12-01","DATE06":"2024-03-08","DATE07":"2024-03-23","DATE08":"2024-04-13","DATE09":"2024-05-28","DATE10":"2024-05-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"315:84:21:7:21:98:15:21:45:4","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-08","FORECAST_END":"2024-03-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgU2VwdCBSaXNrIC0gaWYgYXBwcm92ZWQgd2lsbCBiZSBleGVjdXRlZCBpbiAyMDI0IC0gUHJvamVjdCBSb2xsb3ZlcgoxNCBTZXB0IC0gMTEgU2VwdCAtIEZlZWRiYWNrIHBlbmRpbmcgZnJvbSBCcm9sbCByZSBCYXR0ZXJ5IHdhbGwgLyBHZW5lcmF0b3IgCjUgU2VwdCBCcm9sbCBmZWVkYmFjayBzdGlsbCBvdXRzdGFuZGluZwoxOCBBdWcgRmVlZGJhY2sgcGVuZGluZyBmcm9tIEJyb2xsIHJlIHRoZSBwcm9wb3NlZCByZXBsYWNlbWVudAoxNCBBdWcgQnJvbGwgdG8gc3VibWl0IHRvIExMIGZvciBjb21tZW50IGlucHV0IGluIHRlcm1zIG9mIG5leHQgc3RlcHMKMTAgQXVnIEVuZ2luZWVyaW5nIHNlbnQgaW5mb3JtYXRpb24gdG8gQnJvbGwgZm9yIGxhbmRsb3JkJ3MgYXBwcm92YWwKNyBBdWcgQnJvbGwgdG8gYWR2aXNlCg==","RATING":"Low"} |  |  |  | PHASE12 | 2024-03-08 | 2024-03-23 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000501 | Towers West Install a BYOD in U.6 | Towers West Install a BYOD in U.6 |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-07-10 | 2023-07-10 |  | ASP-GS0712 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-07-10 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000501,"ONEVIEW":"21526X","DATE01":"2023-05-01","DATE02":"2023-05-08","DATE03":"2023-05-29","DATE04":"2023-07-17","DATE05":"2023-07-20","DATE06":"2023-08-03","DATE07":"2023-08-03","DATE08":"2023-08-24","DATE09":"2023-10-08","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"152:7:21:49:3:14:0:21:45:16","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-03","FORECAST_END":"2023-08-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2023-08-03 | 2023-08-03 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000502 | Tambotie Helpline Upgrade | Tambotie Helpline Upgrade |  |  | Region 1 |  | 36269X | 1000-70199-01 | Tambotie Mall-Cnr Lazar & Malan St-Randfontein | N | 2023-07-10 | 2023-07-10 |  | ASP-GS0713 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-07-10 | D | 21092.03 |  | 20 | 2023-07-10 |  | 0 |  | {"MANDT":"111","REFERENCE":90000502,"ONEVIEW":"36269X","DATE01":"2023-05-01","DATE02":"2023-05-08","DATE03":"2023-05-29","DATE04":"2023-06-05","DATE05":"2023-06-26","DATE06":"2023-07-10","DATE07":"2023-07-10","DATE08":"2023-07-31","DATE09":"2023-09-14","DATE10":"2023-09-30","DATE11":"2023-09-14","DATE12":"2023-09-14","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":11,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-10","FORECAST_END":"2023-07-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogU3BlYyByZXZpc2VkIGFuZCBhcHByb3ZlZC4gc3VwcGxpZXIgcmV2aXNpbmcgcXVvdGUu","RATING":""} |  |  |  | PHASE05 | 2023-07-10 | 2023-07-10 | CHRISTOPHER MPOFU | Buhle Qwabe | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000503 | Alice Lane South Upgrade of the 3rd floor Client Suite Kitchen. | Removal of existing cupboards and oven Removal of kitchen equipment for later use. Supply and install new kitchen cupboards. Supply and install 1100 x700x900 Service counter heated warmer Supply and install new floor tiles. Supply and install new wall tiles Reinstall of existing fittings and fixtures Make good on workspace. All work to be undertaken during weekends / afterhours. |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-07-11 | 2023-07-11 |  | ASP-GS0714 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L | 2030-04-29 | GAMIETR | 2023-07-11 | D | 0 | Approved | 100 | 2023-07-13 | 2023-10-07 | 405949.75 |  | {"MANDT":"111","REFERENCE":90000503,"ONEVIEW":"35041X","DATE01":"2023-05-02","DATE02":"2023-04-13","DATE03":"2023-06-30","DATE04":"2023-07-10","DATE05":"2023-07-14","DATE06":"2023-07-11","DATE07":"2023-07-11","DATE08":"2023-08-01","DATE09":"2023-09-15","DATE10":"2023-09-30","DATE11":"2023-09-15","DATE12":"2023-09-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-11","FORECAST_END":"2023-07-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyByZWxlYXNlIG9mIFBPJ3MgLCBjb250cmFjdG9yIGxlYWQgdGltZSBvZiA0IHdlZWtzIHRvIGluc3RhbGxhdGlvbi4=","RATING":""} |  |  | C000112431 | PHASE07 | 2023-07-11 | 2023-07-11 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-09-22 | 466842.21 | 0 |  |  | C000112431 | 352999.78 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000504 | Bridgepark-Smart water meter installation | Bridgepark-Smart water meter installation |  |  | Energy | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town |  | 2023-07-20 | 2023-12-15 |  | ASP-WC0297 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Wesigye Mukuru |  |  | 2023 |  |  |  | LOUISR | 2023-07-11 | D | 43599.65 | Project approved in order to adequately report on sites water consumption as required in the integrated ESG report on an annual basis | 100 | 2023-07-04 | 2023-07-13 | 43599.65 | Project approved in order to adequately report on sites water consumption as required in the integrated ESG report on an annual basis | {"MANDT":"111","REFERENCE":90000504,"ONEVIEW":"36225X","DATE01":"2023-05-11","DATE02":"2023-05-18","DATE03":"2023-06-08","DATE04":"2023-06-15","DATE05":"2023-07-06","DATE06":"2023-07-20","DATE07":"2023-07-22","DATE08":"2023-08-12","DATE09":"2023-09-26","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"294:7:21:7:21:14:2:21:45:10","PROGRESS":20,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-20","FORECAST_END":"2023-07-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000101038 | PHASE11 | 2023-07-20 | 2023-07-22 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-07-31 | 37912.74 | 0 |  |  | C000101038 | 37912.74 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000505 | Absa 13 Van Zyl- Install New Water Tank | Absa 13 Van Zyl- Install New Water Tank |  |  | Region 3 |  | 79299X | 1000-71579-01 | Hoopstad-Van Zyl St-Hoopstad |  | 2023-10-26 |  |  | ASP-CR0464 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  | 2022-03-30 | NOMNGANGAL | 2023-07-12 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000505,"ONEVIEW":"Unknown","DATE01":"2023-08-17","DATE02":"2023-08-24","DATE03":"2023-09-14","DATE04":"2023-09-21","DATE05":"2023-10-12","DATE06":"2023-10-26","DATE07":"2023-11-25","DATE08":"2023-12-16","DATE09":"2024-01-30","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-26","FORECAST_END":"2023-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2023-10-26 | 2023-11-25 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000506 | Absa Heilbron - Waterproofing & Entire r | Absa Heilbron - Waterproofing & Entire roof of the branch |  |  | Region 3 |  | Unknown | 1000-71557-01 | Unknown Building - not in our database |  | 2023-10-27 |  |  | ASP-CR0465 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-12 | D | 0 |  | 40 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000506,"ONEVIEW":"Unknown","DATE01":"2023-08-18","DATE02":"2023-08-25","DATE03":"2023-09-15","DATE04":"2023-09-22","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2023-11-26","DATE08":"2023-12-17","DATE09":"2024-01-31","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":60,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2023-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  |  | PHASE04 | 2023-10-27 | 2023-11-26 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000507 | Absa 17A Joubert Street-Waterproofing | Absa 17A Joubert Street-Waterproofing |  |  | Region 3 |  | Unknown | 1000-71556-01 | Unknown Building - not in our database |  | 2023-10-26 |  |  | ASP-CR0466 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-12 | D | 0 |  | 40 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000507,"ONEVIEW":"Unknown","DATE01":"2023-08-17","DATE02":"2023-08-24","DATE03":"2023-09-14","DATE04":"2023-09-21","DATE05":"2023-10-12","DATE06":"2023-10-26","DATE07":"2023-10-17","DATE08":"2023-11-07","DATE09":"2023-12-22","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"167:7:21:7:21:14:-9:21:45:1","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-26","FORECAST_END":"2023-10-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  | C000118643 | PHASE11 | 2023-10-26 | 2023-10-17 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-24 | 185308.72 | 0 |  |  | C000118643 | 185308.72 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000508 | Absa Hoopstad - Waterproofing | Absa Hoopstad - Waterproofing |  |  | Region 3 |  | 79299X | 1000-71579-01 | Hoopstad-Van Zyl St-Hoopstad |  | 2023-10-26 |  |  | ASP-CR0467 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  | 2022-05-30 | NOMNGANGAL | 2023-07-12 | D | 0 |  | 40 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000508,"ONEVIEW":"79299X","DATE01":"2023-08-17","DATE02":"2023-08-24","DATE03":"2023-09-14","DATE04":"2023-09-21","DATE05":"2023-10-12","DATE06":"2023-10-26","DATE07":"2023-11-25","DATE08":"2023-12-16","DATE09":"2024-01-30","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-26","FORECAST_END":"2023-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  |  | PHASE05 | 2023-10-26 | 2023-11-25 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000509 | Absa Reitz - Waterproofing & Entire Roof | Absa Reitz - Waterproofing & Entire Roof |  |  | Region 3 | Free State | 78402X | 1000-71538-01 | Absa Reitz-Church St-Reitz |  | 2023-10-27 |  |  | ASP-CR0468 | REL BUDG AVAC RESA SETC: |  | false | true |  | Liso Jordan |  |  | 2023 |  |  | 2023-11-29 | NOMNGANGAL | 2023-07-12 | D | 0 |  | 40 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000509,"ONEVIEW":"78402X","DATE01":"2023-08-18","DATE02":"2023-09-29","DATE03":"2023-09-12","DATE04":"2023-09-19","DATE05":"2023-10-10","DATE06":"2023-10-24","DATE07":"2023-10-23","DATE08":"2023-11-13","DATE09":"2023-12-28","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":20,"PROG03":80,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"166:42:-17:7:21:14:-1:21:45:3","PROGRESS":5,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-24","FORECAST_END":"2023-10-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  | C000119249 | PHASE05 | 2023-10-24 | 2023-10-23 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 286816.84 | 0 |  |  | C000119249 | 286816.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000510 | Absa Heilbron - Installation of Water Ta | Absa Heilbron - Installation of Water Ta |  |  | Region 3 |  | Unknown | 1000-71557-01 | Unknown Building - not in our database |  | 2023-11-23 |  |  | ASP-CR0469 | CRTD RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-12 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000510,"ONEVIEW":"Unknown","DATE01":"2023-09-14","DATE02":"2023-03-03","DATE03":"2023-03-03","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-09-07","DATE07":"2023-09-10","DATE08":"2024-09-20","DATE09":"2024-02-27","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-07","FORECAST_END":"2023-09-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2023-09-07 | 2023-10-08 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000511 | Absa 17A Joubert Str - Install Water Tan | Absa 17A Joubert Str - Install Water Tan |  |  | Region 3 |  | Unknown | 1000-71556-01 | Unknown Building - not in our database |  | 2023-10-05 |  |  | ASP-CR0470 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-12 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000511,"ONEVIEW":"Unknown","DATE01":"2023-07-27","DATE02":"2023-03-03","DATE03":"2023-03-03","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-08-10","DATE07":"2023-11-04","DATE08":"2023-11-25","DATE09":"2024-01-09","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-10","FORECAST_END":"2023-11-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE04 | 2023-08-10 | 2023-11-04 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000512 | Absa Villiers - Installation of Water Ta | Absa Villiers - Installation of Water Ta |  |  | Region 3 |  | Unknown | 1000-71554-01 | Unknown Building - not in our database |  | 2023-10-05 |  |  | ASP-CR0471 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-12 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000512,"ONEVIEW":"Unknown","DATE01":"2023-07-27","DATE02":"2023-03-03","DATE03":"2023-03-03","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-08-10","DATE07":"2023-08-14","DATE08":"2023-08-20","DATE09":"2024-01-09","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":50,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-10","FORECAST_END":"2023-08-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE04 | 2023-08-10 | 2023-08-14 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000513 | ALS Replacement of external Absa Vinyl | ALS Replacement of external Absa Vinyl |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-07-12 | 2023-07-12 |  | ASP-GS0715 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-07-12 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 79759.62 |  |  |  |  | C000097245 | PHASE09 | 2023-07-19 | 2023-07-28 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-11 | 79759.62 | 0 |  |  | C000097245 | 69356.19 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000514 | Absa Cpt Intl Airport - Minor Works | Absa Cpt Intl Airport - Minor Works - Painting of Walls with new ABSA colours & Carpets |  |  | Region 2 | Western Cape | 76946X | 1000-70791-01 | Cape Town International Airport-N2-Cape Town | N | 2023-10-01 | 2023-12-29 |  | ASP-WC0298 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-12 | D | 120347.98 |  | 100 | 2023-08-24 | 2023-08-31 | 120347.98 |  | {"MANDT":"111","REFERENCE":90000514,"ONEVIEW":"76946X","DATE01":"2023-07-23","DATE02":"2023-08-11","DATE03":"2023-08-24","DATE04":"2023-08-31","DATE05":"2023-08-31","DATE06":"2023-10-03","DATE07":"2023-10-06","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"161:19:13:7:0:33:3:21:45:17","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-03","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjMgT2N0IEZpZGVsaXR5IEludm9pY2Ugb3V0c3RhbmRpbmcKNiBPY3QgQ29tcGxldGVkIGFuZCBzaWduZWQgb2ZmIDYgT0NUIEludm9pY2luZyBhbmQgUE9DIHRvIGZvbGxvdwoyMiBTZXB0IEFwcHJvdmFsIFJlY2VpdmVkIGZyb20gQUNTQSB0byBwcm9jZWVkCjE4IFNlcHQgLSBQTSBGb2xsb3cgdXAgcmUgQUNTQSByZXF1aXJlbWVudHMK","RATING":"Low"} |  |  | C000108047 | PHASE11 | 2023-10-03 | 2023-10-06 | RODERICK NEVAY | Michael Maluleka | 23000269 |  |  |  |  | 2023-09-04 | 104650.42 | 0 |  |  | C000108047 | 104650.42 |  | 10975.03 |  | 0 | 0 |  | 0 |  | 0
90000515 | Absa Glenfair Phase 2 Dilaps (White Box) | Absa Glenfair Phase 2 Dilaps (White Box) |  |  | Region 1 |  | 76510X | 1000-70276-01 | Glenfair Boulevard-Daventry Rd-Pretoria |  | 2023-07-12 | 2023-08-12 |  | ALP-GS0063 | CLSD BUDG ISBD AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-07-12 | D | 927400.53 | Approved by Lebusa M | 100 | 2023-07-20 | 2023-07-20 | 927400.53 | Approved | {"MANDT":"111","REFERENCE":90000515,"ONEVIEW":"76510X","DATE01":"2023-05-03","DATE02":"2023-07-07","DATE03":"2023-07-07","DATE04":"2023-07-07","DATE05":"2023-07-07","DATE06":"2023-07-12","DATE07":"2023-09-21","DATE08":"2023-10-12","DATE09":"2023-11-26","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":60,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"181:65:0:0:0:5:71:21:45:14","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-12","FORECAST_END":"2023-09-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFByb2plY3QgY29tcGxldGUuIEZpbmFsIFBPQyBwbGFubmVkIGZvciB0aGlzIHdlZWsncyBzdWJtaXNzaW9uLgpBd2FpdGluZyBWUCB0byBhcHByb3ZlIEJDIGZvciBBYnNhIFBPIHNvIEJGTSBQT3MgY2FuIGJlIGlzc3VlZC4gTkI6IHRoZXJlIGlzIGEgbGVhZCB0aW1lIG9mIDEyIGRheXMgb24gdGhlIHNob3Bmcm9udHMu","RATING":""} |  |  | C000099326 | PHASE11 | 2023-07-12 | 2023-09-21 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-21 | 806435.24 | 806435.24 |  |  | C000099326 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000516 | Absa Trompsburg - Install 22000 BTU Midw | Absa Trompsburg - Install 22000 BTU Midw |  |  | Region 3 |  | 79334X | 1000-71585-01 | Absa Trompsburg-Voortrekker St-Trompsburg |  | 2023-10-30 | 2023-10-31 |  | ASP-CR0472 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-14 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000516,"ONEVIEW":"79334X","DATE01":"2023-08-21","DATE02":"2023-08-28","DATE03":"2023-09-18","DATE04":"2023-09-25","DATE05":"2023-10-16","DATE06":"2023-10-30","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-30","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE11 | 2023-10-30 | 2023-10-31 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000140791 | 31131 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000517 | 270 Republic Rd Compressor Chiller 1 | 270 Republic Rd Compressor Chiller 1 |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-07-14 | 2023-07-14 |  | ASP-GS0716 | CRTD: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-07-14 | D | 0 |  | 1 |  |  | 0 | Project Duplicated - Tracking PN# ALP-GS0070 | {"MANDT":"111","REFERENCE":90000517,"ONEVIEW":"21335X","DATE01":"2023-05-05","DATE02":"2023-05-12","DATE03":"2023-06-02","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-08-31","DATE08":"2023-09-21","DATE09":"2023-11-05","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":1,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"148:7:21:55:21:14:0:21:45:12","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgRU5HIGNvbmZpcm1hdGlvbiBvbiBzZXJ2aWNlIGhpc3RvcnkgZm9yIENSRVMgcmV2aWV3LgpQcm9qZWN0IER1cGxpY2F0ZWQgLSBUcmFja2luZyBQTiMgQUxQLUdTMDA3MAo=","RATING":"Medium"} |  |  |  | PHASE12 | 2023-08-31 | 2023-08-31 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000518 | Absa Liberty Promenade - Replace Dynoc with ATM Tiles | Absa Liberty Promenade - Replace Dynoc with ATM Tiles |  |  | Region 2 | Western Cape | 77151X | 1000-71429-01 | Liberty Promenade Shopping Centre-Cnr AZ Berman Dr & Morgenster Rd-Mitchells Pla | N | 2023-09-29 | 2023-12-29 |  | ASP-WC0299 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-14 | D | 23145.76 |  | 100 | 2023-08-24 | 2023-08-31 | 23145.76 | 4 Sept Absa PO received C000108049, BV PO's requested 31 Aug Approved CB33 - Signed Deck Pending in order to request PO's | {"MANDT":"111","REFERENCE":90000518,"ONEVIEW":"77151X","DATE01":"2023-07-14","DATE02":"2023-07-17","DATE03":"2023-08-24","DATE04":"2023-08-31","DATE05":"2023-08-31","DATE06":"2023-09-05","DATE07":"2023-09-06","DATE08":"2023-09-27","DATE09":"2023-11-11","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"139:3:38:7:0:5:1:21:45:3","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-05","FORECAST_END":"2023-09-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgQXVnIEFwcHJvdmVkIENCMzM=","RATING":"Low"} |  |  | C000108049 | PHASE11 | 2023-10-25 | 2023-10-27 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-04 | 20126.74 | 0 |  |  | C000108049 | 20126.74 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000519 | Absa Kokstad - HVAC Replacement | Absa Kokstad - HVAC Replacement |  |  | Region 3 |  | 78005X | 1000-71621-01 | Kokstad-Main St-Kokstad |  | 2023-09-28 | 2023-10-31 |  | ALP-KZ2006 | REL BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-14 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B & Ilana vdW |  | 2023-07-20 | 2023-07-20 | 832777.11 | Approved |  |  |  |  | PHASE05 | 2023-09-28 | 2023-10-31 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000144673 | 724153.91 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000520 | Absa Inquthu - Minor Works | Absa Inquthu - Minor Works |  |  | Region 3 |  | 79051X | 1000-71231-01 | Nquthu Plaza-Manzolwandle Dr-Nquthu |  | 2023-10-27 |  |  | ALP-KZ2007 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-14 | D | 0 |  | 100 |  |  | 1288285 |  | {"MANDT":"111","REFERENCE":90000520,"ONEVIEW":"79051X","DATE01":"2023-08-18","DATE02":"2023-06-01","DATE03":"2023-06-12","DATE04":"2023-06-27","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2023-11-26","DATE08":"2023-12-17","DATE09":"2024-01-31","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2023-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBsZWFkIHRpbWUgcGhhc2UgLSBmaW5hbmNpYWwgcm9sbG92ZXI=","RATING":""} |  |  |  | PHASE05 | 2023-10-27 | 2023-11-26 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000141203 | 1066886.56 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000521 | Absa Stanger - Minor Works | Absa Stanger - Minor Works |  |  | Region 3 |  | 77928X | 1000-71201-01 | Whitehouse Centre-Chief Albert Luthuli St-Stanger |  | 2023-10-27 |  |  | ALP-KZ2008 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-14 | D | 0 |  | 100 |  |  | 1286621 |  | {"MANDT":"111","REFERENCE":90000521,"ONEVIEW":"77928X","DATE01":"2023-08-18","DATE02":"2023-06-07","DATE03":"2023-06-15","DATE04":"2023-06-22","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2023-11-26","DATE08":"2023-12-17","DATE09":"2024-01-31","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2023-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBsZWFkIHRpbWUgcGhhc2UgLSBmaW5hbmNpYWwgcm9sbG92ZXI=","RATING":""} |  |  |  | PHASE05 | 2023-10-27 | 2023-11-26 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142409 | 1065675.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000522 | Pretoria Campus Flammable Storeroom desi | Pretoria Campus Flammable Storeroom desi |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-07-17 | 2023-07-17 |  | ASP-GN0215 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 64299.9 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 64299.9 | Approved | {"MANDT":"111","REFERENCE":90000522,"ONEVIEW":"22491X","DATE01":"2023-05-08","DATE02":"2023-05-15","DATE03":"2023-06-05","DATE04":"2023-06-12","DATE05":"2023-07-03","DATE06":"2023-07-17","DATE07":"2023-10-16","DATE08":"2023-11-06","DATE09":"2023-12-21","DATE10":"2023-12-31","DATE11":"2023-12-21","DATE12":"2023-12-21","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"145:7:21:7:21:14:91:21:45:9","PROGRESS":44,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-10-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogREQgY29tcGxldGUgYW5kIHNlbnQgdG8gdGhlIHByaW5jaXBhbCBlbmdpbmVlci4gRmluYWwgUE9DIGluIHByb2dyZXNzLg==","RATING":""} |  |  | C000100034 | PHASE07 | 2023-07-17 | 2023-10-16 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-25 | 55912.96 | 0 |  |  | C000100034 | 55912.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000523 | Alice Lane South install bosal conduit | Alice Lane South install bosal conduit |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-07-17 | 2023-08-17 |  | ASP-GS0717 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 22484.11 | Approved |  |  |  | C000100096 | PHASE09 | 2023-07-17 | 2023-08-17 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-26 | 22484.11 | 0 |  |  | C000100096 | 19551.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000524 | Alice Lane South Replace Generator Batte | Alice Lane South Replace Generator Batte |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-07-17 | 2023-08-17 |  | ASP-GS0718 | REL BUDG AVAC SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 54251.76 | Approved |  |  |  | C000100102 | PHASE07 | 2023-07-17 | 2023-08-17 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-26 | 54251.76 | 0 |  |  | C000100102 | 52544 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000525 | Alice Lane North Replace Generator Batte | Alice Lane North Replace Generator Batte |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2023-07-17 | 2023-08-17 |  | ASP-GS0719 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 124305.98 | Approved |  |  |  | C000100101 | PHASE09 | 2023-07-17 | 2023-08-17 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-26 | 124305.98 | 0 |  |  | C000100101 | 111624 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000526 | Alice lane North Replacement of Air Handling Unit (AHU) and Computer Room Air Conditioning AC Unit Crac filters | Alice lane North Replacement of 19 Air Handling Unit (AHU) and 48 Computer Room Air Conditioning AC Unit Crac filters |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2023-04-05 | 2023-08-31 |  | ASP-GS0720 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 270224.75 | Approved | {"MANDT":"111","REFERENCE":90000526,"ONEVIEW":"70656X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-08-31","DATE08":"2023-09-21","DATE09":"2023-11-05","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000100103 | PHASE08 | 2023-04-05 | 2023-08-31 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-07-26 | 357372.23 | 0 |  |  | C000100103 | 234978.04 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000527 | Meadowdale Replacement of 86 Air-Conditi | Absa Meadowdale / Highlands HVAC Upgrade DD fees P1 (Replacement of 86 Air-Con units) |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale | N | 2023-04-05 |  |  | ASP-GS0721 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Rob L | 100 | 2023-07-20 | 2023-07-20 | 204561.32 | Approved | {"MANDT":"111","REFERENCE":90000527,"ONEVIEW":"37006X","DATE01":"2023-01-25","DATE02":"2023-06-30","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-07-21","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"2023-07-10","DATE12":"2023-07-10","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":80,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8xNTogREQgQ29tcGxldGUgJiBzZW50IHRvIHRoZSBQcmluY2lwYWwgRW5naW5lZXIuCgpGcm9tOiBQaGF0aHV0c2hlZHpvIE5lZHV2aHVsZWR6YSA8UGhhdGh1dHNoZWR6by5OZWR1dmh1bGVkemFAYmlkdmVzdGZtLmNvLnphPgpTZW50OiBUaHVyc2RheSwgRGVjZW1iZXIgMTQsIDIwMjMgODowMTo1MyBBTQpUbzogTm9rdXRodWxhIE1hbnppbmkgPE5va3V0aHVsYS5NYW56aW5pQGJpZHZlc3RmbS5jby56YT4KQ2M6IEFuZ3VzIFNhcmF3YW4gPEFuZ3VzLlNhcmF3YW5AYmlkdmVzdGZtLmNvLnphPjsgUm9lZ3NoYW5hIEdhbWlldCA8Um9lZ3NoYW5hLkdhbWlldEBiaWR2ZXN0Zm0uY28uemE+OyBLZXZpbiBNYXBldG8gPEtldmluLk1hcGV0b0BiaWR2ZXN0Zm0uY28uemE+OyBMb3lpc28gTWZ1YmVzaSA8TG95aXNvLk1mdWJlc2lAYmlkdmVzdGZtLmNvLnphPjsgTmphYnVsbyBOZ3ViYW5lIDxOamFidWxvLk5ndWJhbmVAYmlkdmVzdGZtLmNvLnphPgpTdWJqZWN0OiBSRTogUmVxdWVzdCBmb3IgU2lnbmF0dXJlOiAzNzAwNlggQWJzYSBNZWFkb3dkYWxlIEFTUC1HUzA3MjEgSFZBQyBVcGdyYWRlIEREIGZlZXMgUDEgLSBQQ0MgMSAKIApIaSBOb2tzLAogCkkgd2lsbCBzZW5kIGl0IGFzIHNvb24gYXMgQkZNIGVuZ2luZWVyaW5nIGFuZCBDcmVzIGVuZ2luZWVyaW5nIHNpZ25zLgogClRoYW5rcwogCkZyb206IE5va3V0aHVsYSBNYW56aW5pIDxOb2t1dGh1bGEuTWFuemluaUBiaWR2ZXN0Zm0uY28uemE+IApTZW50OiBXZWRuZXNkYXksIERlY2VtYmVyIDEzLCAyMDIzIDk6MDkgUE0KVG86IFBoYXRodXRzaGVkem8gTmVkdXZodWxlZHphIDxQaGF0aHV0c2hlZHpvLk5lZHV2aHVsZWR6YUBiaWR2ZXN0Zm0uY28uemE+CkNjOiBBbmd1cyBTYXJhd2FuIDxBbmd1cy5TYXJhd2FuQGJpZHZlc3RmbS5jby56YT47IFJvZWdzaGFuYSBHYW1pZXQgPFJvZWdzaGFuYS5HYW1pZXRAYmlkdmVzdGZtLmNvLnphPjsgS2V2aW4gTWFwZXRvIDxLZXZpbi5NYXBldG9AYmlkdmVzdGZtLmNvLnphPjsgTG95aXNvIE1mdWJlc2kgPExveWlzby5NZnViZXNpQGJpZHZlc3RmbS5jby56YT47IE5qYWJ1bG8gTmd1YmFuZSA8TmphYnVsby5OZ3ViYW5lQGJpZHZlc3RmbS5jby56YT4KU3ViamVjdDogRlc6IFJlcXVlc3QgZm9yIFNpZ25hdHVyZTogMzcwMDZYIEFic2EgTWVhZG93ZGFsZSBBU1AtR1MwNzIxIEhWQUMgVXBncmFkZSBERCBmZWVzIFAxIC0gUENDIDEKSW1wb3J0YW5jZTogSGlnaAogCkhpIFBoYXRodSAsCiAKQ2FuIHlvdSBwbGVhc2Ugc2VuZCBQT0MgUGFjayBmb3IgdGhpcyBwcm9qZWN0IC4KIApSZWdhcmRzCiAK","RATING":""} |  |  | C000100033 | PHASE08 | 2023-04-05 | 2023-05-05 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-25 | 203301.31 | 0 |  |  | C000100033 | 176783.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000528 | Towers North New fire rated doors | Towers North Installation of New 3 fire rated doors |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg | N | 2023-07-17 | 2023-09-18 |  | ASP-GS0722 | CRTD SETC: |  | false | false |  | Athi Magqashela |  | Replace non fire rated 3 doors with fire rated doors | 2023 |  | F |  | GAMIETR | 2023-07-17 | D | 138487.14 | Project was cancelled, the existing doors were said to be compliant | 1 | 2023-07-13 | 2023-07-18 | 138487.14 | to be submitted at CB | {"MANDT":"111","REFERENCE":90000528,"ONEVIEW":"77381X","DATE01":"2023-05-08","DATE02":"2023-07-03","DATE03":"2023-07-10","DATE04":"2023-07-13","DATE05":"2023-07-18","DATE06":"2023-08-18","DATE07":"2023-10-20","DATE08":"2023-11-10","DATE09":"2023-12-25","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:56:7:3:5:31:63:21:45:7","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-18","FORECAST_END":"2023-10-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-08-18 | 2023-10-20 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 138487.14 | 0 |  |  |  | 0 |  | 12589.74 |  | 0 | 0 |  | 0 |  | 0
90000529 | Gilloolys View Welcome Sign | Gilloolys View Welcome Sign |  |  | Region 1 | Gauteng South | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng | N | 2023-07-17 | 2023-08-17 |  | ASP-GS0723 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2024-08-30 | GAMIETR | 2023-07-17 | D | 9993.5 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Winston P | 100 | 2023-07-18 | 2023-08-03 | 9993.5 | Approved | {"MANDT":"111","REFERENCE":90000529,"ONEVIEW":"37140X","DATE01":"2023-05-08","DATE02":"2023-06-19","DATE03":"2023-07-10","DATE04":"2023-07-20","DATE05":"2023-08-10","DATE06":"2023-08-24","DATE07":"2023-09-24","DATE08":"2023-10-15","DATE09":"2023-11-29","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"176:42:21:10:21:14:31:21:45:9","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-24","FORECAST_END":"2023-09-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000104086 | PHASE11 | 2023-08-17 | 2023-09-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 23000436 |  |  |  |  | 2023-08-15 | 8690 | 0 |  |  | C000104086 | 8690 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000530 | OR Tambo Minor Works | Remove 4 x wall plugs, make area safe. Make good wall by painting to match existing. Turn the current mobile Office Cubicle by a 90-degree angle to optimize the space in this area. Reposition the electrical points in the ceiling to accommade new office position. |  |  | Region 1 | Gauteng South | 76576X | 1000-70291-01 | OR Tambo International Airport-R24 Highway-Kempton Park | N | 2023-07-17 | 2023-08-17 |  | ASP-GS0724 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-07-17 | D | 19128.94 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Winston P & Ilana vdW | 100 | 2023-07-20 | 2023-07-20 | 19128.94 | Approved | {"MANDT":"111","REFERENCE":90000530,"ONEVIEW":"76576X","DATE01":"2023-05-08","DATE02":"2023-05-15","DATE03":"2023-06-05","DATE04":"2023-06-12","DATE05":"2023-07-03","DATE06":"2023-07-17","DATE07":"2023-08-17","DATE08":"2023-09-07","DATE09":"2023-10-22","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-08-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000110000 | PHASE11 | 2023-07-17 | 2023-08-17 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-09-12 | 16633.86 | 0 |  |  | C000110000 | 16633.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000531 | Meadowdale Upgrade floor tiles at entran | Meadowdale Upgrade floor tiles at entrance |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2023-07-17 | 2023-08-17 |  | ASP-GS0725 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Winston P | 100 | 2023-07-17 | 2023-07-20 | 69494.5 | Approved | {"MANDT":"111","REFERENCE":90000531,"ONEVIEW":"37006X","DATE01":"2023-05-08","DATE02":"2023-05-15","DATE03":"2023-06-05","DATE04":"2023-06-12","DATE05":"2023-07-03","DATE06":"2023-07-17","DATE07":"2023-08-17","DATE08":"2023-09-07","DATE09":"2023-10-22","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-17","FORECAST_END":"2023-08-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000100099 | PHASE11 | 2023-07-17 | 2023-08-17 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-26 | 69494.5 | 0 |  |  | C000100099 | 60430 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000532 | Absa Clearwater Extra Display Screen | Absa Clearwater Extra Display Screen |  |  | Region 1 |  | 77174X | 1000-70352-01 | Clearwater Office Park Building 4-Millenium Rd-Strubensvalley |  | 2023-07-17 | 2023-08-17 |  | ASP-GS0726 | CRTD SETC: |  | false | false |  | Tsholofelo Sello |  |  | 2023 |  |  |  | GAMIETR | 2023-07-17 | D | 0 | 2023.07.13: Approved by Conrad M 2023.07.11: Supported by Winston P as per email | 100 | 2023-07-13 | 2023-07-13 | 70818.82 | Approved |  |  |  | C000098577 | PHASE08 | 2023-06-17 | 2023-07-18 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-18 | 81441.64 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000533 | Pretoria Campus Golf Carts Batteries | Supply and install 8V US-8VGCE Batteries x16. |  |  | Region 1 | Gauteng North | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2023-07-18 | 2023-08-18 |  | ASP-GN0216 | CLSD CNF BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  | F |  | GAMIETR | 2023-07-18 | D | 0 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Winston P as per email | 100 | 2023-07-17 | 2023-07-20 | 72358 | Approved | {"MANDT":"111","REFERENCE":90000533,"ONEVIEW":"22491X","DATE01":"2023-05-09","DATE02":"2023-07-17","DATE03":"2023-07-17","DATE04":"2023-07-17","DATE05":"2023-08-07","DATE06":"2023-08-21","DATE07":"2023-09-21","DATE08":"2023-10-12","DATE09":"2023-11-26","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"175:69:0:0:21:14:31:21:45:8","PROGRESS":79,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-21","FORECAST_END":"2023-09-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IFByb2plY3Qgc3VibWl0dGVkIG9uIENCMjdhcyBwZXIgcmVxdWVzdG9yIE1hcnNoYSBH","RATING":""} |  |  | C000100674 | PHASE11 | 2023-08-21 | 2023-09-21 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-28 | 62920 | 0 |  |  | C00100674 | 62920 |  | 6578 |  | 0 | 0 |  | 0 |  | 0
90000534 | Absa Zeerust - COC (Reinstatement) | Absa Zeerust - COC (Reinstatement) |  |  | Region 3 |  | 21941X | 1000-71241-01 | Absa Zeerust-Cnr Church & President St-Zeerust |  | 2023-08-31 |  |  | ASP-CR0473 | REL BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-19 | D | 0 | Approved | 1 | 2023-10-07 | 2023-10-07 | 19842.1 |  | {"MANDT":"111","REFERENCE":90000534,"ONEVIEW":"Unknown","DATE01":"2023-06-22","DATE02":"2023-06-29","DATE03":"2023-07-20","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-09-30","DATE08":"2023-10-21","DATE09":"2023-12-05","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":95,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2FuY2VsbGVkLg==","RATING":""} |  |  | C000099328 | PHASE12 | 2023-08-31 | 2023-09-30 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-07-21 | 17254 | 0 |  |  | C000099328 | 17254 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000535 | Absa Colesburg - Connect ATM to UPS | Absa Colesburg - Connect ATM to UPS |  |  | Region 3 |  | 78406X | 1000-71348-01 | Colesberg-Church St-Colesberg |  | 2023-08-31 |  |  | ASP-CR0474 | CLSD BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-19 | D | 0 | 2023.07.27: Approved by Kobus JvR as per email 2023.07.25: Supported by Rob L | 100 | 2023-07-27 | 2023-07-27 | 19493.16 | Approved | {"MANDT":"111","REFERENCE":90000535,"ONEVIEW":"Unknown","DATE01":"2023-06-22","DATE02":"2023-06-29","DATE03":"2023-07-20","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-09-30","DATE08":"2023-10-21","DATE09":"2023-12-05","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":77,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEludm9pY2luZyBpbiBwcm9ncmVzcy4=","RATING":""} |  |  |  | PHASE11 | 2023-08-31 | 2023-09-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000101125 | 16950.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000536 | Absa Sannieshof - Installation of dedica | Absa Sannieshof - Installation of dedica |  |  | Region 3 |  | 77996X | 1000-71305-01 | Sannieshof-Spoor St-Sannieshof |  | 2023-08-31 |  |  | ASP-CR0475 | CLSD BUDG AVAC SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-19 | D | 0 | 2023.07.27: Approved by Kobus JvR as per email 2023.07.25: Supported by Rob L | 100 | 2023-07-27 | 2023-07-27 | 22787.97 | Approved | {"MANDT":"111","REFERENCE":90000536,"ONEVIEW":"Unknown","DATE01":"2023-06-22","DATE02":"2023-06-29","DATE03":"2023-07-20","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-09-30","DATE08":"2023-10-21","DATE09":"2023-12-05","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":76,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLg==","RATING":""} |  |  |  | PHASE11 | 2023-08-31 | 2023-09-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000101119 | 19815.63 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000537 | Absa WC Various - Furniture (Chairs) | Absa WC Various - Furniture (Chairs) - for Cape Town Airport, Laingsburg, Oude Bloemhof, Kleinmond and Piketberg |  |  | Region 2 | Western Cape | Various WC | 1000-70759-01 | Various WC | U | 2023-08-01 | 2023-09-30 |  | ASP-N00063 | CLSD BUDG AVAC RESA SETC: |  | false | true |  | Nyasha Wena |  |  | 2023 |  | U |  | CEASARS | 2023-07-19 | D | 78650.11 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Judith B & Ilana vdW | 100 | 2023-07-20 | 2023-07-27 | 78650.11 | Approved | {"MANDT":"111","REFERENCE":90000537,"ONEVIEW":"Various WC","DATE01":"2023-07-10","DATE02":"2023-07-10","DATE03":"2023-07-13","DATE04":"2023-07-20","DATE05":"2023-07-27","DATE06":"2023-10-03","DATE07":"2023-10-06","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":50,"PROG07":40,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:3:7:7:68:3:21:45:26","PROGRESS":45,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-03","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgQXVnIFBhcnQgMSBTdWJtaXR0ZWQgZm9yIEVyZ290aGVyb3B5IC0gUjM3IDc1NC41MA==","RATING":"Low"} |  |  | C000100703 | PHASE11 | 2023-08-18 | 2023-08-28 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-07-28 | 68391.4 | 0 |  |  | C000100703 | 68391.4 |  | 7150.01 |  | 0 | 0 |  | 0 |  | 0
90000538 | Absa Longbeach Mall - Generator Rental | Absa Longbeach Mall - Generator Rental (Retrosepective for OOC approval) |  |  | Region 2 | Western Cape | 77344X | 1000-70822-01 | Longbeach Mall-Cnr Sunnydale Rd & Buller Louw Dr-Noordhoek | N | 2023-07-26 | 2023-08-30 |  | ASP-WC0300 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-19 | D | 331530.67 | 2023.07.27: Approved by Kobus JvR as per email 2023.07.25: Supported by Rob L | 100 | 2023-07-21 | 2023-07-27 | 331530.67 | Approved | {"MANDT":"111","REFERENCE":90000538,"ONEVIEW":"77344X","DATE01":"2023-07-17","DATE02":"2023-07-17","DATE03":"2023-07-17","DATE04":"2023-07-18","DATE05":"2023-07-27","DATE06":"2023-07-27","DATE07":"2023-08-29","DATE08":"2023-10-10","DATE09":"2023-11-24","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"106:0:0:1:9:0:33:42:45:18","PROGRESS":68,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-27","FORECAST_END":"2023-08-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjcgSnVseSBBYnNhIFBPIHJlY2VpdmVkIGFuZCBCViBQTyBpc3N1ZWQKMjcgSnVseSBBcHByb3ZlZCBPT0MgYW5kIG5vdGVkIENCMjggQWJzYSBQTyByZXF1ZXN0ZWQKMjAgSnVseSBCQyBwYWNrIHN1Ym1pdHRlZCBmb3IgT09DIHJldHJvc3BlY3RpdmUgYXBwcm92YWwgMjAgSnVseQ==","RATING":"Low"} |  |  | C000100386 | PHASE11 | 2023-07-27 | 2023-09-15 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-07-27 | 288287.54 | 0 |  |  | C000100386 | 288287.54 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000539 | Absa Hartbeesfontein - Dilaps | Absa Hartbeesfontein - Dilaps |  |  | Region 3 |  | 77915X | 1000-71302-01 | Hartbeesfontein-Voortrekker St-Hartbeesfontein |  | 2023-09-29 | 2023-10-31 |  | ASP-CR0476 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-20 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 318028.64 |  | {"MANDT":"111","REFERENCE":90000539,"ONEVIEW":"77915X","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-26","DATE10":"2024-02-26","DATE11":"2024-01-05","DATE12":"2024-01-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"194:7:21:7:21:14:32:21:66:26","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDYuMDIuMjAyNCBGTTogRmluYWwgUE9DIHJlY2VpdmVkLiAxM0RlYzIwMjMgQmlsbGVkLiAyNi4wMS4yMDI0IGFmdGVyIEFCU0EgQ3V0IG9mZiAyNi4wMi4yMDI0","RATING":""} |  |  | C000106632 | PHASE11 | 2023-09-29 | 2023-10-31 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-08-28 | 276546.64 | 0 |  |  | C000106632 | 276546.64 |  | 11250.04 |  | 0 | 0 |  | 0 |  | 0
90000540 | Absa Kuyasa Mdantsane Revolving Door REm | Absa Kuyasa Mdantsane Revolving Door REm |  |  | Region 2 | Eastern Cape | 79176X | 1000-71065-01 | Kuyasa Shopping Centre-Sandile Rd-Mdantsane |  | 2023-08-01 | 2023-12-29 |  | ASP-EC0333 | CRTD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-07-20 | D | 0 |  | 1 |  |  | 0 | Not part of CIP to be done 2024 | {"MANDT":"111","REFERENCE":90000540,"ONEVIEW":"79176X","DATE01":"2023-05-23","DATE02":"2023-05-30","DATE03":"2023-06-20","DATE04":"2023-06-27","DATE05":"2023-07-18","DATE06":"2023-08-01","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-01","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-08-01 | 2023-09-01 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000541 | Absa Alexandria - Ceiling tiles and new | Absa Alexandria - Ceiling tiles and new |  |  | Region 2 | Eastern Cape | 76600X | 1000-71015-01 | Absa Alexandria-Cnr Voortrekker & Krog St-Alexandria | N | 2023-12-31 |  |  | ASP-EC0334 | CRTD AVAC RESA: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-07-20 | D | 0 |  | 1 |  |  | 0 | Reallocated to Kareedouw, Sterkspruit, Ntabankulu and other Prioritised Projects 13 June as pe Mail From Planner to be addressed 2024 | {"MANDT":"111","REFERENCE":90000541,"ONEVIEW":"76600X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmVhbGxvY2F0ZWQgdG8gS2FyZWVkb3V3LCBTdGVya3NwcnVpdCwgTnRhYmFua3VsdSBhbmQgb3RoZXIgcmV0YWlsIFByaW9yaXRpc2VkIFByb2plY3RzCjEzIEp1bmUgYXMgcGUgTWFpbCBmcm9tIFBsYW5uZXIgdG8gYmUgYWRkcmVzc2VkIDIwMjQK","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 | RODERICK NEVAY | Floyd Mofokeng | 23000121 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000542 | Alice Lane- Procurement of Mugs and Glas | Alice Lane- Procurement of Mugs and Glas |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-08-10 | 2023-12-15 |  | ASP-GS0727 | CRTD AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2023 |  |  |  | LOUISR | 2023-07-20 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Winston P | 100 | 2023-08-03 | 2023-08-03 | 5415.12 | Approved | {"MANDT":"111","REFERENCE":90000542,"ONEVIEW":"35041X","DATE01":"2023-06-01","DATE02":"2023-06-08","DATE03":"2023-06-29","DATE04":"2023-07-06","DATE05":"2023-07-27","DATE06":"2023-08-10","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-10","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE08 | 2023-08-10 | 2023-12-15 | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000543 | Various-Procurement of 4 Patio Gas Braai | Various-Procurement of 4 Patio Gas Braai |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-08-10 | 2023-12-15 |  | ASP-N00064 | CRTD AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2023 |  |  |  | LOUISR | 2023-07-20 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Winston P |  | 2023-08-03 | 2023-08-03 | 55538.8 | Approved |  |  |  |  | PHASE08 | 2023-08-10 | 2023-12-15 | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000544 | Various- EOL equipment, toaster,fish fry | Various- EOL equipment, toaster,fish fry |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-08-10 | 2023-12-15 |  | ASP-N00065 | CRTD AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2023 |  |  |  | LOUISR | 2023-07-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-10 | 2023-12-15 | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000545 | Cradlestone Relocation of the Forex scr | Cradlestone Relocation of the Forex scr |  |  | Region 1 |  | 22950X | 1000-70081-01 | Cradlestone Mall-Cnr Furrow & Hendrik Potgieter Rd-Krugersdorp | N | 2023-07-24 | 2023-07-24 |  | ASP-GN0217 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-07-24 | D | 0 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Winston P & Ilana vdW | 100 | 2023-07-27 | 2023-07-27 | 20046.91 | Approved | {"MANDT":"111","REFERENCE":90000545,"ONEVIEW":"22950X","DATE01":"2023-05-15","DATE02":"2023-05-22","DATE03":"2023-06-12","DATE04":"2023-06-19","DATE05":"2023-07-10","DATE06":"2023-07-24","DATE07":"2023-09-27","DATE08":"2023-10-18","DATE09":"2023-12-02","DATE10":"2023-12-31","DATE11":"2023-12-02","DATE12":"2023-12-02","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":20,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":14,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-24","FORECAST_END":"2023-09-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogSW5zdGFsbGF0aW9uIGNvbXBsZXRlIHRvZGF5Lg==","RATING":""} |  |  | C000101349 | PHASE07 | 2023-07-24 | 2023-09-27 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-08-01 | 20046.9 | 0 |  |  | C000101349 | 17432.09 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000546 | Menlyn Maine Addition of a 3rd Consultan | Menlyn Maine Addition of a 3rd Consultan |  |  | Region 1 | Gauteng North | 36233X | 1000-70194-01 | Menlyn Maine Central Square-Cnr Aramist & Corobay Ave-Waterkloof Glen | N | 2023-07-24 | 2023-07-24 |  | ASP-GN0218 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-07-24 | D | 49267.18 | 2023.07.26: Approved by Conrad M as per email 2023.07.25: Supported by Winston P & Ilana vdW | 100 | 2023-07-27 | 2023-07-27 | 49267.18 | Approved | {"MANDT":"111","REFERENCE":90000546,"ONEVIEW":"36233X","DATE01":"2023-05-15","DATE02":"2023-05-22","DATE03":"2023-06-12","DATE04":"2023-06-19","DATE05":"2023-07-10","DATE06":"2023-07-24","DATE07":"2023-11-23","DATE08":"2023-12-14","DATE09":"2024-01-28","DATE10":"2024-01-31","DATE11":"2024-01-28","DATE12":"2024-01-28","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":30,"PROG05":100,"PROG06":50,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":29,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-24","FORECAST_END":"2023-11-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUHJvamVjdCBjb21wbGV0ZSBsYXN0IEZyaWRheS4gRmluYWwgUE9DIGluIHByb2dyZXNzLiA=","RATING":""} |  |  | C000101350 | PHASE07 | 2023-07-24 | 2023-11-23 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-08-01 | 42841.01 | 0 |  |  | C000101350 | 42841.01 |  | 4235.2 |  | 0 | 0 |  | 0 |  | 0
90000547 | Absa Mossel Bay - Hydroboil and Minor Wo | Absa Mossel Bay - Hydroboil and Minor Wo |  |  | Region 2 | Eastern Cape | 77747X | 1000-70855-01 | Absa Mossel Bay-Marsh St-Mossel Bay |  | 2023-12-31 |  |  | ASP-EC0335 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to Kareedouw, Sterkspruit, Ntabankulu and other Prioritised Projects 26 May Planner confirmed Fire Life Safety only | {"MANDT":"111","REFERENCE":90000547,"ONEVIEW":"77747X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 | RODERICK NEVAY | nokuthula manzini | 23000049 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000548 | Absa Patensie - Boundary fence - extend | Absa Patensie - Boundary fence - extend |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2023-12-31 |  |  | ASP-EC0336 | CRTD: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 15 June - Fund Reallocate to MOP for Shortfall for MTR room | {"MANDT":"111","REFERENCE":90000548,"ONEVIEW":"","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000378 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000549 | Garden Route Centre - Knysna - Add raili | Garden Route Centre - Knysna - Add raili |  |  | Region 2 | Eastern Cape | 77262X | 1000-70816-01 | Garden Route Centre Knysna-Cnr Gray & Main St-Knysna | N | 2023-12-31 |  |  | ASP-EC0337 | CRTD: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to Kareedouw, Sterkspruit, Ntabankulu and other Prioritised Projects 5 June PM to follow up with planner re final requirements - to be done with Minor works 2024 | {"MANDT":"111","REFERENCE":90000549,"ONEVIEW":"77262X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-05-25 | 2023-06-24 |  |  | 23000422 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000550 | Absa Germiston Dilaps | Absa Germiston Dilaps |  |  | Region 1 | Gauteng South | 70654X | 1000-70237-01 | United House-Cnr Meyer & Library St-Germiston | N | 2023-07-25 | 2023-07-25 |  | ASP-GS0728 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L | 2023-06-29 | GAMIETR | 2023-07-25 | D | 181071.14 | Approved by Lebusa M | 100 | 2023-07-10 | 2023-07-24 | 181074.14 | Approved | {"MANDT":"111","REFERENCE":90000550,"ONEVIEW":"70654X","DATE01":"2023-05-16","DATE02":"2023-05-16","DATE03":"2023-06-07","DATE04":"2023-06-14","DATE05":"2023-08-16","DATE06":"2023-06-22","DATE07":"2023-06-24","DATE08":"2023-09-03","DATE09":"2023-10-18","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"137:0:22:7:63:-55:2:71:45:1","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-22","FORECAST_END":"2023-06-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":"Low"} |  |  | C000099862 | PHASE10 | 2023-05-30 | 2023-06-01 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-25 | 181071.15 | 0 |  |  | C000099862 | 157453.17 |  | 16314.65 |  | 0 | 0 |  | 0 |  | 0
90000551 | Various WC Branches - RBB Shortfall | Various WC Branches - RBB Shortfall |  |  | Region 2 | Western Cape | Various WC |  | Various WC Branches | U | 2023-12-31 |  |  | ASP-N00066 | CRTD: |  | false | true |  | Nyasha Wena |  |  | 2023 |  | U |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to various other retail Prioritised Projects in the region | {"MANDT":"111","REFERENCE":90000551,"ONEVIEW":"Various WC","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000171 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000552 | Various WC Branches - RBB Shortfall 2 | Various WC Branches - RBB Shortfall 2 |  |  | Region 2 | Western Cape | Various WC |  | Various WC Branches | U | 2023-12-31 |  |  | ASP-N00067 | CRTD: |  | false | true |  | Nyasha Wena |  |  | 2023 |  | U |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to various other retail Prioritised Projects in the region | {"MANDT":"111","REFERENCE":90000552,"ONEVIEW":"Various WC","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000091 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000553 | Various WC Branches - RBB Shortfall 3 | Various WC Branches - RBB Shortfall 3 |  |  | Region 2 | Western Cape | Various WC |  | Various WC Branches | U | 2023-12-31 |  |  | ASP-N00068 | CRTD: |  | false | true |  | Nyasha Wena |  |  | 2023 |  | U |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to various other retail Prioritised Projects in the region | {"MANDT":"111","REFERENCE":90000553,"ONEVIEW":"Various WC","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000071 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000554 | Various Sites EC - Budget for RBB Shortfall | Various Sites EC - Budget for RBB Shortfall |  |  | Region 2 | Eastern Cape | Various EC |  | Various EC Branches | U | 2023-12-31 |  |  | ASP-N00069 | CRTD: |  | false | true |  | Laxine Maliffe |  |  | 2023 |  | U |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to various other retail Prioritised Projects in the region | {"MANDT":"111","REFERENCE":90000554,"ONEVIEW":"Various EC","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000031 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000555 | Various EC Branches - RBB Shortfall 2 | Various EC Branches - RBB Shortfall 2 |  |  | Region 2 | Eastern Cape | Various EC |  | Various EC Branches | U | 2023-12-31 |  |  | ASP-N00070 | CRTD: |  | false | true |  | Laxine Maliffe |  |  | 2023 |  | U |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to various other retail Prioritised Projects in the region | {"MANDT":"111","REFERENCE":90000555,"ONEVIEW":"Various EC","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000082 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000556 | Various EC Branches - RBB Shortfall 3 | Various EC Branches - RBB Shortfall 3 |  |  | Region 2 | Eastern Cape | Various EC |  | Various EC Branches | U | 2023-12-31 |  |  | ASP-N00071 | CRTD: |  | false | true |  | Laxine Maliffe |  |  | 2023 |  | U |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to various other retail Prioritised Projects in the region | {"MANDT":"111","REFERENCE":90000556,"ONEVIEW":"Various EC","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmVhbGxvY2F0ZWQgdG8gdmFyaW91cyBvdGhlciByZXRhaWwgUHJpb3JpdGlzZWQgUHJvamVjdHMgaW4gdGhlIHJlZ2lvbg==","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000032 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000557 | Absa Westgate Mall - Minor Works | Absa Westgate Mall - Minor Works |  |  | Region 2 | Western Cape | 77268X | 1000-70817-01 | Westgate Mall Mitchells Plain-Cnr Jakes Gerwel Dr & Morgenster Rd-Mitchells Plai | N | 2023-12-31 |  |  | ASP-WC0301 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to Worcester, Gugulethu, Lutzville, Laingsburg, Eighty Beach RD and other Prioritised Projects 14 April Confirmed Cancelled as PMO project | {"MANDT":"111","REFERENCE":90000557,"ONEVIEW":"77268X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmVhbGxvY2F0ZWQgdG8gV29yY2VzdGVyLCBHdWd1bGV0aHUsIEx1dHp2aWxsZSwgTGFpbmdzYnVyZywgRWlnaHR5IEJlYWNoIFJEIGFuZCBvdGhlciBQcmlvcml0aXNlZCBQcm9qZWN0cw==","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000152 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000558 | The John Montague Centre - Replace ceili | The John Montague Centre - Replace ceili |  |  | Region 2 | Western Cape | 77789X | 1000-70859-01 | The John Montague Centre-Montague Dr-Montague Gardens | N | 2023-12-31 |  |  | ASP-WC0302 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to Worcester, Gugulethu, Lutzville, Laingsburg, Eighty Beach RD and other Prioritised Projects 14 April Confirmed Cancelled as PMO project | {"MANDT":"111","REFERENCE":90000558,"ONEVIEW":"77789X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000201 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000559 | Fish Hoek Town Square - Minor Works | Fish Hoek Town Square - Minor Works |  |  | Region 2 | Western Cape | 77680X | 1000-70845-01 | Fish Hoek Town Square-Main Rd-Fish Hoek | N | 2023-12-31 |  |  | ASP-WC0303 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Reallocated to Worcester, Gugulethu, Lutzville, Laingsburg, Eighty Beach RD and other Prioritised Projects 22 May Cancelled by Planners 20th May | {"MANDT":"111","REFERENCE":90000559,"ONEVIEW":"77680X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000061 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000560 | Absa Erika Sentrum - An improved weather | Absa Erika Sentrum - An improved weather |  |  | Region 2 | Western Cape | 77698X | 1000-70848-01 | Erika Sentrum-Cnr Main Rd & First St-Kleinmond | N | 2023-12-31 |  |  | ASP-WC0304 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 22 May Cancelled by Planners 20th May Reallocated to other retail projects | {"MANDT":"111","REFERENCE":90000560,"ONEVIEW":"77698X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000331 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000561 | De Wagenweg Office Park Block B - Instal | De Wagenweg Office Park Block B - Instal |  |  | Region 2 | Western Cape | 70650X | 1000-70785-01 | De Wagenweg Office Park Block B-Adam Tas Rd-Stellenbosch | N | 2023-12-31 |  |  | ASP-WC0305 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 24 April - ENG indicated - Cummins not compatible with Deep Sea Controllers | {"MANDT":"111","REFERENCE":90000561,"ONEVIEW":"70650X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000335 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000562 | Cape Town International Airport - Painti | Cape Town International Airport - Painti |  |  | Region 2 | Western Cape | 76946X | 1000-70791-01 | Cape Town International Airport-N2-Cape Town | N | 2023-12-31 |  |  | ASP-WC0306 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | Done Against ASP-WC0298 | {"MANDT":"111","REFERENCE":90000562,"ONEVIEW":"76946X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NyBBdWcgUE0gdG8gY29uZmlybSB3aXRoIFBsYW5uZXIgaWYgdG8gcHJvY2VlZCBvciBub3QgZHVlIHRvIHBlbmRpbmcgU2l0ZSBUZW5kZXI=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000269 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000563 | Bridge Park - Creation of large meeting | Bridge Park - Creation of large meeting |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2023-12-31 |  |  | ASP-WC0307 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 5 June - Reallocated to Reg 1 - Winston | {"MANDT":"111","REFERENCE":90000563,"ONEVIEW":"36225X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000025 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000564 | Absa Worcester - Replace Central rooftop | Absa Worcester - Replace Central rooftop |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester-Stockenstrom St-Worcester | N | 2023-12-31 |  |  | ASP-WC0308 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 27 Feb amount to be reallocated to cover other shortfalls with HVAC to be done 2024 | {"MANDT":"111","REFERENCE":90000564,"ONEVIEW":"78016X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000242 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000565 | Absa Villiersdorp - Installation of the | Absa Villiersdorp - Installation of the |  |  | Region 2 | Western Cape | 77712X | 1000-70851-01 | Absa Villiersdorp-Main St-Villiersdorp | N | 2023-12-31 |  |  | ASP-WC0309 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 20 April - On phase 2 rollout for Solar & Possible closure | {"MANDT":"111","REFERENCE":90000565,"ONEVIEW":"77712X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 | RODERICK NEVAY | Michael Magubane | 23000251 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000566 | Absa Malmesbury - Bird proofing - 30m | Absa Malmesbury - Bird proofing - 30m |  |  | Region 2 | Western Cape | 78113X | 1000-70887-01 | Absa Malmesbury-Voortrekker Rd-Malmesbury | N | 2023-12-31 |  |  | ASP-WC0310 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 15 June - Reallocate to MOP for Shortfall for MTR room | {"MANDT":"111","REFERENCE":90000566,"ONEVIEW":"78113X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000312 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000567 | Absa Lower Long Street - New Storerooms | Absa Lower Long Street - New Storerooms |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | N | 2023-12-31 |  |  | ASP-WC0311 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 5 June - Reallocated to Oude Bloemhof Storerooms were fubded from funds available and incoporated with ASP-WC0262 | {"MANDT":"111","REFERENCE":90000567,"ONEVIEW":"77657X","DATE01":"2023-10-22","DATE02":"2023-10-29","DATE03":"2023-11-19","DATE04":"2023-11-26","DATE05":"2023-12-17","DATE06":"2023-12-31","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-31","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000088 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000568 | Simphiwe Building - Saldanha - Connect c | Simphiwe Building - Saldanha - Connect c |  |  | Region 2 | Western Cape | 77766X | 1000-70856-01 | Simphiwe Building-Saldanha Rd-Saldanha | N | 2023-12-31 |  |  | ASP-WC0312 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 3 July - Engineering to advise on requirements and expected loads 15 June Engineering to advise re EB list | {"MANDT":"111","REFERENCE":90000568,"ONEVIEW":"77766X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-07-04","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBKdWx5IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIG9uIHJlcXVpcmVtZW50cyBhbmQgZXhwZWN0ZWQgbG9hZHMKMTUgSnVuZSBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgRUIgbGlzdAo=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000400 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000569 | Eskom Building - Connect critical load t | Eskom Building - Connect critical load t |  |  | Region 2 | Western Cape | 78147X | 1000-70893-01 | Eskom Building-Voortrek St-Swellendam | N | 2023-12-31 |  |  | ASP-WC0313 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 3 July - Engineering to advise on requirements and expected loads 15 June Engineering to advise re EB list | {"MANDT":"111","REFERENCE":90000569,"ONEVIEW":"78147X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-07-04","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBKdWx5IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIG9uIHJlcXVpcmVtZW50cyBhbmQgZXhwZWN0ZWQgbG9hZHMKMTUgSnVuZSBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgRUIgbGlzdAo=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000418 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000570 | Absa Piketberg - Connect critical load o | Absa Piketberg - Connect critical load o |  |  | Region 2 | Western Cape | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg | N | 2023-12-31 |  |  | ASP-WC0314 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 3 July - Engineering to advise on requirements and expected loads 15 June Engineering to advise re EB list | {"MANDT":"111","REFERENCE":90000570,"ONEVIEW":"78132X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-07-04","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBKdWx5IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIG9uIHJlcXVpcmVtZW50cyBhbmQgZXhwZWN0ZWQgbG9hZHMKMTUgSnVuZSBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgRUIgbGlzdAo=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000405 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000571 | Absa Hermanus - Connect critical load to | Absa Hermanus - Connect critical load to |  |  | Region 2 | Western Cape | 77701X | 1000-71438-01 | Hermanus-Main Rd-Hermanus | N | 2023-12-31 |  |  | ASP-WC0315 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 3 July - Engineering to advise on requirements and expected loads 15 June Engineering to advise re EB list | {"MANDT":"111","REFERENCE":90000571,"ONEVIEW":"77701X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-07-04","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBKdWx5IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIG9uIHJlcXVpcmVtZW50cyBhbmQgZXhwZWN0ZWQgbG9hZHMKMTUgSnVuZSBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgRUIgbGlzdAo=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000394 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000572 | Absa Caledon - Connect critical load to | Absa Caledon - Connect critical load to |  |  | Region 2 | Western Cape | 77399X | 1000-70830-01 | Absa Caledon-Donkin Square-Caledon | N | 2023-12-31 |  |  | ASP-WC0316 | CRTD: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-25 | D | 0 |  | 1 |  |  | 0 | 3 July - Engineering to advise on requirements and expected loads 15 June Engineering to advise re EB list | {"MANDT":"111","REFERENCE":90000572,"ONEVIEW":"77399X","DATE01":"2023-01-19","DATE02":"2023-01-26","DATE03":"2023-02-16","DATE04":"2023-02-23","DATE05":"2023-03-16","DATE06":"2023-03-30","DATE07":"2023-04-29","DATE08":"2023-05-20","DATE09":"2023-07-04","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-30","FORECAST_END":"2023-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MyBKdWx5IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIG9uIHJlcXVpcmVtZW50cyBhbmQgZXhwZWN0ZWQgbG9hZHMKMTUgSnVuZSBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgRUIgbGlzdAo=","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-04-29 |  |  | 23000406 | [5 empty] | 0 | 0 |  |  |  | 0 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000573 | Absa Mooi River - Supply Graphic Design | Absa Mooi River - Supply Graphic Design |  |  | Region 3 | [5 empty] | 2023-10-30 |  |  | ASP-CR0477 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-10-30 | 2023-11-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000574 | Absa Mooi River - Installation of plugs | Absa Mooi River - Installation of plugs |  |  | Region 3 |  | Unknown | 1000-71242-01 | Unknown Building - not in our database |  | 2023-09-27 |  |  | ASP-CR0478 | CLSD BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-26 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 25862.15 |  | {"MANDT":"111","REFERENCE":90000574,"ONEVIEW":"Unknown","DATE01":"2023-07-19","DATE02":"2023-07-26","DATE03":"2023-08-16","DATE04":"2023-08-23","DATE05":"2023-09-13","DATE06":"2023-09-27","DATE07":"2023-10-27","DATE08":"2023-11-17","DATE09":"2024-01-01","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":50,"PROG09":30,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":71,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-27","FORECAST_END":"2023-10-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBDb21wbGV0ZWQ7IGludm9pY2luZyBpbiBwcm9ncmVzcw==","RATING":""} |  |  | C000125331 | PHASE11 | 2023-09-27 | 2023-10-27 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-21 | 22488.83 | 0 |  |  | C000102377 | 22488.83 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000575 | Absa Rusternburg Plaza -Installation of | Absa Rusternburg Plaza -Installation of |  |  | Region 3 |  | Unknown | 1000-71603-01 | Unknown Building - not in our database |  | 2023-10-05 |  |  | ASP-CR0479 | CLSD BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-26 | D | 20240.32 |  | 100 |  |  | 20240.32 |  | {"MANDT":"111","REFERENCE":90000575,"ONEVIEW":"Unknown","DATE01":"2023-07-27","DATE02":"2023-08-03","DATE03":"2023-08-24","DATE04":"2023-08-31","DATE05":"2023-09-21","DATE06":"2023-10-05","DATE07":"2023-11-04","DATE08":"2023-11-25","DATE09":"2024-01-09","DATE10":"2024-01-31","DATE11":"2024-01-09","DATE12":"2024-01-09","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-11-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  | C000102217 | PHASE11 | 2023-10-05 | 2023-11-04 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 21861.15 | 0 |  |  | C000102217 | 21861.15 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000576 | Absa Bloemfontein RHO - Minor Works | Absa Bloemfontein RHO - Minor Works |  |  | Region 3 | [5 empty] | 2023-10-31 |  |  | ALP-CR0039 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-07-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-10-31 | 2023-11-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000577 | Absa Humansdorp - Dilaps | Absa Humansdorp - Dilaps for Revamp |  |  | Region 2 | Eastern Cape | 78943X | 1000-71467-01 | 9 Main Street Humansdorp-Main St-Humansdorp | N | 2023-09-29 | 2023-12-29 |  | ASP-EC0338 | TECO BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-07-28 | D | 53888.75 |  | 100 | 2023-08-02 | 2023-08-03 | 53888.75 | 4 Aug Absa PO received C000102209 2 Aug Submitted to Real Estate for Approval | {"MANDT":"111","REFERENCE":90000577,"ONEVIEW":"78943X","DATE01":"2023-07-01","DATE02":"2023-07-08","DATE03":"2023-07-29","DATE04":"2023-08-02","DATE05":"2023-08-03","DATE06":"2023-08-04","DATE07":"2023-08-12","DATE08":"2023-09-28","DATE09":"2023-11-12","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"122:7:21:4:1:1:8:47:45:14","PROGRESS":82,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-04","FORECAST_END":"2023-08-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjggU2VwdCBQT0MgUGFydCAyICYgRmluYWwgUE9DIFN1Ym1pdHRlZCBmb3IgRkFEVCAyOCBTZXB0IC0gNCA4NTUuOTcgVG90YWwgLSA1MiA2MzQuMjgKMjIgU2VwdCBGQURUIEludm9pY2UgU3RpbGwgb3V0c3RhbmRpbmcKUE9DIFBhcnQgMSBTdWJtaXR0ZWQgMjkgQXVnIGZvciBHbG9iYWwsIEtvZW4ncyBhbmQgU2VjdXRlbCAtIFIgNDIgOTIyLjM1IChGQURUIE91dHN0YW5kaW5nKQ==","RATING":""} |  |  | C000102209 | PHASE09 | 2023-08-04 | 2023-08-12 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-04 | 46859.78 | 0 |  |  | C000102209 | 46859.78 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000578 | Absa 32 Voortrekker Bellville - Generator Alternator Replacement (Retrospective) | Absa 32 Voortrekker Bellville - Generator Alternator Replacement (Retrospective) |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2023-06-15 | 2023-08-31 |  | ASP-WC0317 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-07-28 | D | 479188.9 |  | 100 | 2023-08-17 | 2023-08-24 | 479188.9 | 24 Aug Change approved CB32 for new Value of R 479 188.90 was R 347 845.68 | {"MANDT":"111","REFERENCE":90000578,"ONEVIEW":"78126X","DATE01":"2023-07-28","DATE02":"2023-07-28","DATE03":"2023-07-31","DATE04":"2023-07-31","DATE05":"2023-08-11","DATE06":"2023-08-11","DATE07":"2023-08-11","DATE08":"2023-09-01","DATE09":"2023-10-16","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:3:0:11:0:0:21:45:25","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-11","FORECAST_END":"2023-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MiBKdWx5IEZvbGxvd2VkIHVwIHdpdGggQ3JlcyBFbmdpbmVlcmluZyByZSBBcHByb3ZhbCBpbiBvcmRlciB0byBpc3N1ZSB0aGUgUE8ncwozMSBKdWx5IFN1Ym1pdHRlZCBmb3IgQ1JFUyBFbmdpbmVlcmluZyBmb3IgT09DIGFwcHJvdmFsIG9mIGNvc3QK","RATING":""} |  |  | C000102809 | PHASE11 | 2023-09-06 | 2023-09-06 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-06 | 416686 | 0 |  |  | C000102809 | 416686 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000579 | Sanridge Square Ceiling Panels replacement | Sanridge Square Ceiling Panels replacement |  |  | Region 1 |  | 21861X | 1000-70042-01 | Sanridge Square Shopping Centre-Cnr New & Lever Rd-Midrand |  | 2023-07-31 | 2023-08-31 |  | ASP-GN0219 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-07-31 | D | 278231.23 |  | 100 | 2023-08-08 | 2023-08-15 | 278231.23 |  | {"MANDT":"111","REFERENCE":90000579,"ONEVIEW":"21861X","DATE01":"2023-05-22","DATE02":"2023-05-29","DATE03":"2023-07-31","DATE04":"2023-08-07","DATE05":"2023-08-31","DATE06":"2023-09-14","DATE07":"2023-10-20","DATE08":"2023-11-10","DATE09":"2023-12-25","DATE10":"2023-12-31","DATE11":"2023-12-25","DATE12":"2023-12-25","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:7:63:7:24:14:36:21:45:25","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-14","FORECAST_END":"2023-10-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogUHJvamVjdCBjb21wbGV0ZS4gQXdhaXRpbmcgQWJzYSB0byBzaWduIFBPQyAxLiBBd2FpdGluZyBGaWRlbGl0eSAmIFVraHVuaSBJbnZvaWNlcyBmb3IgRmluYWwgUE9DLg==","RATING":""} |  |  | C000104094 | PHASE08 | 2023-09-14 | 2023-10-20 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-09-15 | 241940.2 | 0 |  |  | C000104094 | 241940.2 |  | 25159.2 |  | 0 | 0 |  | 0 |  | 0
90000580 | Rosstax Replace security entrance door | Rosstax Replace security entrance door |  |  | Region 1 |  | 76646X | 1000-70301-01 | Rosstax Centre-Cnr R566 & Hardie Muller St-Rosslyn |  | 2023-07-31 | 2023-08-31 |  | ASP-GN0220 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-07-31 | D | 0 |  | 100 |  |  | 0 | C000119224 - DD PO | {"MANDT":"111","REFERENCE":90000580,"ONEVIEW":"76646X","DATE01":"2023-05-22","DATE02":"2023-05-29","DATE03":"2023-06-19","DATE04":"2023-06-26","DATE05":"2023-09-21","DATE06":"2023-10-05","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:7:21:7:87:14:26:21:45:25","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFBoYXNlIDEgKEREKSwgQXdhaXRpbmcgUE9z","RATING":""} |  |  | C000119224 | PHASE09 | 2023-10-05 | 2023-10-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-10-26 | 16940 | 0 |  |  | C000119224 | 16940 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000581 | Diepsloot Bulk Teller Upgrade | Diepsloot Bulk Teller Upgrade |  |  | Region 1 | Gauteng North | 78651X | 1000-70431-01 | Diepsloot Mall-Cnr William Nicol Dr & Plum St-Diepsloot West | N | 2023-07-31 | 2023-08-31 |  | ASP-GN0221 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  | Suppliers on site on the 25th October and to complete on the same day | 2023 |  | L | 2023-10-30 | GAMIETR | 2023-07-31 | D | 41923.23 | Approved at CB31 | 100 | 2023-08-14 | 2023-08-17 | 41923.23 |  | {"MANDT":"111","REFERENCE":90000581,"ONEVIEW":"78651X","DATE01":"2023-05-22","DATE02":"2023-05-29","DATE03":"2023-06-19","DATE04":"2023-06-26","DATE05":"2023-08-17","DATE06":"2023-10-09","DATE07":"2023-11-09","DATE08":"2023-11-30","DATE09":"2024-01-14","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"223:7:21:7:52:53:31:21:45:25","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-09","FORECAST_END":"2023-11-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VwcGxpZXIgaXMgbWFudWZhY3R1cmluZyB0aGUgY3ViaWNsZQ==","RATING":""} |  |  | C000105055 | PHASE11 | 2023-10-09 | 2023-10-25 | CHRISTOPHER MPOFU | Obakeng Phuti | 23000230 |  |  |  |  | 2023-08-21 | 36454.98 | 0 |  |  | C000105055 | 36454.98 | CIP2023XP | 3660.66 |  | 0 | 0 |  | 0 |  | 0
90000582 | Key West Install vinyl marketing poster | Key West Install vinyl marketing poster |  |  | Region 1 |  | 22890X | 1000-70077-01 | Key West Shopping Centre-Cnr Paardekraal & Viljoen Rd-Krugersdorp |  | 2023-07-31 | 2023-08-31 |  | ASP-GN0222 | REL RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-07-31 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Winston P | 100 | 2023-08-03 | 2023-08-03 | 20463.34 | Approved | {"MANDT":"111","REFERENCE":90000582,"ONEVIEW":"22890X","DATE01":"2023-05-22","DATE02":"2023-05-29","DATE03":"2023-06-19","DATE04":"2023-06-26","DATE05":"2023-08-31","DATE06":"2023-09-14","DATE07":"2023-10-15","DATE08":"2023-11-05","DATE09":"2023-12-20","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:7:21:7:66:14:31:21:45:25","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-14","FORECAST_END":"2023-10-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000104095 | PHASE06 | 2023-09-14 | 2023-10-15 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-08-15 | 23532.84 | 0 |  |  | C000140766 | 17794.21 |  | 1796.67 |  | 0 | 0 |  | 0 |  | 0
90000583 | Towers West Relocate Walk-In Centre | Towers West Relocate Walk-In Centre |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-07-31 | 2023-08-31 |  | ASP-GS0729 | REL BUDG ISBD AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-07-31 | D | 142477.94 |  | 100 | 2023-11-07 | 2023-11-07 | 142477.94 | Awaiting BFM PO | {"MANDT":"111","REFERENCE":90000583,"ONEVIEW":"21526X","DATE01":"2023-05-22","DATE02":"2023-05-29","DATE03":"2023-06-19","DATE04":"2023-08-22","DATE05":"2023-09-12","DATE06":"2023-09-26","DATE07":"2023-10-27","DATE08":"2023-11-17","DATE09":"2024-01-01","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"192:7:21:64:21:14:31:21:45:25","PROGRESS":6,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-26","FORECAST_END":"2023-10-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"TWVldGluZyBzY2hlZHVsZWQgZm9yIDEwLzI3MjAyMyB0byByZXNvbHZlIFZQIGNvbW1lbnRzIC0gcmVsb2NhdGluZyBvZiB0aGUgc2FmZSBkb29yIHRvIHRoZSBpbnNpZGUgb2YgdGhlIENJVCBnYXJhZ2Ugd2hlcmUgdGhlIEJDVFUgaXMgbG9jYXRlZC7CoA==","RATING":""} |  |  | C000121928 | PHASE08 | 2023-11-24 | 2023-11-24 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-08 | 163758.96 | 0 |  |  | C000121928 | 163758.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000584 | Various- Battery Energy Storage Systems | Various- Battery Energy Storage Systems |  |  | Energy | National | Unknown | 1000-70027-01 | Unknown Building - not in our database | N | 2023-08-10 | 2023-12-15 |  | ALP-N00050 | REL BUDG AVAC RESA SETC: |  | false | true |  | Onisms Manyewe |  | Engineer, design, supply, install, and commissioning of battery energy storage systems at 4 Corporate sites, namely Bridge Park East, Auckland Park, PTA Campus and 270 Republic Road. | 2023 |  |  |  | LOUISR | 2023-07-31 | D | 61127150.72 | CP: Approved at BTB 2023/07/27 | 100 | 2023-07-20 | 2023-07-27 | 61127150.72 |  | {"MANDT":"111","REFERENCE":90000584,"ONEVIEW":"21526X","DATE01":"2023-06-01","DATE02":"2023-06-08","DATE03":"2023-06-29","DATE04":"2023-07-06","DATE05":"2023-07-27","DATE06":"2023-08-10","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-10","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QVM6IDAyLzA4LzIwMjMgIFBlciBPbmlzbXMgNzAlIG9mIGNhc2ggZmxvdyBleHBlY3RlZCBieSAzMC4xMS4yMDIzLiBDb250cmFjdHMgc3VibWl0dGVkIHRvIEFCU0EgTGVnYWwgZm9yIGFwcHJvdmFsLgo=","RATING":""} |  |  | C000120110 | PHASE07 | 2023-08-10 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 |  |  |  |  | 2023-10-31 | 53154044.1 | 11974457.15 |  |  | C000141159 | 41179586.95 |  | 2303818.66 |  | 0 | 0 |  | 0 |  | 0
90000585 | Absa Jan Kempdorp - Replacement of AC Sp | Absa Jan Kempdorp - Replacement of AC Sp |  |  | Region 3 |  | 78326X | 1000-71347-01 | Jan Kempdorp-De La Rey St-Jan Kempdorp |  | 2023-10-31 | 2023-10-31 |  | ASP-CR0480 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-02 | D | 31900.32 |  | 100 |  |  | 31900.32 |  | {"MANDT":"111","REFERENCE":90000585,"ONEVIEW":"78326X","DATE01":"2023-08-22","DATE02":"2023-08-29","DATE03":"2023-09-19","DATE04":"2023-09-26","DATE05":"2023-10-17","DATE06":"2023-10-31","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":30,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":84,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgYW5kIGludm9pY2U=","RATING":""} |  |  |  | PHASE09 | 2023-10-31 | 2023-10-31 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 2569.57 |  | 0 | 0 |  | 0 |  | 0
90000586 | Absa Thohoyandou - Teller Closure | Absa Thohoyandou - Teller Closure |  |  | Region 3 |  | 21948X | 1000-70464-01 | Game Shopping Centre-Mphetu Rd-Thohoyandou |  | 2023-09-28 | 2023-10-30 |  | ASP-LP0169 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-02 | D | 0 |  | 100 | 2023-08-07 | 2023-08-11 | 175710.09 |  | {"MANDT":"111","REFERENCE":90000586,"ONEVIEW":"21948X","DATE01":"2023-07-20","DATE02":"2023-07-27","DATE03":"2023-08-17","DATE04":"2023-08-24","DATE05":"2023-08-18","DATE06":"2023-08-24","DATE07":"2023-08-24","DATE08":"2023-11-20","DATE09":"2024-01-04","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":56,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-24","FORECAST_END":"2023-08-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"cHJvamVjdCBzY2hlZHVsZWQ=","RATING":""} |  |  | C000103922 | PHASE11 | 2023-08-24 | 2023-08-24 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-15 | 21848.4 | 0 |  |  | C000103922 | 21848.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000587 | Absa Longbeach Mall - Radiator | Absa Longbeach Mall - Radiator Replacement |  |  | Region 2 | Western Cape | 77344X | 1000-70822-01 | Longbeach Mall-Cnr Sunnydale Rd & Buller Louw Dr-Noordhoek | N | 2023-09-01 | 2023-10-31 |  | ASP-WC0318 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-08-02 | D | 139066.25 |  | 100 | 2023-09-01 | 2023-09-01 | 139066.25 | 5 Sept Absa PO received C000108173 01 Sept New Quote issued and OOC was approved, Absa PO to be requested | {"MANDT":"111","REFERENCE":90000587,"ONEVIEW":"77344X","DATE01":"2023-08-01","DATE02":"2023-08-01","DATE03":"2023-08-03","DATE04":"2023-08-03","DATE05":"2023-08-03","DATE06":"2023-08-17","DATE07":"2023-10-16","DATE08":"2023-11-06","DATE09":"2023-12-21","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:2:0:0:14:60:21:45:26","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-17","FORECAST_END":"2023-10-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBBdWcgLSBBYnNhIEVORyBpbmRpY2F0ZWQgdG8gYmUgZG9uZSB2aWEgR01QLCBCViBFbmcgdG8gcmVzcG9uZAoyIEF1ZyBTdWJtaXR0ZWQgdG8gQWJzYSBDUkVTIGZvciBPT0MgYXBwcm92YWwgaW4gb3JkZXIgdG8gcmVxdWVzdCBQTydzCjEgQXVnIFBSRiByZWNlaXZlZA==","RATING":""} |  |  | C000108173 | PHASE11 | 2023-09-11 | 2023-09-12 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-04 | 120927.18 | 0 |  |  | C000108173 | 120927.18 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000588 | Absa Citrusdal - Generator Major Service | Absa Citrusdal - Generator Major Service |  |  | Region 2 | Western Cape | 78131X | 1000-71446-01 | Absa Citrusdal-Voortrekker St-Citrusdal | N | 2023-09-01 | 2023-10-31 |  | ASP-WC0319 | CRTD SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-08-02 | D | 0 |  | 1 |  |  | 0 | 4 Sept - PE indicated to be done as ABQT as per mail received 14 Aug - Costs to be split for the injectors from service costs and new PRF to be issued 2 Aug PRF received, Mail from Busisiwe re Consolidated BC? | {"MANDT":"111","REFERENCE":90000588,"ONEVIEW":"78131X","DATE01":"2023-08-14","DATE02":"2023-08-21","DATE03":"2023-09-11","DATE04":"2023-09-18","DATE05":"2023-10-09","DATE06":"2023-10-23","DATE07":"2023-12-22","DATE08":"2024-01-12","DATE09":"2024-02-26","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:60:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-23","FORECAST_END":"2023-12-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgQXVnIC0gQ29zdHMgdG8gYmUgc3BsaXQgZm9yIHRoZSBpbmplY3RvcnMgZnJvbSBzZXJ2aWNlIGNvc3RzIGFuZCBuZXcgUFJGIHRvIGJlIGlzc3VlZAoyIEF1ZyBQUkYgcmVjZWl2ZWQsIE1haWwgZnJvbSBCdXNpc2l3ZSByZSBDb25zb2xpZGF0ZWQgQkM/","RATING":""} |  |  |  | PHASE12 | 2023-07-20 | 2023-09-18 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000589 | Absa Walmer Park - Generator | Absa Walmer Park - Generator |  |  | Region 2 | Eastern Cape | 77686X | 1000-71032-01 | Walmer Park Shopping Centre-Main Rd-Port Elizabeth | N | 2023-09-01 | 2023-12-29 |  | ALP-EC0019 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-02 | D | 0 |  | 1 |  |  | 0 | See Prj ASP-EC0282 | {"MANDT":"111","REFERENCE":90000589,"ONEVIEW":"77686X","DATE01":"2023-06-23","DATE02":"2023-06-30","DATE03":"2023-07-21","DATE04":"2023-07-28","DATE05":"2023-08-18","DATE06":"2023-09-01","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-01","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgQXVnIFNpdGUgdmlzaXQgY29uZHVjdGVkIHdpdGggdmVuZG9ycyByZSBFbmdpbmVlcmluZyBwcm9wb3NhbCB0byBkbyBvbiBzaXRlCjcgQXVnIFNpdGUgdmlzaXQgdG8gYmUgY29uZHVjdGVkIHdpdGggVmVuZG9ycyB0byByZXBsYWNlIGNhbm9weSBvbiBzaXRlCjMgQXVnIC0gT3B0aW9uIHRvIGJlIHByZXNlbnRlZCB0byBBYnNhIGZvciBmdWxsIHJlcGxhY2VtZW50CjI1IEp1bHkgQkMgcmVxdWlyZWQgZm9yIHRoZSByZXBsYWNlbWVudAoyMCBKdWx5IC0gUE0gdG8gc3VibWl0dGVkIGZvciBDQgoxMyBKdWx5IC0gQkMgUGFjayBwZW5kaW5nIGZvciBmaW5hbCBhc3Nlc3NtZW50IGFuZCBhcHByb3ZhbAoK","RATING":""} |  |  |  | PHASE12 | 2023-03-30 | 2023-07-27 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000590 | Absa Montana Poster Frames | Absa Montana Poster Frames |  |  | Region 1 | Gauteng North | 78655X | 1000-71412-01 | Fin Forum-Cnr Dr. van der Merwe Rd & Sefako Makgatho Dr-Magalieskruin | N | 2023-08-03 | 2023-08-03 |  | ASP-GN0223 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | L |  | GAMIETR | 2023-08-03 | D | 109536.01 |  | 100 | 2023-09-07 | 2023-09-13 | 109536.01 |  | {"MANDT":"111","REFERENCE":90000590,"ONEVIEW":"78655X","DATE01":"2023-05-25","DATE02":"2023-06-01","DATE03":"2023-06-22","DATE04":"2023-06-29","DATE05":"2023-07-20","DATE06":"2023-10-31","DATE07":"2023-11-04","DATE08":"2023-11-25","DATE09":"2024-01-09","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"159:7:21:7:21:103:4:21:45:23","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-11-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIEF3YWl0aW5nIFBPcw==","RATING":""} |  |  | C000110196 | PHASE11 | 2023-10-31 | 2023-11-04 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-09-13 | 95248.7 | 0 |  |  | C000110196 | 95248.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000591 | Auckland Park CC Greywater Meter | Auckland Park CC Greywater Meter |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-08-03 | 2023-09-04 |  | ASP-GS0730 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-08-03 | D | 36758.57 |  | 100 | 2023-08-08 | 2023-08-10 | 36758.57 |  | {"MANDT":"111","REFERENCE":90000591,"ONEVIEW":"76849X","DATE01":"2023-05-25","DATE02":"2023-06-01","DATE03":"2023-07-03","DATE04":"2023-07-11","DATE05":"2023-07-11","DATE06":"2023-07-25","DATE07":"2023-07-26","DATE08":"2023-08-16","DATE09":"2023-09-30","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"189:7:32:8:0:14:1:21:45:21","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-25","FORECAST_END":"2023-07-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000102807 | PHASE09 | 2023-09-22 | 2023-09-23 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-08 | 29071.79 | 0 |  |  | C000102807 | 29071.79 |  | 3326.01 |  | 0 | 0 |  | 0 |  | 0
90000592 | Absa Hoedspruit - Replacement of APC UPS | Absa Hoedspruit - Replacement of APC UPS |  |  | Region 3 |  | 76718X | 1000-70519-01 | Spar Centre Hoedspruit-Koedoe St-Hoedspruit | Y | 2023-09-27 |  |  | ASP-LP0170 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-08-03 | D | 0 |  | 100 | 2023-08-11 | 2023-08-11 | 175710.09 |  | {"MANDT":"111","REFERENCE":90000592,"ONEVIEW":"76718X","DATE01":"2023-07-19","DATE02":"2023-08-14","DATE03":"2023-08-16","DATE04":"2023-08-23","DATE05":"2023-08-17","DATE06":"2023-09-27","DATE07":"2023-10-27","DATE08":"2023-11-17","DATE09":"2024-01-01","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-27","FORECAST_END":"2023-10-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000103354 | PHASE11 | 2023-08-21 | 2023-08-25 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-11 | 152791.38 | 0 |  |  | C000103354 | 152791.38 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000593 | EOL: Various- Region 3- UPS batteries | EOL: Various- Region 3- UPS batteries |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-08-31 | 2023-12-15 |  | ASP-N00072 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-08-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-31 | 2023-12-15 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000594 | Absa Alice Lane Podium CPF Fish Bowl | Absa Alice Lane Podium CPF Fish Bowl |  |  | Region 1 |  | 21843X | 1000-70039-01 | 15 Alice Lane Podium-Alice Ln-Sandton |  | 2023-08-04 | 2023-10-04 |  | ALP-GS0064 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-08-04 | D | 1156314.56 |  | 70 |  |  | 0 | WA submitted for approval. | {"MANDT":"111","REFERENCE":90000594,"ONEVIEW":"21843X","DATE01":"2023-05-26","DATE02":"2023-06-02","DATE03":"2023-06-23","DATE04":"2023-06-30","DATE05":"2023-07-21","DATE06":"2023-08-04","DATE07":"2023-09-27","DATE08":"2023-10-18","DATE09":"2023-12-02","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":85,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"219:7:21:7:21:14:54:21:45:22","PROGRESS":56,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-04","FORECAST_END":"2023-09-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"aW4gY29uc3RydWN0aW9uIHBoYXNl","RATING":""} |  |  |  | PHASE08 | 2023-08-04 | 2023-11-13 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 1005490.92 | 0 |  |  | C000114558 | 8807956.31 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000595 | Various- Replacement of UPS batteries 2 | Various- Replacement of UPS batteries |  |  | Region 1 | Gauteng | 78297X | 1000-71405-01 | Jabulani Mall-Bolani Rd-Soweto | Y | 2023-08-17 | 2023-12-15 |  | ALP-N00051 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | LOUISR | 2023-08-04 | D | 0 | 2023.07.06: Approved OOC by Conrad M | 100 | 2023-07-06 | 2023-07-06 | 750000 | Approved | {"MANDT":"111","REFERENCE":90000595,"ONEVIEW":"78297X","DATE01":"2023-06-08","DATE02":"2023-06-15","DATE03":"2023-07-06","DATE04":"2023-07-13","DATE05":"2023-08-03","DATE06":"2023-10-09","DATE07":"2023-10-12","DATE08":"2023-10-20","DATE09":"2023-10-20","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:7:21:7:21:67:3:8:0:27","PROGRESS":86,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-09","FORECAST_END":"2023-10-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjM6MTA6MjAyMyBBUzogSW52b2ljZSBoYXMgYmVlbiBzdWJtaXR0ZWQgdG8gRmluYW5jZSBvbiB0aGUgMjAvMTAvMjMuCg==","RATING":"Low"} |  |  | C000105230 | PHASE11 | 2023-10-09 | 2023-10-12 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-08-21 | 652173.91 | 0 |  |  | C000105230 | 652173.91 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000596 | Absa Pretoria Campus 2 X TV Screens | Absa Pretoria Campus 2 X TV Screens |  |  | Region 1 | Gauteng North | 22491x | 1000-70194-01 | Pretoria Campus | N | 2023-08-07 | 2023-08-31 |  | ASP-GN0224 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-08-07 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Winston P | 100 | 2023-08-03 | 2023-08-03 | 37467 | Approved | {"MANDT":"111","REFERENCE":90000596,"ONEVIEW":"22491x","DATE01":"2023-05-29","DATE02":"2023-06-05","DATE03":"2023-06-26","DATE04":"2023-07-03","DATE05":"2023-07-24","DATE06":"2023-08-07","DATE07":"2023-09-15","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"2023-12-15","DATE12":"2023-12-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"185:7:21:7:21:14:39:46:45:10","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-07","FORECAST_END":"2023-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMSAtIFByb2plY3QgY29tcGxldGUgJiBGaW5hbCBQT0MgaW4gcHJvZ3Jlc3Mu","RATING":""} |  |  | C000102805 | PHASE08 | 2023-08-07 | 2023-09-15 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-08-08 | 255094.12 | 0 |  |  | C000102805 | 32580 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000597 | Auckland Park CC Signage | Auckland Park CC Signage |  |  | Region 1 | Gauteng South | 76849X | 1000-70196-01 | Auckland Park Call Centre | N | 2023-08-07 | 2023-09-07 |  | ASP-GS0731 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-08-07 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000597,"ONEVIEW":"76849X","DATE01":"2023-05-29","DATE02":"2023-06-05","DATE03":"2023-06-26","DATE04":"2023-07-03","DATE05":"2023-07-24","DATE06":"2023-11-24","DATE07":"2023-12-25","DATE08":"2024-01-15","DATE09":"2024-02-29","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"185:7:21:7:21:123:31:21:45:18","PROGRESS":11,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-24","FORECAST_END":"2023-12-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"YXBwcm92ZWQgT09DICwgQXdhaXRpbmcgQkZNIFBP","RATING":"Low"} |  |  | C000121662 | PHASE08 | 2023-11-24 | 2023-12-25 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-07 | 114255.4 | 0 |  |  | C000121662 | 114255.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000598 | Absa Wingrin Centre - DILAPS | Absa Wingrin Centre - DILAPS |  |  | Region 3 |  | 76714X | 1000-70517-01 | Wingrin Centre-Railway St-Marble Hall |  | 2023-10-27 | 2023-10-31 |  | ASP-LP0171 | REL BUDG RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-07 | D | 0 | Branch Dilapidations | 100 |  |  | 117940.75 |  | {"MANDT":"111","REFERENCE":90000598,"ONEVIEW":"76714X","DATE01":"2023-08-18","DATE02":"2023-08-01","DATE03":"2023-08-07","DATE04":"2023-09-22","DATE05":"2023-08-08","DATE06":"2023-08-11","DATE07":"2023-08-16","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-11","FORECAST_END":"2023-08-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmVxdWVzdGVkIGludm9pY2VzIGZyb20gc3VwcGxpZXJz","RATING":""} |  |  | C000104091 | PHASE11 | 2023-08-11 | 2023-08-16 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-15 | 102557.17 | 0 |  |  | C000104091 | 102557.17 |  | 9821.89 |  | 0 | 0 |  | 0 |  | 0
90000599 | Absa Tzaneen Hotel - Replace PC board + | Absa Tzaneen Hotel - Replace PC board + |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-09-08 |  |  | ASP-LP0172 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-08 | 2023-10-08 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000600 | Absa Jane Furse Plaza - Replace PCB + Su | Absa Jane Furse Plaza - Replace PCB + Su |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-09-27 |  |  | ASP-LP0173 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-27 | 2023-10-27 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000601 | Absa Eden Square - Replace PCB +Surge Pr | Absa Eden Square - Replace PCB +Surge Pr |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-09-27 |  |  | ASP-LP0174 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-27 | 2023-10-27 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000602 | Absa Kamaqhekeza - Replace PC Board | Absa Kamaqhekeza - Replace PC Board |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-09-08 |  |  | ASP-MP0166 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-08 | 2023-10-08 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000603 | Absa Block 3 Parking Waterproofing reinf | Absa Block 3 Parking Waterproofing reinf |  |  | Region 1 | Gauteng | 77462X | 1000-71398-01 | Absa Kings Parking-Fox St-Johannesburg | Y | 2023-04-05 |  |  | ALP-GS0065 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-08-07 | D | 1068864.86 | Approved at CB/BTB | 40 | 2023-06-29 | 2023-06-29 | 1068864.86 | Awaiting Absa PO supplier in on-boarding process. | {"MANDT":"111","REFERENCE":90000603,"ONEVIEW":"Unknown","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":80,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhcHByb3ZlZCBhdCBCVEIgIGFsbCBjb250cmFjdHVhbCBkb2N1bWVudHMgYXBwcm92ZWQsIEJGTSBidXN5IHdpdGggU3VwcGxpZXIgb24tYm9hcmRpbmcgZm9yIHRoZSBQTydzIHRvIGJlIGlzc3VlZC4KUHJvamVjdCBjb21tZW5jZW1lbnQtIDIwLzEwLzIwMjMKUHJvamVjdCBDb21wbGV0aW9uLSAzMS8xMS8yMDIzIAoK","RATING":"Low"} |  |  | Awaiting PO | PHASE11 | 2023-04-05 | 2023-05-05 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-08-14 | 2023-08-24 |  |  |  | 0 | 0 |  |  | C000144514 | 929447.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000604 | Absa Volksrust - Minor Works | Absa Volksrust - Minor Works |  |  | Region 3 | Mpumalanga | 77566X | 1000-70636-01 | Absa Volksrust-Joubert St-Volksrust | U | 2023-10-27 |  |  | ALP-MP0205 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-08-07 | D | 0 | Approved at CB/BTB | 100 | 2023-06-29 | 2023-06-29 | 569351.03 | Approved | {"MANDT":"111","REFERENCE":90000604,"ONEVIEW":"77566X","DATE01":"2023-08-18","DATE02":"2023-08-25","DATE03":"2023-09-15","DATE04":"2023-09-22","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2023-11-26","DATE08":"2023-12-17","DATE09":"2024-01-31","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":30,"PROG10":30,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2023-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QmFsYW5jZSBvZiBzbmFncyBpbiBwcm9ncmVzcyAtIFByb2plY3QgY29tcGxldGVkIC0gMjkgU2VwLSBQcm9qZWN0IEFwcHJvdmVkIGF0IEJUQiwgQWJzYSBQTyBQZW5kaW5nIGR1ZSB0byBXQStTRkEgbm90IHlldCBhcHByb3ZlZC4=","RATING":""} |  |  | C000119033 | PHASE08 | 2023-10-27 | 2023-11-26 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-10-25 | 495087.85 | 403587.29 |  |  | C000142530 | 91500.56 |  | 45346.24 |  | 0 | 0 |  | 0 |  | 0
90000605 | Absa Piet Retief - External Works | Absa Piet Retief - External Works |  |  | Region 3 | Mpumalanga | 77121X | 1000-70610-01 | Absa Piet Retief-Church St-Piet Retief | U | 2023-10-27 |  |  | ALP-MP0206 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | F |  | NOMNGANGAL | 2023-08-07 | D | 693940.14 | 2023.07.20: Approved by Conrad M 2023.07.19: Supported by Judith B & Ilana vdW | 100 | 2023-07-20 | 2023-07-20 | 693940.14 | Approved | {"MANDT":"111","REFERENCE":90000605,"ONEVIEW":"77121X","DATE01":"2023-08-18","DATE02":"2023-08-25","DATE03":"2023-09-15","DATE04":"2023-09-22","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2023-11-17","DATE08":"2023-12-08","DATE09":"2024-01-22","DATE10":"2024-01-31","DATE11":"2024-01-22","DATE12":"2024-01-22","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"166:7:21:7:21:14:21:21:45:0","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2023-11-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBzY2hlZHVsZWQgdG8gc3RhcnQgMTcgTm92ZW1iZXIgLSBPSFMgUmV2aWV3IGluIHByb2dyZXNz","RATING":"Medium"} |  |  | C000117756 | PHASE11 | 2023-10-27 | 2023-11-17 | NANDE MAQUBELA | Thea Spamers | 0 | 2023-10-06 | 2023-10-20 | 2023-10-20 |  | 2023-10-18 | 603426.21 | 0 |  |  | C000117756 | 603426.21 |  | 31471.21 |  | 0 | 0 |  | 0 |  | 0
90000606 | Various-Installation of Surge Protection | Various-Installation of Surge Protection |  |  | Region 1 |  |  |  | Building not in Real Estate Database |  | 2023-08-31 |  |  | ALP-N00052 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | LOUISR | 2023-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-31 | 2023-09-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000607 | Various-Installation of Surge Protection | Various-Installation of Surge Protection |  |  | Region 1 |  |  |  | Building not in Real Estate Database |  | 2023-08-31 |  |  | ALP-N00053 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | LOUISR | 2023-08-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-31 | 2023-09-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000608 | AL parking-Guidance System Upgrade (SATT | 1.The Supplier to remove old sensors and controllers; 2.Supply and install x No.1425 sensors; 3.Supply and install x No. 27 controllers; 4.Test and commission the system. |  |  | Region 1 | Gauteng South | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2023-08-31 |  |  | ALP-N00054 | REL BUDG AVAC RESA: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L | 2030-04-29 | LOUISR | 2023-08-07 | D | 3334665.55 |  | 100 | 2023-09-18 | 2023-10-13 | 3334665.55 | 27.10 NN: Awaiting Absa PO 03.11 NN: Absa PO Obtained 02.11 09.11 NN: BFM PO Obtained 08.11 | {"MANDT":"111","REFERENCE":90000608,"ONEVIEW":"70656X","DATE01":"2023-09-01","DATE02":"2023-09-06","DATE03":"2023-09-20","DATE04":"2023-09-25","DATE05":"2023-10-27","DATE06":"2023-12-04","DATE07":"2024-03-08","DATE08":"2024-03-29","DATE09":"2024-05-13","DATE10":"2024-05-31","DATE11":"2024-05-13","DATE12":"2024-05-13","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"181:5:14:5:32:38:95:21:45:10","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-04","FORECAST_END":"2024-03-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDkuMTEgTk46IEJGTSBQTyBPYnRhaW5lZCAwOC4xMSBQTyBzZW50IHRvIHRoZSBzdXBwbGllciBLaWNrIG9mZiBtZWV0aW5nIHRvIHRha2UgcGxhY2Ugb24gMTMuMTE=","RATING":"Low"} |  |  | C000120814 | PHASE06 | 2023-12-04 | 2024-03-08 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | 2023-10-06 | 2023-10-20 | 2023-10-20 | 2023-10-23 | 2023-11-02 | 2899709.17 | 0 |  |  | C000120814 | 2899709.17 |  | 250947.98 |  | 0 | 0 |  | 0 |  | 0
90000609 | Absa Alice Lane South Wireless Charging | Absa Alice Lane South Wireless Charging |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-08-08 | 2023-09-08 |  | ASP-GS0732 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-08-08 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Rhulani N | 100 | 2023-08-03 | 2023-08-03 | 17789.55 | Approved | {"MANDT":"111","REFERENCE":90000609,"ONEVIEW":"77326X","DATE01":"2023-05-30","DATE02":"2023-06-06","DATE03":"2023-06-27","DATE04":"2023-07-04","DATE05":"2023-07-25","DATE06":"2023-09-01","DATE07":"2023-09-09","DATE08":"2023-09-30","DATE09":"2023-11-14","DATE10":"2023-11-30","DATE11":"2023-11-14","DATE12":"2023-11-14","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"184:7:21:7:21:38:8:21:45:17","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-01","FORECAST_END":"2023-09-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNl","RATING":""} |  |  | C000104096 | PHASE09 | 2023-09-01 | 2023-09-09 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-08-15 | 17324.18 | 0 |  |  | C000104096 | 15064.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000610 | Absa Alice Lane South Video Conferencing | Absa Alice Lane South Video Conferencing |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-08-08 | 2023-09-08 |  | ASP-GS0733 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-08-08 | D | 0 | 2023.08.02: Approved by Conrad M as per email 2023.08.01: Supported by Winston P & Rhulani N | 100 | 2023-08-03 | 2023-08-03 | 107659.89 | Approved | {"MANDT":"111","REFERENCE":90000610,"ONEVIEW":"77326X","DATE01":"2023-05-30","DATE02":"2023-06-06","DATE03":"2023-06-27","DATE04":"2023-07-04","DATE05":"2023-07-25","DATE06":"2023-09-27","DATE07":"2023-10-07","DATE08":"2023-10-28","DATE09":"2023-12-12","DATE10":"2023-12-31","DATE11":"2023-12-12","DATE12":"2023-12-12","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"184:7:21:7:21:64:10:21:45:17","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-27","FORECAST_END":"2023-10-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RmluYWwgUG9jIFN1Ym1pdHRlZCB0byBGaW5hbmNlLg==","RATING":""} |  |  | C000115060 | PHASE09 | 2023-09-27 | 2023-10-07 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-10-06 | 119900 | 0 |  |  | C000104089 | 119900 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000611 | Absa Alice Lane South Wooden Deck | Absa Alice Lane South Wooden Deck |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-08-08 | 2023-10-09 |  | ALP-GS0066 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-08-08 | D | 889836.87 | Approved at BTB 06/07/2023 | 70 | 2023-07-06 | 2023-07-06 | 889836.87 |  | {"MANDT":"111","REFERENCE":90000611,"ONEVIEW":"77381X","DATE01":"2023-05-30","DATE02":"2023-06-06","DATE03":"2023-06-27","DATE04":"2023-07-04","DATE05":"2023-07-25","DATE06":"2023-10-10","DATE07":"2023-12-11","DATE08":"2024-01-01","DATE09":"2024-02-15","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":30,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"215:7:21:7:21:77:62:21:45:17","PROGRESS":17,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-10","FORECAST_END":"2023-12-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBhcHByb3ZhbCBmcm9tIEdyb3VwIE9ocyBhbmQgTGVnYWwgZG9jdW1lbnRzLg==","RATING":""} |  |  |  | PHASE08 | 2023-10-10 | 2023-12-11 | CHRISTOPHER MPOFU | Michael Maluleka | 23000043 | [5 empty] | 0 | 0 |  |  | NO FUNDS | 773771.19 | CIP2023XP | 0 |  | 0 | 0 |  | 0 |  | 0
90000612 | Absa Vincent Branch - HVAC Repairs Opex | Absa Vincent Branch - HVAC Repairs Opex |  |  | Region 2 | Eastern Cape | 78697X | 1000-71051-01 | Vincent Park-Devereux Ave-East London | N | 2023-09-01 | 2023-12-29 |  | ASP-EC0339 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-14 | D | 0 |  | 1 |  |  | 0 | 21 Sept - Cancelled as to be done via GMP repairs to existing System 11 Sept - PM to clarify with Broll Engineering in terms of specifications and Scope | {"MANDT":"111","REFERENCE":90000612,"ONEVIEW":"78697X","DATE01":"2023-08-08","DATE02":"2023-09-22","DATE03":"2023-10-13","DATE04":"2023-10-20","DATE05":"2023-11-10","DATE06":"2023-11-24","DATE07":"2023-12-07","DATE08":"2023-12-28","DATE09":"2024-02-11","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"176:45:21:7:21:14:13:21:45:24","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"X","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-24","FORECAST_END":"2023-12-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgU2VwdCAtIFBNIHRvIGNsYXJpZnkgd2l0aCBCcm9sbCBFbmdpbmVlcmluZyBpbiB0ZXJtcyBvZiBzcGVjaWZpY2F0aW9ucyBhbmQgU2NvcGUKNyBTZXB0IC0gUG0gdG8gZm9sbG93IHVwIHdpdGggVFNNIHJlIHByb2dyZXNzCg==","RATING":"Low"} |  |  |  | PHASE12 | 2023-09-21 | 2023-09-21 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000613 | Vincent Office Park - Interleading Door - Ablutions + Tiles Under Fridges (X3) | Vincent Office Park - Interleading Door - Ablutions + Tiles Under Fridges (X3) |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Vincent Office Park-Western Ave-East London | N | 2023-09-01 | 2023-12-29 |  | ASP-EC0340 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-14 | D | 23807.99 |  | 100 | 2023-11-02 | 2023-11-02 | 23807.99 | Absa Ref : 240129_089 | {"MANDT":"111","REFERENCE":90000613,"ONEVIEW":"79369X","DATE01":"2023-08-07","DATE02":"2023-10-12","DATE03":"2023-11-02","DATE04":"2023-11-09","DATE05":"2023-11-02","DATE06":"2023-11-07","DATE07":"2023-11-10","DATE08":"2023-12-14","DATE09":"2024-01-28","DATE10":"2024-01-31","DATE11":"2024-01-15","DATE12":"2024-01-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:66:21:7:-7:5:3:34:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-07","FORECAST_END":"2023-11-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgRGVjIC0gUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNlCjExIERlYyBTaWduYWdlIEluc3RhbGxlZCBQT0MgdG8gYmUgc2lnbmVkCjQgRGVjIFBNIHRvIGZvbGxvdyB1cCByZSBTaWducyB0byBiZSBpbnN0YWxsZWQgLSBQbGFubmVkIGZvciBjb21wbGV0aW9uIGJ5IDggRGVjCjI3IE5vdiAtIFNpZ25hZ2UgdG8gYmUgaW5zdGFsbGVkIGJ5IFdlZG5lc2RheSAyOSBOb3YKMTcgTm92IFBPQyBub3Qgc2lnbmVkIC0gU2lnbmFnZSB0byBiZSBjb25maXJtZWQgYXMgaW5zdGFsbGVkCjEwIE5vdiBXb3JrcyBDb21wbGV0ZWQKOSBOb3YgQWJzYSBQTyByZWNlaXZlZCBDMDAwMTIyMDY0IEJWIFBPIHJlcXVlc3RlZAo3IE5vdiBTaWduZWQgRk0gRGVjayBSZWNlaXZlZCBBYnNhIFBPIFJlcXVlc3RlZAoyIE5vdiBBcHByb3ZlZCBpbiBDQiAsIFNpZ25lZCBkZWNrcyB0byBmb2xsb3cgdG8gcmFpc2UgQWJzYSBQTydzCjIgTm92IFNlbnQgZm9yIFZQIFN1cHBvcnQgdG8gYWRkIHRvIENCIGRlY2sgLSBXYXMgU3VwcG9ydGVkCjI3IE9jdCBCQyB0byBiZSBzdWJtaXR0ZWQgYnkgMiBOb3YKMTYgT2N0IFF1b3RlcyByZXF1ZXN0ZWQgUE0gdG8gZm9sbG93IHVwCjExIE9jdCBEcmF3aW5nIHJlY2VpdmVkIHF1b3RlcyB0byBiZSBvYnRhaW5lZAoyMiBTZXB0IERyYXdpbmdzIHRvIGJlIGNvbXBsZXRlZCB0byBkZXRlcm1pbmUgU2NvcGUgLSBJZiBwcm9jZWVkcyB3aWxsIGJlIFJvbGxvdmVyIC0gRmluYW5jaWFsL1Byb2plY3QgYXMgRW5naW5lZXJpbmcgc2NvcGUgdG8gYmUgY29uZmlybWVkCjExIFNlcHQgLSBQTSB0byBlbWFpbCBlbmdpbmVlcmluZyByZSBleHRyYWN0aW9uIAo4IFNlcHQgU2l0ZSBWaXNpdCBDb25kdWN0ZWQgdG8gZGV0ZXJtaW5lIFNjb3BlIC0gQ29zdGluZyBpbiBQcm9ncmVzcwoxNCBBdWcgLSBQbGFucyB0byBiZSByZXF1ZXN0ZWQgZnJvbSAtIERpa2VhbW8gQXJjaGl0ZWN0cwo3IEF1ZyBQUkYgcmVjZWl2ZWQK","RATING":""} |  |  | C000122064 | PHASE11 | 2023-11-07 | 2023-11-10 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-08 | 20702.6 | 0 |  |  | C000122064 | 20702.6 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000614 | Absa Highlands Carport Bulk Diesel Tank | Absa Highlands Carport Cover Bulk Diesel Tank Genset |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2023-08-14 | 2023-08-14 |  | ASP-GS0734 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-08-14 | D | 96605.75 |  | 1 | 2023-09-14 |  | 0 | To be submitted to CB 14/09/2023 Project cancelled. | {"MANDT":"111","REFERENCE":90000614,"ONEVIEW":"37006X","DATE01":"2023-06-05","DATE02":"2023-06-12","DATE03":"2023-07-03","DATE04":"2023-07-10","DATE05":"2023-07-31","DATE06":"2023-08-14","DATE07":"2023-08-14","DATE08":"2023-09-04","DATE09":"2023-10-19","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":1,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-14","FORECAST_END":"2023-08-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjYW5jZWxsZWQu","RATING":""} |  |  |  | PHASE12 | 2023-08-14 | 2023-08-14 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000100099 | 60430 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000615 | Please assist with bulk PN for the suppl | Please assist with bulk PN for the suppl |  |  | Region 3 |  | 77571X | 1000-70637-01 | Kamaqhekeza Plaza-Main Rd-Balfour |  | 2023-09-01 | 2023-12-29 |  | ASP-N00073 | CRTD AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | CEASARS | 2023-08-15 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000615,"ONEVIEW":"77571X","DATE01":"2023-06-23","DATE02":"2023-08-17","DATE03":"2023-07-21","DATE04":"2023-07-28","DATE05":"2023-08-18","DATE06":"2023-09-01","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-01","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-09-01 | 2023-12-29 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000616 | Absa Wibsa Upington -Replace LED Lights | Absa Wibsa Upington -Replace LED Lights |  |  | Region 3 |  | 36271X | 1000-71336-01 | Wibsa Upington-Schroder St-Upington |  | 2023-11-29 |  |  | ALP-CR0040 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-15 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000616,"ONEVIEW":"36271X","DATE01":"2023-09-20","DATE02":"2023-09-27","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJlcGFyYXRpb24gb2YgQlRCIHBhcGVy","RATING":""} |  |  |  | PHASE05 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000617 | Absa Demountable Bank Unit -Repairs to d | Absa Demountable Bank Unit -Repairs to d |  |  | Region 3 |  | 78556X | 1000-71311-01 | Land For Absa Demountable Bank Unit-Cnr Motsatsi & Makheni St-Thlabane |  | 2023-08-30 | 2023-10-26 |  | ASP-CR0481 | CLSD BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-16 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 124917.6 |  | {"MANDT":"111","REFERENCE":90000617,"ONEVIEW":"78556X","DATE01":"2023-06-21","DATE02":"2023-06-28","DATE03":"2023-07-19","DATE04":"2023-07-26","DATE05":"2023-08-16","DATE06":"2023-08-30","DATE07":"2023-10-26","DATE08":"2023-11-16","DATE09":"2023-12-31","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-30","FORECAST_END":"2023-10-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2luZw==","RATING":""} |  |  | C000105231 | PHASE11 | 2023-08-30 | 2023-10-26 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-21 | 108624 | 0 |  |  | C000105231 | 108624 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000618 | Absa Lichtenburg - Repairs to collapsed | Absa Lichtenburg - Repairs to collapsed |  |  | Region 3 |  | 77806X | 1000-71605-01 | Absa Lichtenburg-Nelson Mandela Dr-Lichtenburg |  | 2023-08-25 |  |  | ASP-CR0482 | CLSD ISBD AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-16 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 272875.7 |  | {"MANDT":"111","REFERENCE":90000618,"ONEVIEW":"77806X","DATE01":"2023-06-16","DATE02":"2023-06-23","DATE03":"2023-07-14","DATE04":"2023-07-21","DATE05":"2023-08-11","DATE06":"2023-08-25","DATE07":"2023-09-24","DATE08":"2023-10-15","DATE09":"2023-11-29","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-25","FORECAST_END":"2023-09-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2luZw==","RATING":""} |  |  | C000105232 | PHASE11 | 2023-08-25 | 2023-09-24 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-21 | 237283.22 | 0 |  |  | C000105232 | 237283.22 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000619 | Absa Butterworth - Insurance Claim - Pipes (Retrospective) | Absa Butterworth - Insurance Claim - Pipes (Retrospective) |  |  | Region 2 | Eastern Cape | 78501X | 1000-71048-01 | High Road Butterworth-Cnr High Rd & Bell St-Butterworth | N | 2023-02-01 | 2023-12-29 |  | ASP-EC0341 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-08-16 | D | 4368.91 |  | 100 | 2023-07-27 | 2023-07-27 | 4368.91 | Insurance Claim | {"MANDT":"111","REFERENCE":90000619,"ONEVIEW":"78501X","DATE01":"2023-07-27","DATE02":"2023-07-27","DATE03":"2023-07-27","DATE04":"2023-07-27","DATE05":"2023-07-27","DATE06":"2023-08-18","DATE07":"2023-08-18","DATE08":"2023-09-22","DATE09":"2023-11-06","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"96:0:0:0:0:22:0:35:45:16","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-18","FORECAST_END":"2023-08-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggQXVnIEFic2EgUE8gUmVjZWl2ZWQgLSBDMDAwMTA0NzU0CjE2IEF1ZyBTdWJtaXR0ZWQgdG8gQWJzYSBmb3IgUE8KQ2FwZXggSW5zdXJhbmNlIFJlcXVlc3RzIGFwcHJvdmVkIGF0IENCMjggb24gMjcuMDcuMjAyMw==","RATING":""} |  |  | C000104754 | PHASE11 | 2023-08-18 | 2023-08-18 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-08-18 | 3799.05 | 0 |  |  | C000104754 | 3799.05 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000620 | Absa Vincent Office Park - Tiles Under Fridges (X3) | Absa Vincent Office Park - Tiles Under Fridges (X3) |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Vincent Office Park-Western Ave-East London | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0342 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-16 | D | 0 |  | 1 |  |  | 0 | 2 Nov - Cancelled as included in ASP-EC0340 | {"MANDT":"111","REFERENCE":90000620,"ONEVIEW":"79369X","DATE01":"2023-08-16","DATE02":"2023-09-08","DATE03":"2023-11-02","DATE04":"2023-11-09","DATE05":"2023-11-02","DATE06":"2023-11-28","DATE07":"2023-11-28","DATE08":"2023-12-19","DATE09":"2024-02-02","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"168:23:55:7:-7:26:0:21:45:10","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-28","FORECAST_END":"2023-11-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjcgT2N0IEJDIHRvIGJlIHN1Ym1pdHRlZCBieSAyIE5vdgoxNiBPY3QgUXVvdGVzIHJlcXVlc3RlZCBQTSB0byBmb2xsb3cgdXAgdG8gY29tYmluZSB3aXRoIGRvb3IKMTEgT2N0IFF1b3RlcyByZWNlaXZlZCBCQyBwZW5kaW5nCjIyIFNlcHQgLSBRdW90ZXMgUmVxdWVzdGVkIC0gUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yIHJlIFF1b3RlLiBJZiBhcHByb3ZlZCAtUG9zc2libGUgRmluYW5jaWFsIFJvbGxvdmVyCjExIFNlcHQgLSBUaWxlcyBvbnNpdGUgdG8gYmUgdXNlZAo4IFNlcHQgU2l0ZSBWaXNpdCBDb25kdWN0ZWQgdG8gZGV0ZXJtaW5lIFNjb3BlIC0gQ29zdGluZyBpbiBQcm9ncmVzcwoxNiBBdWcgUFJGIFJlY2VpdmVk","RATING":"Low"} |  |  |  | PHASE12 | 2023-11-28 | 2023-11-28 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000621 | Absa Virginia - HVAC Replacement | Absa Virginia - HVAC Replacement |  |  | Region 3 | [5 empty] | 2023-10-30 |  |  | ASP-CR0483 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-17 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-10-30 | 2023-11-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000622 | Absa Theunissen -Aircon Replacement | Absa Theunissen -Aircon Replacement |  |  | Region 3 | [5 empty] | 2023-10-05 |  |  | ASP-CR0484 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-17 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-10-05 | 2023-11-04 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000623 | Pretoria Campus Canteen Graphic Vinyl | Pretoria Campus Canteen Graphic Vinyl |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-08-17 | 2023-09-18 |  | ASP-GN0225 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-08-17 | D | 187386.75 | Approved | 100 | 2023-10-07 | 2023-10-07 | 187386.75 |  | {"MANDT":"111","REFERENCE":90000623,"ONEVIEW":"22491X","DATE01":"2023-06-08","DATE02":"2023-06-15","DATE03":"2023-07-06","DATE04":"2023-07-13","DATE05":"2023-08-03","DATE06":"2023-09-30","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"175:7:21:7:21:58:31:21:45:7","PROGRESS":40,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-30","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBpbiBwcm9ncmVzcy4gUEMgcGxhbm5lZCBmb3IgNiBPY3Qu","RATING":""} |  |  | C000105056 | PHASE11 | 2023-09-30 | 2023-10-06 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-08-21 | 162945 | 0 |  |  | C000105056 | 162945 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000624 | ALS Legal & Compliance Fish Bowel | ALS Legal & Compliance Fish Bowel |  |  | Region 1 |  | 21843X | 1000-70039-01 | 15 Alice Lane Podium-Alice Ln-Sandton | N | 2023-08-17 | 2023-08-17 |  | ALP-GS0067 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L |  | GAMIETR | 2023-08-17 | D | 1156314.56 |  | 70 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000624,"ONEVIEW":"21526X","DATE01":"2023-06-08","DATE02":"2023-06-15","DATE03":"2023-07-06","DATE04":"2023-07-13","DATE05":"2023-12-27","DATE06":"2024-01-10","DATE07":"2024-02-29","DATE08":"2024-03-21","DATE09":"2024-05-05","DATE10":"2024-05-31","DATE11":"2023-12-11","DATE12":"2023-12-11","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":85,"PROG05":80,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:7:21:7:167:14:50:21:45:20","PROGRESS":79,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-01-10","FORECAST_END":"2024-02-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyByZWxlYXNlIG9mIEFic2EgUG8gaW4gb3JkZXIgdG8gY2xvc2Ugb3V0IHBheW1lbnRz","RATING":""} |  |  |  | PHASE08 | 2024-01-10 | 2024-02-29 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000143838 | 1005490.92 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000625 | Absa Vincent Park - Insurance Claim - Decals (Retrospective) | Absa Vincent Park - Insurance Claim - Decals + Glass (Retrospective) |  |  | Region 2 | Eastern Cape | 78697X | 1000-71051-01 | Vincent Park-Devereux Ave-East London | N | 2023-07-19 | 2023-07-19 |  | ASP-EC0343 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-08-18 | D | 10495.99 |  | 100 | 2023-07-27 | 2023-07-27 | 10495.99 | Insurance Claim - Decals + Glass (Retrospective) | {"MANDT":"111","REFERENCE":90000625,"ONEVIEW":"78697X","DATE01":"2023-07-27","DATE02":"2023-07-27","DATE03":"2023-07-27","DATE04":"2023-08-03","DATE05":"2023-07-27","DATE06":"2023-08-21","DATE07":"2023-08-21","DATE08":"2023-09-14","DATE09":"2023-10-29","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"96:0:0:7:-7:25:0:24:45:30","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-21","FORECAST_END":"2023-08-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgU2VwdCBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2U=","RATING":"Low"} |  |  | C000105229 | PHASE11 | 2023-08-21 | 2023-08-21 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-08-21 | 9126.95 | 0 |  |  | C000105229 | 9126.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000626 | Bizana - Insurance Claim - Replace vandalised Glass(Retrospective) | Bizana - Insurance Claim - Replace vandalised Glass(Retrospective) |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2023-06-13 | 2023-06-13 |  | ASP-EC0344 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-08-18 | D | 9615.15 |  | 100 | 2023-07-27 | 2023-07-27 | 9615.15 | 15 Sept POC Submitted to Finance 14 Sept Absa PO Received C000110557 POC to Follow Capex Insurance Requests approved at CB28 on 27.07.2023 | {"MANDT":"111","REFERENCE":90000626,"ONEVIEW":"78697X","DATE01":"2023-04-04","DATE02":"2023-04-11","DATE03":"2023-05-02","DATE04":"2023-05-09","DATE05":"2023-05-30","DATE06":"2023-06-13","DATE07":"2023-06-13","DATE08":"2023-07-04","DATE09":"2023-08-18","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-06-13","FORECAST_END":"2023-06-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgQXVnIC0gUE8gaXNzdWVkL2NvbWJpbmVkIHdpdGggRUMwMzQzCjE4IEF1ZyBBYnNhIFBPIFJlcXVlc3RlZApDYXBleCBJbnN1cmFuY2UgUmVxdWVzdHMgYXBwcm92ZWQgYXQgQ0IyOCBvbiAyNy4wNy4yMDIz","RATING":"Low"} |  |  | C000110557 | PHASE11 | 2023-09-14 | 2023-09-14 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-14 | 8361 | 0 |  |  | C000110557 | 8361 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000627 | Absa Kirkwood - Insurance Claim - Storm/Flood Damage (Retrospective) | Absa Kirkwood - Insurance Claim - Storm/Flood Damage (Retrospective) |  |  | Region 2 | Eastern Cape | 76548X | 1000-71013-01 | Absa Kirkwood-Hoof St-Kirkwood | N | 2023-06-01 | 2023-06-30 |  | ASP-EC0345 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | F |  | CEASARS | 2023-08-18 | D | 482456.34 |  | 100 | 2023-07-27 | 2023-07-27 | 482456.34 | Capex Insurance Requests approved at CB28 on 27.07.2023 - Various | {"MANDT":"111","REFERENCE":90000627,"ONEVIEW":"76548X","DATE01":"2023-07-27","DATE02":"2023-07-27","DATE03":"2023-07-27","DATE04":"2023-08-03","DATE05":"2023-07-27","DATE06":"2023-09-14","DATE07":"2023-09-14","DATE08":"2023-10-05","DATE09":"2023-11-19","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"96:0:0:7:-7:49:0:21:45:30","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-14","FORECAST_END":"2023-09-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgU2VwdCBBYnNhIFBPIFJlY2VpdmVkICBDMDAwMTEwNjEzIFBPQyB0byBGb2xsb3c=","RATING":"Low"} |  |  | C000110613 | PHASE11 | 2023-09-14 | 2023-09-14 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-14 | 419527.25 | 0 |  |  | C000110613 | 419527.25 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000628 | Absa Kloof Village - Replacement of Ceil | Absa Kloof Village - Replacement of Ceil |  |  | Region 3 |  | Unknown | 1000-71214-01 | Unknown Building - not in our database |  | 2023-08-30 |  |  | ASP-KZ0260 | CLSD BUDG ISBD AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-18 | D | 0 | Approved |  | 2023-10-07 | 2023-10-07 | 4004.65 |  |  |  |  | C000105574 | PHASE11 | 2023-08-18 | 2023-08-18 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-22 | 3482.3 | 0 |  |  | C000105574 | 3482.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000629 | Absa Durban Phoenix Plaza - Replacement | Absa Durban Phoenix Plaza - Replacement |  |  | Region 3 |  | Unknown | 1000-71197-01 | Unknown Building - not in our database |  | 2023-08-30 |  |  | ASP-KZ0261 | CLSD BUDG AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-18 | D | 0 | Approved |  | 2023-10-07 | 2023-10-07 | 6982.57 |  |  |  |  | C000105573 | PHASE11 | 2023-08-30 | 2023-09-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-08-22 | 6071.8 | 0 |  |  | C000105573 | 6071.8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000630 | Absa Nelspruit Crossing - Replace damage | Absa Nelspruit Crossing - Replace damage |  |  | Region 3 |  | 36279X | 1000-70590-01 | Nelspruit Crossing Centre-Cnr Madiba & Samora Machel Dr-Nelspruit |  | 2023-08-30 |  |  | ASP-MP0167 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  | Project submitted as OCC | 2023 |  | L |  | NOMNGANGAL | 2023-08-18 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 39054.99 |  | {"MANDT":"111","REFERENCE":90000630,"ONEVIEW":"36279X","DATE01":"2023-06-21","DATE02":"2023-08-07","DATE03":"2023-07-19","DATE04":"2023-07-26","DATE05":"2023-08-16","DATE06":"2023-08-30","DATE07":"2023-09-08","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-30","FORECAST_END":"2023-09-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCAgc3VibWl0dGVkIGFzIE9PQw==","RATING":""} |  |  | C000105679 | PHASE11 | 2023-08-30 | 2023-09-08 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-08-23 | 33960.86 | 0 |  |  | C000105679 | 33960.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000631 | Absa Kabokweni Plaza - Door Glass Replac | Absa Kabokweni Plaza - Door Glass Replac |  |  | Region 3 |  | 78671X | 1000-70657-01 | Kabokweni Plaza-Cnr Kabokweni & Palaston Rd-White River |  | 2023-08-30 |  |  | ASP-MP0168 | CLSD BUDG ISBD AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-08-18 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 5187.08 |  | {"MANDT":"111","REFERENCE":90000631,"ONEVIEW":"78671X","DATE01":"2023-06-21","DATE02":"2023-06-28","DATE03":"2023-07-19","DATE04":"2023-07-26","DATE05":"2023-08-16","DATE06":"2023-08-30","DATE07":"2023-09-11","DATE08":"2023-09-14","DATE09":"2023-09-15","DATE10":"2023-09-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-30","FORECAST_END":"2023-09-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgLSBQT0Mgc3VibWl0dGVk","RATING":""} |  |  | C000105682 | PHASE11 | 2023-08-30 | 2023-09-11 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-08-23 | 4510.5 | 0 |  |  | C000105682 | 4510.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000632 | Absa Branches (LP/MP)- Supply od Day Die | Absa Branches (LP/MP)- Supply od Day Die |  |  | Region 3 |  | Unknown | 1000-70637-01 | Unknown Building - not in our database |  | 2023-10-12 | 2023-11-30 |  | ALP-N00055 | CRTD: |  | false | true |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-08-21 | D | 1127154.92 | BTB Paper submitted for funding |  | 2023-09-28 |  | 1127154.92 |  | {"MANDT":"111","REFERENCE":90000632,"ONEVIEW":"Unknown","DATE01":"2023-08-03","DATE02":"2023-07-31","DATE03":"2023-08-07","DATE04":"2023-08-07","DATE05":"2023-09-28","DATE06":"2023-09-29","DATE07":"2024-02-05","DATE08":"2024-03-29","DATE09":"2024-04-30","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2024-02-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UFJPSkVDVCBST0xMIE9WRVIgLSBCVEIgUEFQRVIgU1VCTUlUVEVEIEZPUiBBUFBST1ZBTA==","RATING":""} |  |  |  | PHASE04 | 2023-09-29 | 2024-02-05 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000633 | Absa Bizana - Temp Generator Extend Rent | Absa Bizana - Temp Generator Extend Rent |  |  | Region 2 |  | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana |  | 2023-09-01 | 2023-12-29 |  | ASP-EC0346 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-08-23 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-09-01 | 2023-12-29 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000634 | Absa Cradock - Flood Lights | Absa Cradock - Flood Lights |  |  | Region 2 | Eastern Cape | 76934X | 1000-71022-01 | Absa Cradock-Adderley St-Cradock | N | 2023-09-01 | 2023-12-29 |  | ASP-EC0347 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-08-23 | D | 24309.51 |  | 100 | 2023-08-24 | 2023-08-31 | 24309.51 | 31 Aug Approved CB33 | {"MANDT":"111","REFERENCE":90000634,"ONEVIEW":"76934X","DATE01":"2023-08-21","DATE02":"2023-08-22","DATE03":"2023-08-23","DATE04":"2023-08-30","DATE05":"2023-08-31","DATE06":"2023-09-19","DATE07":"2023-09-19","DATE08":"2023-11-06","DATE09":"2023-12-21","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":75,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"101:1:1:7:1:19:0:48:45:6","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-19","FORECAST_END":"2023-09-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBOb3YgRmluYWwgUE9DIFN1Ym1pdHRlZCBSIDIxIDQzNC41MQo2IE5vdiBGb2xsb3cgdXAgd2l0aCBCViBFbmdpbmVlcmluZwoyIE5vdiBTdWJtaXR0ZWQgdG8gQlYgRW5naW5lZXJpbmcgZm9yIFNpZ25vZmYKMSBOb3YgQXNzZXQgQnVpbGQgQ29tcGxldGVkCjMwIE9jdCAtIFVwbG9hZCBjb25maXJtYXRpb24gcGVuZGluZwoyMyBPY3QgLSBMb2NhdGlvbnMgcmVxdWVzdGVkIGZvciBBc3NldCBCdWlsZCBQTSB0byBzdXBwbHkKMTAgT2N0IC0gVXBsb2FkIG91dHN0YW5kaW5nIGZyb20gRW5naW5lZXJpbmcgQXNzZXQgTWFuYWdlciBQTSB0byBmb2xsb3cgdXAK","RATING":"Low"} |  |  | C000107716 | PHASE11 | 2023-09-19 | 2023-09-19 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-01 | 21138.7 | 0 |  |  | C000107716 | 21138.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000635 | Pretoria Campus DD & Consulting Stormwat | Pretoria Campus DD & Consulting Stormwat |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-08-23 | 2023-09-22 |  | ASP-GN0226 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-08-23 | D | 284220.15 |  | 100 | 2023-07-20 | 2023-07-25 | 284220.15 |  | {"MANDT":"111","REFERENCE":90000635,"ONEVIEW":"22491X","DATE01":"2023-06-14","DATE02":"2023-06-21","DATE03":"2023-07-12","DATE04":"2023-07-19","DATE05":"2023-09-08","DATE06":"2023-09-15","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"2024-01-05","DATE12":"2024-01-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"169:7:21:7:51:7:46:21:45:3","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-15","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMSAtIElzc3Vlcy4gRVNNIHRvIHNlbmQgZXh0ZXJuYWwgZW5naW5lZXJzIGV4aXN0aW5nIHNlcnZpY2VzIGRyYXdpbmdzLg==","RATING":""} |  |  | C000100032-2 | PHASE08 | 2023-09-15 | 2023-10-31 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-07-25 | 247147.96 | 0 |  |  | C000100032 | 247147.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000636 | Highlands Meadowdale Due Dilig Phase 1 H | Highlands Meadowdale Due Dilig Phase 1 H |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2023-08-23 | 2023-09-22 |  | ASP-GS0735 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-08-23 | D | 203301.31 |  | 100 | 2023-07-18 | 2023-07-18 | 203301.31 |  | {"MANDT":"111","REFERENCE":90000636,"ONEVIEW":"37006X","DATE01":"2023-06-14","DATE02":"2023-06-21","DATE03":"2023-07-12","DATE04":"2023-07-19","DATE05":"2023-08-09","DATE06":"2023-08-23","DATE07":"2023-09-22","DATE08":"2023-10-13","DATE09":"2023-11-27","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":42,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-23","FORECAST_END":"2023-09-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFByb2plY3QgaW4gcHJvZ3Jlc3MuIFBvc3NpYmxlIGZpbmFuY2Ugcm9sbG92ZXIgKFIgMjA1IDAwMC4wMCk=","RATING":""} |  |  | C000100033 | PHASE06 | 2023-08-23 | 2023-09-22 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-07-25 | 176783.75 | 0 |  |  | C000100033 | 176783.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000637 | Absa Longbeach - Generator Rental Extension | Absa Longbeach - Generator Rental Extension |  |  | Region 2 | Western Cape | 77344X | 1000-70822-01 | Longbeach Mall-Cnr Sunnydale Rd & Buller Louw Dr-Noordhoek | N | 2023-09-01 | 2023-12-29 |  | ASP-WC0320 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-08-23 | D | 57947.58 |  | 100 | 2023-09-05 | 2023-09-05 | 57947.58 |  | {"MANDT":"111","REFERENCE":90000637,"ONEVIEW":"77344X","DATE01":"2023-06-23","DATE02":"2023-06-30","DATE03":"2023-07-21","DATE04":"2023-07-28","DATE05":"2023-08-18","DATE06":"2023-09-01","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-01","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000108690 | PHASE11 | 2023-09-05 | 2023-09-15 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-06 | 50389.2 | 0 |  |  | C000108690 | 50389.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000638 | Pretoria Campus Chiller Plant Condenser | Pretoria Campus Chiller Plant Condenser |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-08-24 | 2023-09-22 |  | ASP-GN0227 | REL BUDG SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-08-24 | D | 480991.18 |  | 100 | 2023-09-25 | 2023-09-29 | 480991.18 |  | {"MANDT":"111","REFERENCE":90000638,"ONEVIEW":"22491X","DATE01":"2023-06-15","DATE02":"2023-06-22","DATE03":"2023-07-13","DATE04":"2023-07-20","DATE05":"2023-08-10","DATE06":"2023-10-31","DATE07":"2023-11-29","DATE08":"2023-12-20","DATE09":"2024-02-03","DATE10":"2024-02-29","DATE11":"2024-02-03","DATE12":"2024-02-03","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"168:7:21:7:21:82:29:21:45:3","PROGRESS":42,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-11-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIvMDEgTk46IFByb2plY3QgOTUlIENvbXBsZXRlIHN1cHBsaWVyIHRvIGRvIHZhY3V1bWluZyBhbmQgcmUtZ2FzIHRoZSBjb21wcmVzc29ycyBieSB0aGUgMTUuMDE=","RATING":""} |  |  | C000113587 | PHASE07 | 2023-10-31 | 2023-11-29 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-09-29 | 418253.2 | 0 |  |  | C000104094 | 241940.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000639 | Absa Mandela Park - Minor Works | Absa Mandela Park - Minor Works |  |  | Region 3 | [5 empty] | 2023-11-15 |  |  | ASP-CR0485 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-25 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-15 | 2023-12-15 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000640 | Absa Virginia - HVAC Replacement | Absa Virginia - HVAC Replacement |  |  | Region 3 |  | Unknown | 1000-71582-01 | Unknown Building - not in our database |  | 2023-09-08 |  |  | ASP-CR0486 | CLSD BUDG AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-25 | D | 0 | Approved |  | 2023-10-07 | 2023-10-07 | 87543.75 |  |  |  |  | C000107138 | PHASE11 | 2023-09-08 | 2023-10-08 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-08-30 | 76125 | 0 |  |  | C000107138 | 76125 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000641 | Absa Demountable Bank Unit -HVAC Replace | Absa Demountable Bank Unit -HVAC Replace |  |  | Region 3 | [5 empty] | 2023-09-08 |  |  | ASP-CR0487 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-25 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-08 | 2023-10-08 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000642 | Absa Towers West Switcher Faulty | Absa Towers West Switcher Faulty |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-08-25 | 2023-09-22 |  | ASP-GS0736 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-08-25 | D | 2484 | Approved | 100 | 2023-10-07 | 2023-10-07 | 2484 |  | {"MANDT":"111","REFERENCE":90000642,"ONEVIEW":"21526X","DATE01":"2023-09-27","DATE02":"2023-10-06","DATE03":"2023-10-27","DATE04":"2023-11-03","DATE05":"2023-11-24","DATE06":"2023-12-08","DATE07":"2024-01-05","DATE08":"2024-01-26","DATE09":"2024-03-11","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:9:21:7:21:14:28:21:45:3","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-08","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RmluYWxpemluZyBzY29wZSB3aXRoIHRoZSBFU00sIHByb2plY3QgdG8gYmUgYSBwcm9qZWN0IHJvbGwgb3Zlcg==","RATING":""} |  |  | C000106521 | PHASE08 | 2023-09-09 | 2023-10-07 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-28 | 2856.6 | 0 |  |  | C000106521 | 2160 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000643 | Absa Witbank - Repairs to Vandalized Ele | Absa Witbank - Repairs to Vandalized Ele |  |  | Region 3 |  | 76953X | 1000-70604-01 | Absa Witbank-Mandela Dr-Witbank |  | 2023-08-30 |  |  | ASP-MP0169 | CLSD BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  | OCC Submission | 2023 |  | F |  | NOMNGANGAL | 2023-08-25 | D | 225175.75 | Approved | 100 | 2023-10-07 | 2023-10-07 | 225175.75 |  | {"MANDT":"111","REFERENCE":90000643,"ONEVIEW":"76953X","DATE01":"2023-06-21","DATE02":"2023-09-04","DATE03":"2023-09-11","DATE04":"2023-09-04","DATE05":"2023-09-14","DATE06":"2023-09-15","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-15","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBzdWJtaXR0ZWQgYXMgT09DIHJlY292ZXJ5IHByb2plY3Q=","RATING":""} |  |  | C000106540 | PHASE11 | 2023-09-15 | 2023-09-29 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-08-28 | 195805 | 0 |  |  | C000106540 | 195805 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000644 | Absa Tonga -Ceiling Mesh Wire Repairs | Absa Tonga -Ceiling Mesh Wire Repairs |  |  | Region 3 |  | 37188X | 1000-77506-01 | Tonga Mall |  | 2023-09-08 |  |  | ASP-MP0170 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  | Project submitted as OCC | 2023 |  | L |  | NOMNGANGAL | 2023-08-25 | D | 7498 | Approved | 100 | 2023-10-07 | 2023-10-07 | 7498 |  | {"MANDT":"111","REFERENCE":90000644,"ONEVIEW":"37188X","DATE01":"2023-06-30","DATE02":"2023-09-04","DATE03":"2023-09-11","DATE04":"2023-08-04","DATE05":"2023-08-25","DATE06":"2023-09-08","DATE07":"2023-10-08","DATE08":"2023-10-29","DATE09":"2023-12-13","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":5,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-08","FORECAST_END":"2023-10-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBkb25lIE9PQw==","RATING":""} |  |  | C000106539 | PHASE11 | 2023-09-08 | 2023-10-08 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-08-28 | 6520 | 0 |  |  | C000106539 | 6520 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000645 | Absa Klersdorp - Minor Works | Absa Klersdorp - Minor Works |  |  | Region 3 |  | 77176X | 1000-71476-01 | Absa Klerksdorp | N | 2023-11-24 |  |  | ASP-CR0488 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  | L | 2023-09-29 | NOMNGANGAL | 2023-08-28 | D | 330161.83 |  | 100 | 2023-09-29 | 2023-10-06 | 330161.83 | Requested Absa PO on 06 October 2023. | {"MANDT":"111","REFERENCE":90000645,"ONEVIEW":"","DATE01":"2023-09-15","DATE02":"2023-09-22","DATE03":"2023-10-13","DATE04":"2023-10-20","DATE05":"2023-11-10","DATE06":"2023-11-24","DATE07":"2023-12-24","DATE08":"2024-01-14","DATE09":"2024-02-28","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-24","FORECAST_END":"2023-12-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000115978 | PHASE10 | 2023-11-24 | 2023-12-24 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-11 | 287097.24 | 0 |  |  | C000115978 | 287097.24 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000646 | Absa Vryburg - Installation of Signage | Absa Vryburg - Installation of Signage |  |  | Region 3 |  | 77745X | 1000-71604-01 | Vryburg-Market St-Vryburg |  | 2023-09-28 |  |  | ASP-CR0489 | REL BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  | 2022-03-30 | NOMNGANGAL | 2023-08-28 | D | 0 | Approved | 20 | 2023-10-07 | 2023-10-07 | 44934.07 |  | {"MANDT":"111","REFERENCE":90000646,"ONEVIEW":"77745X","DATE01":"2023-07-20","DATE02":"2023-07-27","DATE03":"2023-08-17","DATE04":"2023-08-24","DATE05":"2023-09-14","DATE06":"2023-09-28","DATE07":"2023-10-28","DATE08":"2023-11-18","DATE09":"2024-01-02","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":60,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":14,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-28","FORECAST_END":"2023-10-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE0gYnVzeSB3aXRoIGNvdW5jaWwgc3VibWlzc2lvbjsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  | C000108174 | PHASE06 | 2023-09-28 | 2023-10-28 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-09-04 | 39073.1 | 0 |  |  | C000140952 | 39073.1 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000647 | Alice Lane Podium Replacement of Umbrell | Alice Lane Podium Replacement of Umbrell |  |  | Region 1 | Gauteng | Unknown | 1000-71371-01 | Unknown Building - not in our database |  | 2023-04-05 |  |  | ASP-GS0737 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-08-28 | D | 200000 | Approved | 100 | 2023-10-07 | 2023-10-07 | 152197 |  | {"MANDT":"111","REFERENCE":90000647,"ONEVIEW":"Unknown","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-08-01","DATE04":"2023-08-08","DATE05":"2024-02-07","DATE06":"2024-07-19","DATE07":"2024-08-18","DATE08":"2025-01-06","DATE09":"2025-02-20","DATE10":"2025-02-28","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:181:7:183:163:30:141:45:21","PROGRESS":19,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-19","FORECAST_END":"2024-08-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBWUCBhcHByb3ZhbCB0byByZWxlYXNlIDUwJSBwYXltZW50IHRvIHN1cHBsaWVyIGZvciBNYW51ZmFjdHVyZQ==","RATING":""} |  |  | C000108233 | PHASE08 | 2024-07-19 | 2024-08-18 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-09-05 | 175026.55 | 0 |  |  | C000108233 | 132345.22 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000648 | Clearwater O/P hotdesking area | Clearwater O/P hotdesking area |  |  | Region 1 |  | 77174X | 1000-70352-01 | Clearwater Office Park Building 4-Millenium Rd-Strubensvalley |  | 2023-08-28 | 2023-09-28 |  | ASP-GS0738 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-08-28 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000648,"ONEVIEW":"77174X","DATE01":"2023-08-21","DATE02":"2023-09-28","DATE03":"2023-10-19","DATE04":"2023-10-26","DATE05":"2023-11-16","DATE06":"2023-11-30","DATE07":"2023-12-31","DATE08":"2024-01-21","DATE09":"2024-03-06","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":20,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:38:21:7:21:14:31:21:45:28","PROGRESS":1,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-30","FORECAST_END":"2023-12-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QUJTQSBDUkVTIHRvIGZpbmFsaXplIG9uIHdobyBzdXBwbHkgYW5kIGluc3RhbGwgRnJlc2ggYWlyIHN5c3RlbSwgdGhlIHByb2plY3QgaXMgbGlrZWx5IHRvIGJlIGEgcHJvamVjdCByb2xsIG92ZXIg","RATING":""} |  |  |  | PHASE08 | 2023-11-30 | 2024-02-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000142471 | 242160.66 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000649 | Absa Bethlehem - UPS Installation | Absa Bethlehem - UPS Installation |  |  | Region 3 | [5 empty] | 2023-11-29 |  |  | ASP-CR0490 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-29 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000650 | Absa Musina - Replacement of APC UPS | Absa Musina - Replacement of APC UPS |  |  | Region 3 | [5 empty] | 2023-10-05 |  |  | ASP-LP0175 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-29 | D | 0 |  | 100 |  |  | 161.96 |  | {"MANDT":"111","REFERENCE":90000650,"ONEVIEW":"","DATE01":"2023-07-27","DATE02":"2023-08-03","DATE03":"2023-08-24","DATE04":"2023-08-31","DATE05":"2023-09-21","DATE06":"2023-10-05","DATE07":"2023-11-04","DATE08":"2023-11-25","DATE09":"2024-01-09","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-11-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-10-05 | 2023-11-04 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000651 | Absa Savanna Mall - Branch Generator (DI | Absa Savanna Mall - Branch Generator (DI |  |  | Region 3 |  | 21331X | 1000-70452-01 | Savannah Mall-Cnr Grimm & Thabo Mbeki St-Polokwane |  | 2023-10-12 |  |  | ASP-LP0176 | REL BUDG AVAC RESA SETC: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-29 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 209384.04 |  | {"MANDT":"111","REFERENCE":90000651,"ONEVIEW":"Unknown","DATE01":"2023-08-03","DATE02":"2023-08-10","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-09-28","DATE06":"2023-10-12","DATE07":"2023-11-11","DATE08":"2023-12-02","DATE09":"2024-01-16","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-12","FORECAST_END":"2023-11-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQuIEZ1bGx5IGludm9pY2VkLkR1cGxpY2F0aW9uLg==","RATING":""} |  |  | C000111665 | PHASE00 | 2023-10-12 | 2023-11-11 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-19 | 182073.08 | 0 |  |  | C000111665 | 182073.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000652 | Absa 85 Oxford East London - Dilaps | Absa 85 Oxford East London - Dilaps for Revamp |  |  | Region 2 | Eastern Cape | 79244X | 1000-71469-01 | 85 Oxford Street-Oxford St-East London | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0348 | TECO BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-08-30 | D | 111397.76 |  | 100 | 2023-10-16 | 2023-10-17 | 111397.76 |  | {"MANDT":"111","REFERENCE":90000652,"ONEVIEW":"79244X","DATE01":"2023-08-24","DATE02":"2023-09-15","DATE03":"2023-10-16","DATE04":"2023-10-23","DATE05":"2023-10-17","DATE06":"2023-10-18","DATE07":"2023-10-21","DATE08":"2023-11-11","DATE09":"2023-12-26","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"160:22:31:7:-6:1:3:21:45:21","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-18","FORECAST_END":"2023-10-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTcgT2N0IFBhY2sgU3VwcG9ydGVkIGFuZCBTZW50IHRvIFJlYWwgRXN0YXRlIGZvciBhcHByb3ZhbAoxNiBPY3QgUGFjayBTZW50IHN1cHBvcnQgdG8gQ3JlcyBWUC4KMTEgU2VwdCAtIFBNIHRvIHN1Ym1pdCBCQyBwYWNrIHRvZGF5CjIyIFNlcHQgLSBQTSB0byBmaW5hbGlzZSBjb3N0aW5nIGZvciBzdWJtaXNzaW9uCjExIFNlcHQgLSBDb3N0aW5nIGluIHByb2dyZXNzCjI0IEF1ZyBOb3RpY2UgcmVjZWl2ZWQgdG8gYmUgY29tcGxldGVkIGJ5IDIyIE9jdA==","RATING":"Low"} |  |  | C000117493 | PHASE09 | 2023-10-19 | 2023-10-23 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-18 | 96867.61 | 0 |  |  | C000117493 | 96867.61 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000653 | Absa King Williams Town - Dilaps | Absa King Williams Town - Dilaps |  |  | Region 2 | Eastern Cape | 78329X | 1000-71043-01 | Absa King Williams Town-Cnr Cathcart & Maclean St-King Williams Town | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0349 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-08-30 | D | 125854.61 |  | 100 | 2023-09-01 | 2023-09-05 | 125854.61 | 5 Sept Absa PO Issued C000108321 BV PO's requested 5 Sept Approved by Real Estate PO's to follow 4 Sept VP supported Real Estate Approval requested 1 Sept BC pack sent to VP for approval in order to submit to Real Estate Suppliers - Koen's Locksmith Fidelity ADT and Technical (Deinstall) Secutel Technologies (Deinstall), Global Access, Standby Systems, S&G Signs 24 Aug Notice received to be completed by 11 Sept | {"MANDT":"111","REFERENCE":90000653,"ONEVIEW":"78329X","DATE01":"2023-07-07","DATE02":"2023-07-14","DATE03":"2023-08-04","DATE04":"2023-08-11","DATE05":"2023-09-01","DATE06":"2023-09-15","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-15","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000108321 | PHASE11 | 2023-09-07 | 2023-09-09 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-05 | 109438.79 | 0 |  |  | C000108321 | 109438.79 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000654 | Absa Mount Frere - Close off section of Branch | Absa Mount Frere - Close off section of Branch |  |  | Region 2 | Eastern Cape | 78953X | 1000-71060-01 | Mount Frere-Main St-Mount Frere | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0350 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-30 | D | 0 |  | 1 |  |  | 0 | Absa Ref : ??????? Retail Reprioritised | {"MANDT":"111","REFERENCE":90000654,"ONEVIEW":"78953X","DATE01":"2024-01-31","DATE02":"2024-03-29","DATE03":"2024-05-19","DATE04":"2024-05-26","DATE05":"2024-06-08","DATE06":"2024-07-22","DATE07":"2024-08-09","DATE08":"2024-08-30","DATE09":"2024-10-14","DATE10":"2024-10-31","DATE11":"2024-05-05","DATE12":"2024-05-05","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:58:51:7:13:44:18:21:45:26","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-22","FORECAST_END":"2024-08-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCBSZW1vdmUgYXMgcGVyIHByaW9yaXR5IG1lZXRpbmcKMSBNYXJjaCAtIEVCIHRvIGNvbmZpcm0gYXMgcG9zc2libGUgcmVsb2NhdGlvbiAvIHJldmFtcCBSZWR1Y2UgaW4gcGxhbm5pbmcgLSBBcHByb3ZlZCBEcmF3aW5nIHBlbmRpbmcgaWYgdG8gY29udGludWUKMjYgRmViIC0gRUIgdG8gY29uZmlybSBhcyBwb3NzaWJsZSByZWxvY2F0aW9uIC0gQXBwcm92ZWQgRHJhd2luZyBwZW5kaW5nIC0gCjE2IEZlYiBGZWVkYmFjayBmcm9tIFBsYW5uZXIgbm8gY2xlYXIgd2F5IGZvcndhcmQgYXMgdmFyaW91cyBvcHRpb25zIGJlaW5nIGNvbnNpZGVyZWQKNSBGZWIgLSBEcmF3aW5ncyBQZW5kaW5nIGZyb20gUGxhbm5lcgoyOSBKYW4gLSBQbSB0byBmb2xsb3cgdXAgd2l0aCBwbGFubmVyIGZvciBhcHByb3ZlZCBkcmF3aW5ncywgRW5naW5lZXJpbmcgdG8gYmUgaW52b2x2ZWQgcmUgTGlnaHRpbmcgYW5kIEhWQUMKMTQgRGVjIEFwcHJvdmVkIERyYXdpbmdzIHBlbmRpbmcgZnJvbSBFQiwgdG8gYmUgY29uZmlybWVkIGlmIEJGTSB3b3JrCjI3IE5vdiBOZXcgZGVzaWduIHByb3Bvc2VkIG5vIGRpcmVjdGlvbiBhdmFpbGFibGUKMjMgT2N0IE5vIGZpbmFsIGFncmVlbWVudCBvbiBhZGRpdGlvbmFsIHdvcmtzL3Njb3BlIG9yIGZpbmFsIGFwcHJvdmFsIG9mIGRyYXdpbmcgYnkgQVMKMTEgT2N0IFBNIHRvIHZpc2l0IGJyYW5jaCB3aGlsZSBpbiBOdGFiYW5rdWx1IHRvIGdldCBiYWNrZ3JvdW5kIHJlIGFyZWEgCjIyIFNlcHQgLSBBcHByb3ZhbCBvZiBEcmF3aW5nIGFuZCBzY29wZSBvdXRzdGFuZGluZyBpZiB0byBwcm9jZWVkIHdpbGwgYmUgZWl0aGVyIGEgRmluYW5jaWFsIG9yIFByb2plY3QgUm9sbG92ZXIKMTUgU2VwdCAtIFByb3Bvc2VkIERyYXdpbmcgc2VudCB0byBQbGFubmVyIGZvciByZWdpb25hbCBhcHByb3ZhbAoxMSBTZXB0IC0gUFJGIGFuZCBhcHByb3ZlZCBwbGFuIHBlbmRpbmcKMjQgQXVnIC0gQXBwcm92ZWQgUFJGIFJlY2VpdmVkIC0gRHJhd2luZyByZXF1ZXN0ZWQgZnJvbSB0aGUgUGxhbm5lciB0byBkZXRlcm1pbmUgcmVxdWlyZW1lbnRzCjI3IE5vdiBOZXcgZGVzaWduIHByb3Bvc2VkIG5vIGRpcmVjdGlvbiBhdmFpbGFibGUKMjMgT2N0IE5vIGZpbmFsIGFncmVlbWVudCBvbiBhZGRpdGlvbmFsIHdvcmtzL3Njb3BlIG9yIGZpbmFsIGFwcHJvdmFsIG9mIGRyYXdpbmcgYnkgQVMKMTEgT2N0IFBNIHRvIHZpc2l0IGJyYW5jaCB3aGlsZSBpbiBOdGFiYW5rdWx1IHRvIGdldCBiYWNrZ3JvdW5kIHJlIGFyZWEgCjIyIFNlcHQgLSBBcHByb3ZhbCBvZiBEcmF3aW5nIGFuZCBzY29wZSBvdXRzdGFuZGluZyBpZiB0byBwcm9jZWVkIHdpbGwgYmUgZWl0aGVyIGEgRmluYW5jaWFsIG9yIFByb2plY3QgUm9sbG92ZXIKMTUgU2VwdCAtIFByb3Bvc2VkIERyYXdpbmcgc2VudCB0byBQbGFubmVyIGZvciByZWdpb25hbCBhcHByb3ZhbAoxMSBTZXB0IC0gUFJGIGFuZCBhcHByb3ZlZCBwbGFuIHBlbmRpbmcKMjQgQXVnIC0gQXBwcm92ZWQgUFJGIFJlY2VpdmVkIC0gRHJhd2luZyByZXF1ZXN0ZWQgZnJvbSB0aGUgUGxhbm5lciB0byBkZXRlcm1pbmUgcmVxdWlyZW1lbnRz","RATING":"Low"} |  |  |  | PHASE12 | 2024-07-22 | 2024-08-09 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000655 | Absa Greenfields Settlers - Contravision | Absa Greenfields Settlers - Contravision |  |  | Region 2 | Eastern Cape | 79189X | 1000-71468-01 | Settlers Square Greenfields-Cnr Settlers Way & Cloverley Rd-East London | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0351 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-30 | D | 34951.03 |  | 100 | 2024-03-28 | 2024-04-04 | 34951.03 | Absa Ref : 240402_015 Retail Reprioritised | {"MANDT":"111","REFERENCE":90000655,"ONEVIEW":"79189X","DATE01":"2024-01-01","DATE02":"2024-01-26","DATE03":"2024-02-27","DATE04":"2024-03-05","DATE05":"2024-03-15","DATE06":"2024-04-13","DATE07":"2024-04-17","DATE08":"2024-05-08","DATE09":"2024-06-22","DATE10":"2024-06-30","DATE11":"2024-06-22","DATE12":"2024-06-22","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"181:25:32:7:10:29:4:21:45:-62:-62:6","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-13","FORECAST_END":"2024-04-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggLSBOZXcgRGVzaWducyBwZW5kaW5nIGZyb20gQWJzYSBEZXNpZ24gCihUaGlzIGlzIEJBVSDigJMgUmVwdXRhdGlvbmFsIGFuZCBjYW5ub3QgYmUgY29tcHJvbWlzZWQpCjExIE1hcmNoIC0gRmVlZGJhY2sgcGVuZGluZyBmcm9tIERlc2lnbiBUZWFtIHJlIE5ldyBMaWZlc3R5bGUgR3JhcGhpY3Mgd2hpY2ggY291bGQgaW1wYWN0IENvc3QKNSBNYXJjaCBXaXRoZHJhd24gQ0IgMDcsIGFkZGl0aW9uIHJlcXVpcmVtZW50cyBmcm9tIFBsYW5uZXIKNCBNYXJjaCBDb250aW51ZSAtIFN1Ym1pdHRlZCB0byBDQjA3IC0gIC0gUiAzOCA0NDYuMTMKMjYgRmViIC0gVG8gYmUgdGFibGVkIGZvciBDQjA3CjE5IEZlYiAtIDJuZCBRdW90ZSByZXF1ZXN0ZWQgZnJvbSBTJkcgLSBEdWUgMjMgRmViCjUgRmViIC0gQXJ0d29ya3MgcmVxdWVzdGVkIC0gcmUgVmlueWwgdnMgZnVsbCByZXBsYWNlbWVudAoyOSBKYW4gdG8gY29udGludWUgYXMgU2VjdXJpdHkgcmVxdWVzdAoyMiBKYW4gUXVvdGVzIHRvIHJldmlzaXRlZCByZSBVcGRhdGVkIHF1b3RlcwoxMSBEZWMgUE0gdG8gZm9sbG93IHVwIG9uIHRoZSBxdW90ZXMKNCBEZWMgUE0gdG8gZm9sbG93IHVwIG9uIFF1b3RlcyBmb3IgdGhlIHJlcGxhY2VtZW50CjI3IE5vdiAtIFRvIGJlIGRvbmUgMjAyNCAKNiBOb3YgMTUwMCBmcm9zdGluZyBCYW5kIHRvIGJlIGFwcGxpZWQgYXJ0d29yayB0byBiZSBhcHByb3ZlZCByZSBwcm9wb3NlZCBiYW5kCjMwIE9jdCBCQkMgdG8gYmUgcmVhZHkgYnkgMiBOb3YKMjcgT2N0IC0gUkZRIMODwqLDgsKAw4LCkyBEZXBlbmRhbnQgb24gTWFudWZhY3R1cmUgTGVhZCB0aW1lLiB0byBiZSBzdWJtaXR0ZWQgZm9yIGFwcHJvdmFsIDIgTm92CjIzIE9jdCAtIE1lYXN1cmVtZW50cyBvdXRzdGFuZGluZwoxMSBPY3QgUE0gdG8gZm9sbG93IHVwIHdpdGggU2lnbmFnZSBWZW5kb3JzIHJlIHF1b3RlcyAKMjIgU2VwdCAtIENvbnRyYSBWaXNpb24gdG8gYmUgaW5zdGFsbGVkIC0gUXVvdGVzIHRvIGJlIHJlcXVlc3RlZCAtIElmIGFwcHJvdmVkIHdpbGwgYmUgRmluYW5jaWFsIFJvbGxvdmVyCjMwIEF1ZyBBZnJpY2EgU2VjdXJpdHkgcmVxdWVzdGVkIHRvIHJldmlzaXQKMjQgQXVnIC0gQXBwcm92ZWQgUFJGIFJlY2VpdmVkIC0gRHJhd2luZyByZXF1ZXN0ZWQgZnJvbSB0aGUgUGxhbm5lciB0byBkZXRlcm1pbmUgcmVxdWlyZW1lbnRz","RATING":"Low"} |  |  | C000152986 | PHASE06 | 2024-05-15 | 2024-05-19 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-04-08 | 30392.2 | 0 |  |  | C000152986 | 30392.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000656 | Absa Port Alfred Neave Stotter - Generator - Radiator Replacement | Absa Port Alfred Neave Stotter - Generator - Radiator Replacement |  |  | Region 2 | Eastern Cape | 76483X | 1000-71011-01 | Neave Stotter Chambers-Cnr Campbell & Main St-Port Alfred | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0352 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-30 | D | 31219.05 |  | 100 | 2023-09-01 | 2023-09-07 | 31219.05 | 13 Sept Absa PO Received C000110171 11 Sept Approved CB34 Signed deck Received, PO's to be requested | {"MANDT":"111","REFERENCE":90000656,"ONEVIEW":"76483X","DATE01":"2023-08-24","DATE02":"2023-08-31","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-09-07","DATE06":"2023-09-18","DATE07":"2023-09-22","DATE08":"2023-10-13","DATE09":"2023-11-27","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:0:7:0:11:4:21:45:27","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-18","FORECAST_END":"2023-09-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgQXVnIC0gTGVhZCB0aW1lcyB0byBiZSBjb25maXJtZWQgU3VibWl0dGVkIHRvIENCMzQKMjQgQXVnIC0gQXBwcm92ZWQgUFJGIFJlY2VpdmVkCg==","RATING":"Low"} |  |  | C000110171 | PHASE11 | 2023-09-13 | 2023-09-15 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-13 | 27147 | 0 |  |  | C000110171 | 27147 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000657 | Absa Motherwell - Connection of Selecta Door to UPS power | Absa Motherwell - Connection of Selecta Door to UPS power |  |  | Region 2 | Eastern Cape | 76665X | 1000-71018-01 | Motherwell Shopping Centre-Cnr Nyara, Tyiniara & WM Maku St-Port Elizabeth | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0353 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-30 | D | 9467.06 |  | 100 | 2023-09-14 | 2023-09-21 | 9467.06 | 22 Sept Absa Po Received C000112430 BV PO requested | {"MANDT":"111","REFERENCE":90000657,"ONEVIEW":"76665X","DATE01":"2023-08-24","DATE02":"2023-08-31","DATE03":"2023-09-14","DATE04":"2023-09-21","DATE05":"2023-09-21","DATE06":"2023-10-05","DATE07":"2023-10-06","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"129:7:14:7:0:14:1:21:45:13","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgU2VwdCAtIEFwcHJvdmVkIENCMzYgMjEgU2VwdCBTaWduZWQgRGVjayBhbmQgUE8ncyB0byBmb2xsb3c=","RATING":"Low"} |  |  | C000112430 | PHASE11 | 2023-10-14 | 2023-10-14 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-22 | 8232.23 | 0 |  |  | C000112430 | 8232.23 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000658 | Absa Malcomess Park - HVAC server room | Absa Malcomess Park - HVAC server room |  |  | Region 2 | Eastern Cape | 78764X | 1000-71052-01 | Malcomess Park Shopping Centre-St. Peters Rd-East London | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0354 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-30 | D | 36588.34 |  | 100 | 2023-08-31 | 2023-09-07 | 36588.34 | 12 Sept Absa PO received C000110246 11 Sept Approved CB34 Signed deck Received, PO's to be requested | {"MANDT":"111","REFERENCE":90000658,"ONEVIEW":"78764X","DATE01":"2023-08-24","DATE02":"2023-08-25","DATE03":"2023-08-30","DATE04":"2023-09-06","DATE05":"2023-09-07","DATE06":"2023-10-11","DATE07":"2023-10-13","DATE08":"2023-11-03","DATE09":"2023-12-18","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:1:5:7:1:34:2:21:45:27","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-11","FORECAST_END":"2023-10-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MzEgQXVnIFN1Ym1pdHRlZCBmb3IgQ0IzNAozMCBBdWcgdG8gYmUgU3VibWl0dGVkIENCMzQKMjQgQXVnIC0gQXBwcm92ZWQgUFJGIFJlY2VpdmVk","RATING":"Low"} |  |  | C000110246 | PHASE11 | 2023-10-03 | 2023-10-04 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-12 | 31815.95 | 0 |  |  | C000110246 | 31815.95 |  | 3326.21 |  | 0 | 0 |  | 0 |  | 0
90000659 | Absa Kuyasa Mdantsane - Door to ablution | Absa Kuyasa Mdantsane - Door to ablution |  |  | Region 2 | Eastern Cape | 79176X | 1000-71065-01 | Kuyasa Shopping Centre-Sandile Rd-Mdantsane | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0355 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-08-30 | D | 23627.9 |  | 100 | 2023-11-02 | 2023-11-02 | 23627.9 | Approved CB on 2 Nov | {"MANDT":"111","REFERENCE":90000659,"ONEVIEW":"79176X","DATE01":"2023-09-01","DATE02":"2023-10-20","DATE03":"2023-11-02","DATE04":"2023-11-09","DATE05":"2023-11-02","DATE06":"2023-11-07","DATE07":"2023-11-09","DATE08":"2023-11-16","DATE09":"2023-12-31","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"121:49:13:7:-7:5:2:7:45:2","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-07","FORECAST_END":"2023-11-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBOb3YgU3RhcnQgb24gU2l0ZSB0b21vcnJvdyA3IE5vdgoyIE5vdiBBcHByb3ZlZCBpbiBDQiAsIFNpZ25lZCBkZWNrcyB0byBmb2xsb3cgdG8gcmFpc2UgQWJzYSBQTydzCjIgTm92IFNlbnQgZm9yIFZQIFN1cHBvcnQgdG8gYWRkIHRvIENCIGRlY2sgLSBXYXMgU3VwcG9ydGVkCjMwIE9jdCBCQyB0byBiZSByZWFkeSBieSAyIE5vdgoyOCBPY3QgLSBQTSB0byBjb3B5IGFsbCB3aGVuIGZvbGxvd2luZyB1cCBvbiBRdW90ZSBhbmQgY2xlYXIgd2l0aCBFbmdpbmVlcmluZyBCQyB0byBiZSBzdWJtaXR0ZWQgMiBOb3YKMTYgT2N0IFF1b3RlcyByZXF1ZXN0ZWQgUE0gdG8gZm9sbG93IHVwCjExIE9jdCAtIDIyIFNlcHQgV2lsbCBiZSBmaW5hbmNpYWwgb3IgUHJvamVjdCBSb2xsb3ZlciBhcyBQUkYgYW5kIFNjb3BlIG91dHN0YW5kaW5nIGZyb20gUGxhbm5lcgoxMSBTZXB0IC0gUE0gdG8gZm9sbG93IHVwIHdpdGggcGxhbm5lciBmb3IgUFJGCjE4IEF1ZyBQbGFuIHJlY2VpdmVkIC0gQXBwcm92ZWQgUmVxdWVzdCAvIFBSRiBwZW5kaW5n","RATING":"Low"} |  |  | C000121884 | PHASE11 | 2023-11-07 | 2023-11-10 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-11-08 | 20546 | 0 |  |  | C000121884 | 20546 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000660 | Absa Grahamstown - Downlights Installati | Absa Grahamstown - Downlights Installati |  |  | Region 2 | Eastern Cape | 77512X | 1000-71029-01 | Absa Grahamstown-High St-Grahamstown | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0356 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-08-30 | D | 6522.76 |  | 100 | 2023-08-31 | 2023-09-06 | 6522.76 | 13 Sept Absa PO Received C000110187 | {"MANDT":"111","REFERENCE":90000660,"ONEVIEW":"77512X","DATE01":"2023-08-30","DATE02":"2023-08-30","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-09-07","DATE06":"2023-09-20","DATE07":"2023-09-20","DATE08":"2023-10-11","DATE09":"2023-11-25","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"92:0:1:7:0:13:0:21:45:2","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-20","FORECAST_END":"2023-09-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjEgU2VwdCBDb21wbGV0ZWQgMjAgU2VwdCBJbnZvaWNlIG91dHN0YW5kaW5nCg==","RATING":""} |  |  | C000110187 | PHASE11 | 2023-09-20 | 2023-09-20 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-13 | 5671.97 | 0 |  |  | C000110187 | 5671.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000661 | Absa 46 Aiken Street - Internal painting | Absa 46 Aiken Street - Internal painting |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-11-30 |  |  | ASP-KZ0262 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-30 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-30 | 2023-12-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000662 | Absa 18 Swapo Street - Installation of B | Absa 18 Swapo Street - Installation of B |  |  | Region 3 |  | Unknown | 1000-71170-01 | Unknown Building - not in our database |  | 2023-11-30 |  |  | ASP-KZ0263 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-30 | D | 0 | Approved |  | 2023-10-07 | 2023-10-07 | 8579 |  |  |  |  | C000110982 | PHASE00 | 2023-11-30 | 2023-12-30 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-09-15 | 7460 | 0 |  |  | C000140945 | 7460 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000663 | Absa Galleria Mall - Removal of Transpor | Absa Galleria Mall - Removal of Transpor |  |  | Region 3 |  | Unknown | 1000-71073-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-KZ0264 | CLSD BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-30 | D | 0 | Approved |  | 2023-10-07 | 2023-10-07 | 8802.76 |  |  |  |  | C000112432 | PHASE11 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-22 | 7654.57 | 0 |  |  | C000112432 | 7654.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000664 | Absa Pavillion Shopping - Supply Storage | Absa Pavillion Shopping - Supply Storage |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-11-30 |  |  | ASP-KZ0265 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-30 | D | 0 |  | 100 |  |  | 19852.96 |  | {"MANDT":"111","REFERENCE":90000664,"ONEVIEW":"","DATE01":"2023-09-21","DATE02":"2023-09-28","DATE03":"2023-10-19","DATE04":"2023-10-26","DATE05":"2023-11-16","DATE06":"2023-11-30","DATE07":"2023-12-30","DATE08":"2024-01-20","DATE09":"2024-03-05","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-30","FORECAST_END":"2023-12-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-11-30 | 2023-12-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000665 | Centurion Dilaps (Removal of Cameras) | Centurion Dilaps (Removal of Cameras) |  |  | Region 1 |  | 77509X | 1000-70372-01 | United Bank Centurion-Cnr Hendrik Verwoerd Dr & Heuwel Ave-Centurion | N | 2023-08-31 | 2023-09-29 |  | ASP-GN0228 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-08-31 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 17503.46 |  | {"MANDT":"111","REFERENCE":90000665,"ONEVIEW":"77509X","DATE01":"2023-06-22","DATE02":"2023-06-29","DATE03":"2023-07-20","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"2023-12-04","DATE12":"2023-12-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMSBOTjogZm9sbG93IHVwIG9uIGludm9pY2VzIGZvciBTZWN1dGVsICYgRmlkZWxpdHkgZm9yIGZpbmFsIFBPQy4=","RATING":""} |  |  | C000107583 | PHASE08 | 2023-08-31 | 2023-09-29 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-08-31 | 23148.33 | 0 |  |  | C000107583 | 15220.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000666 | Absa Glen Swing Space Dilaps & Reinstate | Absa Glen Swing Space Dilaps & Reinstate |  |  | Region 1 |  | 77239X | 1000-70359-01 | The Glen Shopping Centre-Cnr Orpen & Letaba St-Oakdene | N | 2023-08-31 | 2023-09-29 |  | ASP-GS0739 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-08-31 | D | 0 |  | 100 | 2023-08-21 | 2023-08-24 | 490434.28 |  | {"MANDT":"111","REFERENCE":90000666,"ONEVIEW":"77239X","DATE01":"2023-06-22","DATE02":"2023-06-29","DATE03":"2023-07-20","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQgUE9DIHRvIGJlIGlzc3VlZCBhd2FpdGluZyBzdXBwbGllciBpbnZvaWNlcy4=","RATING":""} |  |  | C000107585 | PHASE11 | 2023-08-31 | 2023-09-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-08-31 | 425564.59 | 0 |  |  | C000107585 | 425564.59 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000667 | Auckland Park Salad Bar | Auckland Park Salad Bar |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-08-31 | 2023-09-29 |  | ASP-GS0740 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-08-31 | D | 130556.05 | Approved | 100 | 2023-08-23 | 2023-08-29 | 130556.05 |  | {"MANDT":"111","REFERENCE":90000667,"ONEVIEW":"76849X","DATE01":"2023-06-22","DATE02":"2023-06-29","DATE03":"2023-07-20","DATE04":"2023-07-27","DATE05":"2023-08-17","DATE06":"2023-08-31","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-08-31","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000108633 | PHASE06 | 2023-08-31 | 2023-09-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-08-31 | 2023-09-06 | 2023-09-07 | 2023-09-13 | 2023-09-06 | 113527 | 0 |  |  | C000108633 | 113527 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000668 | Absa Bridge City Shopping - Install Shop | Absa Bridge City Shopping - Install Shop |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-10-31 |  |  | ASP-KZ0266 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-31 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-10-31 | 2023-11-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000669 | Absa Ridgeside - Painting & Pause Area R | Absa Ridgeside - Painting & Pause Area R |  |  | Region 3 |  | Unknown | 1000-71094-01 | Unknown Building - not in our database |  | 2023-11-22 |  |  | ALP-KZ2009 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-08-31 | D | 0 |  | 100 |  |  | 4324829.1 |  | {"MANDT":"111","REFERENCE":90000669,"ONEVIEW":"","DATE01":"2023-09-13","DATE02":"2023-09-20","DATE03":"2023-10-11","DATE04":"2023-10-18","DATE05":"2023-11-08","DATE06":"2023-11-22","DATE07":"2023-12-22","DATE08":"2024-01-12","DATE09":"2024-02-26","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-22","FORECAST_END":"2023-12-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000127936 | PHASE00 | 2023-11-22 | 2023-12-22 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-30 | 3760720.96 | 0 |  |  | C000140963 | 3760720.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000670 | Absa Bethlehem - Installation of UPS ded | Absa Bethlehem - Installation of UPS ded |  |  | Region 3 |  | 22405X | 1000-71480-01 | Bethlehem Church Street-Cnr Church & Roux St-Bethlehem |  | 2023-09-29 |  |  | ASP-CR0491 | REL BUDG AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  | 2026-10-30 | NOMNGANGAL | 2023-09-01 | D | 27404.05 |  | 100 |  |  | 27404.05 |  | {"MANDT":"111","REFERENCE":90000670,"ONEVIEW":"22405X","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-10-29","DATE08":"2023-11-19","DATE09":"2024-01-03","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":95,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":77,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-10-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2luZw==","RATING":""} |  |  |  | PHASE08 | 2023-09-29 | 2023-10-29 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000110166 | 23830 |  | 2282.09 |  | 0 | 0 |  | 0 |  | 0
90000671 | Absa Botshabelo - Installation of Outdoo | Absa Botshabelo - Installation of Outdoo |  |  | Region 3 | [5 empty] | 2023-11-02 |  |  | ASP-CR0492 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-02 | 2023-12-02 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000672 | Absa Bloemfontein - Install of TV Screen | Absa Bloemfontein - Install of TV Screen |  |  | Region 3 |  | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein |  | 2023-09-29 |  |  | ASP-CR0493 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-01 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 8726.59 |  | {"MANDT":"111","REFERENCE":90000672,"ONEVIEW":"Unknown","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-10-29","DATE08":"2023-11-19","DATE09":"2024-01-03","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-10-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjdXJyZW50bHkgaW4gcHJvZ3Jlc3MsIEVUQyAyNyBTZXAg","RATING":""} |  |  | C000109954 | PHASE12 | 2023-09-29 | 2023-10-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-09-12 | 7588.34 | 0 |  |  | C000109954 | 7588.34 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000673 | Irene ATM room vinyl tile replacement | Irene ATM room vinyl tile replacement |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-09-04 | 2023-10-06 |  | ASP-GN0229 | CRTD SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-09-04 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000673,"ONEVIEW":"22491X","DATE01":"2023-06-26","DATE02":"2023-07-03","DATE03":"2023-07-24","DATE04":"2023-07-31","DATE05":"2023-08-21","DATE06":"2023-09-04","DATE07":"2023-10-06","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":15,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-04","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiDigJMgUHJvamVjdCByb2xsIG92ZXIgKFIgMTcgMDAwLjAwKS4=","RATING":""} |  |  |  | PHASE12 | 2023-09-04 | 2023-10-06 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000674 | Wonderpark Service Desk & x2 Chairs | Wonderpark Service Desk & x2 Chairs |  |  | Region 1 |  | 76677X | 1000-70308-01 | Wonderpark Shopping Centre-Cnr Heinrich Ave & Brits Rd-Pretoria |  | 2023-09-04 | 2023-10-06 |  | ASP-GN0230 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-09-04 | D | 181447.51 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000674,"ONEVIEW":"76677X","DATE01":"2023-06-26","DATE02":"2023-07-03","DATE03":"2023-07-24","DATE04":"2023-07-31","DATE05":"2023-09-21","DATE06":"2023-10-16","DATE07":"2023-10-21","DATE08":"2023-11-11","DATE09":"2023-12-26","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"188:7:21:7:52:25:5:21:45:20","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-16","FORECAST_END":"2023-10-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIEF3YWl0aW5nIFBPJ3MuIFBvc3NpYmxlIGZpbmFuY2lhbCByb2xsb3Zlci4=","RATING":""} |  |  | C000119221 | PHASE07 | 2023-10-16 | 2023-10-21 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-10-26 | 157780.45 | 0 |  |  | C000119221 | 157780.45 |  | 16431.59 |  | 0 | 0 |  | 0 |  | 0
90000675 | Silverton Minor Works | Silverton Minor Works |  |  | Region 1 | Gauteng North | 21242X | 1000-70020-01 | Silverton-De Boulevard St-Pretoria | N | 2023-04-05 |  |  | ASP-GN0231 | CRTD: |  | false | false |  |  |  |  | 2023 |  | L |  | GAMIETR | 2023-09-04 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000675,"ONEVIEW":"","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-04-05 | 2023-05-05 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000676 | Various Sites Catering Equipment | Various Sites Catering Equipment |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-09-04 | 2023-10-04 |  | ASP-GS0741 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-09-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-04 | 2023-10-04 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000677 | Various Sites Hot Trays | Various Sites Hot Trays |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-09-04 | 2023-10-04 |  | ASP-GS0742 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-09-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-09-04 | 2023-10-04 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000678 | Towers West Replace Exco Decks | Towers West Replace Exco Decks |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-09-04 | 2023-10-06 |  | ASP-GS0743 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-09-04 | D | 82810.72 |  | 100 | 2023-09-12 | 2023-09-12 | 82810.72 |  | {"MANDT":"111","REFERENCE":90000678,"ONEVIEW":"21526X","DATE01":"2023-06-26","DATE02":"2023-08-29","DATE03":"2023-09-19","DATE04":"2023-09-26","DATE05":"2023-09-26","DATE06":"2023-11-30","DATE07":"2023-12-08","DATE08":"2023-12-29","DATE09":"2024-02-12","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"188:64:21:7:0:65:8:21:45:14","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-30","FORECAST_END":"2023-12-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VwcGxpZXIgaW4gbWFudWZhY3R1cmluZyB0byBzdGFydCBpbnN0YWxsYXRpb24gb24gdGhlIDMwdGggTm92","RATING":""} |  |  | C000110195 | PHASE08 | 2023-11-30 | 2023-12-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 72009.32 | 0 |  |  | C000110195 | 65463.02 |  | 7528.25 |  | 0 | 0 |  | 0 |  | 0
90000679 | Absa Bank Hopetown - Painting of the Doo | Absa Bank Hopetown - Painting of the Doo |  |  | Region 3 |  | 78645X | 1000-71353-01 | Hopetown-Cnr Widd & Kerk St-Hopetown |  | 2023-09-08 |  |  | ASP-CR0494 | CLSD BUDG ISBD AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 4676.36 |  | 100 |  |  | 4676.36 |  | {"MANDT":"111","REFERENCE":90000679,"ONEVIEW":"78645X","DATE01":"2023-06-30","DATE02":"2023-07-07","DATE03":"2023-07-28","DATE04":"2023-08-04","DATE05":"2023-08-25","DATE06":"2023-09-08","DATE07":"2023-10-08","DATE08":"2023-10-29","DATE09":"2023-12-13","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":65,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-08","FORECAST_END":"2023-10-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2luZzsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  |  | PHASE11 | 2023-09-08 | 2023-10-08 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000109030 | 8510 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000680 | Absa Kimberley RHO - Replace burst geyse | Absa Kimberley RHO - Replace burst geyse |  |  | Region 3 |  | 78326X | 1000-71347-01 | Jan Kempdorp-De La Rey St-Jan Kempdorp |  | 2023-09-08 |  |  | ASP-CR0495 | CLSD BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000680,"ONEVIEW":"Unknown","DATE01":"2023-06-30","DATE02":"2023-07-07","DATE03":"2023-07-28","DATE04":"2023-08-04","DATE05":"2023-08-25","DATE06":"2023-09-08","DATE07":"2023-10-08","DATE08":"2023-10-29","DATE09":"2023-12-13","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-08","FORECAST_END":"2023-10-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhd2FpdGluZyBDQiBhcHByb3ZhbDsgRmluYW5jaWFsIFJvbGxvdmVy","RATING":""} |  |  |  | PHASE11 | 2023-09-08 | 2023-10-08 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000109031 | 8510 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000681 | Absa Jan Kempdorp - Replace Copper Pipes | Absa Jan Kempdorp - Replace Copper Pipes |  |  | Region 3 |  | 78326X | 1000-71347-01 | Jan Kempdorp-De La Rey St-Jan Kempdorp |  | 2023-09-08 |  |  | ASP-CR0496 | CLSD BUDG ISBD AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 5853.5 |  | 100 |  |  | 5853.5 |  | {"MANDT":"111","REFERENCE":90000681,"ONEVIEW":"Unknown","DATE01":"2023-06-30","DATE02":"2023-07-07","DATE03":"2023-07-28","DATE04":"2023-08-04","DATE05":"2023-08-25","DATE06":"2023-09-08","DATE07":"2023-10-08","DATE08":"2023-10-29","DATE09":"2023-12-13","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":95,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-08","FORECAST_END":"2023-10-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZWQsIGF3YWl0aW5nIGludm9pY2luZw==","RATING":""} |  |  |  | PHASE11 | 2023-09-08 | 2023-10-08 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000109030 | 8510 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000682 | Demountable Bank Unit -Aircon Installati | Demountable Bank Unit -Aircon Installati |  |  | Region 3 |  | Unknown | 1000-71311-01 | Unknown Building - not in our database |  | 2023-09-08 |  |  | ASP-CR0497 | CLSD BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE11 | 2023-09-08 | 2023-10-08 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000109028 | 43489 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000683 | Absa Northam Plaza - Installation of Wat | Absa Northam Plaza - Installation of Wat |  |  | Region 3 |  | 79124X | 1000-70554-01 | Northam Plaza-Cnr Rustenburg Rd & R510-Thabazimbi |  | 2023-11-23 |  |  | ASP-LP0177 | REL RESA SETC: |  | false | false |  | Justice Mogadime |  | Costing in progress | 2023 |  | L |  | NOMNGANGAL | 2023-09-05 | D | 0 |  | 15 |  |  | 0 | Project LL approval Pending - Absa Official Letter Head Request | {"MANDT":"111","REFERENCE":90000683,"ONEVIEW":"79124X","DATE01":"2023-09-14","DATE02":"2023-09-21","DATE03":"2023-10-12","DATE04":"2023-10-19","DATE05":"2023-11-09","DATE06":"2023-11-23","DATE07":"2023-12-23","DATE08":"2024-01-13","DATE09":"2024-02-27","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":5,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-23","FORECAST_END":"2023-12-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Tm8gTEwgYXBwcm92YWwgcmVjZWl2ZWQ=","RATING":""} |  |  |  | PHASE00 | 2023-11-23 | 2023-12-23 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000684 | Absa Thulamahashe - DILAPS | Absa Thulamahashe - DILAPS |  |  | Region 3 |  | 79265X | 1000-70559-01 | Thulamahashe Plaza-Main Rd-Phalaborwa |  | 2023-11-02 |  |  | ASP-LP0178 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 0 |  | 1 |  |  | 0 | Project duplicated - may be cancelled | {"MANDT":"111","REFERENCE":90000684,"ONEVIEW":"79265X","DATE01":"2023-08-24","DATE02":"2023-08-31","DATE03":"2023-09-21","DATE04":"2023-09-28","DATE05":"2023-10-01","DATE06":"2023-10-06","DATE07":"2023-11-01","DATE08":"2023-11-30","DATE09":"2023-12-29","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":60,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":5,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-06","FORECAST_END":"2023-11-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RmluYW5jaWFsIFJvbGxvdmVyCkNvc3RpbmcgcmVxdWVzdGVkIGZvciBCQyBwcmVwYXJhdGlvbg==","RATING":""} |  |  |  | PHASE12 | 2023-10-06 | 2023-11-01 | NANDE MAQUBELA | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000685 | Absa Blouberg Mall - Water Tanks | Absa Blouberg Mall - Water Tanks |  |  | Region 3 |  | 22539X | 1000-70473-01 | Blouberg Mall-Blouberg Rd-Bochum |  | 2023-11-29 |  |  | ASP-LP0179 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-09-05 | D | 0 |  | 1 |  |  | 0 | Project Cancelled - LL Approval declined | {"MANDT":"111","REFERENCE":90000685,"ONEVIEW":"22539X","DATE01":"2023-09-20","DATE02":"2023-09-04","DATE03":"2023-09-11","DATE04":"2023-09-04","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":20,"PROG03":100,"PROG04":10,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"RGVjbGluZWQgYnkgTEwsIFJQTSB0byB1cGRhdGUgUmVnaW9u","RATING":""} |  |  |  | PHASE12 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000686 | Absa Kamaqhekeza - Install of New water | Absa Kamaqhekeza - Install of New water |  |  | Region 3 | Mpumalanga | 77571X | 1000-70637-01 | Kamaqhekeza Plaza-Main Rd-Balfour | N | 2023-11-23 |  |  | ASP-MP0171 | REL AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L | 2022-01-30 | NOMNGANGAL | 2023-09-05 | D | 85571.03 |  | 20 | 2023-09-14 |  | 34748.83 | Project to be processed OOC | {"MANDT":"111","REFERENCE":90000686,"ONEVIEW":"77571X","DATE01":"2023-09-14","DATE02":"2023-09-04","DATE03":"2023-09-05","DATE04":"2023-09-14","DATE05":"2023-09-14","DATE06":"2023-09-14","DATE07":"2023-09-22","DATE08":"2023-10-06","DATE09":"2023-10-30","DATE10":"2023-10-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-14","FORECAST_END":"2023-09-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VibWl0dGVkIGFzIE9PQyBhcHByb3ZhbCBwcm9jZXNz","RATING":""} |  |  | C000111234 | PHASE08 | 2023-09-14 | 2023-09-22 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-09-18 | 30216.37 | 0 |  |  |  | 0 |  | 7233.73 |  | 0 | 0 |  | 0 |  | 0
90000687 | Absa Ingwe Mall - Teller Closure | Absa Ingwe Mall - Teller Closure |  |  | Region 3 |  | 37008X | 1000-70592-01 | Ingwe Mall-Impala St-Malelane |  | 2023-11-23 |  |  | ASP-MP0172 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 12682.2 | Closure of unused teller counter with contra Vision vinyl | 100 | 2023-09-08 | 2023-09-14 | 12682.2 |  | {"MANDT":"111","REFERENCE":90000687,"ONEVIEW":"Unknown","DATE01":"2023-09-14","DATE02":"2023-09-21","DATE03":"2023-10-12","DATE04":"2023-10-19","DATE05":"2023-11-09","DATE06":"2023-11-23","DATE07":"2023-12-23","DATE08":"2024-01-13","DATE09":"2024-02-27","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":10,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-23","FORECAST_END":"2023-12-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000110983 | PHASE11 | 2023-09-25 | 2023-10-06 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-09-15 | 12682.2 | 0 |  |  | C000110983 | 11028 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000688 | Absa Piet Retief - DILAPS | Absa Piet Retief - DILAPS |  |  | Region 3 |  | 77121X | 1000-70610-01 | Absa Piet Retief-Church St-Piet Retief |  | 2023-11-15 |  |  | ASP-MP0173 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-05 | D | 0 | Branch Revamp Dilapidations | 100 | 2023-09-28 | 2023-09-28 | 233196.69 |  | {"MANDT":"111","REFERENCE":90000688,"ONEVIEW":"77121X","DATE01":"2023-09-06","DATE02":"2023-09-13","DATE03":"2023-09-20","DATE04":"2023-09-20","DATE05":"2023-09-27","DATE06":"2023-09-28","DATE07":"2023-10-06","DATE08":"2023-10-20","DATE09":"2023-11-14","DATE10":"2023-11-30","DATE11":"2023-11-14","DATE12":"2023-11-14","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"55:7:7:0:7:1:8:14:25:0","PROGRESS":86,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-28","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIElpbiBwcm9ncmVzcyAKUHJvamVjdCBjb21wbGV0ZWQsIGludm9pY2VzIHJlcXVlc3RlZA==","RATING":""} |  |  | C000113390 | PHASE08 | 2023-09-28 | 2023-10-06 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-09-28 | 202779.73 | 68818.76 |  |  | C000145584 | 133960.97 |  | 20245.15 |  | 0 | 0 |  | 0 |  | 0
90000689 | Alice Lane South parking signs | Alice Lane South parking signs |  |  | Region 1 | Gauteng South | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton | N | 2023-09-06 | 2023-10-06 |  | ASP-GS0744 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | L | 2030-04-29 | GAMIETR | 2023-09-06 | D | 77959.42 |  | 100 | 2023-09-08 |  | 77959.42 |  | {"MANDT":"111","REFERENCE":90000689,"ONEVIEW":"35041X","DATE01":"2023-06-28","DATE02":"2023-07-05","DATE03":"2023-07-26","DATE04":"2023-08-02","DATE05":"2023-08-23","DATE06":"2023-09-06","DATE07":"2023-10-06","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":42,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-06","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UGVuZGluZyBSZWxlYXNlIG9mIFBPJ3M=","RATING":""} |  |  | C000110283 | PHASE08 | 2023-09-06 | 2023-10-06 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-09-13 | 67790.8 | 0 |  |  | C000110283 | 67790.8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000690 | Absa Towers West Exco Desks | Absa Towers West Exco Desks |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-09-06 | 2023-10-09 |  | ASP-GS0745 | CRTD SETC: |  | false | false |  | (Non PM) |  |  | 2023 |  | F |  | GAMIETR | 2023-09-06 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000690,"ONEVIEW":"21526X","DATE01":"2023-06-28","DATE02":"2023-07-05","DATE03":"2023-07-26","DATE04":"2023-08-02","DATE05":"2023-08-23","DATE06":"2023-09-06","DATE07":"2023-10-09","DATE08":"2023-10-30","DATE09":"2023-12-14","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-06","FORECAST_END":"2023-10-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCByZXBlYXRlZA==","RATING":""} |  |  |  | PHASE12 | 2023-09-06 | 2023-10-09 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000691 | Auckland Park CC Acoustic Consultant Fee | Auckland Park CC Acoustic Consultant Fee |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-09-06 | 2023-10-09 |  | ASP-GS0746 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  | F |  | GAMIETR | 2023-09-06 | D | 45502 |  | 100 | 2023-10-09 | 2023-09-09 | 45502 |  | {"MANDT":"111","REFERENCE":90000691,"ONEVIEW":"76849X","DATE01":"2023-06-28","DATE02":"2023-07-05","DATE03":"2023-07-26","DATE04":"2023-08-02","DATE05":"2023-08-23","DATE06":"2023-09-06","DATE07":"2023-10-09","DATE08":"2023-10-30","DATE09":"2023-12-14","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-06","FORECAST_END":"2023-10-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIFBoYXNlIDEgREQgUHJvamVjdCBjb21wbGV0ZSAmIEZpbmFsIFBPQyBQbGFubmVkIGZvciBlbmQgb2YgT2N0","RATING":""} |  |  | C000110282 | PHASE08 | 2023-09-06 | 2023-10-09 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-09-13 | 39566.96 | 0 |  |  | C000110282 | 39566.96 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000692 | 16A Central Avenue COC | Conduct a detailed investigation of the electrical infrastructure Compile a detailed list of remedial works Supply and install all the remedial work spares Test and commission Issue a Certificate of Compliance Material Leadtime: +-5 working days. Onsite timeline: 10 working days. |  |  | Region 1 |  | 37163X | 1000-77456-01 | Kempton Square | N | 2023-09-07 | 2023-10-06 |  | ASP-GN0232 | REL SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | L |  | GAMIETR | 2023-09-07 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 712123.13 | New Number created as this is ALP project ALP-GN0014 | {"MANDT":"111","REFERENCE":90000692,"ONEVIEW":"37163X","DATE01":"2023-08-14","DATE02":"2023-08-05","DATE03":"2023-08-26","DATE04":"2023-08-31","DATE05":"2023-09-26","DATE06":"2023-10-11","DATE07":"2023-10-12","DATE08":"2023-11-02","DATE09":"2023-12-17","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"170:-9:21:5:26:15:1:21:45:18","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-11","FORECAST_END":"2023-10-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VwcGxpZXIgc3RhcnRpbmcgd29yayBvbiB0aGUgMTIgT2N0b2JlciAyMDIzIGFuZCBlc3RpbWF0ZWQgY29tcGxldGlvbiBkYXRlIGlzIDNyZCBOb3ZlbWJlciAyMDIzIA==","RATING":""} |  |  | C000112435 | PHASE09 | 2023-10-11 | 2023-10-12 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-09-22 | 712123.13 | 0 |  |  | C000112435 | 619237.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000693 | Pretoria Campus Services of Golf Carts | Pretoria Campus Services of Golf Carts |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-09-08 | 2023-10-06 |  | ASP-GN0233 | CLSD BUDG RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-09-08 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 19765.63 |  | {"MANDT":"111","REFERENCE":90000693,"ONEVIEW":"22491X","DATE01":"2023-06-30","DATE02":"2023-07-07","DATE03":"2023-07-28","DATE04":"2023-08-04","DATE05":"2023-08-25","DATE06":"2023-09-08","DATE07":"2023-10-06","DATE08":"2023-10-27","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":81,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-08","FORECAST_END":"2023-10-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UEMgaXMgaGFuZGxpbmcu","RATING":""} |  |  | C000110990 | PHASE11 | 2023-09-08 | 2023-10-06 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-09-15 | 22730.47 | 0 |  |  | C000110990 | 17187.5 |  | 538 |  | 0 | 0 |  | 0 |  | 0
90000694 | Dobsonville- Hygiene survey | Dobsonville- Hygiene survey |  |  | Region 1 | Gauteng South | 77943X | 1000-70384-01 | Dobsonville Mall-Elias Motsoaledi Rd-Dobsonville | N | 2023-09-29 | 2023-12-15 |  | ASP-GS0747 | REL BUDG AVAC RESA SETC: |  | false | false |  | Lorri-Anne Louis |  |  | 2023 |  | L |  | LOUISR | 2023-09-11 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000694,"ONEVIEW":"36015X","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-09-29 | 2023-12-15 | LUCIA AMUNGA | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000129701 | 12974.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000695 | Pretoria Campus Acoustic Consultancy Fee | Pretoria Campus Acoustic Consultancy Fee |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2023-09-12 | 2023-10-13 |  | ASP-GN0234 | REL BUDG AVAC RESA SETC: |  | false | false |  | Phathutshedzo Neduvhuledza |  |  | 2023 |  |  |  | GAMIETR | 2023-09-12 | D | 14904 |  | 100 | 2023-09-11 | 2023-09-13 | 14904 |  | {"MANDT":"111","REFERENCE":90000695,"ONEVIEW":"22491X","DATE01":"2023-07-04","DATE02":"2023-07-11","DATE03":"2023-08-01","DATE04":"2023-08-08","DATE05":"2023-08-29","DATE06":"2023-09-12","DATE07":"2023-09-22","DATE08":"2023-10-31","DATE09":"2023-12-15","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"149:7:21:7:21:14:10:39:45:3","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-12","FORECAST_END":"2023-09-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMC8wMiAtIEREIFByb2plY3QgY29tcGxldGUgJiBGaW5hbCBQT0MgUGxhbm5lZCBmb3IgZW5kIG9mIE9jdC4=","RATING":""} |  |  | C000110285 | PHASE08 | 2023-09-12 | 2023-09-22 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 12960 | 0 |  |  | C000110285 | 12960 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000696 | Absa 32 Voortrekker - Demolish storeroom | Absa 32 Voortrekker - Demolish storeroom |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2023-10-02 | 2023-12-29 |  | ASP-WC0321 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-09-13 | D | 41776.65 |  | 100 | 2023-09-15 | 2023-09-18 | 41776.65 |  | {"MANDT":"111","REFERENCE":90000696,"ONEVIEW":"78126X","DATE01":"2023-09-04","DATE02":"2023-09-08","DATE03":"2023-09-15","DATE04":"2023-09-22","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2024-01-23","DATE08":"2024-02-13","DATE09":"2024-03-29","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:4:7:7:21:14:88:21:45:27","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2024-01-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgU2VwdCBWUCBTdXBwb3J0ZWQgc3VibWl0dGVkIHRvIHJlYWwgRXN0YXRlIGZvciBhcHByb3ZhbAoxMiBTZXB0IENvc3QgcGVuZGluZyBzdWJtaXNzaW9uIGZvciBhcHByb3ZhbA==","RATING":"Low"} |  |  | C000111232 | PHASE11 | 2023-09-28 | 2023-10-02 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-18 | 36327.52 | 0 |  |  | C000111232 | 36327.52 |  | 3750.15 |  | 0 | 0 |  | 0 |  | 0
90000697 | Absa Worcester - Insurance Claim - Replace vandalised Glass Window (Retrospective) | Absa Worcester - Insurance Claim - Replace vandalised Glass Window (Retrospective) |  |  | Region 2 | Western Cape | 78016X | 1000-70870-01 | Absa Worcester-Stockenstrom St-Worcester | N | 2023-05-30 | 2023-05-30 |  | ASP-WC0322 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | F |  | CEASARS | 2023-09-13 | D | 5630.98 |  | 100 | 2023-07-27 | 2023-07-27 | 5630.98 | 14 Sept Absa PO Received C000110559 POC to Follow Capex Insurance Requests approved at CB28 on 27.07.2023 | {"MANDT":"111","REFERENCE":90000697,"ONEVIEW":"78016X","DATE01":"2023-03-21","DATE02":"2023-03-28","DATE03":"2023-04-18","DATE04":"2023-04-25","DATE05":"2023-05-16","DATE06":"2023-05-30","DATE07":"2023-05-30","DATE08":"2023-06-20","DATE09":"2023-08-04","DATE10":"2023-08-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-05-30","FORECAST_END":"2023-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000110559 | PHASE11 | 2023-09-14 | 2023-09-14 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-14 | 4896.5 | 0 |  |  | C000110559 | 4896.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000698 | Meadowdale Boundary Wall and Clearview | Eastern Boundary Wall: 1. Introduction of horizontal soil anchors into the earth behind the retaining wall and guniting existing retaining wall system 2. Filling and compact the earth on the adjacent property to ensure a high gradient to discharge water. 3. Install 160mm radius weep holes spacing at 3 meter intervals to allow water to flow through the wall unhindered. 4. Cast a hard surface between the top of the retaining wall and boundary wall to minimise water ingress at this point and alleviate storm-water pressure. 5.Build concrete apron with a slope gradient to off-load on the lowest level of the ground on the Northern side. 6.Construct drainage system and manhole as per indications in the Structural Engineers report and drawings 7.Concrete foundation 600mm x 600 x 300mm deep with supporting piers and expansion joints, 8.Sub surface stormwater management. Southern Boundary Wall: 1. Demolish existing brickwall and cart-away rubble. 2.Trim back and remove existing trees within 1,5 meters of the boundary. 3. Erect Clearview fence support poles 2,1 meters apart and do civil works 4.Erect Mid-high Black powder coated Security Clearview fencing 80 meters long x 2,1 meters high . 5.Cast support concrete beam below to support structure and allow 160mm weep holes for drainage 5. Supply and install electrical fencing from ground to height of Clearview fence stretching 80 meters long, ensure communication reporting cable is installed underground including COC 6. Install electric beams at intervals along clearview fence 6. Reinstate existing paving and make good on completion. 7. Cart-away rubble and dispose as required. |  |  | Region 1 | Gauteng South | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale | N | 2023-09-13 | 2023-10-13 |  | ALP-GS0068 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-09-13 | D | 1329469 | Supported by Absa CRES FM VP | 60 | 2023-08-17 | 2023-08-23 | 1329469 | Project approved and BFM PO issued. | {"MANDT":"111","REFERENCE":90000698,"ONEVIEW":"37006X","DATE01":"2023-07-05","DATE02":"2023-07-12","DATE03":"2023-08-02","DATE04":"2023-08-09","DATE05":"2023-08-30","DATE06":"2023-09-13","DATE07":"2023-11-01","DATE08":"2023-11-22","DATE09":"2024-01-06","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"179:7:21:7:21:14:49:21:45:13","PROGRESS":18,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-13","FORECAST_END":"2023-11-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhcHByb3ZlZCBjb21waWxpbmcgV0EgJiBTRkEKQXBwcm92ZWQgYXQgQlRCIEF3YWl0aW5nIFdBIGFwcHJvdmFsIEJGTSBQTyB0byBiZSBpc3N1ZWQgaW4gdGhlIGludGVyaW0KUHJvamVjdCBwbGFubmVkIHN0YXJ0IGRhdGUgMS8xMS8yMDIzClBsYW5uZWQgY29tcGxldGlvbiBkYXRlLTMwLzExLzIwMjMKRnVsbHkgaW52b2ljZSB0aGlzIHllYXI=","RATING":"Medium"} |  |  | 400868637 | PHASE07 | 2023-09-13 | 2024-02-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-10-30 | 2023-09-07 |  |  | 2023-10-26 | 980071.1 | 0 |  |  | C000143992 | 1157392.17 |  | 115428.38 |  | 0 | 0 |  | 0 |  | 0
90000699 | Absa Tzaneen - HVAC Remedial Work | Absa Tzaneen - HVAC Remedial Work |  |  | Region 3 |  | 76808X | 1000-70526-01 | Danie Joubert Street Tzaneen-Danie Joubert St Tzaneen Hotel-Tzaneen |  | 2023-11-28 |  |  | ALP-LP0202 | CRTD AVAC RESA: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-13 | D | 447055.69 | HVAC Remediation due to underperformance | 100 | 2023-09-21 |  | 447055.69 |  | {"MANDT":"111","REFERENCE":90000699,"ONEVIEW":"76808X","DATE01":"2023-09-19","DATE02":"2023-09-26","DATE03":"2023-09-21","DATE04":"2023-09-15","DATE05":"2023-09-21","DATE06":"2023-09-28","DATE07":"2023-10-16","DATE08":"2023-11-16","DATE09":"2023-11-24","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-28","FORECAST_END":"2023-10-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBSb2xsb3ZlcgosY29zdGluZyBiZWluZyByZXZpZXdlZCBieSBlbmdpbmVlcmluZw==","RATING":""} |  |  |  | PHASE07 | 2023-10-19 | 2023-11-07 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000700 | Absa Rustenburg Plaza - Linking Gen to B | Absa Rustenburg Plaza - Linking Gen to B |  |  | Region 3 | [5 empty] | 2023-11-29 |  |  | ASP-CR0498 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-14 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000701 | Absa Britz Mall - Install of midwall Spl | Absa Britz Mall - Install of midwall Spl |  |  | Region 3 |  | Unknown | 1000-71601-01 | Unknown Building - not in our database |  | 2023-11-16 |  |  | ASP-CR0499 | REL BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-14 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000121831 | PHASE00 | 2023-11-16 | 2023-12-16 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-08 | 32590.58 | 0 |  |  | C000121831 | 32590.58 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000702 | Absa Rustenburg - Minor Works | Absa Rustenburg - Minor Works |  |  | Region 3 |  | Unknown | 1000-71273-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0500 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-14 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000121474 | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-06 | 17262.2 | 0 |  |  | C000121474 | 17262.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000703 | Absa Hoopstad - Waterproofing | Absa Hoopstad - Waterproofing |  |  | Region 3 |  | Unknown | 1000-71314-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0501 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-14 | D | 0 |  | 1 |  |  | 0 | See ASP-CR0467 | {"MANDT":"111","REFERENCE":90000703,"ONEVIEW":"Unknown","DATE01":"2023-01-13","DATE02":"2023-01-20","DATE03":"2023-02-10","DATE04":"2023-02-17","DATE05":"2023-03-10","DATE06":"2023-03-24","DATE07":"2023-04-23","DATE08":"2023-05-14","DATE09":"2023-06-28","DATE10":"2023-06-30","DATE11":"2023-06-28","DATE12":"2023-06-28","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:27","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-03-24","FORECAST_END":"2023-04-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U2VlIEFTUC1DUjA0Njc=","RATING":""} |  |  | C000119238 | PHASE12 | 2023-03-24 | 2023-04-23 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 84245.92 | 0 |  |  | C000119238 | 84245.92 |  | 8807.53 |  | 0 | 0 |  | 0 |  | 0
90000704 | Absa Butterworth - Replacement Generator | Absa Butterworth - Replacement Generator |  |  | Region 2 | Eastern Cape | 78501X | 1000-71048-01 | High Road Butterworth-Cnr High Rd & Bell St-Butterworth | N | 2023-09-15 | 2023-12-29 |  | ASP-EC0357 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-09-14 | D | 183558.03 |  | 100 | 2023-09-14 | 2023-09-15 | 183558.03 | 15 Sept Absa PO Received C000111033, BV PO's Requested 15 Sept Approval Received Absa PO Requested 14 Sept Cres Engineering OOC approval pending | {"MANDT":"111","REFERENCE":90000704,"ONEVIEW":"78501X","DATE01":"2023-07-07","DATE02":"2023-07-14","DATE03":"2023-08-04","DATE04":"2023-08-11","DATE05":"2023-09-01","DATE06":"2023-09-15","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-15","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000111033 | PHASE11 | 2023-09-27 | 2023-09-28 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-15 | 159615.68 | 0 |  |  | C000111033 | 159615.68 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000705 | Absa Odendaalsrus- Solar PV DD | Absa Odendaalsrus- Solar PV DD |  |  | Region 3 |  | 79056X | 1000-71599-01 | Absa Odendaalsrus-Odendaal St-Odendaalsrus |  | 2023-04-06 | 2023-09-29 |  | ASP-CR0502 | CLSD BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | CEASARS | 2023-09-15 | D | 35201.5 | Approved | 100 | 2023-09-20 | 2023-09-20 | 35201.5 |  | {"MANDT":"111","REFERENCE":90000705,"ONEVIEW":"79056X","DATE01":"2023-01-26","DATE02":"2023-02-02","DATE03":"2023-02-23","DATE04":"2023-03-02","DATE05":"2023-03-23","DATE06":"2023-04-06","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-06","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UmV0cm9zcGVjdGl2ZSBkdWUgZmluZGluZyBmb3IgYWxyZWFkeSBjb21wbGV0ZWQgZHVlIGRpbGlnZW5jZSBleGVyY2lzZS4=","RATING":"Low"} |  |  | C000112422 | PHASE11 | 2023-04-06 | 2023-09-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-09-28 | 30610 | 0 |  |  | C000112422 | 30610 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000706 | Absa Barkly East - COC Inspection Phase 1 | Absa Barkly East - COC Inspection Phase 1 - COC for Sale of Building |  |  | Region 2 | Eastern Cape | 78658X | 1000-71050-01 | Absa Barkly East-Cole St-Barkly East | N | 2023-10-02 | 2023-12-29 |  | ASP-EC0358 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-09-15 | D | 8981.5 |  | 100 | 2023-10-05 | 2023-10-09 | 8981.5 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000706,"ONEVIEW":"78658X","DATE01":"2023-09-07","DATE02":"2023-09-11","DATE03":"2023-09-28","DATE04":"2023-10-05","DATE05":"2023-10-09","DATE06":"2023-10-24","DATE07":"2023-10-24","DATE08":"2023-12-05","DATE09":"2024-01-19","DATE10":"2024-01-31","DATE11":"2023-12-25","DATE12":"2023-12-25","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"115:4:17:7:4:15:0:42:45:6","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-24","FORECAST_END":"2023-10-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBEZWMgUE9DIFN1Ym1pdHRlZCB0byBmaW5hbmNlIC0gUiA4IDE2NS4wMAozMCBOb3YgUE9DIHRvIGJlIHNlbnQgdG8gUmVhbCBFc3RhdGUgZm9yIGFwcHJvdmFsIC0gQ09DIFJlY2VpdmVkCjIzIE5vdiByZW1lZGlhbCB3b3JrcyBDb21wbGV0ZWQuIAoxNiBOb3YgUE0gdG8gZm9sbG93IHVwIG9uIHRoZSAxc3QgaW5zcGVjdGlvbiBpbnZvaWNlLiBPbnNpdGUgb24gMTYgTm92IGZvciByZW1lZGlhbCB3b3JrCjE1IE5vdiBSZW1lZGlhbCB3b3JrIGJlaW5nIGRvbmUgMTYgTm92CjYgTm92IC0gUE0gdG8gZm9sbG93IHVwIHdpdGggVmVuZG9yIHJlIENPQyAvIHJlcG9ydCAKMyBOb3YgLSBDb21wbGV0ZWQgLSBSZXBvcnQvQ09DIFBlbmRpbmcgUE0gRm9sbG93aW5nIFVwCjMwIE9jdCAtIFBNIHRvIGZvbGxvdyB1cCByZSBSZXBvcnQgLyBDT0MKMjYgT2N0IC0gU2l0ZSBpbnNwZWN0ZWQgMjR0aCAtIFJlcG9ydHMgcGVuZGluZwoyMyBPY3QgLSBQTSB0byBtYWtlIGFycmFuZ2VtZW50cyBmb3IgYnJhbmNoIHZpc2l0CjE5IE9jdCBCViBQTyBJc3N1ZWQgLSA0NTAwODY2NzI1IC0gU2ltYW55ZW5lCjEwIE9jdCBBYnNhIFBPIEMwMDAxMTU1ODQgUmVjZWl2ZWQgQlYgUE8gUmVxdWVzdGVkCjkgT2N0IEFwcHJvdmVkIGJ5IFJlYWwgRXN0YXRlIEFic2EgUE8gUmVxdWVzdGVkCjUgT2N0IFN1Ym1pdHRlZCB0byBDcmVzIEVuZyBGb3Igc3VwcG9ydCB0byBzdWJtaXQgdG8gUmVhbCBFc3RhdGUKMjggU2VwdCBTdWJtaXR0ZWQgdG8gUEUgZm9yIHJldmlldwoyMiBTZXB0IFF1b3RlcyByZWNlaXZlZCAtIEJDIHBhY2sgdG8gYmUgc3VibWl0dGVkCjEyIFNlcHQgUE0gdG8gb2J0YWluIFF1b3RlcyBmb3IgdGhlIEluc3BlY3Rpb25z","RATING":""} |  |  | C000115584 | PHASE11 | 2023-10-24 | 2023-10-24 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-10 | 7810 | 0 |  |  | C000115584 | 7810 |  | 816.5 |  | 0 | 816.5 | C000146630 | 8981.5 |  | 0 |  |  | 2024-03-04
90000707 | Absa Mossel Bay - COC Inspection Phase 1 | Absa Mossel Bay - COC Inspection Phase 1 - COC for Sale of Building |  |  | Region 2 | Eastern Cape | 77747X | 1000-70855-01 | Absa Mossel Bay-Marsh St-Mossel Bay | N | 2023-10-02 | 2023-12-29 |  | ASP-EC0359 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-09-15 | D | 10255.36 |  | 100 | 2023-10-05 | 2023-10-09 | 10255.36 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000707,"ONEVIEW":"77747X","DATE01":"2023-09-07","DATE02":"2023-09-11","DATE03":"2023-09-28","DATE04":"2023-10-05","DATE05":"2023-10-09","DATE06":"2023-10-31","DATE07":"2023-10-31","DATE08":"2024-01-23","DATE09":"2024-01-26","DATE10":"2024-02-26","DATE11":"2024-01-15","DATE12":"2024-01-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:4:17:7:4:22:0:84:3:23","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDYuMDIuMjAyNCBGTTogRmluYWwgUE9DIHJlY2VpdmVkLiAgMjAuMTEuMjAyMyBCaWxsZWQgMjYuMDEuMjAyNCBBYnNhIEN1dCBvZmYgMjYuMDIuMjAyNC4KCjIzIEphbiBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2UKMjIgSmFuIFBNIHRvIGZvbGxvdyB1cCBvbiB0aGUgc2lnbiBvZmYgb2YgdGhlIFBPQwoxNCBEZWMgQ09DIGNvbXBsZXRlZCwgRG9jdW1lbnQgdG8gYmUgZGVsaXZlcmVkIHRvIEVuZyBhbmQgb3JpZ2luYWwgdG8gQlYgT0hTCjExIERlYyBQTSB0byBzZW5kIFBPQyBmb3IgUmVhbCBFc3RhdGUgU2lnbm9mZgo3IERlYyAtIENvbXBsZXRlZCA2IE5vdiAtIFBPQyBQYWNrIHRvIGJlIHN1Ym1pdHRlZCBmb3IgU2lnbm9mZgo0IERlYyBSZW1lZGlhbCB3b3JrIGNvbXBsZXRlZCBDT0MgcGVuZGluZwoyOCBOb3YgdG8gYmUgc2VudCB0byBSZWFsIEVzdGF0ZSBmb3IgYXBwcm92YWwKMjMgTm92IFBNIHRvIHN1Ym1pdCBQT0MgZm9yIHNpZ25vZmYuIEJpZHZlc3QgRW5nIHdhaXRpbmcgb24gUE9zIGZvciByZXBhaXIgd29yawoxNiBOb3YgUE0gcmVxdWVzdGVkIEludm9pY2UgZnJvbSB2ZW5kb3IuIEJpZHZlc3QgRW5nIHRvIHJhaXNlIFBPIGZvciBSZXBhaXIgd29yawo2IE5vdiAtIEluc3BlY3Rpb24gY29tcGxldGVkIFJlcG9ydC9DT0MgcGVuZGluZwozIE5vdiAtIENvbXBsZXRlZCAtIFJlcG9ydC9DT0MgUGVuZGluZwozMSBPY3QgSW5zcGVjdGlvbiBDb25kdWN0ZWQKMzAgT2N0IC0gUGxhbm5lZCBmb3IgMzEgT2N0CjI2IE9jdCAtIERhdGVzIHRvIGJlIEFkdmlzZWQKMTcgT2N0IEJWIFBPIDQ1MDA4NjYwNzcgaXNzdWVkIC0gTmF0aW9uYWwgQUMKMTAgT2N0IEFic2EgUE8gQzAwMDExNTc4MiBSZWNlaXZlZCBCViBQTyBSZXF1ZXN0ZQo5IE9jdCBBcHByb3ZlZCBieSBSZWFsIEVzdGF0ZSBBYnNhIFBPIFJlcXVlc3RlZAo1IE9jdCBTdWJtaXR0ZWQgdG8gQ3JlcyBFbmcgRm9yIHN1cHBvcnQgdG8gc3VibWl0IHRvIFJlYWwgRXN0YXRlCjI4IFNlcHQgU3VibWl0dGVkIHRvIFBFIGZvciByZXZpZXcKMjIgU2VwdCBRdW90ZXMgcmVjZWl2ZWQgLSBCQyBwYWNrIHRvIGJlIHN1Ym1pdHRlZAoxMiBTZXB0IFBNIHRvIG9idGFpbiBRdW90ZXMgZm9yIHRoZSBJbnNwZWN0aW9ucw==","RATING":"Low"} |  |  | C000115782 | PHASE11 | 2023-10-31 | 2023-10-31 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-10 | 8917.7 | 0 |  |  | C000115782 | 8917.7 |  | 932.31 |  | 0 | 932.31 |  | 0 |  | 0
90000708 | Absa Uniondale - Solar PV DD (Retrospective Energy Submission) | Absa Uniondale - Solar PV DD (Retrospective Energy Submission) |  |  | Region 2 | Eastern Cape | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale | N | 2023-04-06 | 2023-09-29 |  | ASP-EC0360 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | F |  | CEASARS | 2023-09-15 | D | 35201.5 |  | 100 | 2023-09-13 | 2023-09-21 | 35201.5 | Approved Retrospective | {"MANDT":"111","REFERENCE":90000708,"ONEVIEW":"78140X","DATE01":"2023-09-14","DATE02":"2023-09-14","DATE03":"2023-09-14","DATE04":"2023-09-21","DATE05":"2023-09-21","DATE06":"2023-09-26","DATE07":"2023-09-26","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"108:0:0:7:0:5:0:24:45:30","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-26","FORECAST_END":"2023-09-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgT2N0IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQoxMCBPY3QgV2l0aCBBYnNhIEVORyBmb3IgU2lnbm9mZgozIE9jdCAtIEJWIFBPIElzc3VlZCA0NTAwODYzMTcyIC0gU2VtIFNvbHV0aW9ucwoyNiBTZXB0IEFic2EgUE8gUmVjZWl2ZWQgQzAwMDExMjczNyBWZW5kb3IgUE8gdG8gIGJlIHJlcXVlc3RlZAoyMiBTZXB0IFRhYmxlZCBmb3IgRW5lcmd5IGFzIHJldHJvc3BlY3RpdmUgYXMgREQgY29tcGxldGVkIGFuZCBzaXRlIGRlY2xpbmVkLiBBYnNhIFBPIHJlcXVlc3RlZAo=","RATING":"Low"} |  |  | C000112737 | PHASE11 | 2023-09-26 | 2023-09-26 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-09-26 | 30610 | 0 |  |  | C000112737 | 30610 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000709 | Absa Simphiwe Saldanha - Insurance Claim - HVAC Rapair Vandalism (Retrospective) | Absa Simphiwe Saldanha - Insurance Claim - HVAC Rapair Vandalism (Retrospective) |  |  | Region 2 | Western Cape | 77766X | 1000-70856-01 | Simphiwe Building-Saldanha Rd-Saldanha | N | 2023-06-15 | 2023-06-15 |  | ASP-WC0323 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-09-15 | D | 53895.33 |  | 100 | 2023-07-27 | 2023-07-27 | 53895.33 | 15 Sept Absa PO Requested Capex Insurance Requests approved at CB28 on 27.07.2023 | {"MANDT":"111","REFERENCE":90000709,"ONEVIEW":"77766X","DATE01":"2023-07-27","DATE02":"2023-07-27","DATE03":"2023-07-27","DATE04":"2023-08-03","DATE05":"2023-07-27","DATE06":"2023-07-27","DATE07":"2023-09-18","DATE08":"2023-10-09","DATE09":"2023-11-23","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":80,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:7:-7:0:53:21:45:11","PROGRESS":66,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-07-27","FORECAST_END":"2023-09-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgU2VwdCBBYnNhIFBPIFJlcXVlc3RlZApDYXBleCBJbnN1cmFuY2UgUmVxdWVzdHMgYXBwcm92ZWQgYXQgQ0IyOCBvbiAyNy4wNy4yMDIz","RATING":"Low"} |  |  | C000111237 | PHASE11 | 2023-07-27 | 2023-09-19 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-18 | 46865.5 | 0 |  |  | C000111237 | 46865.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000710 | Absa 32 Voortrekker Belliville - Insurance Claim - Water Pipes Stolen (Retrospective) | Absa 32 Voortrekker Belliville - Insurance Claim - Water Pipes Stolen (Retrospective) |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2023-03-11 | 2023-03-11 |  | ASP-WC0324 | CRTD AVAC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | F |  | CEASARS | 2023-09-15 | D | 49240.64 |  | 1 | 2023-07-27 | 2023-07-27 | 49240.64 | 26 Sept FM indicated was due to rusted pipe - BAU WO - On hold pending final clarification 23 Sept Work Order Pack outstanding from FM 19 Sept PC followed up as Docs still outstandin | {"MANDT":"111","REFERENCE":90000710,"ONEVIEW":"78126X","DATE01":"2023-07-27","DATE02":"2023-07-27","DATE03":"2023-07-27","DATE04":"2023-08-03","DATE05":"2023-07-27","DATE06":"2023-09-29","DATE07":"2023-09-29","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"188:0:0:7:-7:64:0:21:45:8","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-09-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjcgU2VwdCBTZW50IHRvIE1lcmluZGEgYW5kIENoZXJlc2UgdG8gY2FuY2VsbCBhcyBub3QgYW4gaW5zdXJhbmNlIGNsYWltLgoyNiBTZXB0IEZNIGluZGljYXRlZCB3YXMgZHVlIHRvIHJ1c3RlZCBwaXBlIC0gQkFVIFdPIC0gT24gaG9sZCBwZW5kaW5nIGZpbmFsIGNsYXJpZmljYXRpb24=","RATING":""} |  |  |  | PHASE06 | 2023-09-29 | 2023-09-29 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 42817.95 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000711 | Absa Victoria Rd Woodstock - Insurance Claim - Replace External Signage Theft (Retrospective) | Absa Victoria Rd Woodstock - Insurance Claim - Replace External Signage Theft (Retrospective) |  |  | Region 2 | Western Cape | 78104X | 1000-70883-01 | 264 Victoria Road-Victoria Rd-Woodstock | N | 2023-04-04 | 2023-04-04 |  | ASP-WC0325 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-09-15 | D | 27275.07 |  | 100 | 2023-07-27 | 2023-07-27 | 27275.07 | 15 Sept Absa PO Requested Capex Insurance Requests approved at CB28 on 27.07.2023 | {"MANDT":"111","REFERENCE":90000711,"ONEVIEW":"78104X","DATE01":"2023-07-27","DATE02":"2023-07-27","DATE03":"2023-07-27","DATE04":"2023-08-03","DATE05":"2023-07-27","DATE06":"2023-09-18","DATE07":"2023-09-18","DATE08":"2023-10-09","DATE09":"2023-11-23","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:7:-7:53:0:21:45:21","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-18","FORECAST_END":"2023-09-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgU2VwdCBBYnNhIFBPIFJlcXVlc3RlZApDYXBleCBJbnN1cmFuY2UgUmVxdWVzdHMgYXBwcm92ZWQgYXQgQ0IyOCBvbiAyNy4wNy4yMDIz","RATING":""} |  |  | C000111236 | PHASE11 | 2023-09-18 | 2023-09-19 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-09-18 | 23717.45 | 0 |  |  | C000111236 | 23717.45 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000712 | Absa Zeerust - Installation of Lift Plat | Absa Zeerust - Installation of Lift Plat |  |  | Region 3 |  | 21941X | 1000-71241-01 | Absa Zeerust-Cnr Church & President St-Zeerust |  | 2023-11-29 |  |  | ASP-CR0503 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-19 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 96704.88 |  | {"MANDT":"111","REFERENCE":90000712,"ONEVIEW":"Unknown","DATE01":"2023-09-20","DATE02":"2023-09-27","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000113079 | PHASE06 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-09-27 | 84091.2 | 0 |  |  | C000113079 | 84091.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000713 | Absa Dwarsloop - Installation of Rolldow | Absa Dwarsloop - Installation of Rolldow |  |  | Region 3 |  | 37198X | 1000-77509-01 | Dwarsloop Mall | N | 2023-10-30 |  |  | ASP-MP0174 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L | 2022-10-30 | NOMNGANGAL | 2023-09-19 | D | 34748.83 |  | 100 | 2023-09-07 | 2023-09-13 | 0 |  | {"MANDT":"111","REFERENCE":90000713,"ONEVIEW":"37198X","DATE01":"2023-08-21","DATE02":"2023-08-28","DATE03":"2023-09-18","DATE04":"2023-09-25","DATE05":"2023-10-16","DATE06":"2023-10-30","DATE07":"2023-10-13","DATE08":"2023-11-30","DATE09":"2023-12-11","DATE10":"2023-12-31","DATE11":"2023-12-11","DATE12":"2023-12-11","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":60,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"71:7:21:7:21:14:-17:48:11:0","PROGRESS":89,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-30","FORECAST_END":"2023-10-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFN1Ym1pdHRlZApwcm9qZWN0IGNvbXBsZXRlZCBpbnZvaWNlIHJlcXVlc3RlZA==","RATING":""} |  |  | C000111884 | PHASE11 | 2023-10-30 | 2023-10-13 | NANDE MAQUBELA | Thea Spamers | 0 |  |  |  |  | 2023-09-19 | 30216.37 | 0 |  |  | C000111884 | 30216.37 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000714 | Absa 31 Church Street Victoria West-Gen | Absa 31 Church Street Victoria West-Gen |  |  | Region 3 | [5 empty] | 2023-11-02 |  |  | ASP-CR0504 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-02 | 2023-12-02 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000715 | Absa Bloemhof - Install Midwall Split Un | Absa Bloemhof - Install Midwall Split Un |  |  | Region 3 |  | Unknown | 1000-71314-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0505 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-20 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000118464 | PHASE10 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-23 | 45513.06 | 0 |  |  | C000141158 | 45513.06 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000716 | Absa Calvinia - Waterproofing | Absa Calvinia - Waterproofing |  |  | Region 3 |  | Unknown | 1000-70869-01 | Unknown Building - not in our database |  | 2023-12-07 |  |  | ASP-CR0506 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-20 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000716,"ONEVIEW":"Unknown","DATE01":"2023-09-28","DATE02":"2023-10-05","DATE03":"2023-10-26","DATE04":"2023-11-02","DATE05":"2023-11-23","DATE06":"2023-12-07","DATE07":"2024-01-06","DATE08":"2024-01-27","DATE09":"2024-03-12","DATE10":"2024-03-31","DATE11":"2024-03-12","DATE12":"2024-03-12","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-07","FORECAST_END":"2024-01-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000119237 | PHASE10 | 2023-12-07 | 2024-01-06 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 306711.56 | 0 |  |  | C000119237 | 306711.56 |  | 182.92 |  | 0 | 0 |  | 0 |  | 0
90000717 | Absa Boitekong Mall - Replace Damaged Si | Absa Boitekong Mall - Replace Damaged Si |  |  | Region 3 |  | Unknown | 1000-71245-01 | Unknown Building - not in our database |  | 2023-10-12 |  |  | ASP-CR0507 | CLSD BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE11 | 2023-10-12 | 2023-11-11 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000112623 | 34450.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000718 | Absa Towers Main Lumen Sign Ropes Access | Absa Towers Main Lumen Sign Ropes Access |  |  | Region 1 |  | 78944X | 1000-71415-01 | ABSA TOWERS MAIN-Main St-Johannesburg |  | 2023-09-20 | 2023-10-20 |  | ASP-GS0748 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-09-20 | D | 0 | Approved | 100 | 2023-10-07 | 2023-10-07 | 72476.68 |  |  |  |  | C000112441 | PHASE07 | 2023-09-28 | 2023-09-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-09-22 | 72476.68 | 0 |  |  | C000112441 | 63023.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000719 | Absa Bloemfontein CBD- Minor Works | Absa Bloemfontein CBD- Minor Works |  |  | Region 3 |  | Unknown | 1000-71596-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0508 | REL BUDG AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-21 | D | 0 |  | 100 |  |  | 121086.72 |  | {"MANDT":"111","REFERENCE":90000719,"ONEVIEW":"","DATE01":"2023-09-20","DATE02":"2023-09-27","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000119246 | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 105021.15 | 0 |  |  | C000114115 | 105021.15 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000720 | Absa Moffett Office Park - Chiller Coils | Absa Moffett Office Park - Chiller Coils |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-11-01 | 2023-12-29 |  | ASP-EC0361 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-09-21 | D | 373180.68 |  | 100 | 2023-10-12 | 2023-10-26 | 373180.68 | Absa Ref - 240129_091 | {"MANDT":"111","REFERENCE":90000720,"ONEVIEW":"22937X","DATE01":"2023-09-29","DATE02":"2023-10-06","DATE03":"2023-10-12","DATE04":"2023-10-19","DATE05":"2023-10-26","DATE06":"2024-02-07","DATE07":"2024-03-12","DATE08":"2024-04-02","DATE09":"2024-05-17","DATE10":"2024-05-31","DATE11":"2024-05-17","DATE12":"2024-05-17","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"214:7:6:7:7:104:34:21:45:50:50:14","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-07","FORECAST_END":"2024-03-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgTWFyY2ggLSBJbnN0YWxsZWQgMTIgTWFyY2ggLSBVcGRhdGVkIGludm9pY2UgYW5kIFdhcnJhbnRlZSBEb2N1bWVudGF0aW9uIFJlcXVlc3RlZAoxMSBNYXJjaCBDb2lscyBkZWxpdmVyZWQgdG8gc2l0ZSB0byBhZGRyZXNzIHNuYWdzLCBpbnN0YWxsYXRpb24gdG8gYmUgY29tcGxldGVkIDEyIE1hcmNoCjI5IEZlYiB0byBiZSBpbnN0YWxsZWQgd2VlayBvZiAxMSBNYXJjaAoyNiBGZWIgLSBSZWNlaXZlZCAyMyBGZWIgaW4gZm9yIEJsdWNoZW0gdHJlYXRtZW50IC0gaW5zdGFsbCBkYXRlIHRvIGJlIGNvbmZpcm1lZAoyMiBGZWIgLSBOZXcgUmVwbGFjZW1lbnRzIGV4cGVjdGVkIGJ5IDIzIEZlYiAtIHRvIGJlIHNlbnQgZm9yIEJsdWNoZW0gKy0gMTAgZGF5cyAtIEluc3RhbGwgZGF0ZXMgdG8gYmUgY29uZmlybWVkCjE5IEZlYiBEYW1hZ2VkIGNvaWxzIGluc3RhbGxlZCByZXBsYWNlbWVudCBvZiBEYW1hZ2VkIGNvaWxzIHRvIGJlIGNvbmZpcm1lZAoxNSBGZWIgMiB4IENvaWxzIGFyZSBkYW1hZ2VkIGFuZCByZXF1aXJlIHJlcGxhY2VtZW50LiBQTSB0byBjb25maXJtIHRpbWVsaW5lcyBmcm9tIHRoZSB2ZW5kb3IgcmUgcmVwYWlyIHdvcmsKMTIgRmViIFNuYWdzIHRvIGJlIGFkZHJlc3NlZCAtIFRpbWVsaW5lcyB0byBiZSBwcm92aWRlZCBBU0FQCjA4IEZlYiBQcm9qZWN0IG9uZ29pbmcgYW5kIG9uIHRyYWNrCjUgRmViIC0gU3RhcnQgb24gU2l0ZSA3IEZlYiB0byAxMiBGZWIKMDEgRmViIFBNIHRvIGNvbmZpcm0gcGxhbm5lZCBzdGFydCBNb24gNSBGZWIKMjkgSmFuIERhdGVzIHRvIGJlIGNvbmZpcm1lZCBieSBzdXBwbGllciBpZiByZWNlaXZlZCAyNiBKYW4KMjUgSmFuIC0gUE0gdG8gZm9sbG93IHVwIHJlIGluc3RhbGxhdGlvbiBEYXRlcwoxOCBKYW4gRmluYWwgZGVsaXZlcnkgZGF0ZSB0byBiZSBjb25maXJtZWQKMTQgRGVjIFN0aWxsIG9uIHRyYWNrIGZvciBGZWIgSW5zdGFsbGF0aW9uIC0gSW1wb3J0aW5nIGZyb20gRnJhbmNlCjI3IE5vdiAtIE9uIFRyYWNrIC0gUE0gdG8gZm9sbG93IHVwIHJlIGRlbGl2ZXJ5IG9mIENoaWxsZXJzIAoxNiBOb3YgQ2hpbGxlcnMgb24gT3JkZXIgVmVuZG9yIHRvIGNvbmZpcm0gZmluYWwgZXhwZWN0ZWQgaW5zdGFsbGF0aW9uIGRhdGVzLiBJbnN0YWxsYXRpb24gZGF0ZSBUQkMgb25jZSBjaGlsbGVycyBhcnJpdmUgaW4gdGhlIGNvdW50cnkuCjkgTm92IC0gVmVuZG9yIGZlZWRiYWNrIHBlbmRpbmcgYXMgdGhleSBxdWVyeWluZyBzb21lIHByZXZpb3VzIGludm9pY2VzIG91dHN0YW5kaW5nCjYgTm92IFBPIHNoYXJlZCB3aXRoIFZlbmRvciwgZm9sbG93IHVwIHJlIG1ldGhvZCBzdGF0ZW1lbnRzIGFuZCBleHBlY3RlZCBkZWxpdmVyeS9JbnN0YWxsYXRpb24gZXRjLi4gCjEgTm92IEJWIFBPIElzc3VlZCA0NTAwODY5NjA1IC0gQ2FycmllciBTQSAoUHR5KSBMdGQgCjMxIE9jdCBCViBQTyBmb2xsb3dlZCB1cCBhbmQgcmUgcmVxdWVzdGVkCjI3IE9jdCBBYnNhIFBPIFJlY2VpdmVkIEMwMDAxMTk0NzAgQlYgUE8gUmVxdWVzdGVkCjI2IE9jdCBBcHByb3ZlZCwgU2lnbmVkIERlY2sgUGVuZGluZyBpbiBvcmRlciB0byByZXF1ZXN0IEFic2EgUE8gCjIzIE9jdCBXYXJyYW50ZWUgRG9jIHJlY2VpdmVkIGFkZCB0byBDQjQxCjIzIE9jdCBQTSB0byBmb2xsb3cgdXAgcmUgV2FycmFudGVlIERPQyB0byBiZSBpbmNsdWRlZCBpbiBDQjQxCjE5IE9jdCBGZWVkYmFjayBwZW5kaW5nIHJlIFdhcnJhbnR5IEluZm8gaW4gdGVybXMgb2YgdGhlIENvaWxzCjE2IE9jdCBGZWVkYmFjayBQZW5kaW5nIGZyb20gVmVuZG9yIHJlIFJhdGVzIGFuZCBhZGRpdGlvbmFsIGluZm8gcmVxdWVzdGVkCjEyIE9jdCBTZW50IGZvciBPT0MgYXBwcm92YWwgYW5kIEZpbmFuY2UgQXBwcm92YWwKMTEgT2N0IC0gQkMgdG8gYmUgY29tcGxldGVkIDExIE9jdCB0byBzdWJtaXQgdG8gQWJzYSBmb3IgT09DCjUgU2VwdCAtIFByZiBSZWNlaXZlZCwgU1NKIHRvIGNvbXBsZXRlZCBCQyB0byBiZSBzdWJtaXR0ZWQgZm9yIE9PQyBhcHByb3ZhbC4gKy0gMTIgV2VlayBMZWFkIHRpbWUKMjAgU2VwdCBBcHByb3ZlZCBQUkYgYW5kIEZ1bmRpbmcgUGVuZGluZyAtIFBvdGVudGlhbCBGaW5hbmNpYWwgb3IgUHJvamVjdCBSb2xsb3ZlciBiYXNlZCBvbiBsZWFkIHRpbWVzdGltZXM=","RATING":"Medium"} |  |  | C000119470 | PHASE09 | 2024-02-07 | 2024-03-12 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-27 | 324504.94 | 0 |  |  | C000119470 | 324504.94 |  | 30789.5 |  | 0 | 30789.5 |  | 0 |  | 0
90000721 | Absa Central Square Dutywa - SBV Door | Absa Central Square Dutywa - SBV Door |  |  | Region 2 | Eastern Cape | 35033X | 1000-70958-01 | Central Square-Richardson Rd-Idutywa | N | 2023-11-01 | 2023-12-29 |  | ASP-EC0362 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-09-21 | D | 0 |  | 1 |  |  | 0 | Absa Ref : ??????? Retail Reprioritised | {"MANDT":"111","REFERENCE":90000721,"ONEVIEW":"35033X","DATE01":"2023-09-21","DATE02":"2023-11-28","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-11","DATE06":"2024-06-01","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"2024-05-07","DATE12":"2024-05-07","PROG01":0,"PROG02":100,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"253:68:122:7:6:51:29:21:45:24","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgRmViIC0gTm8gRHJhd2luZ3MgcmVjZWl2ZWQgdG8gZGF0ZSBmcm9tIEVCCjE5IEZlYiBObyBEcmF3aW5ncyByZWNlaXZlZCB0byBkYXRlIGZyb20gRUIKNSBGZWIgLSBEcmF3aW5ncyBwZW5kaW5nIGZyb20gUGxhbm5lciArIFVwZGF0ZWQgUmVxdWVzdAoyOCBKYW4gRHJhd2luZ3Mgc3RpbGwgcGVuZGluZyAtIEZyb250IERvb3JzCjIyIEphbiAtIERyYXdpbmdzIG91dHN0YW5kaW5nIGZyb20gRUIKMTQgRGVjIERyYXdpbmdzIHBlbmRpbmcgZnJvbSBFQgoyNyBOb3YgLSBVcGRhdGVkIGZsb29yIHBsYW4gcGVuZGluZyBmb3IgZHJhd2luZwoyMyBPY3QgLSBQTSB3ZW50IHRvIHNpdGUgdG8gSW5zcGVjdGVkIGRvb3JzLCBhbGwgb3BlcmF0aW9uYWwgUE0gdG8gZm9yd2FyZCBtYWlsIHJlIGRpc2N1c3Npb24gd2l0aCBBZnJpY2EgU2VjdXJpdHkgYW5kIGRyYXdpbmdzIGZvciBuZXcgTWFudHJhcCBEb29yCjExIE9jdCAtIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEVuZ2luZWVyaW5nLCBQTSB0byB2aXNpdCAyMCBPY3QKMjIgU2VwdCAtIEVuZ2luZWVyaW5nIHRvIHZpc2l0IGFuZCBhZHZpc2Ugb24gdGhlIGRvb3JzIGFuZCB0aGUgcmVxdWlyZW1lbnRzIHRvIHJlbWVkaWF0ZSBQb3RlbnRpYWwgUm9sbCBPdmVyIEZpbmFuY2lhbCBpZiBQcm9jZWVkcwoyMSBTZXB0IENvbmZpcm1lZCB0aGF0IHRoZSBCcmFuY2hlcyBsZWFzZSBoYXMgYmVlbiByZW5ld2VkIGZvciAzIFllYXJzIGRvb3JzIHRvIGJlIGFkZHJlc3NlZCB1cmdlbnRseSBiYXNlZCBvbiBwcmV2aW91c2x5IGFwcHJvdmVkIFBSRg==","RATING":""} |  |  |  | PHASE12 | 2024-06-01 | 2024-06-30 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000722 | Absa Albertinia - Dilaps Disposal Inspec | Absa Albertinia - Dilaps Disposal Inspec |  |  | Region 2 | Eastern Cape | 77688X | 1000-71033-01 | Absa Albertinia-Hoof St-Albertinia | N | 2023-10-13 | 2023-12-29 |  | ASP-EC0363 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-09-22 | D | 9295.73 |  | 100 | 2023-10-05 | 2023-10-09 | 9295.73 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000722,"ONEVIEW":"77688X","DATE01":"2023-09-21","DATE02":"2023-09-21","DATE03":"2023-09-28","DATE04":"2023-10-05","DATE05":"2023-10-09","DATE06":"2023-11-02","DATE07":"2023-11-02","DATE08":"2023-12-19","DATE09":"2024-02-02","DATE10":"2024-02-29","DATE11":"2024-01-15","DATE12":"2024-01-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"161:0:7:7:4:24:0:47:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-02","FORECAST_END":"2023-11-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRGVjIFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZQoxNCBEZWMgQ09DIGNvbXBsZXRlZCwgRG9jdW1lbnQgdG8gYmUgZGVsaXZlcmVkIHRvIEVuZyBhbmQgb3JpZ2luYWwgdG8gQlYgT0hTCjExIERlYyBQTSB0byBzZW5kIFBPQyBmb3IgUmVhbCBFc3RhdGUgU2lnbm9mZgo3IERlYyAtIFBNIHRvIGNvbmZpcm0gaWYgd29ya3MgY29tcGxldGVkCjQgRGVjIC0gUmVtZWRpYWwgd29ya3MgdG8gYmUgY29tcGxldGVkIDQgRGVjCjI4IE5vdiB0byBiZSBzZW50IHRvIFJlYWwgRXN0YXRlIGZvciBhcHByb3ZhbAoyMyBOb3YgUE0gdG8gc3VibWl0IHRoZSBQT0MgZm9yIHNpZ25vZmYuIEJpZHZlc3QgRW5nIHRvIHJhaXNlIFBPIGZvciByZXBhaXIgd29yawoxNiBOb3YgUE0gcmVxdWVzdGVkIEludm9pY2UgZnJvbSB2ZW5kb3IuIEJpZHZlc3QgRW5nIHRvIHJhaXNlIFBPIGZvciBSZXBhaXIgd29yawo2IE5vdiAtIEluc3BlY3Rpb24gY29tcGxldGVkIFJlcG9ydC9DT0MgcGVuZGluZwozIE5vdiAtIENvbXBsZXRlZCAtIFJlcG9ydC9DT0MgUGVuZGluZwoyIE5vdiBJbnNwZWN0aW9uIENvbmR1Y3RlZAoyIE5vdiAtIFdhcyByZXNjaGVkdWxlZCB0byB0aGUgMiBOb3YKMzAgT2N0IC0gUGxhbm5lZCBmb3IgMSBOb3YKMjYgT2N0IC0gRGF0ZXMgdG8gYmUgQWR2aXNlZAoyNCBPY3QgQlYgUE8gUmVjZWl2ZWQgNDUwMDg2NzUzNSBOYXRpb25hbCBBL0MKMjMgT2N0IEJWIFBPIG91dHN0YW5kaW5nCjEwIE9jdCBBYnNhIFBPIEMwMDAxMTU1OTUgUmVjZWl2ZWQgQlYgUE8gUmVxdWVzdGVkCjkgT2N0IEFwcHJvdmVkIGJ5IFJlYWwgRXN0YXRlIEFic2EgUE8gUmVxdWVzdGVkCjUgT2N0IFN1Ym1pdHRlZCB0byBDcmVzIEVuZyBGb3Igc3VwcG9ydCB0byBzdWJtaXQgdG8gUmVhbCBFc3RhdGUKMjggU2VwdCBTdWJtaXR0ZWQgdG8gUEUgZm9yIHJldmlldwoyMiBTZXB0IEZpbmFuY2lhbCBSb2xsb3ZlciAtIE9wZXgKMjEgU2VwdCBJZGVudGlmaWVkIGluIFJlYWwgRXN0YXRlIExpc3QgLSBDaGVjayByZXF1aXJlbWVudHMgd2l0aCBFbmdpbmVlcmluZyBmb3IgYW55IG90aGVyIHNlcnZpY2Vz","RATING":"Low"} |  |  | C000115595 | PHASE11 | 2023-11-02 | 2023-11-02 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-10 | 8083.24 | 0 |  |  | C000115595 | 8083.24 |  | 845.07 |  | 0 | 845.07 | C000146629 | 9295.73 |  | 0 |  |  | 2024-03-04
90000723 | Absa Towers West Relocate Multifaith roo | Absa Towers West Relocate Multifaith room |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-09-22 | 2023-10-22 |  | ASP-GS0749 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-09-22 | D | 0 |  | 40 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000723,"ONEVIEW":"21526X","DATE01":"2023-07-14","DATE02":"2023-07-21","DATE03":"2023-08-11","DATE04":"2023-08-18","DATE05":"2023-09-08","DATE06":"2023-09-22","DATE07":"2023-10-22","DATE08":"2023-11-12","DATE09":"2023-12-27","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-22","FORECAST_END":"2023-10-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgdGhlIFZQcyBhcHByb3ZhbA==","RATING":""} |  |  | C000121885 | PHASE08 | 2023-12-04 | 2023-12-11 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-08 | 354448.99 | 0 |  |  | C000121885 | 354448.99 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000724 | Absa Daveyton Replace external signage | Absa Daveyton Replace external signage |  |  | Region 1 | Gauteng | 78727X | 1000-70433-01 | Daveyton Shopping Centre-Eiselen St-Daveyton |  | 2023-09-22 | 2023-10-20 |  | ASP-GS0750 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-09-22 | D | 54326.8 |  | 100 | 2023-09-20 | 2023-09-28 | 54326.8 |  | {"MANDT":"111","REFERENCE":90000724,"ONEVIEW":"78727X","DATE01":"2023-07-14","DATE02":"2023-09-14","DATE03":"2023-09-18","DATE04":"2023-09-25","DATE05":"2023-09-28","DATE06":"2023-10-12","DATE07":"2023-11-09","DATE08":"2023-11-30","DATE09":"2024-01-14","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"170:62:4:7:3:14:28:21:45:6","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-12","FORECAST_END":"2023-11-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QXdhaXRpbmcgQkZNIFBPLgoxMjoxMDoyMyBBUyAtIEJGTSBQTyBpcyBpc3N1ZWQsIHNlbnQgdG8gYSBzdXBwbGllciB3YWl0aW5nIGZvciB0aW1lbGluZXMgb24gdGhlIGxlYWQtdGltZS4gIA==","RATING":"Low"} |  |  | C000115063 | PHASE10 | 2023-11-29 | 2023-12-13 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-10-06 | 47240.7 | 0 |  |  | C000115063 | 47240.7 |  | 4853.7 |  | 0 | 0 |  | 0 |  | 0
90000725 | Absa Paarl - Dilaps Dispose Inspection | Absa Paarl - Dilaps Dispose Inspection |  |  | Region 2 | Western Cape | 77053X | 1000-70798-01 | Absa Paarl-Cnr Main & Nantes St-Paarl | N | 2023-10-13 | 2023-12-29 |  | ASP-WC0326 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-09-22 | D | 20220.62 |  | 100 | 2023-10-05 | 2023-10-09 | 20220.62 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000725,"ONEVIEW":"77053X","DATE01":"2023-09-21","DATE02":"2023-09-28","DATE03":"2023-10-05","DATE04":"2023-10-12","DATE05":"2023-10-09","DATE06":"2023-11-07","DATE07":"2023-11-10","DATE08":"2023-12-12","DATE09":"2024-01-26","DATE10":"2024-01-31","DATE11":"2024-01-15","DATE12":"2024-01-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"132:7:7:7:-3:29:3:32:45:16","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-07","FORECAST_END":"2023-11-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRGVjIEZpbmFsIFBPQyBTdWJtaXR0ZWQgUiAxODM4Mi4yOAo3IERlYyBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgdGhlIHJlbWVkaWFsIHdvcmtzIHJlcXVpcmVkCjQgRGVjIC0gSW52b2ljZSByZWNlaXZlZCBFbmcgdG8gYWR2aXNlIG9uIHRoZSByZXBhaXIgd29ya3MKMzAgTm92IC0gRW5naW5lZXJpbmcgdG8gYWR2aXNlIHJlIHJlbWVkaWFsIHdvcmtzCjcgTm92IEJpZHZlc3QgRW5nIHRvIGFkdmlzZQoyMyBOb3YgQmlkdmVzdCBFbmcgdG8gdmlzaXQgc2l0ZSBvbiAyNCBOb3YgdG8gdmVyaWZ5IHRoZSByZXBvcnQuIEJpZHZlc3QgRW5nIHRvIHJhaXNlIFBPIGZvciBQbHVtYmluZyByZXBhaXJzCjIwIE5vdiAtIEluc3BlY3Rpb24gcmVwb3J0IHN1Ym1pdHRlZCB0byBFbmdpbmVlcmluZyBmb3IgUmV2aWV3CjE2IE5vdiBFbmdpbmVlcmluZyB3aWxsIHJldmlldyB0aGUgaW5zcGVjdGlvbiByZXBvcnQgYW5kIGFkdmlzZSBhY2NvcmRpbmdseQo5IE5vdiBJbnNwZWN0aW9uIGNvbXBsZXRlZCBGaW5kaW5ncy9DT0MgcGVuZGluZwo2IE5vdiBBY2Nlc3MgY29uZmlybWVkIGZvciB0aGUgN3RoIGFuZCA4dGgKMTkgT2N0IFBsYW5uaW5nIGZvciB0aGUgN3RoIGFuZCA4dGggTm92CjEyIE9jdCBCViBQTyBJc3N1ZWQgNDUwMDg2NTIwMSBDYXBlIFdlc3QKMTAgT2N0IEFic2EgUE8gQzAwMDExNTU4MiBSZWNlaXZlZCBCViBQTyBSZXF1ZXN0ZWQKOSBPY3QgQXBwcm92ZWQgYnkgUmVhbCBFc3RhdGUgQWJzYSBQTyBSZXF1ZXN0ZWQKNiBPY3QgQ3JlcyBTdXBwb3J0ZWQgLSBTdWJtaXR0ZWQgdG8gUmVhbCBFc3RhdGUgZm9yIGFwcHJvdmFsCjUgT2N0IFN1Ym1pdHRlZCB0byBDcmVzIEVuZyBGb3Igc3VwcG9ydCB0byBzdWJtaXQgdG8gUmVhbCBFc3RhdGUKNSBPY3QgUXVvdGVzIHJlY2VpdmVkIEJDJ3MgdG8gYmUgc2hhcmVkIHRvZGF5CjIyIFNlcHQgRmluYW5jaWFsIFJvbGxvdmVyIC0gT3BleAoyMSBTZXB0IElkZW50aWZpZWQgaW4gUmVhbCBFc3RhdGUgTGlzdCAtIENoZWNrIHJlcXVpcmVtZW50cyB3aXRoIEVuZ2luZWVyaW5nIGZvciBhbnkgb3RoZXIgc2VydmljZXM=","RATING":"Low"} |  |  | C000115582 | PHASE11 | 2023-11-07 | 2023-11-10 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-10 | 17583.15 | 0 |  |  | C000115582 | 17583.15 |  | 1838.24 |  | 0 | 1838.24 |  | 0 |  | 0
90000726 | Absa Lepelle Crossing -Linking Equipment | Absa Lepelle Crossing -Linking Equipment |  |  | Region 3 | [5 empty] | 2023-10-27 |  |  | ASP-LP0180 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-26 | D | 0 |  | 100 |  |  | 7.15 |  | {"MANDT":"111","REFERENCE":90000726,"ONEVIEW":"","DATE01":"2023-08-18","DATE02":"2023-08-25","DATE03":"2023-09-15","DATE04":"2023-09-22","DATE05":"2023-10-13","DATE06":"2023-10-27","DATE07":"2023-11-26","DATE08":"2023-12-17","DATE09":"2024-01-31","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-27","FORECAST_END":"2023-11-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-10-27 | 2023-11-26 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000727 | Absa Thulamahashe Plaza - Dilaps | Absa Thulamahashe Plaza - Dilaps |  |  | Region 3 |  | 79265X | 1000-70559-01 | Thulamahashe Plaza-Main Rd-Phalaborwa |  | 2023-10-26 |  |  | ASP-LP0181 | CRTD RESA: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-09-26 | D | 251899.6 |  | 40 | 2023-10-27 |  | 251899.6 | BC Submitted for approval | {"MANDT":"111","REFERENCE":90000727,"ONEVIEW":"79265X","DATE01":"2023-08-17","DATE02":"2023-08-24","DATE03":"2023-09-14","DATE04":"2023-09-21","DATE05":"2023-10-12","DATE06":"2023-10-26","DATE07":"2023-11-25","DATE08":"2023-12-16","DATE09":"2024-01-30","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-26","FORECAST_END":"2023-11-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UkZRIHRvIGNsb3NlIFR1ZXNkYXkgMTcgT2N0","RATING":""} |  |  |  | PHASE08 | 2023-10-26 | 2023-12-21 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000728 | Absa Piet Retief -Building Facade & Back | Absa Piet Retief -Building Facade & Back |  |  | Region 3 | [5 empty] | 2023-11-03 |  |  | ALP-MP0207 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-09-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-03 | 2023-12-03 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000729 | 270 Republic Road Replacement of generat | 270 Republic Road Replacement of generat |  |  | Region 1 | Gauteng | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-04-05 |  |  | ASP-GS0751 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | GAMIETR | 2023-09-28 | D | 123681.17 |  | 100 | 2023-09-20 | 2023-09-29 | 123681.17 |  | {"MANDT":"111","REFERENCE":90000729,"ONEVIEW":"21335X","DATE01":"2023-01-25","DATE02":"2023-09-11","DATE03":"2023-09-15","DATE04":"2023-09-19","DATE05":"2023-09-28","DATE06":"2023-11-13","DATE07":"2023-12-13","DATE08":"2024-01-03","DATE09":"2024-02-17","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":60,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"371:229:4:4:9:46:30:21:45:15","PROGRESS":14,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-13","FORECAST_END":"2023-12-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDY6MTA6MjMgQVM6IEJGTSBQTyByZWNlaXZlZCBhbmQgc2VudCB0byB0aGUgc3VwcGxpZXIgYW5kIHRoZSBsZWFkIHRpbWUgZm9yIHRoZSBiYXR0ZXJpZXMgaXMgNCB3ZWVrcy4=","RATING":""} |  |  | C000113624 | PHASE11 | 2023-11-13 | 2023-11-14 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-09-29 | 107548.84 | 0 |  |  | C000113624 | 107548.84 |  | 11198.47 |  | 0 | 0 |  | 0 |  | 0
90000730 | 268 Republic Road Generator Batteries | 268 Republic Road Generator Batteries |  |  | Region 1 | Gauteng | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2023-09-28 | 2023-10-27 |  | ASP-GS0752 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | GAMIETR | 2023-09-28 | D | 20213.66 |  | 100 | 2023-09-28 | 2023-09-29 | 20213.66 |  | {"MANDT":"111","REFERENCE":90000730,"ONEVIEW":"21334X","DATE01":"2023-07-20","DATE02":"2023-07-27","DATE03":"2023-08-17","DATE04":"2023-08-24","DATE05":"2023-10-09","DATE06":"2023-11-13","DATE07":"2023-12-12","DATE08":"2024-01-02","DATE09":"2024-02-16","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:7:21:7:46:35:29:21:45:20","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-13","FORECAST_END":"2023-12-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IDk6MTA6MjAyMyBBUzogIEJGTSBpc3N1ZSBQTyByZWNlaXZlZCBhbmQgc2VudCB0byB0aGUgc3VwcGxpZXIgdGhlIGxlYWQgdGltZSBmb3IgdGhlIGJhdHRlcmllcyBpcyA0IHdlZWtzLiA=","RATING":"Low"} |  |  | C000113585 | PHASE11 | 2023-11-13 | 2023-11-16 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-09-29 | 17577.09 | 0 |  |  | C000113585 | 17577.09 |  | 1792.33 |  | 0 | 0 |  | 0 |  | 0
90000731 | 270 Republic Road Water Tanks | Remove all existing inlet, outlet and overflow flanged fittings from tank and electrical equipment. Strip all bolts and nuts, remove gaskets, strip all internal bracings and cleats Remove tank panels from building and pack on pallets and transport to off-site to workshop Transport panels to workshop for sandblasting and galvanizing. Supply and install new bolts, nuts and gaskets Re-assemble and test for leaks. |  |  | Region 1 | Gauteng South | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-09-28 | 2023-10-27 |  | ALP-GS0069 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-09-28 | D | 900778.74 |  | 100 | 2023-09-12 | 2023-09-21 | 900778.74 | 27.10 NN: Awaiting Absa PO | {"MANDT":"111","REFERENCE":90000731,"ONEVIEW":"21335X","DATE01":"2023-09-01","DATE02":"2023-09-08","DATE03":"2023-09-14","DATE04":"2023-09-19","DATE05":"2023-09-21","DATE06":"2023-11-06","DATE07":"2023-12-06","DATE08":"2024-01-08","DATE09":"2024-02-22","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":80,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:6:5:2:46:30:33:45:30","PROGRESS":53,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-06","FORECAST_END":"2023-12-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"V29yayBpbiBQcm9ncmVlcw==","RATING":"Low"} |  |  |  | PHASE07 | 2023-11-06 | 2023-12-06 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-10-03 | 2023-10-20 | 2023-10-20 | 2023-10-23 |  | 0 | 59057 |  |  | C000143452 | 783286.09 |  | 77864.05 |  | 0 | 0 |  | 0 |  | 0
90000732 | 270 Republic Rd Compressors chilllers | 1. Decommission compressor from Chiller (only for compressor 2. since compressor 1 has already been decommissioned) 2. Overhaul compressors 1 and 2 3. Rebuild screw compressor 4. Rigging compressor in 5. Installation and commissioning |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-09-28 | 2023-10-27 |  | ALP-GS0070 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-09-28 | D | 968694.33 |  | 80 | 2023-09-15 | 2023-09-21 | 968694.33 | BFM PO issued, to expedite critical project. Awaiting Absa PO Absa PO raised 08.11 | {"MANDT":"111","REFERENCE":90000732,"ONEVIEW":"21335X","DATE01":"2023-08-04","DATE02":"2023-08-11","DATE03":"2023-08-14","DATE04":"2023-09-20","DATE05":"2023-09-21","DATE06":"2023-11-01","DATE07":"2023-11-30","DATE08":"2024-01-08","DATE09":"2024-02-22","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":70,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:3:37:1:41:29:39:45:30","PROGRESS":53,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-01","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"U3VwcGxpZXIgdG8gaXNzdWUgdGhlIGNvbW1pc3Npb25pbmcgcmVwb3J0IGFuZCBhbGwgY2xvc2Ugb3V0IGRvY3VtZW50YXRpb24u","RATING":"High"} |  |  | C000122144 | PHASE09 | 2023-11-01 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-10-03 | 2023-10-20 | 2023-10-20 | 2023-10-23 | 2023-11-08 | 816933.04 | 764621 |  |  | C000141037 | 52312.22 |  | 72821.03 |  | 0 | 0 |  | 0 |  | 0
90000733 | Absa Towers West Waterproofing reinforce | Absa Towers West Waterproofing reinforce |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-04-05 | 2023-10-31 |  | ALP-GS0071 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-09-28 | D | 2642503 |  | 80 | 2023-07-20 | 2023-07-27 | 2642503 | Approved | {"MANDT":"111","REFERENCE":90000733,"ONEVIEW":"21526X","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":80,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhcHByb3ZlZCBBd2FpdGluZyBCRk0gUE9z","RATING":"Low"} |  |  | C000117583 | PHASE10 | 2023-04-05 | 2023-10-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-08-08 | 2023-08-17 | 2023-09-18 | 2023-10-24 | 2023-10-18 | 2297853.13 | 0 |  |  | C000117583 | 2323293.49 |  | 198516.5 |  | 0 | 0 |  | 0 |  | 0
90000734 | Absa Viking Park - Minor Works | Absa Viking Park - Minor Works |  |  | Region 2 | Western Cape | 77971X | 1000-70868-01 | Viking Park-Show Grounds Ave-Epping | N | 2023-11-01 | 2023-12-29 |  | ASP-WC0327 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-09-29 | D | 44608.28 |  | 100 | 2023-10-23 | 2023-10-26 | 44608.28 |  | {"MANDT":"111","REFERENCE":90000734,"ONEVIEW":"77971X","DATE01":"2023-09-29","DATE02":"2023-10-17","DATE03":"2023-10-23","DATE04":"2023-10-30","DATE05":"2023-10-26","DATE06":"2023-11-02","DATE07":"2023-11-07","DATE08":"2023-11-10","DATE09":"2023-12-25","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"214:18:6:7:-4:7:5:3:45:9","PROGRESS":15,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-02","FORECAST_END":"2023-11-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgT2N0IEFwcHJvdmVkIGF0IENCNDEgU2lnbmVkIGRlY2sgcGVuZGluZyBpbiBvcmRlciB0byByZXF1ZXN0IEFic2EgUE8ncwoyNCBPY3QgTm90ZTogQWR2aXNlIElsYW5hIHdoZW4gY29tcGxldGVkCjIzIE9jdCBzdWJtaXR0ZWQgZm9yIENCNDEKMTYgT2N0IENvc3RzIHRvIGJlIHN1Ym1pdHRlZCAxNiBPY3QKOSBPY3QgQ29zdGluZ3MgaW4gUHJvZ3Jlc3MsIG5vIGltcGFjdCBvbiBFbmdpbmVlcmluZyBzZXJ2aWNlcy4KNiBPY3QgMyBPY3QgRHJhd2luZyByZWNlaXZlZCBFbmdpbmVlcmluZyBlbmdhZ2VkIHJlIGltcGFjdCBvbiBIdmFjLCBGaXJlIGFuZCBMaWdodGluZwoyOSBTZXB0IC0gUFJGIHJlY2VpdmVkIC0gRHJhd2luZyByZXF1aXJlZCBmcm9tIFBsYW5uZXIgdG8gZGV0ZXJtaW5lIEVuZ2luZWVyaW5nIGFuZCBDb3VuY2lsIHJlcXVpcmVtZW50cy4gV2lsbCBiZSBwcm9qZWN0IFJvbGxvdmVyCg==","RATING":""} |  |  | C000119536 | PHASE11 | 2023-11-02 | 2023-11-07 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-10-27 | 38789.81 | 0 |  |  | C000119536 | 38789.8 |  | 2102.78 |  | 0 | 0 |  | 0 |  | 0
90000735 | 16 Central Avenue electrical COC | 16 Central Avenue electrical COC |  |  | Region 1 |  | 37163X | 1000-77456-01 | Kempton Square |  | 2023-09-29 | 2023-10-27 |  | ALP-GN0014 | REL BUDG AVAC RESA SETC: |  | false | false |  | (Non PM) |  |  | 2023 |  |  |  | GAMIETR | 2023-09-29 | D | 0 |  | 1 |  |  | 0 | Duplicate Project - Tracking Project ASP-GN0232 | {"MANDT":"111","REFERENCE":90000735,"ONEVIEW":"37163X","DATE01":"2023-07-21","DATE02":"2023-07-28","DATE03":"2023-08-18","DATE04":"2023-08-25","DATE05":"2023-09-15","DATE06":"2023-09-29","DATE07":"2023-10-27","DATE08":"2023-11-17","DATE09":"2024-01-01","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":54,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-29","FORECAST_END":"2023-10-27","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCByZXBlYXRlZCA=","RATING":""} |  |  |  | PHASE12 | 2023-09-29 | 2023-10-27 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000112435 | 619237.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000736 | Various- Capital requirments for load sh | Various- Capital requirments for load sh |  |  | National | National | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-31 | 2023-12-29 |  | ALP-N00056 | REL BUDG AVAC RESA SETC: |  | false | false |  | Tshegofatso Segooa |  |  | 2023 |  |  |  | LOUISR | 2023-09-29 | D | 19281887.81 |  | 70 | 2023-10-26 |  | 0 |  | {"MANDT":"111","REFERENCE":90000736,"ONEVIEW":"21526X","DATE01":"2023-08-22","DATE02":"2023-08-29","DATE03":"2023-09-19","DATE04":"2023-09-26","DATE05":"2023-10-17","DATE06":"2023-10-31","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkuMTEuMjMgQVMgOkhpIFRzaGVnbyAuIENhbiB5b3Uga2luZGx5IHVwZGF0ZSBGdW5kaW5nLCBBcHByb3ZhbCBhbmQgUHJvZ3Jlc3MgVGFicw==","RATING":""} |  |  |  | PHASE00 | 2023-10-31 | 2023-12-29 | LUCIA AMUNGA | Michael Maluleka | 0 | 2023-10-26 |  | 2023-10-26 |  |  | 0 | 0 |  |  | C000146115 | 16766859.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000737 | 270 RR Install concrete platform | 270 RR Install concrete platform |  |  | Region 1 | Gauteng | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-10-02 | 2023-10-31 |  | ASP-GS0753 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | GAMIETR | 2023-10-02 | D | 3622.55 |  | 100 | 2023-10-05 | 2023-10-06 | 3622.55 |  | {"MANDT":"111","REFERENCE":90000737,"ONEVIEW":"21335X","DATE01":"2023-09-19","DATE02":"2023-09-19","DATE03":"2023-09-20","DATE04":"2023-09-20","DATE05":"2023-10-06","DATE06":"2023-10-21","DATE07":"2023-10-28","DATE08":"2023-12-01","DATE09":"2024-01-15","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"134:0:1:0:16:15:7:34:45:17","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-21","FORECAST_END":"2023-10-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTI6MTA6MjMgQVM6IEJGTSBQTyByZWNlaXZlZCBhbmQgc2VudCB0byBhIHN1cHBsaWVyLCB3YWl0aW5nIGZvciBhZGp1c3RlZCB0aW1lbGluZXMgZnJvbSB0aGUgc3VwcGxpZXIuIA==","RATING":"Low"} |  |  | C000115061 | PHASE11 | 2023-10-21 | 2023-10-23 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-10-06 | 3150.04 | 0 |  |  | C000115061 | 3150.04 |  | 284.05 |  | 0 | 0 |  | 0 |  | 0
90000738 | Alice Lane North 6 Extractor Fans | Alice Lane North 6 Extractor Fans |  |  | Region 1 | Gauteng | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton | Y | 2023-10-02 | 2023-10-31 |  | ASP-GS0754 | CRTD: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  | F |  | GAMIETR | 2023-10-02 | D | 187328.61 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000738,"ONEVIEW":"70656X","DATE01":"2023-07-24","DATE02":"2023-07-31","DATE03":"2023-08-21","DATE04":"2023-08-28","DATE05":"2023-09-18","DATE06":"2023-10-02","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-02","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2023-10-02 | 2023-10-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000739 | Absa Laingsburg-COC Inspection Phase 1 | Absa Laingsburg-Dilaps COC Inspection Phase 1 |  |  | Region 2 | Western Cape | 78112X | 1000-70886-01 | Absa Laingsburg-Voortrekker Rd-Laingsburg | N | 2023-11-01 | 2023-12-29 |  | ASP-WC0328 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-10-02 | D | 11444.26 |  | 100 | 2023-10-05 | 2023-10-09 | 11444.26 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000739,"ONEVIEW":"78112X","DATE01":"2023-09-29","DATE02":"2023-09-29","DATE03":"2023-10-05","DATE04":"2023-10-12","DATE05":"2023-10-09","DATE06":"2023-10-18","DATE07":"2023-10-18","DATE08":"2023-11-20","DATE09":"2024-01-04","DATE10":"2024-01-31","DATE11":"2024-01-04","DATE12":"2024-01-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"93:0:6:7:-3:9:0:33:45:1","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-18","FORECAST_END":"2023-10-18","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgTm92IC0gUE9DIFN1Ym1pdHRlZCB0byBGaW5hbmNlLCBjb250aW5nZW5jeSBub3QgdXRpbGlzZWQKMjAgTm92IFdpdGggUmVhbCBFc3RhdGUgZm9yIFNpZ25vZmYKMTYgTm92IFBPQyB3aXRoIFJlYWwgRXN0YXRlIGZvciBzaWdub2ZmCjEzIE5vdiBQT0MgcGFjayBzZW50IHRvIFBDIHRvIHVwbG9hZCBmb3IgUmVhbCBFc3RhdGUgU2lnbm9mZgo5IE5vdiAtIFBPQyB0byBiZSBzdWJtaXR0ZWQgdG8gUmVhbCBFc3RhdGUgZm9yIFNpZ25vZmYKNyBOb3YgV29yayB0byBiZSBjb25kdWN0ZWQgdmlzIEdNUCAtIFZlbmRvciB0byBpbnZvaWNlIGZvciBJbnNwZWN0aW9uCjMgTm92IFBFIGNvbmZpcm1lZCByZW1lZGlhbCB3b3JrIHRvIGJlIEdNUAoyMyBPY3QgLSAgUE0gdG8gY3JlYXRlIG5ldyBRdW90ZXMgdG8gc3BsaXQgTWFpbnRlbmFuY2UgYW5kIE90aGVyIHdvcmtzCjE5IE9jdCBWZW5kb3IgaW5zcGVjdGVkIDE4IE9jdCAtIElzc3VlcyBpZGVudGlmaWVkIGFuZCByZXBvcnQgdG8gZm9sbG93CjEyIE9jdCBCViBQTyBJc3N1ZWQgLSA0NTAwODY1MjAyIENhcGUgV2VzdAoxMCBPY3QgQWJzYSBQTyBDMDAwMTE1NTgxIFJlY2VpdmVkIEJWIFBPIFJlcXVlc3RlZAoxMCBPY3QgQWJzYSBQTyBDMDAwMTE1NTgxIFJlY2VpdmVkIEJWIFBPIFJlcXVlc3RlZAo5IE9jdCBBcHByb3ZlZCBieSBSZWFsIEVzdGF0ZSBBYnNhIFBPIFJlcXVlc3RlZAo2IE9jdCBDcmVzIFN1cHBvcnRlZCAtIFN1Ym1pdHRlZCB0byBSZWFsIEVzdGF0ZSBmb3IgYXBwcm92YWwKNSBPY3QgU3VibWl0dGVkIHRvIENyZXMgRW5nIEZvciBzdXBwb3J0IHRvIHN1Ym1pdCB0byBSZWFsIEVzdGF0ZQoyOSBTZXB0IC0gUXVvdGVzIHRvIGJlIG9idGFpbmVkIHRvIG9idGFpbiB1cGRhdGVkIENPQyByZXF1ZXN0ZWQgYnkgdGhlIE11bmljaXBhbGl0eQ==","RATING":"Low"} |  |  | C000115581 | PHASE11 | 2023-10-18 | 2023-10-18 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-10-10 | 9951.52 | 0 |  |  | C000115581 | 9951.52 |  | 1040.39 |  | 0 | 1040.39 |  | 0 |  | 0
90000740 | 270 Republic Jace Panels and Controllers | 270 Republic Jace Panels and Controllers |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-10-02 | 2023-10-31 |  | ALP-GS0072 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-10-02 | D | 2634278 |  | 100 | 2023-10-05 | 2023-10-06 | 2634278 | PO issued, to expedite critical project. Awaiting Absa PO | {"MANDT":"111","REFERENCE":90000740,"ONEVIEW":"21335X","DATE01":"2023-07-24","DATE02":"2023-07-31","DATE03":"2023-08-21","DATE04":"2023-08-28","DATE05":"2023-09-18","DATE06":"2023-10-02","DATE07":"2023-10-31","DATE08":"2023-11-21","DATE09":"2024-01-05","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":60,"PROG06":50,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":50,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-02","FORECAST_END":"2023-10-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBhcHByb3ZlZCBhdCAgQlRCIGJ1c3kgRmluYWxpc2luZyBsZWdhbCBkb2N1bWVudHMgV0EgYW5kIFNGQSAuCkJGTSBQTydzIHdpbGwgYmUgaXNzdWVkIGluIHRoZSBpbnRlcmltIGZvciB0aGUgc3VwcGxpZXIgdG8gcHJvY3VyZSBzcGFyZXMgYW5kIGNvbW1lbmNlIHdpdGggdGhlIHByb2plY3RzLgpUaGUgcHJvamVjdCB3aWxsIGJlIGNvbXBsZXRlZCB0aGlzIHllYXIgYW5kIGZ1bGx5IGludm9pY2VkLg==","RATING":"Low"} |  |  | Await WA approval for Absa PO | PHASE09 | 2023-10-02 | 2023-10-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-08-14 |  |  |  |  | 0 | 0 |  |  | C000143932 | 2290676.29 |  | 128082 |  | 0 | 0 |  | 0 |  | 0
90000741 | Absa Kirkwood - Insurance Claim no 2 - Storm/Flood Damage (Retrospective) | Absa Kirkwood - Insurance Claim no 2 - Storm/Flood Damage (Retrospective) |  |  | Region 2 | Eastern Cape | 76548X | 1000-71013-01 | Absa Kirkwood-Hoof St-Kirkwood | N | 2023-08-02 | 2023-08-02 |  | ASP-EC0364 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | F |  | CEASARS | 2023-10-03 | D | 94968.15 |  | 100 | 2023-08-31 | 2023-08-31 | 94968.15 |  | {"MANDT":"111","REFERENCE":90000741,"ONEVIEW":"76548X","DATE01":"2023-08-31","DATE02":"2023-08-31","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-08-31","DATE06":"2023-10-05","DATE07":"2023-10-05","DATE08":"2023-10-09","DATE09":"2023-11-23","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"91:0:0:7:-7:35:0:4:45:3","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-10-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OSBPY3QgUE9DIHN1Ym1pdHRlZCB0byBGaW5hbmNlCjUgT2N0IEFic2EgUE8gUmVjZWl2ZWQgQzAwMDExNDc5OCBQT0MgdG8gRm9sbG93CjQgT2N0IC0gQWJzYSBQTyBSZXF1ZXN0ZWQKMyBPY3QgMm5kIFBhY2sgcmVjZWl2ZWQgZm9yIEluc3VyYW5jZSBDbGFpbSwgQkMgYW5kIFBhcGVyd29yayBpbiBjb21waWxhdGlvbg==","RATING":"Low"} |  |  | C000114798 | PHASE11 | 2023-10-05 | 2023-10-05 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-10-03 | 82581 | 0 |  |  | C000114798 | 82581 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000742 | Various- Retail BMS Upgrade | Various- Retail BMS Upgrade |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-31 | 2023-12-15 |  | ASP-N00074 | CRTD AVAC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | LOUISR | 2023-10-03 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000742,"ONEVIEW":"21526X","DATE01":"2023-08-22","DATE02":"2023-08-29","DATE03":"2023-09-19","DATE04":"2023-09-26","DATE05":"2023-10-17","DATE06":"2023-10-31","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-10-31 | 2023-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000743 | Auckland Park CC Slab Insulation | Auckland Park CC Slab Insulation |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-10-03 | 2023-11-30 |  | ALP-GS0073 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-10-03 | D | 868164.32 | Project approval to be OCC. | 15 | 2023-10-11 |  | 0 | Project on hold pending CRES decision. | {"MANDT":"111","REFERENCE":90000743,"ONEVIEW":"76849X","DATE01":"2023-07-25","DATE02":"2023-08-01","DATE03":"2023-08-22","DATE04":"2023-08-29","DATE05":"2023-09-19","DATE06":"2023-10-03","DATE07":"2023-11-30","DATE08":"2023-12-21","DATE09":"2024-02-04","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-03","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBCVEIgcGFwZXIgc3VibWl0dGVkIHRvIENSRVMgZm9yIGFwcHJvdmFsLg==","RATING":""} |  |  |  | PHASE05 | 2023-10-03 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000744 | Alternative Energy Programme for 2 x Ret | Alternative Energy Programme for 2 x Retail Mall Of The South Shopping Centre and Arbour Crossing Retail Centre For a battery wall system. |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-31 | 2023-12-15 |  | ALP-N00057 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | LOUISR | 2023-10-03 | D | 5381898.04 |  |  | 2023-08-24 |  | 0 |  | {"MANDT":"111","REFERENCE":90000744,"ONEVIEW":"21526X","DATE01":"2023-08-22","DATE02":"2023-08-29","DATE03":"2023-09-19","DATE04":"2023-09-26","DATE05":"2023-10-17","DATE06":"2023-10-31","DATE07":"2023-12-15","DATE08":"2024-01-05","DATE09":"2024-02-19","DATE10":"2024-02-29","DATE11":"2024-02-19","DATE12":"2024-02-19","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-31","FORECAST_END":"2023-12-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000120723 | PHASE00 | 2023-10-31 | 2023-12-15 | LUCIA AMUNGA | Michael Maluleka | 0 |  |  |  |  | 2023-11-02 | 3414855.43 | 0 |  |  | C000120723 | 3414855.43 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000745 | Absa Hexagon - Insurance Claim - Repair Damaged Roller Door (Retrospective) | Absa Hexagon - Insurance Claim - Repair Damaged Roller Door (Retrospective) |  |  | Region 2 | Eastern Cape | 78801X | 1000-71054-01 | Hexagon Circle-Hexagon Circle-Queenstown | N | 2023-07-26 | 2023-07-26 |  | ASP-EC0365 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-10-04 | D | 27302.09 |  | 100 | 2023-08-31 | 2023-08-31 | 27302.09 |  | {"MANDT":"111","REFERENCE":90000745,"ONEVIEW":"78801X","DATE01":"2023-08-31","DATE02":"2023-08-31","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-08-31","DATE06":"2023-10-19","DATE07":"2023-10-19","DATE08":"2023-10-26","DATE09":"2023-12-10","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"122:0:0:7:-7:49:0:7:45:28","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-19","FORECAST_END":"2023-10-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgT2N0IC0gQWJzYSBQTyBSZWNlaXZlZCAtIEMwMDAxMTc4MzkgSW52b2ljaW5nIGFuZCBQT0MgdG8gZm9sbG93CjE4IE9jdCBBYnNhIFBPIFJlcXVlc3RlZAoxNiBPY3QgLSBQYWNrcyByZWNlaXZlZCBGcmlkYXkgMTN0aAo5IE9jdCBXTyBhbmQgaW52b2ljaW5nIERvY3VtZW50YXRpb24gaW5mbyBzdGlsbCBwZW5kaW5nIGZyb20gdGVhbQo0IE9jdCAtIERldGFpbHMgUmVxdWVzdGVkIGZyb20gRk0K","RATING":""} |  |  | C000117839 | PHASE11 | 2023-10-19 | 2023-10-19 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-10-19 | 23740.95 | 0 |  |  | C000117839 | 23740.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000746 | Cancelled Project | Cancelled Project |  |  | Region 2 |  | 77697X | 1000-70847-01 | Absa Riviersonderend-Main Rd-Riviersonderend |  | 2023-07-10 | 2023-07-10 |  | ASP-EC0366 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-10-04 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED | 2023-07-10 | 2023-07-10 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000747 | Absa Cathedral Square - Insurance Claim - Repair main exit gate is not closing after it was damaged (Retrospective) | Absa Cathedral Square - Insurance Claim - Repair main exit gate is not closing after it was damaged (Retrospective) |  |  | Region 2 | Eastern Cape | 70570X | 1000-71000-01 | Cathedral Square-Cnr York & Victoria St-Mthatha | N | 2023-07-19 | 2023-07-19 |  | ASP-EC0367 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-10-04 | D | 2810.31 |  | 100 | 2023-08-31 | 2023-08-31 | 2810.31 |  | {"MANDT":"111","REFERENCE":90000747,"ONEVIEW":"70570X","DATE01":"2023-08-31","DATE02":"2023-08-31","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-08-31","DATE06":"2023-10-19","DATE07":"2023-10-19","DATE08":"2023-10-20","DATE09":"2023-12-04","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"122:0:0:7:-7:49:0:1:45:13","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-19","FORECAST_END":"2023-10-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgT2N0IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQoxOSBPY3QgLSBBYnNhIFBPIFJlY2VpdmVkIC0gQzAwMDExNzg0MCBJbnZvaWNpbmcgYW5kIFBPQyB0byBmb2xsb3cKMTYgT2N0IC0gUGFja3MgcmVjZWl2ZWQgRnJpZGF5IDEzdGgKOSBPY3QgV08gYW5kIGludm9pY2luZyBEb2N1bWVudGF0aW9uIGluZm8gc3RpbGwgcGVuZGluZyBmcm9tIHRlYW0KNCBPY3QgLSBEZXRhaWxzIFJlcXVlc3RlZCBmcm9tIEZNCg==","RATING":""} |  |  | C000117840 | PHASE11 | 2023-10-19 | 2023-10-19 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-10-19 | 2443.75 | 0 |  |  | C000117840 | 2443.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000748 | Absa 32 Voortrekker Belliville - Insurance Claim - Repairs, burglars broke in external hydrant door and attempted to steal fixtures (Retrospective) | Absa 32 Voortrekker Belliville - Insurance Claim - Repairs, burglars broke in external hydrant door and attempted to steal fixtures (Retrospective) |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2023-08-09 | 2023-08-09 |  | ASP-WC0329 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | F |  | CEASARS | 2023-10-04 | D | 4084.8 |  | 100 | 2023-08-31 | 2023-08-31 | 4084.8 |  | {"MANDT":"111","REFERENCE":90000748,"ONEVIEW":"78126X","DATE01":"2023-08-31","DATE02":"2023-08-31","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-08-31","DATE06":"2023-10-05","DATE07":"2023-10-05","DATE08":"2023-10-12","DATE09":"2023-11-26","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:7:-7:35:0:7:45:17","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-10-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgT2N0IFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQo1IE9jdCBBYnNhIFBPIFJlY2VpdmVkIEMwMDAxMTQ3OTkgUE9DIHRvIEZvbGxvdwo0IE9jdCAtIERldGFpbHMgUmVxdWVzdGVkIC8gQWJzYSBQTyBSZXF1ZXN0ZWQ=","RATING":""} |  |  | C000114799 | PHASE11 | 2023-10-05 | 2023-10-05 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-10-05 | 3552 | 0 |  |  | C000114799 | 3552 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000749 | Absa Piketberg - COC Inspection phase 1 | Absa Piketberg - COC Inspection phase 1 |  |  | Region 2 | Western Cape | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg | N | 2023-10-15 | 2023-12-29 |  | ASP-WC0330 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-10-04 | D | 19627.51 |  | 100 | 2023-10-12 | 2023-10-19 | 19627.51 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000749,"ONEVIEW":"78132X","DATE01":"2023-10-05","DATE02":"2023-10-12","DATE03":"2023-10-12","DATE04":"2023-10-19","DATE05":"2023-10-19","DATE06":"2023-11-14","DATE07":"2023-11-15","DATE08":"2023-12-12","DATE09":"2024-01-26","DATE10":"2024-01-31","DATE11":"2024-01-20","DATE12":"2024-01-20","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"118:7:0:7:0:26:1:27:45:11","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-14","FORECAST_END":"2023-11-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRGVjIEZpbmFsIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQo3IERlYyBFbmdpbmVlcmluZyB0byBhZHZpc2UgcmUgcmVtZWRpYWwgV29yaywgUE9DIFN1Ym1pdHRlZCB0byBFbmdpbmVlcmluZyBmb3IgU2lnbiBPZmYKNCBEZWMgLSBJbnZvaWNlIHJlY2VpdmVkIEVuZyB0byBhZHZpc2Ugb24gdGhlIHJlcGFpciB3b3JrcwozMCBOb3YgLSBSZXBvcnQgc3VibWl0dGVkIHRvIEVORyAtIFJlcGFpciB3b3JrcyB0byBiZSBjb25maXJtZWQKMjcgTm92IEJpZHZlc3QgRW5nIHRvIGFkdmlzZSBvbiB0aGUgcXVvdGUgYW5kIGluc3BlY3Rpb24gcmVwb3J0CjIzIE5vdiBQTSB0byBmb2xsb3cgdXAgb24gdGhlIHJlcG9ydCBmcm9tIHRoZSB2ZW5kb3IKMjAgTm92IC0gUmVwb3J0IHBlbmRpbmcgZm9yIGluc3BlY3Rpb24KMTYgTm92IFZlbmRvciBjb21wbGV0ZWQgdGhlIGluc3BlY3Rpb24KMTUgTm92IENvbXBsZXRlZCAtIFJlcG9ydCBhbmQgUE9DIHBlbmRpbmcKMzAgT2N0IFByb3Bvc2VkIGRhdGVzIDE0IGFuZCAxNSBOb3YKMjcgT2N0IEJpZHZlc3QgUE8gUmVjZWl2ZWQgLSA0NTAwODY4NzY1IENhcGUgV2VzdAoyNCBPY3QgQWJzYSBQTyBSZWNlaXZlZCBDMDAwMTE4NjQyIEJWIFBPIHJlcXVlc3RlZAoyMCBPY3Qgc2lnbmVkIENCNDAgRGVjayByZWNlaXZlZCBQTydzIHRvIGJlIHJlcXVlc3RlZAoxOSBPY3QgQXBwcm92ZWQgYXQgQ0I0MCBTaWduZWQgZGVjayBwZW5kaW5nIGluIG9yZGVyIHRvIHJlcXVlc3QgQWJzYSBQTydzCjE5IE9jdCBJbiBDQiBmb3IgYXBwcm92YWwgQ0I0MCAxOSBPY3QKMTIgT2N0IFJlcXVlc3RlZCBjbGFyaXR5IG9uIGFwcHJvdmFsIGZyb20gQWJzYSBFbmdpbmVlcmluZwoxMCBPY3QgUmVxdWVzdCBzZW50IHRvIEJpZHZlc3QgZW5naW5lZXJpbmcgZm9yIFN1cHBvcnQgdG8gc3VibWl0IHRvIFJlYWwgRXN0YXRlCjkgT2N0IC0gUE0gdG8gcmVxdWVzdCBRdW90ZSB0byBjb21wbGV0ZSBpbnNwZWN0aW9uIGVudGlyZSBidWlsZGluZwo2IE9jdCAtIEFzIHBlciBtZWV0aW5nIGhlbGQgd2l0aCBDUkVTLCBCaWR2ZXN0IHRvIG9idGFpbiBDT0MgZm9yIGVudGlyZSBCdWlsZGluZwo1IE9jdCBBcHByb3ZlZCBQUkYgcmVjZWl2ZWQKNCBPY3QgQXBwcm92ZWQgUFJGIHBlbmRpbmcsIHRvIGNsZWFyIHdpdGggRW5naW5lZXJpbmc=","RATING":"Low"} |  |  | C000118642 | PHASE11 | 2023-11-14 | 2023-11-15 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-24 | 17067.4 | 0 |  |  | C000118642 | 17067.4 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000750 | Absa Riviersonderend - Insurance Claim - Vandalised HVAC system at the branch (Retrospective) | Absa Riviersonderend - Insurance Claim - Vandalised HVAC system at the branch (Retrospective) |  |  | Region 2 | Western Cape | 77697X | 1000-70847-01 | Absa Riviersonderend-Main Rd-Riviersonderend | N | 2023-07-10 | 2023-07-10 |  | ASP-WC0331 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Surina Ceaser |  |  | 2023 |  | L |  | CEASARS | 2023-10-04 | D | 276598 |  | 100 | 2023-08-31 | 2023-08-31 | 276598 | 4 Oct - Details Requested / Absa PO Requested | {"MANDT":"111","REFERENCE":90000750,"ONEVIEW":"77697X","DATE01":"2023-08-31","DATE02":"2023-08-31","DATE03":"2023-08-31","DATE04":"2023-09-07","DATE05":"2023-08-31","DATE06":"2023-10-05","DATE07":"2023-10-05","DATE08":"2023-10-12","DATE09":"2023-11-26","DATE10":"2023-11-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"91:0:0:7:-7:35:0:7:45:25","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-05","FORECAST_END":"2023-10-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggT2N0IFN1Ym1pdHRlZCBmb3IgQlYgRW5naW5lZXJpbmcgU2lnbm9mZgo1IE9jdCBBYnNhIFBPIFJlY2VpdmVkIEMwMDAxMTQ4MDAgUE9DIHRvIEZvbGxvdwo0IE9jdCAtIERldGFpbHMgUmVxdWVzdGVkIC8gQWJzYSBQTyBSZXF1ZXN0ZWQ=","RATING":""} |  |  | C000114800 | PHASE11 | 2023-10-05 | 2023-10-05 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-10-05 | 240520 | 0 |  |  | C000114800 | 240520 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000751 | Absa Kuruman - Replace Motor Gate | Absa Kuruman - Replace Motor Gate |  |  | Region 3 |  | Unknown | 1000-71350-01 | Unknown Building - not in our database |  | 2023-11-24 |  |  | ASP-CR0509 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-05 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000118466 | PHASE00 | 2023-11-24 | 2023-12-24 | NANDE MAQUBELA | floyd mofokeng | 0 |  |  |  |  | 2023-10-23 | 17527.6 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000752 | Absa Moffett Office Park - BMS Connectio | Absa Moffett Office Park - BMS Connectio |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-11-01 | 2023-12-29 |  | ASP-EC0368 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-10-05 | D | 0 |  | 1 |  |  | 0 | 6 Oct - As per meeting held 6 OCT bidvest to fund this from GMP it has been receiving 5 Oct OOC PRF Received | {"MANDT":"111","REFERENCE":90000752,"ONEVIEW":"22937X","DATE01":"2023-10-05","DATE02":"2023-10-12","DATE03":"2023-11-02","DATE04":"2023-11-09","DATE05":"2023-11-30","DATE06":"2023-12-14","DATE07":"2024-02-10","DATE08":"2024-03-02","DATE09":"2024-04-16","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:58:21:45:27","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-14","FORECAST_END":"2024-02-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBPY3QgT09DIFBSRiBSZWNlaXZlZA==","RATING":""} |  |  |  | PHASE12 | 2023-12-14 | 2024-02-10 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000753 | ATW Industrial & Commerical Microwaves | ATW Industrial & Commerical Microwaves |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-06 | 2023-10-31 |  | ASP-GS0755 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-10-06 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-10-06 | 2023-10-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000145241 | 311980 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000754 | Absa De Doorns - Tenant Flats Minor Work | Absa De Doorns - Tenant Flats Minor Work |  |  | Region 2 | Western Cape | 78111X | 1000-70885-01 | Absa De Doorns-Voortrekker Rd-De Doorns | N | 2023-10-23 | 2023-12-29 |  | ASP-WC0332 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-10-06 | D | 283431.95 |  | 100 | 2023-10-19 | 2023-11-01 | 283431.95 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000754,"ONEVIEW":"78111X","DATE01":"2023-10-06","DATE02":"2023-10-09","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-01","DATE06":"2023-11-09","DATE07":"2023-11-24","DATE08":"2023-12-08","DATE09":"2024-01-22","DATE10":"2024-01-31","DATE11":"2024-01-19","DATE12":"2024-01-19","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"117:3:9:7:7:8:15:14:45:12","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-09","FORECAST_END":"2023-11-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBEZWMgRmluYWwgUE9DIFN1Ym1pdHRlZCBSIDI1MiA1NzQuNTAKNCBEZWMgLSBXb3JrcyBjb21wbGV0ZWQgSW52b2ljZSByZXF1ZXN0ZWQKMjcgTm92IFdpbGwgaW5zcGVjdCBvbiAwMSBEZWMKMjAgTm92IC0gRGVsYXllZCBkdWUgdG8gYWRkaXRpb25hbCBtYWludGVuYW5jZSB3b3JrcyByZXF1ZXN0ZWQgYnkgRk0gdGVhbSBleHBlY3RlZCBjb21wbGV0aW9uIDI0IE5vdgoxMSBOb3YgV29ya3MgaW4gcHJvZ3Jlc3MKNiBOb3YgU3RhcnQgb24gc2l0ZSA5IE5vdiAtIGNvbXBsZXRlIGJ5IDIxIE5vdgozIE5vdiBCViBQTyBJc3N1ZWQgNDUwMDg3MDA1NCBKTSBDb3Jwb3JhdGUgUmVhbCBFc3RhdGUgU29sdXRpb25zCjEgTm92IEFwcHJvdmFsIFJlY2VpdmVkLCBBYnNhIFBPICBDMDAwMTIwNDY2IFJlY2VpdmVkIEJWIFBPIFJlcXVlc3RlZAoyMyBPY3QgLSBGZWVkYmFjayBwZW5kaW5nIGZyb20gUmVhbCBFc3RhdGUKMTkgT2N0IFN1Ym1pdHRlZCB0byBSZWFsIEVzdGF0ZSBhbmQgVlAgZm9yIEFwcHJvdmFsCjE2IE9jdCB0byBiZSBzdWJtaXR0ZWQgMTZ0aAoxMiBPY3QgLSBRdW90ZXMgZHVlIEZyaWRheSAxMyBPY3QKOSBPY3QgUE0gY29uZHVjdGluZyBzaXRlIHZpc2l0IHRvIGRldGVybWluZSBzY29wZSA5IE9jdAo2IE9jdCBSZXF1ZXN0IHJlY2VpdmVkIHRvIHJlbWVkaWF0ZSBUZW5hbnQgRmxhdHMK","RATING":"Low"} |  |  | C000120466 | PHASE11 | 2023-11-09 | 2023-11-24 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-01 | 246462.57 | 0 |  |  | C000120466 | 246462.57 |  | 25257.45 |  | 0 | 25257.45 |  | 0 |  | 0
90000755 | Absa 270 Republic Rd Carports | Absa 270 Republic Rd Carports Scope of Works: Structural assessment: . Attend a compulsory site meeting for scope definition ; . Conduct an assessment of the parking area ; . Issue a report with findings and commendations ; . Compile a BOQ for the remedial works to be carried out ; Fully Galvanised Carports Scope of Works: . Supply & install new steel carport size 3 x 6m high x No. 116 ; . Supply & install hot dipped galvanised frame-poles roof - main frame size (150x50x20x2,5m); . Supply and install perlins (100x50x20x2,5m); ,Supply and install new galvernised 0,5mm IBR roof sheeting . Supply and install hot dipped galvanized poles (76x76x2mm) ,Supply and install 116 LED lights and fittings and lighting in the carports . Issue COC on works completion. Re-taring of Asphalt Surface and Reinstating of Concrete Pavers: . Allowance for a precast edge beam x 10m long; . Reinstating of concrete pavers including backfilling x 43m2; . Backfilling to area underneath concrete pavers x 5m3 . Remove damaged asphalt surface and relay to correct slope x 140m2; . Allowance for a new concrete half pipe channel x 45m long; |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa 270 Republic Road, Randburg | Y | 2023-10-09 | 2023-11-30 |  | ALP-GS0074 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-10-09 | D | 3112110 | Supported by CRES FM | 60 | 2023-09-28 |  | 3112110 | Project approved at MANCO request to issue BFM PO's while compiling legal document to release Absa PO, | {"MANDT":"111","REFERENCE":90000755,"ONEVIEW":"21526X","DATE01":"2023-07-31","DATE02":"2023-08-07","DATE03":"2023-08-28","DATE04":"2023-09-04","DATE05":"2023-09-25","DATE06":"2023-10-09","DATE07":"2023-11-30","DATE08":"2023-12-21","DATE09":"2024-02-04","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-09","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE07 | 2023-10-09 | 2023-12-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-11-06 |  |  |  |  | 0 | 0 |  |  | C000142953 | 2706182.61 |  | 270438 |  | 0 | 0 |  | 0 |  | 0
90000756 | 8 Top Road Bird proofing warehouse | 8 Top Road Bird proofing warehouse |  |  | Region 1 | Gauteng South | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg | N | 2023-04-05 |  |  | ALP-GS0075 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-10-09 | D | 1134152.83 |  | 100 |  |  | 1134152.83 |  | {"MANDT":"111","REFERENCE":90000756,"ONEVIEW":"Unknown","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-10-30","DATE08":"2023-11-20","DATE09":"2024-01-04","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"187:7:21:7:21:14:208:21:45:21","PROGRESS":52,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-10-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000115596 | PHASE09 | 2023-04-05 | 2023-10-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-10-10 | 986219.85 | 0 |  |  | C000140961 | 986219.85 |  | 96263.05 |  | 0 | 0 |  | 0 |  | 0
90000757 | Absa Parys - Replace broken Glass (INSOG | Absa Parys - Replace broken Glass (INSOG |  |  | Region 3 |  | Unknown | 1000-71537-01 | Unknown Building - not in our database |  | 2023-10-24 |  |  | ASP-CR0510 | CLSD BUDG AVAC RESA: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-12 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000117989 | PHASE11 | 2023-10-24 | 2023-11-23 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-19 | 4672.75 | 0 |  |  | C000117989 | 4672.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000758 | Absa Hartswater - Connect Workstations t | Absa Hartswater - Connect Workstations t |  |  | Region 3 |  | Unknown | 1000-71610-01 | Unknown Building - not in our database |  | 2023-11-02 |  |  | ASP-CR0511 | REL BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-12 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000118636 | PHASE00 | 2023-11-02 | 2023-12-02 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-24 | 14567.57 | 0 |  |  | C000118636 | 14567.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000759 | Absa Butterworth - UPS Replacement | Absa Butterworth - UPS Replacement |  |  | Region 2 | Eastern Cape | 78501X | 1000-71048-01 | High Road Butterworth-Cnr High Rd & Bell St-Butterworth | N | 2023-11-01 | 2023-12-29 |  | ASP-EC0369 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-10-12 | D | 178505.84 |  | 100 | 2023-10-30 | 2023-10-30 | 178505.84 | Absa Ref : 240129_092 | {"MANDT":"111","REFERENCE":90000759,"ONEVIEW":"78501X","DATE01":"2023-10-26","DATE02":"2023-10-26","DATE03":"2023-10-30","DATE04":"2023-11-06","DATE05":"2023-10-30","DATE06":"2023-11-06","DATE07":"2023-11-08","DATE08":"2024-01-24","DATE09":"2024-01-26","DATE10":"2024-02-26","DATE11":"2023-12-28","DATE12":"2023-12-28","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"123:0:4:7:-7:7:2:77:2:0","PROGRESS":93,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-06","FORECAST_END":"2023-11-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDYuMDIuMjAyNDAgRk06IEZpbmFsIFBPQyByZWNlaXZlZC4gIDE1IE5vdiAyMDIzIEJpbGxlZCAyNiBKYW4uIDIwMjQgQWJhIGN1dCBvZmYgMjZGZWIgMjAyNC4KCjI0IEphbiBQT0MgU3VibWl0dGVkIHRvIEZpbmFuY2UKMjIgSmFuIFBNIHRvIGZvbGxvdyB1cCByZSBzaWduIG9mZiBmcm9tIEFic2EKMTggSmFuIFdpdGggQWJzYSBFbmdpbmVlcmluZyBmb3IgU2lnbm9mZgoxMSBEZWMgUE9DIHNlbmQgdG8gQmlkdmVzdCBFbmdpbmVlcmluZyBmb3Igc2lnbm9mZgo3IERlYyBBc3NldCBidWlsZCBDb21wbGV0ZWQgLSBTZW50IHRvIEJWIEVuZ2luZWVyaW5nIGZvciBTaWduIE9mZgo0IERlYyBBc3NldCBCdWlsZCBvdXRzdGFuZGluZywgd2FzIHNlbnQgdG8gYXNzZXQgbWFuYWdlciAyMCBOb3YgZm9yIHVwZGF0ZSAgLSBlc2NhbGF0ZWQgdG8gRU5HCjMwIE5vdiAtIEFzc2V0IGJ1aWxkIHRvIGJlIGNvbXBsZXRlZCB0b2RheSBhbmQgc3VibWl0dGVkIGZvciBTaWdub2ZmCiAyNyBOb3YgUE0gdG8gZm9sbG93IHVwIHdpdGggRW5naW5lZXJpbmcgcmUgYXNzZXQgYnVpbGQKMjMgTm92IEFzc2V0IEJ1aWxkIHBlbmRpbmcgZm9yIFBPQyB0byBiZSBzdWJtaXR0ZWQKMTYgTm92IFBNIHRvIHNlbmQgUE9DIHRvIEVTTSAKOSBOb3YgLSBXb3JrIENvbXBsZXRlZCA4dGggUE9DIHRvIGZvbGxvdwo2IE5vdiAtIFRvIGJlIENvbW1pc3Npb25lZCA4IE5vdgo2IE5vdiAtIFBPIDQ1MDA4NzAzODMgSXNzdWVkIEludGVsY2FiCjMxIE9jdCAtIEFCU0EgUE8gQzAwMDEyMDI2OSByZWNlaXZlZCAtIEJWIFBPIHJlcXVlc3RlZAozMSBPY3QgQWJzYSBQTyBmb2xsb3cgdXAgcmVxdWVzdCBzZW50CjMwIE9jdCBPT0MgUmVxdWVzdCBBcHByb3ZlZCBBYnNhIFBPIFJlcXVlc3RlZAozMCBPY3QgT09DIEFwcHJvdmFsIHJlcXVlc3Qgc3VibWl0dGVkIDMwIE9DVC4KTm90ZTogQnVkZ2V0OiBCdWRnZXQgQXZhaWxhYmxlIGluIFJldGFpbCBFbGVjdHJpY2FsIC0gU2F2aW5ncyBmcm9tIFdhbG1lciBQYXJrIEdlbmVyYXRvciBSZWZ1cmJpc2ggLSBSOThLIGFuZCBNb29ycmVlc2J1cmcgVVBTIEluc3RhbGxhdGlvbiAtIFI4MmsKMjYgT2N0IEFwcHJvdmVkIFBSRiBSZWNlaXZlZCAtIE9PQyBCQyB0byBGb2xsb3cgZm9yIGFwcHJvdmFsCjI2IE9jdCBBcHByb3ZlZCBQUkYgUGVuZGluZwoxNiBPY3QgQXBwcm92ZWQgUFJGIFBlbmRpbmcgLSBCQyB0byBGb2xsb3cgZm9yIGFwcHJvdmFsCjEyIE9jdCAtIFBSRiBQZW5kaW5nCgo=","RATING":"Medium"} |  |  | C000120269 | PHASE11 | 2023-11-06 | 2023-11-08 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-10-31 | 155222.47 | 0 |  |  | C000120269 | 155222.47 |  | 5750 |  | 0 | 5750 |  | 0 |  | 0
90000760 | Absa Vincent Office Park - Connect HVAC to Generator | Absa Vincent Office Park - Connect HVAC to Generator |  |  | Region 2 | Eastern Cape | 79369X | 1000-71071-01 | Vincent Office Park-Western Ave-East London | N | 2023-11-01 | 2023-12-29 |  | ASP-EC0370 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-10-12 | D | 28357.98 |  | 100 | 2023-10-31 | 2023-11-01 | 28357.98 | Absa Ref : 240129_223 | {"MANDT":"111","REFERENCE":90000760,"ONEVIEW":"79369X","DATE01":"2023-10-26","DATE02":"2023-10-26","DATE03":"2023-10-31","DATE04":"2023-11-07","DATE05":"2023-11-01","DATE06":"2023-11-16","DATE07":"2023-11-17","DATE08":"2023-12-18","DATE09":"2024-02-01","DATE10":"2024-02-29","DATE11":"2024-01-15","DATE12":"2024-01-15","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"126:0:5:7:-6:15:1:31:45:26","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-16","FORECAST_END":"2023-11-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggRGVjIFBPQyBTdWJtaXR0ZWQgdG8gRmluYW5jZQoxNCBEZWMgV2l0aCBBYnNhIEVuZ2luZWVyaW5nIGZvciBzaWdub2ZmCjExIERlYyBQTSB0byBmb2xsb3cgdXAgb24gUE9DIHdpdGggTWhvbGkKNyBOb3YgV2l0aCBCViBFbmdpbmVlcmluZyBmb3Igc2lnbm9mZiAtIEZvbGxvdyBVUAozMCBOb3YgV2l0aCBCViBFbmdpbmVlcmluZyBmb3Igc2lnbm9mZgoyNyBOb3YgLSBQT0Mgd2l0aCBCViBlbmdpbmVlcmluZyB0byBTaWdub2ZmIFBNIHRvIGZvbGxvdyB1cAoxNyBOb3YgLSBXb3JrcyBDb21wbGV0ZWQgQ09DIGFuZCBJbnZvaWNlIHRvIGZvbGxvdwoxNiBOb3YgVmVuZG9yIG9uc2l0ZS4gUE0gdG8gZW5nYWdlIEVTTSBpbiByZWdhcmRzIHRvIHByb2JsZW1zIG9uc2l0ZSAuIFRvIGNvbXBsZXRlIGJ5IDE3IE5vdgo5IE5vdiBXb3JrIHRvIGJlIGNvbmR1Y3RlZCAxMyBhbmQgMTQgTm92CjQgTm92IEJWIFBPIFJlY2VpdmVkIDQ1MDA4NzAzMDkgVmhhc2hhCjIgTm92IEFic2EgUE8gQzAwMDEyMDcyMCBSZWNlaXZlZCBCViBQTyBSZXF1ZXN0ZWQKMSBOb3YgQXBwcm92ZWQgT09DIGJ5IEFic2EgRU5HIDEgTm92IEFic2EgUE8gUmVxdWVzdGVkCjMxIE9jdCBTdWJtaXR0ZWQgZm9yIE9PQyBBcHByb3ZhbAozMCBPY3QgdG8gYmUgc3VibWl0dGVkIDMwIE9jdCBmb3IgT09DCjI2IE9jdCBBcHByb3ZlZCBQUkYgUmVjZWl2ZWQgLSBPT0MgQkMgdG8gRm9sbG93IGZvciBhcHByb3ZhbCB0byBiZSBzdWJtaXR0ZWQgMzAgT0NUIGZvciBPT0MKMjYgT2N0IEFwcHJvdmVkIFBSRiBSZWNlaXZlZCAtIE9PQyBCQyB0byBGb2xsb3cgZm9yIGFwcHJvdmFsCjI2IE9jdCBBcHByb3ZlZCBQUkYgUGVuZGluZwoxNiBPY3QgQXBwcm92ZWQgUFJGIFBlbmRpbmcgLSBCQyB0byBGb2xsb3cgZm9yIGFwcHJvdmFsCjEyIE9jdCBQUkYgcGVuZGluZwoKCg==","RATING":""} |  |  | C000120720 | PHASE11 | 2023-11-16 | 2023-11-17 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-02 | 24659.11 | 0 |  |  | C000120720 | 24659.11 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000761 | Absa Active Park - Installation of UPS P | Absa Active Park - Installation of UPS P |  |  | Region 3 |  | Unknown | 1000-71237-01 | Unknown Building - not in our database |  | 2023-11-02 |  |  | ASP-KZ0267 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-12 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000118658 | PHASE00 | 2023-11-02 | 2023-12-02 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-24 | 13064.6 | 0 |  |  | C000118658 | 13064.6 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000762 | Absa Gardens ShopCntr -Dilaps for Revamp | Absa Gardens ShopCntr -Dilaps for Revamp |  |  | Region 2 | Western Cape | 77773X | 1000-70857-01 | Gardens Shopping Centre-Cnr Buitekant & Mill St-Cape Town | N | 2023-11-01 | 2023-12-29 |  | ASP-WC0333 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-10-12 | D | 48415.95 |  | 100 | 2023-10-17 | 2023-10-17 | 48415.95 |  | {"MANDT":"111","REFERENCE":90000762,"ONEVIEW":"77773X","DATE01":"2023-10-10","DATE02":"2023-10-13","DATE03":"2023-10-17","DATE04":"2023-10-24","DATE05":"2023-10-17","DATE06":"2023-11-01","DATE07":"2023-11-06","DATE08":"2023-11-27","DATE09":"2024-01-11","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"113:3:4:7:-7:15:5:21:45:20","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-01","FORECAST_END":"2023-11-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTcgT2N0IEFwcHJvdmVkIDE3IE9jdCBBYnNhIFBPIHRvIGJlIHJlcXVlc3RlZAoxNyBPY3QgUGFjayByZWNlaXZlZCBmcm9tIFBNIGFuZCBzZW50IHRvIENyZXMgVlAgZm9yIHN1cHBvcnQKMTYgT2N0IC0gT25lIHF1b3RlIG91dHN0YW5kaW5nIGZyb20gR0EKMTAgT2N0IFJlcXVlc3QgcmVjZWl2ZWQgcmUgbGltaXRlZCBzY29wZSByZXZhbXAsIERpbGFwcyB0byBiZSBjb25jbHVkZWQgYnkgNiBOb3Y=","RATING":"Low"} |  |  | C000117469 | PHASE11 | 2023-11-01 | 2023-11-06 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-10-18 | 42100.83 | 0 |  |  | C000117469 | 42100.83 |  | 2284.09 |  | 0 | 0 |  | 0 |  | 0
90000763 | Clearwater Dilaps | Clearwater Dilaps |  |  | Region 1 | Gauteng South | 76470X | 1000-71381-01 | Clearwater Mall-Cnr Hendrik Potgieter Rd & Christiaan De Wet Rd-Roodepoort | N | 2023-10-16 | 2023-11-16 |  | ASP-GS0756 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-10-16 | D | 274063.16 |  | 60 | 2023-10-16 | 2023-10-19 | 274063.16 |  | {"MANDT":"111","REFERENCE":90000763,"ONEVIEW":"76470X","DATE01":"2023-08-07","DATE02":"2023-08-14","DATE03":"2023-09-04","DATE04":"2023-09-11","DATE05":"2023-10-02","DATE06":"2023-10-16","DATE07":"2023-11-16","DATE08":"2023-12-07","DATE09":"2024-01-21","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-16","FORECAST_END":"2023-11-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000117988 | PHASE10 | 2023-11-02 | 2024-01-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-10-19 | 238315.79 | 0 |  |  | C000117988 | 238315.79 |  | 23756.05 |  | 0 | 0 |  | 0 |  | 0
90000764 | Absa Jan Kempdorp -Install of plug point | Absa Jan Kempdorp -Install of plug point |  |  | Region 3 |  | Unknown | 1000-71347-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0512 | REL BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-17 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000118211 | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-20 | 5851.57 | 0 |  |  | C000118211 | 5851.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000765 | Absa Welkom - Install palisade fence/Bar | Absa Welkom - Install palisade fence/Bar |  |  | Region 3 | [5 empty] | 2023-11-29 |  |  | ASP-CR0513 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000766 | Absa Mooi River - Supply Furniture & Bli | Absa Mooi River - Supply Furniture & Bli |  |  | Region 3 |  | Unknown | 1000-71242-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0514 | REL BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-18 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000121549 | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-07 | 69582.71 | 0 |  |  | C000121549 | 69582.71 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000767 | Absa Taung Forum - Installation of Water | Absa Taung Forum - Installation of Water |  |  | Region 3 |  | Unknown | 1000-71608-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0515 | CRTD RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000768 | Absa Foreshore Place - Diffusers & Sensor | Absa Foreshore Place - Diffusers & Sensor |  |  | Region 2 | Western Cape | 76937X | 1000-70790-01 | Foreshore Place-Riebeek St-Cape Town | N | 2023-10-26 | 2023-12-29 |  | ASP-WC0334 | REL BUDG AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-10-19 | D | 41865.75 |  | 1 | 2023-10-19 | 2023-10-19 | 41865.75 | Approved Kobus OOC, then cancelled as to be GMP 8 Nov Confirmation Absa PO Cancelled - BV PO to be Cancelled | {"MANDT":"111","REFERENCE":90000768,"ONEVIEW":"76937X","DATE01":"2023-10-19","DATE02":"2023-10-19","DATE03":"2023-10-19","DATE04":"2023-10-26","DATE05":"2023-10-19","DATE06":"2023-10-30","DATE07":"2023-11-03","DATE08":"2023-11-10","DATE09":"2023-12-25","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"164:0:0:7:-7:11:4:7:45:27","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-30","FORECAST_END":"2023-11-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBOb3YgUEMgdG8gZm9sbG93IHVwIHJlIGNhbmNlbGF0aW9uIG9mIFBPCjMgTm92IFBDIHJlcXVlc3RlZCBBYnNhIFBPIHRvIGJlIGNhbmNlbGxlZCB3YXMgUiA0MSA4NjUuNzUgSW5jbCBWYXQKMzAgT2N0IFByb2plY3QgdG8gYmUgY2FuY2VsbGVkIGFzIHRvIGJlIGRvbmUgdmlhIEdNUAoyNSBPY3QgVG8gYmUgY2FuY2VsbGVkIGFuZCBwcm9jZXNzZWQgdmlhIEdNUCBhcyBwZXIgSGVhZCBFbmdpbmVlcmluZywgY29uZmlybWF0aW9uIHJlcXVlc3RlZCBpbiB3cml0aW5nCjI0IE9jdCBCViBQTyBJc3N1ZWQgLSA0NTAwODY3NTYxIC0gQ29hc3RhbCBBaXJjb25kaXRpb25pbmcKMjMgT2N0IEFic2EgUE8gQzAwMDExODM4OSBSZWNlaXZlZCAtIEJWIFBPIFJlcXVlc3RlZAoyMyBPY3QgLSBQQyB0byByZXF1ZXN0IEFic2EgUE8ncyBhcyBwZXIgRVNNIG1haWwgYW5kIGxpc3QgaW4gQ0I0MSBhcyBpdGVtIGZvciBOb3RpbmcKMjAgT2N0IEJGTSBFbmcgcmVxdWVzdGVkIHdhaXQgcHJpb3IgdG8gc3VibWlzc2lvbgo=","RATING":""} |  |  | C000118389 | PHASE12 | 2023-10-30 | 2023-11-03 | RODERICK NEVAY | Michael Maluleka | 0 |  |  |  |  | 2023-10-20 | 36405 | 0 |  |  | C000118389 | 36405 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000769 | Absa Bank Hopetown - Installation of Plu | Absa Bank Hopetown - Installation of Plu |  |  | Region 3 |  | Unknown | 1000-71353-01 | Unknown Building - not in our database |  | 2023-11-03 |  |  | ASP-CR0516 | REL BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-20 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000119149 | PHASE00 | 2023-11-03 | 2023-12-03 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 7998.78 | 0 |  |  | C000119149 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000770 | Absa Blouberg Mall - Kitchen Sink Replac | Absa Blouberg Mall - Kitchen Sink Replac |  |  | Region 3 | Limpopo | 22539X | 1000-70473-01 | Blouberg Mall-Blouberg Rd-Bochum |  | 2023-11-29 |  |  | ASP-LP0182 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-10-20 | D | 0 |  | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000770,"ONEVIEW":"22539X","DATE01":"2023-09-20","DATE02":"2023-09-27","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-01-26","DATE10":"2024-02-26","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"159:7:21:7:21:14:30:21:7:34","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UHJvamVjdCBjb21wbGV0ZS4gCiBGTTogRmluYWwgUE9DIHdhcyByZWNlaXZlZCwgMTkgSkFOIDIwMjQgQmlsbGVkIDI2LjAxLjIwMjQgQWJzYSBDdXQgb2ZmIDI2LjAyLjIwMjM=","RATING":""} |  |  | C000123757 | PHASE11 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-15 | 1954 | 0 |  |  | C000123757 | 1954 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000771 | Various - Corporate EOL LED panels | Various - Corporate EOL LED panels |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-20 | 2024-03-31 |  | ALP-N00058 | CRTD AVAC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | DUPREEZK | 2023-10-20 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000771,"ONEVIEW":"21526X","DATE01":"2023-08-11","DATE02":"2023-08-18","DATE03":"2023-09-08","DATE04":"2023-09-15","DATE05":"2023-10-06","DATE06":"2023-10-20","DATE07":"2024-03-31","DATE08":"2024-04-21","DATE09":"2024-06-05","DATE10":"2024-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-20","FORECAST_END":"2024-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-10-20 | 2024-03-31 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000772 | Various - Retail EOL LED panels | Various - Retail EOL LED panels |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-20 | 2024-03-31 |  | ALP-N00059 | CRTD AVAC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | DUPREEZK | 2023-10-20 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000772,"ONEVIEW":"21526X","DATE01":"2023-08-11","DATE02":"2023-08-18","DATE03":"2023-09-08","DATE04":"2023-09-15","DATE05":"2023-10-06","DATE06":"2023-10-20","DATE07":"2024-03-31","DATE08":"2024-04-21","DATE09":"2024-06-05","DATE10":"2024-06-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-20","FORECAST_END":"2024-03-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-10-20 | 2024-03-31 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000773 | Absa Primrose Install of Roller Shutter | Absa Primrose Install of Roller Shutter |  |  | Region 1 | Gauteng South | 76610X | 1000-70297-01 | Primrose Mall-Randfontein Rd-Germiston | N | 2023-10-23 | 2023-11-23 |  | ASP-GS0757 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-10-23 | D | 48488.6 |  | 60 | 2023-10-26 | 2023-11-07 | 48488.6 |  | {"MANDT":"111","REFERENCE":90000773,"ONEVIEW":"76610X","DATE01":"2023-08-14","DATE02":"2023-09-21","DATE03":"2023-10-09","DATE04":"2023-10-11","DATE05":"2023-11-07","DATE06":"2023-11-21","DATE07":"2023-12-22","DATE08":"2024-01-12","DATE09":"2024-02-26","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":60,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"199:38:18:2:27:14:31:21:45:15","PROGRESS":11,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-21","FORECAST_END":"2023-12-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDg6MTE6MjAyMyBBUyBwcm9qZWN0IGFwcHJvdmVkIGF0IENCIDQyIGRlY2suIHdhaXRpbmcgZm9yIEFic2EgUE8u","RATING":"Low"} |  |  | C000122184 | PHASE11 | 2023-11-23 | 2023-11-24 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  | 2023-11-07 |  | 2023-11-09 | 42164 | 0 |  |  | C000122184 | 42164 |  | 4355.05 |  | 0 | 0 |  | 0 |  | 0
90000774 | Absa Boksburg 2 roller Shutters | Absa Boksburg 2 roller Shutters |  |  | Region 1 | Gauteng South | 76384X | 1000-70238-01 | Boksburg-Cnr Burg & Commissioner St-Boksburg |  | 2023-10-23 | 2023-11-23 |  | ASP-GS0758 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-10-23 | D | 232150.16 |  | 60 | 2023-10-26 | 2023-11-07 | 232150.16 |  | {"MANDT":"111","REFERENCE":90000774,"ONEVIEW":"76384X","DATE01":"2023-08-14","DATE02":"2023-10-04","DATE03":"2023-10-10","DATE04":"2023-10-11","DATE05":"2023-11-07","DATE06":"2023-11-21","DATE07":"2023-12-22","DATE08":"2024-01-12","DATE09":"2024-02-26","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":60,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"199:51:6:1:27:14:31:21:45:16","PROGRESS":11,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-21","FORECAST_END":"2023-12-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDg6MTE6MjAyMyBBUyBwcm9qZWN0IGFwcHJvdmVkIGF0IENCIDQyIGRlY2suIHdhaXRpbmcgZm9yIEFic2EgUE8=","RATING":""} |  |  | C000121886 | PHASE11 | 2023-11-24 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-08 | 201869.7 | 0 |  |  | C000121886 | 201869.7 |  | 20082.11 |  | 0 | 0 |  | 0 |  | 0
90000775 | Absa Southdale Close off Tellers | Absa Southdale Close off Tellers |  |  | Region 1 |  | 22679X | 1000-70073-01 | Atm Southdale Shopping Centre-Cnr Alamein & Landsborough St-Johannesburg | N | 2023-10-23 | 2023-11-23 |  | ASP-GS0759 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-10-23 | D | 140056.68 |  | 100 | 2023-10-26 | 2023-10-26 | 140056.68 |  | {"MANDT":"111","REFERENCE":90000775,"ONEVIEW":"22679X","DATE01":"2023-08-14","DATE02":"2023-10-05","DATE03":"2023-09-29","DATE04":"2023-10-02","DATE05":"2023-10-25","DATE06":"2023-11-08","DATE07":"2023-12-09","DATE08":"2023-12-30","DATE09":"2024-02-13","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"170:52:-6:3:23:14:31:21:45:3","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-08","FORECAST_END":"2023-12-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QkMgYXBwcm92ZWQgMjYvMTAvMjAyMyBBd2FpdGluZyBBYnNhIGFuZCBCRk0gUE9z","RATING":""} |  |  | C000119692 | PHASE11 | 2023-11-17 | 2023-12-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-10-30 | 121788.41 | 0 |  |  | C000119692 | 121788.41 |  | 12711.97 |  | 0 | 0 |  | 0 |  | 0
90000776 | ATW -Villa of Hope Repair Wall and paint | ATW -Villa of Hope Repair Wall and paint |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-10-23 | 2023-11-23 |  | ASP-GS0760 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-10-23 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE11 | 2023-10-23 | 2023-11-23 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000097682 | 47338 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000777 | Absa Welkom Pick & Pay - DILAPS | Absa Welkom Pick & Pay - DILAPS |  |  | Region 3 | [5 empty] | 2023-11-28 |  |  | ASP-CR0517 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-28 | 2023-12-28 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000778 | Absa Laingsburg - COC Phase 2 Remedial Work | Absa Laingsburg - COC Phase 2 Remedial Work |  |  | Region 2 | Western Cape | 78112X | 1000-70886-01 | Absa Laingsburg-Voortrekker Rd-Laingsburg | N | 2023-11-13 | 2023-12-29 |  | ASP-WC0335 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-10-24 | D | 63159.38 |  | 1 | 2023-11-01 |  | 0 | Declined By Absa ENG - BV ENG to advise a | {"MANDT":"111","REFERENCE":90000778,"ONEVIEW":"78112X","DATE01":"2023-10-23","DATE02":"2023-10-24","DATE03":"2023-11-01","DATE04":"2023-11-01","DATE05":"2023-11-03","DATE06":"2023-11-09","DATE07":"2023-11-11","DATE08":"2023-11-15","DATE09":"2023-12-30","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"160:1:8:0:2:6:2:4:45:2","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-09","FORECAST_END":"2023-11-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBOb3YgUE0gZm9sbG93IHVwIHdpdGggRW5naW5lZXJpbmcgcmUgdGhlIFBPIGZvciB0aGUgcmVtZWRpYWwgd29yayBQTy4KMyBOb3YgUEUgY29uZmlybWVkIHJlbWVkaWFsIHdvcmsgdG8gYmUgR01QCjEgTm92IFN1Ym1pdHRlZCB0byBBYnNhIEVuZyBmb3IgU3VwcG9ydCAtIENoYWxsZW5nZWQgYnkgQWJzYSBFbmcgYXMgR01QLCBCViBFbmcgdG8gYWR2aXNlLgoyNSBPY3QgQkMgQ29tcGlsYXRpb24gb2YgRGlsYXBzIHdvcmtzIHRvIGJlIHVuZGVydGFrZW4gdGhlIHJlbWVkaWFsIHBvcnRpb24gdG8gYmUgZG9uZSB2aWEgR01QCjI0IE9jdCBQUkogTnVtYmVyIFJlcXVlc3RlZAo=","RATING":"Low"} |  |  |  | PHASE12 | 2023-11-09 | 2023-11-11 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000779 | Absa Rosstax Minor Works | Absa Rosstax Minor Works |  |  | Region 1 | Gauteng North | 76646X | 1000-70301-01 | Rosstax Centre-Cnr R566 & Hardie Muller St-Rosslyn | N | 2023-10-02 | 2023-11-30 |  | ALP-GN0015 | REL BUDG SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | L |  | GAMIETR | 2023-10-24 | D | 0 |  | 40 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000779,"ONEVIEW":"76646X","DATE01":"2023-07-24","DATE02":"2023-07-31","DATE03":"2023-08-21","DATE04":"2023-08-28","DATE05":"2023-09-18","DATE06":"2023-10-02","DATE07":"2023-11-30","DATE08":"2023-12-21","DATE09":"2024-02-04","DATE10":"2024-02-29","DATE11":"2024-02-04","DATE12":"2024-02-04","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":9,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-02","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMS8yMTogV0Egc2VudCB0byBBYnNhIGxlZ2FsLgou","RATING":""} |  |  |  | PHASE05 | 2023-10-02 | 2023-11-30 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000142619 | 1561584.35 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000780 | Absa Top Road Shade Netting | Absa Top Road Shade Netting 1.Supply and install new galvanized steel structure including support beams. 2.Supply and install new Knittex 100 shade netting including tension cables and tensioners for all 45 double carports. 3. Supply and install new Knittex 100 shade netting including tension cables and tensioners for 2 single carports. 4.Remove all old rusted uprights from site. 5.Excavate and plant new galvanized uprights and concrete in 6.Remove old netting and steel from site. 7.Clean to site before handover to the client. |  |  | Region 1 | Gauteng South | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg | N | 2023-10-02 | 2023-11-02 |  | ALP-GS0076 | REL BUDG AVAC RESA SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | F |  | GAMIETR | 2023-10-24 | D | 1773655 | Supported by CRES FM | 60 | 2023-09-04 | 2023-09-07 | 1773655 | Request to issued BFM while WA & SFA in process. | {"MANDT":"111","REFERENCE":90000780,"ONEVIEW":"78451X","DATE01":"2023-07-24","DATE02":"2023-07-31","DATE03":"2023-08-21","DATE04":"2023-08-28","DATE05":"2023-09-18","DATE06":"2023-10-02","DATE07":"2023-11-02","DATE08":"2023-11-23","DATE09":"2024-01-07","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":70,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":12,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-10-02","FORECAST_END":"2023-11-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE07 | 2023-11-13 | 2023-12-14 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-10-30 |  |  |  |  | 0 | 0 |  |  | C000130349 | 1542308.38 |  | 133957 |  | 0 | 0 |  | 0 |  | 0
90000781 | Absa Auckland Park CC Replace 6 older hy | Absa Auckland Park CC Replace 6 older hydro Taps. |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-04-05 |  |  | ALP-GS0077 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-10-24 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000781,"ONEVIEW":"","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Q2xvc2luZyBlbmdpbmVlcmluZyBjb21tZW50IC0gcHJvdmlkZSBpbiBpbnRlcm5hbCByZXZpZXcgYm9hcmQs","RATING":""} |  |  |  | PHASE05 | 2024-04-11 | 2024-05-11 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000148138 | 585948.7 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000782 | Absa Auckland Park- Tiling to reception and lobby areas | Hack out existing tiles and prepare screeds for new tiling. Lay tiles to adhesive and flush the joints |  |  | Region 1 | Gauteng South | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | N | 2023-04-05 |  |  | ALP-GS0078 | CRTD: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-10-24 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000782,"ONEVIEW":"","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-05-05","DATE08":"2023-05-26","DATE09":"2023-07-10","DATE10":"2023-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":80,"PROG03":80,"PROG04":0,"PROG05":20,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2023-04-05 | 2023-05-05 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000783 | Absa 291 Anton Lembede (Durban City) Sec | Absa 291 Anton Lembede (Durban City) Sec |  |  | Region 3 |  | 77987X | 1000-71206-01 | Absa 291 Anton Lembede Street-Anton Lembede St-Durban |  | 2023-11-27 | 2023-11-30 |  | ASP-KZ0268 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-25 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000119244 | PHASE00 | 2023-11-27 | 2023-11-30 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-26 | 148565.27 | 0 |  |  | C000119244 | 148565.27 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000784 | Absa Orkney - PC Board Replacement | Absa Orkney - PC Board Replacement |  |  | Region 3 |  | Unknown | 1000-71304-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0518 | CLSD BUDG ACPT AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-26 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000784,"ONEVIEW":"Unknown","DATE01":"2023-09-20","DATE02":"2023-09-27","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000120452 | PHASE11 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-01 | 29475.64 | 0 |  |  | C000120452 | 29475.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000785 | Absa Burgersdorp - Connect DVR to UPS | Absa Burgersdorp - Connect DVR to UPS |  |  | Region 2 | Eastern Cape | 79098X | 1000-71063-01 | Absa Burgersdorp-Pieter Retief St-Burgersdorp | N | 2023-11-13 | 2023-12-29 |  | ASP-EC0371 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-10-26 | D | 9748.15 |  | 100 | 2023-10-31 | 2023-10-31 | 9748.15 | Absa Ref : 240129_095 | {"MANDT":"111","REFERENCE":90000785,"ONEVIEW":"79098X","DATE01":"2023-10-26","DATE02":"2023-10-26","DATE03":"2023-10-31","DATE04":"2023-11-07","DATE05":"2023-10-31","DATE06":"2023-11-08","DATE07":"2023-11-08","DATE08":"2023-11-14","DATE09":"2023-12-29","DATE10":"2023-12-31","DATE11":"2023-12-30","DATE12":"2023-12-30","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"66:0:5:7:-7:8:0:6:45:1","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-08","FORECAST_END":"2023-11-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQgRGVjIFBPQyBTdWJtaXR0ZWQgLSBSIDk3NDguMTUKMTEgRGVjIFBNIGZvbGxvd2VkIHVwIG9uIHRoZSBQT0Mgc2lnbm9mZgo3IERlYyAtIHRvIGZvbGxvdyB1cCByZSBzaWduIG9mZiBieSBBYnNhIEVuZ2luZWVyaW5nCjMwIE5vdiAtIFdpdGggQWJzYSBFbmcgZm9yIFNpZ25vZmYKMjcgTm92IFNldCB0byBCViBFbmdpbmVlcmluZyBmb3IgU2lnbm9mZgoyMyBOb3YgUGF5bWVudCBDZXJ0IHRvIGJlIHNpZ25lZCBvZmYgYnkgUlBNLiBSZXNlbnQgYXMgd2FzIHNpZ25lZAo5IE5vdiAtIFdvcmsgY29tcGxldGVkIDggTm92IENPQyBhbmQgaW52b2ljZSB0byBmb2xsb3cKNiBOb3YgVmVuZG9yIG9uIHNpdGUgNiBOb3YKMiBOb3YgQlYgUE8gSXNzdWVkIDQ1MDA4Njk5NTcgVmhhc2hhCjEgTm92IEFic2EgUE8gQzAwMDEyMDM3NiBSZWNlaXZlZCBCViBQTyBSZXF1ZXN0ZWQKMzEgT2N0IEFwcHJvdmVkIE9PQyBBcHByb3ZhbCBBYnNhIFBPIFJlcXVlc3RlZAozMSBPY3QgU3VibWl0dGVkIGZvciBPT0MgYXBwcm92YWwKMzAgT2N0IHRvIGJlIHN1Ym1pdHRlZCAzMCBPY3QKMjYgT2N0IFBNIHRvIGZvbGxvdyB1cCBvbiBhZGRpdGlvbmFsIFF1b3RlcwoyMyBPY3QgUE0gdG8gcmVxdWVzdCBBZGRpdGlvbmFsIFF1b3RlcwoyMCBPY3QgUFJGIFJlY2VpdmVkCg==","RATING":""} |  |  | C000120376 | PHASE11 | 2023-11-08 | 2023-11-08 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-01 | 8476.65 | 0 |  |  | C000120376 | 8476.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000786 | Absa Moffett Office Park - High Desks & Chatterbox s | Absa Moffett Office Park - High Desks |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2023-11-13 | 2023-12-29 |  | ASP-EC0372 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-10-26 | D | 44746.27 |  | 100 | 2024-02-08 | 2024-02-13 | 44746.27 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000786,"ONEVIEW":"22937X","DATE01":"2023-10-20","DATE02":"2023-11-24","DATE03":"2024-02-08","DATE04":"2024-02-08","DATE05":"2024-02-13","DATE06":"2024-02-27","DATE07":"2024-03-01","DATE08":"2024-03-22","DATE09":"2024-05-06","DATE10":"2024-05-31","DATE11":"2024-05-06","DATE12":"2024-05-06","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"224:35:76:0:5:14:3:21:45:-20:-20:23","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-27","FORECAST_END":"2024-03-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFBDIHRvIGZvbGxvdyB1cCBvbiB0aGUgUE8ncyBmcm9tIFJlYWwgRXN0YXRlCjEzIEZlYiAtIEFwcHJvdmVkIGJ5IFJlYWwgRXN0YXRlIFBPIFBlbmRpbmcKMTIgRmViIMOiwoDCkyBDUkVTIFZQIFN1Ym1pdHRlZCB0byBSZWFsIEVzdGF0ZSBmb3IgQXBwcm92YWwsIDQ0MTfDosKAwplzIFBlbmRpbmcKOCBGZWIgQ29zdCBhbmQgUGFjayBzZW50IHRvIFZQIHRvIGFkdmlzZSBvbiBGdW5kaW5nCjYgRmViIEZvbGxvdyB1cCBzZW50IHJlIERyYXdpbmdzCjUgRmViIC0gQWxsIHF1b3RlcyByZWNlaXZlZCBQTSB0byBzdWJtaXQgZm9yIENSRVMgYXBwcm92YWwKMiBGZWIgRHJhd2luZ3MgcmVxdWVzdGVkCjI5IEphbiBRdW90ZXMgdG8gYmUgc3VibWl0dGVkIDI5IEphbgoyMiBKYW4gLSBRdW90ZXMgcmVjZWl2ZWQgdG8gcmVsb2NhdGUgLSB0byBiZSBvYnRhaW5lZCBmb3IgRWxlY3RyaWNhbAoxNCBEZWMgUXVvdGVzIHRvIGJlIFJlcXVlc3RlZCB0byByZW1vdmUgdGhlIEhpZ2ggRGVzayBmcm9tIENQVCBhbmQgaW5zdGFsbCBpbiBNb2ZmZXR0CjExIERlYyBQTXMgdG8gZW5nYWdlIGluIHJlZ2FyZHMgdG8gcmVsb2NhdGlvbiBvZiB0aGUgZGVza3MgZnJvbSBDYXBlIFRvd24gdG8gUEUKNCBEZWMgLSBQTSdzIHRvIGVuZ2FnZSByZSB0aGUgcmVsb2NhdGlvbiBvZiB0aGUgZGVza3MgZnJvbSBDYXBlIFRvd24gdG8gUEUKMjcgTm92IFBtIHRvIGdldCBjb3N0cyB0byBnZXQgZGVzayBmcm9tIENhcGUgVG93bgoxNiBOb3YgLSBDb3N0IGZvciBIaWdoIERlc2sgY2x1c3RlciBuZWVkcyB0byBiZSBvYnRhaW5lZCwgQ2hhdHRlcmJveGVzIG5vIGxvbmdlciByZXF1aXJlZCwgdG8gYmUgYXBwcm92ZWQgYXQgUklGCjcgTm92IE9uIGhvbGQgcGVuZGluZyBkZWNpc2lvbiBmcm9tIHJlZ2lvbiByZSBIaWdoIGRlc2tzIGFuZCBDaGF0dGVyIEJveGVzCjYgTm92IFBNIGVucXVpcmluZyB3aXRoIENPIERlc2lnbnMgcmUgb3B0aW9ucyB0byBCdXkgb3IgUmVudCBmb3IgMiBZZWFycwozMCBPY3QgLSBSUE0gdG8gZm9sbG93IHVwIG9uIGRyYXdpbmdzIGRvIHNpdGUgdmlzaXQgd2l0aCBQTSAxIE5vdgoyNyBPY3QgQ3JlcyBWUCB0byBzaGFyZSBkcmF3aW5ncyBvZiBwcm9wb3NlZCBsb2NhdGlvbnMgZm9yIHRoZSBkZXNrcyB0byB2ZXJpZnkgaW5zdGFsbGF0aW9uIHNwZWNpZmljYXRpb25zCjIzIE9jdCBQTSB0byByZXF1ZXN0IHVwZGF0ZWQgZHJhd2luZ3MgYW5kIGRldGFpbHMgb2YgcmVxdWlyZW1lbnRzCjIwIE9jdCBQUkYgcmVjZWl2ZWQ=","RATING":""} |  |  | C000143411 | PHASE08 | 2024-02-27 | 2024-03-05 | RODERICK NEVAY | Nokuthula Manzini | 0 |  |  |  |  | 2024-02-19 | 38909.8 | 0 |  |  | C000143411 | 38909.8 |  | 3246.22 |  | 0 | 0 |  | 0 |  | 0
90000787 | Alice lane North Floor Blinds - new blin | Alice lane North Floor Blinds - new blin |  |  | Region 1 |  | Unknown | 1000-71378-01 | Unknown Building - not in our database |  | 2023-04-05 |  |  | ASP-GS0761 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-10-26 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000120717 | PHASE06 | 2023-12-10 | 2023-12-10 | CHRISTOPHER MPOFU | Michael Maluleka | 0 |  |  |  |  | 2023-11-02 | 296553.51 | 0 |  |  | C000120717 | 296553.51 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000788 | Absa Musgrave Rd - DILAPS | Absa Musgrave Rd - DILAPS |  |  | Region 3 |  | Unknown | 1000-71620-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-KZ0269 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000130152 | 21084.42 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000789 | Absa Newcastle - Construction of Bund Wa | Absa Newcastle - Construction of Bund Wa |  |  | Region 3 |  | Unknown | 1000-71215-01 | Unknown Building - not in our database |  | 2023-11-16 |  |  | ASP-KZ0270 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-27 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000789,"ONEVIEW":"Unknown","DATE01":"2023-09-07","DATE02":"2023-09-14","DATE03":"2023-10-05","DATE04":"2023-10-12","DATE05":"2023-11-02","DATE06":"2023-11-16","DATE07":"2023-12-16","DATE08":"2024-01-06","DATE09":"2024-01-26","DATE10":"2024-02-26","DATE11":"2024-02-20","DATE12":"2024-02-20","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":100,"PROG10":100,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"175:7:21:7:21:14:30:21:20:9","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-16","FORECAST_END":"2023-12-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDYuMDIuMjAyNCBGTSBGaW5hbCBQT0MgcmVjZWl2ZWQgMjkuMTEuMjAyMyBCaWxsZWQgMjYuMDEuMjAyNCBBYnNhIEN1dG9mZiBkYXRlIDI2LjAyLjIwMjQu","RATING":""} |  |  | C000119679 | PHASE10 | 2023-11-16 | 2023-12-16 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-10-28 | 66488.23 | 0 |  |  | C000119679 | 66488.23 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000790 | Absa Mimosa Mall - Connect Teller comput | Absa Mimosa Mall - Connect Teller comput |  |  | Region 3 |  | Unknown | 1000-71542-01 | Unknown Building - not in our database |  | 2023-12-07 |  |  | ASP-CR0519 | REL BUDG AVAC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-31 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000125069 | PHASE00 | 2023-12-07 | 2024-01-06 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-21 | 9096.51 | 0 |  |  | C000125069 | 9096.51 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000791 | Absa Vryburg - Gate Replacement | Absa Vryburg - Gate Replacement |  |  | Region 3 | [5 empty] | 2023-11-29 |  |  | ASP-CR0520 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-31 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000792 | Absa Thulamahashi - Reinstatement | Absa Thulamahashi - Reinstatement |  |  | Region 3 | Limpopo | 79265X | 1000-70559-01 | Thulamahashe Plaza-Main Rd-Phalaborwa |  | 2023-11-29 |  |  | ASP-LP0183 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  | L |  | NOMNGANGAL | 2023-10-31 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000792,"ONEVIEW":"79265X","DATE01":"2023-09-20","DATE02":"2023-09-27","DATE03":"2023-10-18","DATE04":"2023-10-25","DATE05":"2023-11-15","DATE06":"2023-11-29","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-29","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000129469 | PHASE10 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 |  |  |  |  | 2023-12-06 | 588234.86 | 0 |  |  | C000129469 | 588234.86 |  | 6719.21 |  | 0 | 0 |  | 0 |  | 0
90000793 | Absa Thaba Mall - Additional Consultant | Absa Thaba Mall - Additional Consultant |  |  | Region 3 |  | Unknown | 1000-70507-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-LP0184 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-10-31 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000149955 | 58423.66 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000794 | Retail Various Sites-UPS Batteries Repla | Retail Various Sites-UPS Batteries Repla |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-30 | 2024-06-28 |  | ALP-N00060 | REL BUDG AVAC SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-10-31 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-30 | 2024-06-28 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000143223 | 610633.04 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000795 | Absa Wellington - Motorised Gate | Absa Wellington - Motorised Gate |  |  | Region 2 | Western Cape | 77126X | 1000-70801-01 | Wellington-Cnr Church & Prince St-Wellington | N | 2023-11-20 | 2023-12-29 |  | ASP-WC0336 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-11-01 | D | 44917.35 |  | 100 | 2024-03-13 | 2024-03-20 | 44917.35 | Absa Ref : 240402_002 Retail Reprioritised | {"MANDT":"111","REFERENCE":90000795,"ONEVIEW":"77126X","DATE01":"2023-10-31","DATE02":"2023-12-08","DATE03":"2024-03-13","DATE04":"2024-03-20","DATE05":"2024-03-20","DATE06":"2024-05-15","DATE07":"2024-05-31","DATE08":"2024-06-21","DATE09":"2024-08-05","DATE10":"2024-08-31","DATE11":"2024-08-05","DATE12":"2024-08-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"305:38:96:7:0:56:16:21:45:45:45:4","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggU2lnbmVkIERlY2sgcmVjZWl2ZWQgIC0gQWJzYSBQTyBSZXF1ZXN0ZWQKMTkgTWFyY2ggQ0IgRGVjayBhcHByb3ZlZCBzaWduZWQgZGVjayBwZW5kaW5nIHRvIHJlcXVlc3QgUE8ncwoxMyBNYXJjaCBTdWJtaXR0ZWQgZm9yIENCMDkgLSBSIDQ0IDkxNy4zNQoxMSBNYXJjaCAtIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEFsdGVybmF0ZSBWZW5kb3JzIC0gcmUgR2F0ZXMgLSBDdXJyZW50ICstUjQ1awo0IE1hcmNoIC0gUXVvdGVzIHJlY2VpdmVkIEVsZWN0cmljYWwgdG8gYmUgY29uZmlybWVkCjI2IEZlYiAtIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEZhYnJpYyBWZW5kb3JzIGFuZCB3aXRoIEZNIGZvciBzdWl0YWJsZSBzdXBwbGllcgoxMiBGZWIgLSBQTSB0byBmb2xsb3cgdXAgb24gUXVvdGVzCjUgRmViIC0gUXVvdGVzIGR1ZSB3ZWVrIG9mIHRoZSA1dGgKMjkgSmFuIFBNIHRvIGZvbGxvdyB1cCBvbiBRdW90ZXMKMjIgSmFuIFF1b3RlcyBmb3IgbW90b3IgdG8gYmUgc291cmNlZAoxMSBEZWMgUE0gdG8gZm9sbG93IHVwIGFzIHZlbmRvcnMgdW5hYmxlIHRvIHByb3ZpZGUgcXVvdGVzCjQgRGVjIC0gUE0gdG8gZm9sbG93IHVwIGFzIFZlbmRvcnMgdW5hYmxlIHRvIHByb3ZpZGUgcXVvdGVzCjI3IE5vdiBTdGlsbCBhd2FpdGluZyBvbiBxdW90ZXMuIEFsbCB2ZW5kb3JzIGhhdmVuJ3Qgc2VudCBxdW90ZXMuIFdpbGwgcmVhY2ggb3V0IHRvIG1haW50ZW5hbmNlIHZlbmRvcnMgZm9yIGFzc2lzdGFuY2UKMjAgTm92IFZlbmRvcnMgLSBRdW90ZXMgb3V0c3RhbmRpbmcgLSBubyByZXNwb25zZQo2IE5vdiBRdW90ZXMgb3V0c3RhbmRpbmcgaW4gb3JkZXIgdG8gY29tcGxldGUgQkMKMDEgTm92IFF1b3RlcyByZXF1ZXN0ZWQgdG8gY29tcGxldGUgQkMKMzEgT2N0IEFwcHJvdmVkIFBSRiByZWNlaXZlZCBhbmQgc2l0ZSB2aXNpdCBjb25kdWN0ZWQgdG8gZGV0ZXJtaW5lIFNjb3BlLg==","RATING":""} |  |  | C000151209 | PHASE06 | 2024-05-15 | 2024-05-31 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-03-27 | 39058.57 | 0 |  |  | C000151209 | 39058.56 |  | 1267.5 |  | 0 | 0 |  | 0 |  | 0
90000796 | Absa Ntabankulu - Insurance Claim - HVAC Replacement (Retrospective) | Absa Ntabankulu - Insurance Claim - HVAC Replacement (Retrospective) |  |  | Region 2 | Eastern Cape | 20949X | 1000-70921-01 | Ntabankulu-Main St-Ntabankulu | N | 2023-01-26 | 2023-01-26 |  | ASP-EC0373 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-11-02 | D | 347159.29 |  | 100 | 2023-04-20 | 2023-04-20 | 347159.29 | Insurance Claim - HVAC Replacement (Retrospective) | {"MANDT":"111","REFERENCE":90000796,"ONEVIEW":"20949X","DATE01":"2023-04-20","DATE02":"2023-04-20","DATE03":"2023-04-20","DATE04":"2023-04-27","DATE05":"2023-04-20","DATE06":"2023-04-20","DATE07":"2023-04-20","DATE08":"2023-11-10","DATE09":"2023-12-25","DATE10":"2023-12-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:0:0:7:-7:0:0:204:45:28","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-20","FORECAST_END":"2023-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MiBOb3YgUmFpc2VkIGFzIG91dHN0YW5kaW5nIGR1ZSB0byBhbWVuZGVkIHByb2Nlc3MgLSBBYnNhIFBPIFJlcXVlc3RlZA==","RATING":""} |  |  | C000125714 | PHASE11 | 2023-04-20 | 2023-04-20 | RODERICK NEVAY | Juanita van Coller | 0 |  |  |  |  | 2023-11-23 | 301877.64 | 0 |  |  | C000121244 | 301877.64 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000797 | Absa Patensie - Structural DD | Absa Patensie - Structural DD |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2023-11-27 | 2023-12-29 |  | ASP-EC0374 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-11-06 | D | 0 |  | 1 |  |  | 0 | Cancelled to be part of Bulk PO ALP-N00061 | {"MANDT":"111","REFERENCE":90000797,"ONEVIEW":"77876X","DATE01":"2023-11-06","DATE02":"2023-11-06","DATE03":"2023-12-01","DATE04":"2023-12-08","DATE05":"2023-12-29","DATE06":"2024-01-12","DATE07":"2024-02-13","DATE08":"2024-03-05","DATE09":"2024-04-19","DATE10":"2024-04-30","DATE11":"2024-04-19","DATE12":"2024-04-19","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"146:0:25:7:21:14:32:21:45:2","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-01-12","FORECAST_END":"2024-02-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgRGVjIFBNIHRvIHN1Ym1pdCBCQyBwYWNrIGZvciBhcHByb3ZhbAo3IERlYyBCQyB0byBiZSBzdWJtaXR0ZWQgZm9yIGFwcHJvdmFsIGJ5IEFic2EKMjcgTm92IEJDIHRvIGJlIHByZXBhcmVkIGZvciBTdWJtaXNzaW9uIHRvIEFic2EKMjMgTm92IFBNIHRvIHJlcXVlc3QgYWRkaXRpb25hbCBxdW90ZXMKMTcgTm92IFF1b3RlIFJlY2VpdmVkICstUjIwMGsgYWRkaXRpb25hbCBxdW90ZXMgdG8gYmUgc291cmNlZAoxNiBOb3YgUE0gaGFzIHJlcXVlc3RlZCBxdW90ZSBmcm9tIHRoZSBwcm9wb3NlZCBzdHJ1Y3R1cmFsIEVuZ2luZWVyCjkgTm92IFBNIHRvIGZpbmQgYWx0ZXJuYXRlIFF1b3RlcyBhcyB2ZW5kb3IgY2FuIG9ubHkgYXR0ZW5kIGluIDIwMjQsIHByb2N1cmVtZW50IHRvIGJlIGFwcHJvYWNoZWQgZm9yIEFsdGVybmF0ZSBRdW90ZQo2IE5vdiAtIFBNIHRvIGdldCB1cGRhdGVkIHF1b3RlIGZyb20gVmVuZG9yIHJlIGluZGljYXRpbmcgdGhlIGRlbGl2ZXJhYmxlcwozIE5vdiBQUkYgcmVjZWl2ZWQgdG8gZG8gc3RydWN0dXJhbCBERCAvIEluc3BlY3Rpb24=","RATING":""} |  |  |  | PHASE12 | 2024-01-12 | 2024-02-13 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000798 | Absa Hatfield Replac Faulty 10 UPS | Installation of EATON 9SX 11000I Power module 11000VKA Installation of Eaton rack kit Installation of Eaton network card Installation of maintenance bypass switch Commissioning of the new 10KVAUPS |  |  | Region 1 |  | 77036X | 1000-70346-01 | Hatfield Mall-Burnett St-Hatfield |  | 2023-11-06 | 2023-12-06 |  | ASP-GN0235 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-06 | D | 161278.7 |  |  | 2023-10-30 |  | 161278.7 | 16.11 NN: No funding for the project, funds to be allocated | {"MANDT":"111","REFERENCE":90000798,"ONEVIEW":"77036X","DATE01":"2023-09-29","DATE02":"2023-10-06","DATE03":"2023-10-27","DATE04":"2023-11-03","DATE05":"2023-11-09","DATE06":"2023-11-22","DATE07":"2023-11-24","DATE08":"2023-12-15","DATE09":"2024-01-29","DATE10":"2024-01-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:6:13:2:21:45:19","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-22","FORECAST_END":"2023-11-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDcuMTEgTk46IEJDIHJlYWR5IGF3YWl0aW5nIGJ1ZGdldCBjb25maXJtYXRpb24gYW5kIGNvc3QgYm9hcmQgYXBwcm92YWw=","RATING":""} |  |  |  | PHASE09 | 2024-01-22 | 2024-01-24 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000799 | Absa 270 Republic Rd Directional Signage | Absa 270 Republic Rd Directional Signage |  |  | Region 1 | Gauteng | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-11-06 | 2023-12-06 |  | ASP-GS0762 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | GAMIETR | 2023-11-06 | D | 126698.83 |  | 15 | 2023-11-07 |  | 0 |  | {"MANDT":"111","REFERENCE":90000799,"ONEVIEW":"21335X","DATE01":"2023-08-28","DATE02":"2023-11-07","DATE03":"2023-10-25","DATE04":"2023-10-13","DATE05":"2023-11-07","DATE06":"2023-11-21","DATE07":"2023-11-14","DATE08":"2023-12-05","DATE09":"2024-01-19","DATE10":"2024-01-31","DATE11":"2024-01-19","DATE12":"2024-01-19","PROG01":0,"PROG02":80,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":100,"PROG07":100,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"185:71:-13:-12:25:14:-7:21:45:4","PROGRESS":74,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-21","FORECAST_END":"2023-11-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Mjk6MTE6MjMgQVM6IHNjb3BlIHZlcmlmaWNhdGlvbg==","RATING":""} |  |  |  | PHASE08 | 2023-11-21 | 2023-11-14 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 11443.08 |  | 0 | 0 |  | 0 |  | 0
90000800 | Absa Towers West HVAC - Upgrade of the R | Ricard Diffuser System Repair & Recommissioning |  |  | Region 1 | Gauteng | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-04-05 | 2023-12-31 |  | ALP-GS0079 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  | F |  | GAMIETR | 2023-11-06 | D | 1580722.21 |  | 100 | 2023-10-31 | 2023-11-03 | 1580722.21 |  | {"MANDT":"111","REFERENCE":90000800,"ONEVIEW":"21526X","DATE01":"2023-07-03","DATE02":"2023-07-31","DATE03":"2023-08-31","DATE04":"2023-09-30","DATE05":"2023-10-31","DATE06":"2024-02-29","DATE07":"2024-04-30","DATE08":"2024-05-21","DATE09":"2024-07-05","DATE10":"2024-07-31","DATE11":"2024-07-05","DATE12":"2024-07-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:28:31:30:31:121:61:21:45:25","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-29","FORECAST_END":"2024-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"IDIwMjMvMTIvMDY6IFN0aWxsIGF3YWl0aW5nIFdBIGFwcHJvdmFsIGZyb20gQWJzYSBsZWdhbC4=","RATING":""} |  |  |  | PHASE05 | 2024-02-29 | 2024-04-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | NO FUNDING | 1374722.79 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000801 | 20 Goldman Str - Install frosting vinyl | Apply frosted vinyl to the shop front window at the consultants office and at the helpdesk. Work to be done during normal working hours |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-07 | 2023-12-07 |  | ASP-GS0763 | REL BUDG AVAC RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-07 | D | 16372.22 |  | 100 | 2023-10-25 | 2023-10-26 | 16372.22 |  | {"MANDT":"111","REFERENCE":90000801,"ONEVIEW":"21526X","DATE01":"2023-09-27","DATE02":"2023-10-04","DATE03":"2023-10-25","DATE04":"2023-11-01","DATE05":"2023-11-22","DATE06":"2023-12-06","DATE07":"2024-01-05","DATE08":"2024-01-26","DATE09":"2024-03-11","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":90,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:30:21:45:18","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-06","FORECAST_END":"2024-01-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDkuMTEgTk46IEFic2EgUE8gb2J0YWluZWQgMzAuMTAgYXdhaXRpbmcgQkZNIFBP","RATING":""} |  |  | C000119691-2 | PHASE08 | 2023-11-24 | 2023-11-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-10-27 | 2023-10-31 | 2023-11-08 | 2023-11-14 | 2023-10-30 | 14236.71 | 0 |  |  | C000119691 | 14236.71 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000802 | Alice Lane Towers Kwena Cable 2 | Alice Lane Towers Kwena Cable 2 |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-07 | 2023-12-06 |  | ALP-GS0080 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-11-07 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000802,"ONEVIEW":"21526X","DATE01":"2023-08-29","DATE02":"2023-09-05","DATE03":"2023-09-26","DATE04":"2023-10-03","DATE05":"2023-10-24","DATE06":"2023-11-07","DATE07":"2023-12-06","DATE08":"2023-12-27","DATE09":"2024-02-10","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-07","FORECAST_END":"2023-12-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000121834 | PHASE11 | 2023-11-07 | 2023-12-06 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-08 | 714056.08 | 0 |  |  | C000121834 | 714056.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000803 | Towers West- Emergency Generator Spares | Towers West- Emergency Generator Spares |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-07 | 2023-12-29 |  | ALP-GS0081 | CRTD: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-07 | D | 870714.33 |  | 70 | 2023-10-26 | 2023-10-26 | 870714.33 | 16.11 NN: WA reviewed with Palesa on the 10.11 awaiting Absa Legal approval | {"MANDT":"111","REFERENCE":90000803,"ONEVIEW":"21526X","DATE01":"2023-08-29","DATE02":"2023-09-05","DATE03":"2023-09-26","DATE04":"2023-10-03","DATE05":"2023-10-24","DATE06":"2023-11-07","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-07","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-11-07 | 2023-12-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | 2023-10-30 |  |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000804 | Absa Mount Frere - UPS Exhange Unit | Absa Mount Frere - UPS Exhange Unit |  |  | Region 2 | Eastern Cape | 78953X | 1000-71060-01 | Mount Frere-Main St-Mount Frere | N | 2023-11-27 | 2023-12-29 |  | ASP-EC0375 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | L |  | CEASARS | 2023-11-09 | D | 38865.2 |  | 100 | 2023-11-13 | 2023-11-16 | 38865.2 | Absa Ref : 240129_120 | {"MANDT":"111","REFERENCE":90000804,"ONEVIEW":"78953X","DATE01":"2023-11-06","DATE02":"2023-11-09","DATE03":"2023-11-13","DATE04":"2023-11-20","DATE05":"2023-11-16","DATE06":"2023-12-04","DATE07":"2023-12-05","DATE08":"2023-12-18","DATE09":"2024-01-26","DATE10":"2024-02-29","DATE11":"2024-02-01","DATE12":"2024-02-01","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":60,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"115:3:4:7:-4:18:1:13:39:28","PROGRESS":91,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-04","FORECAST_END":"2023-12-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggRGVjIFBPQyBTdWJtaXR0ZWQgdG8gZmluYW5jZQoxNCBEZWMgc2VudCB0byBCaWR2ZXN0IEVuZ2luZWVyaW5nIGZvciBzaWdub2ZmIDEzIERlYwo3IE5vdiAtIFBhcGVyd29yaydzIHJlcXVlc3RlZCB0byBjb21wbGV0ZSBBc3NldCBidWlsZCBhbmQgY29tbWlzc2lvbmluZyBkb2N1bWVudGF0aW9uCjMwIE5vdiB0byBiZSBpbnN0YWxsZWQgNSBEZWMKMjggTm92IEJWIFBPIElzc3VlZCAgLSBTdGFuZGJ5IDQ1MDA4NzUxMTkKMjcgVXJnZW50IGZvbGxvdyB1cCByZXF1aXJlZCByZSBQTwoyMyBOb3YgQWJzYSBQTyBSZWNlaXZlZCBDMDAwMTI1NzE1CjIwIE5vdiBBcHByb3ZlZCBkZWNrIHJlY2VpdmVkIFBPIHJlcXVlc3RlZAoxNiBOb3YgQXBwcm92ZWQgQ0I0NCBTaWduZWQgRGVjayB0byBGb2xsb3cgaW4gb3JkZXIgdG8gcmVxdWVzdCBQTydzCjEzIE5vdiBTdWJtaXR0ZWQgZm9yIENCNDMgQXBwcm92YWwKMTMgTm92IEJ1ZGdldCBmcm9tIEhlcm1hbnVzIC0gQ29ubmVjdCBDcml0aWNhbCBMb2FkIC0gUjQwayAtIEFTUC1XQzAzMTUKOSBOb3YgdG8gYmUgc3VibWl0dGVkIGZvciBDQiAKNiBOb3YgT09DIFBSRiByZWNlaXZlZCAtIERhdGVkIDI2IE9jdA==","RATING":""} |  |  | C000125715 | PHASE11 | 2023-12-04 | 2023-12-05 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-11-23 | 33795.83 | 0 |  |  | C000125715 | 33795.83 |  | 1850.72 |  | 0 | 1850.72 |  | 0 |  | 0
90000805 | Absa Gahamstown Gen Injector unit | Absa Gahamstown Gen Injector unit |  |  | Region 2 | Eastern Cape | 77512X | 1000-71029-01 | Absa Grahamstown-High St-Grahamstown | N | 2023-11-27 | 2023-12-29 |  | ASP-EC0376 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-11-09 | D | 0 |  | 1 |  |  | 0 | Being done via GMP | {"MANDT":"111","REFERENCE":90000805,"ONEVIEW":"77512X","DATE01":"2023-11-09","DATE02":"2023-11-16","DATE03":"2023-12-07","DATE04":"2023-12-14","DATE05":"2024-01-04","DATE06":"2024-01-18","DATE07":"2024-02-19","DATE08":"2024-03-11","DATE09":"2024-04-25","DATE10":"2024-04-30","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:32:21:45:27","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-01-18","FORECAST_END":"2024-02-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjMgTm92IEJpZHZlc3QgRW5nIHRvIGFkdmlzZSBvbiB0aGUgd2F5IGZvcndhcmQKMTcgTm92IFBSRiByZWNlaXZlZCBidXQgb24gaG9sZCBhcyBwZXIgaW50ZXJuYWwgQ0IuCjE2IE5vdiBQTSB0byBjb21waWxlIEJDIC4gQmlkdmVzdCBFbmcgaW5kaWNhdGVkIHRoZXkgdGFraW5nIHZpYSBwcm9jdXJlbWVudCB0byBnZXQgVmVuZG9yIHRvIHJlcGxhY2UuIE1haWwgc2VudCBjb25maXJtaW5nIGRpc2N1c3Npb24gYXQgSW50ZXJuYWwgQ0IgcmV2aWV3LgoxNSBOb3YgUFJGIGFwcHJvdmFsIGluIFByb2dyZXNzIFBNIHRvIHByZXAgQkMgYWNjb3JkaW5nbHkgCjE0IE5vdiBCViBlbmdpbmVlcmluZyB0byBhZHZpc2UgYXMgbm8gYXBwcm92ZWQgUFJGIHJlY2VpdmVkCjkgTm92IFBSRiBwZW5kaW5nIC0gUG9zc2libGUgR01Q","RATING":""} |  |  |  | PHASE12 | 2024-01-18 | 2024-02-19 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000806 | Absa Meyerton Signage | Absa Meyerton Signage |  |  | Region 1 | Gauteng | 77636X | 1000-71363-01 | Absa Meyerton - 15C Loch Roadh |  | 2023-11-09 | 2023-12-08 |  | ASP-GS0764 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | GAMIETR | 2023-11-09 | D | 35830.65 |  |  | 2023-11-07 | 2023-11-07 | 35830.65 |  | {"MANDT":"111","REFERENCE":90000806,"ONEVIEW":"77636X","DATE01":"2023-08-31","DATE02":"2023-09-07","DATE03":"2023-09-28","DATE04":"2023-10-05","DATE05":"2023-10-26","DATE06":"2023-11-09","DATE07":"2023-12-08","DATE08":"2023-12-29","DATE09":"2024-02-12","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-09","FORECAST_END":"2023-12-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE11 | 2023-11-22 | 2023-12-07 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000122451 | 31157.09 |  | 3129.16 |  | 0 | 0 |  | 0 |  | 0
90000807 | Absa Limpopo Mall - water damaged kitche | Absa Limpopo Mall - water damaged kitche |  |  | Region 3 | Limpopo | 78979X | 1000-70547-01 | Limpopo Mall-Cnr Rissik, Market, Devenish & Kerk St-Polokwane |  | 2023-11-14 |  |  | ASP-LP0185 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-09 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000807,"ONEVIEW":"Unknown","DATE01":"2023-09-05","DATE02":"2023-09-12","DATE03":"2023-10-03","DATE04":"2023-10-10","DATE05":"2023-10-31","DATE06":"2023-11-14","DATE07":"2023-12-14","DATE08":"2024-01-04","DATE09":"2024-02-18","DATE10":"2024-02-29","DATE11":"2024-02-18","DATE12":"2024-02-18","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-14","FORECAST_END":"2023-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-11-14 | 2023-12-14 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000808 | Trade Route Mall HVAC | Trade Route Mall HVAC 1. Supply and install the VRV heat recovery system, fresh air system and DX unit 2. Connect the newly installed HVAC system into the backup generator power. 2. Decommission and remove the old landlord's HVAC system 3. Test and Commission the new system 5. Sign off and handover Scope of Works - Karo Solutions: 1 Conduct a full HVAC due diligence of the existing branch to identify the plantrooms, pipe routes and weather louvre positions. 2 Produce HVAC drawings, BOQ and tender specifications. 3 Call for contractor tenders, evaluations and recommendations. 4 Site monitoring and project close out. |  |  | Region 1 | Gauteng South | 77216X | 1000-70356-01 | Trade Route Mall Centre-Cnr K43 & Nirvana Dr-Lenasia | N | 2023-11-09 | 2023-12-29 |  | ALP-GS0082 | REL BUDG AVAC SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | L |  | GAMIETR | 2023-11-09 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000808,"ONEVIEW":"77216X","DATE01":"2023-08-31","DATE02":"2023-09-07","DATE03":"2023-09-28","DATE04":"2023-10-05","DATE05":"2023-10-26","DATE06":"2023-11-09","DATE07":"2023-12-29","DATE08":"2024-03-29","DATE09":"2024-05-13","DATE10":"2024-05-31","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":60,"PROG06":50,"PROG07":40,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"213:7:21:7:21:14:50:91:45:27","PROGRESS":38,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-09","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE07 | 2023-11-09 | 2024-04-01 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000141050 | 1294944.2 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000809 | Absa Orkney - Installation of Dedicated | Absa Orkney - Installation of Dedicated |  |  | Region 3 |  | Unknown | 1000-71304-01 | Unknown Building - not in our database |  | 2023-11-29 |  |  | ASP-CR0521 | REL BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-10 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000125055 | PHASE00 | 2023-11-29 | 2023-12-29 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-21 | 14291.85 | 0 |  |  | C000125055 | 14291.85 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000810 | Towers North Electrically Damaged Compon | 1.Supply and Install Variable Speed Drive (VSD) Assembly Kit (Capacitors, Capacitor Bridge Plate, Insulated Gate Bipolar Transistor (IGBT) Board) 2.Supply and Install Condenser Fan Speed Drive 3.Supply and Install Suction Pressure Transducer 4.Supply and Install Temperature Sensor Kit 5.Supply and Install Refrigeration Gas 6.Supply and Install Variable Speed Drive (VSD) Logic Board 7.Supply and Install Expansion Valve 8.Test and Commission |  |  | Region 1 | Gauteng South | 77381X | 1000-71397-01 | Absa Towers North-Commissioner St-Johannesburg |  | 2023-11-10 | 2023-12-11 |  | ALP-GS0083 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-10 | D | 1118581.16 |  |  | 2023-10-27 |  | 0 |  | {"MANDT":"111","REFERENCE":90000810,"ONEVIEW":"77381X","DATE01":"2023-09-01","DATE02":"2023-09-08","DATE03":"2023-09-29","DATE04":"2023-10-06","DATE05":"2023-10-27","DATE06":"2023-11-10","DATE07":"2023-12-11","DATE08":"2024-01-01","DATE09":"2024-02-15","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-10","FORECAST_END":"2023-12-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2023-12-27 | 2024-01-04 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000143225 | 972679.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000811 | Absa Towers West Replace restaurant cupb | Absa Towers West Replace restaurant cupboards |  |  | Region 1 | Gauteng South | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg | N | 2023-04-05 | 2023-12-31 |  | ALP-GS0084 | CRTD: |  | false | false |  | Athi Magqashela |  |  | 2023 |  | F |  | GAMIETR | 2023-11-10 | D | 1262831.25 |  | 20 | 2023-11-14 |  | 1262831.25 | The quote was sent back to the supplier to amend the quote | {"MANDT":"111","REFERENCE":90000811,"ONEVIEW":"","DATE01":"2023-01-25","DATE02":"2023-02-01","DATE03":"2023-02-22","DATE04":"2023-03-01","DATE05":"2023-03-22","DATE06":"2023-04-05","DATE07":"2023-12-31","DATE08":"2024-01-21","DATE09":"2024-03-06","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-04-05","FORECAST_END":"2023-12-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2024-01-29 | 2024-05-02 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000812 | Absa Kuruman - Installation of Security | Absa Kuruman - Installation of Security |  |  | Region 3 |  | Unknown | 1000-71350-01 | Unknown Building - not in our database |  | 2023-12-14 |  |  | ASP-CR0522 | REL BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-14 | 2024-01-13 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142476 | 21718.13 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000813 | Absa Ventersdorp -Install PC Board & UPS | Absa Ventersdorp -Install PC Board & UPS |  |  | Region 3 | [5 empty] | 2023-11-29 |  |  | ASP-CR0523 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000814 | Krugersdorp Dilaps | Krugersdorp Dilaps |  |  | Region 1 |  | 76486X | 1000-70267-01 | Absa Centre Krugersdorp-Cnr Burger & Monument St-Krugersdorp |  | 2023-11-13 | 2023-12-18 |  | ASP-GN0236 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  |  |  | GAMIETR | 2023-11-13 | D | 145075.87 |  | 60 | 2023-11-16 |  | 145075.87 |  | {"MANDT":"111","REFERENCE":90000814,"ONEVIEW":"76486X","DATE01":"2023-09-04","DATE02":"2023-11-01","DATE03":"2023-11-14","DATE04":"2023-11-14","DATE05":"2023-12-05","DATE06":"2023-12-19","DATE07":"2024-01-23","DATE08":"2024-02-13","DATE09":"2024-03-29","DATE10":"2024-03-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"178:58:13:0:21:14:35:21:45:7","PROGRESS":8,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-19","FORECAST_END":"2024-01-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000124365 | PHASE11 | 2023-12-01 | 2023-12-11 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-11-17 | 126156.41 | 0 |  |  | C000124365 | 126156.41 |  | 13079.99 |  | 0 | 0 |  | 0 |  | 0
90000815 | Quagga Centre Dilaps | Quagga Centre Dilaps |  |  | Region 1 |  | 77315X | 1000-71396-01 | Quagga Centre-Cnr Quagga & Elias Motswaledi St-Pretoria |  | 2023-11-13 | 2023-12-29 |  | ASP-GN0237 | REL ISBD AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  |  |  | GAMIETR | 2023-11-13 | D | 218038.69 |  | 60 | 2023-12-13 | 2024-01-22 | 218038.69 |  | {"MANDT":"111","REFERENCE":90000815,"ONEVIEW":"77315X","DATE01":"2023-09-04","DATE02":"2023-09-06","DATE03":"2023-09-27","DATE04":"2023-10-04","DATE05":"2023-10-25","DATE06":"2023-11-08","DATE07":"2023-12-24","DATE08":"2024-01-14","DATE09":"2024-02-28","DATE10":"2024-02-29","DATE11":"2024-02-28","DATE12":"2024-02-28","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"209:2:21:7:21:14:46:21:45:27","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-08","FORECAST_END":"2023-12-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjE6MTE6MjAyMyBBUzogRmluYWxpemluZyB0aGUgc2NvcGUgb2Ygd29yay4=","RATING":""} |  |  | C000133459 | PHASE11 | 2024-01-10 | 2024-01-16 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2023-12-22 | 189598.86 | 0 |  |  | C000133459 | 189598.86 |  | 17627.91 |  | 0 | 0 |  | 0 |  | 0
90000816 | Alice Lane South bosal conduit for secur | Alice Lane South bosal conduit for secur |  |  | Region 1 | Gauteng South | 35041 | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg | N | 2023-11-13 | 2023-12-13 |  | ASP-GS0765 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-11-13 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000816,"ONEVIEW":"21335X","DATE01":"2023-09-04","DATE02":"2023-09-11","DATE03":"2023-10-02","DATE04":"2023-10-09","DATE05":"2023-10-30","DATE06":"2023-11-13","DATE07":"2023-12-13","DATE08":"2024-01-03","DATE09":"2024-02-17","DATE10":"2024-02-29","DATE11":"2024-02-17","DATE12":"2024-02-17","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-13","FORECAST_END":"2023-12-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-11-13 | 2023-12-13 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000113624 | 107548.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000817 | New Market Dilaps | New Market Dilaps |  |  | Region 1 |  | 36102X | 1000-70181-01 | Mall @ Newmarket-Cnr Heidelberg & Swartkoppies Rd-Alberton |  | 2023-11-13 | 2023-12-18 |  | ASP-GS0766 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  |  |  | GAMIETR | 2023-11-13 | D | 0 |  | 15 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000817,"ONEVIEW":"36102X","DATE01":"2023-09-04","DATE02":"2023-10-12","DATE03":"2023-10-12","DATE04":"2023-10-12","DATE05":"2023-10-18","DATE06":"2023-11-01","DATE07":"2023-12-06","DATE08":"2023-12-27","DATE09":"2024-02-10","DATE10":"2024-02-29","DATE11":"2024-02-10","DATE12":"2024-02-10","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"178:38:0:0:6:14:35:21:45:7","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-01","FORECAST_END":"2023-12-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTQ6MTE6MjMgQVM6IHdhaXRpbmcgZm9yIFZQIHRvIHN1cHBvcnQgdGhlIGJ1c2luZXNzIGNhc2UgdG8gcmFpc2UgYSBQTy4=","RATING":""} |  |  |  | PHASE11 | 2023-11-01 | 2023-12-06 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000818 | Absa Alberton Dilaps | Absa Alberton Dilaps |  |  | Region 1 |  | 79331X | 1000-70447-01 | Absa Voortrekker Street Alberton-Voortrekker St-Alberton |  | 2023-11-13 | 2023-12-28 |  | ASP-GS0767 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  |  |  | GAMIETR | 2023-11-13 | D | 1620873.43 |  |  | 2024-03-11 |  | 0 | Business Case has been submitted for approval | {"MANDT":"111","REFERENCE":90000818,"ONEVIEW":"79331X","DATE01":"2023-09-04","DATE02":"2023-09-11","DATE03":"2023-10-02","DATE04":"2023-10-09","DATE05":"2023-10-30","DATE06":"2023-11-13","DATE07":"2023-12-28","DATE08":"2024-01-18","DATE09":"2024-03-03","DATE10":"2024-03-31","DATE11":"2024-03-03","DATE12":"2024-03-03","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-13","FORECAST_END":"2023-12-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjE6MTE6MjMgQVM6IGZpbmlsaXNpbmcgc2NvcGU=","RATING":""} |  |  |  | PHASE05 | 2024-03-25 | 2024-05-09 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000819 | Auckland Park External signage | Auckland Park External signage |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2023-11-13 | 2023-12-28 |  | ASP-GS0768 | REL BUDG AVAC SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | F |  | GAMIETR | 2023-11-13 | D | 232440.15 |  | 60 | 2024-02-15 | 2024-02-20 | 23240.15 |  | {"MANDT":"111","REFERENCE":90000819,"ONEVIEW":"76849X","DATE01":"2023-09-04","DATE02":"2024-01-11","DATE03":"2024-01-08","DATE04":"2024-02-14","DATE05":"2024-02-23","DATE06":"2024-03-08","DATE07":"2024-04-22","DATE08":"2024-05-13","DATE09":"2024-06-27","DATE10":"2024-06-30","DATE11":"2024-06-27","DATE12":"2024-06-27","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"270:129:-3:37:9:14:45:21:45:45:45:25","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-08","FORECAST_END":"2024-04-22","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Mjc6MDI6MjQgQVM6IFdhaXRpbmcgZm9yIEJGTSBQTyB0byBiZSBpc3N1ZWQsIHRoZSBwcm9qZWN0IGlzIGhpZ2hsaWdodGVkIGFzIGhpZ2ggcmlzay0gd2FpdGluZyBmb3IgT0hTIGFwcHJvdmFsLg==","RATING":""} |  |  |  | PHASE07 | 2024-03-01 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2024-02-23 | 125751.3 | 0 |  |  | C000144614 | 202121.87 |  | 21103.65 |  | 0 | 0 |  | 0 |  | 0
90000820 | Absa Kanyamazane - PCB Fan & Surge prote | Absa Kanyamazane - PCB Fan & Surge prote |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-12-01 |  |  | ASP-MP0175 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-01 | 2023-12-31 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000821 | Absa Ladybrand (17A Joubert)- UPS plug p | Absa Ladybrand (17A Joubert)- UPS plug p |  |  | Region 3 |  | Unknown | 1000-71556-01 | Unknown Building - not in our database |  | 2023-12-07 |  |  | ASP-CR0524 | REL BUDG AVAC SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-14 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-07 | 2024-01-06 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142477 | 13637 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000822 | Gilloolys View UPS Power | Supply and install 7x new plugs, 5x extension leads, 4x 20a circuit breakers, 7x extension boxes, electrical COC, Test and commission. |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2023-11-14 | 2023-12-14 |  | ASP-GS0769 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-14 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000822,"ONEVIEW":"37140X","DATE01":"2023-09-05","DATE02":"2023-09-12","DATE03":"2023-10-03","DATE04":"2023-10-10","DATE05":"2023-10-31","DATE06":"2023-11-14","DATE07":"2023-12-14","DATE08":"2024-01-04","DATE09":"2024-02-18","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-14","FORECAST_END":"2023-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE08 | 2023-12-25 | 2024-01-24 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000823 | Towers West Power Dashboard PC to BMS Ne | Towers West Power Dashboard PC to BMS Ne |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-14 | 2023-12-14 |  | ASP-GS0770 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-14 | D | 84618.05 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000823,"ONEVIEW":"21526X","DATE01":"2023-11-09","DATE02":"2023-11-10","DATE03":"2023-11-14","DATE04":"2023-11-21","DATE05":"2023-11-30","DATE06":"2023-12-14","DATE07":"2023-12-20","DATE08":"2024-01-10","DATE09":"2024-02-24","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:1:4:7:9:14:6:21:45:11","PROGRESS":2,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-14","FORECAST_END":"2023-12-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTYuMTEgTk46IEJDIHByZXNlbnRlZCBhdCBpbnRlcm5hbCBjb3N0IGJvYXJkIDE2LjExIGNvbW1lbnRzIHdlcmUgcmFpc2VkIHRvIHNlcGFyYXRlIHRoZSBjb3N0cyBvZiBzb2Z0d2FyZSB1cGdyYWRlIHRvIG9uZSBvZiBjb25uZWN0aW5nIHRoZSBkYXNoYm9hcmQgdG8gdGhlIEJNUyBuZXR3b3Jr","RATING":""} |  |  |  | PHASE05 | 2023-12-14 | 2023-12-20 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000824 | Gilloolys View Boardroom Expansion | Gilloolys View Boardroom Expansion |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2023-11-14 | 2023-12-18 |  | ASP-GS0771 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-11-14 | D | 383222.27 |  | 100 | 2023-11-07 | 2023-12-12 | 383222.27 |  | {"MANDT":"111","REFERENCE":90000824,"ONEVIEW":"37140X","DATE01":"2023-09-05","DATE02":"2023-09-12","DATE03":"2023-10-03","DATE04":"2023-11-22","DATE05":"2023-12-13","DATE06":"2023-12-27","DATE07":"2024-01-30","DATE08":"2024-02-20","DATE09":"2024-04-05","DATE10":"2024-04-30","DATE11":"2024-04-05","DATE12":"2024-04-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":60,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:7:21:50:21:14:34:21:45:7","PROGRESS":14,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-27","FORECAST_END":"2024-01-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"QkMgUGFwZXIgcmVzdWJtaXR0ZWQgZm9yIE9PQyBhcHByb3ZhbApQcm9qZWN0IGFwcHJvdmVkIGFuZCBhd2FpdGluZyBBQlNBIFBP","RATING":""} |  |  | C000142480 | PHASE07 | 2023-12-27 | 2024-02-26 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2024-02-14 | 333236.76 | 0 |  |  | C000142480 | 343136.76 |  | 34807.02 |  | 0 | 0 |  | 0 |  | 0
90000825 | Absa Volksrust - Replacement of Faulty U | Absa Volksrust - Replacement of Faulty U |  |  | Region 3 |  |  |  | Building not in Real Estate Database |  | 2023-11-30 |  |  | ASP-MP0176 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-14 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-30 | 2023-12-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000826 | Towers West Villa of Hope Project | Villa of Hope Orphanage Project Earthworks, Vegetation removal, compaction and weed killer spray. Asphalt Re-surface path area behind REC Hall, Painting of toilets and installation of new geyser in unit 19 |  |  | Region 1 | Gauteng South | 37140X | 1000-71710-01 | Nancified | N | 2023-11-15 | 2023-11-30 |  | ASP-GS0772 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  | U |  | GAMIETR | 2023-11-15 | D | 174880 |  | 100 | 2023-11-09 | 2023-11-09 | 174880 |  | {"MANDT":"111","REFERENCE":90000826,"ONEVIEW":"37140X","DATE01":"2023-09-06","DATE02":"2023-09-13","DATE03":"2023-10-04","DATE04":"2023-10-11","DATE05":"2023-11-01","DATE06":"2023-11-15","DATE07":"2023-11-30","DATE08":"2023-12-21","DATE09":"2024-02-04","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-15","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000123251 | PHASE09 | 2023-11-15 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-14 | 152069.57 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000827 | Absa Letsoho Replace generator battery | Absa Letsoho Replace generator battery |  |  | Region 1 |  | 76627X | 1000-70299-01 | Letsoho Shopping Centre-Cnr Hospital & Letsoho St-Katlehong | N | 2023-11-15 | 2023-11-30 |  | ASP-GS0773 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  | L |  | GAMIETR | 2023-11-15 | D | 0 | Retrospective Request |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000827,"ONEVIEW":"37140X","DATE01":"2023-09-06","DATE02":"2023-09-13","DATE03":"2023-10-04","DATE04":"2023-10-11","DATE05":"2023-11-01","DATE06":"2023-11-15","DATE07":"2023-11-30","DATE08":"2023-12-21","DATE09":"2024-02-04","DATE10":"2024-02-29","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-11-15","FORECAST_END":"2023-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2023-11-15 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000828 | Absa Fourways Replace aircon unit compre | Absa Fourways Replace aircon unit compre |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2023-11-15 | 2023-11-30 |  | ASP-GS0774 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-11-15 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000125070 | PHASE00 | 2023-11-15 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-21 | 17806.25 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000829 | 268 Republic Road COC Inspection | 268 Republic Road COC Inspection |  |  | Region 1 |  | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2023-11-16 | 2023-11-30 |  | ASP-GS0775 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-11-16 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-16 | 2023-11-30 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000830 | Absa Soshanguve PnP - Insurance Various | Absa Soshanguve PnP - Insurance Various |  |  | Region 1 |  | 22606X | 1000-70067-01 | Pick & Pay Centre Soshanguve-Buitekant St-Soshanguve |  | 2023-02-01 | 2023-07-31 |  | ASP-GN0238 | REL BUDG AVAC RESA SETC: |  | false | false |  | Yashir Somaru |  |  | 2023 |  |  |  | CEASARS | 2023-11-17 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000124519 | PHASE00 | 2023-02-01 | 2023-07-31 | PRESHANE MUNTHREE | Obakeng Phuti | 0 |  |  |  |  | 2023-11-17 | 321013.57 | 0 |  |  | C000124519 | 321013.57 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000831 | Absa Evaton Mall - Shopfront | Absa Evaton Mall - Shopfront |  |  | Region 1 |  | 77172X | 1000-70351-01 | Evaton Mall-Cnr Golden Highway & Easton Rd-Sebokeng |  | 2023-06-09 | 2023-06-26 |  | ASP-GS0776 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2023-11-17 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000124524 | PHASE00 | 2023-06-09 | 2023-06-26 | OTHER | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-17 | 10608.08 | 0 |  |  | C000124524 | 10608.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000832 | Absa Vanderbijlpark new outdoor unit RET | Absa Vanderbijlpark new outdoor unit RET |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2023-11-17 | 2023-12-18 |  | ASP-GS0777 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-11-17 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000125072 | PHASE00 | 2023-11-17 | 2023-12-18 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-21 | 18160 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000833 | Absa Lenasia - Insurance Ceiling Tiles | Absa Lenasia - Insurance Ceiling Tiles |  |  | Region 1 |  | 77329X | 1000-70367-01 | Absa Lenasia-Cnr Rose & Gemsbok Ave-Lenasia |  | 2023-06-09 | 2023-06-13 |  | ASP-GS0778 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2023-11-17 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000124434 | PHASE00 | 2023-06-09 | 2023-06-13 | OTHER | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-17 | 2857 | 0 |  |  | C000124434 | 2857 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000834 | Absa Canal Walk Century City - Carpets | Absa Canal Walk Century City - Carpets |  |  | Region 2 | Western Cape | 77087X | 1000-70799-01 | Canal Walk Shopping Centre-Century Blvd-Milnerton | N | 2024-01-03 | 2024-04-30 |  | ASP-WC0337 | REL BUDG AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2023-11-17 | D | 122198.21 |  | 100 | 2024-02-01 | 2024-02-08 | 122198.21 | Absa Ref : 240402_001 Retail Reprioritised | {"MANDT":"111","REFERENCE":90000834,"ONEVIEW":"77087X","DATE01":"2023-11-17","DATE02":"2023-11-30","DATE03":"2024-02-01","DATE04":"2024-02-08","DATE05":"2024-02-08","DATE06":"2024-02-27","DATE07":"2024-03-01","DATE08":"2024-03-18","DATE09":"2024-05-02","DATE10":"2024-05-31","DATE11":"2024-05-02","DATE12":"2024-05-02","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":100,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"196:13:63:7:0:19:3:17:45:127:127:18","PROGRESS":85,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-27","FORECAST_END":"2024-03-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggRmluYWwgUE9DIHN1Ym1pdHRlZCAxOCBNYXJjaAo0IE1hcmNoIC0gV29ya3MgQ29tcGxldGVkIEhhbmRvdmVyIDQgTWFyY2gKQjQgRmlyZSAtIFBPIC0gNDUwMDg5NTYxMwoyMyBGZWIgRGF0ZXMgc2V0IGZyb20gMjcgRmViIHRvIDEgTWFyY2ggLSBJbml0aWFsIERhdGVzIHdlcmUgMSBNYXJjaCB0byA4IE1hcmNoCjE5IEZlYiAtIEtpY2sgb2ZmIG1lZXRpbmcgdG8gYmUgc2NoZWR1bGVkIHRvIGZpbmFsaXNlIGRhdGVzIHdpdGggQnJhbmNoCjE2IEZlYiBCViBQTydzIElzc3VlZCA0NTAwODkwMjE2IEZpZGVsaXR5LCA0NTAwODkwMjE1IEJsdWUgU2FuZHMKMTQgRmViIEFic2EgUE8gcmVjZWl2ZWQgQzAwMDE0MjM3NwoxMiBGZWIgLSBTaWduZWQgRGVjayByZWNlaXZlZCAxMiBGRUIgQWJzYSBwbyByZXF1ZXN0ZWQKOCBGZWIgQXBwcm92ZWQgQ0IwMyBTaWduZWQgRGVjayBQZW5kaW5nCjYgRmViIHRvIGZvbGxvdyB1cCBhbmQgdXBkYXRlIGFzIFBNTyBhZGRyZXNzZWQgdGhlIGhvbGVzCjUgRmViIFN1Ym1pdHRlZCBmb3IgQ0IKMzEgSmFuIEJDIFN1Ym1pdHRlZCBmb3IgTmV4dCBDQiBDeWNsZQoyOSBKYW4gLSBDb3N0cyBzdWJtaXR0ZWQgdG8gRUIgZm9yIEFwcHJvdmFsIC0gUG9zc2libGUgbmV4dCBDQgoxOCBKYW4gUXVvdGUgUGVuZGluZyB0byBzdWJtaXQgdG8gRUIgZm9yIHN1cHBvcnQKMTQgRGVjIC0gQWRkaXRpb24gUXVvdGVzIHRvIGJlIHJlcXVlc3RlZCBmb3IgRG9vciBIIGZyYW1lCjExIERlYyBQTSB0byBzdWJtaXQgQkMgcGFjayB0byBSQkIgZm9yIGFwcHJvdmFsIDExIERlYwo0IERlYyAtIFF1b3RlcyBkdWUgNCBEZWMgdG8gYmUgc3VibWl0dGVkIHRvIEFic2EgZm9yIGFwcHJvdmFsCjI3IE5vdiBTaXRlIHZpc2l0IHNjaGVkdWxlZCBmb3IgMzAgTm92CjIwIE5vdiAtIFNpdGUgdmlzaXQgdG8gYmUgY29uZHVjdGVkIGJ5IDI1Tm92CjE3IE5vdiAtIFBSRiBQZW5kaW5n","RATING":""} |  |  | C000142377 | PHASE09 | 2024-02-27 | 2024-03-01 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-02-14 | 106259.31 | 0 |  |  | C000142377 | 106259.31 |  | 5811.82 |  | 1293.17 | 4518.65 |  | 0 |  | 0
90000835 | Absa Gansbaai - Minor Works | Absa Gansbaai - Minor Works |  |  | Region 2 | Western Cape | 77700X | 1000-70849-01 | 49 Main Road Gansbaai-Main Rd-Gansbaai | N | 2024-01-03 | 2024-04-30 |  | ASP-WC0338 | CRTD RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2023-11-17 | D | 0 |  | 1 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000835,"ONEVIEW":"77700X","DATE01":"2023-11-17","DATE02":"2023-12-05","DATE03":"2023-12-26","DATE04":"2024-01-02","DATE05":"2024-01-23","DATE06":"2024-02-06","DATE07":"2024-06-03","DATE08":"2024-06-24","DATE09":"2024-08-08","DATE10":"2024-08-31","DATE11":"2024-08-08","DATE12":"2024-08-08","PROG01":0,"PROG02":20,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"288:18:21:7:21:14:118:21:45:28","PROGRESS":1,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-06","FORECAST_END":"2024-06-03","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkgSmFuIC0gV2FpdCBmb3IgaW5wdXQgZnJvbSBFQiByZSA1IFllYXIgUGxhbgoyMiBKYW4gLSBUbyBiZSBzdWJtaXR0ZWQgaW4gRmViCjE0IERlYyAtIFRvIGJlIGEgQlRCIHRvIGJlIHN1Ym1pdHRlZCBKYW4KMTEgRGVjIFF1b3RlcyBkdWUgb24gMTMgRGVjCjQgRGVjIC0gU2l0ZSBWaXNpdCA0IERlYyBRdW90ZXMgdG8gZm9sbG93CjI3IE5vdiBTaXRlIHZpc2l0IHRvIGJlIGFycmFuZ2VkIGZvciAwNSBEZWMgMjAyMwoyMCBOb3YgLSBTaXRlIHZpc2l0IHRvIGJlIGFycmFuZ2VkIHRvIGRldGVybWluZSBzY29wZQoxNyBOb3YgLSBQUkYgUGVuZGluZw==","RATING":""} |  |  |  | PHASE12 | 2024-02-06 | 2024-06-03 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000836 | Alice Lane North Operational Equipment | Alice Lane North Operational Equipment |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-17 | 2023-12-18 |  | ALP-GS0086 | REL BUDG AVAC SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-11-17 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE06 | 2023-11-17 | 2023-12-18 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | NO FUNDING | 703292.56 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000837 | Absa De Doorns - HVAC Replacement | Absa De Doorns - HVAC Replacement - 1x Office + Tellers |  |  | Region 2 | Western Cape | 78111X | 1000-70885-01 | Absa De Doorns-Voortrekker Rd-De Doorns | N | 2023-12-01 | 2023-12-29 |  | ASP-WC0339 | PREL AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | F |  | CEASARS | 2023-11-20 | D | 0 |  | 1 |  |  | 0 | Done as Part of Bulk PO ALP-N00069 | {"MANDT":"111","REFERENCE":90000837,"ONEVIEW":"78111X","DATE01":"2023-11-17","DATE02":"2023-11-20","DATE03":"2023-11-28","DATE04":"2023-12-05","DATE05":"2023-11-29","DATE06":"2023-12-11","DATE07":"2023-12-14","DATE08":"2024-01-04","DATE09":"2024-02-18","DATE10":"2024-02-29","DATE11":"2024-02-18","DATE12":"2024-02-18","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"165:3:8:7:-6:12:3:21:45:22","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-11","FORECAST_END":"2023-12-14","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBEZWMgLSBQQyB0byBmb2xsb3cgdXAgd2l0aCBDaGVyZXNlIHJlIGFwcHJvdmFsIG9mIEhlYWR3aW5kIEJDICBpbiB0ZXJtcyBvZiBBYnNhIFBPJ3MKMjkgTm92IEFwcHJvdmVkIG9uIGNvbmRpdGlvbiBvZiBCdWRnZXQgQXZhaWxhYmlsaXR5IGFuZCBpc3N1ZSBvZiBBYnNhIFBPCjI4IE5vdiBTdWJtaXR0ZWQgdG8gQ1JFUyBFTkcgZm9yIE9PQyBhcHByb3ZhbAoyMyBOb3YgQmlkdmVzdCBFbmcgdG8gcHJvdmlkZSBIVkFDIENhbGN1bGF0aW9ucyBmb3IgdGhlIEJDIHBhY2sgdG8gYmUgc3VibWl0dGVkCjIwIE5vdiAtIEJDIHRvIGJlIHN1Ym1pdHRlZCB3aXRoIHVwZGF0ZWQgY29zdGluZwoxNyBOb3YgUFJGIFJlY2VpdmVk","RATING":""} |  |  |  | PHASE06 | 2023-12-11 | 2023-12-14 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000838 | Absa Ceres - Minor Works | Absa Ceres - Minor Works |  |  | Region 2 | Western Cape | 70568X | 1000-70782-01 | Ceres-Voortrekker St-Ceres | N | 2024-01-03 | 2024-04-30 |  | ASP-WC0340 | CRTD RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2023-11-20 | D | 0 |  | 1 |  |  | 0 | Absa Ref : ??????? Retail Reprioritised | {"MANDT":"111","REFERENCE":90000838,"ONEVIEW":"70568X","DATE01":"2023-10-25","DATE02":"2023-12-06","DATE03":"2023-12-27","DATE04":"2024-01-03","DATE05":"2024-01-24","DATE06":"2024-02-07","DATE07":"2024-06-04","DATE08":"2024-06-25","DATE09":"2024-08-09","DATE10":"2024-08-31","DATE11":"2024-08-09","DATE12":"2024-08-09","PROG01":0,"PROG02":20,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"311:42:21:7:21:14:118:21:45:20","PROGRESS":1,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-07","FORECAST_END":"2024-06-04","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgRmViIFJldmFtcCByZWR1Y2UgY29uZmlybWVkIGJ5IFBsYW5uZXIKNyBGZWIgLSBNYWlsIGZyb20gUGxhbm5lciAtIFRvIGJlIGNvbnNpZGVyZWQgZm9yIGEgcmV2YW1wIHJlZHVjZSAtIGludmVzdGlnYXRpb24gYnkgRUIgaW4gUHJvZ3Jlc3MKMjkgSmFuIC0gV2FpdCBmb3IgaW5wdXQgZnJvbSBFQiByZSA1IFllYXIgUGxhbiAtIHdlZWsgNSBGZWIKMjIgSmFuIEJUQiB0byBiZSBzdWJtaXR0ZWQgaW4gRkVCCjE4IEphbiAtIEluZm8gc2VudCB0byBwbGFubmVyIHJlIHRoZSBzY29wZQoxNCBEZWMgIC0gUG90ZW50aWFsIEJUQiBiYXNlZCBvbiBmaW5hbCBTY29wZQoxMSBEZWMgUXVvdGVzIGR1ZSBvbiAxMyBEZWMKMjcgTm92IFNpdGUgdmlzaXQgdG8gYmUgc2NoZWR1bGVkIGZvciAwNiBEZWMKMjAgTm92IC0gQWRkZWQgYXMgcGFydCBvZiBDSVAyMDI0IHBsYW5uaW5n","RATING":""} |  |  |  | PHASE12 | 2024-02-07 | 2024-06-04 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000046438 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000839 | Region 2 - Various - Bulk PO - Eng Prioritised Requests | Region 2 - Various - Bulk PO - Eng Prioritised Requests |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | U | 2024-01-03 | 2024-12-30 |  | ALP-N00061 | REL BUDG AVAC SETC: |  | false | true |  | Surina Ceaser |  | Various Bulk PO for Region 2 | 2024 |  | U |  | CEASARS | 2023-11-20 | D | 1000000 |  | 100 | 2023-11-23 | 2023-12-08 | 1000000 | Absa Ref : 240129_521 | {"MANDT":"111","REFERENCE":90000839,"ONEVIEW":"36225X","DATE01":"2023-10-25","DATE02":"2023-11-22","DATE03":"2023-11-30","DATE04":"2023-11-30","DATE05":"2023-12-08","DATE06":"2024-01-15","DATE07":"2024-09-25","DATE08":"2024-10-16","DATE09":"2024-11-30","DATE10":"2024-11-30","DATE11":"2025-03-04","DATE12":"2025-03-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":60,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"523:28:8:0:8:38:254:21:45:27","PROGRESS":54,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-01-15","FORECAST_END":"2024-09-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBNYXJjaCBBYnNhIFBPIFJlY2VpdmVkIC0gQzAwMDE0NzIzNAo1IE1hcmNoIFNpZ25lZCBXQSByZWNlaXZlZCAtIEJ1bGsgQWJzYSBQTyBSZXF1ZXN0ZWQKNCBNYXJjaCBXQSBpbiBjaXJjdWxhdGlvbiBmb3IgU2lnbm9mZiBpbiBvcmRlciB0byBpc3N1ZSB0aGUgcGVuZGluZyBBYnNhIFBPCjE5IEZlYiAtIEFwcHJvdmVkIHRvIERhdGUgYWdhaW5zdCBIZWFkd2luZC4uLi4gQWJzYSBQTyBQZW5kaW5nCkF2YWlsYWJsZSAxOSBGZWIgUiAgUiA1OTcgOTkwLjUxIApBcHByb3ZlZCB0byBEYXRlIDE5IEZlYiBSICBSNDAyIDAwOS40OSAKNyBGZWIgNjAgU3V0aGVybGFuZCBTdHJlZXQgQ29ubmVjdCBBZGRpdGlvbmFsIEVxdWlwbWVudCB0byB0aGUgVVBTIFIxNCA0MzkuNjgKNyBGZWIgQWJzYSBCdXR0ZXJ3b3J0aCBDb25uZWN0IEFkZGl0aW9uYWwgRXF1aXBtZW50IHRvIHRoZSBVUFMgUjEwIDU4Mi4xNgoyMiBKYW4gTW9mZmV0dCBPZmZpY2UgUGFyayBIVkFDIC0gU2VjdXJpdHkgU2VydmVyIFJvb20gUjMyIDU2My42MwoxOSBGZWIgQWJzYSBNcWFuZHVsaSBIdmFjIGZvciBBdG0gcm9vbSBhbmQgU2VydmVyIFJvb20gIFI3NiA5NTkuMTIgCjE2IEZlYiBOZWF2ZSBTdG90dGVyIENoYW1iZXJzIC0gUG9ydCBBbGZyZWQgSFZBQyByZXBsYWNlbWVudCBCYWNrIE9mZmljZSAvIEtpdGNoZW4gUjQyIDU2OC4yNAoxNiBGZWIgVG9rYWkgSnVuY3Rpb24gSFZBQyAtIEhpZGVhd2F5IFNwbGl0IC0gQmFua2luZyBIYWxsIFIxNjcgODc2Ljg1CjE2IEZlYiBDZXJlcyBVUFMgRXhjaGFuZ2UgUiA1NyAwMTkuODEKCg==","RATING":""} |  |  | C000147234 | PHASE07 | 2024-01-15 | 2024-09-25 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-03-06 | 869565.22 | 0 |  |  | C000147234 | 1000000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000840 | Region 2 - Bulk PO - Various Retail Electrical Priority Requests - Cancelled | Region 2 - Bulk PO - Various Retail Electrical Priority Requests - Cancelled |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | U | 2024-01-03 | 2024-12-30 |  | ALP-N00062 | CRTD DLFL AVAC SETC: |  | false | true |  | Surina Ceaser |  | Region 2 Bulk PO | 2024 |  | U |  | CEASARS | 2023-11-20 | D | 0 |  | 1 |  |  | 0 | Cancelled 7 Dec 2023 by Absa Engineering | {"MANDT":"111","REFERENCE":90000840,"ONEVIEW":"36225X","DATE01":"2023-10-25","DATE02":"2023-11-22","DATE03":"2023-11-22","DATE04":"2023-11-22","DATE05":"2023-12-07","DATE06":"2023-12-21","DATE07":"2024-12-17","DATE08":"2025-01-07","DATE09":"2025-02-21","DATE10":"2025-02-28","DATE11":"2025-02-21","DATE12":"2025-02-21","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"492:28:0:0:15:14:362:21:45:14","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-21","FORECAST_END":"2024-12-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBEZWMgRGVjbGluZWQgYXQgUFJFIENCIHRvIGJlIHRyYW5zYWN0ZWQgYWdhaW5zdCBJbmRpdmlkdWFsIFJlcXVlc3RzCjIyIE5vdiBCdWxrIEJUQiB0byBiZSBzdWJtaXR0ZWQgZm9yIGFwcHJvdmFsIC0gMzAgTk9W","RATING":""} |  |  |  | DELETED | 2023-12-21 | 2024-12-17 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000841 | Absa Robertson - Minor Works | Absa Robertson - Minor Works |  |  | Region 1 |  | 77877X | 1000-70863-01 | Robertson-Paul Kruger St-Robertson |  | 2024-01-03 | 2024-04-30 |  | ALP-WC0028 | CRTD AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2024 |  |  |  | CEASARS | 2023-11-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-03 | 2024-04-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000842 | EOL-Various sites-Generator Starter Batt | EOL-Various sites-Generator Starter Batt |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-01-04 | 2023-12-14 |  | ALP-N00063 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2023 |  |  |  | LOUISR | 2023-11-21 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-01-04 | 2023-12-14 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000843 | Region1 BULK ENG Priority Requests | Region1 BULK ENG Priority Requests |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-01-03 | 2024-12-29 |  | ALP-N00064 | REL BUDG AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2024 |  |  |  | CEASARS | 2023-11-21 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-03 | 2024-12-29 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000147236 | 1000000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000844 | Region3 BULK ENG Priority Requests | Region3 BULK ENG Priority Requests |  |  | Region 3 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-01-03 | 2024-12-30 |  | ALP-N00065 | REL BUDG AVAC SETC: |  | false | false |  | Lindile Nomnganga |  |  | 2024 |  |  |  | CEASARS | 2023-11-21 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-03 | 2024-12-30 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000147155 | 1000000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000845 | Alice Lane BULK ENG Priority Requests | Alice Lane BULK ENG Priority Requests |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-01-03 | 2024-12-30 |  | ALP-N00066 | CRTD AVAC SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2024 |  |  |  | CEASARS | 2023-11-21 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-03 | 2024-12-30 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000846 | Absa Alberton Voortrekker Str- INS Glass | Absa Alberton Voortrekker Str- INS Glass |  |  | Region 1 |  | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville |  | 2023-07-11 | 2023-10-30 |  | ASP-GS0779 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2023-11-22 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-07-11 | 2023-10-30 |  | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000141974 | 8011.86 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000847 | Absa 190 Commissioner- INS Glass | Absa 190 Commissioner- INS Glass |  |  | Region 1 |  | 37039X | 1000-70208-01 | Absa 190 Commissioner St-Commissioner St-Johannesburg |  | 2023-03-08 | 2023-03-08 |  | ASP-GS0780 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2023-11-22 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-03-08 | 2023-03-08 |  | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000142323 | 6643.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000848 | Absa Sasol Pioneer Blg- INS Door | Absa Sasol Pioneer Blg- INS Door |  |  | Region 1 |  | 70647X | 1000-71518-01 | Sasol Pioneer Building-Cnr Fichardt & Bell St-Sasolburg |  | 2023-08-07 | 2023-08-28 |  | ASP-GS0781 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2023-11-22 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-08-07 | 2023-08-28 | PRESHANE MUNTHREE | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000142339 | 4981 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000849 | Absa Southdale banking Decal Retrospecti | Absa Southdale banking Decal Retrospecti |  |  | Region 1 |  | 77230X | 1000-70357-01 | Southdale Shopping Centre-Alamein Rd-Johannesburg |  | 2023-11-22 | 2023-11-22 |  | ASP-GS0782 | CRTD SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | GAMIETR | 2023-11-22 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000125594 | PHASE00 | 2023-11-22 | 2023-11-22 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2023-11-22 | 2101.11 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000850 | Absa Welkom - REplacement of HVAC Unit | Absa Welkom - REplacement of HVAC Unit |  |  | Region 3 | [5 empty] | 2023-12-28 |  |  | ASP-CR0525 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-28 | 2024-01-27 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000851 | Absa Bank Frankfort - Install dedicated | Absa Bank Frankfort - Install dedicated |  |  | Region 3 | [5 empty] | 2023-12-14 |  |  | ASP-CR0526 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-14 | 2024-01-13 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000852 | Absa Burger Street - Replacement of Fire | Absa Burger Street - Replacement of Fire |  |  | Region 3 | [5 empty] | 2023-12-28 |  |  | ASP-CR0527 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-28 | 2024-01-27 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000853 | Absa Zeerust - UPS plug installation | Absa Zeerust - UPS plug installation |  |  | Region 3 | [5 empty] | 2023-12-21 |  |  | ASP-CR0528 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-21 | 2024-01-20 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000854 | Absa Burger Street - Installation of Tim | Absa Burger Street - Installation of Tim |  |  | Region 3 | [5 empty] | 2023-11-29 |  |  | ASP-CR0529 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-11-29 | 2023-12-29 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000855 | Absa Mall@Carnival - INS Geyser | Absa Mall@Carnival - INS Geyser |  |  | Region 1 |  | 21869X | 1000-70043-01 | Mall@Carnival-Cnr Airport & Heidelberg Rd-Brakpan |  | 2023-06-30 | 2023-06-30 |  | ASP-GS0783 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roegshana Gamiet |  |  | 2023 |  |  |  | CEASARS | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-06-30 | 2023-06-30 | PRESHANE MUNTHREE | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000142356 | 3753.27 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000856 | Absa The Glen Additional power point | Absa The Glen Additional power point |  |  | Region 1 |  | 77239X | 1000-70359-01 | The Glen Shopping Centre-Cnr Orpen & Letaba St-Oakdene |  | 2023-11-24 | 2023-12-25 |  | ASP-GS0784 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2023 |  |  |  | GAMIETR | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-24 | 2024-02-24 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000857 | Absa Towers West 5th FLR Space Upgrade | Absa Towers West 5th FLR Space Upgrade |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-11-24 | 2023-12-18 |  | ASP-GS0785 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE08 | 2023-11-24 | 2023-12-18 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000138632 | 228240.75 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000858 | Absa Towers West Villa of Hope Electrica | Absa Towers West Villa of Hope Electrica |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2023-11-24 | 2023-12-11 |  | ASP-GS0786 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2023 |  |  |  | GAMIETR | 2023-11-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE10 | 2023-11-24 | 2023-12-11 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000859 | Absa Bloemfontein CBD - Minor Works (VO) | Absa Bloemfontein CBD - Minor Works (VO) |  |  | Region 3 | [5 empty] | 2023-12-28 |  |  | ASP-CR0530 | CRTD: |  | false | false |  |  |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-27 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-28 | 2024-01-27 |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000860 | Absa Sannieshof - Replace Rota Booth Doo | Absa Sannieshof - Replace Rota Booth Doo |  |  | Region 3 |  | 77996X | 1000-71305-01 | Sannieshof-Spoor St-Sannieshof |  | 2023-12-07 | 2023-12-21 |  | ASP-CR0531 | REL BUDG AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-07 | 2023-12-21 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142358 | 5997.1 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000861 | Absa Bultfontein - Repair Devils Fork | Absa Bultfontein - Repair Devils Fork |  |  | Region 3 |  | 79115X | 1000-71574-01 | Absa Bultfontein-President Swart St-Bultfontein |  | 2023-12-07 |  |  | ASP-CR0532 | REL BUDG AVAC RESA: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-07 | 2024-01-06 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142344 | 5500 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000862 | Absa Kathu - Replace Shopfront Glass | Absa Kathu - Replace Shopfront Glass |  |  | Region 3 |  | 21345X | 1000-71317-01 | Kathu-Rietbok St-Kathu |  | 2023-12-15 |  |  | ASP-CR0533 | CRTD BUDG AVAC RESA: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-15 | 2024-01-14 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142337 | 4510.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000863 | Absa Colesburg - Replace stolen electric | Absa Colesburg - Replace stolen electric |  |  | Region 3 |  | 78406X | 1000-71348-01 | Colesberg-Church St-Colesberg |  | 2023-12-07 |  |  | ASP-CR0534 | REL BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-07 | 2024-01-06 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000146008 | 8830.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000864 | Absa King Williams Town - Dilaps | Absa King Williams Town - Dilaps Brick 2x Ground Floor Windows in Vacant Space |  |  | Region 2 | Eastern Cape | 78329X | 1000-71043-01 | Absa King Williams Town-Cnr Cathcart & Maclean St-King Williams Town | N | 2023-12-01 | 2023-12-29 |  | ASP-EC0377 | CLSD BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-11-28 | D | 64776.98 |  | 100 | 2023-11-28 | 2023-12-05 | 64776.98 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000864,"ONEVIEW":"78329X","DATE01":"2023-11-07","DATE02":"2023-11-14","DATE03":"2023-11-28","DATE04":"2023-11-28","DATE05":"2023-12-05","DATE06":"2023-12-13","DATE07":"2024-01-13","DATE08":"2024-01-26","DATE09":"2024-03-11","DATE10":"2024-03-31","DATE11":"2024-02-18","DATE12":"2024-02-18","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"145:7:14:0:7:8:31:13:45:12","PROGRESS":83,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-13","FORECAST_END":"2024-01-13","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgSmFuIC0gRmluYWwgUE9DIFN1Ym1pdHRlZCAyNiBKYW4KMjIgSmFuIC0gSW52b2ljZSByZWNlaXZlZCB0byBiZSBzZW50IGZvciBzaWdub2ZmCjE1IEphbiBDb21wbGV0ZWQgUE9DIFBlbmRpbmcKMTQgRGVjIGluIFByb2dyZXNzIHRvIGJlIGNvbXBsZXRlZCBieSAyMHRoIERlYwoxMSBEZWMgQlYgcG8gcmVjZWl2ZWQgLSA0NTAwODc3OTkzCjcgRGVjIFBDIHRvIGZvbGxvdyB1cCBvbiBCViBQTwo2IERlYyBBYnNhIFBPIEMwMDAxMjk0NjggUmVjZWl2ZWQgQlYgUE8gUmVxdWVzdGVkCjUgRGVjIEFwcHJvdmVkIGJ5IFJlYWwgRXN0YXRlIFBPJ3MgdG8gRm9sbG93CjQgRGVjIEZvbGxvdyB1cCBzZW50IHRvIHJlYWwgZXN0YXRlIGZvciBhcHByb3ZhbAozMCBOb3YgU3VibWl0dGVkIHRvIFJlYWwgRXN0YXRlIGZvciBhcHByb3ZhbAoyOSBOb3YgU3VwcG9ydGVkIGJ5IENSRVMgVlAKMjggTm92IFN1Ym1pdHRlZCBmb3IgQ3JlcyBBcHByb3ZhbCB0byBzdWJtaXQgdG8gUmVhbCBFc3RhdGUgUiA2NCA3NzYuOTgKMjcgTm92IEJDIHBhY2sgdG8gYmUgc2VudCBmb3IgcmV2aWV3IGFuZCBhcHByb3ZhbCBieSBSZWFsIEVzdGF0ZS4yMyBOb3YgUE0gdG8gc3VibWl0IEJDIHBhY2sgb24gMjMuMTEuMjMKIDcgTm92IFJlcXVlc3QgZnJvbSBSZWFsIEVzdGF0ZSB0byBCcmljayB1cCBXaW5kb3dzIC0gUE0gdG8gcmVxdWVzdCBjb3N0cw==","RATING":""} |  |  | C000129468 | PHASE11 | 2023-12-13 | 2024-01-13 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2023-12-06 | 56327.81 | 0 |  |  | C000129468 | 56327.8 |  | 5429.73 |  | 0 | 5429.73 | C000146875 | 64776.98 |  | 0 |  |  | 2024-03-05
90000865 | Absa Grahamstown - Generator Rental | Absa Grahamstown - Generator Rental |  |  | Region 2 | Eastern Cape | 77512X | 1000-71029-01 | Absa Grahamstown-High St-Grahamstown | N | 2023-12-01 | 2024-04-30 |  | ASP-EC0378 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  | F |  | CEASARS | 2023-11-28 | D | 0 |  | 1 |  |  | 0 | Repairs to be conducted on site | {"MANDT":"111","REFERENCE":90000865,"ONEVIEW":"77512X","DATE01":"2023-09-22","DATE02":"2023-09-29","DATE03":"2023-10-20","DATE04":"2023-10-27","DATE05":"2023-11-17","DATE06":"2023-12-01","DATE07":"2024-04-30","DATE08":"2024-05-21","DATE09":"2024-07-05","DATE10":"2024-07-31","DATE11":"0000-00-00","DATE12":"0000-00-00","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-01","FORECAST_END":"2024-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2024-02-02 | 2024-07-02 | RODERICK NEVAY | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000866 | Alice Lane South Install VC equipment Ground floor boardroom | Alice Lane South Install VC Ground floor Boardroom |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2023-11-28 | 2023-12-28 |  | ASP-GS0787 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2023 |  |  |  | GAMIETR | 2023-11-28 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000866,"ONEVIEW":"37140X","DATE01":"2023-09-06","DATE02":"2023-09-07","DATE03":"2023-09-16","DATE04":"2023-09-23","DATE05":"2023-09-05","DATE06":"2023-09-19","DATE07":"2023-10-19","DATE08":"2023-11-11","DATE09":"2023-11-30","DATE10":"2023-11-30","DATE11":"2023-11-30","DATE12":"2023-11-30","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":100,"PROG09":100,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"","PROGRESS":88,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-09-19","FORECAST_END":"2023-10-19","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UE9DIFN1Ym1pdHRlZCB0byBmaW5hbmNl","RATING":""} |  |  |  | PHASE10 | 2023-09-19 | 2023-10-19 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000129678 | 12000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000867 | 270 Republic- Request for drawings | 270 Republic- Request for drawings |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2023-12-05 | 2024-01-31 |  | ASP-GS0788 | CRTD AVAC: |  | false | false |  | Loreshan Naicker |  |  | 2023 |  |  |  | LOUISR | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-05 | 2024-01-31 | LUCIA AMUNGA |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000868 | Absa House Pinetown- Replace damaged Cei | Absa House Pinetown- Replace damaged Cei |  |  | Region 3 |  | 77102X | 1000-71156-01 | House Pinetown-Church Ln-Pinetown |  | 2023-12-07 |  |  | ASP-KZ0271 | REL BUDG AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-07 | 2024-01-06 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000145601 | 3592.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000869 | Absa Limpopo Mall - Branch Dilaps | Absa Limpopo Mall - Branch Dilaps |  |  | Region 3 |  | 78979X | 1000-70547-01 | Limpopo Mall-Cnr Rissik, Market, Devenish & Kerk St-Polokwane |  | 2023-12-29 |  |  | ASP-LP0186 | CRTD RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-29 | 2024-01-28 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000870 | Absa Elim Mall - Branch Dilaps | Absa Elim Mall - Branch Dilaps |  |  | Region 3 |  | 35022X | 1000-70483-01 | Elim Mall-Cnr Giyani & Levubu Rd-Elim |  | 2023-12-28 | 2024-03-07 |  | ASP-LP0187 | CRTD RESA: |  | false | false |  | Kagiso Seothaeng |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-11-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-28 | 2024-03-07 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000871 | Absa Robertson - Minor Works | Absa Robertson - Minor Works |  |  | Region 2 | Western Cape | 77877X | 1000-70863-01 | Robertson-Paul Kruger St-Robertson | N | 2023-12-01 | 2024-04-30 |  | ASP-WC0341 | CRTD SETC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-11-28 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_337 4 March Planner to confirm cancel in writing as planned IOP facelift 2025 | {"MANDT":"111","REFERENCE":90000871,"ONEVIEW":"77877X","DATE01":"2023-11-20","DATE02":"2023-12-08","DATE03":"2023-12-29","DATE04":"2024-01-05","DATE05":"2024-01-26","DATE06":"2024-04-15","DATE07":"2024-05-20","DATE08":"2024-06-10","DATE09":"2024-07-25","DATE10":"2024-07-31","DATE11":"2024-09-13","DATE12":"2024-09-13","PROG01":0,"PROG02":20,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"315:18:21:7:21:80:35:21:45:17","PROGRESS":1,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-15","FORECAST_END":"2024-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgRmViIFBsYW5uZXIgY29uZmlybWVkIElPUCBwcm9qZWN0CjI5IEphbiAtIFRPIGJlIGRvbmUgdmlhIElPUAoyMiBKYW4gUGxhbm5lciB5ZXQgdG8gY29uZmlybSBhcyBwb3NzaWJseSBhbiBJT1AgcHJvamVjdCAtIFBsYW5uaW5nIDE1IEFwciB0byAyMCBNYXkKMTEgRGVjIFBsYW5uZXIgdG8gY29uZmlybSBhcyBwb3NzaWJseSBhbiBJT1AgcHJvamVjdAo0IERlYyBQbGFubmVyIHRvIGNvbmZpcm0gYXMgcG9zc2libHkgYW4gSU9QIHByb2plY3QKMjcgTm92IFBsYW5uZXIgdG8gY29uZmlybSBpZiBsaW1pdGVkIHNjb3BlIG9yIG1pbm9yIHdvcmtzIChoYXMgdG8gZW5nYWdlIHdpdGggbWFuYWdlbWVudCBmb3IgY29uZmlybWF0aW9uKQoyMCBOb3YgLSBBZGRlZCBhcyBwYXJ0IG9mIENJUDIwMjQ=","RATING":""} |  |  |  | PHASE12 | 2024-04-15 | 2024-05-20 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000872 | Absa De Wagenweg - HVAC - Back Office | Absa De Wagenweg - HVAC - Back Office |  |  | Region 2 | Western Cape | 70650X | 1000-70785-01 | De Wagenweg Office Park Block B-Adam Tas Rd-Stellenbosch | N | 2023-12-01 | 2024-04-30 |  | ASP-WC0342 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2023 |  | L |  | CEASARS | 2023-11-28 | D | 0 |  | 1 |  |  | 0 | Done as Part of Bulk PO ALP-N00069 | {"MANDT":"111","REFERENCE":90000872,"ONEVIEW":"70650X","DATE01":"2023-12-04","DATE02":"2023-12-11","DATE03":"2024-01-01","DATE04":"2024-01-08","DATE05":"2024-01-29","DATE06":"2024-02-12","DATE07":"2024-07-12","DATE08":"2024-08-02","DATE09":"2024-09-16","DATE10":"2024-09-30","DATE11":"2024-09-11","DATE12":"2024-09-11","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:151:21:45:19","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-12","FORECAST_END":"2024-07-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NyBEZWMgLSBMZWFkIHRpbWVzIGFuZCBHTVAgdG8gYmUgY29uZmlybWVkLiBQTSB0byBmb2xsb3cgdXAgcmUgcXVvdGVzLgo0IERlYyBQTSBmb2xsb3dpbmcgdXAgb24gUFJGIGFuZCBRdW90ZXMKMzAgTm92IFBSRiBQZW5kaW5n","RATING":""} |  |  |  | PHASE12 | 2024-02-12 | 2024-07-12 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000873 | Absa Trompsburg - Water Tank Installatio | Absa Trompsburg - Water Tank Installatio |  |  | Region 3 |  | 79334X | 1000-71585-01 | Absa Trompsburg-Voortrekker St-Trompsburg |  | 2024-01-10 |  |  | ASP-CR0535 | REL BUDG AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2023-11-30 | D | 0 |  |  |  |  | 0 |  |  |  |  | C000121836 | PHASE00 | 2024-01-10 | 2024-02-09 | NANDE MAQUBELA | Juanita Van Coller | 0 |  |  |  |  | 2023-11-08 | 99776.82 | 0 |  |  | C000141200 | 99776.82 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000874 | EOL: Corp LED- Yellow lights | EOL: Corp LED- Yellow lights |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-01-27 | 2024-06-28 |  | ALP-N00067 | REL BUDG AVAC SETC: |  | false | false |  | Mukuru Wesigye |  |  | 2023 |  |  |  | LOUISR | 2023-12-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-01-27 | 2024-06-28 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000140950 | 6844710.93 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000875 | EOL: Retail LED- Yellow lights | EOL: Retail LED- Yellow lights |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-01-27 | 2024-06-28 |  | ALP-N00068 | REL BUDG AVAC RESA SETC: |  | false | false |  | Mukuru Wesigye |  |  | 2023 |  |  |  | LOUISR | 2023-12-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-01-27 | 2024-06-28 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000140948 | 5297300.14 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000876 | Absa Klerksdorp - DILAPS | Absa Klerksdorp - DILAPS |  |  | Region 3 |  | 77852X | 1000-71301-01 | Absa Church Street-Oliver Tambo St-Klerksdorp |  | 2023-12-27 | 2024-02-14 |  | ASP-CR0536 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-12-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-27 | 2024-02-14 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000877 | Absa Bela Bela - DILAPS | Absa Bela Bela - DILAPS |  |  | Region 3 |  | 76787X | 1000-70523-01 | Bushveld Pick & Pay Centre-Cnr Mark & Potgieter St-Bela Bela |  | 2023-12-21 | 2024-02-22 |  | ASP-LP0188 | REL ISBD AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2023 |  |  |  | NOMNGANGAL | 2023-12-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-21 | 2024-02-22 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000878 | Absa Riversdale - UPS ex stock | Absa Riversdale - UPS ex stock |  |  | Region 2 |  | 37159X | 1000-70797-01 | Absa Riversdale-Cnr Church & Dixon St-Riversdale |  | 2023-12-11 | 2023-12-29 |  | ASP-EC0379 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2023 |  |  |  | CEASARS | 2023-12-07 | D | 0 |  | 1 |  |  | 0 | Done as Part of Bulk PO ALP-N00069 | {"MANDT":"111","REFERENCE":90000878,"ONEVIEW":"37159X","DATE01":"2023-09-22","DATE02":"2023-09-29","DATE03":"2023-10-20","DATE04":"2023-10-27","DATE05":"2023-11-17","DATE06":"2023-12-01","DATE07":"2023-12-07","DATE08":"2023-12-28","DATE09":"2024-02-11","DATE10":"2024-02-29","DATE11":"2024-02-11","DATE12":"2024-02-11","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-01","FORECAST_END":"2023-12-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2023-12-01 | 2023-12-07 | RODERICK NEVAY | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000879 | Absa Rosslyn Security Door Implementatio | Absa Rosslyn Security Door Implementatio |  |  | Region 1 |  | 76646X | 1000-70301-01 | Rosstax Centre-Cnr R566 & Hardie Muller St-Rosslyn |  | 2023-12-07 | 2023-12-29 |  | ASP-GN0239 | REL RESA SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2023 |  |  |  | GAMIETR | 2023-12-07 | D | 0 |  | 100 |  |  | 332352.98 |  | {"MANDT":"111","REFERENCE":90000879,"ONEVIEW":"76646X","DATE01":"2023-09-28","DATE02":"2023-10-05","DATE03":"2023-10-26","DATE04":"2023-11-02","DATE05":"2023-11-23","DATE06":"2023-12-07","DATE07":"2023-12-29","DATE08":"2024-01-19","DATE09":"2024-03-04","DATE10":"2024-03-31","DATE11":"2024-03-04","DATE12":"2024-03-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2023-12-07","FORECAST_END":"2023-12-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAuMDIgTk46IEFic2EgUE8gb2J0YWluZWQgYXdhaXRpbmcgQkZNIFBP","RATING":""} |  |  | C000142469 | PHASE06 | 2023-12-07 | 2023-12-29 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2024-02-14 | 289002.59 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000880 | Absa Clearwater- Reinstatement | Absa Clearwater -Reinstatement |  |  | Region 1 | Gauteng | 77174X | 1000-70352-01 | Clearwater Office Park Building 4-Millenium Rd-Strubensvalley |  | 2023-12-07 | 2024-01-31 |  | ALP-GS0087 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  | L |  | GAMIETR | 2023-12-07 | D | 2299861.81 |  | 100 | 2023-12-07 | 2023-12-07 | 2299861.81 |  | {"MANDT":"111","REFERENCE":90000880,"ONEVIEW":"77174X","DATE01":"2023-09-28","DATE02":"2023-11-01","DATE03":"2023-11-10","DATE04":"2023-11-17","DATE05":"2023-12-07","DATE06":"2024-01-02","DATE07":"2024-02-02","DATE08":"2024-02-23","DATE09":"2024-04-08","DATE10":"2024-04-30","DATE11":"2024-04-06","DATE12":"2024-04-06","PROG01":0,"PROG02":100,"PROG03":0,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"215:34:9:7:20:26:31:21:45:24","PROGRESS":13,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-01-02","FORECAST_END":"2024-02-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAyMy8xMi8wOCBBUzogVGhlIGJyYW5jaCBpcyBjbG9zaW5nIG9uIHRoZSAzMC8xMi8yMDIzLCBjb250cmFjdG9yIHdpbGwgYmUgb25zaXRlIG9uIHRoZSAwMi8wMS8yNA==","RATING":""} |  |  | C000130154 | PHASE10 | 2024-01-02 | 2024-01-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 1999879.83 | 1730738.8 |  |  | C000148137 | 227450.18 |  | 199034.96 |  | 0 | 0 |  | 0 |  | 0
90000881 | Absa Krugersdorp Dilaps Security VO | Absa Krugersdorp Dilaps Security VO |  |  | Region 1 |  | 76486X | 1000-70267-01 | Absa Centre Krugersdorp-Cnr Burger & Monument St-Krugersdorp |  | 2023-12-08 | 2023-12-29 |  | ASP-GN0240 | REL BUDG ISBD AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2023 |  |  |  | GAMIETR | 2023-12-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE09 | 2023-12-05 | 2023-12-12 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000130474 | 126156.41 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000882 | Emergency Engineering Requests | Emergency Engineering Requests |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2023-12-18 | 2024-06-28 |  | ALP-N00069 | REL BUDG AVAC RESA SETC: |  | false | false |  | Lucia Amunga |  |  | 2023 |  |  |  | LOUISR | 2023-12-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2023-12-18 | 2024-06-28 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000130156 | 4753565.22 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000883 | Absa Bloemfontein CBD- Minor Works | Absa Bloemfontein CBD- Minor Works |  |  | Region 3 |  | 22161X | 1000-71476-01 | Bloemfontein Forum-Donald Murray Ave-Bloemfontein |  | 2024-01-22 | 2024-01-31 |  | ASP-CR0537 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2023-12-11 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-22 | 2024-01-31 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000884 | Absa Bank Hopetown- Install 15KVA UPS | Absa Bank Hopetown- Install 15KVA UPS |  |  | Region 3 |  | 78645X | 1000-71353-01 | Hopetown-Cnr Widd & Kerk St-Hopetown |  | 2024-01-23 | 2024-01-31 |  | ASP-CR0538 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2023-12-11 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-23 | 2024-01-31 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000885 | Absa Harrismith - Minor Works | Absa Harrismith - Minor Works |  |  | Region 3 |  | 78625X | 1000-71546-01 | Harrismith-Cnr Southey & Stuart St-Harrismith |  | 2024-02-08 | 2024-04-30 |  | ASP-CR0539 | REL BUDG AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000149478 | 56051.53 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000886 | Absa Hennenman - Minor Works | Absa Hennenman - Minor Works |  |  | Region 3 |  | 78855X | 1000-71558-01 | Absa Hennenman-Kerk St-Hennenman |  | 2024-02-08 | 2024-04-30 |  | ASP-CR0540 | CRTD RESA: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000887 | Absa Carnarvon - Replacement of Louvers | Absa Carnarvon - Replacement of Louvers |  |  | Region 3 |  | 79297X | 1000-71360-01 | Absa Carnarvon-Cnr Victoria & Van Riebeeck St-Carnarvon |  | 2024-02-08 | 2024-05-02 |  | ASP-CR0541 | CRTD: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-05-02 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000888 | Pretoria Campus non slip stair nosings | Pretoria Campus non slip stair nosings |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2024-01-08 | 2024-02-08 |  | ASP-GN0241 | REL BUDG AVAC SETC: |  | false | false |  | Phathu Neduvhuledza |  |  | 2024 |  |  |  | GAMIETR | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-08 | 2024-02-08 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000142479 | 19410.93 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000889 | Absa Warden - Minor Works | Absa Warden - Minor Works |  |  | Region 3 |  | 79096X | 1000-71571-01 | Absa Warden-Piet Retief St-Warden |  | 2024-02-08 | 2024-04-30 |  | ALP-CR0041 | CRTD AVAC RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000890 | Absa Ladybrand - Minor Works | Absa Ladybrand - Minor Works |  |  | Region 3 |  | 78841X | 1000-71556-01 | Absa 17A Joubert Street-Joubert St-Ladybrand |  | 2024-02-08 | 2024-04-30 |  | ALP-CR0042 | CRTD RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000891 | Absa Carnarvon - Construction of BM Offi | Absa Carnarvon - Construction of BM Offi |  |  | Region 3 |  | 79297X | 1000-71360-01 | Absa Carnarvon-Cnr Victoria & Van Riebeeck St-Carnarvon |  | 2024-02-08 | 2024-04-30 |  | ALP-CR0043 | CRTD RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000892 | Absa Demountable Thlabane- Dilaps | Absa Demountable Thlabane- Dilaps |  |  | Region 3 |  | 78556X | 1000-71311-01 | Land For Absa Demountable Bank Unit-Cnr Motsatsi & Makheni St-Thlabane |  | 2024-02-08 | 2024-05-02 |  | ASP-CR0542 | REL BUDG AVAC RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-09 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-05-02 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000152536 | 233249.04 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000893 | Absa Active Park Office - Minor Refresh | Absa Active Park Office - Minor Refresh |  |  | Region 3 |  | 79379X | 1000-71237-01 | Active Park Newcastle-Whyte St-Newcastle |  | 2024-03-01 | 2024-05-30 |  | ALP-KZ0008 | CRTD AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-15 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000894 | Absa Phokeng Mall - Construction of Offi | Absa Phokeng Mall - Construction of Offi |  |  | Region 3 |  | 78032X | 1000-71306-01 | Phokeng Mall-Main Rd-Rustenburg |  | 2024-02-28 | 2024-04-30 |  | ASP-CR0543 | CRTD RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-28 | 2024-04-30 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000895 | Absa Rusternburg Mall - Enlarge ATMRoom | Absa Rusternburg Mall - Enlarge ATMRoom |  |  | Region 3 |  | 37048X | 1000-71273-01 | Rustenburg Mall-Swartruggens Rd-Rustenburg |  | 2024-02-28 | 2024-05-30 |  | ASP-CR0544 | CRTD RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-28 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000896 | Absa Mega City Centre-Replace Carpets | Absa Mega City Centre-Replace Carpets |  |  | Region 3 |  | 77784X | 1000-71299-01 | Mega City Shopping Centre-Cnr Sekame St & Dr. James Maroka Dr-Mmabatho |  | 2024-02-29 | 2024-05-30 |  | ASP-CR0545 | CRTD RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-29 | 2024-05-30 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000897 | Absa Blouberg Mall- Minor Works | Absa Blouberg Mall- Minor Works |  |  | Region 3 |  | 76787X | 1000-70523-01 | Bushveld Pick & Pay Centre-Cnr Mark & Potgieter St-Bela Bela |  | 2024-03-01 | 2024-05-02 |  | ASP-LP0189 | CRTD AVAC RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-02 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000898 | Absa Groblersdal Mall- Minor Works | Absa Groblersdal Mall- Minor Works |  |  | Region 3 |  | 36251X | 1000-70667-01 | Groblersdal Mall-Main Rd-Groblersdal |  | 2024-03-01 | 2024-04-29 |  | ASP-LP0190 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-04-29 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000899 | Absa Jane Furse - Minor Works | Absa Jane Furse - Minor Works |  |  | Region 3 |  | 76783X | 1000-70521-01 | Jane Furse Plaza-Groblersdal Rd-Jane Furse |  | 2024-03-01 | 2024-05-02 |  | ASP-LP0191 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-02 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000900 | Absa Thavhani Mall - Minor Works | Absa Thavhani Mall - Minor Works |  |  | Region 3 |  | 36254X | 1000-70503-01 | Thavhani Mall-Cnr R524 & Giyani Rd-Thohoyandou |  | 2024-03-01 | 2024-05-02 |  | ASP-LP0192 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-02 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000901 | Absa Musina Mall - Minor Works | Absa Musina Mall - Minor Works |  |  | Region 3 |  | 36246X | 1000-70502-01 | Musina Mall-Smelter Ave-Musina |  | 2024-03-01 | 2024-05-02 |  | ASP-LP0193 | CRTD RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-02 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000902 | Absa Mokopane - Minor Works | Absa Mokopane - Minor Works |  |  | Region 3 |  | 76787X | 1000-70523-01 | Bushveld Pick & Pay Centre-Cnr Mark & Potgieter St-Bela Bela |  | 2024-03-01 | 2024-05-02 |  | ASP-LP0194 | CRTD BUDG SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-02 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000903 | Absa Carolina- Minor Works | Absa Carolina- Minor Works |  |  | Region 3 |  | 78145X | 1000-70684-01 | Absa Carolina-Voortrekker St-Carolina |  | 2024-02-28 | 2024-04-29 |  | ASP-MP0177 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-28 | 2024-04-29 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000904 | Absa Matsamo Plaza- Minor Works | Absa Matsamo Plaza- Minor Works |  |  | Region 3 |  | 77316X | 1000-70622-01 | Matsamo Plaza-Cnr R570 & R323 Rd-Matsamo |  | 2024-03-28 | 2024-05-02 |  | ASP-MP0178 | CRTD RESA: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-02 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000905 | Absa Kabokweni Plaza-Minor Works | Absa Kabokweni Plaza-Minor Works |  |  | Region 3 |  | 78671X | 1000-70657-01 | Kabokweni Plaza-Cnr Kabokweni & Palaston Rd-White River |  | 2024-03-28 | 2024-06-28 |  | ALP-MP0208 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-06-28 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000906 | Absa Kriel Mall - Minor Works | Absa Kriel Mall - Minor Works |  |  | Region 3 |  | 77028X | 1000-70606-01 | Kriel Mall-Bronwyn St-Kriel |  | 2024-03-28 | 2024-06-28 |  | ALP-MP0209 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-06-28 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000907 | Absa United Building-Minor Works | Absa United Building-Minor Works |  |  | Region 3 |  | 77584X | 1000-70638-01 | United Building-Kerk St-Ermelo |  | 2024-03-28 | 2024-06-28 |  | ALP-MP0210 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-06-28 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000908 | Absa Cathcart Queenstown - Internal Painting | Absa Cathcart Queenstown - Internal Painting |  |  | Region 2 | Eastern Cape | 78381X | 1000-71465-01 | Cathcart-Cathcart Rd-Queenstown | N | 2024-08-30 | 2024-12-31 |  | ASP-EC0380 | CRTD SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 4 March Remove Not Priority as per priority meeting | {"MANDT":"111","REFERENCE":90000908,"ONEVIEW":"78381X","DATE01":"2024-06-21","DATE02":"2024-06-28","DATE03":"2024-07-19","DATE04":"2024-07-26","DATE05":"2024-08-16","DATE06":"2024-08-25","DATE07":"2024-09-25","DATE08":"2024-10-16","DATE09":"2024-11-30","DATE10":"2024-11-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"283:7:21:7:21:9:31:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-08-25","FORECAST_END":"2024-09-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCBSZW1vdmUgTm90IFByaW9yaXR5IGFzIHBlciBwcmlvcml0eSBtZWV0aW5nCjI4IEZlYiAgaW5pdGlhbCAtIE5vdCBwcmlvcml0eSAsIEVCIHRvIGNvbmZpcm0gbWVldGluZyAtIDQgTWFyY2gKMjkgSmFuIC0gTm90IHByaW9yaXR5IHdpdGggcmVnaW9uIHBvc3NpYmxlIDIwMjUgYXMgcGVyIGRpc2N1c3Npb24gd2l0aCBFQihGRykgMjYgSmFuCjIyIEphbiAtIFBNIHRvIGNvbmZpcm0gd2l0aCBwbGFubmVyIC0gRXhlY3V0aW9uIFBsYW5uaW5nIDI1IEF1ZyAtIDI1IFNlcHQ=","RATING":""} |  |  |  | PHASE12 | 2024-08-25 | 2024-09-25 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000909 | Absa Cradock - Internal Painting | Absa Cradock - Internal Painting |  |  | Region 2 | Eastern Cape | 76934X | 1000-71022-01 | Absa Cradock-Adderley St-Cradock | N | 2024-07-31 | 2024-12-31 |  | ASP-EC0381 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 15 |  |  | 0 | Absa Ref : Opex 4 March On Hold as per priority Meeting TBC due to planned Facelift 2025 | {"MANDT":"111","REFERENCE":90000909,"ONEVIEW":"76934X","DATE01":"2024-05-01","DATE02":"2024-05-08","DATE03":"2024-05-29","DATE04":"2024-06-05","DATE05":"2024-06-26","DATE06":"2024-07-15","DATE07":"2024-08-15","DATE08":"2024-09-05","DATE09":"2024-10-20","DATE10":"2024-10-31","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:19:31:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-15","FORECAST_END":"2024-08-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgRmViIE9uIEhvbGQgLCBFQiB0byBjb25maXJtIG1lZXRpbmcgLSAyOCBGZWIKMTkgRmViIE9OIEhvbGQgUE0gdG8gZm9sbG93IHVwIHJlIE91dGNvbWUgb2YgRUIgcGxhbm5pbmcgbWVldGluZwoyOSBKYW4gLSBPbiBIb2xkIC0gTm90IHByaW9yaXR5IHdpdGggcmVnaW9uIHBvc3NpYmxlIElPUCBhcyBwZXIgZGlzY3Vzc2lvbiB3aXRoIEVCKEZHKSAyNiBKYW4KMjIgSmFuIC0gUE0gdG8gY29uZmlybSB3aXRoIHBsYW5uZXIgLSBFeGVjdXRpb24gUGxhbm5pbmcgMTUgSnVsIC0gMTUgQXVn","RATING":""} |  |  |  | PHASE00 | 2024-07-15 | 2024-08-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000910 | Absa Despatch - Minor Works | Absa Despatch - Minor Works |  |  | Region 2 | Eastern Cape | 76549X | 1000-71459-01 | Absa Despatch-Main St-Despatch | N | 2024-06-01 | 2024-12-31 |  | ASP-EC0382 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_344 4 March - Defer as per priority meeting to be done 2025 | {"MANDT":"111","REFERENCE":90000910,"ONEVIEW":"76549X","DATE01":"2024-03-23","DATE02":"2024-03-30","DATE03":"2024-04-20","DATE04":"2024-04-27","DATE05":"2024-05-18","DATE06":"2024-06-01","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"373:7:21:7:21:14:29:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIERlZmVyIGFzIHBlciBwcmlvcml0eSBtZWV0aW5nCjQgTWFyY2ggLSBFQiB0byBjb25maXJtIGFzIG5vIFByb2plY3QgcGxhbm5lZCBmcm9tIElPUAoyOCBGZWIgSW5pdGlhbCBJbmRpY2F0aW9uIE5vdCBwcmlvcml0eSAsIEVCIHRvIGNvbmZpcm0gbWVldGluZyAtIDQgTWFyY2gKMjYgRmViIEluaXRpYWwgSW5kaWNhdGlvbiBOb3QgcHJpb3JpdHkgLCBFQiB0byBjb25maXJtIG1lZXRpbmcgLSAyOCBGZWIKMjggRmViIEluaXRpYWwgSW5kaWNhdGlvbiBOb3QgcHJpb3JpdHkgLCBFQiB0byBjb25maXJtIG1lZXRpbmcgLSA0IE1hcmNoCjI5IEphbiAtIE5vdCBwcmlvcml0eSB3aXRoIHJlZ2lvbiBwb3NzaWJsZSAyMDI1IGFzIHBlciBkaXNjdXNzaW9uIHdpdGggRUIoRkcpIDI2IEphbgoyMiBKYW4gUE0gdG8gY29uZmlybSBzY29wZSBhbmQgcmVxdWVzdCBxdW90ZXMgLSBQbGFubmVkIGV4ZWN1dGlvbiAxIEp1bmUgdG8gMzAgSnVuZQ==","RATING":""} |  |  |  | PHASE12 | 2024-06-01 | 2024-06-30 | RODERICK NEVAY | Juanita van Coller | 0 | [5 empty] | 0 | 288285.98 |  |  | 2910289 | 4984.28 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000911 | Absa Grahamstown - Internal Painting | Absa Grahamstown - Internal Painting |  |  | Region 2 | Eastern Cape | 77512X | 1000-71029-01 | Absa Grahamstown-High St-Grahamstown | N | 2024-08-30 | 2024-12-31 |  | ASP-EC0383 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 15 |  |  | 0 | Absa Ref : Opex 4 March On Hold as per priority Meeting TBC due to planned Facelift 2025 | {"MANDT":"111","REFERENCE":90000911,"ONEVIEW":"77512X","DATE01":"2024-05-08","DATE02":"2024-05-15","DATE03":"2024-06-05","DATE04":"2024-06-12","DATE05":"2024-07-03","DATE06":"2024-08-01","DATE07":"2024-08-30","DATE08":"2024-09-20","DATE09":"2024-11-04","DATE10":"2024-11-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:29:29:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-08-01","FORECAST_END":"2024-08-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgRmViIERyYXdpbmdzIFJlY2VpdmVkIC0gUHJpb3JpdHkgdG8gYmUgY29uZmlybWVkIGJ5IEVCIDI4IEZlYgoxOSBGZWIgRmxvb3IgcGxhbnMgcmVjZWl2ZWQgc2l0ZSB2aXNpdCB0byBiZSBjb25kdWN0ZWQKNSBGZWIgc2l0ZSB2aXNpdCB0byBiZSBjb25kdWN0ZWQsIEZsb29yIHBsYW5zIHRvIGJlIHJlcXVlc3RlZAoyOSBKYW4gLVByaW9yaXR5IHdpdGggcmVnaW9uIGFzIHBlciBkaXNjdXNzaW9uIHdpdGggRUIoRkcpIDI2IEphbiAtIFNpdGUgdmlzaXQgdG8gYmUgYXJyYW5nZWQKMjIgSmFuIC0gUE0gdG8gY29uZmlybSB3aXRoIHBsYW5uZXIgLSBFeGVjdXRpb24gUGxhbm5pbmcgMSBBdWcgLSAzMCBBdWc=","RATING":""} |  |  |  | PHASE00 | 2024-08-01 | 2024-08-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000912 | Absa Patensie - Minor Works | Absa Patensie - Minor Works |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2024-07-31 | 2024-12-31 |  | ASP-EC0384 | CRTD: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_340 | {"MANDT":"111","REFERENCE":90000912,"ONEVIEW":"77876X","DATE01":"2024-01-01","DATE02":"2024-01-08","DATE03":"2024-01-29","DATE04":"2024-02-05","DATE05":"2024-02-26","DATE06":"2024-05-20","DATE07":"2024-06-20","DATE08":"2024-07-11","DATE09":"2024-08-25","DATE10":"2024-08-31","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:84:31:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-20","FORECAST_END":"2024-06-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFJvdW5kIHRyaXAgcmVxdWVzdGVkIHdlZWsgb2YgMjYgRmViIGZvciBidWlsZGluZyBSZWZ1cmJpc2hlcwo1IEZlYiBSb3VuZCB0cmlwIHJlcXVlc3RlZCB3ZWVrIG9mIDI2IEZlYiBmb3IgYnVpbGRpbmcgUmVmdXJiaXNoZXMKMjkgSmFuIC1Qcmlvcml0eSB3aXRoIHJlZ2lvbiBhcyBwZXIgZGlzY3Vzc2lvbiB3aXRoIEVCKEZHKSAyNiBKYW4gLSBTaXRlIHZpc2l0IHRvIGJlIGFycmFuZ2VkCjIyIEphbiAtIFBNIHRvIGFycmFuZ2Ugc2l0ZSB2aXNpdCB0byBkZXRlcm1pbmUgZnVsbCBzY29wZSAtIFBsYW5uaW5nIGZvciAyMCBNYXkgdG8gMjAgSnVuZQ==","RATING":""} |  |  |  | PHASE00 | 2024-08-03 | 2024-09-02 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000913 | Absa Somerset East - Minor Works | Absa Somerset East - Minor Works |  |  | Region 2 | Eastern Cape | 76426X | 1000-71008-01 | Absa Somerset East-Njoli St-Somerset East | N | 2024-06-01 | 2024-12-31 |  | ASP-EC0385 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_341 4 March -On Hold as per priority meeting possible IOP project - If IOP approved cancel | {"MANDT":"111","REFERENCE":90000913,"ONEVIEW":"76426X","DATE01":"2024-03-23","DATE02":"2024-03-30","DATE03":"2024-04-20","DATE04":"2024-04-27","DATE05":"2024-05-18","DATE06":"2024-05-15","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"373:7:21:7:21:-3:46:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtT24gSG9sZCBhcyBwZXIgcHJpb3JpdHkgbWVldGluZyBwb3NzaWJsZSBJT1AgcHJvamVjdCAtIElmIElPUCBhcHByb3ZlZCBjYW5jZWwKNCBNYXJjaCAtIElPUCBQcm9qZWN0IHRvIGNvbXBsZXRlIHRoZSBzY29wZSBpZiBBcHByb3ZlZCBhdCBJQwoyNiBGZWIgLSBTaXRlIHZpc2l0IHRvIGJlIHNjaGVkdWxlZCB3ZWVrIG9mIDQgTWFyY2gKMTkgRmViIFJvdW5kIHRyaXAgcmVxdWVzdGVkIHdlZWsgb2YgMjYgRmViIGZvciBidWlsZGluZyBSZWZ1cmJpc2hlcwo1IEZlYiBSb3VuZCB0cmlwIHJlcXVlc3RlZCB3ZWVrIG9mIDI2IEZlYiBmb3IgYnVpbGRpbmcgUmVmdXJiaXNobWVudHMKMjkgSmFuIC1Qcmlvcml0eSB3aXRoIHJlZ2lvbiBhcyBwZXIgZGlzY3Vzc2lvbiB3aXRoIEVCKEZHKSAyNiBKYW4gLSBTaXRlIHZpc2l0IHRvIGJlIGFycmFuZ2VkCjIyIEphbiAtIFNjb3BlIHRvIGJlIGNvbmZpcm1lZCBhbmQgaW5jbHVkZWQgaW4gYnVpbGRpbmcgcm91bmQgdHJpcCAtIFBsYW5uaW5nIDE1IE1heSB0byAzMCBKdW5l","RATING":""} |  |  |  | PHASE12 | 2024-05-15 | 2024-06-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000914 | Absa Willowmore - Minor Works | Absa Willowmore - Minor Works |  |  | Region 2 | Eastern Cape | 77596X | 1000-71031-01 | Absa Willowmore-Knysna St-Willowmore | N | 2024-07-31 | 2024-12-31 |  | ASP-EC0386 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_342 4 March - On Hold as per priority meeting TBC | {"MANDT":"111","REFERENCE":90000914,"ONEVIEW":"77596X","DATE01":"2024-02-22","DATE02":"2024-02-29","DATE03":"2024-03-21","DATE04":"2024-03-28","DATE05":"2024-04-18","DATE06":"2024-06-17","DATE07":"2024-07-17","DATE08":"2024-08-07","DATE09":"2024-09-21","DATE10":"2024-09-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:60:30:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-17","FORECAST_END":"2024-07-17","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIE9uIEhvbGQgYXMgcGVyIHByaW9yaXR5IG1lZXRpbmcgVEJDCjQgTWFyY2ggLSBDUkVTIGluZGljYXRlIGRlZmVyIC0gIEVCIHRvIGNvbmZpcm0gbWVldGluZyAtIDQgTWFyY2gKMjggRmViIE5vdCBwcmlvcml0eSAsIEVCIHRvIGNvbmZpcm0gbWVldGluZyAtIDQgTWFyY2gKMjkgSmFuIC0gTm90IHByaW9yaXR5IHdpdGggcmVnaW9uIHBvc3NpYmxlIDIwMjUgYXMgcGVyIGRpc2N1c3Npb24gd2l0aCBFQihGRykgMjYgSmFuCjIyIEphbiAtIFBNIHRvIGZpbmFsaXNlIHNjb3BlIHdpdGggcGxhbm5lciAtIFBsYW5uZWQgRXhlY3V0aW9uIDEgSnVuZSB0byAzMCBBdWc=","RATING":""} |  |  |  | PHASE12 | 2024-06-17 | 2024-07-17 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000915 | Absa Broadway Uitenhage - Internal Painting + Tileing | Absa Broadway Uitenhage - Internal Painting + Tileing |  |  | Region 2 | Eastern Cape | 36206X | 1000-70986-01 | Broadway Building-Cnr Chase & Caledon St-Uitenhage | N | 2024-08-30 | 2024-12-31 |  | ASP-EC0387 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_345 4 March - On Hold as per priority meeting TBC | {"MANDT":"111","REFERENCE":90000915,"ONEVIEW":"36206X","DATE01":"2024-04-01","DATE02":"2024-04-08","DATE03":"2024-04-29","DATE04":"2024-05-06","DATE05":"2024-05-27","DATE06":"2024-08-01","DATE07":"2024-08-15","DATE08":"2024-09-05","DATE09":"2024-10-20","DATE10":"2024-10-31","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:66:14:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-08-01","FORECAST_END":"2024-08-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIE9uIEhvbGQgYXMgcGVyIHByaW9yaXR5IG1lZXRpbmcgVEJDIAoyNiBGZWIgUHJpb3JpdHkgdG8gYmUgY29uZmlybWVkIGJ5IEVCIDQgTWFyY2gKMTkgRmViIFBNIHRvIGZvbGxvdyB1cCByZSBPdXRjb21lIG9mIEVCIHBsYW5uaW5nIG1lZXRpbmcKNSBGZWIgUE0gdG8gZm9sbG93IHVwIHJlIHByaW9yaXR5IAoyOSBKYW4gLSBQTSB0byBjaGVjayBvbiBwcmlvcml0eSB3aXRoIEVCKEZHKQoyMiBKYW4gU2l0ZSB0byBiZSB2aXNpdGVkIHRvIGRlZmluZSBzY29wZSAgLSBFeGVjdXRpb24gUGxhbm5pbmcgMSBBdWcgLSAxNSBBdWc=","RATING":""} |  |  |  | PHASE12 | 2024-08-01 | 2024-08-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000916 | Absa Garden Route Knysna - Minor works | Absa Garden Route Knysna - Minor works |  |  | Region 2 | Eastern Cape | 77262X | 1000-70816-01 | Garden Route Centre Knysna-Cnr Gray & Main St-Knysna | N | 2024-04-01 | 2024-06-30 |  | ASP-EC0388 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_348 4 March - On Hold as per priority meeting - | {"MANDT":"111","REFERENCE":90000916,"ONEVIEW":"77262X","DATE01":"2024-01-22","DATE02":"2024-01-29","DATE03":"2024-02-19","DATE04":"2024-02-26","DATE05":"2024-03-18","DATE06":"2024-04-01","DATE07":"2024-04-30","DATE08":"2024-05-21","DATE09":"2024-07-05","DATE10":"2024-07-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"252:7:21:7:21:14:29:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-01","FORECAST_END":"2024-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIE9uIEhvbGQgYXMgcGVyIHByaW9yaXR5IG1lZXRpbmcgLQoyOCBGZWIgSW5pdGlhbCBPbiBIb2xkICwgRUIgdG8gY29uZmlybSBtZWV0aW5nIC0gNCBNYXJjaAoxOSBGZWIgT04gSG9sZCBQTSB0byBmb2xsb3cgdXAgcmUgT3V0Y29tZSBvZiBFQiBwbGFubmluZyBtZWV0aW5nCjI5IEphbiAtIE9OIEhvbGQgd2l0aCByZWdpb24gcG9zc2libGUgSU9QIGFzIHBlciBkaXNjdXNzaW9uIHdpdGggRUIoRkcpIDI2IEphbgoyMiBKYW4gUE0gdG8gY2hlY2sgd2l0aCBwbGFubmVyIHJlIHNjb3BlIGFuZCBkcmF3aW5ncyAtIEV4ZWN1dGlvbiBwbGFubmluZyAxIEFwciB0byAzMCBBcHI=","RATING":""} |  |  |  | PHASE12 | 2024-04-01 | 2024-04-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000917 | Absa Libode - Internal Painting | Absa Libode - Internal Painting |  |  | Region 2 | Eastern Cape | 36281X | 1000-70990-01 | Libode Shopping Centre-Main Rd-Libode | N | 2024-07-20 | 2024-08-05 |  | ASP-EC0389 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 15 |  |  | 0 | Absa Ref : Opex 4 March On Hold as per priority Meeting TBC | {"MANDT":"111","REFERENCE":90000917,"ONEVIEW":"36281X","DATE01":"2024-05-11","DATE02":"2024-05-18","DATE03":"2024-06-08","DATE04":"2024-06-15","DATE05":"2024-07-06","DATE06":"2024-07-20","DATE07":"2024-08-05","DATE08":"2024-08-26","DATE09":"2024-10-10","DATE10":"2024-10-31","DATE11":"2024-10-10","DATE12":"2024-10-10","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-20","FORECAST_END":"2024-08-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgRmViIFByaW9yaXR5IHRvIGJlIGNvbmZpcm1lZCBieSBFQiAyOCBGZWIKMTkgRmViIFBNIHRvIGZvbGxvdyB1cCByZSBPdXRjb21lIG9mIEVCIHBsYW5uaW5nIG1lZXRpbmcKNSBGZWIgUE0gdG8gZm9sbG93IHVwIHJlIHByaW9yaXR5IAoyOSBKYW4gLSBQTSB0byBjaGVjayBvbiBwcmlvcml0eSB3aXRoIEVCKEZHKQoyMiBKYW4gLSBQTSB0byBjb25maXJtIHdpdGggcGxhbm5lciAtIEV4ZWN1dGlvbiBQbGFubmluZyAyMCBKdWwgdG8gNSBBdWc=","RATING":""} |  |  |  | PHASE00 | 2024-07-20 | 2024-08-05 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000918 | Absa Linton Arcade - Contravision Shopfront | Absa Linton Arcade - Contravision Shopfront |  |  | Region 2 | Eastern Cape | 76436X | 1000-71457-01 | Linton Arcade-Cape Rd-Port Elizabeth | N | 2024-02-15 | 2024-03-31 |  | ASP-EC0390 | REL BUDG AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 36319.3 |  | 100 | 2024-03-28 | 2024-04-04 | 36319.3 | Absa Ref : 240129_346 | {"MANDT":"111","REFERENCE":90000918,"ONEVIEW":"76436X","DATE01":"2024-01-01","DATE02":"2024-02-09","DATE03":"2024-03-01","DATE04":"2024-03-08","DATE05":"2024-03-15","DATE06":"2024-03-16","DATE07":"2024-04-01","DATE08":"2024-04-15","DATE09":"2024-05-30","DATE10":"2024-05-31","DATE11":"2024-05-30","DATE12":"2024-05-30","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"181:39:21:7:7:1:16:14:45:45:45:24","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-16","FORECAST_END":"2024-04-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggLSBOZXcgRGVzaWducyBwZW5kaW5nIGZyb20gQWJzYSBEZXNpZ24KIChUaGlzIGlzIEJBVSDigJMgUmVwdXRhdGlvbmFsIGFuZCBjYW5ub3QgYmUgY29tcHJvbWlzZWQpCjExIE1hcmNoIC0gRmVlZGJhY2sgcGVuZGluZyBmcm9tIERlc2lnbiBUZWFtIHJlIE5ldyBMaWZlc3R5bGUgR3JhcGhpY3Mgd2hpY2ggY291bGQgaW1wYWN0IENvc3QgLSBFc3QgUjQwSwo0IE1hcmNoIC0gQ29udGludWUgYXMgcGVyIHByaW9yaXR5IC0gUDMgU3VibWl0dGluZyBpbiBDQiAwOCBzdWJqZWN0IHRvIFJNIGFwcHJvdmFsIC0gUiAzOSA5NTEuMjMgCjQgTWFyY2ggT04gaG9sZCBmcm9tIEVCIGR1ZSB0byBjb3N0IGFwcHJvdmFsIFBlbmRpbmcKMjYgRmViIHRvIGJlIHN1Ym1pdHRlZCBmb3IgQ0IwNwoxOSBGZWIgQXJ0d29yayBBcHByb3ZlZCBjb3N0IHRvIGJlIHN1Ym1pdHRlZCB0byBFQiBmb3IgQXBwcm92YWwKMTIgRmViIE1haWwgZnJvbSBBYnNhIHNhbWUgQXJ0d29ya3MgYXMgcGVyIFJvZ2dlYmFhaSBicmFuY2ggCjUgRmViIEFydHdvcmsgcmVxdWVzdGVkIGZvciBMaW50b24gaW4gb3JkZXIgdG8gcmVxdWVzdCBRdW90ZXMKMjIgSmFuIC0gUE0gdG8gcmVxdWVzdCBxdW90ZXMgZm9yIHJlcGxhY2VtZW50IC0gUGxhbm5lZCAxNSBGZWIgdG8gMjkgRmViCgo=","RATING":""} |  |  | C000152988 | PHASE06 | 2024-04-05 | 2024-04-21 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-04-08 | 31582 | 0 |  |  | C000152988 | 31582 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000919 | Absa Riversdale - Kitchen Upgrade | Absa Riversdale - Kitchen Upgrade |  |  | Region 2 | Eastern Cape | 37159X | 1000-70797-01 | Absa Riversdale-Cnr Church & Dixon St-Riversdale | N | 2024-07-01 | 2024-12-31 |  | ASP-EC0391 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_545 4 March - Remove as per meeting - IOP revamp required to address other shortcomings | {"MANDT":"111","REFERENCE":90000919,"ONEVIEW":"37159X","DATE01":"2024-04-22","DATE02":"2024-04-29","DATE03":"2024-05-20","DATE04":"2024-05-27","DATE05":"2024-06-17","DATE06":"2024-07-01","DATE07":"2024-08-06","DATE08":"2024-08-27","DATE09":"2024-10-11","DATE10":"2024-10-31","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"343:7:21:7:21:14:36:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-01","FORECAST_END":"2024-08-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIFJlbW92ZSBhcyBwZXIgbWVldGluZyAtIElPUCByZXZhbXAgcmVxdWlyZWQgdG8gYWRkcmVzcyBvdGhlciBzaG9ydGNvbWluZ3MgCjI4IEZlYiBQcmlvcml0eSB0byBiZSBjb25maXJtZWQgYnkgRUIgNCBNYXJjaCAtIFBvc3NpYmxlIFBNTwoxOSBGZWIgUE0gdG8gZm9sbG93IHVwIHJlIE91dGNvbWUgb2YgRUIgcGxhbm5pbmcgbWVldGluZwo1IEZlYiAtIFBNIHRvIGZvbGxvdyB1cCByZSBwcmlvcml0eQoyOSBKYW4gLSBQTSB0byBjaGVjayBvbiBwcmlvcml0eSB3aXRoIEVCKEZHKQoyMiBKYW4gLSBQTSB0byBvYnRhaW4gdXBkYXRlZCBxdW90ZSAtICAtIEV4ZWN1dGlvbiBQbGFubmluZyAxIEp1bCB0byA2IEF1Zw==","RATING":""} |  |  |  | PHASE12 | 2024-07-01 | 2024-08-06 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000920 | Absa Aliwal North - Tube System | Absa Aliwal North - Replace Tube System |  |  | Region 2 | Eastern Cape | 79209X | 1000-71069-01 | Absa Aliwal North-Somerset St-Aliwal North | N | 2024-03-01 | 2024-06-30 |  | ASP-EC0392 | REL BUDG AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 304987.93 |  | 100 | 2024-03-13 | 2024-03-20 | 304987.93 | Absa Ref : 240402_008 Retail Reprioritised | {"MANDT":"111","REFERENCE":90000920,"ONEVIEW":"79209X","DATE01":"2024-01-28","DATE02":"2024-02-12","DATE03":"2024-03-13","DATE04":"2024-03-20","DATE05":"2024-03-20","DATE06":"2024-04-26","DATE07":"2024-04-29","DATE08":"2024-05-20","DATE09":"2024-07-04","DATE10":"2024-07-31","DATE11":"2024-07-04","DATE12":"2024-07-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"277:15:30:7:0:37:3:21:45:45:45:15","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-26","FORECAST_END":"2024-04-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggU2lnbmVkIENCIERlY2sgUmVjZWl2ZWQgQWJzYSBQTyBSZXF1ZXN0ZWQKMTkgTWFyY2ggQ0IgRGVjayBhcHByb3ZlZCBzaWduZWQgZGVjayBwZW5kaW5nIHRvIHJlcXVlc3QgUE8ncwoxNSBNYXJjaCBTdWJtaXR0ZWQgZm9yIENCMDkgLSBSIDMwNCA5ODcuOTMKMTMgTWFyY2ggU3VibWl0dGluZyBmb3IgQ0IwOQoxMSBNYXJjaCAtIFRvIGJlIHN1Ym1pdHRlZCB0byBFQiBmb3IgYXBwcm92YWwgdG8gYmUgc3VibWl0dGVkIGZvciBDQjkKNCBNYXJjaCAtIENvbnRpbnVlIFAxICBQcm9qZWN0CjQgTWFyY2ggUXVvdGUgcmVjZWl2ZWQgZm9yIFR1YmUgU3lzdGVtLCBSZW1lZGlhbCBXb3JrcyBCQyBpbiBQcm9ncmVzcwoyNiBGRUIgUE0gdG8gZm9sbG93IHVwIHdpdGggR1BUIHJlIHF1b3RlcyBvdXRzdGFuZGluZyAtIFF1b3RlcyBkdWUgd2VlayBvZiAyNiBGRUIKMTkgRmViIFNpdGUgbWVldGluZyBoZWxkIDEyIEZlYiwgUXVvdGUgZHVlIDIxIEZFQiwgR1BUICsgTWFrZSBHb29kIFdvcmtzCjcgRmViIE9uIHNpdGUgbWVldGluZyByZXF1ZXN0ZWQgZm9yIE1vbmRheSAxMnRoIEZlYiB3aXRoIEdQVCBmb3Igc2NvcGUgc3BlY2lmaWNhdGlvbnMgdG8gYmUgZmluYWxpc2VkCjUgRmViIC0gUE0gdG8gZW5nYWdlIEdQVCByZSB0dWJlIHN5c3RlbQoyOCBKYW4gLSBBcHByb3ZlZCBQUkYgcmVjZWl2ZWQKMjIgSmFuIC0gUXVvdGUgdG8gYmUgcmVxdWVzdGVkIHRvIHJlcGxhY2UgZXhpc3RpbmcgdHViZSBzeXN0ZW0KMTUgSmFuIFBSRiByZWNlaXZlZCB0byBiZSBzZW50IGZvciBhcHByb3ZhbCBieSBGTQ==","RATING":""} |  |  | C000151286 | PHASE06 | 2024-04-19 | 2024-04-22 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-03-27 | 265206.9 | 0 |  |  | C000151286 | 265206.89 |  | 13205.99 |  | 0 | 0 |  | 0 |  | 0
90000921 | Absa Somerset West - Shade Cloth Parking | Absa Somerset West - Shade Cloth Parking |  |  | Region 2 | Western Cape | 77702X | 1000-70850-01 | 116 Main Road Somerset West-Main Rd-Somerset West | N | 2024-07-01 | 2024-08-31 |  | ASP-WC0343 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_350 4 March - On hold project to be submitted to IC in March | {"MANDT":"111","REFERENCE":90000921,"ONEVIEW":"77702X","DATE01":"2024-04-22","DATE02":"2024-04-29","DATE03":"2024-05-20","DATE04":"2024-05-27","DATE05":"2024-06-17","DATE06":"2024-07-01","DATE07":"2024-07-20","DATE08":"2024-08-10","DATE09":"2024-09-24","DATE10":"2024-09-30","DATE11":"2024-11-05","DATE12":"2024-11-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"222:7:21:7:21:14:19:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-01","FORECAST_END":"2024-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTMgTWFyY2ggQ29uZmlybWVkIG5vdCBwcmlvcml0eSAtIENhbmNlbGxlZCBQcm9qZWN0IHRvIElDIGluIE1hcmNoCjQgTWFyY2ggLSBPbiBob2xkIHByb2plY3QgdG8gYmUgc3VibWl0dGVkIHRvIElDIGluIE1hcmNoCjUgRmViIE1haWwgZnJvbSBwbGFubmVyKEpCKSB0byBwdXQgb24gSG9sZCBhbmQgcGxhbm5lZCByZXZhbXAgcmVkdWNlCjUgRmViIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEJyb2xsIHJlIHJlc3BvbnNpYmlsaXR5CjIyIEphbiAtIHRvIGNvbmZpcm0gd2l0aCBCcm9sbCByZSBMYW5kbG9yZCAtIFBsYW5uaW5nIGZyb20gMSBKdWx5IHRvIDIwIEp1bHkK","RATING":""} |  |  |  | PHASE12 | 2024-07-01 | 2024-07-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000922 | Absa Gansbaai - Floor Tiles | Absa Gansbaai - Floor Tiles |  |  | Region 2 | Western Cape | 77700X | 1000-70849-01 | 49 Main Road Gansbaai-Main Rd-Gansbaai | N | 2024-04-01 | 2024-06-30 |  | ASP-WC0344 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | ALP-WC0034 Created - As Large Project | {"MANDT":"111","REFERENCE":90000922,"ONEVIEW":"77700X","DATE01":"2024-01-22","DATE02":"2024-01-29","DATE03":"2024-02-19","DATE04":"2024-02-26","DATE05":"2024-03-18","DATE06":"2024-05-01","DATE07":"2024-05-15","DATE08":"2024-06-05","DATE09":"2024-07-20","DATE10":"2024-07-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"252:7:21:7:21:44:14:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-01","FORECAST_END":"2024-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBGZWIgTWFpbCBzZW50IHRvIFByb2N1cmVtZW50IHJlIFZlbmRvciBTZWxlY3Rpb24gQXMgc2NvcGUgY2hhbmdlZCB0byBiZSBMYXJnZSBQcm9qZWN0Ky1SMS4ybSAtIFdhcyBjb25maXJtZWQgYXMgcGFydCBvZiBZZWxsb3cgTEVEIFJvbGwgT1VUIC0gVGhlIGxpZ2h0cyBhdWRpdCBhdCB0aGlzIHNpdGUgaXMgc2NoZWR1bGVkIGZvciA3dGggRmViIGFuZCBpbnN0YWxsYXRpb25zIGFyZSBwbGFubmVkIGZvciBtaWQtTWFyY2gKMjkgSmFuIC0gV2FpdCBmb3IgaW5wdXQgZnJvbSBFQiByZSA1IFllYXIgUGxhbiAtIHdlZWsgNSBGZWIKMjIgSmFuIC0gUE0gdG8gY29uZmlybSBzY29wZSB3aXRoIHBsYW5uZXIgYXMgdG8gYmUgQlRCLiBQbGFubmluZyAxIE1heSAxNSBNYXk=","RATING":""} |  |  |  | PHASE12 | 2024-05-01 | 2024-05-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000923 | Absa Caledon - Minor Works | Absa Caledon - Minor Works |  |  | Region 2 | Western Cape | 77399X | 1000-70830-01 | Absa Caledon-Donkin Square-Caledon | N | 2024-04-15 | 2024-05-31 |  | ASP-WC0345 | REL AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_338 Was Small Project ASP-WC0345 converted to Large Project - ALP-WC0035 | {"MANDT":"111","REFERENCE":90000923,"ONEVIEW":"77399X","DATE01":"2024-02-05","DATE02":"2024-03-04","DATE03":"2024-03-13","DATE04":"2024-03-20","DATE05":"2024-04-10","DATE06":"2024-05-15","DATE07":"2024-07-15","DATE08":"2024-08-14","DATE09":"2024-09-28","DATE10":"2024-09-30","DATE11":"2024-09-28","DATE12":"2024-09-28","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"208:28:9:7:21:35:61:30:45:45:45:2","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-07-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggLSBCQyB0byBiZSBjb21wbGV0ZWQgYW5kIHNoYXJlZCB3aXRoIEVCIGFzIEdyZWF0ZXIgdGhhblI1MDBrIGZvciBhcHByb3ZhbCAtICstIFI4MDBrCjExIE1hcmNoIFJGUSBpbiBwcm9ncmVzcywgRnVybml0dXJlIHRvIGNvbmZpcm0gcmUgZnVybml0dXJlIHJlcXVlc3RlZAo0IE1hcmNoIFNpdGUgVmlzaXQgY29uZHVjdGVkIDQgTWFyY2ggUXVvdGVzIGR1ZSA4IE1hcmNoCjI2IEZlYiAtIFBNIHRvIHZpc2l0IHNpdGUgMSBNYXJjaCBhbmQgaW5jbHVkZSBxdW90ZXMgZm9yIFNvZnQgU2VhdGluZwoxOSBGZWIgLSBTaXRlIHZpc2l0IGNvbmR1Y3RlZCAxNCBGZWIsIFNjb3BlIGZpbmFsaXNlZCAtIENlaWxpbmcgVGlsZXMsIFNvZnQgU2VhdGluZywgUGFpbnR3b3JrLCBUaWxpbmcgYXJvdW5kIFNob3Bmcm9udCAoRk0gdGVhbSwgUGxhbm5lciwgU2VjdXJpdHkpCjEyIEZlYiBDb250aW51aW5nIHNpdGUgdmlzaXQgcGxhbm5lZCBmb3IgMTQgRmViCjI5IEphbiAtIFdhaXQgZm9yIGlucHV0IGZyb20gRUIgcmUgNSBZZWFyIFBsYW4gLSB3ZWVrIDUgRmViCjIyIEphbiAtIFNpdGUgdmlzaXQgcGVuZGluZyB0byBmaW5hbGlzZSBzY29wZSB3aXRoIHBsYW5uZXIgLSBQbGFubmluZyAxNSBBcHJpbCAtIDE1IE1heQ==","RATING":""} |  |  |  | PHASE12 | 2024-05-15 | 2024-07-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000924 | Absa Malmesbury - Carpets 1st Floor | Absa Malmesbury - Carpets 1st Floor |  |  | Region 2 | Western Cape | 78113X | 1000-70887-01 | Absa Malmesbury-Voortrekker Rd-Malmesbury | N | 2024-05-01 | 2024-06-30 |  | ASP-WC0346 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_540 4 March - Planner to provide written confirmation of cancelation | {"MANDT":"111","REFERENCE":90000924,"ONEVIEW":"78113X","DATE01":"2024-02-21","DATE02":"2024-02-28","DATE03":"2024-03-20","DATE04":"2024-03-27","DATE05":"2024-04-17","DATE06":"2024-05-20","DATE07":"2024-06-20","DATE08":"2024-07-11","DATE09":"2024-08-25","DATE10":"2024-08-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"222:7:21:7:21:33:31:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-20","FORECAST_END":"2024-06-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjYgRmViIENhcnBldHMgaW4gR29vZCBjb25kaXRpb24gUGxhbm5lciB0byBjb25maXJtIGlmIHByb2NlZWQKMTkgRmViIC0gU2l0ZSB2aXNpdCAxOSBGZWIgLSBDb25maXJtZWQgQ2FycGV0cyBpbiBHb29kIGNvbmRpdGlvbiwgcG9zc2libGUgcmVtb3ZhbAoxMiBGZWIgLSB0byBjb250aW51ZSBTaXRlIFZpc2l0IHRvIGJlIHNjaGVkdWxlZAo1IEZlYiBQTSB0byBmb2xsb3cgdXAgd2l0aCBGTSByZSBQT0UKMjkgSmFuIFBPRSByZXF1ZXN0ZWQgZnJvbSBGTSB0byBldmFsdWF0ZQoyMiBKYW4gLSBQTSB0byBmb2xsb3cgdXAgcmUgc2NvcGUgd2l0aCBQbGFubmVyIC0gUGxhbm5pbmcgMjAgTWF5IC0gMjAgSnVuZQ==","RATING":""} |  |  |  | PHASE12 | 2024-05-20 | 2024-06-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000925 | Absa Vredendal - Bumper Rails | Absa Vredendal - Bumper Rails |  |  | Region 2 | Western Cape | 78130X | 1000-70889-01 | Vredendal-Voortrekker St-Vredendal | N | 2024-02-15 | 2024-03-31 |  | ASP-WC0347 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_347 | {"MANDT":"111","REFERENCE":90000925,"ONEVIEW":"78130X","DATE01":"2023-12-07","DATE02":"2023-12-14","DATE03":"2024-01-04","DATE04":"2024-01-11","DATE05":"2024-02-01","DATE06":"2024-04-01","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-05","DATE12":"2024-06-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:7:21:7:21:60:19:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-01","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NSBGZWIgLSBUTyB2aXNpdCBzaXRlIHNhbWUgdGltZSBhcyBMdXR6dmlsbGUgRGlsYXBzCjI5IEphbiBUbyBjb250aW51ZSBhcyBwZXIgUGxhbm5lcgoyMiBKYW4gLSBQbGFubmVyIHRvIGNvbmZpcm0gcmVxdWlyZW1lbnQuIFBsYW5uZWQgRXhlY3V0aW9uIC0gMSBBcHIgLSAyMCBBcHI=","RATING":""} |  |  |  | PHASE00 | 2024-04-01 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000926 | Absa Belhar - Minor Works | Absa Belhar - Minor Works |  |  | Region 2 | Western Cape | 78324X | 1000-70896-01 | Airport Shopping Centre-Cnr Belhar & Stellenbosch Arterial Dr-Belhar | N | 2024-05-15 | 2024-06-30 |  | ASP-WC0348 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_339 4 March Planner to confirm cancel in writing as planned relocation / reduce | {"MANDT":"111","REFERENCE":90000926,"ONEVIEW":"78324X","DATE01":"2024-03-06","DATE02":"2024-03-13","DATE03":"2024-04-03","DATE04":"2024-04-10","DATE05":"2024-05-01","DATE06":"2024-05-15","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFRvIEJlIHJlbW92ZWQgYXMgUGVyIFBsYW5uZXIKMTggSmFuIC0gRUIgaW5kaWNhdGVkIHBvc3NpYmxlIENsb3N1cmUgUE0gdG8gY29uZmlybSB3aXRoIFBsYW5uZXIgcmUgY2FuY2VsIG9yIGNvbnRpbnVlIC0gUGxhbm5pbmcgZXhlY3V0aW9uIGZyb20gMTUgTWF5IHRvIDE1IEp1bmU=","RATING":""} |  |  |  | PHASE12 | 2024-05-15 | 2024-06-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000927 | Absa Gansbaai - HVAC Upgrade | Absa Gansbaai - HVAC Upgrade |  |  | Region 2 | Western Cape | 77700X | 1000-70849-01 | 49 Main Road Gansbaai-Main Rd-Gansbaai | N | 2024-04-01 | 2024-06-30 |  | ASP-WC0349 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 497655.37 |  | 40 | 2024-03-22 |  | 0 | Absa Ref : 240129_290 | {"MANDT":"111","REFERENCE":90000927,"ONEVIEW":"77700X","DATE01":"2024-01-22","DATE02":"2024-01-29","DATE03":"2024-02-19","DATE04":"2024-02-26","DATE05":"2024-03-18","DATE06":"2024-05-15","DATE07":"2024-05-31","DATE08":"2024-06-21","DATE09":"2024-08-05","DATE10":"2024-08-31","DATE11":"2024-08-05","DATE12":"2024-08-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"191:7:21:7:21:58:16:21:45:91:91:11","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggLSBTdWJtaXR0ZWQgZm9yIENCMDgKNCBNYXJjaCAtIFVwZGF0ZWQgcXVvdGVzIHJlcXVlc3RlZCB0byBpbnN0YWxsIGFsbCAzIFVuaXRzIGFzIEVPTAoyOSBGZWIgRGVjaXNpb24gYXQgcHJlIENCIHRvIGRvIGFsbCAzIFVuaXRzIGFuZCB0YWJsZSBhZ2FpbnN0IEVPTCBCdWRnZXQKMjkgRmViIEJDIHRvIGJlIHByZXNlbnRlZCBmb3IgQ0IwNywgQnVkZ2V0IFNob3J0ZmFsbAoyNiBGZWIgLSBGaW5hbCBzY29wZSBhbmQgc3BlY2lmaWNhdGlvbnMgdG8gYmUgY29uZmlybWVkIEVuZyB0byBjb25maXJtIHJlIGJ1ZGdldAoyMiBGZWIgRmluYWwgU2NvcGUgYW5kIFNwZWNpZmljYXRpb25zIFBlbmRpbmcKMTkgRmViIEZpbmFsIFNjb3BlIGFuZCBTcGVjaWZpY2F0aW9ucyBwZW5kaW5nCjE1IEZlYiBFbmcgYnVzeSB3aXRoIHRoZSBzY29wZSBhbmQgd2lsbCBzZW5kIHRvIFBNIG9uIDE1IEZlYgowOCBGZWIgUE0gdG8gZm9sbG93IHVwIHdpdGggRW5nIGZvciBzcGVjaWZpY2F0aW9uL3Njb3BlCjAxIEZlYiAtIFNwZWNpZmljYXRpb25zIHBlbmRpbmcgZnJvbSBFbmdpbmVlcmluZwoyMiBKYW4gLSBQTSB0byBlbmdhZ2UgRW5nIHJlIFVuaXQgdG8gYmUgcmVwbGFjZWQgLSBQbGFubmVkIEV4ZWN1dGlvbiAxIE1heSB0byAxNSBNYXk=","RATING":""} |  |  |  | PHASE05 | 2024-05-10 | 2024-05-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000928 | Absa Prins Albert - Minor Works | Absa Prins Albert - Minor Works |  |  | Region 2 | Eastern Cape | 77111X | 1000-71024-01 | Absa Prins Albert-Church St-Prins Albert | N | 2024-07-01 | 2024-12-31 |  | ALP-EC0020 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_542 4 March - Remove as per meeting - IOP POC project pending | {"MANDT":"111","REFERENCE":90000928,"ONEVIEW":"77111X","DATE01":"2024-04-22","DATE02":"2024-04-29","DATE03":"2024-05-20","DATE04":"2024-05-27","DATE05":"2024-06-17","DATE06":"2024-07-01","DATE07":"2024-08-30","DATE08":"2024-09-20","DATE09":"2024-11-04","DATE10":"2024-11-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"343:7:21:7:21:14:60:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-01","FORECAST_END":"2024-08-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIFJlbW92ZSBhcyBwZXIgbWVldGluZyAtIElPUCBQT0MgcHJvamVjdCBwZW5kaW5nCjQgTWFyY2ggT24gSG9sZCBhcyBQcm9vZiBvZiBDb25jZXB0IHBsYW5uZWQgYnkgRUIKMjggRmViIC0gUG90ZW50aWFsIElPUCBwcm9qZWN0IHBsYW5uZWQgdG8gYmUgY29uZmlybWVkIDQgTWFyY2gKMTkgRmViIFBNIHRvIGZvbGxvdyB1cCByZSBPdXRjb21lIG9mIEVCIHBsYW5uaW5nIG1lZXRpbmcKNSBGZWIgUE0gdG8gZm9sbG93IHVwIHJlIHByaW9yaXR5IAoyOSBKYW4gLSBQTSB0byBjaGVjayBvbiBwcmlvcml0eSB3aXRoIEVCKEZHKQoyMiBKYW4gaGF2ZSBhcHByb3ZlZCBkcmF3aW5ncyBhbmQgc2NvcGUgb2YgdGhlIHdvcmtzLCBQbSB0byBjaGVjayByZSBjb3VuY2lsIGFwcHJvdmFsIC0gUGxhbm5lZCBFeGVjdXRpb24gMSBKdWx5IHRvIDMwIEF1Z3VzdA==","RATING":""} |  |  |  | PHASE12 | 2024-07-01 | 2024-08-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000929 | Absa Uniondale - Minor Works | Absa Uniondale - Minor Works |  |  | Region 2 | Eastern Cape | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale | N | 2024-04-01 | 2024-12-31 |  | ALP-EC0021 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_543 4 March - On Hold as per priority meeting TBC | {"MANDT":"111","REFERENCE":90000929,"ONEVIEW":"78140X","DATE01":"2024-01-22","DATE02":"2024-01-29","DATE03":"2024-02-19","DATE04":"2024-02-26","DATE05":"2024-03-18","DATE06":"2024-06-01","DATE07":"2024-08-30","DATE08":"2024-09-20","DATE09":"2024-11-04","DATE10":"2024-11-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"434:7:21:7:21:75:90:21:45:24","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-08-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIE9uIEhvbGQgYXMgcGVyIHByaW9yaXR5IG1lZXRpbmcgVEJDCjQgTWFyY2ggLSBDUkVTIGluZGljYXRlIGRlZmVyIC0gIEVCIHRvIGNvbmZpcm0gbWVldGluZyAtIDQgTWFyY2gKMjggRmViIE5vdCBwcmlvcml0eSAsIEVCIHRvIGNvbmZpcm0gbWVldGluZyAtIDQgTWFyY2gKMjkgSmFuIC0gTm90IHByaW9yaXR5IHdpdGggcmVnaW9uIHBvc3NpYmxlIDIwMjUgYXMgcGVyIGRpc2N1c3Npb24gd2l0aCBFQihGRykgMjYgSmFuCjIyIEphbiAtIFBNIHRvIGZpbmFsaXNlIHNjb3BlIHdpdGggcGxhbm5lciAtIFBsYW5uZWQgRXhlY3V0aW9uIDEgSnVuZSB0byAzMCBBdWc=","RATING":""} |  |  |  | PHASE12 | 2024-06-01 | 2024-08-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000930 | Absa Baywest Mall - Minor Works | Absa Baywest Mall - Minor Works |  |  | Region 2 | Eastern Cape | 36106X | 1000-70985-01 | Baywest Mall-Baywest Blvd-Port Elizabeth | N | 2024-06-15 | 2024-09-30 |  | ALP-EC0022 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_544 4 March - Defer as per priority meeting to be done 2025 | {"MANDT":"111","REFERENCE":90000930,"ONEVIEW":"36106X","DATE01":"2024-04-06","DATE02":"2024-04-13","DATE03":"2024-05-04","DATE04":"2024-05-11","DATE05":"2024-06-01","DATE06":"2024-06-15","DATE07":"2024-07-30","DATE08":"2024-08-20","DATE09":"2024-10-04","DATE10":"2024-10-31","DATE11":"2024-12-05","DATE12":"2024-12-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"269:7:21:7:21:14:45:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-15","FORECAST_END":"2024-07-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjggRmViIE5vdCBwcmlvcml0eSBwb3NzaWJsZSAyMDI1ICwgRUIgdG8gY29uZmlybSBtZWV0aW5nIC0gNCBNYXJjaAoyOSBKYW4gLSBOb3QgcHJpb3JpdHkgd2l0aCByZWdpb24gcG9zc2libGUgMjAyNSBhcyBwZXIgZGlzY3Vzc2lvbiB3aXRoIEVCKEZHKSAyNiBKYW4KMjIgSmFuIFBNIHRvIGNvbmZpcm0gaWYgdG8gcHJvY2VlZCB3aXRoIGFueSBXb3JrcyAtIFBsYW5lZCBFeGVjdXRpb24gMTUgSnVuZSB0byAzMCBKdWx5","RATING":""} |  |  |  | PHASE12 | 2024-06-15 | 2024-07-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000931 | Absa Kuyansa Mdantsane - Ceiling Tiles | Absa Kuyansa Mdantsane - Ceiling Tiles |  |  | Region 2 | Eastern Cape | 79176X | 1000-71065-01 | Kuyasa Shopping Centre-Sandile Rd-Mdantsane | N | 2024-04-15 | 2024-06-30 |  | ALP-EC0023 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_349 12 March Removed from Priority list - Possible Cancel / Defer due to IOP project approval in April | {"MANDT":"111","REFERENCE":90000931,"ONEVIEW":"79176X","DATE01":"2024-02-05","DATE02":"2024-02-12","DATE03":"2024-03-04","DATE04":"2024-03-11","DATE05":"2024-04-01","DATE06":"2024-07-15","DATE07":"2024-08-15","DATE08":"2024-09-05","DATE09":"2024-10-20","DATE10":"2024-10-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"238:7:21:7:21:105:31:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-15","FORECAST_END":"2024-08-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NCBNYXJjaCAtIE9uIEhvbGQgcGVuZGluZyBJQyBBcHByb3ZhbCBpbiBBcHJpbAo0IE1hcmNoIFJldmFtcCBTYW1lIFNpemUgZ29pbmcgdG8gSUMgaW4gQXByaWwgLSBFQiB0byBjb25maXJtCjI4IEZlYiBFQiB0byBjb25maXJtIGlmIHByb2NlZWQgNCBNYXJjaCBhcyBwb3NzaWJsZSByZWxvY2F0aW9uIHBlbmRpbmcKMTkgRmViIHBvc3NpYmxlIHJlbG9jYXRpb24gUE0gdG8gZm9sbG93IHVwIHdpdGggUGxhbm5lcgo1IEZlYiBTaXRlIHZpc2l0IHRvIGJlIHNjaGVkdWxlZCB0byBkZXRlcm1pbmUgZnVsbCBzY29wZQoyOSBKYW4gLVByaW9yaXR5IHdpdGggcmVnaW9uIGFzIHBlciBkaXNjdXNzaW9uIHdpdGggRUIoRkcpIDI2IEphbiAtIFNpdGUgdmlzaXQgdG8gYmUgYXJyYW5nZWQKMjIgSmFuIFBNIHRvIGNvbmZpcm0gZnVsbCBzY29wZSB3aXRoIFBsYW5uZXIgUGxhbm5lZCAxNSBKdWx5IHRvIDE1IEF1Zw==","RATING":""} |  |  |  | PHASE12 | 2024-07-15 | 2024-08-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000932 | Absa Albertinia - Waterproofing | Absa Albertinia - Waterproofing |  |  | Region 2 | Eastern Cape | 77688X | 1000-71033-01 | Absa Albertinia-Hoof St-Albertinia | N | 2024-07-01 | 2024-08-31 |  | ALP-EC0024 | CRTD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 6 March - Project changed to Small Project - was - ALP-EC0024 - Now - ASP-EC0416 | {"MANDT":"111","REFERENCE":90000932,"ONEVIEW":"77688X","DATE01":"2024-04-22","DATE02":"2024-02-22","DATE03":"2024-03-14","DATE04":"2024-03-21","DATE05":"2024-04-11","DATE06":"2024-07-01","DATE07":"2024-08-30","DATE08":"2024-09-20","DATE09":"2024-11-04","DATE10":"2024-11-30","DATE11":"2024-11-04","DATE12":"2024-11-04","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"222:-60:21:7:21:81:60:21:45:46:46:26","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-01","FORECAST_END":"2024-08-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBNYXJjaCAtIFByb2plY3QgY2hhbmdlZCB0byBTbWFsbCBQcm9qZWN0IC0gd2FzIC0gQUxQLUVDMDAyNCAtICBOb3cgLSBBU1AtRUMwNDE2CjQgTWFyY2ggUXVvdGVzIHJlY2VpdmVkIGFkanVkaWNhdGlvbiBpbiBwcm9ncmVzcwoyNiBGZWIgLSBTaXRlIHZpc2l0IGNvbmR1Y3RlZCAyMiBGZWIgUXVvdGVzIGR1ZSAxIE1hcmNoCjIyIEZlYiAtIFNpdGUgTWVldGluZyBiZWluZyBjb25kdWN0ZWQgMjIgRmViIFNjb3BlIGFuZCBSRlEgdG8gZm9sbG93CjE5IEZlYiAtIFNpdGUgdmlzaXQgd2l0aCBFbmdpbmVlcmluZyAyMiBGZWIKOSBGZWIgLSBNYWlsIHNlbnQgdG8gZm9sbG93IHVwIFdpdGggUHJvY3VyZW1lbnQKMDggRmViIFNpdGUgdmlzaXQgc2NoZWR1bGVkIGZvciAyMiBGZWIKNyBGZWIgTWFpbCB0byBwcm9jdXJlbWVudCByZSBWZW5kb3IgU2VsZWN0aW9uIHNlbnQKNSBGZWIgUm91bmQgdHJpcCBwbGFubmVkIDIybmQgMjMgRmViCjI1IEphbiAtIFBNIHRvIGFycmFuZ2Ugcm91bmQgdHJpcCB0byBpbnNwZWN0IGFuZCBkZXRlcm1pbmUgc2NvcGUgYW5kIHNwZWNpZmljYXRpb25zCjIyIEphbiAtIFBtIHRvIGVuZ2FnZSByZSB3YXRlcnByb29maW5nIFNwZWMgYW5kIFZlbmRvcnMgUGxhbm5lZCAxIEp1bHkgdG8gMzAgQXVn","RATING":""} |  |  |  | PHASE12 | 2024-07-01 | 2024-08-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000933 | Absa Alexandria - Minor Works | Absa Alexandria - Minor Works |  |  | Region 2 | Eastern Cape | 76600X | 1000-71015-01 | Absa Alexandria-Cnr Voortrekker & Krog St-Alexandria | N | 2024-08-01 | 2024-09-30 |  | ALP-EC0025 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_541 Small project Created was ALP-EC0025(240129_541) now ASP-EC0419 | {"MANDT":"111","REFERENCE":90000933,"ONEVIEW":"76600X","DATE01":"2024-05-23","DATE02":"2024-04-05","DATE03":"2024-04-19","DATE04":"2024-04-26","DATE05":"2024-05-17","DATE06":"2024-08-01","DATE07":"2024-09-15","DATE08":"2024-10-06","DATE09":"2024-11-20","DATE10":"2024-11-30","DATE11":"2024-11-20","DATE12":"2024-11-20","PROG01":0,"PROG02":80,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"191:-48:14:7:21:76:45:21:45:60:60:10","PROGRESS":6,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-08-01","FORECAST_END":"2024-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggU2l0ZSBWaXNpdCBjb25kdWN0ZWQgUkZRIGluIFByb2dyZXNzCjE1IE1hcmNoIFNpdGUgVmlzaXQgMTggTWFyY2ggLSBFc3QgUjMwMGsKMTEgTWFyY2ggU2l0ZSB2aXNpdCB0byBiZSBjb25kdWN0ZWQgd2VlayBvZiAxMXRoIHdpdGggYWxsIHBhcnRpZXMKNCBNYXJjaCAtIENvbnRpbnVlIFAxIC0gUmV2aXNlZCBTY29wZSBEcmF3aW5nIFJlY2VpdmVkIC0gRXh0ZXJuYWwgQVRNIERvb3IgT25seSwgSW50ZXJuYWwgU2lnbmFnZSBhbmQgQmxhbmsgb2ZmIHRlbGxlcnMgYXMgcGVyIEVCCjQgTWFyY2ggLSBEb29yIHRvIGNvbnRpbnVlIGFwcHJvdmVkIHBsYW4gcGVuZGluZwoyNiBGZWIgLSBEcmF3aW5ncyBzZW50IGJhY2sgdG8gZGVzaWduIHRvIGluY29ycG9yYXRlIEFGUyBjaGFuZ2VzCjE1IEZlYiBEcmF3aW5nIHJlY2VpdmVkLSBzaXRlIHZpc2l0IHRvIGJlIGNvbmR1Y3RlZAo4IEZlYiBBcHByb3ZlZCBQUkYgcmVjZWl2ZWQgZm9yIHJldmlzZWQgcHJpb3JpdGlzZWQgU2NvcGUsIERyYXdpbmdzIGhhdmUgYmVlbiBSZXF1ZXN0ZWQgZnJvbSBQbGFubmVyCjUgRmViIC0gRmxvb3IgUGxhbnMgcGVuZGluZyBmcm9tIFBsYW5uZXJzCjI5IEphbiAtUHJpb3JpdHkgdG8gaW5zdGFsbCBFeHRlcm5hbCBBVE0gZG9vciwgbm8gaW50ZXJuYWwgd29yayBhcyBwZXIgZGlzY3Vzc2lvbiB3aXRoIEVCKEZHKSAyNiBKYW4gLSBTaXRlIHZpc2l0IHRvIGJlIGFycmFuZ2VkCjIyIEphbiAtIFBNIHRvIGNvbmZpcm0gd2l0aCBwbGFubmVyIHJlIFNjb3Bl","RATING":""} |  |  |  | PHASE12 | 2024-08-01 | 2024-09-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000934 | Absa Graaff-Reinet - Exterior Refurb | Absa Graaff-Reinet - Exterior Refurb |  |  | Region 2 | Eastern Cape | 76442X | 1000-71458-01 | Absa Graaff-Reinet-Church St-Graaff-Reinet | N | 2024-05-15 | 2024-07-31 |  | ALP-EC0026 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000934,"ONEVIEW":"76442X","DATE01":"2024-03-06","DATE02":"2024-03-13","DATE03":"2024-04-03","DATE04":"2024-04-10","DATE05":"2024-05-01","DATE06":"2024-05-15","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"2024-10-05","DATE12":"2024-10-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"239:7:21:7:21:14:46:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFJvdW5kIHRyaXAgcmVxdWVzdGVkIHdlZWsgb2YgMjYgRmViIGZvciBidWlsZGluZyBSZWZ1cmJpc2hlcwo1IEZlYiBSb3VuZCB0cmlwIHJlcXVlc3RlZCB3ZWVrIG9mIDI2IEZlYiBmb3IgYnVpbGRpbmcgUmVmdXJiaXNoZXMKMjIgSmFuIFJvdW5kIHRyaXAgdG8gYmUgY29uZmlybWVkIHdpdGggVmVuZG9ycyB0byBxdW90ZSAgLSBTaXRlIHZpc2l0cyB0byBiZSBjb25kdWN0ZWQgLSBQbGFubmluZyB0byBFeGVjdXRlIDE1IE1heSB0byAzMCBKdW5l","RATING":""} |  |  |  | PHASE00 | 2024-05-31 | 2024-07-16 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000935 | Absa Patensie - Exterior Refurb | Absa Patensie - Exterior Refurb |  |  | Region 2 | Eastern Cape | 77876X | 1000-71036-01 | Absa Patensie-Paul Ferreira St-Patensie | N | 2024-04-01 | 2024-06-30 |  | ALP-EC0027 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000935,"ONEVIEW":"77876X","DATE01":"2024-01-22","DATE02":"2024-01-29","DATE03":"2024-02-19","DATE04":"2024-02-26","DATE05":"2024-03-18","DATE06":"2024-04-20","DATE07":"2024-05-20","DATE08":"2024-06-10","DATE09":"2024-07-25","DATE10":"2024-07-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"191:7:21:7:21:33:30:21:45:11","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-20","FORECAST_END":"2024-05-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFJvdW5kIHRyaXAgcmVxdWVzdGVkIHdlZWsgb2YgMjYgRmViIGZvciBidWlsZGluZyBSZWZ1cmJpc2hlcwo1IEZlYiBSb3VuZCB0cmlwIHJlcXVlc3RlZCB3ZWVrIG9mIDI2IEZlYiBmb3IgYnVpbGRpbmcgUmVmdXJiaXNoZXMKMjIgSmFuIFJvdW5kIHRyaXAgdG8gYmUgY29uZmlybWVkIHdpdGggVmVuZG9ycyB0byBxdW90ZSAgLSBTaXRlIHZpc2l0cyB0byBiZSBjb25kdWN0ZWQgLSBQbGFubmluZyB0byBFeGVjdXRlIDE1IEFwciB0byAxNSBNYXk=","RATING":""} |  |  |  | PHASE00 | 2024-08-03 | 2024-09-02 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000936 | Absa Somerset East - Paint Window Frames | Absa Somerset East - Paint Window Frames |  |  | Region 2 | Eastern Cape | 76426X | 1000-71008-01 | Absa Somerset East-Njoli St-Somerset East | N | 2024-04-15 | 2024-06-30 |  | ALP-EC0028 | CRTD AVAC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000936,"ONEVIEW":"76426X","DATE01":"2024-02-05","DATE02":"2024-02-12","DATE03":"2024-03-04","DATE04":"2024-03-11","DATE05":"2024-04-01","DATE06":"2024-04-15","DATE07":"2024-05-15","DATE08":"2024-06-05","DATE09":"2024-07-20","DATE10":"2024-07-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"238:7:21:7:21:14:30:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-15","FORECAST_END":"2024-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFJvdW5kIHRyaXAgcmVxdWVzdGVkIHdlZWsgb2YgMjYgRmViIGZvciBidWlsZGluZyBSZWZ1cmJpc2hlcwo1IEZlYiBSb3VuZCB0cmlwIHJlcXVlc3RlZCB3ZWVrIG9mIDI2IEZlYiBmb3IgYnVpbGRpbmcgUmVmdXJiaXNoZXMKMjIgSmFuIFJvdW5kIHRyaXAgdG8gYmUgY29uZmlybWVkIHdpdGggVmVuZG9ycyB0byBxdW90ZSAgLSBTaXRlIHZpc2l0cyB0byBiZSBjb25kdWN0ZWQgLSBQbGFubmluZyB0byBFeGVjdXRlIDE1IEFwciB0byAxNSBNYXk=","RATING":""} |  |  |  | PHASE00 | 2024-07-01 | 2024-07-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000937 | Absa Bonnievale - Exterior Refurb | Absa Bonnievale - Exterior Refurb |  |  | Region 2 | Western Cape | 77671X | 1000-70842-01 | Absa Bonnievale-Main Rd-Bonnievale | N | 2024-01-01 | 2024-09-30 |  | ALP-WC0029 | REL AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 20 March New Project Number ASP-WC0369 Was ALP-WC0029 - Submitting CB10 | {"MANDT":"111","REFERENCE":90000937,"ONEVIEW":"77671X","DATE01":"2024-01-15","DATE02":"2024-02-20","DATE03":"2024-03-20","DATE04":"2024-03-27","DATE05":"2024-04-17","DATE06":"2024-08-15","DATE07":"2025-09-15","DATE08":"2025-10-06","DATE09":"2025-11-20","DATE10":"2025-11-30","DATE11":"2025-11-20","DATE12":"2025-11-20","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:36:29:7:21:120:396:21:45:-305:-305:10","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-08-15","FORECAST_END":"2025-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggdG8gYmUgc3VibWl0dGVkIHRvIENCMDkKNCBNYXJjaCAtIFJGUSBpbiBQcm9ncmVzcyBjbG9zaW5nIDggTWFyY2gKMjYgRmViIC0gU2NvcGUgdG8gYmUgY29uZmlybWVkIHdpdGggQ3JlcyBwcmlvciB0byBSRlEKMjkgSmFuIFNpdGUgTWVldGluZyAyMCBGRUIKMjIgSmFuIC0gU2l0ZSB2aXNpdHMgdG8gYmUgY29uZHVjdGVkIC0gUGxhbm5pbmcgdG8gRXhlY3V0ZSAxNSBBdWcgdG8gMTUgU2VwdA==","RATING":""} |  |  |  | PHASE12 | 2024-08-15 | 2025-09-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000938 | Absa Citrusdal - Exterior Refurb | Absa Citrusdal - Exterior Refurb |  |  | Region 2 | Western Cape | 78131X | 1000-71446-01 | Absa Citrusdal-Voortrekker St-Citrusdal | N | 2024-05-15 | 2024-08-31 |  | ALP-WC0030 | CRTD AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 20 March New Project Number ASP-WC0370 Was ALP-WC0030 - Submitting CB10 | {"MANDT":"111","REFERENCE":90000938,"ONEVIEW":"78131X","DATE01":"2024-02-01","DATE02":"2024-02-19","DATE03":"2024-03-20","DATE04":"2024-03-27","DATE05":"2024-04-17","DATE06":"2024-05-15","DATE07":"2024-06-15","DATE08":"2024-07-06","DATE09":"2024-08-20","DATE10":"2024-08-31","DATE11":"2024-08-20","DATE12":"2024-08-20","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:18:30:7:21:28:31:21:45:122:122:11","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-06-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggdG8gYmUgc3VibWl0dGVkIHRvIENCMDkKNCBNYXJjaCAtIFJGUSBpbiBQcm9ncmVzcyBjbG9zaW5nIDggTWFyY2gKMjYgRmViIC0gU2NvcGUgdG8gYmUgY29uZmlybWVkIHdpdGggQ3JlcyBwcmlvciB0byBSRlEKMTkgRmViIFNpdGUgdmlzaXRzIGluIHByb2dyZXNzIDE5IEZlYgoyOSBKYW4gU2l0ZSBtZWV0aW5nIHNldCBmb3IgMTkgRkVCCjIyIEphbiAtIFNpdGUgdmlzaXRzIHRvIGJlIGNvbmR1Y3RlZCAtIFBsYW5uaW5nIHRvIEV4ZWN1dGUgMTUgTWF5IHRvIDE1IEp1bmU=","RATING":""} |  |  |  | PHASE12 | 2024-05-15 | 2024-06-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000939 | Absa Malmesbury - Exterior Refurb | Absa Malmesbury - Exterior Refurb |  |  | Region 2 | Western Cape | 78113X | 1000-70887-01 | Absa Malmesbury-Voortrekker Rd-Malmesbury | N | 2024-04-01 | 2024-08-31 |  | ALP-WC0031 | CRTD AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 20 March New Project Number ASP-WC0368 Was ALP-WC0031 - Submitting CB10 | {"MANDT":"111","REFERENCE":90000939,"ONEVIEW":"78113X","DATE01":"2024-01-22","DATE02":"2024-03-12","DATE03":"2024-03-27","DATE04":"2024-04-03","DATE05":"2024-04-24","DATE06":"2024-08-15","DATE07":"2025-09-15","DATE08":"2025-10-06","DATE09":"2025-11-20","DATE10":"2025-11-30","DATE11":"2025-11-20","DATE12":"2025-11-20","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"678:50:15:7:21:113:396:21:45:-335:-335:10","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-08-15","FORECAST_END":"2025-09-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggLSBSRlEgY2xvc2luZyAxMiBNYXJjaAo0IE1hcmNoIC0gUkZRIGluIFByb2dyZXNzIGNsb3NpbmcgMTIgTWFyY2gKMjYgRmViIC0gU2NvcGUgdG8gYmUgY29uZmlybWVkIHdpdGggQ3JlcyBwcmlvciB0byBSRlEKMTkgRmViIFZpc2l0IGNvbmR1Y3RlZCAxOSBGZWIKMjkgSmFuIFNpdGUgTWVldGluZyAyMCBGRUIKMjIgSmFuIC0gU2l0ZSB2aXNpdHMgdG8gYmUgY29uZHVjdGVkIC0gUGxhbm5pbmcgdG8gRXhlY3V0ZSAxNSBBdWcgdG8gMTUgU2VwdA==","RATING":""} |  |  |  | PHASE03 | 2024-08-15 | 2025-09-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000940 | Absa Piketberg - Exterior Refurb | Absa Piketberg - Exterior Refurb |  |  | Region 2 | Western Cape | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg | N | 2024-06-15 | 2024-08-31 |  | ALP-WC0032 | CRTD AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-19 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 20 March New Project Number ASP-WC0371 Was ALP-WC0032 - Submitting to CB10 | {"MANDT":"111","REFERENCE":90000940,"ONEVIEW":"78132X","DATE01":"2024-04-06","DATE02":"2024-02-26","DATE03":"2024-03-21","DATE04":"2024-03-28","DATE05":"2024-04-18","DATE06":"2024-09-15","DATE07":"2024-10-15","DATE08":"2024-11-05","DATE09":"2024-12-20","DATE10":"2024-12-31","DATE11":"2024-12-20","DATE12":"2024-12-20","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"269:-40:24:7:21:150:30:21:45:0:0:11","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-09-15","FORECAST_END":"2024-10-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggdG8gYmUgc3VibWl0dGVkIHRvIENCMDkKNCBNYXJjaCAtIFJGUSBpbiBQcm9ncmVzcyBjbG9zaW5nIDggTWFyY2gKMjYgRmViIC0gU2NvcGUgdG8gYmUgY29uZmlybWVkIHdpdGggQ3JlcyBwcmlvciB0byBSRlEKMTkgRmViIC0gT24gc2l0ZSBjb25kdWN0aW5nIEREIDE5IEZlYgoyOSBKYW4gU2l0ZSBNZWV0aW5nIDE5IEZFQgoyMiBKYW4gLSBTaXRlIHZpc2l0cyB0byBiZSBjb25kdWN0ZWQgLSBwbGFubmluZyB0byBleGVjdXRlIDE1IFNlcHQgdG8gMTUgT2N0","RATING":""} |  |  |  | PHASE03 | 2024-09-15 | 2024-10-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000941 | Various Sites (EC) - Drip Trays | Various Sites (EC) - Drip tray for HVAC in server room with water pump |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Various EC Branches | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0393 | REL BUDG AVAC SETC: |  | false | true |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 80878.09 |  | 100 | 2024-02-08 | 2024-02-15 | 80878.09 | Absa Ref - 240129_364, 240129_365, 240129_362, 240129_367, 240129_363, 240129_366, 240129_417 79209X Absa Aliwal North: 1of @ R13 493.96 Incl. VAT ( Absa CIP Ref: 240129_363) 78540X Absa Cofimvaba: 1of @ R13 494.34 Incl. VAT ( Absa CIP Ref: 240129_364) 20949X Absa Ntabankulu: 1of @ R13 494.34 Incl. VAT ( Absa CIP Ref: 240129_365) 36267X Absa Bisho: 2of @ R19 437.14 Incl. VAT ( Absa CIP Ref: 240129_362) 70631X Absa Lusikisiki: 1of @ R13 494.34 Incl. VAT ( Absa CIP Ref: 240129_367) 76387X Absa Newton Park: 1of @ R7 463.96 Incl. VAT ( Absa CIP Ref: 240129_366) 8 Feb Cip Combined to ASP-EC0393 ex Aliwal North CIP and renamed Various | {"MANDT":"111","REFERENCE":90000941,"ONEVIEW":"22937X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-08","DATE04":"2024-02-08","DATE05":"2024-02-15","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:7:27:0:7:29:36:21:45:45:45:5","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIEFic2EgUE8gUmVjZWl2ZWQgLSBDMDAwMTQzMjI2IC0gQlYgUG8ncyByZXF1ZXN0ZWQKMTUgRmViIEFwcHJvdmVkIGF0IENCIEFic2EgUE8gUGVuZGluZwowOCBGZWIgQ29zdCBib2FyZCBmb3IgSW50ZXJuYWwgUmV2aWV3CuKAoiA3OTIwOVggQWJzYSBBbGl3YWwgTm9ydGg6IDFvZiBAIFIxMyA0OTMuOTYgSW5jbC4gVkFUICggQWJzYSBDSVAgUmVmOiAyNDAxMjlfMzYzKQrigKIgNzg1NDBYIEFic2EgQ29maW12YWJhOiAxb2YgQCBSMTMgNDk0LjM0IEluY2wuIFZBVCAgICAoIEFic2EgQ0lQIFJlZjogMjQwMTI5XzM2NCkK4oCiIDIwOTQ5WCBBYnNhIE50YWJhbmt1bHU6IDFvZiBAIFIxMyA0OTQuMzQgSW5jbC4gVkFUICAoIEFic2EgQ0lQIFJlZjogMjQwMTI5XzM2NSkK4oCiIDM2MjY3WCBBYnNhIEJoaXNobzogMm9mIEAgUjE5IDQzNy4xNCBJbmNsLiBWQVQgICAgICAgICAgICAgICggQWJzYSBDSVAgUmVmOiAyNDAxMjlfMzYyKQrigKIgNzA2MzFYIEFic2EgTHVzaWtpc2lraTogMW9mIEAgUjEzIDQ5NC4zNCAgSW5jbC4gVkFUICAgICAgICggQWJzYSBDSVAgUmVmOiAyNDAxMjlfMzY3KQrigKIgNzYzODdYIEFic2EgTmV3dG9uIFBhcms6IDFvZiBAIFI3IDQ2My45NiBJbmNsLiBWQVQgICggQWJzYSBDSVAgUmVmOiAyNDAxMjlfMzY2KQo4IEZlYiBDaXAgQ29tYmluZWQgdG8gQVNQLUVDMDM5MyBleCBBbGl3YWwgTm9ydGggQ0lQIGFuZCByZW5hbWVkIFZhcmlvdXMKNSBGZWIgUXVvdGVzIGZvciBFbGVjdHJpY2FsIHBlbmRpbmcgdG8gYmUgc3VibWl0dGVkIGZvciBpbnRlcm5hbCByZXYgNyBGZWIKMSBGZWIgLSBCQyB0byBiZSBpbiBDQiB3ZWVrIG9mIHRoZSA1dGggRmViCjI5IEphbiBRdW90ZXMgcmVjZWl2ZWQgVG8gYmUgc2hhcmVkIGZvciBpbnQgcmV2IFRodXJzZGF5CjI1IEphbiAtIE9uZSBRdW90ZSBSZWNlaXZlZCBmb3IgUm91bmQgVHJpcCBhZGRpdGlvbmFsIFF1b3RlIHJlcXVlc3RlZCBkdWUgMjYgSmFuLiB0byBiZSBzdWJtaXR0ZWQgaW50ZXJuYWxseSAzMSBKYW4KMjIgSmFuIC0gUE0gdG8gcmVxdWVzdCBxdW90ZXMgcm91bmQgVHJpcCAtIFBsYW5uaW5nIGV4ZWN1dGlvbiBmcm9tIDE1IE1hciB0byAyMCBBcHJpbA==","RATING":""} |  |  | C000143226 | PHASE08 | 2024-03-05 | 2024-03-11 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-02-19 | 70328.77 | 0 |  |  | C000143226 | 70328.77 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000942 | Absa Beaufort West - DB Upgrade | Absa Beaufort West - DB Board Upgrade |  |  | Region 2 | Eastern Cape | 77401X | 1000-71026-01 | Absa Beaufort West-Donkin St-Beaufort West | N | 2024-06-15 | 2024-06-30 |  | ASP-EC0394 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 136646.61 |  | 100 | 2024-03-14 | 2024-03-20 | 136646.61 | Absa Ref: 240129_309 | {"MANDT":"111","REFERENCE":90000942,"ONEVIEW":"77401X","DATE01":"2024-02-01","DATE02":"2024-02-08","DATE03":"2024-03-12","DATE04":"2024-03-19","DATE05":"2024-03-20","DATE06":"2024-04-12","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:33:7:1:23:8:21:45:45:45:1","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-12","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggU2lnbmVkIENCIERlY2sgUmVjZWl2ZWQgQWJzYSBQTyBSZXF1ZXN0ZWQKMjAgTWFyY2ggQXBwcm92ZWQgYXQgc2lnbmVkIGRlY2sgcGVuZGluZyBpbiBvcmRlciB0byByZXF1ZXN0IEFic2EgUE8KMTQgTWFyY2ggLSBTdWJtaXR0ZWQgZm9yIENCMDkKMTEgTWFyY2ggLSBSRlEgY29tcGxldGVkIEJDIGNvbXBpbGF0aW9uIGluIHByb2dyZXNzCjQgTWFyY2ggUXVvdGVzIHNlbnQgdG8gRVNNIGZvciBWZXJpZmljYXRpb24vQWRqdWRpY2F0aW9uCjI5IEZlYiBRdW90ZXMgcmVjZWl2ZWQgdG8gYmUgdmVyaWZpZWQgd2l0aCBUU00gdG8gY29tcGxldGUgQkMKMjYgRmViIC0gMiBRdW90ZXMgcmVjZWl2ZWQgLSAzIFF1b3RlIFBlbmRpbmcgLSBDQjA3CjIyIEZlYiAtIFNpdGUgVmlzaXQgY29uZHVjdGVkIDE1IEZlYiBTY29wZSB0byBjb25maXJtZWQKMTkgRmViIFNjb3BpbmcgRG9jIHJlY2VpdmVkIFF1b3RlcyBkdWUgV2VkIDIxIEZlYgoxNSBGZWIgU2l0ZSB2aXNpdCBjb25kdWN0ZWQuIFNjb3BlIHRvIGJlIGZpbmFsaXNlZCBmb3IgY29zdGluZy4gRW5nIHRvIHByb3ZpZGUgc2NvcGluZyBkb2N1bWVudCBhbmQgUUNQCjA4IEZlYiBPbnNpdGUgbWVldGluZyBzY2hlZHVsZWQgZm9yIDA5IEZlYiBmb3IgdGhlIHNjb3BlL3NwZWNpZmljYXRpb25zCjEgRmViIC0gU3BlY2lmaWNhdGlvbnMgUGVuZGluZyBpbiBvcmRlciB0byBjb21wbGV0ZSBjb3N0aW5nLCBTaXRlIFZpc2l0IEZyaWRheSA5IEZlYgoyMiBKYW4gUE0gdG8gRW5nYWdlIEVuZ2luZWVyaW5nIGZvciBTY29wZSwgbm90ZSBkcmF3aW5ncyB3aWxsIGJlIHJlcXVpcmVkLiBQbGFubmVkIDE1IEp1bmUgdG8gMzAgSnVuZQ==","RATING":""} |  |  | C000151210 | PHASE06 | 2024-04-20 | 2024-05-15 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-03-27 | 118823.14 | 0 |  |  | C000151210 | 118823.13 |  | 11829.24 |  | 0 | 0 |  | 0 |  | 0
90000943 | Absa Cofimvaba - HVAC Drip Tray | Absa Cofimvaba - HVAC Drip Tray |  |  | Region 2 | Eastern Cape | 78540X | 1000-71049-01 | Cofimvaba-Cnr Market & Main St-Cofimvaba | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0395 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000943,"ONEVIEW":"78540X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | DELETED | 2024-03-15 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000944 | Absa Ntabankulu - HVAC Drip Tray | Absa Ntabankulu - HVAC Drip Tray |  |  | Region 2 | Eastern Cape | 20949X | 1000-70921-01 | Ntabankulu-Main St-Ntabankulu | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0396 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000944,"ONEVIEW":"20949X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | DELETED | 2024-03-15 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000945 | Absa Bhisho Seta Bldg - HVAC Drip Trays X2 | Absa Bhisho Seta Bldg - HVAC Drip Trays X2 |  |  | Region 2 | Eastern Cape | 36267X | 1000-70989-01 | Bhisho Seta Building-Phalo Ave-Bisho | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0397 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000945,"ONEVIEW":"36267X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | DELETED | 2024-03-15 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000946 | Absa Newton Park - HVAC Drip Tray | Absa Newton Park - HVAC Drip Tray |  |  | Region 2 | Eastern Cape | 76387X | 1000-71004-01 | Newton Park-Cape Rd-Port Elizabeth | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0398 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | 8 Feb Cip of R15000 moved to ASP-EC0393 Aliwal North And Renamed to Various | {"MANDT":"111","REFERENCE":90000946,"ONEVIEW":"76387X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkgSmFuIFF1b3RlcyByZWNlaXZlZCBUbyBiZSBzaGFyZWQgZm9yIGludCByZXYgVGh1cnNkYXkKMjUgSmFuIC0gT25lIFF1b3RlIFJlY2VpdmVkIGZvciBSb3VuZCBUcmlwIGFkZGl0aW9uYWwgUXVvdGUgcmVxdWVzdGVkIGR1ZSAyNiBKYW4uIHRvIGJlIHN1Ym1pdHRlZCBpbnRlcm5hbGx5IDMxIEphbgoyMiBKYW4gLSBQTSB0byByZXF1ZXN0IHF1b3RlcyByb3VuZCBUcmlwIC0gUGxhbm5pbmcgZXhlY3V0aW9uIGZyb20gMTUgTWFyIHRvIDIwIEFwcmls","RATING":""} |  |  |  | PHASE12 | 2024-03-15 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000947 | Absa Rhino Lusikisiki - HVAC Drip Tray | Absa Rhino Lusikisiki - HVAC Drip Tray |  |  | Region 2 | Eastern Cape | 70631X | 1000-71001-01 | Rhino Centre Lusikisiki-Main Rd-Lusikisiki | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0399 | CRTD DLFL AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90000947,"ONEVIEW":"70631X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | DELETED | 2024-03-15 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000948 | Absa Settlers Greenfields - HVAC Drip Tray | Absa Settlers Greenfields - HVAC Drip Tray |  |  | Region 2 | Eastern Cape | 79189X | 1000-71468-01 | Settlers Square Greenfields-Cnr Settlers Way & Cloverley Rd-East London | N | 2024-03-15 | 2024-04-20 |  | ASP-EC0400 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | 8 Feb Cip of R15000 moved to ASP-EC0393 Aliwal North And Renamed to Various | {"MANDT":"111","REFERENCE":90000948,"ONEVIEW":"79189X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-04-20","DATE08":"2024-05-11","DATE09":"2024-06-25","DATE10":"2024-06-30","DATE11":"2024-06-25","DATE12":"2024-06-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-04-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgSmFuIC0gQ2FuY2VsbGVkIGFzIHBlciBNYWlsIGZyb20gVFNNICgyNyBOb3YgLSBNYWlsIEZyb20gVFNNIC0gTm8gbG9uZ2VyIHJlcXVpcmVkKQ==","RATING":""} |  |  |  | PHASE12 | 2024-03-15 | 2024-04-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000949 | Absa Willowmore - Windows to be replaced (glass) | Absa Willowmore - Windows to be replaced (glass) |  |  | Region 2 | Eastern Cape | 77596X | 1000-71031-01 | Absa Willowmore-Knysna St-Willowmore | N | 2024-04-15 | 2024-05-31 |  | ASP-EC0401 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 70722.66 | Note in CB 9 April request deemed to be Opex by Absa Finance. | 40 | 2024-04-04 |  | 0 | Absa Ref : 240129_324 Note in CB 9 April request deemed to be Opex by Absa Finance. | {"MANDT":"111","REFERENCE":90000949,"ONEVIEW":"77596X","DATE01":"2024-02-05","DATE02":"2024-03-22","DATE03":"2024-04-04","DATE04":"2024-04-11","DATE05":"2024-04-11","DATE06":"2024-05-11","DATE07":"2024-06-06","DATE08":"2024-06-27","DATE09":"2024-08-11","DATE10":"2024-08-31","DATE11":"2024-08-11","DATE12":"2024-08-11","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"208:46:13:7:0:30:26:21:45:45:45:9","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-11","FORECAST_END":"2024-06-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBcHJpbCAtIFN1Ym1pdHRlZCBmb3IgQ0IxMgoyMiBNYXJjaCAtIEJDIENvbXBpbGF0aW9uIC0gQ0IxMgoxNSBNYXJjaCBTaXRlIHZpc2l0IHdpdGggc3VwcGxpZXJzIGNvbmR1Y3RlZCAxNSBNYXJjaCBSRlEgaW4gUHJvZ3Jlc3MKMTEgTWFyY2ggU3BlY3MgdG8gY29uZmlybWVkIHJlIFdpbmRvd3MgdG8gYmUgcmVwbGFjZWQgUE0gdG8gZW5nYWdlIEVORwpEYXRlcyAxNSBNYXkgMTAgSnVuZQo0IE1hcmNoIC0gU2l0ZSB2aXNpdCB0byBiZSBjb25kdWN0ZWQgYnkgVmVuZG9ycwoyNiBGZWIgLSBQTSB0byByZXF1ZXN0IEFsdGVybmF0ZSB2ZW5kb3JzIGZvciBRdW90ZXMKMTkgRmViIC0gRm9sbG93IHVwIHdpdGggUHJvY3VyZW1lbnQgcmUgVmVuZG9ycwo3IEZlYiBNYWlsIHNlbnQgdG8gcHJvY3VyZW1lbnQgcmUgR2xhc3MgVmVuZG9ycyB0byBzZXJ2aWNlIHRoZSByZXF1ZXN0CjUgRmViIC0gUE0gdG8gYXJyYW5nZSB3aXRoIHByb2N1cmVtZW50IHJlIEdsYXNzIHN1cHBsaWVyCjIyIEphbiAtIFBNIHRvIHNvdXJjZSBHbGFzcyBzdXBwbGllciAtIEV4ZWN1dGlvbiBQbGFubmluZyAxNSBBcHIgdG8gMTAgTWF5","RATING":""} |  |  |  | PHASE05 | 2024-05-11 | 2024-06-06 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000950 | Absa Moffett Office Park - Sluice Room | Absa Moffett Office Park - Sluice Room |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2024-03-15 | 2024-05-31 |  | ASP-EC0402 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 35380.94 |  | 40 | 2024-04-04 |  | 0 | Absa Ref : 240129_535 | {"MANDT":"111","REFERENCE":90000950,"ONEVIEW":"22937X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-04-15","DATE07":"2024-05-15","DATE08":"2024-06-05","DATE09":"2024-07-20","DATE10":"2024-07-31","DATE11":"2024-08-05","DATE12":"2024-08-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":10,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"239:7:21:7:21:45:30:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-15","FORECAST_END":"2024-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggLSBSRlEgaW4gcHJvZ3Jlc3MgdG8gYmUgZmluYWxpc2VkIHdlZWsgb2YgdGhlIDExIE1hcmNoIC0gcmUgQTQgRnJhbWVzIGZyb20gc3RvY2sgaW4gVm9vcnRyZWtrZXIKNCBNYXJjaCBTY29wZSBjbGFyaXR5IG1lZXRpbmcgaGVsZCB3aXRoIFZQIHJlIGNsYXJpZnkgb2YgdGhlIHJlcXVpcmVtZW50LCBhZGRpdGlvbmFsIGl0ZW1zIHRvIGJlIGFkZHJlc3NlZAoyNiBGZWIgLSBUbyBiZSBzdWJtaXR0ZWQgdG8gQ0IwNyAtIDEgUXVvdGUgcmVjZWl2ZWQgLSAyIFF1b3RlcyBwZW5kaW5nCjE5IEZlYiAtIERyYXdpbmcgcmVjZWl2ZWQgLCBSRlEgZHVlIDIwIEZlYgo2IEZlYiBGb2xsb3cgdXAgc2VudCByZSBEcmF3aW5ncwo1IEZlYiAtIERyYXdpbmdzIHJlcXVlc3RlZCBmb3IgaGlnaCBkZXNrcyBhbmQgc2x1aWNlIHJvb20KMiBGZWIgRHJhd2luZ3MgcmVxdWVzdGVkCjI5IEphbiAtIFBNIHRvIHJlcXVlc3QgZHJhd2luZ3MgdG8gYmUgdXBkYXRlZCByZSBTbHVpY2Ugcm9vbSBhbmQgSGlnaCBEZXNrCjIyIEphbiAtIFBNIHRvIGVuZ2FnZSBGTSBhbmQgdXBkYXRlZCBkcmF3aW5ncyB0byBiZSByZXF1ZXN0ZWQgLSBQbGFubmVkIDE1IEFwciB0byAxNSBNYXk=","RATING":""} |  |  |  | PHASE05 | 2024-05-26 | 2024-06-25 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000951 | Absa Broadway Uitenhage - HVAC Cages | Absa Broadway Uitenhage - HVAC Cages |  |  | Region 2 | Eastern Cape | 36206X | 1000-70986-01 | Broadway Building-Cnr Chase & Caledon St-Uitenhage | N | 2024-04-01 | 2024-06-30 |  | ASP-EC0403 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_507 | {"MANDT":"111","REFERENCE":90000951,"ONEVIEW":"36206X","DATE01":"2024-01-22","DATE02":"2024-01-29","DATE03":"2024-02-19","DATE04":"2024-02-26","DATE05":"2024-03-18","DATE06":"2024-04-01","DATE07":"2024-04-30","DATE08":"2024-05-21","DATE09":"2024-07-05","DATE10":"2024-07-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"252:7:21:7:21:14:29:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-01","FORECAST_END":"2024-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgRmViIFNpdGUgdmlzaXQgdG8gYmUgc2NoZWR1bGVkIG9uIHRoZSB3ZWVrIG9mIHRoZSAxOXRoCiAwOCBGZWIgU2l0ZSB2aXNpdCB0byBiZSBzY2hlZHVsZWQgb24gdGhlIHdlZWsgb2YgdGhlIDEydGggLCBQTSB0byBjb25maXJtIGRhdGUgd2l0aCBFU00KNSBGZWIgLSBQTSB0byB2aXNpdCBzaXRlIHdpdGggVmVuZG9yL3MgdG8gbWVhc3VyZSBhbmQgb2J0YWluIHF1b3RlcwoxIEZlYiAtIFBNIHRvIHZpc2l0IHNpdGUgd2l0aCBWZW5kb3IgdG8gb2J0YWluIHF1b3RlcwoyMiBKYW4gLSBQTSB0byBlbmdhZ2Ugd2l0aCBlbmdpbmVlcmluZyByZSBzY29wZSAtIEV4ZWN1dGlvbiBwbGFubmluZyAxIEFwciB0byAzMCBBcHI=","RATING":""} |  |  |  | PHASE00 | 2024-05-01 | 2024-05-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000952 | Absa Fynbos Stillbay - Hvac ATM Room | Absa Fynbos Stillbay - Hvac ATM Room |  |  | Region 2 | Eastern Cape | 78314X | 1000-70895-01 | The Fynbos Centre-Cnr Main Rd & Buitekant St-Stilbaai | N | 2024-05-15 | 2024-09-30 |  | ASP-EC0404 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_516 | {"MANDT":"111","REFERENCE":90000952,"ONEVIEW":"78314X","DATE01":"2024-03-06","DATE02":"2024-03-13","DATE03":"2024-04-03","DATE04":"2024-04-10","DATE05":"2024-05-01","DATE06":"2024-05-15","DATE07":"2024-05-30","DATE08":"2024-06-20","DATE09":"2024-08-04","DATE10":"2024-08-31","DATE11":"2024-12-05","DATE12":"2024-12-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"300:7:21:7:21:14:15:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTUgRmViIEVuZyB0byBwcm92aWRlIHRoZSBRQ1AgYW5kIHNjb3BpbmcgZG9jdW1lbnQuIFBNIHRvIHNlbmQgdG8gdmVuZG9ycyBmb3IgY29zdGluZwowOCBGZWIgRW5nIHRvIHByb3ZpZGUgUUNQIGFuZCBTcGVjaWZpY2F0aW9ucy9TY29wZQoxIEZlYiAtIFNwZWNpZmljYXRpb25zIFBlbmRpbmcgLSBOb3RlIExMIGFwcHJvdmFsIHdpbGwgYmUgcmVxdWlyZWQKMjkgSmFuIFF1b3RlcyB0byBiZSByZXF1ZXN0ZWQgYXMgcmVxdWlyZWQKMjIgSmFuIC0gUE0gdG8gY29uZmlybSBpZiBzdGlsbCByZXF1aXJlZCAtIEV4ZWN1dGlvbiBQbGFuIDE1IE1heSB0byAzMCBNYXk=","RATING":""} |  |  |  | PHASE00 | 2024-05-31 | 2024-06-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000953 | Absa Moffett Office Park - ENG Worktop | Absa Moffett Office Park - ENG Worktop |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2024-03-01 | 2024-06-30 |  | ASP-EC0405 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : TBA Corp Reprioritised | {"MANDT":"111","REFERENCE":90000953,"ONEVIEW":"22937X","DATE01":"2024-01-17","DATE02":"2024-02-09","DATE03":"2024-03-01","DATE04":"2024-03-08","DATE05":"2024-03-29","DATE06":"2024-04-12","DATE07":"2024-08-11","DATE08":"2024-09-01","DATE09":"2024-10-16","DATE10":"2024-10-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":80,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:23:21:7:21:14:121:21:45:26","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-12","FORECAST_END":"2024-08-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggLSBCQyBDb21waWxhdGlvbiBpbiBQcm9ncmVzcyAtIFdvcmt0b3AgT05MWSAtIE9wdGlvbnMgdG8gYmUgY2hlY2tlZAo0IE1hcmNoIC0gRHJhd2luZ3MgaW5kaWNhdGUgd29ya3RvcCwgcG93ZXIgcmVxdWlyZW1lbnRzIHRvIGJlIGNvbmZpcm1lZAoyNiBGZWIgLSBEcmF3aW5ncyB0byBiZSBVcGRhdGVkCjE5IEZlYiBQTSB0byBtZWFzdXJlIGFuZCB2ZXJpZnkgd2hlbiBvbiBzaXRlIHdlZWsgb2YgMTkgRmViCjUgRmViIC0gUE0gdG8gdmVyaWZ5IG9uIFNpdGUgcmUgU2NvcGUKMjIgSmFuIC0gUE0gdG8gZm9sbG93IHVwIHJlIHBvc2l0aW9uIGFuZCByZXF1aXJlbWVudCBmcm9tIEVuZ2luZWVyaW5nCjE3IEphbiAtIFBSRiBSZWNlaXZlZCBmcm9tIEZN","RATING":""} |  |  |  | PHASE00 | 2024-04-12 | 2024-08-11 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000954 | Absa Morcross Matatiele - Internet Kiosk | Absa Morcross Matatiele - Internet Kiosk |  |  | Region 2 | Eastern Cape | 77213X | 1000-71025-01 | Morcross Centre-Cnr Jagger & North St-Matatiele | N | 2024-03-01 | 2024-06-30 |  | ASP-EC0406 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_009 Retail Reprioritised | {"MANDT":"111","REFERENCE":90000954,"ONEVIEW":"77213X","DATE01":"2024-01-28","DATE02":"2024-02-04","DATE03":"2024-02-25","DATE04":"2024-03-03","DATE05":"2024-03-24","DATE06":"2024-04-07","DATE07":"2024-08-06","DATE08":"2024-08-27","DATE09":"2024-10-11","DATE10":"2024-10-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:121:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-07","FORECAST_END":"2024-08-06","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggUE0gZm9sbG93ZWVkIHVwIHdpdGggcGxhbm5lciByZSBkcmF3aW5ncyByZXF1aXJlZAo0IE1hcmNoIC0gQ29udGludWUgUDEgLSBEcmF3aW5ncyBvdXRzdGFuZGluZyBmcm9tIEFic2EgUGxhbm5lciAtIEVzdCBSMzVrCjI2IEZlYiAtIERyYXdpbmdzIG91dHN0YW5kaW5nIGluIG9yZGVyIHRvIHF1b3RlIGJlIHRvIGNvbmZpcm0KMTkgRmViIC0gRHJhd2luZ3Mgb3V0c3RhbmRpbmcgZnJvbSBQbGFubmVyCjUgRmViIC0gRHJhd2luZ3Mgb3V0c3RhbmRpbmcgZnJvbSBQbGFubmVyCjI5IEphbiAtIERyYXdpbmdzIHBlbmRpbmcgZm9yIHRoZSBzaXRlCjI4IEphbiAtIEFwcHJvdmVkIFBSRiByZWNlaXZlZAoyMiBKYW4gRHJhd2luZ3MgcGVuZGluZyBmcm9tIHBsYW5uZXIKMTUgSmFuIFBSRiByZWNlaXZlZCB0byBiZSBzZW50IGZvciBhcHByb3ZhbCBieSBGTSwgUE0gcmVxdWVzdGVkIFBsYW5uZXIgdG8gcHJvdmlkZSBkcmF3aW5n","RATING":""} |  |  |  | PHASE00 | 2024-04-07 | 2024-08-06 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000955 | Absa Bushveld Pick&Pay-Generator Removal | Absa Bushveld Pick&Pay-Generator Removal |  |  | Region 3 |  | 76787X | 1000-70523-01 | Bushveld Pick & Pay Centre-Cnr Mark & Potgieter St-Bela Bela |  | 2024-02-09 | 2024-04-05 |  | ASP-LP0195 | REL BUDG ISBD AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-22 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-09 | 2024-04-05 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000142478 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000956 | Absa Bredasdorp - Boundary Fence | Absa Bredasdorp - Boundary Fence |  |  | Region 2 | Western Cape | 77641X | 1000-70839-01 | Absa Bredasdorp-Long St-Bredasdorp | N | 2024-07-10 | 2024-07-20 |  | ASP-WC0350 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_323 | {"MANDT":"111","REFERENCE":90000956,"ONEVIEW":"77641X","DATE01":"2024-05-01","DATE02":"2024-05-08","DATE03":"2024-05-29","DATE04":"2024-06-05","DATE05":"2024-06-26","DATE06":"2024-07-10","DATE07":"2024-07-20","DATE08":"2024-08-10","DATE09":"2024-09-24","DATE10":"2024-09-30","DATE11":"2024-09-24","DATE12":"2024-09-24","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-10","FORECAST_END":"2024-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEZNIGZvciBjb3JyZWN0IFNjb3BlCjEyIEZlYiAtIFBNIHRvIHJlLWVuZ2FnZSBGTSByZSBTY29wZSBpbnB1dHMgcmVjZWl2ZWQgZnJvbSBBZnJpY2EgU2VjdXJpdHkKNSBGZWIgLSBQTSB0byBjb25maXJtIGluIHdyaXRpbmcgd2l0aCBBZnJpY2EgU2VjdXJpdHkgd2hvIGhhcyBpbmRpY2F0ZWQgbm8gcmlza3MKMjIgSmFuIFBNIHRvIGVuZ2FnZSBBZnJpY2EgU2VjdXJpdHkgYW5kIHBvc3NpYmx5IGp1c3QgZW5jbG9zZSBQYWxtIFRyZWUgLSBQbGFubmluZyBmb3IgMTAgSnVseSB0byAyMCBKdWx5","RATING":""} |  |  |  | PHASE00 | 2024-07-10 | 2024-07-20 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000039619 | 433584.73 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000957 | Absa Lower Long - Sluice Rooms | Absa Lower Long - Sluice Rooms |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | N | 2024-03-15 | 2024-05-15 |  | ASP-WC0351 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_536 | {"MANDT":"111","REFERENCE":90000957,"ONEVIEW":"77657X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-05-15","DATE07":"2024-06-15","DATE08":"2024-07-06","DATE09":"2024-08-20","DATE10":"2024-08-31","DATE11":"2024-07-20","DATE12":"2024-07-20","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"208:7:21:7:21:75:31:21:45:11","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-15","FORECAST_END":"2024-06-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIERyYXdpbmcgY29zdCBhcHByb3ZlZCwgb25jZSByZWNlaXZlZCB0byBiZSBzdWJtaXR0ZWQgdG8gQXJjaGl0ZWN0cyBmb3IgZHJhd2luZyB1cGRhdGVzCjEyIEZlYiBTdWJtaXR0ZWQgZm9yIENCNCBmb3IgZHJhd2luZyBSZXF1ZXN0IC0gQVNQLVdDMDM2MQo4IEZlYiBEcmF3aW5nIFF1b3RlcyByZWNlaXZlZCBTdWJtaXR0ZWQgdG8gVlAsIFZQIGluZGljYXRlZCB0byB0YWtlIFZpYSBDQihTZWUgQVNQLVdDMDM2MSkgCjUgRmViIC0gUE0gdG8gZm9sbG93IHVwIEFydXAgQXJjaGl0ZWN0cyByZSBEV0cgZHJhd2luZyBxdW90ZXMKMjkgSmFuIEZvcm1hbCBRdW90ZSBvdXRzdGFuZGluZyBmcm9tIFZlbmRvcgoyMiBKYW4gLSBQTSB0byBwcmVwYXJlIEJDIHRvIG9idGFpbiBwbGFucyBmcm9tIEFyY2hpdGVjdCAtIFBsYW5uaW5nIDE1IE1heSB0byAxNSBKdW5l","RATING":""} |  |  |  | PHASE00 | 2024-05-15 | 2024-06-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000958 | Absa Bridge Park - Wayfinder ClientSuite | Absa Bridge Park - Wayfinder ClientSuite |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2024-03-01 | 2024-04-30 |  | ASP-WC0352 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_577 Removed from Regional CIP | {"MANDT":"111","REFERENCE":90000958,"ONEVIEW":"36225X","DATE01":"2023-12-22","DATE02":"2023-12-29","DATE03":"2024-01-19","DATE04":"2024-01-26","DATE05":"2024-02-16","DATE06":"2024-03-01","DATE07":"2024-03-15","DATE08":"2024-04-05","DATE09":"2024-05-20","DATE10":"2024-05-31","DATE11":"2024-07-05","DATE12":"2024-07-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"222:7:21:7:21:14:14:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-01","FORECAST_END":"2024-03-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViICBTaXRlIElkZW50aWZpZWQgd2l0aCBGTSwgcXVvdGUgcmVxdWVzdGVkIGZvciBUViBFbGVjdHJpY2FsLCBJVCBjb3N0cyAtIEluc3RhbGwgcG9zaXRpb24gc2l0ZSBJZGVudGlmaWVkIHdpdGggRk0KMTIgRmViIFRvIGNvbnRpbnVlIGhvd2V2ZXIgbm90IHBhcnQgb2YgUmVnaW9uYWwgQ0lQIC0gVXNlIDMvMDkKNyBGZWIgQ2FwaXRhbCBQcm9qZWN0cyBoYXZlIHN1Ym1pdHRlZCBCQyBjYW5ub3QgYWRkIGl0ZW1zIGN1cnJlbnRseQo2IEZlYiBSZXF1ZXN0IHNlbnQgdG8gQ2FwaXRhbCBwcm9qZWN0IHJlIFdheSBGaW5kZXIgUXVlcnkgaWYgd2l0aGluIHRoZWlyIFNjb3BlCjUgRmViIFBNIHRvIGZvbGxvdyB1cCB3aXRoIENhcGl0YWwgUHJvamVjdHMgcmUgaW5jbHVzaW9uIGluIHRoZWlyIHNjb3BlCjIyIEphbiBQTSB0byBjaGVjayB3aXRoIENhcGl0YWwgUHJvamVjdCB0byBpbmNsdWRlIGluIHRoZWlyIHNjb3BlIC0gUGxhbm5pbmcgMSBNYXJjaCAxNSBNYXJjaA==","RATING":""} |  |  |  | PHASE00 | 2024-04-26 | 2024-05-10 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000959 | Absa Bridge Park - Shower rooftop - Replace Chipped Stone | Absa Bridge Park - Shower rooftop - Replace Chipped Stone |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2024-02-15 | 2024-03-31 |  | ASP-WC0353 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_423 | {"MANDT":"111","REFERENCE":90000959,"ONEVIEW":"36225X","DATE01":"2023-12-07","DATE02":"2023-12-14","DATE03":"2024-01-04","DATE04":"2024-01-11","DATE05":"2024-02-01","DATE06":"2024-04-15","DATE07":"2024-05-15","DATE08":"2024-06-05","DATE09":"2024-07-20","DATE10":"2024-07-31","DATE11":"2024-06-05","DATE12":"2024-06-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"206:7:21:7:21:74:30:21:45:25","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-15","FORECAST_END":"2024-05-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIHRvIEZvbGxvdyB1cCB3aXRoIEJWIEVuZ2luZWVyaW5nLCBRdW90ZXMgcmVxdWVzdGVkIGZvciBFeGhhdXN0IAoxMiBGZWIgLSBTcGVjaWZpY2F0aW9uIGZvciB0aGUgZXhoYXVzdCByZXF1ZXN0ZWQgZnJvbSBFbmdpbmVlcmluZwo1IEZlYiBQTSB0byBlbmdhZ2UgRW5naW5lZXJpbmcgcmUgc2NvcGUgcmUgZXhoYXVzdHMKMjIgSmFuIFBNIHRvIGVuZ2FnZSBFbmcgcmUgR2VuZXJhdG9yIGV4aGF1c3QgcGlwZXMgLSBQbGFubmluZyAxNSBBcHIgdG8gMTUgTWF5","RATING":""} |  |  |  | PHASE00 | 2024-04-15 | 2024-05-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000960 | Absa Bridge Park - Kitchen floor vinyl replacement | Absa Bridge Park - Kitchen floor vinyl replacement |  |  | Region 2 | Western Cape | 36225X | 1000-70759-01 | Bridge Park Bridgeway Century City-Bridgeway Rd-Cape Town | N | 2024-04-15 | 2024-06-30 |  | ASP-WC0354 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_581 Removed | {"MANDT":"111","REFERENCE":90000960,"ONEVIEW":"36225X","DATE01":"2024-06-03","DATE02":"2024-06-10","DATE03":"2024-07-01","DATE04":"2024-07-08","DATE05":"2024-07-29","DATE06":"2024-10-01","DATE07":"2024-10-30","DATE08":"2024-11-20","DATE09":"2025-01-04","DATE10":"2025-01-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:64:29:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-10-01","FORECAST_END":"2024-10-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRmViIC0gVklQIFJlcXVlc3RlZCBmb3IgaXRlbSB0byBiZSByZW1vdmVkIGZyb20gQ0lQIGFzIEJ1ZGdldCBEZWNsaW5lZCAtIFdhcyBSMzYwawoyMiBKYW4gLSBWUCBpbmRpY2F0ZWQgYXQgbWVldGluZyBoZWxkIDE5IEphbiB0byBiZSBRNCAtIFBsYW5uaW5nIGZvciAxIE9jdCB0byAzMCBPY3Q=","RATING":""} |  |  |  | PHASE12 | 2024-10-01 | 2024-10-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000961 | Absa Mountain Mill - Hvac in server room | Absa Mountain Mill - Hvac in server room |  |  | Region 2 | Western Cape | 77271X | 1000-71431-01 | Mountain Mill Shopping Centre-Mountain Mill Dr-Worcester | N | 2024-07-01 | 2024-09-30 |  | ASP-WC0355 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_427 | {"MANDT":"111","REFERENCE":90000961,"ONEVIEW":"77271X","DATE01":"2024-04-22","DATE02":"2024-04-29","DATE03":"2024-05-20","DATE04":"2024-05-27","DATE05":"2024-06-17","DATE06":"2024-07-01","DATE07":"2024-07-20","DATE08":"2024-08-10","DATE09":"2024-09-24","DATE10":"2024-09-30","DATE11":"2024-12-05","DATE12":"2024-12-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"253:7:21:7:21:14:19:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-01","FORECAST_END":"2024-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgRmViIEZpbmFsIFNjb3BlIGFuZCBTcGVjaWZpY2F0aW9ucyBQZW5kaW5nCjE1IEZlYiBFbmcgYnVzeSB3aXRoIHRoZSBzcGVjaWZpY2F0aW9ucy9zY29wZSwgUE0gdG8gcmVjZWl2ZSBpbmZvcm1hdGlvbiBvbiAxNiBGZWIKMDggRmViIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEVuZyBmb3Igc3BlY2lmaWNhdGlvbnMvc2NvcGUKMDEgRmViIC0gU3BlY2lmaWNhdGlvbnMgcGVuZGluZyBmcm9tIEVuZ2luZWVyaW5nCjIyIEphbiBQTSB0byBmb2xsb3cgdXAgd2l0aCBFbmdpbmVlcmluZyByZSBTY29wZSAtIFBsYW5uaW5nIDEgSnVseSB0byAyMCBKdWx5","RATING":""} |  |  |  | PHASE03 | 2024-07-01 | 2024-07-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000962 | Mountain Mill Shopping Centre - Install HVAC unit in the hosting office | Mountain Mill Shopping Centre - Install HVAC unit in the hosting office |  |  | Region 2 | Western Cape | 77271X | 1000-71431-01 | Mountain Mill Shopping Centre-Mountain Mill Dr-Worcester | N | 2024-07-01 | 2024-09-30 |  | ASP-WC0356 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_418 | {"MANDT":"111","REFERENCE":90000962,"ONEVIEW":"77271X","DATE01":"2024-04-22","DATE02":"2024-04-29","DATE03":"2024-05-20","DATE04":"2024-05-27","DATE05":"2024-06-17","DATE06":"2024-07-01","DATE07":"2024-07-20","DATE08":"2024-08-10","DATE09":"2024-09-24","DATE10":"2024-09-30","DATE11":"2024-12-05","DATE12":"2024-12-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"253:7:21:7:21:14:19:21:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-01","FORECAST_END":"2024-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgRmViIEZpbmFsIFNjb3BlIGFuZCBTcGVjaWZpY2F0aW9ucyBQZW5kaW5nCjE1IEZlYiBFbmcgYnVzeSB3aXRoIHRoZSBzcGVjaWZpY2F0aW9ucy9zY29wZSwgUE0gdG8gcmVjZWl2ZSBpbmZvcm1hdGlvbiBvbiAxNiBGZWIKMDggRmViIFBNIHRvIGZvbGxvdyB1cCB3aXRoIEVuZyBmb3Igc3BlY2lmaWNhdGlvbnMvc2NvcGUKMDEgRmViIC0gU3BlY2lmaWNhdGlvbnMgcGVuZGluZyBmcm9tIEVuZ2luZWVyaW5nCjIyIEphbiBQTSB0byBmb2xsb3cgdXAgd2l0aCBFbmdpbmVlcmluZyByZSBTY29wZSAtIFBsYW5uaW5nIDEgSnVseSB0byAyMCBKdWx5","RATING":""} |  |  |  | PHASE00 | 2024-07-01 | 2024-07-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000963 | Absa Piketberg - COC Remedial | Absa Piketberg - COC Remedial |  |  | Region 2 | Western Cape | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg | N | 2024-02-01 | 2024-04-30 |  | ASP-WC0357 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | 10 Jan - Absa Eng indicated GMP as was to be maintained. | {"MANDT":"111","REFERENCE":90000963,"ONEVIEW":"78132X","DATE01":"2023-11-23","DATE02":"2023-11-30","DATE03":"2023-12-21","DATE04":"2023-12-28","DATE05":"2024-01-18","DATE06":"2024-02-01","DATE07":"2024-04-30","DATE08":"2024-05-21","DATE09":"2024-07-05","DATE10":"2024-07-31","DATE11":"2024-07-05","DATE12":"2024-07-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-01","FORECAST_END":"2024-04-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE12 | 2024-02-01 | 2024-04-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000964 | Absa Lutzville - Dilaps Closure | Absa Lutzville - Dilaps Closure |  |  | Region 2 | Western Cape | 77802X | 1000-70860-01 | Lutzville-Namakwa St-Lutzville | N | 2024-08-01 | 2024-12-31 |  | ASP-WC0358 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000964,"ONEVIEW":"77802X","DATE01":"2023-12-01","DATE02":"2024-02-16","DATE03":"2024-02-23","DATE04":"2024-02-26","DATE05":"2024-02-25","DATE06":"2024-03-01","DATE07":"2024-03-29","DATE08":"2024-04-19","DATE09":"2024-06-03","DATE10":"2024-06-30","DATE11":"2025-03-07","DATE12":"2025-03-07","PROG01":0,"PROG02":60,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"151:77:7:3:-1:5:28:21:45:9","PROGRESS":5,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-01","FORECAST_END":"2024-03-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRmViIEZlZWRiYWNrIHBlbmRpbmcgZnJvbSBCcm9sbCByZSBwcm9wb3NlZCB0ZW5hbnQKNSBGZWIgLSBQb3RlbnRpYWwgdGVuYW50IHJldmlzZWQgc2NvcGUgcGVuZGluZyBmcm9tIEJyb2xsIC8gTEwKMzAgSmFuIFBvc3NpYmxlIGVhcmx5IGhhbmQgYmFjayB3aXRoIHNvbWUgcmVpbnN0YXRlbWVudCByZXF1aXJlbWVudHMgQkMgaGVsZCBCYWNrIGZvciBub3cgYXMgcGVyIFBsYW5uZXIKMjkgSmFuIEJDIHRvIGJlIHN1Ym1pdHRlZCAyOSBKYW4gZm9yIFJlYWwgRXN0YXRlIGFwcHJvdmFsCjIyIEphbiBTZWN1cml0eSBjb3N0cyBwZW5kaW5nIGZvciBCQyB0byBiZSBzdWJtaXR0ZWQKMTEgRGVjIC4gRGlsYXBzIHRvIGNvbW1lbmNlIGZyb20gMTEgRmViIDIzIC4gCjcgRGVjIEtpY2sgb2ZmIG1lZXRpbmcgdG8gYmUgaGVsZCA3IERlYyAtIChGaXJlIFBhbmVsKQo0IERlYyAtIEtpY2sgb2ZmIG1lZXRpbmcgdG8gYmUgaGVsZCByZSBjbG9zdXJlCjI4IE5vdiBNYW5kYXRlIFNoYXJlZCBDbG9zdXJlIDI5IERlY2VtYmVyIHRvIGhhbmQgYmFjayAzMCBTZXB0ZW1iZXIgMjAyNS4gQVRNJ3MgdG8gcmVtYWluIG9uIHNpdGUu","RATING":""} |  |  |  | PHASE00 | 2024-04-19 | 2024-05-17 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000965 | Absa Uniondale - Waterproofing | Absa Uniondale - Waterproofing |  |  | Region 2 | Eastern Cape | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale | N | 2024-06-01 | 2024-08-30 |  | ALP-EC0029 | CRTD AVAC RESA SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | Absa Ref : Opex 6 March - Project changed to Small Project - was - ALP-EC0029 - Now - ASP-EC0417 | {"MANDT":"111","REFERENCE":90000965,"ONEVIEW":"78140X","DATE01":"2024-03-23","DATE02":"2024-02-22","DATE03":"2024-03-14","DATE04":"2024-03-21","DATE05":"2024-04-11","DATE06":"2024-06-01","DATE07":"2024-08-30","DATE08":"2024-09-20","DATE09":"2024-11-04","DATE10":"2024-11-30","DATE11":"2024-11-04","DATE12":"2024-11-04","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"252:-30:21:7:21:51:90:21:45:45:45:26","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-08-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"NiBNYXJjaCAtIFByb2plY3QgY2hhbmdlZCB0byBTbWFsbCBQcm9qZWN0IC0gd2FzIC0gQUxQLUVDMDAyOSAtICBOb3cgLSBBU1AtRUMwNDE3CjQgTWFyY2ggUXVvdGVzIHJlY2VpdmVkIGFkanVkaWNhdGlvbiBpbiBwcm9ncmVzcwoyNiBGZWIgLSBTaXRlIHZpc2l0IGNvbmR1Y3RlZCAyMiBGZWIgUXVvdGVzIGR1ZSAxIE1hcmNoCjIyIEZlYiAtIFNpdGUgVmlzaXQgYmVpbmcgY29uZHVjdGVkIDIyIEZlYiBTY29wZSBhbmQgUkZRIHRvIGZvbGxvdwoxOSBGZWIgLSBTaXRlIHZpc2l0IHdpdGggRW5naW5lZXJpbmcgMjIgRmViCjkgRmViIC0gTWFpbCBzZW50IHRvIGZvbGxvdyB1cCBXaXRoIFByb2N1cmVtZW50CjA4IEZlYiBTaXRlIFZpc2l0IHNjaGVkdWxlZCAyMyBGZWIKNyBGZWIgTWFpbCB0byBwcm9jdXJlbWVudCByZSBWZW5kb3IgU2VsZWN0aW9uIHNlbnQKNSBGZWIgUm91bmQgdHJpcCBwbGFubmVkIDIybmQgMjMgRmViCjI1IEphbiAtIFBNIHRvIGFycmFuZ2Ugcm91bmQgdHJpcCB0byBpbnNwZWN0IGFuZCBkZXRlcm1pbmUgc2NvcGUgYW5kIHNwZWNpZmljYXRpb25zCjIyIEphbiAtIFBNIHRvIGVuZ2FnZSByZSB3YXRlcnByb29maW5nIFNwZWMgYW5kIFZlbmRvcnMgIC0gUGxhbm5lZCBFeGVjdXRpb24gMSBKdW5lIHRvIDMwIEF1Zwo=","RATING":""} |  |  |  | PHASE03 | 2024-06-01 | 2024-08-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000966 | Absa Bizana - Generator Replacement | Absa Bizana - Generator Replacement |  |  | Region 2 | Eastern Cape | 70633X | 1000-71002-01 | Bizana Shopping Square-Cnr Church, Main & Hope St-Bizana | N | 2024-06-15 | 2024-08-31 |  | ALP-EC0030 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_506 10 April Deferred as per mail received from Absa Engineering | {"MANDT":"111","REFERENCE":90000966,"ONEVIEW":"70633X","DATE01":"2024-04-06","DATE02":"2024-03-05","DATE03":"2024-04-16","DATE04":"2024-04-23","DATE05":"2024-05-14","DATE06":"2024-07-03","DATE07":"2024-08-02","DATE08":"2024-08-23","DATE09":"2024-10-07","DATE10":"2024-10-31","DATE11":"2024-10-07","DATE12":"2024-10-07","PROG01":0,"PROG02":100,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:-32:42:7:21:50:30:21:45:45:45:11","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-03","FORECAST_END":"2024-08-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBcHJpbCAtIFF1b3RlcyBzaGFyZWQgbWlub3IgY2hhbmdlcyByZXF1ZXN0ZWQgLSBkdWUgOSBBcHJpbAowNCBBcHJpbCBRdW90ZXMgcmVjZWl2ZWQsIExMIGFwcHJvdmFsIHBlbmRpbmcgZm9yIHRoZSBwYWxpc2FkZSBmZW5jZQoyOCBNYXJjaCAtIFF1b3RlcyB0byBiZSB1cGRhdGVkICBhbmQgc2hhcmVkIHdpdGggZW5naW5lZXJpbmcgMyBBcHJpbAoxOCBNYXJjaCBQb3NzaWJsZSBTYXZpbmcgZGVwZW5kYW50IG9uIG91dGNvbWUgb2YgY3VycmVudCByZXBhaXJzIC0gUkZRIHRvIENvbnRpbnVlLgoxNCBNYXJjaCBRdW90ZXMgdG8gYmUgb2J0YWluZWQgdG8gaW5zdGFsbCBidW5kIGFuZCBtb2RpZnkgZmVuY2UgZm9yIGRvdWJsZSBnYXRlLgoxMSBNYXJjaCBSRlEgaW4gcHJvZ3Jlc3MgZHVlIDE1IE1hcmNoCjQgTWFyY2ggUkZRIGluIFByb2dyZXNzIC0gUXVvdGVzIGR1ZSAxNSBNYXJjaAoyNiBGZWIgUE0gdG8gZ28gb3V0IG9uIFJGUSBmb3IgcmVwbGFjZW1lbnQgZ2VuZXJhdG9yCjIyIEZlYiAtIFBNIHRvIGFwcHJvYWNoIHByb2N1cmVtZW50IGZvciBWZW5kb3IgU2VsZWN0aW9uIGFuZCBnbyBvdXQgdG8gdGVuZGVyCjA4IEZlYiBJbiBFbmdpbmVlcmluZyBzcGFjZSB3aWxsIGJlIHByb2Nlc3NlZCB0aHJvdWdoIEdNUC4gRW5nIHRvIGZvbGxvdyB1cCBvbiB0aGUgUE8gYW5kIGFkdmlzZSByZSByZXBsYWNlbWVudAoxIEZlYiAtIFBNIHRvIGZvbGxvdyB1cCBmb3IgU3BlY2lmaWNhdGlvbnMgZm9yIG5ldyBHZW5lcmF0b3IKMjUgSmFuIHRvIGJlIHByaW9yaXRpc2VkIEVuZyB0byBzaGFyZSBTcGVjaWZpY2F0aW9ucwogMjIgSmFuIFBNIHRvIGNvbmZpcm0gd2l0aCBFbmdpbmVlcmluZyByZSBzcGVjaWZpY2F0aW9ucyBhbmQgc2NvcGUgLSBQcm9wb3NlZCBleGVjdXRpb24gMTUgSnVuZSB0byAxNSBKdWx5","RATING":""} |  |  |  | PHASE12 | 2024-07-03 | 2024-08-02 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000967 | Absa Uniondale - Electrical Infrastructure Degrading - Upgrade | Absa Uniondale - Electrical Infrastructure Degrading - Upgrade |  |  | Region 2 | Eastern Cape | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale | N | 2024-06-01 | 2024-08-30 |  | ALP-EC0031 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_308 | {"MANDT":"111","REFERENCE":90000967,"ONEVIEW":"78140X","DATE01":"2024-03-23","DATE02":"2024-03-30","DATE03":"2024-04-20","DATE04":"2024-04-27","DATE05":"2024-05-18","DATE06":"2024-06-01","DATE07":"2024-08-30","DATE08":"2024-09-20","DATE09":"2024-11-04","DATE10":"2024-11-30","DATE11":"2024-11-04","DATE12":"2024-11-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-08-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgRmViIC0gU2l0ZSBWaXNpdCBiZWluZyBjb25kdWN0ZWQgMjIgRmViIFNjb3BlIGFuZCBSRlEgdG8gZm9sbG93CjE5IEZlYiAtIFNpdGUgdmlzaXQgd2l0aCBFbmdpbmVlcmluZyAyMiBGZWIKMTUgRmViIFBNIGFuZCBFU00gdG8gc2NoZWR1bGUgc2l0ZSB2aXNpdAogMDggRmViIFNpdGUgdmlzaXQgc2NoZWR1bGVkIGZvciAxNiBGZWIgdG8gZGV0ZXJtaW5lIHNwZWNpZmljYXRpb25zIGFuZCBzY29wZQo1IEZlYiBzaXRlIHZpc2l0IHNjaGVkdWxlZCAxNiBGZWIgdG8gZGV0ZXJtaW5lIFNwZWNpZmljYXRpb25zIGFuZCBTY29wZQoxIEZlYiAtIFNjb3BlIGFuZCBzcGVjaWZpY2F0aW9ucyB0byBiZSBjb25maXJtZWQKMjkgSmFuIFByaW9yaXR5IHRvIGJlIFNjb3BlZCBBU0FQCjI1IEphbiAtIFBNIHRvIGFycmFuZ2Ugcm91bmQgdHJpcCB0byBpbnNwZWN0IGFuZCBkZXRlcm1pbmUgc2NvcGUgYW5kIHNwZWNpZmljYXRpb25zCjIyIEphbiAtIFBNIHRvIGZpbmFsaXNlIHNjb3BlIHdpdGggRW5naW5lZXJpbmcgIC0gUGxhbm5lZCBFeGVjdXRpb24gMSBKdW5lIHRvIDMwIEF1Zw==","RATING":""} |  |  |  | PHASE00 | 2024-05-25 | 2024-08-23 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000968 | Absa Nautilus Jeffreys Bay - Generator Replacement | Absa Nautilus Jeffreys Bay - Generator Replacement |  |  | Region 2 | Eastern Cape | 22196X | 1000-70942-01 | The Nautilus Builiding-Da Gama Rd-Jeffreys Bay | N | 2024-06-15 | 2024-09-30 |  | ALP-EC0032 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-01-22 | D | 0 |  | 1 |  |  | 0 | Absa Ref : 240129_505 10 April Deferred as per mail received from Absa Engineering | {"MANDT":"111","REFERENCE":90000968,"ONEVIEW":"22196X","DATE01":"2024-04-06","DATE02":"2024-02-26","DATE03":"2024-04-12","DATE04":"2024-04-19","DATE05":"2024-05-10","DATE06":"2024-06-29","DATE07":"2024-07-29","DATE08":"2024-08-19","DATE09":"2024-10-03","DATE10":"2024-10-31","DATE11":"2024-10-03","DATE12":"2024-10-03","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"177:-40:46:7:21:50:30:21:45:45:45:11","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-29","FORECAST_END":"2024-07-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBBcHJpbCAtIEJDIHRvIGJlIHByZXBhcmVkIGFuZCByZXZpZXdlZCA5IEFwcmlsIGluIG9yZGVyIHRvIHN1Ym1pdCB0byBDQiA+UjUwMGsKMDQgQXByaWwgUE0gdG8gZW5nYWdlIEVuZyBpbiByZWdhcmRzIHRvIHRoZSBhZGp1ZGljYXRpb24gb2YgdGhlIHF1b3RlcwoyOCBNYXJjaCAtIFF1b3RlcyB0byBiZSB1cGRhdGVkICBhbmQgc2hhcmVkIHdpdGggZW5naW5lZXJpbmcgMyBBcHJpbAoyNSBNYXJjaCAtIFJGUSBkdWUgMjggTWFyY2guCjExIE1hcmNoIFJGUSBpbiBwcm9ncmVzcyBkdWUgMTUgTWFyY2gKNCBNYXJjaCBSRlEgaW4gUHJvZ3Jlc3MgLSBRdW90ZXMgZHVlIDE1IE1hcmNoCjI2IEZlYiBQTSB0byBnbyBvdXQgb24gUkZRIGZvciByZXBsYWNlbWVudCBnZW5lcmF0b3IKMjIgRmViIC0gUE0gdG8gYXBwcm9hY2ggcHJvY3VyZW1lbnQgZm9yIFZlbmRvciBTZWxlY3Rpb24gYW5kIGdvIG91dCB0byB0ZW5kZXIKMTUgRmViIEVuZyB0byBwcm92aWRlIHNjb3BlL3NwZWNpZmljYXRpb25zIGFuZCBRQ1AgZm9yIHRoZSBnZW5lcmF0b3IgcmVwbGFjZW1lbnQKIDA4IEZlYiBFbmcgdG8gcHJvdmlkZSBzY29wZS9zcGVjaWZpY2F0aW9ucyBhbmQgUUNQIGZvciB0aGUgZ2VuZXJhdG9yIHJlcGxhY2VtZW50CjYgRmViIE1haWxzIGZyb20gQWJzYSByZSB0aGUgdW5pdCB0byBCViBFbmdpbmVlcmluZyAsIFNwZWNpZmljYXRpb25zIHBlbmRpbmcKMSBGZWIgLSBERCBhbmQgU3BlY2lmaWNhdGlvbnMgdG8gYmUgc2hhcmVkIHdpdGggUE0KMjIgSmFuIFBNIHRvIGNvbmZpcm0gd2l0aCBFbmdpbmVlcmluZyByZSBzcGVjaWZpY2F0aW9ucyBhbmQgc2NvcGUgLSBQcm9wb3NlZCBleGVjdXRpb24gMTUgSnVuZSB0byAxNSBKdWx5","RATING":""} |  |  |  | PHASE12 | 2024-06-29 | 2024-07-29 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000969 | Absa Lower Long - 8th Fl Waterproofing | Absa Lower Long - 8th Fl Waterproofing |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | N | 2024-03-15 | 2024-05-15 |  | ALP-WC0033 | CRTD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-22 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000969,"ONEVIEW":"77657X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-09-15","DATE07":"2024-10-15","DATE08":"2024-11-05","DATE09":"2024-12-20","DATE10":"2024-12-31","DATE11":"2024-07-20","DATE12":"2024-07-20","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"208:7:21:7:21:198:30:21:45:11","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-09-15","FORECAST_END":"2024-10-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgRmViIFNpdGUgdmlzaXQgY29uZHVjdGVkIDIxIEZlYiAyIFZpc2l0IHJlcXVpcmVkIGFzIHJlcXVlc3RlZCBieSBWZW5kb3JzIDI4IEZlYiB0byBpbmNsdWRlIHNwZWNpYWxpc3RzCjA4IEZlYiBTaXRlIHZpc2l0IHNjaGVkdWxlZCBmb3IgMjEgRmViCjI1IEphbiBTaXRlIFZpc2l0IHBsYW5uZWQgZm9yIDIxIEZlYiB0byBkZXRlcm1pbmUgc2NvcGUgYW5kIHNwZWNpZmljYXRpb25zIHdpdGggVmVuZG9ycwoyMiBKYW4gLSBDYWxsIHRoZSBzdXBwbGllcnMgZnJvbSBSRUcxIHRvIGFycmFuZ2Ugc2l0ZSBtZWV0aW5nIC0gUHJvcG9zZWQgRXhlY3V0aW9uIDE1IFNlcHQgdG8gMTUgT2N0","RATING":""} |  |  |  | PHASE00 | 2024-11-08 | 2024-12-08 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000970 | Absa Musgrave Centre - Dilaps VO | Absa Musgrave Centre - Dilaps VO |  |  | Region 3 |  | 77800X | 1000-71620-01 | Musgrave Centre-Musgrave Rd-Musgrave |  | 2024-03-01 | 2024-05-02 |  | ASP-KZ0272 | REL ISBD AVAC RESA: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-05-02 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000140127 | 8695 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000971 | Replacement of UPS Batteries Jan- 2024 | Replacement of UPS Batteries Jan- 2024 |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-01-31 | 2024-12-13 |  | ALP-N00070 | REL BUDG AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2024 |  |  |  | LOUISR | 2024-01-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-31 | 2024-12-13 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000147068 | 1304347.83 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000972 | Replacement of Small FM Items- Jan 2024 | Replacement of Small FM Items- Jan 2024 |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-01-31 | 2024-12-13 |  | ALP-N00071 | REL BUDG AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2024 |  |  |  | LOUISR | 2024-01-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-31 | 2024-12-13 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000148432 | 652173.91 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000973 | Procurement of White Goods- Jan 2024 | Procurement of White Goods- Jan 2024 |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-01-31 | 2024-12-13 |  | ALP-N00072 | REL BUDG AVAC RESA: |  | false | false |  | Lorri-Anne Louis |  |  | 2024 |  |  |  | LOUISR | 2024-01-24 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-01-31 | 2024-12-13 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000147102 | 1000000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000974 | Auckland Park MTR Room | Auckland Park MTR Room |  |  | Region 1 |  | 37140X | 1000-71710-01 | Gilloolys View-Osborne Ln-Gauteng |  | 2024-01-25 | 2024-02-23 |  | ASP-GS0789 | REL BUDG AVAC RESA SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-01-25 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE09 | 2024-01-25 | 2024-02-23 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000142487 | 418109.3 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000975 | Land for Absa Demountable-Stolen Aircon | Land for Absa Demountable-Stolen Aircon |  |  | Region 3 |  | 78556X | 1000-71311-01 | Land For Absa Demountable Bank Unit-Cnr Motsatsi & Makheni St-Thlabane |  | 2024-02-22 | 2024-04-04 |  | ASP-CR0546 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-22 | 2024-04-04 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000976 | Absa Bell Str(Greytown)- Geyser Replacem | Absa Bell Str(Greytown)- Geyser Replacem |  |  | Region 3 |  | 76978X | 1000-71151-01 | Absa Bell Street-Cnr Bell & Pine St-Greytown |  | 2024-02-22 | 2024-03-22 |  | ASP-KZ0273 | CRTD AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-22 | 2024-03-22 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142002 | 8320 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000977 | Absa Spar Lydenburg-Replc Vandalized Uni | Absa Spar Lydenburg-Replc Vandalized Uni |  |  | Region 3 |  | 77360X | 1000-70623-01 | Spar Centre Lydenburg-Cnr Voortrekker & Viljoen St-Lydenburg |  | 2024-02-28 | 2024-03-19 |  | ASP-MP0179 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-28 | 2024-03-19 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000978 | Absa 291 Anton Lembede-Aircon Unit Repai | Absa 291 Anton Lembede-Aircon Unit Repai |  |  | Region 3 |  | 77987X | 1000-71206-01 | Absa 291 Anton Lembede Street-Anton Lembede St-Durban |  | 2024-03-01 | 2024-04-25 |  | ALP-KZ0009 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-04-25 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000979 | Absa Theunissen - Install Dedicated Plug | Absa Theunissen - Install Dedicated Plug |  |  | Region 3 |  | 79293X | 1000-71578-01 | Theunissen-Van Heerden St-Theunissen |  | 2024-02-08 | 2024-03-28 |  | ASP-CR0547 | CRTD: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-29 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-08 | 2024-03-28 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000980 | Absa 32 Voortrekker - Dilaps Phase1 | Absa 32 Voortrekker - Dilaps Phase1 |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2024-02-12 | 2024-04-30 |  | ASP-WC0359 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-01-29 | D | 165902.76 |  | 100 | 2024-01-30 | 2024-01-31 | 165902.76 | Absa Ref : Opex 31 Jan Supported by VP, Submitted to Real Estate for Approval | {"MANDT":"111","REFERENCE":90000980,"ONEVIEW":"78126X","DATE01":"2024-01-08","DATE02":"2024-01-22","DATE03":"2024-01-29","DATE04":"2024-01-29","DATE05":"2024-01-31","DATE06":"2024-02-12","DATE07":"2024-02-29","DATE08":"2024-03-21","DATE09":"2024-05-05","DATE10":"2024-05-31","DATE11":"2024-07-05","DATE12":"2024-07-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":100,"PROG06":100,"PROG07":20,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"144:14:7:0:2:12:17:21:45:27","PROGRESS":30,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-12","FORECAST_END":"2024-02-29","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRmViIFdvcmtzIHN0YXJ0ZWQgMTIgRmViIAo4IEZlYiAtIEJpZHZlc3QgUE8ncyBJc3N1ZWQgLSA0NTAwODg4MzU3IC0gR2xvYmFsIEFjY2VzcywgNDUwMDg4ODM1OCBTZWN1dGVsLCA0NTAwODg4MzYyIEZBRFQsIDQ1MDA4ODgzNjQgSGxhbmdhbmlzYSBUZWNobm9sb2dpZXMgUHR5IEx0ZAo3IEZlYiBBYnNhIFBPIHJlY2VpdmVkIEMwMDAxNDAxNDIsIEJWIFBPJ3MgcmVxdWVzdGVkCjMxIEphbiBBcHByb3ZlZCBieSBSZWFsIEVzdGF0ZSAtIEFic2EgUE8gUGVuZGluZwozMSBKYW4gU3VwcG9ydGVkIGJ5IFZQLCBTdWJtaXR0ZWQgdG8gUmVhbCBFc3RhdGUgZm9yIEFwcHJvdmFsCjMwIEphbiBCViBTdWJtaXR0ZWQgdG8gQ3JlcyBWUCBmb3IgU3VwcG9ydAoyOSBKYW4gUFJKIE51bWJlciByZXF1ZXN0ZWQ=","RATING":""} |  |  | C000140142 | PHASE08 | 2024-02-12 | 2024-03-22 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-02-07 | 144263.27 | 0 |  |  | C000140142 | 144263.27 |  | 7872.99 |  | 0 | 0 |  | 0 |  | 0
90000981 | Absa Mega City Shopping-Install Carpets | Absa Mega City Shopping-Install Carpets |  |  | Region 3 |  | 77784X | 1000-71299-01 | Mega City Shopping Centre-Cnr Sekame St & Dr. James Maroka Dr-Mmabatho |  | 2024-03-06 | 2024-05-30 |  | ALP-CR0044 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-29 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-06 | 2024-05-30 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000982 | Absa Arbour Crossing-Replace Ceiling Til | Absa Arbour Crossing-Replace Ceiling Til |  |  | Region 3 |  | 70634X | 1000-71145-01 | Arbour Crossing Retail Centre-Arbour Rd-Amanzimtoti |  | 2024-03-05 | 2024-03-20 |  | ASP-KZ0274 | CRTD ISBD AVAC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-01-31 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-05 | 2024-03-20 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000142376 | 172755.79 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000983 | Absa Kempston Road - Reinstatement | Absa Kempston Road - Reinstatement |  |  | Region 2 | Eastern Cape | 76390X | 1000-71006-01 | Kempston Road-Kempston Rd-Port Elizabeth | N | 2024-03-01 | 2024-06-30 |  | ASP-EC0407 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-02-02 | D | 52550.45 |  | 100 | 2024-02-06 | 2024-02-08 | 52550.45 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000983,"ONEVIEW":"76390X","DATE01":"2024-01-25","DATE02":"2024-02-01","DATE03":"2024-02-07","DATE04":"2024-02-07","DATE05":"2024-02-08","DATE06":"2024-02-26","DATE07":"2024-02-28","DATE08":"2024-03-20","DATE09":"2024-05-04","DATE10":"2024-05-31","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:6:0:1:18:2:21:45:26","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-26","FORECAST_END":"2024-02-28","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIgRmViIFBPJ3MgSXNzdWVkIC0gQ1MgU29sdXRpb25zIDQ1MDA4ODg3MDQsIFByZXN0aWdlIENsZWFuaW5nIDQ1MDA4ODg3MTMsIFMmRyBTaWducyA0NTAwODg4NzE4CjkgRmViIEFic2EgUE8gQzAwMDE0MTE0MSBSZWNlaXZlZCAtIEJWIFBPJ3MgUmVxdWVzdGVkCjggRmViIEFwcHJvdmVkIFBPIFBlbmRpbmcKNyBGZWIgU2VudCB0byBSZWFsIEVzdGF0ZSBmb3IgQXBwcm92YWwKNiBGZWIgU3VibWl0dGVkIHRvIENyZXMgVlAgZm9yIFN1cHBvcnQgLSBXYXMgU3VwcG9ydGVk","RATING":""} |  |  | C000141141 | PHASE08 | 2024-02-26 | 2024-03-04 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-02-09 | 45696.04 | 0 |  |  | C000141141 | 45696.05 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000984 | Absa Bank Frankfort - Water Tank Install | Absa Bank Frankfort - Water Tank Install |  |  | Region 3 |  | 78306X | 1000-71536-01 | Frankfort-Brand St-Frankfort |  | 2024-03-07 | 2024-05-30 |  | ASP-CR0548 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-05 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-07 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000985 | Absa Theunissen- Water Tank Installation | Absa Theunissen- Water Tank Installation |  |  | Region 3 |  | 79293X | 1000-71578-01 | Theunissen-Van Heerden St-Theunissen |  | 2024-03-14 | 2024-05-30 |  | ASP-CR0549 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-06 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-14 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000986 | Absa Warden-Water Tank Installation | Absa Warden-Water Tank Installation |  |  | Region 3 |  | 79096X | 1000-71571-01 | Absa Warden-Piet Retief St-Warden |  | 2024-03-28 | 2024-05-30 |  | ASP-CR0550 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-06 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-30 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000987 | Absa Kimberley RHO- Dilaps VO | Absa Kimberley RHO- Dilaps VO |  |  | Region 3 |  | 78316X | 1000-71346-01 | Absa Regional Head Office Kimberley-Bultfontein Rd-Kimberley |  | 2024-02-28 | 2024-03-29 |  | ASP-CR0551 | REL BUDG AVAC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-06 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-28 | 2024-03-29 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000143221 | 27528.1 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000988 | Absa Strand - Additional red plugs | Absa Strand - Additional red plugs |  |  | Region 2 |  | 78020X | 1000-71443-01 | 14 Strand Road-Strand Rd-Bellville |  | 2024-02-20 | 2024-03-31 |  | ASP-WC0360 | CRTD DLFL SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  |  |  | CEASARS | 2024-02-06 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED |  |  | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000989 | Absa Lower Long - CAD Drawings | Absa Lower Long - CAD Drawings |  |  | Region 2 | Western Cape | 77657X | 1000-71437-01 | Absa Lower Long Street-Lower Long St-Cape Town | N | 2024-03-01 | 2024-06-30 |  | ASP-WC0361 | REL BUDG AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-02-07 | D | 2300 |  | 100 | 2024-02-08 | 2024-02-15 | 2300 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90000989,"ONEVIEW":"77657X","DATE01":"2024-01-15","DATE02":"2024-01-22","DATE03":"2024-02-08","DATE04":"2024-02-08","DATE05":"2024-02-15","DATE06":"2024-02-20","DATE07":"2024-02-20","DATE08":"2024-03-12","DATE09":"2024-04-26","DATE10":"2024-04-30","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:17:0:7:5:0:21:45:26","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-20","FORECAST_END":"2024-02-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTkgRmViIEFic2EgUE8gQzAwMDE0MzQxMiBSZWNlaXZlZCBCViBQTydzIHJlcXVlc3RlZAoxNSBGZWIgQXBwcm92ZWQgYXQgQ0IgQWJzYSBQTyBQZW5kaW5nCjEyIEZlYiBTdWJtaXR0ZWQgZm9yIENCNCBmb3IgZHJhd2luZyBSZXF1ZXN0CjcgRmViIFByb2plY3QgTnVtYmVyIHJlY2VpdmVkLCBzdWJtaXR0ZWQgdG8gVlAgZm9yIHN1cHBvcnQgYW5kIGd1aWRhbmNlIHRvIG9idGFpbiB0aGUgZHJhd2luZ3MgLSBWUCBpbmRpY2F0ZWQgdG8gQ0IK","RATING":""} |  |  | C000143412 | PHASE07 | 2024-02-20 | 2024-03-20 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-02-19 | 2000 | 0 |  |  | C000143412 | 2000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000990 | Absa Burger Street- External Works | Absa Burger Street- External Works |  |  | Region 3 |  | 77057X | 1000-71282-01 | Absa Burger Street-Cnr Nelson Mandela & Beyers Naude St-Rustenburg |  | 2024-04-22 | 2024-05-27 |  | ALP-CR0045 | CRTD RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-22 | 2024-05-27 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000991 | Hygiene surveys at Corp and retail sites | Hygiene surveys at Corp and retail sites |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-02-29 | 2024-12-17 |  | ALP-N00073 | CRTD: |  | false | false |  | Lorri-Anne Louis |  |  | 2024 |  |  |  | LOUISR | 2024-02-09 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-29 | 2024-12-17 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000992 | Absa Paulpietersburg (17High) Minor Work | Absa Paulpietersburg (17High) Minor Work |  |  | Region 3 |  | 77511X | 1000-71177-01 | Absa 17 High Street-High St-Paulpietersburg |  | 2024-03-28 | 2024-05-30 |  | ASP-KZ0275 | CRTD RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-30 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000993 | Absa Ulundi ShopCentre - Minor Works | Absa Ulundi ShopCentre - Minor Works |  |  | Region 3 |  | 77891X | 1000-71198-01 | Ulundi Shopping Centre-Princess Mbakayi St-Ulundi |  | 2024-03-28 | 2024-05-30 |  | ASP-KZ0276 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-30 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000994 | Absa Vryheid Centre-Minor Works | Absa Vryheid Centre-Minor Works |  |  | Region 3 |  | 37154X | 1000-77453-01 | Vryheid Spar Centre-Cnr President & Church St-KwaZulu-Natal |  | 2024-03-28 | 2024-05-30 |  | ASP-KZ0277 | CRTD RESA SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000995 | Absa Port Edward-Minor Works | Absa Port Edward-Minor Works |  |  | Region 3 |  | 77893X | 1000-71199-01 | Port Edward Mall-Owen Ellis Dr-Port Edward |  | 2024-03-28 | 2024-05-30 |  | ASP-KZ0278 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-30 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000996 | Absa Parys - Minor Works | Absa Parys - Minor Works |  |  | Region 3 |  | 78350X | 1000-71537-01 | Absa Parys-Cnr Middel & Kerk St-Parys |  | 2024-03-28 | 2024-05-30 |  | ASP-CR0552 | CRTD RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000997 | Absa Moruleng Mall-Damaged Sign INSOG | Absa Moruleng Mall-Damaged Sign INSOG |  |  | Region 3 |  | 36104X | 1000-71268-01 | Moruleng Mall-Main Hospital Rd-Moruleng |  | 2024-03-07 | 2024-04-04 |  | ASP-CR0553 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-07 | 2024-04-04 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000998 | Absa Corner Church& Johan Signage INSOG | Absa Corner Church& Johan Signage INSOG |  |  | Region 3 |  | 37181X | 1000-77497-01 | Corner of Church Street and Johanna Van Der Merwe Streets |  | 2024-03-07 | 2024-04-04 |  | ASP-CR0554 | CRTD: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-07 | 2024-04-04 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90000999 | Absa Phokeng Mall- DB (INSOG) | Absa Phokeng Mall- DB (INSOG) |  |  | Region 3 |  | 78032X | 1000-71306-01 | Phokeng Mall-Main Rd-Rustenburg |  | 2024-03-07 | 2024-04-04 |  | ASP-CR0555 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-07 | 2024-04-04 | NANDE MAQUBELA | Juanita van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001000 | Absa Gansbaai - Minor Works | Absa Gansbaai - Minor Works |  |  | Region 2 | Western Cape | 77700X | 1000-70849-01 | 49 Main Road Gansbaai-Main Rd-Gansbaai | N | 2024-05-01 | 2024-07-31 |  | ALP-WC0034 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-02-13 | D | 828127.98 |  | 20 | 2024-03-22 |  | 0 | Absa Ref : 240129_343 New Project Created ALP-WC0034 was ASP-WC0344 | {"MANDT":"111","REFERENCE":90001000,"ONEVIEW":"77700X","DATE01":"2024-01-08","DATE02":"2024-02-13","DATE03":"2024-03-11","DATE04":"2024-03-18","DATE05":"2024-04-08","DATE06":"2024-06-01","DATE07":"2024-06-30","DATE08":"2024-07-21","DATE09":"2024-09-04","DATE10":"2024-09-30","DATE11":"2024-09-04","DATE12":"2024-09-04","PROG01":0,"PROG02":100,"PROG03":80,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"205:36:27:7:21:54:29:21:45:45:45:11","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-06-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggU3VibWl0dGVkIHRvIEFic2EgUHJvY3VyZW1lbnQgZm9yIHN1cHBvcnQKNCBNYXJjaCAtIEludGVybmFsIFBhcGVyIHRvIGJlIHByZXNlbnRlZCAtIDEyIE1hcmNoCjI2IEZlYiBSZWdpb24gdG8gYXBwcm92ZWQgb2YgZXhwZWN0ZWQgY29zdHMgYW5kIHRvIGJlIHByZXNlbnRlZCBpbnRlcm5hbGx5IDQgTWFyY2ggb25jZSBhY2NlcHRlZCAoPlIxbSkKMTkgRmViIC0gUE0gY29tcGlsaW5nIEJUQiBQYWNrLCBBZGp1ZGljYXRpb24gdG8gYmUgY29uZmlybWVkCjEzIEZlYiBOZXcgUHJvamVjdCBDcmVhdGVkIEFMUC1XQzAwMzQgIHdhcyBBU1AtV0MwMzQ0ICBkdWUgdG8gaW5jcmVhc2VkIFNjb3BlCjYgRmViIE1haWwgc2VudCB0byBQcm9jdXJlbWVudCByZSBWZW5kb3IgU2VsZWN0aW9uIEFzIHNjb3BlIGNoYW5nZWQgdG8gYmUgTGFyZ2UgUHJvamVjdCstUjEuMm0gLSBXYXMgY29uZmlybWVkIGFzIHBhcnQgb2YgWWVsbG93IExFRCBSb2xsIE9VVCAtIFRoZSBsaWdodHMgYXVkaXQgYXQgdGhpcyBzaXRlIGlzIHNjaGVkdWxlZCBmb3IgN3RoIEZlYiBhbmQgaW5zdGFsbGF0aW9ucyBhcmUgcGxhbm5lZCBmb3IgbWlkLU1hcmNoCjI5IEphbiAtIFdhaXQgZm9yIGlucHV0IGZyb20gRUIgcmUgNSBZZWFyIFBsYW4gLSB3ZWVrIDUgRmViCjIyIEphbiAtIFBNIHRvIGNvbmZpcm0gc2NvcGUgd2l0aCBwbGFubmVyIGFzIHRvIGJlIEJUQi4gUGxhbm5pbmcgMSBNYXkgMTUgTWF5","RATING":""} |  |  |  | PHASE05 | 2024-05-10 | 2024-05-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001001 | Absa Pinecrest- Minor Works | Absa Pinecrest- Minor Works |  |  | Region 3 |  | 77591X | 1000-71616-01 | Pine Crest Shopping Centre-Kings Rd-Pinetown |  | 2024-03-08 | 2024-03-15 |  | ASP-KZ0279 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-14 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-08 | 2024-03-15 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001002 | 190 Commissioner Str COC | 190 Commissioner Str COC |  |  | Region 1 |  | 37039X | 1000-70208-01 | Absa 190 Commissioner St-Commissioner St-Johannesburg |  | 2024-02-15 | 2024-03-15 |  | ASP-GS0791 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-02-15 | D | 28176.25 |  | 100 | 2024-02-13 | 2024-02-19 | 28176.25 |  | {"MANDT":"111","REFERENCE":90001002,"ONEVIEW":"37140X","DATE01":"2023-12-07","DATE02":"2024-02-13","DATE03":"2024-02-13","DATE04":"2024-02-20","DATE05":"2024-02-22","DATE06":"2024-02-22","DATE07":"2024-02-26","DATE08":"2024-03-18","DATE09":"2024-05-02","DATE10":"2024-05-31","DATE11":"2024-05-02","DATE12":"2024-05-02","PROG01":0,"PROG02":100,"PROG03":0,"PROG04":0,"PROG05":100,"PROG06":100,"PROG07":100,"PROG08":50,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"237:68:0:7:2:0:4:21:45:45:45:25","PROGRESS":78,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-22","FORECAST_END":"2024-02-26","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"Mjc6MDI6MjAyNCBCRk0gUE8gaGFzIGJlZW4gaXNzdWVkIHRvIHRoZSBzdXBwbGllci4gCjA4LzA0LzIwMjQgV29yayBoYXMgYmVlbiBjb21wbGV0ZWQsIFBPQyBoYXMgYmVlbiBzdWJtaXR0ZWQgZm9yIHNpZ25hdHVyZXMu","RATING":""} |  |  | C000143293 | PHASE08 | 2024-02-22 | 2024-02-26 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 |  |  |  |  | 2024-02-19 | 24501.09 | 0 |  |  | C000143293 | 24501.09 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001003 | EOL:Various- LED Lighting Panels Retail | EOL:Various- LED Lighting Panels Retail |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-03-28 | 2024-12-13 |  | ALP-N00074 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2024 |  |  |  | LOUISR | 2024-02-15 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-12-13 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001004 | EOL:Various- LED Lighting Panels at Corp | EOL:Various- LED Lighting Panels at Corp |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-03-28 | 2024-12-13 |  | ALP-N00075 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2024 |  |  |  | LOUISR | 2024-02-15 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-12-13 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001005 | Absa Metash Building Pongola-Minor Works | Absa Metash Building Pongola-Minor Works |  |  | Region 3 |  | 21868X | 1000-71087-01 | Metash Building Pongola-Nuwe Republic St-Pongola |  | 2024-03-28 | 2024-06-20 |  | ASP-KZ0280 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-19 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-06-20 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001006 | Absa Kamaqhekeza - DILAPS | Absa Kamaqhekeza - DILAPS |  |  | Region 3 |  | 77571X | 1000-70637-01 | Kamaqhekeza Plaza-Main Rd-Balfour |  | 2024-03-28 | 2024-04-30 |  | ASP-MP0181 | REL BUDG AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-19 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-04-30 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000149576 | 794555.36 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001007 | Absa University of Free State-Furniture | Absa University of Free State-Furniture |  |  | Region 3 |  | 78702X | 1000-71595-01 | University of the Free State Bloemfontei-Nelson Mandela Dr-Bloemfontein |  | 2024-03-28 | 2024-05-09 |  | ASP-CR0556 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-05-09 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001008 | Absa Towers North Replacement FCU | Absa Towers North Replacement FCU |  |  | Region 1 |  | 37039X | 1000-70208-01 | Absa 190 Commissioner St-Commissioner St-Johannesburg |  | 2024-02-20 | 2024-03-20 |  | ASP-GS0792 | CRTD: |  | false | false |  | Roegshana Gamiet |  |  | 2024 |  |  |  | GAMIETR | 2024-02-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-20 | 2024-03-20 |  | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000142323 | 6643.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001009 | Absa Sannieshof - Create Space ITAS Door | Absa Sannieshof - Create Space ITAS Door |  |  | Region 3 |  | 77996X | 1000-71305-01 | Sannieshof-Spoor St-Sannieshof |  | 2024-03-08 | 2024-05-09 |  | ASP-CR0557 | CRTD AVAC RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-21 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-08 | 2024-05-09 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001010 | Absa Montague Gardens - Dilaps | Absa Montague Gardens - Dilaps |  |  | Region 2 | Western Cape | 77789X | 1000-70859-01 | The John Montague Centre-Montague Dr-Montague Gardens | N | 2024-03-01 | 2024-06-30 |  | ASP-WC0362 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-02-21 | D | 82910.48 |  | 100 | 2024-03-07 | 2024-03-11 | 82910.48 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001010,"ONEVIEW":"77789X","DATE01":"2024-02-21","DATE02":"2024-02-28","DATE03":"2024-03-07","DATE04":"2024-03-07","DATE05":"2024-03-11","DATE06":"2024-03-25","DATE07":"2024-07-24","DATE08":"2024-08-14","DATE09":"2024-09-28","DATE10":"2024-09-30","DATE11":"2024-09-28","DATE12":"2024-09-28","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"253:7:8:0:4:14:121:21:45:45:45:8","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-25","FORECAST_END":"2024-07-24","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OCBNYXJjaCBTdXBwb3J0ZWQgYnkgQ1JFUyBWUCBTZW50IHRvIENQIHRvIHN1Ym1pdCB0byBSZWFsIEVzdGF0ZQo3IE1hcmNoIFN1Ym1pdHRlZCBmb3IgVlAgZm9yIFN1cHBvcnQgdG8gU3VibWl0IHRvIFJlYWwgRXN0YXRlCjQgTWFyY2ggLSBCQyB0byBiZSBzdWJtaXR0ZWQgLSB3ZWVrIG9mIDQgTWFyY2gKMjIgRmViIC0gU2l0ZSBWaXNpdCBjb25kdWN0ZWQgMjQgRmViLCBRdW90ZXMgdG8gYmUgcmVxdWVzdGVkIC0gU3RhcnQgZGF0ZSB0byBiZSAxMSB0byAxNSBNYXJjaAoyMSBGZWIgUmVxdWVzdCByZWNlaXZlZCwgU2NvcGUgYW5kIENvc3RpbmcgdG8gYmUgY29uZmlybWVk","RATING":""} |  |  | C000148139 | PHASE08 | 2024-03-12 | 2024-03-15 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-03-11 | 72096.07 | 0 |  |  | C000148139 | 72096.06 |  | 7510.04 |  | 0 | 0 |  | 0 |  | 0
90001011 | Absa Swartruggens - Replace ATM Midwall | Absa Swartruggens - Replace ATM Midwall |  |  | Region 3 |  | 77433X | 1000-71291-01 | Swartruggens-Sarel Cilliers St-Swartruggens |  | 2024-04-02 | 2024-04-11 |  | ASP-CR0558 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-22 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-02 | 2024-04-11 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001012 | Absa Mandela Park - Minor Works | Absa Mandela Park - Minor Works |  |  | Region 3 |  | 37226X | 1000-77586-01 | Absa Mandela Park shopping Centre |  | 2024-04-05 | 2024-05-09 |  | ASP-CR0559 | CRTD RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-23 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-05 | 2024-05-09 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001013 | Absa Jock of the Busgveld Centre-DILAPS | Absa Jock of the Busgveld Centre-DILAPS |  |  | Region 3 |  | 77136X | 1000-70611-01 | Jock of the Bushveld Centre-General St-Barberton |  | 2024-04-05 | 2024-05-09 |  | ASP-MP0182 | CRTD AVAC RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-23 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-05 | 2024-05-09 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001014 | Absa 264 Victoria Rd Woodstock - UPS | Absa 264 Victoria Rd Woodstock - UPS Replacement |  |  | Region 2 | Western Cape | 78104X | 1000-70883-01 | 264 Victoria Road-Victoria Rd-Woodstock | N | 2024-03-01 | 2024-06-30 |  | ASP-WC0363 | REL BUDG AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-02-23 | D | 170391.44 |  | 100 | 2024-02-26 | 2024-02-27 | 170391.44 | Absa Ref : 240129_358 Approved Against EOL Retail Electrical budget | {"MANDT":"111","REFERENCE":90001014,"ONEVIEW":"78104X","DATE01":"2024-02-22","DATE02":"2024-02-23","DATE03":"2024-02-26","DATE04":"2024-02-26","DATE05":"2024-03-27","DATE06":"2024-02-29","DATE07":"2024-03-01","DATE08":"2024-03-22","DATE09":"2024-05-06","DATE10":"2024-05-31","DATE11":"2024-05-06","DATE12":"2024-05-06","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":100,"PROG06":50,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"99:1:3:0:30:-27:1:21:45:45:45:24","PROGRESS":16,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-02-29","FORECAST_END":"2024-03-01","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjkgRmViIEFic2EgUE8gQzAwMDE0NTU5NiByZWNlaXZlZCAsIEJWIFBPIHJlcXVlc3RlZAoyNyBGZWIgT09DIEFwcHJvdmFsIHJlY2VpdmVkIEFic2EgUE8gcmVxdWVzdGVkCjI2IEZlYiAtIFN1Ym1pdHRlZCBmb3IgT09DIEFwcHJvdmFsIHRvIGJlIHRhYmxlZCBDQjA2CjI2IEZlYiBCdWRnZXQgZnJvbSBOYXRpb25hbCBFT0wgRWxlY3RyaWNhbAoyMiBGZWIgUFJGIFJlY2VpdmVkIHRvIGJlIHN1Ym1pdHRlZCBDQjA2","RATING":""} |  |  | C000145596 | PHASE09 | 2024-03-06 | 2024-03-06 | Rick Nevay | Floyd Mofokeng | 0 |  |  |  |  | 2024-02-29 | 148166.47 | 0 |  |  | C000145596 | 148166.47 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001015 | Absa Petrusburg - Install Water Tank | Absa Petrusburg - Install Water Tank |  |  | Region 3 |  | 79067X | 1000-71569-01 | Absa Petrusburg-Ossewa St-Petrusburg |  | 2024-04-02 | 2024-05-09 |  | ASP-CR0560 | CRTD SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-02 | 2024-05-09 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001016 | Meadowdale-Replacement of 4 x Split Air | Meadowdale-Replacement of 4 x Split Air |  |  | Region 1 |  | 37006X | 1000-70205-01 | Highlands Warehouse Meadowdale-Herman Rd-Edenvale |  | 2024-03-08 | 2024-09-30 |  | ASP-GN0242 | REL BUDG AVAC SETC: |  | false | false |  | Sanelisiwe Celu |  |  | 2024 |  |  |  | LOUISR | 2024-02-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-08 | 2024-09-30 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000148223 | 205729.88 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001017 | Alice Lane South Smalls Catering Equipme | Alice Lane South Smalls Catering Equipme |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2024-02-26 | 2024-02-26 |  | ASP-GS0793 | REL BUDG AVAC RESA SETC: |  | false | false |  | Roshen Aniruth |  |  | 2024 |  |  |  | GAMIETR | 2024-02-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-02-26 | 2024-02-26 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000145567 | 23014.02 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001018 | Absa Phakamile Mabhija - Minor Works | Absa Phakamile Mabhija - Minor Works |  |  | Region 3 |  | 78838X | 1000-71355-01 | Jones Street CBD-Jones St-Kimberley |  | 2024-04-04 | 2024-06-27 |  | ALP-CR0046 | CRTD AVAC RESA SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-04 | 2024-06-27 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001019 | Absa Koppies - External Refurbishment | Absa Koppies - External Refurbishment |  |  | Region 3 |  | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies |  | 2024-03-27 | 2024-04-03 |  | ASP-CR0561 | CRTD AVAC RESA: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-27 | 2024-04-03 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001020 | Absa Ridgeside - Automation Parting Door | Absa Ridgeside - Automation Parting Door |  |  | Region 3 |  | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2024-03-22 | 2024-03-22 |  | ASP-KZ0281 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-22 | 2024-03-22 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001021 | Queensburgh Centre -Install Vinyl Frosti | Queensburgh Centre -Install Vinyl Frosti |  |  | Region 3 |  | 77323X | 1000-71165-01 | Queensburgh Centre-Cnr Ridley Park & Old Main Rd-Queensburgh |  | 2024-03-18 | 2024-03-18 |  | ASP-KZ0282 | REL BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-18 | 2024-03-18 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000148340 | 102947.5 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001022 | Various- Procure 9 15kW UPSs for stock | Various- Procure 9 15kW UPSs for stock |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-03-28 | 2024-12-13 |  | ALP-N00076 | CRTD AVAC: |  | false | false |  | Lorri-Anne Louis |  |  | 2024 |  |  |  | LOUISR | 2024-02-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-12-13 | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001023 | Absa Schweizer Reneke - Minor Works | Absa Schweizer Reneke - Minor Works |  |  | Region 3 |  | 77953X | 1000-71303-01 | Absa Schweizer Reneke-Schweizer St-Schweizer Reneke |  | 2024-03-26 | 2024-04-30 |  | ASP-CR0562 | CRTD AVAC RESA: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-29 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-26 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001024 | Absa- Bela Bela (Bushveld)-DILAPS VO | Absa- Bela Bela (Bushveld)-DILAPS VO |  |  | Region 3 |  | 76787X | 1000-70523-01 | Bushveld Pick & Pay Centre-Cnr Mark & Potgieter St-Bela Bela |  | 2024-03-14 | 2024-03-29 |  | ASP-LP0196 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-02-29 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-14 | 2024-03-29 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000153645 | 43910.58 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001025 | Absa Ottosdal - Install 15KVA UPS | Absa Ottosdal - Install 15KVA UPS |  |  | Region 3 |  | 78143X | 1000-71606-01 | Absa Ottosdal-Voortrekker St-Ottosdal |  | 2024-03-27 | 2024-04-10 |  | ASP-CR0563 | REL BUDG AVAC SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-27 | 2024-04-10 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000146292 | 66707.95 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001026 | Absa Alice Lane North power socket | Absa Alice Lane North power socket |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2024-03-01 | 2024-03-05 |  | ASP-GS0797 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-01 | 2024-03-05 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000146191 | 93841 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001027 | Absa Thaba Mall - Install Eaton UPS | Absa Thaba Mall - Install Eaton UPS |  |  | Region 3 |  | 37045X | 1000-70507-01 | Thaba Mall-Cnr Warmbad Weg Rd & R510-Thabazimbi |  | 2024-03-14 | 2024-03-19 |  | ASP-LP0197 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-14 | 2024-03-19 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  | C000146287 | 149673.47 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001028 | Absa Thohoyandou West - Minor Works | Absa Thohoyandou West - Minor Works |  |  | Region 3 |  | 21948X | 1000-70464-01 | Game Shopping Centre-Mphetu Rd-Thohoyandou |  | 2024-04-25 | 2024-06-26 |  | ASP-LP0198 | CRTD RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-25 | 2024-06-26 | NANDE MAQUBELA | floyd mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001029 | Absa Ermelo - Minor Works | Absa Ermelo - Minor Works |  |  | Region 3 |  | 77584X | 1000-70638-01 | United Building-Kerk St-Ermelo |  | 2024-03-27 | 2024-05-03 |  | ASP-MP0183 | CRTD RESA SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-01 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-27 | 2024-05-03 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001030 | 230 Lilian Ngoyi Street, Carpet replacem | 230 Lilian Ngoyi Street, Carpet replacem |  |  | Region 1 |  | 22896X | 1000-70079-01 | 230 Lilian Ngoyi Street-Lilian Ngoyi St-Pretoria |  | 2024-03-04 | 2024-04-03 |  | ASP-GN0243 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-03 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001031 | 230 Lilian Ngoyi Street Frosting intern | 230 Lilian Ngoyi Street Frosting intern |  |  | Region 1 |  | 22896X | 1000-70079-01 | 230 Lilian Ngoyi Street-Lilian Ngoyi St-Pretoria |  | 2024-03-04 | 2024-04-08 |  | ASP-GN0244 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001032 | Alice lane South generator starter batte | Alice lane South generator starter batte |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-05 |  | ASP-GS0798 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-05 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001033 | Alice Lane North, Block out vinyl | Alice Lane North, Block out vinyl |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-04 |  | ASP-GS0799 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-04 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001034 | Alice lane North, Replacement of CRAC Un | Alice lane North, Replacement of CRAC Un |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-04 |  | ASP-GS0800 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-04 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001035 | Alice Lane North generator starter batte | Alice Lane North generator starter batte |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-05 |  | ASP-GS0801 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-05 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001036 | Alice lane North Prayer rooms revamp | Alice lane North Prayer rooms revamp |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-05 |  | ASP-GS0802 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-05 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001037 | 8 Top Road All blinds require replacemen | 8 Top Road All blinds require replacemen |  |  | Region 1 |  | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0803 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE03 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001038 | 8 Top Road Roof over office at mech wor | 8 Top Road Roof over office at mech wor |  |  | Region 1 |  | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg |  | 2024-03-05 | 2024-04-08 |  | ASP-GS0804 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-05 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001039 | 13 Top Road Installation of blinds | 13 Top Road Installation of blinds |  |  | Region 1 |  | 79271X | 1000-71418-01 | 13 Top Road-Top Rd-Boksburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0805 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001040 | 17 Harrison Street Frosting requires by | 17 Harrison Street Frosting requires by |  |  | Region 1 |  | 78786X | 1000-70435-01 | 17 Harrison Street-Harrison St-Johannesburg |  | 2024-03-05 | 2024-04-09 |  | ASP-GS0806 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-05 | 2024-04-09 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001041 | Alice Lane North BMS and EMS Systems | Alice Lane North BMS and EMS Systems |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-02 | 2024-03-02 |  | ALP-GS0088 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001041,"ONEVIEW":"21526X","DATE01":"2023-12-23","DATE02":"2023-12-30","DATE03":"2024-01-20","DATE04":"2024-01-27","DATE05":"2024-02-17","DATE06":"2024-03-02","DATE07":"2024-03-02","DATE08":"2024-03-23","DATE09":"2024-05-07","DATE10":"2024-05-31","DATE11":"2024-05-07","DATE12":"2024-05-07","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-02","FORECAST_END":"2024-03-02","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-02 | 2024-03-02 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001042 | Absa Towers West Upgrade BMS | Absa Towers West Upgrade BMS |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-03-02 | 2024-04-05 |  | ALP-GS0089 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-02 | 2024-04-05 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001043 | 270 Republic Rd 4 Chiller compressor | 270 Republic Rd 4 Chiller compressor |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-03-02 | 2024-04-05 |  | ALP-GS0090 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-02 | 2024-04-05 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001044 | Alice Lane North Shower rooms and abluti | Alice Lane North Shower rooms and abluti |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-04 |  | ALP-GS0091 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-04 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001045 | Alice Lane North main restaurant, servin | Alice Lane North main restaurant, servin |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-05 |  | ALP-GS0092 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-05 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001046 | Alice Lane South Restaurant Serving Area | Alice Lane South Restaurant Serving Area |  |  | Region 1 |  | 35041X | 1000-71371-01 | 15 Alice Lane-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-04 |  | ALP-GS0093 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-04 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001047 | Alice lane North Upgrade for Basement 3 | Alice lane North Upgrade for Basement 3 |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-03 |  | ALP-GS0094 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-03 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001048 | Alice Lane North Crack unit replacements | Alice Lane North Crack unit replacements |  |  | Region 1 |  | 70656X | 1000-71378-01 | Alice Lane Towers (12 Alice Lane)-Alice Ln-Sandton |  | 2024-03-04 | 2024-04-08 |  | ALP-GS0095 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001049 | 13 Top Road Shading net replacement & re | 13 Top Road Shading net replacement & re |  |  | Region 1 |  | 79271X | 1000-71418-01 | 13 Top Road-Top Rd-Boksburg | Y | 2024-03-04 | 2024-04-08 |  | ALP-GS0096 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001049,"ONEVIEW":"79271X","DATE01":"2023-12-25","DATE02":"2024-01-01","DATE03":"2024-01-22","DATE04":"2024-01-29","DATE05":"2024-02-19","DATE06":"2024-03-04","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-04","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE09 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001050 | 8 Top Road Carpet replacement through ou | 8 Top Road Carpet replacement through ou |  |  | Region 1 |  | 78451X | 1000-70406-01 | 8 Top Road-Top Rd-Boksburg |  | 2024-03-04 | 2024-04-03 |  | ALP-GS0097 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-02 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-03 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001051 | 270 Republic Rd Generator starter batter | 270 Republic Rd Generator starter batter |  |  | Region 1 |  | 21335X | 1000-71363-01 | Absa 270 Republic Road-Republic Rd-Randburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0807 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-03 | D | 0 |  | 15 |  |  | 0 | The project will be executed in Q3 | {"MANDT":"111","REFERENCE":90001051,"ONEVIEW":"21335X","DATE01":"2023-12-25","DATE02":"2024-01-01","DATE03":"2024-01-22","DATE04":"2024-01-29","DATE05":"2024-02-19","DATE06":"2024-03-04","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-04","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001052 | Auckland Park CC Replace blue desk panel | Auckland Park CC Replace blue desk panel |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0808 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-03 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001053 | Auckland Park CC FCU Controllers To BMS | Auckland Park CC FCU Controllers To BMS |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg | Y | 2024-03-04 | 2024-04-08 |  | ASP-GS0809 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-03 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001053,"ONEVIEW":"76849X","DATE01":"2023-12-25","DATE02":"2024-01-01","DATE03":"2024-01-22","DATE04":"2024-01-29","DATE05":"2024-02-19","DATE06":"2024-03-04","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-04","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001054 | Auckland Park CC Replace entire palisade | Auckland Park CC Replace entire palisade |  |  | Region 1 |  |  |  | Building not in Real Estate Database |  | 2024-03-04 | 2024-04-08 |  | ALP-GS0098 | CRTD: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-03 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001055 | Absa Auckland Park CC BMS HVAC Controlle | Absa Auckland Park CC BMS HVAC Controlle |  |  | Region 1 |  |  |  | Building not in Real Estate Database |  | 2024-03-04 | 2024-04-08 |  | ALP-GS0099 | CRTD: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-03 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001056 | Pretoria Campus Walk off mats | Pretoria Campus Walk off mats |  |  | Region 1 | Gauteng | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2024-03-04 | 2024-04-08 |  | ASP-GN0245 | REL BUDG AVAC SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  | F |  | GAMIETR | 2024-03-04 | D | 360843.53 |  | 60 | 2024-02-29 | 2024-03-07 | 360843.53 | 12/03/2024 AS: Waiting for Absa PO. | {"MANDT":"111","REFERENCE":90001056,"ONEVIEW":"22896X","DATE01":"2023-12-25","DATE02":"2024-01-31","DATE03":"2024-02-08","DATE04":"2024-02-15","DATE05":"2024-03-07","DATE06":"2024-03-21","DATE07":"2024-04-25","DATE08":"2024-05-16","DATE09":"2024-06-30","DATE10":"2024-06-30","DATE11":"2024-06-30","DATE12":"2024-06-30","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":60,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"188:37:8:7:21:14:35:21:45:45:45:17","PROGRESS":11,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-21","FORECAST_END":"2024-04-25","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTIvMDMvMjAyNCBBUzogV2FpdGluZyBmb3IgQWJzYSBQTy4=","RATING":""} |  |  | C000148160 | PHASE06 | 2024-05-10 | 2024-05-10 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2024-03-11 | 313776.98 | 0 |  |  | C000148160 | 313776.98 |  | 32604.87 |  | 0 | 0 |  | 0 |  | 0
90001057 | Absa Boksburg Dilaps | Absa Boksburg Dilaps |  |  | Region 1 |  | 76384X | 1000-70238-01 | Boksburg-Cnr Burg & Commissioner St-Boksburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0810 | REL BUDG AVAC SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-04 | D | 8789.45 |  | 60 | 2024-03-08 | 2024-03-08 | 8789.45 |  | {"MANDT":"111","REFERENCE":90001057,"ONEVIEW":"76849X","DATE01":"2023-12-25","DATE02":"2024-01-01","DATE03":"2024-01-22","DATE04":"2024-01-29","DATE05":"2024-02-19","DATE06":"2024-03-04","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-04","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000146524 | PHASE09 | 2024-02-22 | 2024-02-29 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 7643 | 0 |  |  | C000146524 | 7643 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001058 | Alice Lane North Replace Display TV at t | Alice Lane North Replace Display TV at t |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0811 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000148167 | 17520 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001059 | Towers West HVAC Unit Filters | Towers West HVAC Unit Filters |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0812 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001060 | Auckland Park CC HVAC Unit Filters | Auckland Park CC HVAC Unit Filters |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0813 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-04 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-04 | 2024-04-08 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001061 | Absa Dobsonville Dilaps Phase 1 | Absa Dobsonville Dilaps Phase 1 |  |  | Region 1 |  | 77943X | 1000-70384-01 | Dobsonville Mall-Elias Motsoaledi Rd-Dobsonville |  | 2024-03-04 | 2024-04-08 |  | ASP-GS0814 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-04 | D | 399518.86 |  | 60 | 2024-02-28 | 2024-03-01 | 399518.86 |  | {"MANDT":"111","REFERENCE":90001061,"ONEVIEW":"77943X","DATE01":"2023-12-25","DATE02":"2024-01-01","DATE03":"2024-01-22","DATE04":"2024-01-29","DATE05":"2024-02-19","DATE06":"2024-03-04","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-04","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000146762 | PHASE09 | 2024-03-17 | 2024-03-13 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 34740.75 | 0 |  |  | C000146762 | 347407.71 |  | 179524.9 |  | 0 | 0 |  | 0 |  | 0
90001062 | Absa Motherwell - Dilaps for Revamp | Absa Motherwell - Dilaps for Revamp |  |  | Region 2 | Eastern Cape | 76665X | 1000-71018-01 | Motherwell Shopping Centre-Cnr Nyara, Tyiniara & WM Maku St-Port Elizabeth | N | 2024-04-01 | 2024-12-30 |  | ASP-EC0409 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-05 | D | 86027.85 |  | 100 | 2024-04-02 | 2024-04-03 | 86027.85 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001062,"ONEVIEW":"76665X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-02-07","DATE08":"2025-02-28","DATE09":"2025-04-14","DATE10":"2025-04-30","DATE11":"2025-04-14","DATE12":"2025-04-14","PROG01":0,"PROG02":80,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:273:21:45:45:45:25","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-02-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggUkZRIGluIHByb2dyZXNzIFF1b3RlcyBkdWUgMTUgTWFyY2gKIDQgTWFyY2ggRGlsYXBzIHRvIGJlIGNvbmR1Y3RlZCAtIFByb2plY3Qgc3RhcnQgZGF0ZSB0ZW50YXRpdmUgLSA1IEFwcmls","RATING":""} |  |  | C000152690 | PHASE00 | 2024-04-08 | 2024-04-08 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-04-05 | 74806.83 | 0 |  |  | C000152690 | 74806.83 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001063 | Absa Kareedouw - New Coin Cage | Absa Kareedouw - New Coin Cage |  |  | Region 2 | Eastern Cape | 78089X | 1000-71462-01 | Kareedouw Shopping Centre-Van Riebeeck St-Kareedouw | N | 2024-10-01 | 2024-12-30 |  | ASP-EC0410 | CRTD: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-05 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_012 | {"MANDT":"111","REFERENCE":90001063,"ONEVIEW":"78089X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2024-08-08","DATE08":"2024-08-29","DATE09":"2024-10-13","DATE10":"2024-10-31","DATE11":"2024-10-13","DATE12":"2024-10-13","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:90:21:45:45:45:25","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2024-08-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTEgTWFyY2ggQ29pbiBDYWdlIHRvIGJlIHNlbnQgdG8gS2FyZWVkb3V3IGZyb20gR3JlZW5hY3JlcyAtIEFsdCBFc3QgNDBLCjkgTWFyY2ggQXBwcm92ZWQgUFJGIFJlY2VpdmVkCjQgTWFyY2ggLSBQMiAtIEFwcHJvdmVkIFJlcXVlc3QgUGVuZGluZyAoUFJGKSAtIEVCIFJlcXVlc3QgLSBEcmF3aW5ncyBSZXF1aXJlZA==","RATING":""} |  |  |  | PHASE00 | 2024-05-10 | 2024-08-08 | RODERICK NEVAY | nokuthula manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001064 | Absa Somerset East - New Coin Cage | Absa Somerset East - New Coin Cage |  |  | Region 2 | Eastern Cape | 76426X | 1000-71008-01 | Absa Somerset East-Njoli St-Somerset East | N | 2024-05-01 | 2024-12-30 |  | ASP-EC0411 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-03-05 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_014 | {"MANDT":"111","REFERENCE":90001064,"ONEVIEW":"76426X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-01-08","DATE08":"2025-01-29","DATE09":"2025-03-15","DATE10":"2025-03-31","DATE11":"2025-03-15","DATE12":"2025-03-15","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:243:21:45:45:45:25","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-01-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"OSBNYXJjaCBBcHByb3ZlZCBQUkYgUmVjZWl2ZWQgc2NvcGUgdG8gYmUgY2xhcmlmaWVkIGFzIG90aGVyIGVxdWlwbWVudCB0byBiZSByZW1vdmVkCjQgTWFyY2ggLSBQMiAtIEFwcHJvdmVkIFJlcXVlc3QgUGVuZGluZyAoUFJGKSAtIEVCIFJlcXVlc3QgLSBEcmF3aW5ncyBSZXF1aXJlZA==","RATING":""} |  |  |  | PHASE00 | 2024-05-31 | 2025-01-29 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001065 | Absa Malcomess Park - TTW Drop Safe | Absa Malcomess Park - New TTW Drop Safe |  |  | Region 2 | Eastern Cape | 78764X | 1000-71052-01 | Malcomess Park Shopping Centre-St. Peters Rd-East London | N | 2024-05-02 | 2024-12-30 |  | ASP-EC0412 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-05 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_013 | {"MANDT":"111","REFERENCE":90001065,"ONEVIEW":"78764X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-01-07","DATE08":"2025-01-28","DATE09":"2025-03-14","DATE10":"2025-03-31","DATE11":"2025-03-14","DATE12":"2025-03-14","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:242:21:45:45:45:25","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-01-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggUE0gZm9sbG93ZWQgdXAgd2l0aCBQbGFubmVyIHJlIGRyYXdpbmdzIHJlcXVpcmVkCjggTWFyY2ggUFJGIFJlY2VpdmVkIC0gRHJhd2luZ3MgcGVuZGluZyBmcm9tIEFic2EgUGxhbm5lciBFc3QgUjcwawo0IE1hcmNoIC0gUDIgLSBBcHByb3ZlZCBSZXF1ZXN0IFBlbmRpbmcgKFBSRikgLSBFQiBSZXF1ZXN0IC0gRHJhd2luZ3MgUmVxdWlyZWQ=","RATING":""} |  |  |  | PHASE00 | 2024-05-10 | 2025-01-07 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001066 | Absa Broadway Uitenhage - TTW Drop Safe | Absa Broadway Uitenhage - New TTW Drop Safe |  |  | Region 2 | Eastern Cape | 36206X | 1000-70986-01 | Broadway Building-Cnr Chase & Caledon St-Uitenhage | N | 2024-05-02 | 2024-12-30 |  | ASP-EC0413 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-05 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_010 | {"MANDT":"111","REFERENCE":90001066,"ONEVIEW":"36206X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-01-07","DATE08":"2025-01-28","DATE09":"2025-03-14","DATE10":"2025-03-31","DATE11":"2025-03-14","DATE12":"2025-03-14","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:242:21:45:45:45:25","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-01-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggRHJhd2luZyBvdXRzdGFuZGluZyBmcm9tIHBsYW5uZXIgZm9sbG93IHVwIE1haWwgU2VudAoxMSBNYXJjaCBBcHByb3ZlZCBQUkYgUmVjZWl2ZWQgLSBEcmF3aW5ncyBQZW5kaW5nIGZyb20gUGxhbm5lciBFc3QgUjcwawo0IE1hcmNoIC0gUDIgLSBBcHByb3ZlZCBSZXF1ZXN0IFBlbmRpbmcgKFBSRikgLSBFQiBSZXF1ZXN0IC0gRHJhd2luZ3MgUmVxdWlyZWQ=","RATING":""} |  |  |  | PHASE00 | 2024-05-20 | 2025-01-17 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001067 | Absa Bhisho Seta Bldg - Closing Off of Tellers | Absa Bhisho Seta Bldg - Closing Off of Tellers |  |  | Region 2 | Eastern Cape | 36267X | 1000-70989-01 | Bhisho Seta Building-Phalo Ave-Bisho | N | 2024-05-02 | 2024-12-30 |  | ASP-EC0414 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-05 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_011 | {"MANDT":"111","REFERENCE":90001067,"ONEVIEW":"36267X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-01-07","DATE08":"2025-01-28","DATE09":"2025-03-14","DATE10":"2025-03-31","DATE11":"2025-03-14","DATE12":"2025-03-14","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:242:21:45:45:45:25","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-01-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggLSBBcHByb3ZlZCBSZXF1ZXN0IFBlbmRpbmcgKFBSRikgLSBFQiBSZXF1ZXN0IC0gRHJhd2luZ3MgUmVxdWlyZWQgLSBFc3QgLSBSNjBrCjQgTWFyY2ggLSBBcHByb3ZlZCBSZXF1ZXN0IFBlbmRpbmcgKFBSRikgLSBFQiBSZXF1ZXN0IC0gRHJhd2luZ3MgUmVxdWlyZWQgLSBFc3QgLSBSNjBr","RATING":""} |  |  |  | PHASE00 | 2024-05-10 | 2025-01-07 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001068 | Absa Stone Towers - New Replacement External Sign | Absa Stone Towers - New Replacement External Sign |  |  | Region 2 | Eastern Cape | 78247X | 1000-71463-01 | Stone Towers Shopping Centre-Alexandra Rd-King Williams Town | N | 2024-05-02 | 2024-12-30 |  | ASP-EC0415 | REL BUDG AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-05 | D | 38100.54 |  | 100 | 2024-03-28 | 2024-04-04 | 38100.54 | Absa Ref : 240402_016 Reprioritised | {"MANDT":"111","REFERENCE":90001068,"ONEVIEW":"78247X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-01-07","DATE08":"2025-01-28","DATE09":"2025-03-14","DATE10":"2025-03-31","DATE11":"2025-03-14","DATE12":"2025-03-14","PROG01":0,"PROG02":60,"PROG03":0,"PROG04":10,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:242:21:45:45:45:25","PROGRESS":3,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-01-07","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggLSBMYXRlIHdpdGhkcmF3bCAtIE5vdCBGdWxsIHJlcGxhY2VtZW50IC0gdG8gYmUgY3V0LW91dCByYXRoZXIgdGhhbiAzRCBzaWduIC0gRGVzaWduIGFuZCBDb3N0IHRvIGJlIHJldmlld2VkCihUaGlzIGlzIEJBVSDigJMgUmVwdXRhdGlvbmFsIGFuZCBjYW5ub3QgYmUgY29tcHJvbWlzZWQpIAoxNSBNYXJjaCBUbyBiZSBzdWJtaXR0ZWQgZm9yIENCMTAgLSBFc3QgUjQwSwoxMSBNYXJjaCAtIFJGUSBjb21wbGV0ZWQgLSB0byBiZSBzdWJtaXR0ZWQgQ0IwOQo5IE1hcmNoIEFwcHJvdmVkIFBSRiBSZWNlaXZlZAo0IE1hcmNoIC0gUDIgLSBBcHByb3ZlZCBSZXF1ZXN0IFBlbmRpbmcgKFBSRikgIC0gRUIgUmVxdWVzdA==","RATING":""} |  |  | C000152987 | PHASE06 | 2024-05-01 | 2024-05-15 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-04-08 | 33130.9 | 0 |  |  | C000152987 | 33130.9 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001069 | Pretoria Campus refurbishment Cabinets | Pretoria Campus refurbishment Cabinets |  |  | Region 1 |  | 22896X | 1000-70079-01 | 270 Maggs street -Pretoria | Y | 2024-03-05 | 2024-04-08 |  | ASP-GN0246 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001069,"ONEVIEW":"22896X","DATE01":"2023-12-26","DATE02":"2024-01-02","DATE03":"2024-01-23","DATE04":"2024-01-30","DATE05":"2024-02-20","DATE06":"2024-03-05","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-05 | 2024-04-08 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001070 | Pretoria Campus Install flammable storage | Pretoria Campus Supply and Install container storage for storing flammable goods with shelving and rotational ventilation on the top and louvers. |  |  | Region 1 |  | 22896X | 1000-70079-01 | 270 Maggs street -Pretoria | N | 2024-03-05 | 2024-04-09 |  | ASP-GN0247 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001070,"ONEVIEW":"22896X","DATE01":"2023-12-26","DATE02":"2024-01-02","DATE03":"2024-01-23","DATE04":"2024-01-30","DATE05":"2024-02-20","DATE06":"2024-03-05","DATE07":"2024-04-09","DATE08":"2024-04-30","DATE09":"2024-06-14","DATE10":"2024-06-30","DATE11":"2024-06-14","DATE12":"2024-06-14","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-04-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-05 | 2024-04-09 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001071 | Pretoria Campus enclose garden refusal | Pretoria Campus enclose garden refusal |  |  | Region 1 | Gauteng | 22896X | 1000-70079-01 | 270 Maggs Street Pretoria Campus Watloo | N | 2024-03-05 | 2024-04-09 |  | ASP-GN0248 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001071,"ONEVIEW":"22896X","DATE01":"2023-12-26","DATE02":"2024-01-02","DATE03":"2024-01-23","DATE04":"2024-01-30","DATE05":"2024-02-20","DATE06":"2024-03-05","DATE07":"2024-04-09","DATE08":"2024-04-30","DATE09":"2024-06-14","DATE10":"2024-06-30","DATE11":"2024-06-14","DATE12":"2024-06-14","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-04-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-05 | 2024-04-09 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001072 | Pretoria Campus Gas cage and 2X9 kg cyli | Pretoria Campus Gas cage and 2X9 kg cylinder |  |  | Region 1 | Gauteng | 22896X | 1000-70079-01 | 270 Maggs St-Pretoria Campus Watloo | N | 2024-03-05 | 2024-04-09 |  | ASP-GN0249 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001072,"ONEVIEW":"22896X","DATE01":"2023-12-26","DATE02":"2024-01-02","DATE03":"2024-01-23","DATE04":"2024-01-30","DATE05":"2024-02-20","DATE06":"2024-03-05","DATE07":"2024-04-09","DATE08":"2024-04-30","DATE09":"2024-06-14","DATE10":"2024-06-30","DATE11":"2024-06-14","DATE12":"2024-06-14","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-04-09","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-05 | 2024-04-09 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001073 | Absa 32 Voortrekker - Dilaps Phase 2 | Absa 32 Voortrekker - Dilaps Phase 2 |  |  | Region 2 | Western Cape | 78126X | 1000-70888-01 | Absa 32 Voortrekker Road-Voortrekker Rd-Bellville | N | 2024-04-01 | 2024-12-31 |  | ASP-WC0364 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-05 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001073,"ONEVIEW":"78126X","DATE01":"2024-03-01","DATE02":"2024-03-08","DATE03":"2024-03-29","DATE04":"2024-04-05","DATE05":"2024-04-26","DATE06":"2024-05-10","DATE07":"2025-02-08","DATE08":"2025-03-01","DATE09":"2025-04-15","DATE10":"2025-04-30","DATE11":"2025-04-15","DATE12":"2025-04-15","PROG01":0,"PROG02":80,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:274:21:45:45:45:24","PROGRESS":4,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-10","FORECAST_END":"2025-02-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggLSBDb3N0IHRvIGF1Y3Rpb24gcG9zc2libHkgbm90IGZlYXNpYmxlIGR1ZSB0byBjb3N0IHRvIGZpcnN0bHkgcmVtb3ZlIGZyb20gc2l0ZQoxMSBNYXJjaCAtIEF1Y3Rpb24gY29zdHMgYW5kIEV4cGVjdGVkIGluY29tZSByZWNlaXZlZCwgcGFjayB0byBiZSBwcmVzZW50ZWQgZm9yIHN1cHBvcnQsIFBNIHRvIGNvbmZpcm0gd2l0aCBFbmdpbmVlcmluZyByZSBVUFMncyBpdGVtcwo0IE1hcmNoIC0gRnJpZGdlcywgTWljcm93YXZlcywgV2hpdGUgQm9hcmRzLCA1MCBDaGFpcnMsIEZpcnN0IGFpZCBCb3hlcyB0byBCUCwgNCBFdmFjdWF0aW9uIENoYWlycyB0byBMb3dlciBMb25nLiAoNDQxNydzIHRvIGJlIGRvbmUgYnkgRk0pLiBSZW1haW5kZXIgZnVybml0dXJlLCBCZXRobGVoZW0gZnVybml0dXJlIHRvIGJlIGNvbGxlY3RlZCBkYXRlIHRvIGJlIGNvbmZpcm1lZC4gTGlzdCB0byBiZSBzaGFyZWQgb2YgcmVtYWluaW5nIGl0ZW1zIHRvIGJlIGF1Y3Rpb25lZCAoQ29zdCB2cyBwb3RlbnRpYWwgaW5jb21lKSBvciB0byBiZSBsZWZ0IGFuZCBzb2xkIHdpdGggdGhlIGJ1aWxkaW5nLg==","RATING":""} |  |  |  | PHASE00 | 2024-05-10 | 2025-02-08 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001074 | Pretoria Campus Block A,VAMM storeroom | Pretoria Campus Block A,VAMM storeroom |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2024-03-05 | 2024-04-08 |  | ALP-GN0016 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-05 | 2024-04-08 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000142619 | 1561584.35 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001075 | Pretoria Campus supply and Install drain | Pretoria Campus supply and Install drainage system |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2024-03-05 | 2024-04-08 |  | ALP-GN0017 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001075,"ONEVIEW":"22491X","DATE01":"2024-04-30","DATE02":"2024-05-07","DATE03":"2024-05-28","DATE04":"2024-06-04","DATE05":"2024-06-25","DATE06":"2024-07-09","DATE07":"2024-08-12","DATE08":"2024-09-02","DATE09":"2024-10-17","DATE10":"2024-10-31","DATE11":"2024-10-17","DATE12":"2024-10-17","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:34:21:45:45:45:17","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-07-09","FORECAST_END":"2024-08-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"UkZRIGluIHByb2dyZXNzIA==","RATING":"Low"} |  |  |  | PHASE00 | 2024-07-09 | 2024-08-12 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001076 | Pretoria Campus Block A Pink toilet lobb | Pretoria Campus Block A Pink toilet lobby |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2024-03-05 | 2024-04-08 |  | ALP-GN0018 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 | Approved at CIP 2024 | 100 |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001076,"ONEVIEW":"22491X","DATE01":"2023-12-26","DATE02":"2024-01-02","DATE03":"2024-01-23","DATE04":"2024-01-30","DATE05":"2024-02-20","DATE06":"2024-03-05","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-03-05 | 2024-04-08 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001077 | Pretoria Campus Replace Hydro taps x 4 | Pretoria Campus Replace Hydro taps x 4 |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria | N | 2024-03-05 | 2024-04-08 |  | ALP-GN0019 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  | F |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001077,"ONEVIEW":"22491X","DATE01":"2023-12-26","DATE02":"2024-01-02","DATE03":"2024-01-23","DATE04":"2024-01-30","DATE05":"2024-02-20","DATE06":"2024-03-05","DATE07":"2024-04-08","DATE08":"2024-04-29","DATE09":"2024-06-13","DATE10":"2024-06-30","DATE11":"2024-06-13","DATE12":"2024-06-13","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-05","FORECAST_END":"2024-04-08","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-07-02 | 2024-08-05 | CHRISTOPHER MPOFU | Obakeng Phuti | 40129444 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001078 | Pretoria Campus UPS Battery Replacement | Pretoria Campus UPS Battery Replacement |  |  | Region 1 |  | 22491X | 1000-70065-01 | Absa Pretoria Campus Block A - M-Maggs St-Pretoria |  | 2024-03-05 | 2024-04-08 |  | ALP-GN0020 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-05 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-05-13 | 2024-06-16 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001079 | Absa Albertinia - Waterproofing | Absa Albertinia - Waterproofing |  |  | Region 2 | Eastern Cape | 77688X | 1000-71033-01 | Absa Albertinia-Hoof St-Albertinia |  | 2024-05-01 | 2024-11-30 |  | ASP-EC0416 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  |  |  | CEASARS | 2024-03-06 | D | 282476.23 |  | 40 | 2024-03-13 |  | 0 | Absa Ref : Opex 6 March - Project changed to Small Project - was - ALP-EC0024 - Now - ASP-EC0416 19 March Declined as part of the Asbestos remediation programme, any additional items not part of the Asbestos roof to be resubmitted | {"MANDT":"111","REFERENCE":90001079,"ONEVIEW":"77688X","DATE01":"2024-02-21","DATE02":"2024-02-26","DATE03":"2024-03-13","DATE04":"2024-03-20","DATE05":"2024-03-29","DATE06":"2024-04-12","DATE07":"2024-11-11","DATE08":"2024-12-02","DATE09":"2025-01-16","DATE10":"2025-01-31","DATE11":"2025-01-16","DATE12":"2025-01-16","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"373:5:16:7:9:14:213:21:45:45:45:26","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-12","FORECAST_END":"2024-11-11","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MDggQXByaWwgLSBQTSB0byBjb25maXJtIHdpdGggY29tcGxpYW5jZSByZSBBc2Jlc3RvcyBSb29mCjA0IEFwcmlsIERlY2xpbmVkIGFzIHBhcnQgb2YgdGhlIEFzYmVzdG9zIHJlbWVkaWF0aW9uIHByb2dyYW1tZSwgYW55IGFkZGl0aW9uYWwgaXRlbXMgbm90IHBhcnQgb2YgdGhlIEFzYmVzdG9zIHJvb2YgdG8gYmUgcmVzdWJtaXR0ZWQKIDE5IE1hcmNoIERlY2xpbmVkIGFzIHBhcnQgb2YgdGhlIEFzYmVzdG9zIHJlbWVkaWF0aW9uIHByb2dyYW1tZSwgYW55IGFkZGl0aW9uYWwgaXRlbXMgbm90IHBhcnQgb2YgdGhlIEFzYmVzdG9zIHJvb2YgdG8gYmUgcmVzdWJtaXR0ZWQKMTQgTWFyY2ggLSBTdWJtaXR0ZWQgZm9yIENCMDkKMTEgTWFyY2ggLSBSRlEgY29tcGxldGVkIC0gQkMgaW4gUHJvZ3Jlc3MKNiBNYXJjaCAtIFByb2plY3QgY2hhbmdlZCB0byBTbWFsbCBQcm9qZWN0IC0gd2FzIC0gQUxQLUVDMDAyNCAtICBOb3cgLSBBU1AtRUMwNDE2CjQgTWFyY2ggUXVvdGVzIHJlY2VpdmVkIGFkanVkaWNhdGlvbiBpbiBwcm9ncmVzcwoyNiBGZWIgLSBTaXRlIHZpc2l0IGNvbmR1Y3RlZCAyMiBGZWIgUXVvdGVzIGR1ZSAxIE1hcmNoCjIyIEZlYiAtIFNpdGUgTWVldGluZyBiZWluZyBjb25kdWN0ZWQgMjIgRmViIFNjb3BlIGFuZCBSRlEgdG8gZm9sbG93CjE5IEZlYiAtIFNpdGUgdmlzaXQgd2l0aCBFbmdpbmVlcmluZyAyMiBGZWIKOSBGZWIgLSBNYWlsIHNlbnQgdG8gZm9sbG93IHVwIFdpdGggUHJvY3VyZW1lbnQKMDggRmViIFNpdGUgdmlzaXQgc2NoZWR1bGVkIGZvciAyMiBGZWIKNyBGZWIgTWFpbCB0byBwcm9jdXJlbWVudCByZSBWZW5kb3IgU2VsZWN0aW9uIHNlbnQKNSBGZWIgUm91bmQgdHJpcCBwbGFubmVkIDIybmQgMjMgRmViCjI1IEphbiAtIFBNIHRvIGFycmFuZ2Ugcm91bmQgdHJpcCB0byBpbnNwZWN0IGFuZCBkZXRlcm1pbmUgc2NvcGUgYW5kIHNwZWNpZmljYXRpb25zCjIyIEphbiAtIFBtIHRvIGVuZ2FnZSByZSB3YXRlcnByb29maW5nIFNwZWMgYW5kIFZlbmRvcnMgUGxhbm5lZCAxIEp1bHkgdG8gMzAgQXVn","RATING":""} |  |  |  | PHASE04 | 2024-04-12 | 2024-11-11 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001080 | Absa Uniondale - Waterproofing | Absa Uniondale - Waterproofing |  |  | Region 2 | Eastern Cape | 78140X | 1000-71039-01 | Absa Uniondale-Voortrekker St-Uniondale | N | 2024-05-01 | 2024-11-30 |  | ASP-EC0417 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | CEASARS | 2024-03-06 | D | 0 |  | 20 |  |  | 0 | 6 March - Project changed to Small Project - was - ALP-EC0029 - Now - ASP-EC0417 | {"MANDT":"111","REFERENCE":90001080,"ONEVIEW":"78140X","DATE01":"2024-02-21","DATE02":"2024-02-28","DATE03":"2024-03-20","DATE04":"2024-03-27","DATE05":"2024-04-17","DATE06":"2024-05-01","DATE07":"2024-11-30","DATE08":"2024-12-21","DATE09":"2025-02-04","DATE10":"2025-02-28","DATE11":"2025-02-04","DATE12":"2025-02-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-01","FORECAST_END":"2024-11-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2024-05-10 | 2024-05-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001081 | Smart electrical and water meters rollou | Smart electrical and water meters rollou |  |  | Region 1 |  |  |  | Building not in Real Estate Database |  | 2024-03-06 | 2024-03-31 |  | ABS-G00013 | CRTD SETC: |  | false | false |  | Mukuru Wesigye |  |  | 2024 |  |  |  | DUPREEZK | 2024-03-06 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-06 | 2024-03-31 | ONISMS MANYEWE | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  | C000152391 | 3867978.37 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001082 | Absa Vrede-Minor Works | Absa Vrede-Minor Works |  |  | Region 3 |  | 77122X | 1000-71531-01 | Absa Vrede-Church St-Vrede |  | 2024-04-04 | 2024-05-30 |  | ASP-CR0564 | CRTD RESA SETC: |  | false | false |  | Liso Jordan |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-07 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-04 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001083 | Absa Vryburg -External Signage | Absa Vryburg -External Signage |  |  | Region 3 |  | 77745X | 1000-71604-01 | Vryburg-Market St-Vryburg |  | 2024-04-26 | 2024-05-30 |  | ASP-CR0565 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-26 | 2024-05-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001084 | Absa Dwarsloop Mall -New Desk | Absa Dwarsloop Mall -New Desk |  |  | Region 3 |  | 37198X | 1000-77509-01 | Dwarsloop Mall |  | 2024-04-05 | 2024-05-29 |  | ASP-MP0184 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-05 | 2024-05-29 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000153644 | 161608.08 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001085 | Absa Tonga - New Desk | Absa Tonga - New Desk |  |  | Region 3 |  | 37188X | 1000-77506-01 | Tonga Mall |  | 2024-04-04 | 2024-05-30 |  | ASP-MP0185 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-04 | 2024-05-30 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000153642 | 55462.16 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001086 | Absa Mall@Emba - Tube New System | Absa Mall@Emba - Tube New System |  |  | Region 3 |  | 78542X | 1000-70653-01 | Mall@Emba-Cnr Old Provincial & Embalenhle Rd-Secunda |  | 2024-04-02 | 2024-05-30 |  | ASP-MP0186 | REL BUDG AVAC SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-11 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-02 | 2024-05-30 | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  | C000152185 | 128184.69 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001087 | Absa Brackenfell ShopCentre - Blinds | Absa Brackenfell ShopCentre - Blinds |  |  | Region 2 | Western Cape | 77848X | 1000-70862-01 | Brackenfell Shopping Centre-Old Paarl Rd-Brackenfell | N | 2024-04-29 | 2024-06-30 |  | ASP-WC0365 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-03-11 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_003 | {"MANDT":"111","REFERENCE":90001087,"ONEVIEW":"77848X","DATE01":"2024-03-11","DATE02":"2024-03-18","DATE03":"2024-04-08","DATE04":"2024-04-15","DATE05":"2024-05-06","DATE06":"2024-05-20","DATE07":"2024-07-21","DATE08":"2024-08-11","DATE09":"2024-09-25","DATE10":"2024-09-30","DATE11":"2024-09-25","DATE12":"2024-09-25","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:62:21:45:45:45:26","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-20","FORECAST_END":"2024-07-21","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggUE0gdG8gY29uZmlybSB2aWEgSWxhbmEgaWYgcm9sbGVyIGJsaW5kcyBhY2NlcHRhYmxlIHdpdGggU3BlY2lmaWNhdGlvbiAtIEVzdCBSNy41awoxMSBNYXJjaCBQUkYgcmVjZWl2ZWQsIFBNIHRvIGNoZWNrIHJlIFNwZWNpZmljYXRpb25zIGFsbG93ZWQ=","RATING":""} |  |  |  | PHASE00 | 2024-06-12 | 2024-08-13 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001088 | Absa Mall of Africa Dilaps | Absa Mall of Africa Dilaps |  |  | Region 1 |  | 36105X | 1000-70182-01 | Mall Of Africa-Magwa Cres-Midrand |  | 2024-03-12 | 2024-04-12 |  | ASP-GN0250 | REL BUDG AVAC RESA SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-12 | D | 130717.19 |  |  | 2024-03-14 | 2024-03-15 | 130717.19 |  | {"MANDT":"111","REFERENCE":90001088,"ONEVIEW":"36105X","DATE01":"2024-01-02","DATE02":"2024-01-09","DATE03":"2024-01-30","DATE04":"2024-02-06","DATE05":"2024-02-27","DATE06":"2024-03-12","DATE07":"2024-04-12","DATE08":"2024-05-03","DATE09":"2024-06-17","DATE10":"2024-06-30","DATE11":"2024-06-17","DATE12":"2024-06-17","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-12","FORECAST_END":"2024-04-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  | C000148463 | PHASE07 | 2024-03-13 | 2024-04-13 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 |  |  |  |  | 2024-03-12 | 113667.12 | 0 |  |  | C000148463 | 113667.12 |  | 10046.4 |  | 0 | 0 |  | 0 |  | 0
90001089 | Absa Ithala Centre (Manguzi)-Furniture | Absa Ithala Centre (Manguzi)-Furniture |  |  | Region 3 |  | 77685X | 1000-71188-01 | Ithala Centre Manguzi-Main Rd-Manguzi |  | 2024-04-24 | 2024-06-06 |  | ASP-KZ0283 | REL BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-24 | 2024-06-06 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000151208 | 53109.84 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001090 | Absa Bluff Hillside- Furniture Replaceme | Absa Bluff Hillside- Furniture Replaceme |  |  | Region 3 |  | 77346X | 1000-71167-01 | Bluff Hillside Mall-Cnr Tara & Greys Inn Rd-Bluff |  | 2024-04-05 | 2024-06-06 |  | ASP-KZ0284 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-05 | 2024-06-06 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001091 | Absa Port Edward - Minor Works | Absa Port Edward - Minor Works |  |  | Region 3 |  | 77893X | 1000-71199-01 | Port Edward Mall-Owen Ellis Dr-Port Edward |  | 2024-04-05 | 2024-06-06 |  | ASP-KZ0285 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-05 | 2024-06-06 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001092 | Absa 145 Murchison - Security Upgrades | Absa 145 Murchison - Security Upgrades |  |  | Region 3 |  | 77798X | 1000-71619-01 | Absa 145 Murchison Street-Murchison St-Ladysmith |  | 2024-04-05 | 2024-06-06 |  | ASP-KZ0286 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-05 | 2024-06-06 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001093 | Mall@Reds Expansion Joints | Mall@Reds Expansion Joints |  |  | Region 1 |  | 36105X | 1000-70182-01 | Mall Of Africa-Magwa Cres-Midrand |  | 2024-03-13 | 2024-04-12 |  | ASP-GN0251 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-13 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-13 | 2024-04-12 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000148552 | 11577 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001094 | Absa Boulders - Reinstatement | Absa Boulders - Reinstatement |  |  | Region 1 |  | 78425X | 1000-70404-01 | Atm Boulders Shopping Centre-Cnr Alexandria & Tonette St-Midrand |  | 2024-03-13 | 2024-04-12 |  | ALP-GN0021 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-13 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001094,"ONEVIEW":"22491X","DATE01":"2024-01-03","DATE02":"2024-01-10","DATE03":"2024-01-31","DATE04":"2024-02-07","DATE05":"2024-02-28","DATE06":"2024-03-13","DATE07":"2024-04-12","DATE08":"2024-05-03","DATE09":"2024-06-17","DATE10":"2024-06-30","DATE11":"2024-06-17","DATE12":"2024-06-17","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-13","FORECAST_END":"2024-04-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE03 | 2024-04-08 | 2024-05-08 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001095 | Absa Boulders - Reinstatement | Absa Boulders - Reinstatement |  |  | Region 1 |  | 78425X | 1000-70404-01 | Atm Boulders Shopping Centre-Cnr Alexandria & Tonette St-Midrand |  | 2024-03-14 | 2024-04-12 |  | ALP-GN0022 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-14 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001095,"ONEVIEW":"22491X","DATE01":"2024-01-04","DATE02":"2024-01-11","DATE03":"2024-02-01","DATE04":"2024-02-08","DATE05":"2024-02-29","DATE06":"2024-03-14","DATE07":"2024-04-12","DATE08":"2024-05-03","DATE09":"2024-06-17","DATE10":"2024-06-30","DATE11":"2024-06-17","DATE12":"2024-06-17","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-14","FORECAST_END":"2024-04-12","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE03 | 2024-04-11 | 2024-05-10 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001096 | Absa Ga-Rankuwa Replace frosting on shop | Absa Ga-Rankuwa Replace frosting on shop |  |  | Region 1 |  | 76686X | 1000-70313-01 | Ga-Rankuwa Shopping Centre-Manyope Highway St-Pretoria |  | 2024-03-15 | 2024-03-15 |  | ASP-GN0252 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-15 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001096,"ONEVIEW":"36105X","DATE01":"2024-01-05","DATE02":"2024-01-12","DATE03":"2024-02-02","DATE04":"2024-02-09","DATE05":"2024-03-01","DATE06":"2024-03-15","DATE07":"2024-03-15","DATE08":"2024-04-05","DATE09":"2024-05-20","DATE10":"2024-05-31","DATE11":"2024-05-20","DATE12":"2024-05-20","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-15","FORECAST_END":"2024-03-15","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE03 | 2024-05-16 | 2024-05-16 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000148463 | 113667.12 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001097 | Alice Lane North install Patio Furniture | Alice Lane North install Patio Furniture |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-15 | 2024-04-15 |  | ASP-GS0815 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-15 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-15 | 2024-04-15 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001098 | Absa Alice Lane North Client Suites Artw | Absa Alice Lane North Client Suites Artw |  |  | Region 1 |  | 79271X | 1000-71418-01 | 13 Top Road-Top Rd-Boksburg |  | 2024-03-15 | 2024-04-15 |  | ALP-GS0100 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-15 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-15 | 2024-04-15 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001099 | Various retail sites- Surge Protectors | Various retail sites- Surge Protectors |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-03-28 | 2024-12-13 |  | ALP-N00077 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2024 |  |  |  | LOUISR | 2024-03-15 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-12-13 | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001100 | Absa Bloemfontein CBD-Install BMS System | Absa Bloemfontein CBD-Install BMS System |  |  | Region 3 |  | 78754X | 1000-71596-01 | Bloemfontein CBD-Charlotte Maxeke St-Bloemfontein |  | 2024-04-30 | 2024-05-30 |  | ASP-CR0566 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-30 | 2024-05-30 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001101 | Absa Renbro SC Water Filtration system | Absa Renbro SC Water Filtration system |  |  | Region 1 |  | 37152X | 1000-77429-01 | Hammanskraal Renbro Shopping Centre |  | 2024-03-18 | 2024-04-16 |  | ASP-GN0253 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001101,"ONEVIEW":"36105X","DATE01":"2024-01-08","DATE02":"2024-01-15","DATE03":"2024-02-05","DATE04":"2024-02-12","DATE05":"2024-03-04","DATE06":"2024-03-18","DATE07":"2024-04-16","DATE08":"2024-05-07","DATE09":"2024-06-21","DATE10":"2024-06-30","DATE11":"2024-06-21","DATE12":"2024-06-21","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-18","FORECAST_END":"2024-04-16","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE03 | 2024-05-06 | 2024-06-04 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  | C000148463 | 113667.12 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001102 | Absa Jubilee Water Filtration systems | Absa Jubilee Water Filtration systems |  |  | Region 1 |  | 35109X | 1000-70088-01 | Jubilee Mall-Cnr Jubilee & Harry Gwala Rd-Hammanskraal |  | 2024-03-18 | 2024-05-13 |  | ASP-GN0254 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE03 | 2024-05-20 | 2024-07-15 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001103 | Absa Rayton Plaza Partition dividers bet | Absa Rayton Plaza Partition dividers bet |  |  | Region 1 |  | 78058X | 1000-70387-01 | Rayton Park Plaza-Cnr Theurnicht & Alley St-Rayton |  | 2024-03-18 | 2024-04-23 |  | ASP-GN0255 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001103,"ONEVIEW":"36105X","DATE01":"2024-01-08","DATE02":"2024-01-15","DATE03":"2024-02-05","DATE04":"2024-02-12","DATE05":"2024-03-04","DATE06":"2024-03-18","DATE07":"2024-04-23","DATE08":"2024-05-14","DATE09":"2024-06-28","DATE10":"2024-06-30","DATE11":"2024-06-28","DATE12":"2024-06-28","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-18","FORECAST_END":"2024-04-23","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-06-11 | 2024-07-17 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001104 | Absa Cosmo Mall Repainting, carpets and | Absa Cosmo Mall Repainting, carpets and |  |  | Region 1 |  | 36105X | 1000-70182-01 | Mall Of Africa-Magwa Cres-Midrand |  | 2024-03-18 | 2024-05-22 |  | ASP-GN0256 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-18 | 2024-05-22 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001105 | Centurion bldg Marketing frosting on Sho | Centurion bldg Marketing frosting on Sho |  |  | Region 1 |  | 77427X | 1000-70368-01 | Centurion Mall-Heuwel Ave-Centurion |  | 2024-03-18 | 2024-05-30 |  | ASP-GN0257 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 |  | {"MANDT":"111","REFERENCE":90001105,"ONEVIEW":"36105X","DATE01":"2024-01-08","DATE02":"2024-01-15","DATE03":"2024-02-05","DATE04":"2024-02-12","DATE05":"2024-03-04","DATE06":"2024-03-18","DATE07":"2024-05-30","DATE08":"2024-06-20","DATE09":"2024-08-04","DATE10":"2024-08-31","DATE11":"2024-08-04","DATE12":"2024-08-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-03-18","FORECAST_END":"2024-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE03 | 2024-04-14 | 2024-06-26 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001106 | Absa Jubilee Mall Walk off mat at front | Absa Jubilee Mall Walk off mat at front |  |  | Region 1 |  | 35109X | 1000-70088-01 | Jubilee Mall-Cnr Jubilee & Harry Gwala Rd-Hammanskraal |  | 2024-03-18 | 2024-04-23 |  | ASP-GN0258 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE03 | 2024-05-11 | 2024-06-16 | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001107 | Absa Towers West 3 x Hydrotaps | Absa Towers West 3 x Hydrotaps |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-18 | 2024-05-31 |  | ASP-GS0816 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-18 | 2024-05-31 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001108 | Absa Trade Route MInor Works | Absa Trade Route MInor Works |  |  | Region 1 |  | 77216X | 1000-70356-01 | Trade Route Mall Centre-Cnr K43 & Nirvana Dr-Lenasia |  | 2024-03-18 | 2024-04-23 |  | ASP-GS0817 | CRTD SETC: |  | false | false |  | Christopher Mpofu |  |  | 2024 |  |  |  | GAMIETR | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-18 | 2024-04-23 | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001109 | Absa Scottburgh - Temporary Generator | Absa Scottburgh - Temporary Generator |  |  | Region 3 |  | 77691X | 1000-71189-01 | Scottburgh Mall-Cnr Old Main Rd & Margaret Ave-Scottburgh |  | 2024-03-28 | 2024-04-03 |  | ASP-KZ0287 | REL BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-18 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-04-03 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000149951 | 81326.01 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001110 | Absa Oude Bloemhof - Roller shutter door | Absa Oude Bloemhof - Roller shutter door |  |  | Region 2 | Western Cape | 77946X | 1000-70866-01 | Oude Bloemhof Building-Cnr Van Ryneveld & Plein St-Stellenbosch | N | 2024-04-15 | 2024-06-30 |  | ASP-WC0366 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-18 | D | 158099.86 |  | 100 | 2024-03-22 | 2024-03-28 | 158099.86 | Absa Ref : TBA | {"MANDT":"111","REFERENCE":90001110,"ONEVIEW":"77946X","DATE01":"2024-03-05","DATE02":"2024-03-14","DATE03":"2024-03-22","DATE04":"2024-03-29","DATE05":"2024-03-28","DATE06":"2024-05-04","DATE07":"2024-05-05","DATE08":"2024-05-26","DATE09":"2024-07-10","DATE10":"2024-07-31","DATE11":"2024-07-10","DATE12":"2024-07-10","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:9:8:7:-1:37:1:21:45:45:45:26","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-04","FORECAST_END":"2024-05-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggUGFjayBTZW50IHRvIFZQIHN1cHBvcnQgYW5kIEJ1ZGdldCBRdWVyeSBhcyB0byBiZSBzdWJtaXR0ZWQgQ0IxMAoxOCBNYXJjaCAtICBUbyBiZSBmdW5kZWQgYnkgQ29ycCBGYWJyaWMgKy0gUjE3NWsKIDExIE1hcmNoIHRvIGJlIGZ1bmRlZCBieSBDb3JwIEZhYnJpYyArLSBSMTUwayAtIFJGUSBpbiBwcm9ncmVzcyBmb3IgSGlnaCBGcmVxdWVuY3kgRG9vcgo1IE1hcmNoIC0gUFJGIHJlY2VpdmVkIGZyb20gRU5H","RATING":""} |  |  | C000151714 | PHASE06 | 2024-04-22 | 2024-04-26 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-04-02 | 137478.14 | 0 |  |  | C000151714 | 137478.14 |  | 7449.99 |  | 0 | 0 |  | 0 |  | 0
90001111 | Absa De Doorns - Mesh Fence | Absa De Doorns - Mesh Fence |  |  | Region 2 | Western Cape | 78111X | 1000-70885-01 | Absa De Doorns-Voortrekker Rd-De Doorns | N | 2024-04-15 | 2024-07-31 |  | ASP-WC0367 | CRTD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-18 | D | 117655 |  | 40 | 2024-04-04 |  | 0 | Absa Ref : 240402_004 Reprioritised | {"MANDT":"111","REFERENCE":90001111,"ONEVIEW":"78111X","DATE01":"2024-03-12","DATE02":"2024-03-19","DATE03":"2024-04-09","DATE04":"2024-04-16","DATE05":"2024-05-07","DATE06":"2024-05-21","DATE07":"2024-09-05","DATE08":"2024-09-26","DATE09":"2024-11-10","DATE10":"2024-11-30","DATE11":"2024-11-10","DATE12":"2024-11-10","PROG01":0,"PROG02":100,"PROG03":60,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:7:21:7:21:14:107:21:45:45:45:26","PROGRESS":7,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-21","FORECAST_END":"2024-09-05","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MTggTWFyY2ggU2l0ZSB2aXNpdCBiZWluZyBjb25kdWN0ZWQgMTggTWFyY2ggLSBFc3QgLSBSNDUwMDAKMTIgTWFyY2ggLSBQUkYgcmVjZWl2ZWQ=","RATING":""} |  |  |  | PHASE04 | 2024-04-25 | 2024-08-10 | RODERICK NEVAY | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001112 | Alice Lane South create space for additi | Alice Lane South create space for additi |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-19 | 2024-04-23 |  | ASP-GS0818 | REL BUDG AVAC SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-19 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-19 | 2024-04-23 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000151319 | 144745.15 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001113 | Absa Windermere-Replace HVAC in ATM Room | Absa Windermere-Replace HVAC in ATM Room |  |  | Region 3 |  | 78193X | 1000-71216-01 | Windermere Shopping Centre-Windermere Rd-Durban |  | 2024-04-12 | 2024-04-30 |  | ASP-KZ0288 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-19 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-12 | 2024-04-30 | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001114 | Absa 145 Murchison-External Refurbishmen | Absa 145 Murchison-External Refurbishmen |  |  | Region 3 |  | 77798X | 1000-71619-01 | Absa 145 Murchison Street-Murchison St-Ladysmith |  | 2024-04-25 | 2024-05-30 |  | ASP-KZ0289 | REL BUDG AVAC SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-20 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-04-25 | 2024-05-30 | NANDE MAQUBELA | Jaunita Van Coller | 0 | [5 empty] | 0 | 0 |  |  | C000152194 | 420295.65 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001115 | Absa Malmesbury - External Refurb | Absa Malmesbury - External Refurb |  |  | Region 2 | Western Cape | 78113X | 1000-70887-01 | Absa Malmesbury-Voortrekker Rd-Malmesbury | N | 2024-04-20 | 2024-07-31 |  | ASP-WC0368 | CRTD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-20 | D | 455181.93 |  | 40 | 2024-03-22 |  | 0 | Absa Ref - Opex | {"MANDT":"111","REFERENCE":90001115,"ONEVIEW":"78113X","DATE01":"2024-02-10","DATE02":"2024-02-17","DATE03":"2024-03-09","DATE04":"2024-03-16","DATE05":"2024-04-06","DATE06":"2024-04-20","DATE07":"2024-07-31","DATE08":"2024-08-21","DATE09":"2024-10-05","DATE10":"2024-10-31","DATE11":"2024-10-05","DATE12":"2024-10-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-20","FORECAST_END":"2024-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2024-05-01 | 2024-06-15 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001116 | Absa Bonnievale - External Refurb | Absa Bonnievale - External Refurb |  |  | Region 2 | Western Cape | 77671X | 1000-70842-01 | Absa Bonnievale-Main Rd-Bonnievale | N | 2024-04-22 | 2024-07-31 |  | ASP-WC0369 | CRTD AVAC RESA: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-20 | D | 335399.8 |  | 40 | 2024-03-22 |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001116,"ONEVIEW":"77671X","DATE01":"2024-02-12","DATE02":"2024-03-04","DATE03":"2024-03-20","DATE04":"2024-03-27","DATE05":"2024-03-28","DATE06":"2024-05-01","DATE07":"2024-05-30","DATE08":"2024-06-20","DATE09":"2024-08-04","DATE10":"2024-08-31","DATE11":"2024-08-04","DATE12":"2024-08-04","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":10,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"262:21:16:7:1:34:29:21:45:45:45:26","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-01","FORECAST_END":"2024-05-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggU3VibWl0dGVkIGZvciBDQjEwIHByb3Bvc2VkIERhdGVzIDEgTWF5IHRvIDMwIE1heSB3YXMgMTUtOCB0byAxNS05CjIwIE1hcmNoIE5ldyBQcm9qZWN0IE51bWJlciBBU1AtV0MwMzY5IFdhcyBBTFAtV0MwMDI5IC0gU3VibWl0dGluZyBDQjEwCjE4IE1hcmNoIHRvIGJlIHN1Ym1pdHRlZCB0byBDQjEwIDxSNTAwawoxMiBNYXJjaCAtIFJlcXVlc3RlZCB0byBob2xkIHJlIFZlbmRvciBBbGxvY2F0aW9uCjExIE1hcmNoIHRvIGJlIHN1Ym1pdHRlZCB0byBDQj8/CjQgTWFyY2ggLSBSRlEgaW4gUHJvZ3Jlc3MgY2xvc2luZyA4IE1hcmNoCjI2IEZlYiAtIFNjb3BlIHRvIGJlIGNvbmZpcm1lZCB3aXRoIENyZXMgcHJpb3IgdG8gUkZRCjI5IEphbiBTaXRlIE1lZXRpbmcgMjAgRkVCCjIyIEphbiAtIFNpdGUgdmlzaXRzIHRvIGJlIGNvbmR1Y3RlZCAtIFBsYW5uaW5nIHRvIEV4ZWN1dGUgMTUgQXVnIHRvIDE1IFNlcHQ=","RATING":""} |  |  |  | PHASE05 | 2024-05-01 | 2024-05-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001117 | Absa Citrusdal - External Refurb | Absa Citrusdal - External Refurb |  |  | Region 2 | Western Cape | 78131X | 1000-71446-01 | Absa Citrusdal-Voortrekker St-Citrusdal | N | 2024-04-22 | 2024-07-31 |  | ASP-WC0370 | REL BUDG AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-20 | D | 133785.58 |  | 100 | 2024-03-22 | 2024-03-28 | 133785.58 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001117,"ONEVIEW":"78131X","DATE01":"2024-02-12","DATE02":"2024-03-04","DATE03":"2024-03-20","DATE04":"2024-03-27","DATE05":"2024-03-28","DATE06":"2024-05-01","DATE07":"2024-05-31","DATE08":"2024-06-21","DATE09":"2024-08-05","DATE10":"2024-08-31","DATE11":"2024-08-05","DATE12":"2024-08-05","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"262:21:16:7:1:34:30:21:45:45:45:26","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-05-01","FORECAST_END":"2024-05-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjIgTWFyY2ggU3VibWl0dGVkIGZvciBDQjEwIHByb3Bvc2VkIERhdGVzIDEgTWF5IHRvIDMwIE1heSB3YXMgMTUtNSB0byAxNS02CjIwIE1hcmNoIE5ldyBQcm9qZWN0IE51bWJlciBBU1AtV0MwMzcwIFdhcyBBTFAtV0MwMDMwIC0gU3VibWl0dGluZyBDQjEwCjE4IE1hcmNoIHRvIGJlIHN1Ym1pdHRlZCB0byBDQjEwIDxSNTAwawoxMiBNYXJjaCAtIFJlcXVlc3RlZCB0byBob2xkIHJlIFZlbmRvciBBbGxvY2F0aW9uCjExIE1hcmNoIHRvIGJlIHN1Ym1pdHRlZCB0byBDQj8/CjQgTWFyY2ggLSBSRlEgaW4gUHJvZ3Jlc3MgY2xvc2luZyA4IE1hcmNoCjI2IEZlYiAtIFNjb3BlIHRvIGJlIGNvbmZpcm1lZCB3aXRoIENyZXMgcHJpb3IgdG8gUkZRCjE5IEZlYiBTaXRlIHZpc2l0cyBpbiBwcm9ncmVzcyAxOSBGZWIKMjkgSmFuIFNpdGUgbWVldGluZyBzZXQgZm9yIDE5IEZFQgoyMiBKYW4gLSBTaXRlIHZpc2l0cyB0byBiZSBjb25kdWN0ZWQgLSBQbGFubmluZyB0byBFeGVjdXRlIDE1IE1heSB0byAxNSBKdW5l","RATING":""} |  |  | C000151855 | PHASE06 | 2024-05-01 | 2024-05-31 | RODERICK NEVAY | Floyd Mofokeng | 0 |  |  |  |  | 2024-04-05 | 116335.29 | 0 |  |  | C000151855 | 116335.29 |  | 11507.78 |  | 0 | 0 |  | 0 |  | 0
90001118 | Absa Piketberg - External Refurb | Absa Piketberg - External Refurb |  |  | Region 2 | Western Cape | 78132X | 1000-70890-01 | Absa Piketberg-Voortrekker St-Piketberg | N | 2024-04-22 | 2024-07-31 |  | ASP-WC0371 | CRTD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-20 | D | 291623.54 |  | 40 | 2024-03-22 |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001118,"ONEVIEW":"78132X","DATE01":"2024-02-12","DATE02":"2024-02-19","DATE03":"2024-03-11","DATE04":"2024-03-18","DATE05":"2024-04-08","DATE06":"2024-04-22","DATE07":"2024-07-31","DATE08":"2024-08-21","DATE09":"2024-10-05","DATE10":"2024-10-31","DATE11":"2024-10-05","DATE12":"2024-10-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-22","FORECAST_END":"2024-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE05 | 2024-05-01 | 2024-05-30 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001119 | Absa Bonnievale - HVAC | Absa Bonnievale - HVAC |  |  | Region 2 | Western Cape | 77671X | 1000-70842-01 | Absa Bonnievale-Main Rd-Bonnievale | Y | 2024-04-22 | 2024-07-31 |  | ASP-WC0372 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-20 | D | 78569.66 |  | 40 | 2024-03-22 |  | 0 | Absa Ref : TBA EOL Retial Mech | {"MANDT":"111","REFERENCE":90001119,"ONEVIEW":"77671X","DATE01":"2024-03-13","DATE02":"2024-03-15","DATE03":"2024-03-22","DATE04":"2024-03-29","DATE05":"2024-03-28","DATE06":"2024-04-11","DATE07":"2024-07-20","DATE08":"2024-08-10","DATE09":"2024-09-24","DATE10":"2024-09-30","DATE11":"2024-09-24","DATE12":"2024-09-24","PROG01":0,"PROG02":100,"PROG03":100,"PROG04":0,"PROG05":40,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"NaN:2:7:7:-1:14:100:21:45:45:45:26","PROGRESS":10,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-11","FORECAST_END":"2024-07-20","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"MjAgTWFyY2ggVG8gYmUgc3VibWl0dGVkIENCMTAKMTggTWFyY2ggLSBBZGRpdGlvbmFsIFF1b3RlcyByZXF1ZXN0ZWQgYXMgPlI1MGsKMTQgTWFyY2ggQWRkaXRpb25hbCBRdW90ZXMgcmVxdWVzdGVkLCBFTkcgdG8gcHJvdmlkZSBHTVAgYW5kIHNpemluZyBjYWxjdWxhdGlvbnMKMTMgTWFyY2ggUFJGIHJlY2VpdmVkIC0gRU9MIHVuaXQ=","RATING":""} |  |  |  | PHASE05 | 2024-04-11 | 2024-07-20 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001120 | Absa Nicolway Supply and install glass d | Absa Nicolway Supply and install glass d |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-25 | 2024-04-23 |  | ASP-GS0819 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-03-25 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001121 | Absa Ridgeside-Masterpack Breakers | Absa Ridgeside-Masterpack Breakers |  |  | Region 3 |  | 22460X | 1000-71094-01 | Ridgeside Absa Regional Office-Richefond Circle-Umhlanga |  | 2024-04-29 | 2024-05-09 |  | ASP-KZ0290 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001122 | Various- Replacement of UPS battries-AL | Various- Replacement of UPS battries-AL |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-04-19 | 2024-06-28 |  | ASP-N00075 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2024 |  |  |  | LOUISR | 2024-03-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001123 | Absa Willowbrooke-Enclosure Managers Off | Absa Willowbrooke-Enclosure Managers Off |  |  | Region 3 |  | 77584X | 1000-70638-01 | United Building-Kerk St-Ermelo |  | 2024-05-03 | 2024-06-28 |  | ALP-MP0211 | CRTD SETC: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-03-26 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001124 | Absa Caledon - Minor Works | Absa Caledon - Minor Works |  |  | Region 2 | Western Cape | 77399X | 1000-70830-01 | Absa Caledon-Donkin Square-Caledon | N | 2024-04-22 | 2024-07-31 |  | ALP-WC0035 | CRTD AVAC RESA SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | F |  | CEASARS | 2024-03-26 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240129_338 Was Small Project ASP-WC0345 converted to Large Project - ALP-WC0035 | {"MANDT":"111","REFERENCE":90001124,"ONEVIEW":"77399X","DATE01":"2024-02-12","DATE02":"2024-02-19","DATE03":"2024-03-11","DATE04":"2024-03-18","DATE05":"2024-04-08","DATE06":"2024-04-22","DATE07":"2024-07-31","DATE08":"2024-08-21","DATE09":"2024-10-05","DATE10":"2024-10-31","DATE11":"2024-10-05","DATE12":"2024-10-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-22","FORECAST_END":"2024-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-05-30 | 2024-09-07 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001125 | Absa Moffett Office Park - Cable install | Absa Moffett Office Park - Cable install |  |  | Region 2 | Eastern Cape | 22937X | 1000-70957-01 | Moffett Office Park-William Moffett Express Way-Port Elizabeth | N | 2024-04-22 | 2024-07-31 |  | ASP-EC0418 | CRTD AVAC SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | L |  | CEASARS | 2024-03-28 | D | 0 |  | 20 |  |  | 0 | Absa Ref : Opex | {"MANDT":"111","REFERENCE":90001125,"ONEVIEW":"22937X","DATE01":"2024-02-12","DATE02":"2024-02-19","DATE03":"2024-03-11","DATE04":"2024-03-18","DATE05":"2024-04-08","DATE06":"2024-04-22","DATE07":"2024-07-31","DATE08":"2024-08-21","DATE09":"2024-10-05","DATE10":"2024-10-31","DATE11":"2024-10-05","DATE12":"2024-10-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-22","FORECAST_END":"2024-07-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-04-22 | 2024-07-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001126 | Absa Alice Lane North 2 MTR units global | Absa Alice Lane North 2 MTR units global |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-28 | 2024-04-29 |  | ASP-GS0820 | REL BUDG AVAC SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  | C000151715 | 310610.34 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001127 | Alice Lane Replace LED Clocks 9 | Alice Lane Replace LED Clocks 9 |  |  | Region 1 |  | 76849X | 1000-71392-01 | Absa Call Centre Auckland Park-Lothbury Rd-Johannesburg |  | 2024-03-28 | 2024-04-29 |  | ASP-GS0821 | CRTD SETC: |  | false | false |  | Njabulo Ngubane |  |  | 2024 |  |  |  | GAMIETR | 2024-03-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 | 2024-03-28 | 2024-04-29 | CHRISTOPHER MPOFU | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001128 | EOL- Various- UPS batteries- Bridgepark- | EOL- Various- UPS batteries- Bridgepark- |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-04-30 | 2024-12-13 |  | ASP-N00076 | CRTD AVAC: |  | false | false |  | Sanelisiwe Celu |  |  | 2024 |  |  |  | LOUISR | 2024-03-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | LUCIA AMUNGA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001129 | National Retail LED Rollout (50 Sites) | National Retail LED Rollout (50 Sites) |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-04-30 | 2024-12-13 |  | ALP-N00078 | CRTD AVAC: |  | false | false |  | Mukuru Wesigye |  |  | 2024 |  |  |  | LOUISR | 2024-03-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001130 | Retail Yellow Lights Retrofit (19 Sites) | Retail Yellow Lights Retrofit (19 Sites) |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-04-30 | 2024-12-13 |  | ALP-N00079 | CRTD AVAC: |  | false | false |  | Mukuru Wesigye |  |  | 2024 |  |  |  | LOUISR | 2024-03-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001131 | Corporate Yellow Lights Retrofit (2 Site | Corporate Yellow Lights Retrofit (2 Site |  |  | Region 1 |  | 21526X | 1000-70027-01 | Absa Towers West-Troye St-Johannesburg |  | 2024-04-30 | 2024-12-13 |  | ALP-N00080 | CRTD AVAC: |  | false | false |  | Mukuru Wesigye |  |  | 2024 |  |  |  | LOUISR | 2024-03-28 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | LUCIA AMUNGA | Michael Maluleka | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001132 | Absa 31 Church Street - Install IK Booth | Absa 31 Church Street - Install IK Booth |  |  | Region 3 |  | 21821X | 1000-71320-01 | 31 Church Street Victoria West-Church St-Victoria West |  | 2024-05-02 | 2024-06-28 |  | ASP-CR0567 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-03 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001133 | Absa Phuthaditjhaba- DILAPS | Absa Phuthaditjhaba- DILAPS |  |  | Region 3 |  | 78615X | 1000-71593-01 | Phuthaditjhaba Shopping Centre-Cnr Setai & Motloung St-Phuthaditjhaba |  | 2024-04-18 | 2024-05-30 |  | ASP-CR0568 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-03 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001134 | Absa Alexandria ATM Room | Absa Alexandria ATM Room |  |  | Region 2 | Eastern Cape | 76600X | 1000-71015-01 | Absa Alexandria-Cnr Voortrekker & Krog St-Alexandria | N | 2024-04-03 | 2024-05-10 |  | ASP-EC0419 | CRTD SETC: |  | false | false |  | Laxine Maliffe |  |  | 2024 |  | F |  | GAMIETR | 2024-04-03 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_007 Small project Created was ALP-EC0025(240129_541) now ASP-EC0419 | {"MANDT":"111","REFERENCE":90001134,"ONEVIEW":"76600X","DATE01":"2024-01-24","DATE02":"2024-01-31","DATE03":"2024-02-21","DATE04":"2024-02-28","DATE05":"2024-03-20","DATE06":"2024-04-03","DATE07":"2024-05-10","DATE08":"2024-05-31","DATE09":"2024-07-15","DATE10":"2024-07-31","DATE11":"2024-07-15","DATE12":"2024-07-15","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-04-03","FORECAST_END":"2024-05-10","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-05-23 | 2024-06-29 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001135 | Mall@Reds Expansion Joints Implementatio | Mall@Reds Expansion Joints Implementatio |  |  | Region 1 |  | 76471X | 1000-71382-01 | Mall@Reds-Cnr Hendrik Verwoerd Dr & Rooihuiskraal Rd-Pretoria |  | 2024-04-05 | 2024-05-06 |  | ASP-GN0259 | CRTD SETC: |  | false | false |  | Athi Magqashela |  |  | 2024 |  |  |  | GAMIETR | 2024-04-05 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001136 | Pretoria Campus IT Workstation | Pretoria Campus IT Workstation |  |  | Region 1 |  | 76471X | 1000-71382-01 | Mall@Reds-Cnr Hendrik Verwoerd Dr & Rooihuiskraal Rd-Pretoria |  | 2024-04-05 | 2024-05-06 |  | ASP-GN0260 | CRTD SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | GAMIETR | 2024-04-05 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | CHRISTOPHER MPOFU | Obakeng Phuti | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001137 | Absa Vryheid - Replacement of Compressor | Absa Vryheid - Replacement of Compressor |  |  | Region 3 |  | 77113X | 1000-71614-01 | Absa Vryheid-Church St-Vryheid |  | 2024-05-08 | 2024-05-10 |  | ASP-KZ0291 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001138 | Absa Villiersdorp - Fence & Gates | Absa Villiersdorp - Fence & Gates |  |  | Region 2 | Western Cape | 78810X | 1000-71554-01 | Absa Villiers-Hoof St-Villiers | N | 2024-06-01 | 2024-07-30 |  | ASP-WC0373 | CRTD AVAC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-04-08 | D | 0 |  | 20 |  |  | 0 | Absa Ref : 240402_006 Reprioritised | {"MANDT":"111","REFERENCE":90001138,"ONEVIEW":"78810X","DATE01":"2024-03-23","DATE02":"2024-03-30","DATE03":"2024-04-20","DATE04":"2024-04-27","DATE05":"2024-05-18","DATE06":"2024-06-01","DATE07":"2024-07-30","DATE08":"2024-08-20","DATE09":"2024-10-04","DATE10":"2024-10-31","DATE11":"2024-10-04","DATE12":"2024-10-04","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-07-30","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-06-01 | 2024-07-30 | NANDE MAQUBELA | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001139 | Absa Cape Town Intl Airport - Shelving | Absa Cape Town Intl Airport - Shelving |  |  | Region 2 | Western Cape | 76946X | 1000-70791-01 | Cape Town International Airport-N2-Cape Town | N | 2024-06-01 | 2024-08-31 |  | ASP-WC0374 | CRTD AVAC SETC: |  | false | false |  | Nyasha Wena |  |  | 2024 |  | L |  | CEASARS | 2024-04-08 | D | 0 |  | 20 |  |  | 0 | Absa Ref : To Be Allocated Reprioritised | {"MANDT":"111","REFERENCE":90001139,"ONEVIEW":"76946X","DATE01":"2024-03-23","DATE02":"2024-03-30","DATE03":"2024-04-20","DATE04":"2024-04-27","DATE05":"2024-05-18","DATE06":"2024-06-01","DATE07":"2024-08-31","DATE08":"2024-09-21","DATE09":"2024-11-05","DATE10":"2024-11-30","DATE11":"2024-11-05","DATE12":"2024-11-05","PROG01":0,"PROG02":0,"PROG03":0,"PROG04":0,"PROG05":0,"PROG06":0,"PROG07":0,"PROG08":0,"PROG09":0,"PROG10":0,"PROG11":0,"PROG12":0,"DATE_A":"0000-00-00","DATABAG":"7:21:7:21:14:21:45","PROGRESS":0,"FORECASTDATES":"","CHANGEDON":"0000-00-00","TOPLEVEL":"","LAST_TRACKDATE":"0000-00-00","FORECAST_START":"2024-06-01","FORECAST_END":"2024-08-31","BUDGETAMT":0,"LAST_COMMENT":"","TRACKNOTE":"","RATING":""} |  |  |  | PHASE00 | 2024-06-01 | 2024-08-31 | RODERICK NEVAY | Floyd Mofokeng | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001140 | Absa Convention House-Replace Condens Un | Absa Convention House-Replace Condens Un |  |  | Region 3 |  | 36266X | 1000-71134-01 | Convention House-Florence Nzama St-Durban |  | 2024-05-23 | 2024-05-27 |  | ALP-KZ0010 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-08 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001141 | Absa Chatterton Road - Replace Carpets | Absa Chatterton Road - Replace Carpets |  |  | Region 3 |  | 78398X | 1000-71221-01 | Chatterton Road Private Bank-Chatterton Rd-Pietermaritzburg |  | 2024-05-08 | 2024-05-23 |  | ASP-KZ0292 | CRTD SETC: |  | false | false |  | Mpendulo Sibanyoni |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-09 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001142 | Testing - for deletion | Testing - for deletion |  |  | Region 1 |  | 70647X | 1000-71518-01 | Sasol Pioneer Building-Cnr Fichardt & Bell St-Sasolburg |  | 2024-06-01 | 2024-08-31 |  | ASP-GS0822 | CRTD DLFL AVAC SETC: |  | false | false |  | Renando Jacobs |  |  | 2024 |  |  |  | CEASARS | 2024-04-11 | D | 0 |  |  |  |  | 0 | [5 empty] | DELETED |  |  | OTHER | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001143 | Absa 268 Republic Road - PA System | Absa 268 Republic Road - PA System |  |  | Region 1 |  | 21334X | 1000-70026-01 | Absa 268 Republic Road Block A, B, C-Republic Rd-Randburg |  | 2024-03-01 | 2024-06-30 |  | ASP-GS0823 | CRTD AVAC SETC: |  | false | false |  | Aphiwe Sidlayiya |  |  | 2024 |  |  |  | CEASARS | 2024-04-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | CHRISTOPHER MPOFU | Nokuthula Manzini | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001144 | Absa Carolina - External Refurbishment | Absa Carolina - External Refurbishment |  |  | Region 3 |  | 78145X | 1000-70684-01 | Absa Carolina-Voortrekker St-Carolina |  | 2024-05-30 | 2024-06-28 |  | ASP-MP0187 | CRTD: |  | false | false |  | Justice Mogadime |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Thea Spamers | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
90001145 | Absa Koppies - External Refurbishment | Absa Koppies - External Refurbishment |  |  | Region 3 |  | 78856X | 1000-71559-01 | Absa Koppies Bloemfontein-Kerk St-Koppies |  | 2024-05-30 | 2024-06-28 |  | ALP-CR0047 | CRTD SETC: |  | false | false |  | Bubele Mshumpela |  |  | 2024 |  |  |  | NOMNGANGAL | 2024-04-12 | D | 0 |  |  |  |  | 0 | [5 empty] | PHASE00 |  |  | NANDE MAQUBELA | Juanita Van Coller | 0 | [5 empty] | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0